## Sheet1
Sno. | CIRCLE | NOMINAL_AOP | NOMINAL_QUARTER | SITE_ID | Unique_SITE_ID | ENODEB_ID | BAND | Chur/Non Churn/Super Churn | Incase of Relocation (Old TOCO) | PROJECT | BTS_TYPE | Allocation | OEM_NAME | TOCO_NAME | LOCATOR_ID | RFAI_DATE | POST_RFAI_SURVEY_DATE | RFAI_REJECTION_DATE | RFAI_REGENERATION_DATE | MO_PUNCHING_DATE | MATERIAL_DISPATCH_(MD)_DATE | MATERIAL_DELIVERY_(MOS)_DATE | INSTALLATION_START_DATE | INSTALLATION_END_DATE | POST_MEDIA_ISSUE_OPEN_DATE | POST_MEDIA_ISSUE_CLOSE_DATE | Integration Date | SACFA_APPLIED_DATE | SACFA_APPLICATION_ID | DEVIATION_APPROVAL_MAIL_RX_DATE_(IF_APPLICABLE) | WPC_ACCEPTANCE_DATE | WPC_ACCEPTANCE_ID | EMF_SUBMISSION_DATE | SCFT_COMPLETION_DATE | OA_(COMMERCIAL_TRAFFIC_PUT_ON_AIR)_(MS1)_DATE | RFAI VSMS1 | Reason for Delay over period of more than 14 Days | Action Taken against Pending RFAI | Physical AT Offered Date | PHYSICAL_AT_ACCEPTANCE_DATE | PHYSICAL_AT_Status( Accepted/Rejected/Offered/Pending/Dismantle) | MS1 Vs PHY AT Acceptance- Ageing | Reason for PHY AT Rejection/ Not offered beyond 5 days | Soft AT Offered Date | SOFT_AT_ACCEPTANCE_DATE | Soft_AT_Status( Accepted/Rejected/Offered/Pending/Dismantle) | MS1 Vs Soft AT Acceptance- Ageing | Reason for Soft AT Rejection/ Not offered beyond 5 days | PERFORMANCE_AT_Offered_DATE | PERFORMANCE_AT_ACCEPTANCE_DATE2 | Performance_AT_Status( Accepted/Rejected/Offered/Pending/Dismantle) | MS1 Vs Performance AT Acceptance- Ageing | Reason for Performance AT Rejection/ Not offered beyond 7 days | MAPA_INCLUSION_DATE | MS1 Vs MS2 Ageing | Reason for delay more than 15 days | PRI_CATEGORY_(ACCESS/INFRA) | PRI_CATEGORY_(ACCESS/INFRA)- Last Discussion Date | CURRENT_STATUS_OF_SITE | Circle Reamarks | MS2 Pending Reason | MS2 Pending Responsibilty | CATS STATUS(installed/On air | CATS Mobility | SIWA | SRN STATUS | Internal RFAI Vs Ms1 | Internal Ms1 Vs Ms2 | RFAI Vs MS1 | Ms1 Vs Ms2 | Total Allocation | RFAI VS MS1 Remarks | Phy AT Status | Phy AT Owner | Soft AT Status2 | Soft AT Owner2 | KPI AT Status | KPI AT Owner4 | Project | Activity | MS1 VS MS2 Responsibility | RFAI VS MS1- Responsibility | RFS Month | A bcd | Quality Remarks | RFAI-Week | MS1 -week | MS2-Week | Relocation Vs Dismantle | WH Submisstion | Remarks
1 | AP | FY_22-23 |  | APNT13 | APNT13 | 999795 | G1800_L900_L1800_L2300 | Non-Churn | BSNL | Relocation | MACRO_OUTDOOR |  | Ericsson | ATC | 15136-1772-23785434 | 2022-06-09 | 2022-06-11 |  |  | 2022-06-23 | 2022-06-24 | 2022-06-28 | 2022-06-28 | 2022-07-03 |  |  | 2022-07-20 | 2022-05-25 | ST202205145242 |  | 2022-06-02 | P/FVC/HYD/1046168/2022 | 2022-07-20 | 2022-07-24 | 2022-08-14 | 66 | Due to Material Shortage & LKF not received |  |  |  | Physical AT Pending | 124 |  | 2022-09-01 | 2022-09-02 | Soft AT Accepted | 19 |  |  | 2022-10-18 | KPI AT Accepted | 65 |  |  | 124 |  |  |  | Under_ATP |  | Under_Physical_Soft_Performance_AT | [5 empty] | >30days | >30days | >14days | >10days | Under_MS1_MS2 | Due to Material Shortage- Delay | AT Report WIP | Mcomm | AT-Accepted | Closed | KPI Under Observation | Mcomm | Relocation | Relocation | MobileComm |  |  |  |  | 24 | 34 |  | Submitted in WH |  | Closed
2 | AP | FY_22-23 |  | KOKD12 | KOKD12 | 999802 | G1800_L1800 | Non-Churn | BSNL | Relocation | MACRO_OUTDOOR |  | Ericsson | ATC | 15136-1863-90794081 | 2022-06-08 | 2022-06-11 |  |  | 2022-06-23 | 2022-06-24 | 2022-06-28 | 2022-06-29 | 2022-07-07 |  |  | 2022-07-16 | 2022-05-25 | ST202205145228 |  | 2022-06-02 | P/FVC/HYD/1046166/2022 | 2022-07-20 | 2022-08-02 | 2022-08-14 | 67 | Due to Material Shortage & LKF not received |  |  |  | Physical AT Pending | 124 |  | 2022-09-01 | 2022-09-02 | Soft AT Accepted | 19 |  |  | 2022-09-15 | KPI AT Accepted | 32 |  |  | 124 |  |  |  | Under_ATP |  | Under_Physical_Soft_Performance_AT | [5 empty] | >30days | >30days | >14days | >10days | Under_MS1_MS2 | Due to Material Shortage- Delay | AT Report WIP | Mcomm | AT-Accepted | Closed | KPI Under Observation | Mcomm | Relocation | Relocation | MobileComm |  |  |  |  | 24 | 34 |  | Submitted in WH |  | Closed
3 | AP | FY_22-23 |  | BKD007 | BKD007 | 999790 | G1800_L1800 | Non-Churn | BSNL | Relocation | MACRO_OUTDOOR |  | Ericsson | ATC | 15136-1840-15777065 | 2022-06-13 | 2022-06-13 |  |  | 2022-06-23 | 2022-06-24 | 2022-06-27 | 2022-06-28 | 2022-07-06 |  |  | 2022-07-14 | 2022-05-25 | ST202205145235 |  | 2022-06-02 | P/FVC/HYD/1046167/2022 | 2022-07-19 | 2022-07-20 | 2022-07-25 | 42 | Due to Material Shortage & LKF not received |  | 2022-09-10 |  | Physical AT Pending | 144 | Rejected Due to Photos Mis-Mactch, Reprot Rectification WIP | 2022-09-01 | 2022-09-02 | Soft AT Accepted | 39 |  |  | 2022-10-18 | KPI AT Accepted | 85 |  |  | 144 |  |  |  | Under_ATP |  | Under_Physical_Soft_Performance_AT | [5 empty] | >30days | >30days | >14days | >10days | Under_MS1_MS2 | Due to Material Shortage- Delay | AT Report WIP | Mcomm | AT-Accepted | Closed | KPI Under Observation | Mcomm | Relocation | Relocation | MobileComm |  |  |  |  | 25 | 31 |  | Submitted in WH |  | Closed
4 | AP | FY_22-23 |  | AVPL12 | AVPL12 | 998983 | G1800_L900_L1800 | Non-Churn | BSNL | Relocation | MACRO_OUTDOOR |  | Ericsson | Ascend | 15136-1733-29795142 | 2022-06-30 | 2022-07-02 |  |  | 2022-08-07 | 2022-08-07 | 2022-08-08 | 2022-09-28 | 2022-09-30 |  |  | 2022-10-01 | 2022-05-30 | ST202205150839 |  | 2022-06-03 | P/FVC/HYD/1046257/2022 | 2022-10-04 | 2022-10-05 | 2022-10-09 | 101 | Due to Infra issue |  |  |  | Physical AT Pending | 68 |  |  | 2022-10-08 | Soft AT Accepted | -1 |  |  | 2022-11-04 | KPI AT Accepted | 26 |  |  | 68 |  | INFRA |  | Under_ATP | [7 empty] | >30days | >30days | >14days | >10days | Under_MS1_MS2 | Due to Infra Issue- Delay | [6 empty] | Relocation | Relocation | MobileComm |  |  |  |  | 27 | 42 |  | Site to Site Relocation done |  | Closed
Formulas:
RFAI VSMS1 = IF([1]Details!$[RFAI_DATE]="","",IF([1]Details!$AJ2="",TODAY()-[1]Details!$[RFAI_DATE],[1]Details!$AJ2-[1]Details!$[RFAI_DATE]))
MS1 Vs PHY AT Acceptance- Ageing = IF([1]Details!$AJ2="","",IF([1]Details!$[PHYSICAL_AT_ACCEPTANCE_DATE]="",TODAY()-[1]Details!$AJ2,[1]Details!$[PHYSICAL_AT_ACCEPTANCE_DATE]-[1]Details!$AJ2))
MS1 Vs Soft AT Acceptance- Ageing = IF([1]Details!$AJ2="","",IF([1]Details!$[SOFT_AT_ACCEPTANCE_DATE]="",TODAY()-[1]Details!$AJ2,[1]Details!$[SOFT_AT_ACCEPTANCE_DATE]-[1]Details!$AJ2))
MS1 Vs Performance AT Acceptance- Ageing = IF([1]Details!$AJ2="","",IF([1]Details!$[PERFORMANCE_AT_ACCEPTANCE_DATE2]="",TODAY()-[1]Details!$AJ2,[1]Details!$[PERFORMANCE_AT_ACCEPTANCE_DATE2]-[1]Details!$AJ2))
MS1 Vs MS2 Ageing = IF([1]Details!$AJ2="","",IF([1]Details!$[MAPA_INCLUSION_DATE]="",TODAY()-[1]Details!$AJ2,[1]Details!$[MAPA_INCLUSION_DATE]-[1]Details!$AJ2))
RFAI-Week = WEEKNUM([RFAI_DATE])