## Sheet1
id | SITE_ID | CIRCLE | Unique_SITE_ID | BAND | TOCO_NAME | OA_COMMERCIAL_TRAFFIC_PUT_ON_AIR_MS1_DATE | Project | Activity | Soft_AT_Status | SOFT_AT_ACCEPTANCE_DATE | SOFT_AT_ACCEPTANCE_MAIL | SOFT_AT_REJECTION_DATE | SOFT_AT_REJECTION_REASON | SOFT_AT_OFFERED_DATE | SOFT_AT_OFFERED_REMARKS | SOFT_AT_PENDING_REASON | SOFT_AT_PENDING_REMARK | SOFT_AT_PENDING_TAT_DATE | PHYSICAL_AT_Status | PHYSICAL_AT_ACCEPTANCE_DATE | PHYSICAL_AT_ACCEPTANCE_MAIL | PHYSICAL_AT_REJECTION_DATE | PHYSICAL_AT_REJECTION_REASON | PHYSICAL_AT_OFFERED_DATE | PHYSICAL_AT_OFFERED_REMARKS | PHYSICAL_AT_PENDING_REASON | PHYSICAL_AT_PENDING_REMARK | PHYSICAL_AT_PENDING_TAT_DATE | Performance_AT_Status | PERFORMANCE_AT_ACCEPTANCE_DATE | PERFORMANCE_AT_REJECTION_DATE | PERFORMANCE_AT_REJECTION_REASON | PERFORMANCE_AT_OFFERED_DATE | PERFORMANCE_AT_OFFERED_REMARKS | PERFORMANCE_AT_PENDING_REASON | PERFORMANCE_AT_PENDING_REMARK | PERFORMANCE_AT_PENDING_TAT_DATE | MAPA_STATUS | RFAI_DATE | MAPA_INCLUSION_DATE | Internal_RFAI_Vs_Ms1_In_Days | Internal_Ms1_Vs_Ms2_In_days
PBUMH139L2300Indus NBULSNew Tower_ULS | UMH139 | PB | UMH139 | L2300 | Indus NB | 2022-04-10 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-04 | 2022-04-21 | 0-15 | 0-15
PBUMH142L2300Indus NbULSNew Tower_ULS | UMH142 | PB | UMH142 | L2300 | Indus Nb | 2022-04-04 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-03-19 | 2022-04-19 | 16-30 | 0-15
PBUMH032L2300Indus NBULSNew Tower_ULS | UMH032 | PB | UMH032 | L2300 | Indus NB | 2022-04-09 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-04 | 2022-04-19 | 0-15 | 0-15
PBULD057L2300SpacetelULSNew Tower_ULS | ULD057 | PB | ULD057 | L2300 | Spacetel | 2022-04-12 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-08 | 2022-04-19 | 0-15 | 0-15
PBUHS009L2300Airtel NBULSNew Tower_ULS | UHS009 | PB | UHS009 | L2300 | Airtel NB | 2022-04-12 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-02 | 2022-04-29 | 0-15 | 16-30
PBULD121L2300TVI SHULSNew Tower_ULS | ULD121 | PB | ULD121 | L2300 | TVI SH | 2022-04-12 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-04 | 2022-05-01 | 0-15 | 16-30
PBULD122L2300TVI SHULSNew Tower_ULS | ULD122 | PB | ULD122 | L2300 | TVI SH | 2022-04-12 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-04 | 2022-07-04 | 0-15 | 61-90
PBUMN010L2300AscendULSNew Tower_ULS | UMN010 | PB | UMN010 | L2300 | Ascend | 2022-04-14 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-09 | 2022-06-08 | 0-15 | 31-60
PBUMG031L2300Suyog TelematicsULSNew Tower_ULS | UMG031 | PB | UMG031 | L2300 | Suyog Telematics | 2022-04-14 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-09 | 2022-09-30 | 0-15 | GT90
PBULD077L2300Airtel NBULSNew Tower_ULS | ULD077 | PB | ULD077 | L2300 | Airtel NB | 2022-04-15 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-06 | 2022-09-21 | 0-15 | GT90
PBUFD013L2300AscendULSNew Tower_ULS | UFD013 | PB | UFD013 | L2300 | Ascend | 2022-04-15 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-07 | 2022-09-26 | 0-15 | GT90
PBUSG021L2300TVI NBULSNew Tower_ULS | USG021 | PB | USG021 | L2300 | TVI NB | 2022-04-15 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-08 | 2022-09-16 | 0-15 | GT90
PBUMH064L2300Indus NbULSNew Tower_ULS | UMH064 | PB | UMH064 | L2300 | Indus Nb | 2022-04-16 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-11 | 2022-10-13 | 0-15 | GT90
PBULS360L2300Indus NBULSNew Tower_ULS | ULS360 | PB | ULS360 | L2300 | Indus NB | 2022-04-16 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-07 | 2022-06-02 | 0-15 | 31-60
PBUJL063L2300Suyog TelematicsULSNew Tower_ULS | UJL063 | PB | UJL063 | L2300 | Suyog Telematics | 2022-04-18 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-11 | 2022-05-13 | 0-15 | 16-30
PBUKP043L2300Indus NBULSNew Tower_ULS | UKP043 | PB | UKP043 | L2300 | Indus NB | 2022-04-18 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-13 | 2022-05-07 | 0-15 | 16-30
PBULD016L2300Airtel NBULSNew Tower_ULS | ULD016 | PB | ULD016 | L2300 | Airtel NB | 2022-04-20 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-10 | 2022-05-31 | 0-15 | 31-60
PBUPA015L2300Indus SHULSNew Tower_ULS | UPA015 | PB | UPA015 | L2300 | Indus SH | 2022-04-20 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-13 | 2022-05-17 | 0-15 | 16-30
PBUMH050L2300Indus NBULSNew Tower_ULS | UMH050 | PB | UMH050 | L2300 | Indus NB | 2022-04-20 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-12 | 2022-09-28 | 0-15 | GT90
PBULD070L2300Indus NBULSNew Tower_ULS | ULD070 | PB | ULD070 | L2300 | Indus NB | 2022-04-02 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-03-28 | 2022-04-10 | 0-15 | 0-15
PBUJL054L2300Indus SHULSNew Tower_ULS | UJL054 | PB | UJL054 | L2300 | Indus SH | 2022-04-20 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-03 | 2022-05-29 | 16-30 | 31-60
PBUFZ023L2300Indus SHULSNew Tower_ULS | UFZ023 | PB | UFZ023 | L2300 | Indus SH | 2022-04-23 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-09 | 2022-07-04 | 0-15 | 61-90
PBULD133L2300ASCENDULSNew Tower_ULS | ULD133 | PB | ULD133 | L2300 | ASCEND | 2022-04-23 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-13 | 2022-12-22 | 0-15 | GT90
PBUPA121L2300IndusULSNew Tower_ULS | UPA121 | PB | UPA121 | L2300 | Indus | 2022-04-24 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-14 | 2022-05-24 | 0-15 | 16-30
PBUHS027L2300IndusULSNew Tower_ULS | UHS027 | PB | UHS027 | L2300 | Indus | 2022-04-23 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-14 | 2022-05-18 | 0-15 | 16-30
PBUBT041L2300AscendULSNew Tower_ULS | UBT041 | PB | UBT041 | L2300 | Ascend | 2022-04-22 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-14 | 2022-09-12 | 0-15 | GT90
PBUJL070L2300AscendULSNew Tower_ULS | UJL070 | PB | UJL070 | L2300 | Ascend | 2022-04-24 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-19 | 2022-06-02 | 0-15 | 31-60
PBULS354L2300Space Tele infraULSNew Tower_ULS | ULS354 | PB | ULS354 | L2300 | Space Tele infra | 2022-04-24 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 |  | 0-15 | GT90
PBUMH145L2300SuyogULSNew Tower_ULS | UMH145 | PB | UMH145 | L2300 | Suyog | 2022-04-24 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 | 2022-09-28 | 0-15 | GT90
PBUAS015L2300Indus SHULSNew Tower_ULS | UAS015 | PB | UAS015 | L2300 | Indus SH | 2022-04-25 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 |  | 0-15 | GT90
PBUPK008L2300AscendULSNew Tower_ULS | UPK008 | PB | UPK008 | L2300 | Ascend | 2022-04-25 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 | 2022-05-17 | 0-15 | 16-30
APUPK008L2300AscendULSNew Tower_ULS | UPK008 | AP | UPK008 | L2300 | Ascend | 2022-04-25 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 | 2022-05-17 | 0-15 | 16-30
APUPK001L2300AscendULSNew Tower_ULS | UPK001 | AP | UPK001 | L2300 | Ascend | 2022-04-25 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 | 2022-05-17 | 0-15 | 16-30
APUPK002L2300AscendULSNew Tower_ULS | UPK002 | AP | UPK002 | L2300 | Ascend | 2022-04-25 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 | 2022-05-17 | 0-15 | 16-30
APUPK003L2300AscendULSNew Tower_ULS | UPK003 | AP | UPK003 | L2300 | Ascend | 2022-04-25 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 | 2022-05-17 | 0-15 | 16-30
APUPK004L2300AscendULSNew Tower_ULS | UPK004 | AP | UPK004 | L2300 | Ascend | 2022-04-25 00:00:00 | ULS | New Tower_ULS | [29 empty] | NOT OK | 2022-04-17 | 2022-05-17 | 0-15 | 16-30