## Feb - Jan Summary
Month | Feb'23 | RELOCATION | [9 empty] | Month | Jan'23 | RELOCATION
Zone | RFAI | Survey | MO | MD | MoS | Dismantle | Installation | Integration | EMF | SCFT | MS1 | Zone | RFAI | Survey | MO | MD | MoS | Dismantle | Installation | Integration | EMF | SCFT | MS1
CBE | 12 | 9 | 6 | 6 | 5 | 2 | 2 | 2 | 0 | 0 | 1 | CBE | 27 | 27 | 23 | 23 | 23 | 27 | 27 | 27 | 27 | 20 | 27
CHN | 11 | 9 | 5 | 5 | 5 | 1 | 2 | 1 | 1 | 1 | 1 | CHN | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
MDU | 7 | 7 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | MDU | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
VLR | 14 | 12 | 7 | 7 | 6 | 4 | 4 | 4 | 2 | 0 | 4 | VLR | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 4 | 11
TRY | 10 | 9 | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | TRY | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 10
Grand Total | 54 | 46 | 28 | 28 | 26 | 8 | 9 | 8 | 4 | 2 | 7 | Grand Total | 53 | 53 | 49 | 49 | 49 | 53 | 53 | 53 | 53 | 37 | 53
Month | Feb'23 | NEW SITE | [9 empty] | Month | Jan'23 | NEW SITE
Zone | RFAI | Survey | MO | MD | MoS | Installation | Integration | EMF | SCFT | MS1 |  | Zone | RFAI | Survey | MO | MD | MoS | Dismantle | Installation | Integration | EMF | SCFT | MS1
CBE | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | CBE | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
CHN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CHN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MDU | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | MDU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VLR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | VLR | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
TRY | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TRY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | Grand Total | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2

## Summary
RELOCATION |  |  | Feb'23 | NEW TOWER |  |  | Feb'23
Activity's | Sites | Gap | Remarks | Activity's | Sites | Gap | Remarks
RFAI | 54 |  |  | RFAI | 6
SURVEY DONE | 46 | 8 |  | SURVEY DONE | 1 | 5
MO | 28 | 18 |  | MO | 1 | 0
MATERIAL DISPATCH | 28 | 0 |  | MATERIAL DISPATCH | 1 | 0
MATERIAL DELIVERED | 26 | 2 |  | MATERIAL DELIVERED | 1 | 0
DISMANTLE | 8 | 18 |  | INSTALLATION | 1 | 0
INSTALLATION | 9 | -1 | New Mat | MEDIA AVAILABLE | 1 | 0
MEDIA AVAILABLE | 9 |  |  | INTEGRATED | 1 | 0
INTEGRATED | 8 | 1 |  | READY FOR SCFT | 0 | 1
SCFT Done | 2 | 6 |  | MS1 | 0 | 1
MS1 | 7 | 2

## Pending
SCFT Pending Against MS1 Done
Activity's | 0 to 3 Days | 4 to 7 Days | Morethan 7 Days | Total
NEW SITE | 0 | 0 | 2 | 2
RELOCATION | 0 | 0 | 23 | 23
Grand Total | 0 | 0 | 25 | 25
Survey Pending Against RFAI
Activity's | 0 to 5 Days | 6 to 10 Days | Morethan 10 Days | Total
NEW SITE | 0 | 0 | 5 | 5
RELOCATION | 0 | 1 | 7 | 8
Grand Total | 0 | 1 | 12 | 13
| Total | 11 | 12 | 24 | 12
| Dist - Relocation | Only Phy Pending | Only SOFT Pending | Only KPI Pending | Need Field Visit | Month | Only Phy Pending | Only SOFT Pending | Only KPI Pending | Phy & Soft AT Pending | Phy & KPI AT Pending | Soft & KPI AT Pending | Phy & Soft & KPI AT Pending
| Chengalpet | 1 | 0 | 0 |  | MAR | 3 | 0 | 2 | 0 | 0 | 0 | 0
| Chennai | 1 | 0 | 4 | 3 | APR | 0 | 0 | 3 | 0 | 0 | 0 | 1
| Coimbatore | 2 | 4 | 2 | 1 | MAY | 1 | 0 | 1 | 0 | 0 | 0 | 0
| Dharmapuri | 0 | 0 | 2 | 1 | JUN | 0 | 2 | 3 | 0 | 0 | 0 | 0
| Dindigul | 0 | 0 | 4 | 1 | July | 1 | 0 | 2 | 0 | 0 | 0 | 0
| Erode | 0 | 2 | 2 |  | Aug | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Karur | 0 | 0 | 1 | 1 | Sep | 1 | 1 | 3 | 0 | 1 | 1 | 0
| Namakkal | 1 | 1 | 1 | 1 | Oct | 0 | 1 | 5 | 0 | 4 | 1 | 0
| Pondy | 0 | 1 | 0 |  | Nov | 4 | 6 | 1 | 1 | 3 | 4 | 0
| Ramanathapuram | 0 | 1 | 0 |  | Dec | 1 | 6 | 3 | 5 | 2 | 13 | 7
| Salem | 0 | 0 | 1 | 1 | Jan'23 | 0 | 0 | 0 | 3 | 1 | 15 | 36
| Theni | 0 | 0 | 1 | 1 | Total | 11 | 16 | 24 | 9 | 11 | 34 | 44
| Tiruchirappalli | 1 | 1 | 3 | 1 | Month | Only Phy Pending | Only SOFT Pending | Only KPI Pending | Phy & Soft AT Pending | Phy & KPI AT Pending | Soft & KPI AT Pending | Phy & Soft & KPI AT Pending
| Tirunelveli | 1 | 1 | 1 | 1 | Relocation | 8 | 8 | 23 | 7 | 9 | 27 | 44
| Tiruppur | 3 | 0 | 1 |  | New Site | 3 | 8 | 1 | 2 | 2 | 7 | 3
| Tutucorin | 1 | 1 | 0 |  | SC HPSC | 0 | 6 | 5 | 19 | 0 | 1 | 16
| Vellore | 0 | 0 | 1 |  | SC-LPSC | 2 | 4 | 20 | 1 | 12 | 24 | 30
[6 empty] | Total | 13 | 26 | 49 | 29 | 23 | 59 | 93

## DATA
291 | 291 | 291 | 289 | 288 | 291 | 291 | 227 | 182 | 180 | 287 | 187 | 150 | 108 | 108 | 187 | 187 | 280 | 206 | 189 | 206 | 160 | 177 | 121 | 291 | 291 | 166 | 0 | 3 | 287 | 287 | 278 | 278 | 281 | 284 | 284 | 291 | 278 | 66 | 219 | 175 | 217 | 252 | 224 | 250 | 291 | 291 | 291 | 238 | 249 | 253 | 253 | 251 | 0 | 273 | 201 | 122 | 241 | 160 | 0 | 6 | 6 | 240 | 0 | 182 | 12 | 236 | 172 | 213 | 124 | 283 | 283 | 281 | 281 | 0 | 290 | 238 | 249 | 3 | 142 | 5 | 1 | 142 | 123 | 168 | 166 | 0 | 212 | 176 | 0 | 186 | 181 | 74 | 179 | 179 | 1 | 84 | 152 | 122 | 287 | 99 | 234 | 0 | 160
SI. No. | Circle | New Site ID | Old Site ID | FD Site | Zone | NEW / RELOCATION | OEM | Site Name | Site Address | District | Tower Type | Remarks to relocate | Old Lat | Old Lon | New Lat | New Lon | Locator ID | CONFIGURATION | Old ToCo | New ToCo | Old ToCo ID | New ToCo ID | Product | Priority | RFAI Date | Reasons | N RFAI | M RFAI | RND | LB Plan | MW CR | New MW RL No. | RF Plan | IP Plan | CGI Status | Site Allocated | Survey Completed | Survey Team | Config Tech | Huawei Curr. Config | Eric Curr. Config | Sec Count | Survey Pending Status | Total Radio Count | Ageing - Survey vs RFAI | Days - Survey vs RFAI | Month | Mcom Monh | MO No. | MO Date | MD | MoS Date | Ageing RFAI vs MOS | Status | Dismantle Date | Dismantle Team Name | Installation Date | Installation Team | Ageing | CAM No. | CAM Raise Date | Integration Date | Ageing | Final Status | Reason for Delay | EMF Date | EMF No | SCFT | SCFT Engg | Ageing - SCFT vs RFAI | Days - SCFT vs RFAI | Ageing - MS1 vs SCFT | Days - MS1 vs SCFT | SACFA ID | SACFA | MS1 Date | AGEING | Phy AT Offer | Soft AT Offer | MW Phy AT | Responsibility | MW Soft AT | Responsibility | Huawei PHY AT Offered | Huawei Phy AT | Responsibility | Huawei Soft AT Offered | Huawei Soft AT | Responsibility | Ericsson Phy AT Offered | Ericsson Phy AT | Responsibility | Ericsson Soft AT Offered | Ericsson Soft AT | Responsibility | MS2 Date | KPI Offered | KPI Status | Reason for MS1 to MS2 gap | Final Status | Remarks | AT Remarks | Detailed remarks
1 | TN | KLKLU2 | KLKLU1 | Ok | TRY | Relocation | Huawei + Ericsson | Kilanilaikottai _Kallur | Sf.No.463/1, Pillayar koil st, K rayapuram, Post: Kalllur, Taluk & District: Pudukottai, State: Tamilnadu, Pincode-622209 | Pudukottai | GBT | MS1 DONE | 10.1528 | 78.85 | 10.1532 | 78.85 | 155-1015-31788500 | Hua (2G+4G) + Eric 4G | BSNL | INDUS | 5630 | IN-3133834 | STANDARD_PRODUCT | Done | 2022-08-13 | BSNL Exit Feasible Sites |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-18 | 2022-08-20 |  | L18+L23+L900 | L18 | L900+L2300 | 3+1 | NA | 8 |  |  | Sep | Aug | 20332935 | 2022-08-23 | 2022-08-22 | 2022-08-24 |  | MS1 DONE | 2022-08-26 | Boss management | 2022-08-26 | RS Teletude |  | CREQ97497 | 2022-08-27 | 2022-08-27 |  | Relocated | Rain | 2022-08-27 | TN/13/5177/01994/0043/04/01/16694/NS/27082022 | 2022-08-29 | R.MANIKANDAN | [5 empty] | Yes | 2022-08-29 |  |  | 2022-09-26 |  | Dharun | 2022-09-26 | Rahul | 2022-08-30 | 2022-09-03 |  | 2022-09-01 | 2022-09-03 |  | 2022-09-01 | 2022-09-06 | kuldeep | 2022-10-16 | 2022-10-20 | Aashis | 2023-01-14 | 2023-01-06 | 2023-01-06 | MS2 Done | MAPA_Done | All 3 Accepted |  | BSNL Exit Feasible Sites | 29-08-2022
2 | TN | VDATL2 | VDATL1 | Ok | VLR | Relocation | Ericsson | Vandaranthangal | Sf.No.329/4, 33, Post: Vandarahtangal, Taluk: Katpadi, District: Vellore, State: Tamilnadu, Pincode-632059. 9843111713 | Vellore | GBT | MS1 DONE | 12.9872 | 79.1244 | 12.9866 | 79.1234 | 155-1298-66791234 | GL1800+L2100+L2300 | BSNL | INDUS | 4646 | IN-3133857 | ECO | Done | 2022-08-13 | High Opex Saving_Sep'21 |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-18 | 2022-08-20 |  | L18+L23 | NA | UBR+L23 | 3 | NA | 6 |  |  | Sep | Aug | 20323304 | 2022-08-23 | 2022-08-22 | 2022-08-24 |  | MS1 DONE | 2022-08-26 | Boss management | 2022-08-26 | RS Teletude |  | CREQ97576 | 2022-08-27 | 2022-08-26 |  | Relocated | No delay | 2022-08-30 | TN/15/5177/01999/0043/04/01/16706/NS/30082022 | 2022-08-29 | R.MANIKANDAN | [5 empty] | Yes | 2022-08-29 |  |  | 2022-09-24 | NA |  | 2022-09-24 | Rahul | [6 empty] | 2022-09-09 | 2022-09-14 | kuldeep | 2022-09-22 | 2022-09-24 |  | 2022-12-26 | 2022-11-15 | 2022-11-15 | MS2 Done | MAPA_Done | All 3 Accepted |  | High Opex Saving_Sep'21 | 29-08-2022
3 | TN | PLGA10 | PLGAM1 | Ok | TRY | Relocation | Huawei | Polagam | Sf.No.13/18, 13/19, Post: Polagam, Taluk & District: Nagapattinam, State: Tamil Nadu, Pincode-609702 | Nagapattinam | GBT | MS1 DONE | 10.8997 | 79.7122 | 10.9 | 79.712 | 155-1089-99797120 | 2G+L1800+L2100+L2300+L900 | BSNL | INDUS | 5555 | IN-3133804 | ECO | Done | 2022-08-17 | High Opex Saving_Sep'21 |  | Public Issue | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-17 | 2022-08-20 |  | L18+L21+L23 | L18+L21+L23 | NA | 3 | NA | 9 |  |  | Dec | Dec | 20323117 | 2022-08-23 | 2022-08-23 | 2022-08-24 |  | MS1 DONE | 2022-11-30 | Shajofonica | 2022-12-01 | BOSS MANAGEMENT |  |  |  | 2022-12-03 |  | Relocated |  | 2022-12-02 | TN/11/5177/00305/0043/04/01/17215/NS/02122022 | 2022-12-14 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-03 | [10 empty] | 2023-01-09 | [9 empty] | 2022-12-20 | 2022-12-20 | Phy & Soft AT Pending |  | Phy & Soft AT Pending |  | High Opex Saving_Sep'21 | 2022-12-03
4 | TN | SARKR2 | SARKR1 | Ok | CBE | Relocation | Huawei + Ericsson | Sarkar KannadiPuttur 2 | S.F.No.438/E, Patta No.314, Post: Kannadiputhur Village, Madathukulam, Taluk & District: Tirupur, State: Tamil Nadu, Pincode-642204 | Tiruppur | GBT | MS1 DONE | 10.5308 | 77.3681 | 10.5309 | 77.3681 | 155-1053-09773681 | Hua (2G+4G) + Eric 4G | INDUS | INDUS | IN-1067292 | IN-3138568 | ECO | Done | 2022-08-18 | Opex Saving |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-18 | 2022-08-20 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 4 | NA | 16 |  |  | Sep | Aug | 20323311 | 2022-08-23 | 2022-08-22 | 2022-08-24 |  | MS1 DONE | 2022-08-27 | Shajofonica | 2022-08-27 | RS Teletude |  | CREQ97582 | 2022-08-27 | 2022-08-28 |  | Relocated | Rain | 2022-08-30 | TN/01/5177/01689/0043/04/01/16705/NS/30082022 | 2022-08-30 | V.MANIKANDAN | [5 empty] | Yes | 2022-08-30 |  |  | 2022-10-05 | NA |  | 2022-10-05 | Rahul | 2023-01-16 | 2023-01-19 |  | 2022-08-30 | 2022-08-31 |  | 2023-01-06 | 2023-01-11 |  | 2022-09-27 | 2022-10-01 |  |  | 2023-01-11 |  | Only KPI Pending |  | Only KPI Pending |  | Opex Saving | 30-08-2022
5 | TN | CENYH2 | CENYH1 | Ok | VLR | Relocation | Ericsson | Chennarayanahalli 2 | S. No.216, Patta No.248, Post: Baisuhalli Village, Palacode Union, Taluk: Karimangalam, District: Dharmapuri, State: Tamil Nadu, Pincode-636701 | Dharmapuri | GBT | MS1 DONE | 12.2236 | 78.1889 | 12.224 | 78.189 | 155-1222-39781890 | GL1800+L2100+L2300 | Reliance | INDUS | TN5PLCD001B_37 | IN-3136150 | ECO | Done | 2022-08-20 | Opex Saving |  | Realince confirmation need | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-20 | 2022-08-24 |  | L18+L21+L23+L900 | NA | L18+L21+L23+L900 | 3 | NA | 12 |  |  | Oct | Oct | 20388248 | 2022-08-26 | 2022-08-25 | 2022-08-26 |  | MS1 DONE | 2022-08-08 | Boss management | 2022-08-09 | BOSS MANAGEMENT |  |  |  | 2022-08-10 |  | Relocated |  | 2022-10-10 | TN/03/5177/00519/0043/04/01/16918/NS/10102022 | 2022-10-11 | E.SENTHIL | [5 empty] | Yes | 2022-10-11 |  |  | 2022-10-22 |  |  | 2022-10-22 | Rahul | 2022-11-22 | 2022-11-22 |  | 2023-01-20 | 2022-10-31 |  | 2022-10-29 | 2022-11-03 | kuldeep | 2022-10-27 | 2022-10-31 |  |  | 2022-11-03 |  | Only KPI Pending |  | Only KPI Pending |  | Opex Saving | 2022-10-11
6 | TN | MANVL2 | MANVLl | LINK | TRY | Relocation | Huawei + Ericsson | MANAVELLI | Rasu body builders backside, Post: Manaveli, Taluk & District: Pondicherry, State: Tamil Nadu, Pincode-605502 | Pondy | GBT | MS1 DONE | 11.9911 | 79.6594 | 11.9916 | 79.6595 | 15534-1199-16796594 | Hua (2G+4G) + Eric 4G | Indus | INDUS | IN-1113834 | IN-3131828 | ECO | Done | 2022-08-26 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-26 | 2022-08-30 |  | L18+L2300 | L18 | L2300 | 3 | NA | 6 |  |  | Sep | Sep | 1003427 | 2022-08-31 | 2022-09-01 | 2022-09-01 |  | MS1 DONE | 2022-09-18 | Boss management | 2022-09-18 | BOSS MANAGEMENT |  |  |  | 2022-09-18 |  | Relocated | 0 | 2022-09-19 | TN/16/5177/00330/0043/04/01/16808/NS/19092022 | 2022-09-20 | R.MANIKANDAN | [5 empty] | Yes | 2022-09-20 |  |  | 2022-09-26 |  |  | 2022-09-26 | Rahul | 2022-11-14 | 2022-11-16 |  | 2022-10-01 | 2022-10-01 |  | 2022-11-11 | 2022-11-16 | kuldeep | 2022-09-27 | 2022-10-01 |  | 2023-01-14 | 2023-01-06 | 2023-01-06 | MS2 Done | MAPA_Done | All 3 Accepted |  | LL Issue | 2022-09-20
7 | TN | SLM394 | SLM146 | OK | VLR | Relocation | Huawei | Near Balamani Theatre | TS No.16/2B, S. No.462, ward 9, Balaji Nagar, Post: Ammapet, Taluk & District: Salem, State: Tamilnadu, Pincode-636001 | Salem | GBT | MS1 DONE | 11.6583 | 78.175 | 11.6583 | 78.175 | 155-1165-82781749 | L1800-D | BSNL | INDUS | 3811 | IN-3133899 | ECO | Done | 2022-08-26 | High Opex Saving_Sep'21 |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-26 | 2022-08-30 |  | L18+L21+L23 | L18+L21+L23 | NA | 3 | NA | 9+2 |  |  | Sep | Sep | 20490475 | 2022-08-31 | 2022-08-31 | 2022-09-01 |  | MS1 DONE | 2022-09-05 | Boss management | 2022-09-05 | BOSS MANAGEMENT |  | CREQ98397 | 2022-09-05 | 2022-09-05 |  | Relocated | 0 | 2022-09-10 | TN/10/5177/00858/0043/04/01/16734/NS/06092022 | 2022-09-08 | E.SENTHIL | [5 empty] | Yes | 2022-09-08 |  |  | 2022-10-05 |  |  | 2022-10-05 | Rahul | 2022-09-09 | 2022-09-11 |  | 2023-01-20 | 2022-09-11 |  | 2022-09-07 | 2022-09-11 |  | 2022-10-05 | 2022-10-05 |  | 2023-01-27 | 2023-01-25 | 2023-01-25 | All 3 Accepted | MAPA_Done | All 3 Accepted |  | High Opex Saving_Sep'21 | 2022-09-08
8 | TN | GVPTI4 | GVPTI2 | FD | MDU | Relocation | Ericsson | Ganguvarpatti | Sf.No.8/5/158, Vsaiyappa st, Post: Genguvarpatti, Taluk & District: Theni, State: Tamilnadu, Pincode-625203 | Theni | GBT | MS1 DONE | 10.1694 | 77.6967 | 10.1706 | 77.698 | 155-1017-06776979 | Hua (2G+4G) + Eric 4G | Indus | INDUS | IN-1030719 | IN-3132119 | ECO | Done | 2022-08-26 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-26 | 2022-08-30 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 4 | NA | 15 |  |  | Oct | Oct | 20489029 | 2022-08-30 | 2022-08-31 | 2022-09-01 |  | MS1 DONE | 2022-08-08 | Shajofonica | 2022-08-09 | BOSS MANAGEMENT |  |  |  | 2022-06-10 |  | Relocated |  | 2022-10-07 | TN/06/5177/01094/0043/04/01/16913/NS/07102022 | 2022-10-13 | E.SENTHIL | [5 empty] | Yes | 2022-10-13 |  |  | 2023-02-03 |  |  | 2023-02-03 |  | 2022-11-24 |  |  | 2023-01-20 | 2022-11-20 |  | 2022-11-19 | 2022-11-24 |  | 2022-11-16 | 2022-11-20 |  |  | 2022-11-24 |  | Phy & KPI AT Pending |  | Phy & KPI AT Pending |  | LL Issue | 2022-10-13
9 | TN | TRY403 | TRY66 | FD | TRY | Relocation | Huawei + Ericsson | Central excise quarters | Sf.No.150/1, Mullai st, Ashok Nagar W, Post: Karumandapam, Taluk & District: Tiruchirappalli, State: Tamil Nadu, Pincode-620001 | Tiruchirappalli | GBT | MS1 DONE | 10.7856 | 78.6631 | 10.7845 | 78.6633 | 155-1078-45786633 | Hua (2G+4G) + Eric 4G | Indus | INDUS | IN-1062128 | IN-3131827 | Indus_Lite+ | Done | 2022-08-26 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-26 | 2022-08-30 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 4 | NA | 14 |  |  | Sep | Sep | 20489214 | 2022-08-31 | 2022-08-30 | 2022-08-31 |  | MS1 DONE | 2022-09-03 | Shajofonica | 2022-09-03 | BOSS MANAGEMENT |  | SREQ868606 | 2022-09-05 | 2022-09-02 |  | Relocated | 0 | 2022-09-06 | TN/13/5177/01996/0043/04/01/16732/NS/06092022 | 2022-09-07 | R.MANIKANDAN | [5 empty] | Yes | 2022-09-07 |  |  | 2022-09-26 |  |  | 2022-09-26 | Rahul |  |  |  | 2022-10-19 | 2022-10-21 |  | 2022-12-20 | 2022-12-25 |  | 2022-12-23 | 2022-12-25 |  |  | 2022-10-28 | 2022-10-28 | Only Phy Pending |  | Only Phy Pending |  | LL Issue | 2022-09-07
10 | TN | ERD247 | ERD60 | Ok | CBE | Relocation | Huawei + Ericsson | Manickampalayam | New door no.167 to 179, T.S.No.1321, Ward no.53, Nethaji Rd, Kalukadimedu, Post: Surampattivalasu, Taluk: Marapalam, District: Erode: State: Tamil Nadu, Pincode-638001 | Erode | RTT | MS1 DONE | 11.335 | 77.7319 | 11.335 | 77.7332 | 155-1133-50777331 | Hua (2G+4G) + Eric 4G | Reliance | INDUS | TN6ERODE0006G_12 | IN-3136109 | STANDARD_PRODUCT | Done | 2022-08-26 | Opex Saving |  | Realince confirmation need | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-08-26 | 2022-08-30 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 3 | NA | 12 |  |  | Oct | Oct | 20478549 | 2022-08-30 | 2022-08-29 | 2022-08-30 |  | MS1 DONE | 2022-11-02 | Shajofonica | 2022-08-09 | BOSS MANAGEMENT |  |  |  | 2022-08-10 |  | Relocated |  | 2022-10-10 | TN/04/5177/00467/0043/04/01/16920/NS/10102022 | 2022-10-11 | V.MANIKANDAN | [5 empty] | Yes | 2022-10-11 |  |  | 2022-11-19 |  |  | 2022-11-19 | Rahul |  |  |  | 2023-01-20 | 2022-10-20 |  | 2022-10-15 | 2022-10-20 |  | 2022-10-16 | 2022-10-20 |  |  | 2022-10-20 |  | Phy & KPI AT Pending |  | Phy & KPI AT Pending |  | Opex Saving | 2022-10-11
11 | TN | KDKL46 | KDKL14 | OK | MDU | Relocation | Huawei + Ericsson | Shenbaganur kodaikanal | S.F.No: 70/3 & 72/1, Mr. Selvaraj.S S/o Sebastian, Post: Senbahanoor, Taluk: Kodaikanal, District: Dindigul, State: Tamil Nadu, Pincode-624101. | Dindigul | GBT | MS1 DONE | 10.233 | 77.5097 | 10.233 | 77.5097 | 155-1023-29775097 | Hua (2G+4G) + Eric 4G | BSNL | ATC | 2467 | TN/DI/AT/23081 | ECO | Done | 2022-08-30 | BSNL Exit Feasible Sites |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-02 | 2022-09-06 |  | L18+L23+L900 | L18 | L23+L900 | 3 | NA | 10 |  |  | Sep | Sep | 20621740 | 2022-09-07 | 2022-09-08 | 2022-09-09 |  | MS1 DONE | 2022-09-11 | Shajofonica | 2022-09-11 | BOSS MANAGEMENT |  | SREQ879085 | 2022-09-13 | 2022-09-11 |  | Relocated | 0 | 2022-09-12 | TN/06/5126/00240/0043/04/01/16753/NS/12092022 | 2022-09-12 | V.MANIKANDAN | [5 empty] | Yes | 2022-09-13 |  |  | 2022-09-26 |  |  | 2022-09-26 | Rahul |  |  |  | 2022-10-19 | 2022-10-21 |  | 2022-09-19 | 2022-09-24 |  | 2022-09-20 | 2022-09-24 |  |  | 2022-09-24 |  | Phy & KPI AT Pending |  | Phy & KPI AT Pending |  | BSNL Exit Feasible Sites | 2022-09-13
12 | TN | NLGRI4 | NLGR1 | OK | TRY | Relocation | Huawei + Ericsson | Neelagiri 14 | Mr.Sivakumar, No.60, Maris Nagar St, MC Road, Post & Taluk & District: Thanjavur, State: Tamilnadu, Pincode-613004 | Thanjavur | GBT | MS1 DONE | 10.7503 | 79.0908 | 10.7503 | 79.0908 | 155-1074-99790909 | Hua (2G+4G) + Eric 4G | Indus | Summit | IN-1059525 | I-TN-TJVR-ENB-0043 | STANDARD_PRODUCT | Done | 2022-09-02 | Opex Saving |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-02 | 2022-09-06 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 4 | NA | 16 |  |  | Sep | Sep | 20684546 | 2022-09-09 | 2022-09-10 | 2022-09-11 |  | MS1 DONE | 2022-09-14 | Boss management | 2022-09-14 | BOSS MANAGEMENT |  |  |  | 2022-09-14 |  | Relocated | 0 | 2022-09-16 | TN/17/5428/0249/0043/04/01/16790/NS/17092022 | 2022-09-17 | V.MANIKANDAN | [5 empty] | Yes | 2022-09-17 |  |  | 2022-10-04 | 2022-10-04 |  | 2022-10-04 | Rahul | 2022-09-14 | 2022-10-04 |  | 2022-09-30 | 2022-10-04 |  | 2022-10-05 | 2022-10-10 | kuldeep | 2022-09-27 | 2022-10-01 |  |  | 2022-10-10 |  | Soft & KPI AT Pending | MAPA_Done | Soft & KPI AT Pending |  | Opex Saving | 2022-09-17
13 | TN | DGL123 | DGL38 | OK | MDU | Relocation | Huawei + Ericsson | Hasthanapuram | Mr.Hasan Mohamed,CHITHARA HALLOW BLOCKS, Dindigul - Vellodu - Madurai Rd, Post: Begambur, Taluk & District: Dindigul, State: Tamil Nadu, Pincode-624002 | Dindigul | GBT | MS1 DONE | 10.3378 | 77.9578 | 10.3378 | 77.9576 | 155-1033-78779575 | Hua (2G+4G) + Eric 4G | Tower Vision | Summit | DATNDGL1372 | I-TN-DDGL-ENB-0038 | STANDARD_PRODUCT | Done | 2022-09-05 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-06 | 2022-09-06 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 3 | NA | 12 |  |  | Sep | Sep | 20651999 | 2022-09-08 | 2022-09-09 | 2022-09-10 |  | MS1 DONE | 2022-09-16 | Boss management | 2022-09-16 | BOSS MANAGEMENT |  |  |  | 2022-09-16 |  | Relocated | 0 | 2022-09-19 | TN/06/5428/0576/0043/04/01/16807/NS/19092022 | 2022-09-17 | E.SENTHIL | [5 empty] | Yes | 2022-09-20 |  |  | 2022-11-19 |  |  | 2022-11-19 | Rahul | 2022-10-22 | 2022-10-24 |  | 2022-11-20 | 2022-10-24 |  | 2022-10-12 | 2022-10-17 | kuldeep | 2022-09-27 | 2022-10-01 |  |  | 2022-10-17 |  | Only KPI Pending |  | Only KPI Pending |  | Opex Saving(344) | 2022-09-20
14 | TN | PDY391 | PDY04 | FD | TRY | Relocation | Huawei + Ericsson | Ellapillaichavadi | RS No.62/78, Iyyanar Koil St, Post: Ellaipillaichavady, Sithananda Nagar, Kuyavarpalayam, Taluk & District: Puducherry, State: Tamilnadu, Pincode-605005 | Pondy | RTT | MS1 DONE | 11.9333 | 79.8072 | 11.9337 | 79.8066 | 15534-1193-36798065 | Hua (2G+4G) + Eric 4G | Indus | Indus | IN-1061659 | IN-3139956 | Indus_Lite+ | Done | 2022-09-05 | Unsafe |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-06 | 2022-09-06 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 4 | NA | 16 |  |  | Nov | Nov | 1003449 | 2022-09-08 | 2022-09-09 | 2022-09-10 |  | MS1 DONE | 2022-11-15 | Shajofonica | 2022-11-15 | RS Teletude |  |  |  | 2022-11-17 |  | Relocated |  | 2022-11-21 | TN/16/5177/00333/0043/04/01/17103/NS/21112022 | 2022-11-23 | R.MANIKANDAN | [5 empty] | Yes | 2022-11-23 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul | 2022-12-05 | 2022-12-09 |  | 2022-12-05 | 2022-12-09 |  | 2022-12-01 | 2022-12-06 | kuldeep | 2023-01-19 | 2023-01-19 |  |  | 2022-12-15 | 2022-12-15 | Only SOFT Pending |  | Only SOFT Pending |  | Unsafe | 2022-11-23
15 | TN | VNDNI3 | VNDNI1 | OK | MDU | Relocation | Huawei + Ericsson | Vendoni | Patta no.2883, 334/21, Post: Vendoni village, Taluk: Paramakudi, District: Ramnad, State: Tamilnadu, Pincode-623707 | Ramanathapuram | GBT | MS1 DONE | 9.5169 | 78.6014 | 9.5169 | 78.6014 | 155-0951-45786008 | Hua (2G+4G) + Eric 4G | BSNL | Indus | 3661 | IN-3133822 | ECO | Done | 2022-09-05 | BSNL Exit Feasible Sites |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-06 | 2022-09-06 |  | L18+L21 | L18 | L21 | 3 | NA | 6 |  |  | Sep | Sep | 20651954 | 2022-09-08 | 2022-09-09 | 2022-09-10 |  | MS1 DONE | 2022-09-13 | Shajofonica | 2022-09-13 | BOSS MANAGEMENT |  |  |  | 2022-09-13 |  | Relocated |  | 2022-09-16 | TN/05/5177/00486/0043/04/01/16786/NS/16092022 | 2022-09-17 | V.MANIKANDAN | [5 empty] | Yes | 2022-09-17 |  |  | 2022-09-24 | 2022-09-24 |  | 2022-09-24 | Rahul | 2022-09-21 | 2022-09-24 |  | 2022-10-19 | 2022-09-24 |  | 2022-09-17 | 2022-09-22 | kuldeep | 2022-09-20 | 2022-09-24 |  |  | 2023-01-06 | 2023-01-06 | Only SOFT Pending |  | Only SOFT Pending |  | BSNL Exit Feasible Sites | 2022-09-17
16 | CHN | ASHO23 | ASHOK | FD | CHN | Relocation | Huawei + Ericsson |  |  | Chennai | RTT | MS1 DONE | 13.0322 | 80.2197 | 13.0321 | 80.2194 | 152-1303-20802195 | Hua (2G+4G) + Eric 4G | INDUS | Indus | IN-1043982 | IN-3042571 | STANDARD_PRODUCT | Done | 2022-09-07 | Unsafe |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-08 | 2022-09-07 |  | L18+L21+L23+L900 | L23 | L900+UBR | 3 | NA | 12 |  |  | Oct | Oct | 79365 | 2022-09-16 | 2022-09-17 | 2022-09-18 |  | MS1 DONE | 2022-09-24 | Shajofonica | 2022-09-23 | BOSS MANAGEMENT |  |  |  | 2022-09-24 |  | Relocated | pri issue | 2022-09-28 |  | 2022-10-01 | R.MANIKANDAN | [5 empty] | Yes | 2022-10-01 |  |  | 2022-09-30 |  |  | 2022-09-30 | Rahul | 2022-11-09 | 2022-11-14 |  | 2022-10-01 | 2022-10-01 |  | 2022-11-19 | 2022-11-24 | kuldeep | 2022-09-27 | 2022-10-01 |  |  |  |  | Only KPI Pending | Under_ATP | Only KPI Pending |  | Unsafe | 2022-10-01
17 | TN | TECGE3 | TECGE1 | ok | TRY | Relocation | Huawei + Ericsson | Trichy Engg college | S.F.No.81/7, Post: Konalai Village, Taluk: Manchanallur, District: Tiruchirappalli, State: Tamil Nadu, Pincode-621105 | Tiruchirappalli | GBT | MS1 DONE | 10.9822 | 78.7733 | 10.9835 | 78.7728 | 155-1098-34787728 | Hua (2G+4G) + Eric 4G | BSNL | Indus | 6231 | IN-3144602 | ECO | Done | 2022-09-10 | High Opex Saving_Sep'21 |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-12 | 2022-09-16 |  | L18+L21+L23 | L18 | L21+L23 | 3 | NA | 8 |  |  | Sep | Sep | 20817618 | 2022-09-16 | 2022-09-19 | 2022-09-20 |  | MS1 DONE | 2022-09-20 | Boss management | 2022-09-20 | BOSS MANAGEMENT |  |  |  | 2022-09-21 |  | Relocated | No delay | 2022-09-23 | TN/13/5177/01999/0043/04/01/16841/NS/23092022 | 2022-09-24 | R.MANIKANDAN | [5 empty] | Yes | 2022-09-25 |  |  | 2022-09-26 |  |  | 2022-09-26 | Rahul | 2022-10-01 | 2022-10-04 |  | 2022-11-20 | 2022-10-04 |  | 2022-09-22 | 2022-09-27 | kuldeep | 2022-10-16 | 2022-10-20 |  |  | 2022-09-27 |  | Only KPI Pending |  | Only KPI Pending |  | High Opex Saving_Sep'21 | 2022-09-25
18 | TN | NSNP17 | NSNP6 | Ok | CBE | Relocation | Huawei + Ericsson | Gudalur | No.63, Narayanasamy Lay-out, ksb, opposite Samraj Avenue, Post: Narasimhanaickenpalayam, Taluk & District: Coimbatore, State: Tamil Nadu, Pincode-641031 | Coimbatore | GBT | MS1 DONE | 11.1225 | 76.9353 | 11.122 | 76.9378 | 155-1112-19769378 | Hua (2G+4G) + Eric 4G | Indus | Indus | IN-1307896 | IN-3096531 | STANDARD_PRODUCT | Done | 2022-09-12 | Agreement expiry |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-13 | 2022-09-16 |  | L18+L21+L23 | L18 | L21+L23(TB IN B) | 3 | NA | 10 |  |  | Dec | Dec | 22309170 | 2022-12-08 | 2022-12-08 | 2022-12-08 |  | MS1 DONE | 2022-12-12 | RS Teletude | 2022-12-12 | RS Teletude |  |  |  | 2022-12-12 |  | Relocated |  | 2022-12-12 | TN/01/5177/01659/0043/04/01/17253/NS/13122022 | 2022-12-23 | SATHISH | [5 empty] | Yes | 2022-12-12 | [10 empty] | 2023-01-09 |  |  | 2023-01-02 | 2023-01-07 |  | 2022-12-16 | 2022-12-20 |  |  | 2022-12-20 | 2022-12-20 | Only Phy Pending |  | Only Phy Pending |  | Agreement expiry | 2022-12-14
19 | TN | KMKPM2 | KMKPM1 | Ok | VLR | Relocation |  | Kalmelkuppam 2 | Sf.No.426/1c, Post: Kanikapuram, Taluk: kalmelkuppam village, District: Ranipet, State: Tamilnadu, Pincode-632405 | VELLORE | GBT | AOM Approval Pending | 12.9928 | 79.3417 | 12.993 | 79.3416 | 155-1299-30793416 | 2G+L1800+L2300+L900 | GTL | Indus | TAM/GBT/K/28551 | IN-3138296 | ECO | Done | 2022-09-13 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-14 | 2022-09-16 |  | L18+L21+L23+L900 | - | UBR+L23+L900 | 3 | NA | 9 |  |  | Feb'23 |  | 20820603 | 2022-09-16 | 2022-09-19 | 2022-09-20 |  | CNIL ACCESS NOT CLEAR//Followup Mail given | [9 empty] | Pending | [10 empty] | Yes |  | 149 | [21 empty] | Installation Pending |  |  |  | Opex Saving(344) | #N/A
20 | TN | TINDL2 | TINDL1 | LINK | CBE | Relocation |  | Indra Nagar Near Thindal 2 | S.F.No.81/1, Post: Mel Thindal, Taluk & District: Erode, State: Tamil Nadu, Pincode-638012 | Erode | GBT | New site change to FD,then only we can relocate , | 11.3181 | 77.6739 | 11.3183 | 77.6739 | 155-1131-79776738 | Hua (2G+4G) + Eric 4G | TVI | Indus | DATNERD1395 | IN-3138660 | ECO | Done | 2022-09-17 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-17 | 2022-09-19 |  | L18+L21+L23+L900 | L18+L21+L23 | L900 | 3 | NA | 14 |  |  | Feb'23 |  | 20924860 | 2022-09-21 | 2022-09-20 | 2022-09-21 |  | Access issue //Mail given to toco | [9 empty] | Pending | [10 empty] | Yes |  | 146 | [21 empty] | Installation Pending |  |  |  | Opex Saving(344) | #N/A
21 | TN | UDYPT3 | UDYPT2 | Ok | TRY | Relocation | Huawei + Ericsson |  |  | Tiruchirappalli | GBT | MS1 DONE | 10.7425 | 78.6892 | 10.7425, | 78.6892 | 155-1074-23786885 | Hua (2G+4G) + Eric 4G | Ascend | Indus | 0007178 | IN-3138340 | ECO | Done | 2022-09-18 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-19 | 2022-09-20 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 4 | NA | 14 |  |  | Oct | Oct | 20917446 | 2022-09-21 | 2022-09-20 | 2022-09-21 |  | MS1 DONE | 2022-10-01 | Shajofonica | 2022-10-02 | BOSS MANAGEMENT |  |  |  | 2022-10-02 |  | Relocated | Height Issues so SCFT not done | 2022-10-02 | TN/13/5177/02001/0043/04/01/16908/NS/06102022 | 2022-10-08 | E.SENTHIL | [5 empty] | Yes | 2022-10-08 |  |  | 2022-10-18 | 2022-10-18 |  | 2022-10-18 | Rahul | 2022-12-22 | 2022-10-11 |  | 2022-11-15 | 2022-10-11 |  | 2022-12-17 | 2022-10-18 | [5 empty] | 2022-10-18 |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | Field visit required for rectification | 2022-10-08
22 | TN | CBE948 | CBE253 | Ok | CBE | Relocation | Huawei + Ericsson |  |  | Coimbatore | YET_TO_BE_FINALIZED | MS1 DONE | 10.9536 | 76.9769 | 10.9537 | 76.9772 | 155-1095-47769790 | Hua (2G+4G) + Eric 4G | ATC | TVI | TN4110 | VDTNCBE1774 | STANDARD_PRODUCT | Done | 2022-09-19 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-20 | 2022-09-22 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 4 | NA | 17 |  |  | Oct | Oct | 20953731 | 2022-09-22 | 2022-09-23 | 2022-09-24 |  | MS1 DONE | 2022-04-08 | Shajofonica | 2022-05-08 | BOSS MANAGEMENT |  |  |  | 2022-05-08 |  | Relocated |  | 2022-05-08 | TN/01/5113/0146/0043/04/01/16907/NS/06102022 | 2022-10-08 | V.MANIKANDAN | [5 empty] | Yes | 2022-10-08 |  |  | 2022-10-17 |  |  | 2022-10-17 | Rahul | 2022-10-14 | 2022-10-18 |  | 2022-11-20 | 2022-10-18 |  | 2022-10-10 | 2022-10-15 | kuldeep | 2022-10-10 | 2022-10-14 |  |  | 2022-10-15 |  | Only KPI Pending |  | Only KPI Pending |  | Opex Saving(344) | 2022-10-08
23 | TN | VDGPI2 | VDGPI1 | Ok | CBE | Relocation | Huawei + Ericsson | Vadugapatti 2 | MRS. ANKODI LAND, W/O. K.N. SUBRAMANIAM, SF NO. 665/1, POST: VADUGAPATTI, TALUK: ARCHALLUR, DISTRICT: ERODE, STATE: TAMILNADU, PINCODE-638101 | Erode | GBT | MS1 DONE | 11.1511 | 77.7378 | 11.1511 | 77.7378 | 155-1115-21777362 | 2G+L1800+L2300+L900 | GTL | Indus | TAM/GBT/K/30945 | IN-1059252 | Sharing | Done | 2022-09-19 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-20 | 2022-09-21 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L2100+L900 | 4 | done | 15 |  |  | Dec | Dec | 22252762 | 2022-12-02 | 2022-12-02 | 2022-12-02 |  | MS1 DONE | 2022-12-02 | Shajofonica | 2022-12-02 | BOSS MANAGEMENT |  |  |  | 2022-12-04 |  | Relocated |  | 2022-12-03 | TN/14/5177/0748/0043/04/01/17220/NS/03122022 | 2022-12-04 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-04 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2023-01-02 | 2023-01-03 |  | 2023-01-09 | 2023-01-03 |  | 2022-12-20 | 2022-12-25 |  | 2022-12-23 | 2022-12-25 |  |  | 2022-12-15 | 2022-12-15 | Only SOFT Pending |  | Only SOFT Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-04
24 | CHN | BESA12 | BESAN2 | Ok | CHN | Relocation | Ericsson | Adyar Besant Court | Mr. M Ravi, No.89, Ellaiamman Koil Street, Vannadurai, Post: Adyar, Taluk & District: Chennai, State: Tamilnadu, Pincode-600020 | Chennai | RTT | FTTH Provisional Pending | 13 | 80.2628 | 12.99972, | 80.2625 | 152-1299-97802624 | Hua(4G)+Eric(2G+4G) | INDUS | TVI | IN-1006924 | BSTNCHN1884 | STANDARD_PRODUCT | Done | 2022-09-19 | High Opex |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-20 | 2022-09-21 |  | L18+L21+L23+L900 | L23 | UBR+L900 | 3 | NA | 12 |  |  | Feb'23 | Feb'23 | 79540 | 2022-09-23 | 2022-09-24 | 2022-09-25 |  | Installation completed, New Material,2G not ping wip | 2023-01-25 | Boss Management | 2022-10-17 | BOSS MANAGEMENT |  |  |  | 2023-01-10 |  |  |  | 2023-02-03 |  | 2023-02-02 | V.SIVA | [5 empty] | Yes | 2023-02-03 | [22 empty] | MS1 Pending |  |  |  | High Opex | 2023-01-02
25 | TN | DPI061 | DPI10 | Ok | VLR | Relocation |  | Old Dharmapuri 61 | Mr M Perumal Mr M Perumal, S/o Molai Ghounder, No.4/247, Krishnagiri Road, Pillayar Kovil St, 5557+F33, Post: Hale, Taluk & District: Dharmapuri, State: Tamil Nadu, Pincode-636701 | Dharmapuri | GBT | Access issue, Inc new matiriels required | 12.1583 | 78.1614 | 12.1583 | 78.1614 | 155-1215-81781621 | 2G+L1800+L2100+L2300+L900(Don’t put L2100 in 100) | Indus | Summit | IN-1031175 | I-TN-DMPI-ENB-0010 | STANDARD_PRODUCT | Done | 2022-09-22 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-22 | 2022-09-24 |  | L18+L21+L23+L900 | L18 | L23+L18+L900 | 4 | NA | 15 |  |  | Feb'23 | [6 empty] | Access issue, Material need to take back to Warehouse | [9 empty] | Pending | [10 empty] | Yes |  | 141 | [21 empty] | Installation Pending |  |  |  | Opex Saving(344) | #N/A
26 | CHN | ANNA34 | ANNAN7 | Ok | CHN | Relocation | Huawei + Ericsson | Anna Nagar34 | No.108, A Block, 5th st, Post: Anna nagar east, Taluk & District: Chennai, State: Tamilnadu, Pincode-600102 | Chennai | RTT | Power cable approval pending | 13.0839 | 80.2181 | 13.0839 | 80.2181 | 152-1308-38802181 | 2G+L1800+L2100+L2300+L900 | Reliance | Indus | TN_CHENN_099 | IN-3134201 | Indus_Lite+ | Done | 2022-09-22 | High Opex Saving_Sep'21 |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-22 | 2022-09-26 |  | L18+L21+L23+L900 | L23 | UBR+L900 | 3 | NA | 9 |  |  | Feb'23 | [6 empty] | FTTH MEDIA NOT READY |  |  | 2022-11-01 | SHAJOFONICA | [5 empty] | Pending | [10 empty] | Yes |  | 141 | [21 empty] | Installation Pending |  |  |  | High Opex Saving_Sep'21 | #N/A
27 | TN | DGL122 | DGL18 | Ok | MDU | Relocation | Huawei + Ericsson |  |  | Dindigul | RTT | MS1 DONE | 10.3625 | 77.9822 | 10.3625 | 77.9822 | 155-1036-35779823 | 1800 + 2100 + 2300 (2G + 4G) | ATC | Indus | TANDIN0347 | IN-3138629 | Indus_Lite+ | Done | 2022-09-22 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-23 | 2022-09-24 |  | L18+l21+l2300 | L18 | L21+L23 | 3 | NA | 14 |  |  | Oct | Oct | 21402217 | 2022-10-13 | 2022-10-13 | 2022-10-15 |  | MS1 DONE | 2022-10-18 | Shajofonica | 2022-10-18 | BOSS MANAGEMENT |  |  |  | 2022-10-18 |  | Relocated |  | 2022-10-19 | TN/06/5177/01098/0043/04/01/16954/NS/19102022 | 2022-11-05 | V.MANIKANDAN | [5 empty] | Yes | 2022-10-18 |  | 2022-11-24 | 2022-11-19 |  |  | 2022-11-19 | Rahul | 2022-11-24 | 2022-11-27 |  | 2022-11-20 | 2022-11-20 |  | 2022-11-19 | 2022-11-24 |  | 2022-11-16 | 2022-11-20 |  |  | 2022-11-24 |  | Only KPI Pending |  | Only KPI Pending |  | Opex Saving(344) | 2022-10-20
28 | TN | KPKTR2 | KPKTR1 | Ok | TRY | Relocation | Huawei + Ericsson |  |  | Karur | YET_TO_BE_FINALIZED | MS1 DONE | 10.9883 | 78.055 | 10.9883 | 78.055 | 155-1098-84780551 | Hua(4G)+Eric(2G+4G) | Tower Vision | Indus | BSTNKAR1339 | - | ECO | Done | 2022-09-22 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-23 | 2022-09-24 |  | L18+L21+L23+L900 | L18 | L21+L23+L900 | 3 | NA | 12 |  |  | Oct | Oct | 21096242 | 2022-09-29 | 2022-09-30 | 2022-10-01 |  | MS1 DONE | 2022-10-12 | Shajofonica | 2022-10-12 | BOSS MANAGEMENT |  |  |  | 2022-10-12 |  | Relocated |  | 2022-10-12 | TN/13/5177/02002/0043/04/01/16929/NS/12102022 | 2022-10-17 | V.MANIKANDAN | [5 empty] | Yes | 2022-10-17 |  |  | 2022-10-22 |  |  | 2022-10-22 | Rahul | 2022-10-12 | 2022-10-16 |  | 2022-11-20 | 2022-10-16 |  | 2022-10-13 | 2022-10-17 |  |  | 2022-10-20 |  |  | 2022-10-17 |  | Only KPI Pending |  | Only KPI Pending |  | Opex Saving(344) | 2022-10-17
29 | TN | CBE929 | CBEM65 | Ok | CBE | Relocation | Huawei | Hotel Lemon Tree¦Relocation | Mr. Dharmaraja R, S/o. Ramasamy, Site No. 2, S.No. 169/1, Siva Nagar, Post: Kalapatti, Taluk & District: Coimbatore, State: Tamil Nadu, Pincode-641035 | Coimbatore | GBM | MS1 DONE | 11.075 | 77.0281 | 11.0765 | 77.029 | 155-1107-65770289 | 2G+L1800+L2300+L900 | ATC | ATC | TANCOI5645 | TN/CO/AT/23065 | ATC_LITE_POLE_SITE | Done | 2022-09-25 | Less AGL |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-25 | 2022-09-28 |  | L18+L23 | L18+L23 | NA | 3 | NA | 5 |  |  | Nov | Nov | 21425296 | 2022-10-14 | 2022-10-15 | 2022-10-16 |  | MS1 DONE | 2022-11-02 | Shajofonica | 2022-11-02 | SHAJOFONICA |  |  |  | 2022-11-02 |  | Relocated |  | 2022-11-17 | TN/01/5126/00431/0043/04/01/17081/NS/17112022 | 2022-11-24 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-24 |  |  | 2022-12-17 |  |  | 2022-12-17 | Rahul | 2022-11-11 | 2022-11-16 |  | 2023-01-09 | 2022-11-16 |  | 2022-11-12 | 2022-11-16 | [5 empty] | 2022-12-06 | 2022-12-06 | Only SOFT Pending |  | Only SOFT Pending |  | Less AGL | 2022-11-24
30 | CHN | TRUST8 | TRUST3 | Ok | CHN | Relocation |  | Trust puram | MR.S.ABDUL AZEEM, NO.4/99 , 6th CROSS STREET, TRUSTPURAM, POST: KODAMBAKKAM, TALUK & DISTRICT: CHENNAI, STATE: TAMILNADU, PINCODE-600024 | Chennai | RTT | Material Dispatched means relocate. | 13.0566 | 80.2265 | 13.05692, | 80.226 | 152-1305-69802259 | 2G+L1800+L2300+L900(Don’t put L900 in 60) | INDUS | ATC | IN-1237752 | TN/CH/VD/12654 | STANDARD_PRODUCT | Done | 2022-09-25 | High Opex |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-26 | 2022-09-27 |  | L18+L21 | L18+L21 | NA | 3 | NA | 6 |  |  | Feb'23 |  | 79918 | 2022-10-12 | 2022-10-13 | 2022-10-13 |  | Access issue //Mail given to toco | [9 empty] | Pending | [10 empty] | Yes |  | 137 | [21 empty] | Installation Pending |  |  |  | High Opex | #N/A
31 | CHN | MOGW31 | MOGWE7 | Ok | CHN | Relocation | Huawei + Ericsson |  |  | Chennai | RTT | MS1 DONE | 13.085 | 80.1656 | 13.08508, | 80.1657 | 152-1308-50801656 | GL1800+L2100+L2300+L900 | INDUS | ATC | IN-1070952 | TN/CH/VO/10915 | STANDARD_PRODUCT | Done | 2022-09-25 | High Opex |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-26 | 2022-09-30 |  | L18+L21+L23 | L18+L21+L23 | NA | 4 | NA | 12 |  |  | Oct | Oct | [5 empty] | MS1 DONE | 2022-10-16 | Boss management | 2022-10-18 | BOSS MANAGEMENT |  |  |  | 2022-10-16 |  | Relocated |  | 2022-10-25 |  | 2022-10-25 | R.MANIKANDAN | [5 empty] | Yes | 2022-10-25 |  |  | 2022-12-17 |  |  | 2022-12-17 | Rahul |  |  |  | 2023-01-20 | 2022-10-31 |  | 2022-10-26 | 2022-10-31 |  | 2022-10-27 | 2022-10-31 |  |  |  |  | Phy & KPI AT Pending | Under_ATP | Phy & KPI AT Pending |  | High Opex | 2022-10-25
32 | CHN | NMROA3 | NMROA | Ok | CHN | Relocation |  | Nelson Manickm Rd | AMPA Manor, No.623, Poonamallee High Rd, Post: Aminjikarai, Taluk & District: Chennai, State: Tamilnadu, Pincode-600029 | Chennai | RTT | Ericssion Done means will plan | 13.0714 | 80.2228 | 13.0718 | ,80.2225 | 152-1307-17802221 | 2G+L1800+L2100+L2300+TTB-A | INDUS | ATC | IN-1044190 | TN/CH/TT/12843 | STANDARD_PRODUCT | Done | 2022-09-25 | High Opex |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-26 | 2022-09-27 |  | L23+L18+L21 | L18+L21+L23 | NA | 4 | NA | 11 |  |  | Feb'23 |  | 79917 | 2022-10-12 | 2022-10-13 | 2022-10-14 |  | Access issue //Mail given to toco | [9 empty] | Pending | [10 empty] | Yes |  | 137 | [21 empty] | Installation Pending |  |  |  | High Opex | #N/A
33 | CHN | PATT30 | PATT22 | Ok | CHN | Relocation |  | Pattabiram 30 | S. No.1/4, 3, Pandiyan St,Rajiv Nagar, No.10, Mechanical Block Rd, Shastri Nagar, Post: Muthapudupet, Taluk: Pattabiram, District: Chennai, State: Tamil Nadu, Pincode-600055 | Chennai | GBT | AOM Approval Pending, | 13.1469 | 80.0558 | 13.146944, | 80.0558 | 152-1314-69800560 | 2G+L1800+L2100+L2300+L900+TTB-B | GTL | Indus | CHN/GBT/K/08601 | IN-3138219 | ECO | Done | 2022-09-25 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-26 | 2022-09-30 |  | L18+L21+L23+L900 | L23 | L18+L21+L23 | 4 | NA |  |  |  | Feb'23 |  | 79702 | 2022-09-30 | 2022-09-04 | 2022-09-05 |  | CNIL ACCESS NOT CLEAR//Followup Mail given | [9 empty] | Pending | [10 empty] | Yes |  | 137 | [21 empty] | Installation Pending |  |  |  | LL Issue | #N/A
34 | TN | VYMDU2 | VYMDU1 | Ok | TRY | Relocation | Huawei + Ericsson |  |  | Nagapattinam | GBT | MS1 DONE | 10.4083 | 79.6892 | 10.408707, | 79.687 | 155-1040-76796868 | GL1800+L2100 | BSNL | Indus | 1654 | IN-3133854 | ECO | Done | 2022-09-25 | BSNL Exit Feasible Sites |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-26 | 2022-09-30 |  | L2100 |  | L2100 | 3 | NA | 2219B1*3 |  |  | Oct | Oct | 21120773 | 2022-09-30 | 2022-09-04 | 2022-09-05 |  | MS1 DONE | 2022-10-07 | Boss management | 2022-07-10 | BOSS MANAGEMENT |  |  |  | 2022-08-10 |  | Relocated |  | 2022-10-10 | TN/17/5177/01876/0043/04/01/16919/NS/10102022 | 2022-10-10 | V.MANIKANDAN | [5 empty] | Yes | 2022-10-10 |  |  | 2022-11-19 |  |  | 2022-11-19 | Rahul | 2022-10-28 | 2022-11-01 |  | 2022-10-28 | 2022-11-01 |  | 2022-10-26 | 2022-10-31 | kuldeep | 2022-10-16 | 2022-10-20 |  | 2022-12-05 | 2022-11-11 | 2022-11-15 | MS2 Done | MAPA_Done | All 3 Accepted |  | BSNL Exit Feasible Sites | 2022-10-10
35 | TN | TOTNU2 | TOTNU1 | Ok | MDU | Relocation |  | Tottanuthu 2 | Sf.No.490, Post: Thotanathu village, Taluk & District: Dindigul, State: Tamil Nadu, Pincode-624003 | Dindigul | GBT | AOM Approval Pending | 10.3414 | 80.0558 | 10.3414 | 78.0174 | 155-1034-14780173 | 2G+L1800+L2100+L2300+L900 | Reliance | Indus | TN5DDGL005B_26 | IN-3136093 | ECO | Done | 2022-09-25 | Opex Saving |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-26 | 2022-09-27 |  | L18+L21+L23+L900 | L18+L21+L23 | L900 | 3 | NA | 12 |  |  | Feb'23 |  | 21284690 | 2022-10-08 | 2022-10-10 | 2022-10-10 |  | Access issue //Mail given to toco | [9 empty] | Pending | [10 empty] | Yes |  | 137 | [21 empty] | Installation Pending |  |  |  | Opex Saving | #N/A
36 | TN | KLPVR6 | KLPVR2 | Ok | MDU | Relocation | Huawei + Ericsson |  |  | Tirunelveli | GBT | MS1 DONE | 8.9183 | 77.3967 | 8.918333, | 77.3967 | 155-0891-88773963 | GL1800+L2100+L2300+900 | Tower Vision | Indus | BSTNTNL1208 | IN-3138433 | ECO | Done | 2022-09-25 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-26 | 2022-09-27 |  | L18+L21+L23+L900(TB-A) | L18 | L21+L23+L900 | 4 | NA | 16 |  |  | Oct | Oct | 21284629 | 2022-10-08 | 2022-10-10 | 2022-10-11 |  | MS1 DONE | 2022-10-15 | Boss management | 2022-10-15 | BOSS MANAGEMENT |  |  |  | 2022-10-15 |  | Relocated |  | 2022-10-20 | TN/12/5426/00001/0043/04/01/16955/NS/19102022 | 2022-10-20 | E.SENTHIL | [5 empty] | Yes | 2022-10-20 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul | 2022-10-17 | 2022-10-21 |  | 2022-11-20 | 2022-10-21 |  | 2022-10-26 | 2022-10-31 | kuldeep | 2022-10-16 | 2022-10-20 |  |  | 2022-11-15 | 2022-11-15 | Only SOFT Pending |  | Only SOFT Pending |  | Opex Saving(344) | 2022-10-20
37 | TN | RMPM51 | RMPM32 | Ok | MDU | Relocation | Ericsson | Chalai Bazar Ramanathapuram | No.10, Ramanathapuram sub, Post & Taluk & District: Ramanathapuram, State: Tamilnadu, Pincode-623501 | Ramanathapuram | RTT | Waiting for AOM approval | 9.3633 | 80.0558 | 9.3633 | 78.8328 | 155-0936-36788338 | 2G+L1800+L2300 | GTL | Indus | TAM/RTT/K/29438 | IN-3131824 | Indus_Lite+ | Done | 2022-09-28 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-29 | 2022-09-30 |  | l23+l18 | 1l8 | l23 | 4 | done | 6 |  |  | Jan'23 | Jan'23 | 21425594 | 2022-10-14 | 2022-10-15 | 2022-10-15 |  | MS1 DONE | 2022-11-19 | Shajofonica | 2022-11-20 | BOSS MANAGEMENT |  |  |  | 2022-11-18 |  | Relocated |  | 2023-01-07 | TN/05/5177/00487/0043/04/01/17450/NS/07012023 | 2023-01-27 | E.SENTHIL | [5 empty] | Yes | 2023-01-07 | [7 empty] | 2023-01-12 | 2023-01-15 |  | 2023-01-11 | 2023-01-15 |  | 2023-01-08 | 2023-01-13 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | LL Issue | 2023-01-07
38 | TN | TIR513 | TIR60 | ok | CBE | Relocation |  | Thirumalai nagar | D.Rajamani, W/o, Devaraj, No.25, Pillaiyar kovil street, Post: Tirumalai Nagar, Taluk & District: Tirupur, State: Tamilnadu, Pincode-641602. 94434-75005. | Tiruppur | RTT | Resurvey | 11.1261 | 80.0558 | 11.1261 | 77.3444 | 155-1112-72773444 | 2G+L1800+L2100+L2300+FTB-A+TTB-A,B,C | Indus | Indus | IN-1062173 | IN-1074957 | STANDARD_PRODUCT | Done | 2022-09-30 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-30 | 2022-01-10 |  | l23+l18+l21 | l23+l18+l21 | na | 3 | NA | 12 |  |  | Feb'23 |  | 21922136 | 2022-11-07 | 2022-11-08 | 2022-11-08 |  | FTTH MEDIA NOT READY | [9 empty] | Pending | [10 empty] | Yes |  | 133 | [21 empty] | Installation Pending |  |  |  | LL Issue | #N/A
39 | CHN | VAND31 | VANDA3 | Ok | CHN | Relocation | Ericsson | Vandalore31 | Sf.No.149/1, 23, 175, Kambar st, Grand Southern Trunk Rd, Post: Urapakkam, Taluk & District: Chennai, State: Tamil Nadu, Pincode-603210 | Chennai | RTT | MS1 DONE | 12.8706 | 80.0758 | 12.8706 | 80.0758 | 152-1287-12800762 | GL1800+L2100+L2300+L900 | Indus | Indus | IN-1043640 | IN-3138703 | STANDARD_PRODUCT | Done | 2022-09-29 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-09-30 | 2022-10-03 |  | GL1800+L900+L2100 |  | GL1800+L900+L2100 | 4+4+3 | NA | RRU2219 B0A*4 + RRU2279*3+RRU2219 B3*1 |  |  | Nov | Oct |  | 2022-10-21 | 2022-10-21 | 2022-10-21 |  | MS1 DONE | 2022-10-21 | Shajofonica | 2022-10-21 | SHAJOFONICA |  |  |  | 2022-10-21 |  | Relocated |  | 2022-10-27 |  | 2022-10-27 | R.MANIKANDAN | [5 empty] | Yes | 2022-10-27 |  |  | 2022-12-17 |  |  | 2022-12-17 | Rahul |  |  |  | 2023-01-20 | 2022-10-31 |  | 2022-10-26 | 2022-10-31 |  | 2022-10-27 | 2022-10-31 |  |  |  |  | Phy & KPI AT Pending | Under_ATP | Phy & KPI AT Pending |  | LL Issue | 2022-10-27
40 | CHN | TARA33 | TARA16 | Ok | CHN | Relocation | Huawei + Ericsson |  |  | Chennai | RTT | MS1 DONE | 12.974444, | 80.2358 | 12.974444, | 80.2358 | 152-1297-54802363 | GL1800+L2100+L2300+L900+TTB-A,B,C+FTB-B,C | ATC | TVI | TN/CH/VO/10710 | - | ECO | Done | 2022-10-04 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-05 | 2022-08-09 |  | L23+L18+L21+L900 | L23 | L18+L21+L900 | 4 | NA | 17 |  |  | Oct | Oct | [5 empty] | MS1 DONE | 2022-10-12 | Shajofonica | 2022-10-12 | BOSS MANAGEMENT |  |  |  | 2022-10-12 |  | Relocated |  | 2022-10-13 |  | 2022-10-12 | R.MANIKANDAN | [5 empty] | Yes | 2022-10-12 | [7 empty] | 2022-11-10 | 2022-11-14 |  | 2022-11-20 | 2022-11-14 |  | 2022-10-26 | 2022-10-31 |  | 2022-10-27 | 2022-10-31 |  |  | 2022-10-31 |  | Phy & KPI AT Pending | Under_ATP | Phy & KPI AT Pending |  | Opex Saving(344) | 2022-10-17
41 | TN | NGPM24 | NGPM5 | Ok | TRY | Relocation | Huawei | MELAKOTTAVASAL 24 | No.23/4, Post: Melakottaivasal, Nagore, Taluk & District: Nagapattinam, State: Tamil Nadu, Pincode-611001 | Nagapattinam | GBT | Power cable approval pending | 10.7616 | 80.0558 | 10.7616 | ,79.83819 | 155-1076-05798379 | 2G+L1800+L2100+L2300+L900 | Indus | Indus | IN-1062514 | IN-3138662 | ECO | Done | 2022-10-04 | Unsafe |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-03 | 2022-10-04 |  |  | L2300+L2100+L1800 |  | 3 | done | 9 |  |  | Dec | Dec | 21870552 | 2022-11-04 | 2022-11-05 | 2022-11-06 |  | MS1 DONE | 2022-12-17 | RS Teletude | 2022-12-17 | RS Teletude |  |  |  | 2022-12-17 |  | Relocated |  | 2022-12-22 | TN/17/5177/01878/0043/04/01/17326/NS/23122022 | 2023-01-06 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-22 | [10 empty] | 2023-01-09 | [11 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Unsafe | 2022-12-24
42 | CHN | ANNA25 | ANNA11 | FD | CHN | Relocation | Huawei + Ericsson | shanti colony | A-K-1, 10TH MAIN ROAD, POST: SHANTHI COLONY, ANNA NAGAR WEST, TALUK & DISTRICT: CHENNAI, STATE: TAMILNADU, PINCODE-600040(ph . Arish k Chatrani) | Chennai | RTT | MS1 DONE | 13.0831 | 80.0558 | 13.0824 | 80.2078 | 152-1308-24802078 | 2G+L1800+L2100+L2300+L900 | INDUS | ATC | IN-1006644 | TN/CH/TT/12610 | STANDARD_PRODUCT | Done | 2022-10-10 | Unsafe |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-10 | 2022-10-11 |  | GL1800+L2100 |  | GL1800+L2100 | 4+4 | NA | RRU2279*4 |  |  | Nov | Nov | 80415 | 2022-11-04 | 2022-11-05 | 2022-11-06 |  | MS1 DONE | 2022-11-09 | Shajofonica | 2022-11-09 | SHAJOFONICA |  |  |  | 2022-11-09 |  | Relocated |  | 2022-11-14 |  | 2022-11-10 | R.MANIKANDAN | [5 empty] | Yes | 2022-11-15 |  |  | 2022-12-17 |  |  | 2022-12-17 | Rahul |  |  |  | 2023-01-20 |  |  | 2022-12-11 | 2022-12-16 |  | 2022-12-12 | 2022-12-16 |  |  | 2023-01-06 | 2023-01-06 | Only Phy Pending | Under_ATP | Only Phy Pending |  | Unsafe | 2022-11-15
43 | TN | KLVNG2 | KLVN1 | Ok | VLR | Relocation | Huawei + Ericsson | Kalvadangam 2 | Mr. Mahibalan M, S/o. Muthusamy Poosari, D.No. 5/68 A, R.S.No. 327/1 & 4, Patta No. 1675, Post: Koneripatti Agraharam Village, Taluk: Sankari, Edaipatti SRO, District: Namakkal, State: Tamilnadu, Pincode-637104. | Salem | GBT | MS1 DONE | 11.5597 | 80.0558 | 11.5597 | ,77.742222 | 155-MTNU-1630877 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/28556 | TN/ER/AT/23428 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-13 | 2022-10-17 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Dec | Nov | 22177607 | 2022-11-24 | 2022-11-24 | 2022-11-24 |  | MS1 DONE | 2022-11-27 | RS Teletude | 2022-11-29 | RS Teletude |  |  |  | 2022-11-29 |  | Relocated |  | 2022-11-29 | TN/10/5126/00278/0043/04/01/17197/NS/30112022 | 2022-12-09 | E.SENTHIL | [5 empty] | Yes | 2022-11-29 |  |  | 2022-12-17 |  |  | 2022-12-17 | Rahul | 2022-12-19 | 2022-12-23 |  | 2022-12-19 | 2022-12-23 |  | 2022-12-14 | 2022-12-19 |  | 2022-12-12 | 2022-12-16 |  |  |  |  | Only KPI Pending |  | Only KPI Pending |  | CNIL Free Exit Feasble Relocation | 2022-11-30
44 | TN | TUPGN2 | TUPGN1 | Ok | VLR | Relocation | Ericsson | Thupuganapalli 2 | Mr.B.Muniappa, S/o.Bellappa, S.F.No.413/23, Patta No.488, Post: Thiyanadhurgam Village, Taluk: Sulagiri, District: Krishnagiri, State: Tamilnadu, Pincode-635119 | Krishnagiri | GBT | Survey wip, | 12.6344 | 80.0558 | 12.6344 | 77.9178 | 155-MTNU-1684215 | 2G+L1800+L2300+L900 | GTL | ATC | TAM/GBT/K/28934 | TN/DH/AT/23441 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-12 | 2022-12-15 | KARTHIK/INHOUSE | 2G+L1800+L2300+L900 | GL1800 | L2300+L900 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22517264 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-22 | Boss Management | 2023-01-22 | BOSS MANAGEMENT |  |  |  | 2023-01-22 |  |  |  | 2023-01-22 | TN/10/5126/00281/0043/04/01/17547/NS/22012023 |  |  | 121 | Morethan 7 Days | 19 | Morethan 7 Days |  | Yes | 2023-01-22 | 75 | [12 empty] | 2023-01-30 |  |  | 2023-01-23 | [5 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Need to check for offering | 2023-01-23
45 | TN | VLKTI2 | VLKT1 | Ok | VLR | Relocation |  | Vallakuttapatati 2 | Mr.S.Ramasamy, So/.Seerangan, S.F.No.143/11, Patta No.781, Post: Vallakuttapatai, Taluk: Edapadi, District: Salem, State: Tamilnadu, Pincode-639210 | Salem | GBT | Survey wip, | 11.6 | 80.0558 | 11.6006 | 77.8729 | 155-MTNU-1648617 | 2G+L1800+L2300+L900 | GTL | ATC | TAM/GBT/K/30923 | TN/SA/AT/23481 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-12 | 2023-01-28 | SHYON | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 4 | done | 12 |  |  | Feb'23 | [6 empty] | Antenna & Power,Cpri Cables req | [9 empty] | Pending | [10 empty] | Yes |  | 75 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
46 | TN | JDPLM2 | JDPL1 | LINK | VLR | Relocation | Ericsson | Jedarpalayam 2 | Mr. Subramanian K, S/o. Kaliyannan,S.No. 14/1D3, Post: Thondipatti Village, Taluk: Thiruchengode, Velagoundampatti SRO, District: Namakkal, State: Tamilnadu, Pincode-637410 | Namakkal | GBT | Survey wip, | 11.3661 | 78.0836 | 11.3661 | 78.0836 | 155-MTNU-1635969 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/28442 | TN/NM/AT/23426 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-13 | 2022-10-17 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 4 | done | 16 |  |  | Jan'23 | Jan'23 | 22706616 | 2023-01-21 | 2023-01-21 | 2023-01-23 |  | MS1 DONE | 2023-01-22 | BOSS MANAGEMENT | 2023-01-22 | BOSS MANAGEMENT |  |  |  | 2023-01-22 |  |  |  | 2023-01-22 | TN/10/5126/00305/0043/04/01/17545/NS/22012023 | 2023-02-02 | SATHISH | [5 empty] | Yes | 2023-01-22 | 74 |  | 2023-02-03 |  |  | 2023-02-03 | [7 empty] | 2023-01-30 |  |  | 2023-01-23 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-23
47 | TN | UTHIG2 | UTHIG1 | ok | VLR | Relocation | Ericsson | Uthiragadikaval 2 | Mr. Ramasami, S/o. Palaniyandi, S.No. 61/3A, Post: Uthirakidi Kaval Village, Taluk: Senthamangalam, District: Namakkal, State: Tamilnadu, Pincode-637404 | Namakkal | GBT | Survey wip, | 11.3508 | 78.2569 | 11.3508 | ,78.256944 | 155-MTNU-1684309 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/31009 | TN/NM/AT/23483 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-13 | 2022-12-14 | KARTHIK/INHOUSE | 2G+L1800+L2300+L900 | GL1800 | L2300+L900 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22516518 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-22 | Boss Management | 2023-01-22 | BOSS MANAGEMENT |  |  |  | 2023-01-22 |  |  |  | 2023-01-22 | TN/10/5126/00306/0043/04/01/17548/NS/22012023 | 2023-01-31 | SATHISH | [5 empty] | Yes | 2023-01-22 | 74 | [15 empty] | 2023-01-23 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-23
48 | TN | PLPTI2 | PLPTI1 | ok | VLR | Relocation |  | Pulliyampatti 2 | Mr.D.Rangasamy, S/o.Duraisamy, S.F.No.284/1, Post: Panagattur, Puliyampatti, Taluk: Edapadi, District: Salem, State: Tamilnadu, Pincode-637101 | Salem | GBT | Survey wip, | 11.6642 | 77.8033 | 11.6642 | 77.8033 | 155-MTMN-1704357 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/11531 | TN/SA/AT/23401 | ECO | Done | 2022-10-15 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-14 | 2023-01-28 | SHYEON | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 4 | done | 15 |  |  | Feb'23 | [6 empty] | Antenna & Power,Cpri Cables req | [9 empty] | Pending | [10 empty] | Yes |  | 73 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
49 | TN | ATRPL2 | ATRPL1 | ok | MDU | Relocation | Huawei + Ericsson | Athurallipallam 2 | S.No. 523/B4B, Post: Narayanapuram Village, Vasudevanallur SRO, Taluk & District: Tenkasi, State: Tamilnadu, Pincode-627760 | Tirunelveli | GBT | MS1 DONE | 9.2666 | ,77.40845 | 9.2666 | ,77.40845 | 155-MTNU-1635948 | 2G+L1800+L2100+L900 | CNIL / GTL | ATC | TAM/GBT/K/27964 | TN/TR/AT/23411 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-15 | 2022-10-16 |  | L900+L2100 |  | L900+L2100 | 3+3 | NA | RRU2219 B1*3+RRU2219 B0*3 |  |  | Nov | Nov | 22109577 | 2022-11-18 | 2022-11-19 | 2022-11-19 |  | MS1 DONE | 2022-11-18 | Shajofonica | 2022-11-18 | SHAJOFONICA |  |  |  | 2022-11-18 |  | Relocated |  | 2022-11-22 | TN/12/5126/00136/0043/04/01/17108/NS/22112022 | 2022-11-28 | E.SENTHIL | [5 empty] | Yes | 2022-11-23 | [10 empty] | 2023-01-20 | 2022-11-27 |  | 2022-11-22 | 2022-11-27 |  | 2022-11-23 | 2022-11-27 |  |  | 2022-12-15 | 2022-12-15 | Only Phy Pending |  | Only Phy Pending |  | CNIL Free Exit Feasble Relocation | 2022-11-23
50 | TN | KNYUR3 | KNYR1 | Link | VLR | Relocation |  | Koonandiyur 3 | Mr. Jayaraman R, S/o. Raja, S.No. 92/1, Post: Amani Koonandiyur Village, Taluk: Mettur, Mecheri SRO, District: Salem, State: Tamilnadu, Pincode-636458. | Salem | GBT | Survey wip, | 11.8975 | 77.8822 | 11.8975 | 77.8822 | 155-MTNU-1636929 | 2G+L1800+L2100 | CNIL / GTL | ATC | TAM/GBT/K/28759 | TN/SA/AT/23435 | ECO | Done | 2022-10-15 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-15 | 2022-10-27 |  | 2G+L1800+L2100 | L1800 | L2100 | 3 | done | 6 |  |  | Jan'23 | Jan'23 | 22698532 | 2023-01-21 | 2023-01-21 | 2023-01-23 |  | MS1 DONE | 2023-01-24 | Shyon Enterprises | 2023-01-24 | Shyon Enterprises |  |  |  | 2023-01-24 |  | Relocated |  | 2023-01-24 |  |  |  | 118 | Morethan 7 Days | 16 | Morethan 7 Days |  | Yes | 2023-01-25 | 72 | [15 empty] | 2023-01-28 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-25
51 | TN | CHPRM2 | CHPRM1 | FD | MDU | Relocation | Ericsson | Cholarpuram | S.F.No.319/3B, Post: Ethilappanaickenpatti Village, Kovilpatti Panchayat Union, Taluk: Cholarpuram, District: Thoothukudi, State: Tamil Nadu, Pincode-628908 | Thoothukkudi | GBT | Power cable approval pending | 9.0458 | 78.0339 | 9.0529 | 78.0305 | 155-MTNU-401424 | 2G+L1800+L2100+L2300+L900 | Indus | Indus | IN-1059917 | IN-3144173 | ECO | Done | 2022-10-17 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-17 | 2022-12-03 |  | 2G+L1800+L2100+L2300+L900 | L2300 | 2G+L1800+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 6207727 | 2022-12-08 | 2022-12-08 | 2022-12-08 |  | MS1 DONE | 2022-12-29 | Shajofonica | 2022-12-29 | Shajofonica |  |  |  | 2022-12-29 |  | Relocated |  | 2023-01-06 | TN/14/5177/01911/0043/04/01/17440/NS/06012023 | 2023-01-17 | E.SENTHIL | [5 empty] | Yes | 2023-01-07 | 70 |  | 2023-02-03 |  |  | 2023-02-03 |  |  |  |  | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | LL Issue | 2023-01-07
52 | CHN | BHAR19 | BHARA2 | FD | CHN | Relocation |  | Bharat Engg College2 | Sf.No.283/1c, Jagajeevan ram nagar, Post: Selaiyur, Taluk: Tambaram, District: Chennai, State: Tamilandu, Pincode-600073 | Chennai | GBT | Power cable approval pending | 12.9153 | 80.1444 | 12.9153 | 80.1444 | 152-1291-59801448 | 2G+L1800+L2100+L2300+L900+TTB-C(Don’t put L2100&L900 in 200) | INDUS | Indus | IN-1007098 | IN-3138679 | NON ECO | Done | 2022-10-17 | High Opex Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-17 | 2022-10-18 | SANJAY /ONCALL | 2G+L1800+L2100+L2300+L900+TTB-C(Don’t put L2100&L900 in 200) | - | L900+UBR+L2300 | 4 | done | 12 |  |  | Feb'23 | [6 empty] | Material need to take back to Warehouse | [9 empty] | Pending | [10 empty] | Yes |  | 70 | [21 empty] | Installation Pending |  |  |  | High Opex Relocation | #N/A
53 | TN | TRY410 | TRY195 | OK | TRY | Relocation | Huawei + Ericsson | St.Mary Teacher Training Institute, Ponmalaipatti | S.F.No.42/5J and 42/7, 22, Sembattu Mariamman Kovil Street, Post: Kottappattu Village, Taluk & District: Trichy, State: Tamilnadu, Pincode-621005 | Tiruchirappalli | GBT | MS1 DONE | 10.7739 | 78.7142 | 10.7739 | 78.7142 | 155-1077-46787128 | 2G+L1800+L2100+L2300+L900 | TVI | Indus | DATNTRY0737 | IN-3149244 | ECO | Done | 2022-10-17 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-17 | 2022-10-18 |  | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | Nov | Nov | 21730460 | 2022-10-28 | 2022-10-29 | 2022-10-30 |  | MS1 DONE | 2022-11-05 | Shajofonica | 2022-11-05 | BOSS MANAGEMENT |  |  |  | 2022-11-05 |  | Relocated |  | 2022-11-05 | TN/13/5177/02005/0043/04/01/17044/NS/05112022 | 2022-11-07 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-07 |  |  | 2023-02-03 |  |  | 2023-02-03 |  | 2022-11-29 | 2022-11-26 |  | 2022-11-22 | 2022-11-26 |  | 2022-11-24 | 2022-11-29 |  | 2022-12-12 | 2022-12-16 |  |  | 2022-11-29 |  | Only KPI Pending |  | Only KPI Pending |  | Opex Saving(344) | 2022-11-07
54 | TN | CBE954 | CBE865 | OK | CBE | Relocation | Huawei + Ericsson | Bommnampalayam | Sf.No.493/499, Lakshmi Nagar, Post: Vadavalli, Taluk & District: Coimbatore, State: Tamil Nadu, Pincode-641007 | Coimbatore | GBT | MS1 DONE | 11.0172 | 76.8798 | 11.0172 | 76.8798 | 155-1101-72768799 | 2G+L1800+L2100+L2300+L900 | INDUS | Indus | IN-1789555 | IN-3139958 | ECO | Done | 2022-10-17 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-17 | 2022-10-18 |  | L900+L2100 |  | L900+L2100 | 4+4 | NA | RRU2219 B1*4+RRU2219 B0*4 |  |  | Nov | Nov | 21870594 | 2022-11-04 | 2022-11-05 | 2022-11-06 |  | MS1 DONE | 2022-11-09 | Shajofonica | 2022-11-09 | BOSS MANAGEMENT |  |  |  | 2022-11-09 |  | Relocated |  | 2022-11-10 | TN/01/5177/01696/0043/04/01/17053/NS/10112022 | 2022-11-14 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-12 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul | 2022-11-16 | 2022-11-16 |  | 2023-01-09 | 2022-12-08 |  | 2022-11-11 | 2022-12-13 | kuldeep | 2022-11-17 | 2022-11-21 |  |  | 2022-12-13 |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | LL Issue | 2022-11-12
55 | TN | KAYAM2 | KAYAM1 | Link | CBE | Relocation | Ericsson | Kasba Ayyampalayam 2 | Sf.No.202/5, Post: Ayyampalayam village, Taluk: Palladam, District: Tiruppur, State: Tamilnadu, Pincode-641662 | Tiruppur | GBT | Survey wip, | 10.9847 | 77.2222 | 10.9847 | 77.2222 | 155-1098-50772222 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/29481 | IN-3149785 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-16 | 2022-12-08 | RS TELE | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 6346856 | 2023-01-13 | 2023-01-13 | 2023-01-14 |  | MS1 DONE | 2023-01-10 | Boss Management | 2023-01-10 | BOSS MANAGEMENT |  |  |  | 2023-01-10 |  |  |  | 2023-01-13 | TN/01/5177/01734/0043/04/01/17490/NS/13012023 | 2023-02-03 | E.SENTHIL | [5 empty] | Yes | 2023-01-15 | 71 |  | 2023-02-03 |  |  | 2023-02-03 |  |  |  |  | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-18 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-14
56 | TN | SNTKD2 | SNTKD1 | OK | MDU | Relocation | Huawei + Ericsson | Sinthalagundu 2 | S.F.No.58/2, Post: Sinthalagundu village, Taluk & District: Dindigul, State: Tamilnadu, Pincode-624002 | Dindigul | GBT | MS1 DONE | 10.3744 | 77.911 | 10.3744 | 77.911 | 155-1037-44779110 | 2G+L1800+L2100+L2300+L900(Don’t put L2100&L900 in 210) | CNIL / GTL | Indus | TAM/GBT/K/30528 | IN-3149868 | ECO | Done | 2022-10-17 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-17 | 2022-10-18 |  | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 2+2+3 | NA | RRU2219 B1*2+RRU2219 B0*2+RRU8863*1 |  |  | Nov | Nov | 22121669 | 2022-11-19 | 2022-11-19 | 2022-11-19 |  | MS1 DONE | 2022-11-18 | Shajofonica | 2022-11-18 | SHAJOFONICA |  |  |  | 2022-11-19 |  | Relocated |  | 2022-11-22 | TN/06/5177/01104/0043/04/01/17110/NS/22112022 | 2022-12-07 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-23 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul |  |  |  | 2023-01-20 | 2022-12-08 |  | 2023-01-11 | 2023-01-12 |  | 2022-11-18 | 2022-11-22 |  |  | 2023-01-12 |  | Phy & KPI AT Pending |  | Phy & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-11-23
57 | TN | SINVD2 | SINVD1 | Link | CBE | Relocation |  | Sinchuvadi 2 | Mr.P.Rathinam, Sf.No.371/10A, Post: Sinjuvadi Village, Lakshmapuram, Taluk: Pollachi, District: Coimbatore, State: Tamilnadu, Pincode-642107 | Coimbatore | GBT | Survey wip, | 10.5978 | 77.1158 | 10.5978 | 77.1158 | 155-1059-74771170 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Summit | TAM/GBT/K/08707 | I-TN-PLLC-ENB-9108 | SHARING | Done | 2022-10-18 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Feb'23 |  | 22089332 | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | Workable | [20 empty] | Yes |  | 69 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
58 | TN | NMSNM2 | NMSN1 | FD | CBE | Relocation |  | N.M.Sungam 2 | D/No:11/27A1, Valparai Main Road, Samiyar Gounder Thottam, NM Sungam, Post & Taluk: Pollachi, District: Coimbatore, State: Tamilnadu, Pincode-642007. 9750356771 | Coimbatore | GBT | Survey wip, | 10.5542 | 77.0017 | 10.5542 | 77.0017 | 155-1055-07770007 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Summit | TAM/GBT/K/29322 | I-TN-PLLC-ENB-9047 | SHARING | Done | 2022-10-18 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 2 | done | 8 |  |  | Feb'23 |  | 22516111 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | Workable | [20 empty] | Yes |  | 69 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
59 | TN | KANAA2 | KANAA1 | OK | TRY | Relocation | Ericsson | Konai | MR.VIJAYAKUMAR, Post: Konai, Taluk: Gingee, District: Villupuram, State: Tamil Nadu, Pincode-604205 | Viluppuram | GBT | Survey wip, | 12.2131 | 79.4039 | 12.2131 | 79.4039 | 155-1221-34794043 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Ascend | TAM/GBT/K/30223 | YET_TO_GENERATE | ECO | Done | 2022-10-28 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-28 | 2022-11-30 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22568137 | 2023-01-05 | 2023-01-05 | 2023-01-05 |  | MS1 DONE | 2023-01-09 | RS Teletude | 2023-01-09 | RS Teletude |  |  |  | 2023-01-09 |  |  |  | 2023-01-11 | TN/02/5115/00170/0043/04/01/17478/NS/11012023 |  |  | 105 | Morethan 7 Days | 30 | Morethan 7 Days |  | Yes | 2023-01-11 | 59 |  | 2023-02-03 |  |  | 2023-02-03 |  | 2023-01-17 | 2023-01-22 |  | 2023-01-20 | 2023-01-22 |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-11
60 | TN | SLM420 | SLM157 | OK | VLR | Relocation | Huawei + Ericsson | Valakrishnaputhur | No.470, S. No.258/4, 196/3, Sathya nagar, Post: Ammapet, Taluk & District: Salem, State: Tamil Nadu, Pincode-636003 | Salem | GBT | MS1 DONE | 11.6664 | 78.1908 | 11.6664 | 78.1908 | 155-1166-60781911 | 2G+L1800+L2100+L2300+L900(Don’t put L2100&L900 in 320) | TVI | Indus | DATNSLM0857 | IN-3138350 | ECO | Done | 2022-10-18 | Opex Saving(344) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 | 2022-10-19 |  | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | Nov | Nov | 21959677 | 2022-11-09 | 2022-11-10 | 2022-11-11 |  | MS1 DONE | 2022-11-14 | RS Teletude | 2022-11-14 | RS Teletude |  |  |  | 2022-11-14 |  | Relocated |  | 2022-11-17 | TN/10/5177/00869/0043/04/01/17074/NS/16112022 | 2022-11-21 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-17 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul | 2022-11-17 | 2022-11-22 |  | 2022-11-18 | 2022-11-22 |  | 2022-11-14 | 2022-11-19 | kuldeep | 2022-12-12 | 2022-12-16 |  |  | 2022-11-19 |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | Opex Saving(344) | 2022-11-17
61 | TN | RENGM2 | RENGM1 | OK | VLR | Relocation |  | Rengampatti 2 | 1. Mr. Kumar S, S/o. Sennam, 2. Mr. Shankar, S/o. Sennam and 3. Mr. Ravi Sennan, S/o. Sennam, S.No. 323/1D, Post: Rangampatti Village, Taluk: Uthangarai SRO, District: Krishnagiri, State: Tamilnadu, Pincode-635306 | Krishnagiri | GBT | Survey wip, | 12.3819 | 78.4883 | 12.3819 | 78.4883 | 155-1238-22784887 | 2G+L1800+L2100+L900 | CNIL / GTL | ATC | TAM/GBT/K/28828 | TN/DH/AT/23438 | ECO | Done | 2022-10-18 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 | 2022-10-27 |  | 2G+L1800+L2100+L900 | L1800 | L2100+L900 | 3 | done | 9 |  |  | Feb'23 | Jan'23 | 22706662 | 2023-01-21 | 2023-01-21 | 2023-01-23 |  |  | 2023-01-27 | RS Teletude | 2023-01-27 | RS Teletude |  |  |  | 2023-01-28 | [7 empty] | 115 | Morethan 7 Days | 10 | Morethan 7 Days |  | Yes | 2023-01-31 | 69 | [21 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-31
62 | TN | PALYM2 | PALYM1 | OK | VLR | Relocation |  | Palayam 2 | Mrs.C.Lakshmi, W/o.Chinnasami, S.F.No. 59/2, Patta No.2183, Post: Palayampudur Village, Taluk: Nallampalli, District: Dharmapuri, State: Tamilnadu, Pincode-636807 | Dharmapuri | GBT | Survey wip, | 12.0167 | 78.0967 | 12.0167 | 78.0967 | 155-1201-67780968 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30765 | TN/DH/AT/23477 | ECO | Done | 2022-10-18 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 |  |  | 2G+L1800+L2300+L900 | - | L2300+L2100 | 3 | done | 7 | 115 | Morethan 10 Days | Feb'23 | [6 empty] | Re-Survey | [20 empty] | Yes |  | 69 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
63 | TN | INDNR2 | INDNR1 | OK | CBE | Relocation | Huawei + Ericsson | Indra Nagar 2 | Old S.No. 304/1, 305/1, New R.S.No. 330/1, Post: Puthurpudupalayam Village, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638112 | Erode | GBT | MS1 DONE | 11.3117 | 77.665 | 11.3117 | 77.665 | 155-1131-12776652 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30772 | TN/ER/AT/23478 | ECO | Done | 2022-10-18 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 | 2022-11-01 |  | 2G+L1800+L2100+L2300+L900 | 3 2G+FDD | L18+L900+L23 | 3 | done | 9 |  |  | Nov | Nov | 22089304 | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | MS1 DONE | 2022-11-18 | RS Teletude | 2022-11-18 | RS Teletude |  |  |  | 2022-11-18 |  | Relocated |  | 2022-11-21 | TN/04/5126/00180/0043/04/01/17102/NS/21112022 | 2022-11-23 | R.MANIKANDAN | [5 empty] | Yes | 2022-11-21 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul | 2022-11-23 | 2022-11-26 |  | 2022-12-19 | 2022-12-23 |  | 2022-11-21 | 2022-11-26 | kuldeep | 2022-12-12 | 2022-12-16 |  |  | 2023-01-06 | 2023-01-06 | Phy & Soft AT Pending |  | Phy & Soft AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-11-21
64 | TN | MOREP2 | MOREP1 | Link | CBE | Relocation | Ericsson | Morepalayam 2 | Mr.R.Velusamy, S/o.Ramasamy, S.F.No.452/3F, Patta No.1121, Post: Karumapuram Village, Taluk: Thiruchengode, District: Namakkal, State: Tamilnadu, Pincode-637302 | Namakkal | GBT | Survey wip, | 11.4453 | 77.9639 | 11.4453 | 77.9639 | 155-1144-58779646 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30178 | TN/NM/AT/23462 | ECO | Done | 2022-10-19 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22516067 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-06 | Shyon Enterprises | 2023-01-06 | Shyon Enterprises |  |  |  | 2023-01-06 |  | Relocated |  | 2023-01-07 | TN/10/5126/00293/0043/04/01/17448/NS/07012023 | 2023-02-01 | SATHISH | [5 empty] | Yes | 2023-01-07 | 69 | [6 empty] | 2023-01-17 | 2023-01-22 |  | 2023-01-20 | 2023-01-22 |  | 2023-01-19 | 2023-01-20 | [7 empty] | Phy & Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | Field visit required for rectification | 2023-01-07
65 | TN | KRAMR2 | KRAMR1 | OK | VLR | Relocation |  | Keeerampur 2 | Mr.P.Mani, S/o.Periyannan, S.F.No.200/3, Patta No. 534, Post: Puthur Kilmugam Village, Taluk: Thiruchengode, District: Namakkal, State: Tamilnadu, Pincode-637212 | Namakkal | GBT | Survey wip, | 11.2978 | 78.0814 | 11.2978 | 78.0814 | 155-1129-81780815 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/28652 | TN/NM/AT/23430 | ECO | Done | 2022-10-19 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-18 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Feb'23 | Jan'23 | 22698534 | 2023-01-21 | 2023-01-21 | 2023-01-23 |  | MS1 DONE | 2023-01-25 | Shyon Enterprises | 2023-01-25 | Shyon Enterprises |  |  |  | 2023-01-27 |  |  |  | 2023-01-28 |  |  |  | 115 | Morethan 7 Days | 13 | Morethan 7 Days |  | Yes | 2023-01-28 | 69 | [21 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-28
66 | TN | POMPM2 | POMPM1 | OK | TRY | Relocation | Ericsson | Poonampalayam 2 | Mr.A.Ondimuthu, S/o.Alagaperumal, S.F.No.537/1A, Post: Poonampalayam Village, Taluk: Manachanallur, District: Trichy, State: Tamilnadu, Pincode-621009 | Tiruchirappalli | GBT | Survey wip, | 10.9356 | 78.6858 | 10.9356 | 78.6858 | 155-1093-59786854 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/29530 | TN/TR/AT/23452 | ECO | Done | 2022-10-20 | CNIL Given Access |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-19 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 21980817 | 2022-11-10 | 2022-11-11 | 2022-11-11 |  | MS1 DONE | 2023-01-10 | Shajofonica | 2023-01-10 | Shajofonica |  |  |  | 2023-01-10 |  |  |  | 2023-01-11 | TN/13/5126/00317/0043/04/01/17476/NS/11012023 | 2023-01-20 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-11 | 68 |  | 2023-02-03 |  |  | 2023-02-03 |  | 2023-01-17 | 2023-01-22 |  | 2023-01-20 | 2023-01-22 |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Given Access | 2023-01-11
67 | TN | AMMAM4 | AMMAM3 | OK | VLR | Relocation | Ericsson | Ammapalayam 4 | Mr. Muthusamy C, S/o. Chinnasamy, S.No. 73/6A & 6C, Post: Ammampalayam Village, Taluk: Aathur, District: Salem, State: Tamilnadu, Pincode-636141 | Salem | GBT | Power cable approval pending | 11.6011 | 78.6394 | 11.6011 | 78.6394 | 155-1160-11786394 | 2G+L1800+L2300+L900(Don’t put L900 in 80) | CNIL / GTL | ATC | TAM/GBT/K/28121 | TN/SA/AT/23415 | ECO | Done | 2022-10-20 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-19 | 2022-11-26 | RS TELE | 2G+L1800+L2300+L900 | 0 | 0 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22516544 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-05 | Shyon Enterprises | 2023-01-05 | Shyon Enterprises |  |  |  | 2023-01-05 |  | Relocated |  | 2023-01-08 | TN/10/5126/00294/0043/04/01/17458/NS/08012023 | 2023-01-19 | SATHISH | [5 empty] | Yes | 2023-01-08 | 68 |  | 2023-02-03 |  |  | 2023-02-03 |  | 2023-01-23 | 2023-01-25 |  | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-08
68 | TN | VPDAI3 | VPDAI1 | Link | VLR | Relocation |  | Veppadai 3 | V.N.Kalliann, No.1D/5, VNK lllam behind, Sangamitra Gas Ageciey, Byepass Rd, Post & Taluk: Palliapalayam, District: Erode, State: Tamilnadu, Pincode-638008.9994946127. 04288-241445. | Namakkal | GBT | Survey wip, | 11.4064 | 77.7867 | 11.4064 | 77.7867 | 155-1140-65777868 | 2G+L1800+L2100+L2300+L900+TTB-B,C(Don’t put L2100 in 320) | CNIL / GTL | Indus | TAM/GBT/K/30747 | IN-1030622 | SHARING | Done | 2022-10-20 | CNIL Given Access |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-19 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900+TTB-B,C(Don’t put L2100 in 320) | L1800 | L2300+L2100+L900 | 4 | done | 17 |  |  | Feb'23 |  | 21959730 | 2022-11-09 | 2022-11-10 | 2022-11-10 |  | Antenna & Power,Cpri Cables req | [20 empty] | Yes |  | 68 | [21 empty] | Installation Pending |  |  |  | CNIL Given Access | #N/A
69 | TN | OTNGP2 | OTNGP1 | OK | MDU | Relocation | Huawei + Ericsson | Ottanagampatti 2 | S.F.No.1720/2A, 370/1, Post: Ottangampatti, Taluk: Vedasandur, District: Dindigul, State: Tamilnadu, Pincode-624710 | Dindigul | GBT | MS1 DONE | 10.5294 | 77.9044 | 10.5294 | 77.9044 | 155-1052-96779036 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30954 | IN-3149855 | ECO | Done | 2022-10-20 | alarm clearence wip |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-20 | 2022-10-21 |  | L900+L2300 |  | L900+L2300 | 3+3 | NA | RRU4418*3+RRU2219 B0*3 |  |  | Nov | Nov | 22089265 | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | MS1 DONE | 2022-11-17 | RS Teletude | 2022-11-17 | SHAJOFONICA |  |  |  | 2022-11-17 |  | Relocated |  | 2022-11-21 | TN/06/5177/01103/0043/04/01/17106/NS/21112022 | 2022-11-25 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-21 | [10 empty] | 2023-01-09 | 2023-01-09 |  | 2022-12-20 | 2022-12-25 |  | 2022-12-23 | 2022-12-25 |  |  | 2022-12-25 |  | Phy & KPI AT Pending |  | Phy & KPI AT Pending |  | alarm clearence wip | 2022-11-21
70 | TN | PTMPT2 | PTMP1 | OK | VLR | Relocation |  | Pethampatti 2 | Mr. Samynathan P, S/o. Perumal, R.S.No. 30/1, Sub-Division R.S.No. 30/1C, Post: Pethampatti Village, Taluk: Veerapandi, District: Salem, State: Tamilnadu, Pincode-637501. | Salem | GBT | Survey wip, | 11.5544 | 78.0586 | 11.5544 | 78.0586 | 155-1155-45780586 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/29779 | TN/SA/AT/23457 | ECO | Done | 2022-10-20 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-20 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 4 | done | 16 |  |  | Feb'23 | Jan'23 | 22089351 | 2022-11-17 | 2022-11-17 | 2022-11-17 |  | MS1 DONE | 2023-01-24 | Shyon Enterprises | 2023-01-24 | Shyon Enterprises |  |  |  | 2023-01-28 |  |  |  | 2023-01-28 |  |  |  | 113 | Morethan 7 Days | 13 | Morethan 7 Days |  | Yes | 2023-01-28 | 67 | [21 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-28
71 | TN | KLINR2 | KLINR1 | Link | CBE | Relocation | Ericsson | Kalliyanur 2 | Mrs. Saroja P, W/o. Palanisamy, S.No. 69/9B, 9C, 1A2 and 1C1, Post: Kaliliyanur Village, Taluk: Kumarapalayam, District: Namakkal, State: Tamilnadu-638008 | Namakkal | GBT | Survey wip, | 11.3931 | 77.745 | 11.3931 | 77.745 | 155-1139-31777446 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30168 | TN/NM/AT/23461 | ECO | Done | 2022-10-20 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-20 | 2022-12-16 | DHILEEP/ONCALL | 2G+L1800+L2100+L2300+L900 | 2G+L1800 | L2100+L2300+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22516569 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-20 | Shyon Enterprises | 2023-01-20 | Shyon Enterprises |  |  |  | 2023-01-22 |  |  |  | 2023-01-22 | TN/10/5126/00302/0043/04/01/17546/NS/22012023 | 2023-01-24 | E.SENTHIL | [5 empty] | Yes | 2023-01-22 | 67 |  | 2023-02-03 |  |  | 2023-02-03 | [10 empty] | 2023-01-23 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-23
72 | TN | PLAGR2 | PLAGR1 | Link | VLR | Relocation | Ericsson | Pillari Agraharam 2 | Mrs. Ponni Krishnan, W/o. Krishnan, S.No. 207/8, Post: Pillari Agraharam Village, Meda Agraharam, Taluk: Thenkanikottai, Rayakottai SRO, District: Krishnagiri, State: Tamilnadu, Pincode-635116 | Krishnagiri | GBT | Survey wip, | 12.5317 | 78.0206 | 12.5317 | 78.0206 | 155-1253-29780240 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30272 | TN/DH/AT/23467 | ECO | Done | 2022-10-20 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-20 | 2022-12-15 | KARTHIK/INHOUSE | 2G+L1800+L2300+L900 | GL1800 | L2300+L900 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22516462 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-20 | Boss Management | 2023-01-20 | BOSS MANAGEMENT |  |  |  | 2023-01-22 |  |  |  | 2023-01-22 | TN/03/5126/00151/0043/04/01/17538/NS/22012023 |  |  | 113 | Morethan 7 Days | 19 | Morethan 7 Days |  | Yes | 2023-01-22 | 67 |  | 2023-02-03 |  |  | 2023-02-03 | [16 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Need to check for offering | 2023-01-23
73 | TN | CMPYM2 | CMPYM1 | Link | CBE | Relocation | Ericsson | Chinnamathampalayam 2 | K.MAGENDRAN, NO.2/117, BETTATHAPURAM PUDUR, THANEERPANDAL, POST: KARAMADAI, TALUK & DISTRICT: COIMBATORE, STATE: TAMILNADU, PINCODE-641104 | Coimbatore | GBT | Survey wip, | 11.2192 | 76.9625 | 11.2192 | 76.9625 | 155-1122-02769634 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28306 | IN-1030592 | SHARING | Done | 2022-10-21 | CNIL Given Access |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-20 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | [5 empty] | MS1 DONE | 2023-01-06 | Boss Management | 2023-01-06 | BOSS MANAGEMENT |  |  |  | 2023-01-06 |  |  |  | 2023-01-08 | TN/01/5177/1297/0043/04/01/17456/NS/08012023 | 2023-01-22 | E.SENTHIL | [5 empty] | Yes | 2023-01-08 | 67 | [9 empty] | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Given Access | 2023-01-08
74 | TN | PLMLM3 | PLMLM2 | OK | CBE | Relocation | Huawei + Ericsson | Pethampalayam 3 | R. Chinnasamy, No: 81, P.S. Kuppusamy Street, Post: Nari Palayam , Opp To Mr.Saravanan House, Petham Palayam, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638116, Ph: 04294-236306, 093631 11642 (Acq- Capital Govindaraj - | Erode | GBT | Survey wip, | 11.3492 | 77.5692 | 11.3492 | 77.5692 | 155-MPAY-400549 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28557 | IN-1059566 | SHARING | Done | 2022-10-21 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-20 | 2022-10-27 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Dec | 22472555 | 2022-12-23 | 2022-12-23 | 2022-12-23 |  | MS1 DONE | 2022-12-30 | BOSS MANAGEMENT | 2022-12-30 | BOSS MANAGEMENT |  |  |  | 2022-12-30 |  | Relocated |  | 2023-01-01 | TN/04/5177/0044/0043/04/01/17397/NS/31122022 | 2023-01-12 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-01 | 67 | [9 empty] | 2023-01-09 |  |  | 2023-01-01 | 2023-01-06 |  | 2023-01-05 | 2023-01-06 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-01
75 | TN | VAGIK2 | VAGIK1 | OK | MDU | Relocation | Huawei + Ericsson | Vagaikulam 2 | 1. Mr. Kanagaraj Velu, S/o. Velu, 2. Mr. Pauldurai, S/o. Velu and 3. Mr. Veerakumar, S/o. Velu, S.No. 150/1B, 5 and 9, Patta No. 1001, Post: South Kuruvikulam Village, Taluk: Thiruvengadam, District: Tenkasi, State: Tamilnadu, Pincode-627754 | Tirunelveli | GBT | MS1 DONE | 9.1622 | 77.6511 | 9.1622 | 77.6511 | 155-0916-22776511 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30911 | TN/TR/AT/23480 | ECO | Done | 2022-10-21 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-21 | 2022-10-29 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Dec | Dec | 22181382 | 2022-11-24 | 2022-11-24 | 2022-11-24 |  | MS1 DONE | 2022-11-28 | KING CORP | 2022-11-28 | KING CORP |  |  |  | 2022-11-28 |  | Relocated |  | 2022-12-01 | TN/12/5126/00140/0043/04/01/17206/NS/01122022 | 2022-12-01 | E.SENTHIL | [5 empty] | Yes | 2022-12-01 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul | 2022-12-05 | 2022-12-09 |  | 2023-01-09 | 2022-12-09 |  | 2022-12-20 | 2022-12-25 |  | 2022-12-23 | 2022-12-25 |  |  | 2022-12-25 |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-01
76 | TN | KAPLM2 | KAPLM1 | OK | CBE | Relocation | Huawei + Ericsson | Kallipalayam 2 | Sf.No.4/1 and 2 , Post: Polarapalayam village, Taluk: Nambiyur, District: Erode, State: Tamilnadu, Pincode-638458 | Erode | GBT | MS1 DONE | 11.3597 | 77.2908 | 11.3597 | 77.2908 | 155-1135-99772907 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28549 | IN-3149822 | ECO | Done | 2022-10-22 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-22 | 2022-10-29 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 12 |  |  | Dec | Dec | [5 empty] | MS1 DONE | 2022-12-07 | Shajofonica | 2022-12-07 | BOSS MANAGEMENT |  |  |  | 2022-12-07 |  | Relocated |  | 2022-12-09 | TN/04/5177/00486/0043/04/01/17244/NS/09122022 | 2022-12-10 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-10 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2022-12-13 | 2022-12-13 |  | 2023-01-20 |  |  | 2022-12-09 | 2022-12-13 |  | 2022-12-16 | 2022-12-20 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-10
77 | TN | THIYM2 | THIYM1 | OK | TRY | Relocation | Ericsson | Thiniyam 2 | Mr. Chidambaram G, S/o. Govindasamy, New No.310/3, Post: Thiniyam Village, Taluk: Lalgudi, District: Trichy, State: Tamilnadu, Pincode-621706 | Tiruchirappalli | GBT | Survey wip, | 10.8836 | 78.9031 | 10.8836 | 78.9031 | 155-1088-64788994 | 2G+L1800+L2100+L900 | CNIL / GTL | ATC | TAM/GBT/K/10899 | TN/TR/AT/23399 | ECO | Done | 2022-10-22 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-22 | 2022-12-07 | Inhouse | 2G+L1800+L2100+L900 | L1800 | L2300+L2100 | 3 | done | 6 |  |  | Jan'23 | Jan'23 | 22516489 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-04 | RS Teletude | 2023-01-04 | RS Teletude |  |  |  | 2023-01-04 |  | Relocated |  | 2023-01-07 | TN/13/5126/00334/0043/04/01/17444/NS/07012023 | 2023-01-24 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-07 | 65 |  | 2023-02-03 |  |  | 2023-02-03 |  | 2023-01-23 | 2023-01-25 |  | 2023-01-20 |  |  | 2023-01-20 | 2023-01-20 |  | 2023-01-19 | 2023-01-19 |  |  | 2023-01-20 | 2023-01-20 | Phy & Soft & KPI AT Pending |  | Phy & Soft AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-07
78 | TN | POLPM2 | POLPM1 | OK | CBE | Relocation |  | Poolapalayam 2 | Mr. Perumal K, S/o. Karuppana Goundar,R.S.No. 286/2, 3 and 11, Post: Elvamalai Village, Taluk: Bhavani SRO, District: Erode, State: Tamilnadu, Pincode-638316 | Erode | GBT | Survey wip, | 11.43 | 77.6525 | 11.43 | 77.6525 | 155-1143-22776557 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30466 | TN/ER/AT/23472 | ECO | Done | 2022-10-22 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-22 |  |  | 2G+L1800+L2300+L900 | L1800 | L2300+(L900+1) | 3 | done | 10 | 111 | Morethan 10 Days | Feb'23 | [6 empty] | Re-Survey | [20 empty] | Yes |  | 65 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
79 | TN | KTVMP2 | KTVMP1 | OK | TRY | Relocation | Ericsson | Kathavampatti 2 | Mrs. Gandhimathi D, W/o. Duraisamy, S.No. 100/3A1, Post: Kadhavampatti Village, Taluk: Annavasal, District: Pudukkottai, State: Tamilnadu, Pincode-622102 | Pudukottai | GBT | Survey wip, | 10.4847 | 78.5933 | 10.4847 | 78.5933 | 155-1048-49785927 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30787 | TN/PU/AT/23479 | ECO | Done | 2022-10-22 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-22 | 2022-10-29 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 8 |  |  | Jan'23 | Jan'23 | 22683220 | 2023-01-19 | 2023-01-19 | 2023-01-19 |  | MS1 DONE | 2023-01-23 | Shajofonica | 2023-01-23 | Shajofonica |  |  |  | 2023-01-24 |  |  |  | 2023-01-24 |  | 2023-01-28 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-24 | 65 | [12 empty] | 2023-01-30 |  |  | 2023-01-28 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-24
80 | TN | VLYNK2 | VLYN1 | OK | MDU | Relocation | Huawei + Ericsson | Vellayanaikottai 2 | S.No. 401/14 A, S.No. 446/65, Post: Subramanipuram Village, Taluk: Vellanaikottai, Tharugapuram Road, Vasudevanallur SRO, District: Tenkasi, State: Tamilnadu, Pincode-627758 | Tirunelveli | GBT | MS1 DONE | 9.2194 | 77.4122 | 9.2194 | 77.4122 | 155-0921-89774138 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/08302 | TN/TR/AT/23391 | ECO | Done | 2022-10-25 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-25 | 2022-11-01 |  | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3 | done | 12 |  |  | Dec | Nov | 22208320 | 2022-11-27 | 2022-11-28 | 2022-11-28 |  | MS1 DONE | 2022-11-27 | RS Teletude | 2022-11-28 | RS Teletude |  |  |  | 2022-11-28 |  | Relocated |  | 2022-11-28 | TN/12/5126/00139/0043/04/01/17172/NS/28112022 | 2022-12-14 | E.SENTHIL | [5 empty] | Yes | 2022-11-29 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul |  |  |  | 2023-01-20 |  |  | 2022-12-15 | 2022-12-20 |  | 2022-12-16 | 2022-12-20 |  |  | 2022-12-20 |  | Phy & KPI AT Pending |  | Phy & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-11-29
81 | TN | VAYLR2 | VAYL1 | OK | TRY | Relocation | Huawei + Ericsson | Vayalur 2 | S.No. 61/1, UDR New S.No. 61/1A, Post: Adavathur, Taluk: Srirangam, District: Tiruchirappalli, State: Tamilnadu, Pincode-620102 | Tiruchirappalli | GBT | Survey wip, | 10.8169 | 78.6197 | 10.8169 | 78.6197 | 155-1081-70786199 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/27612 | TN/TR/AT/23405 | ECO | Done | 2022-10-25 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-23 | 2022-10-29 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100 | 3 | done | 10 |  |  | Dec | Dec | 6207993 | 2022-12-08 | 2022-12-08 | 2022-12-08 |  | MS1 DONE | 2022-12-18 | Boss management | 2022-12-18 | BOSS MANAGEMENT |  |  |  | 2022-12-18 |  |  |  | 2022-12-21 | TN/13/5126/00329/0043/04/01/17308/NS/21122022 | 2022-12-21 | E.SENTHIL | [5 empty] | Yes | 2022-12-21 | [10 empty] | 2023-01-09 |  |  | 2022-12-20 | 2022-12-25 |  | 2022-12-23 | 2022-12-25 |  |  | 2022-12-22 | 2022-12-22 | Phy & Soft AT Pending |  | Phy & Soft AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-21
82 | TN | GOVTC3 | GOVTC1 | OK | MDU | Relocation | Huawei + Ericsson | GOVT. COLLEGE TNV 3 | S.F.No.780/2, Post: Kulavanigarpuram Village, Melapapalayam, Taluk: Palayamkottai, District: Tirunelveli, State: Tamil Nadu, Pincode-627007 | Tirunelveli | GBT | MS1 DONE | 8.6822 | 77.7297 | 8.6822 | 77.7297 | 155-0868-39777303 | 2G+L1800+L2100+L2300+L900+TTB-C | Indus | Indus | IN-1265018 | IN-3139160 | ECO | Done | 2022-10-26 | LL Issue |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-26 | 2022-10-27 |  | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | Nov | Nov | 22060970 | 2022-11-15 | 2022-11-15 | 2022-11-15 |  | MS1 DONE | 2022-11-16 | Boss management | 2022-11-16 | BOSS MANAGEMENT |  |  |  | 2022-11-16 |  | Relocated |  | 2022-11-22 | TN/12/5177/00540/0043/04/01/17109/NS/22112022 | 2022-11-23 | E.SENTHIL | [5 empty] | Yes | 2022-11-23 |  |  | 2022-12-15 |  |  | 2022-12-15 | Rahul | 2022-11-23 | 2022-11-26 |  | 2022-11-22 | 2022-11-26 |  | 2022-11-21 | 2022-11-26 | kuldeep | 2022-12-12 | 2022-12-16 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | LL Issue | 2022-11-23
83 | CHN | BELLS6 | BELLS3 | FD | CHN | Relocation |  | Bells Road6 | Survey No.1164, Re Survey No.2872/2, Krishnappa mudali st, Police Quarters, Post: Triplicane, Taluk & District: Chennai, State: Tamil Nadu, Pincode-600014 | Chennai | RTT | Today Inc Planned | 13.0617 | 80.2767 | 13.0617 | 80.2767 | 152-1306-19802770 | 2G+L1800+L2100+L2300+L900+TTB-A | Indus | Indus | IN-1072210 | IN-3147352 | ECO | Done | 2022-10-26 | Un Safe |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-26 | [8 empty] | 107 | Morethan 10 Days | Feb'23 | [6 empty] | Installation completed, FTTH media | [20 empty] | Yes |  | 61 | [21 empty] | Installation Pending |  |  |  | Un Safe | #N/A
84 | TN | MNSRT2 | MNSRT1 | OK | TRY | Relocation |  | Meensuruti 2 | Veeraswamy, Survey No:335/11, Colony Road, Kundaveli west, Post: Meensuruti, Taluk & District: Perambalur, State: Tamilnadu, Pincode-612903 | Ariyalur | GBT | Survey wip, | 11.2367 | 79.475 | 11.2367 | 79.475 | 155-1123-70794750 | 2G+L1800+L2100+L2300+L900(Don’t put L2100&L900 In 290) | CNIL / GTL | Indus | TAM/GBT/K/28011 | IN-1030546 | SHARING | Done | 2022-10-26 | CNIL Given Access |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-25 | 2022-10-29 |  | 2G+L1800+L2100+L2300+L900(Don’t put L2100&L900 In 290) | - | (L2300+1)+L900 | 3 | done | 7 |  |  | Feb'23 |  | 21956945 | 2022-11-09 | 2022-11-10 | 2022-11-10 |  | FD rerouting pending | [20 empty] | Yes |  | 62 | [21 empty] | Installation Pending |  |  |  | CNIL Given Access | #N/A
85 | TN | KKMBI2 | KKMBI1 | OK | TRY | Relocation |  | Karuvikarambai 2 | K. VAIRAVAN, Post: Kuruvikkarambai, Taluk: Peravoorani, District: Thanjavur, State: Tamil Nadu, Pincode-614802. PH- 94439-79529 | Thanjavur | GBT | Survey wip, | 10.2775 | 79.2439 | 10.2775 | 79.2439 | 155-1027-93792447 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28661 | IN-1074780 | SHARING | Done | 2022-10-26 | CNIL Given Access |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-25 | 2022-10-29 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 11 |  |  | Feb'23 |  | 21959677 | 2022-11-09 | 2022-11-10 | 2022-11-10 |  | Antenna & Power,Cpri Cables req | [20 empty] | Yes |  | 62 | [21 empty] | Installation Pending |  |  |  | CNIL Given Access | #N/A
86 | TN | KGVLU2 | KGVLU1 | OK | CBE | Relocation | Huawei + Ericsson | K.G.Valasu 2 | M.LAKSHMAN, No.11-26, Post: Kandappagoundenvalasu, Taluk: Perundurai, District: Erode, State: Tamil Nadu, Pincode-638101 PH NO-9965835260,04294-256208 | Erode | GBT | MS1 DONE | 11.1319 | 77.6486 | 11.1319 | 77.6486 | 155-MTNU-403362 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30865 | IN-1074416 | SHARING | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-26 | 2022-10-29 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Dec | Dec |  | 2022-11-28 | 2022-11-29 | 2022-11-29 |  | MS1 DONE | 2022-11-29 | RS Teletude | 2022-11-29 | RS Teletude |  |  |  | 2022-11-29 |  | Relocated |  | 2022-12-01 | TN/04/5177/0229/0043/04/01/17207/NS/01122022 | 2022-12-09 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-01 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2022-12-27 | 2022-12-30 |  | 2022-12-19 | 2022-12-30 |  | 2022-12-30 | 2023-01-04 |  | 2022-12-16 | 2022-12-20 |  |  | 2023-01-04 |  | Only KPI Pending |  | Only KPI Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-01
87 | TN | NJPYM2 | NJPM1 | OK | CBE | Relocation | Ericsson | Nanjiyampalayam 2 | Sf.No.85/1a, 616/a, Post: Nanjiyampalayam Village, Taluk: Dharapuram, District: Tiruppur, State: Tamilandu, Pincode-638657 | Tiruppur | GBT | Survey wip, | 10.77 | 77.5192 | 10.77 | 77.5192 | 155-1077-00775193 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/27554 | IN-3149761 | ECO | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-25 | 2022-12-14 | SHIVA/SUMAN-INHOUSE | 2G+L1800+L2300+L900 | L1800+L2300 | L900 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22496571 | 2022-12-26 | 2022-12-26 | 2022-12-29 |  | MS1 DONE | 2022-12-31 | SK Telecom | 2022-12-31 | SK Telecom |  |  |  | 2022-12-31 |  | Relocated |  | 2023-01-03 | TN/01/5177/01723/0043/04/01/17411/NS/03012023 | 2023-01-03 | [6 empty] | Yes | 2023-01-03 | 62 | [6 empty] | 2023-01-16 | 2023-01-19 |  | 2023-01-15 | 2023-01-19 |  | 2023-01-12 | 2023-01-17 |  | 2023-01-06 | 2023-01-06 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-03
88 | TN | KLKIR2 | KLKIR1 | OK | CBE | Relocation |  | Kalakinar 2 | Sf.No.839, Post: Madapur Village, Kallakinar, Taluk: Palladam, District: Tiruppur, State: Tamilnadu, Pincode-641664 | Tiruppur | GBT | Survey wip, | 10.9581 | 77.3164 | 10.9581 | 77.3164 | 155-1095-76773164 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28545 | IN-3149612 | ECO | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-25 | [6 empty] | done |  | 108 | Morethan 10 Days | Feb'23 | [6 empty] | Re-Survey | [20 empty] | Yes |  | 62 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
89 | TN | NMBYP2 | NMBYP1 | OK | CBE | Relocation | Ericsson | Nambiampalayam 2 | Sf.No.384/1B1A, Patta No:1857, Post: Nambiyampalayam Village, Taluk: Avinashi, District: Tiruppur, State: Tamilnadu, Pincode-641654 | Tiruppur | GBT | Survey wip, | 11.1792 | 77.2297 | 11.1792 | 77.2297 | 155-1118-09772300 | 2G+L1800+L2100+L2300+L900+TTB-B,C | CNIL / GTL | Indus | TAM/GBT/K/28836 | IN-3149784 | ECO | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-23 | 2022-12-13 | SHIVA/SUMAN-INHOUSE | 2G+L1800+L2100+L2300+L900 | 2G+L1800 | L2100+L2300+L900+TTB-B, | 3 | done | 13 |  |  | Jan'23 | Jan'23 | 22495761 | 2022-12-26 | 2022-12-26 | 2022-12-29 |  | MS1 DONE | 2023-01-11 | SK Telecom | 2023-01-11 | SK Telecom |  |  |  | 2023-01-11 |  |  |  | 2023-01-14 | TN/01/5177/01710/0043/04/01/17498/NS/14012023 |  |  | 110 | Morethan 7 Days | 26 | Morethan 7 Days |  | Yes | 2023-01-15 | 64 | [9 empty] | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-18 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-15
90 | TN | SENML2 | SENM1 | OK | CBE | Relocation | Huawei + Ericsson | Sencherimalai 2 | Sf.No.122/1a, 1554, Post: Kumarapalayam village, Taluk: Sulur, District: Coimbatore, State: Tamilnadu, Pincode-641671 | Coimbatore | GBT |  | 10.8314 | 77.1975 | 10.8314 | 77.1975 | 155-1083-02771957 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/29103 | IN-3149549 | ECO | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-25 | 2022-10-29 | RS TELE | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Dec | Dec | 6193134 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE | 2022-12-16 | RS Teletude | 2022-12-16 | RS Teletude |  |  |  | 2022-12-16 |  |  |  | 2022-12-20 | TN/01/5177/01713/0043/04/01/17299/NS/20122022 | 2022-12-20 | E.SENTHIL | [5 empty] | Yes | 2022-12-20 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2022-12-27 | 2022-12-30 |  | 2023-01-09 | 2022-12-30 |  | 2022-12-23 | 2022-12-25 | [7 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | Field visit required for rectification | 2022-12-20
91 | TN | ATMRV2 | ATMR1 | OK | MDU | Relocation | Ericsson | Athimarathu Valasu 2 | Sf.No.272a2, No.2/10, Athimarthu valasur, Post: Rajampatti, Taluk & District: Dindigul, State: Tamilandu, Pincode-624617 | Dindigul | GBT | Survey wip, | 10.62 | 77.45 | 10.62 | 77.45 | 155-1062-01774501 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30457 | IN-3149846 | ECO | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-24 | 2022-12-14 | SHIVA/SUMAN-INHOUSE | 2G+L1800+L2300+L900 | L1800+L2300 | L900 | 2 | done | 6 |  |  | Jan'23 | Jan'23 | 22493276 | 2022-12-25 | 2022-12-25 | 2022-12-26 |  | MS1 DONE | 2022-12-31 | RS Teletude | 2022-12-31 | RS Teletude |  |  |  | 2022-12-31 |  | Relocated |  | 2023-01-03 | TN/06/5177/01111/0043/04/01/17409/NS/03012023 | 2023-01-10 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-03 | 63 | [6 empty] | 2023-01-12 | 2023-01-15 |  | 2023-01-11 | 2023-01-15 |  | 2023-01-09 | 2023-01-14 |  | 2023-01-06 | 2023-01-06 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-03
92 | TN | NARPI2 | NARPI1 | OK | CBE | Relocation | Ericsson | Nariyampalli 2 | Sf.No.551, Post: Ramanathapuram Village, Taluk: Avinashi, District: Coimbatore, State-Tamilnadu, Pincode-641670 | Tiruppur | GBT | Survey wip, | 11.2186 | 77.1561 | 11.2186 | 77.1561 | 155-1121-63771660 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30473 | IN-3149852 | ECO | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-25 | 2022-12-13 | SHIVA/SUMAN-INHOUSE | 2G+L1800+L2300+L900 | L1800 | L900+L2300 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22496532 | 2022-12-26 | 2022-12-26 | 2022-12-29 |  | MS1 DONE | 2023-01-02 | Boss management | 2023-01-02 | BOSS MANAGEMENT |  |  |  | 2023-01-02 |  | Relocated |  | 2023-01-03 | TN/01/5177/01709/0043/04/01/17412/NS/03012023 | 2023-01-03 | [6 empty] | Yes | 2023-01-03 | 62 | [6 empty] | 2023-01-16 | 2023-01-19 |  | 2023-01-15 | 2023-01-19 |  | 2023-01-12 | 2023-01-17 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-03
93 | TN | PNJPI2 | PNJPI1 | OK | MDU | Relocation |  | Panjampatti 2 | Sf.NO.98/2B, 3,5, Post: Panjampatti village, Taluk: Sanarpati, District: Dindigul, State: Tamilnadu, Pincode-624304 | Dindigul | GBT | Survey wip, | 10.3008 | 78.0736 | 10.3008 | 78.0736 | 155-1030-10780736 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30702 | IN-3150143 | ECO | Done | 2022-10-26 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-24 | 2022-10-29 | On Call | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 11 |  |  | Feb'23 |  | 22698539 | 2023-01-21 | 2023-01-21 | 2023-01-23 |  | Antenna & Power,Cpri Cables req |  | Parfect Well |  | Parfect Well | [16 empty] | Yes |  | 63 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
94 | TN | PRDI59 | SRLI1 | OK | CBE | Relocation |  | Ponmudi 59 | SF No:25/2, Post: Kambuliampatti Village, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638056 | Erode | GBT | Survey wip, | 11.2494 | 77.5355 | 11.2494 | 77.5355 | 155-1124-94775355 | 2G+L1800+L2100+L2300+L900+TTB-A | Indus | Indus | TAM/GBT/K/30318 | IN-3149847 |  | Done | 2022-10-31 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-29 | 2022-11-06 |  | 2G+L1800+L2100+L2300+L900+TTB-A | L1800 | (L2300+1)+L2100+L900 | 3 | done | 13 |  |  | Jan'23 | Jan'23 | 22697628 | 2023-01-20 | 2023-01-20 | 2023-01-21 |  | MS1 DONE | 2023-01-23 | Shyon Enterprises | 2023-01-23 | Shyon Enterprises |  |  |  | 2023-01-24 |  |  |  | 2023-01-24 |  |  |  | 104 | Morethan 7 Days | 17 | Morethan 7 Days |  | Yes | 2023-01-24 | 58 | [15 empty] | 2023-01-28 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-24
95 | TN | SHBAR2 | SHBAR1 | OK | CBE | Relocation | Huawei + Ericsson | Shenbagapudur 2 | Sf.No.130/2 -d, Post: Shenbagaputur village, Taluk: Satyamangalam, District: Erode, State: Tamilnadu, Pincode-638402 | Erode | GBT |  | 11.4614 | 77.2183 | 11.4614 | 77.2183 | 155-1146-14772183 | 2G+L1800+L2300+L900 | Indus | Indus | TAM/GBT/K/30622 | IN-3149853 |  | Done | 2022-10-31 | WAITING FOR SURVEY |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-30 | 2022-11-06 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 9 |  |  | Dec | Dec | 22318677 | 2022-12-08 | 2022-12-08 | 2022-12-09 |  | MS1 DONE | 2022-12-17 | RS Teletude | 2022-12-17 | RS Teletude |  |  |  | 2022-12-17 |  |  |  | 2022-12-20 | TN/04/5177/00490/0043/04/01/17303/NS/20122022 |  |  | 103 | Morethan 7 Days | 52 | Morethan 7 Days |  | Yes | 2022-12-20 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2022-12-27 | 2022-12-30 |  | 2023-01-09 | 2022-12-30 |  | 2022-12-25 | 2022-12-30 |  | 2022-12-23 | 2022-12-25 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | WAITING FOR SURVEY | 2022-12-20
96 | TN | URLPT2 | URLPT1 | OK | CBE | Relocation | Huawei + Ericsson | Udukkampalayam 2 | No.22/6,25/4, Post: Andigoundanur Village, Taluk: Udumalaipettai, District: Tiruppur, State: Tamilnadu, Pincode-642204 | Tiruppur | GBT | Survey wip, | 10.5352 | 77.2994 | 10.5352 | 77.2994 | 155-1053-52772994 | 2G+L1800+L2100+L2300+L900 | Indus | Indus | TAM/GBT/K/30866 | IN-3149869 |  | Done | 2022-10-31 | WAITING FOR SURVEY |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-10-30 | 2022-12-14 | SHIVA/SUMAN-INHOUSE | GL1800+L2100+L2300+L900 | GL1800 | L2100+L2300+L900 | 3 | done | 10 |  |  | Dec | Dec | 22432898 | 2022-12-20 | 2022-12-20 | 2022-12-20 |  | MS1 DONE | 2022-12-19 | RS Teletude | 2022-12-19 | RS Teletude |  |  |  | 2022-12-19 |  |  |  | 2022-12-21 | TN/01/5177/01715/0043/04/01/17310/NS/21122022 | 2022-12-21 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-21 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2023-01-16 | 2023-01-19 |  | 2023-01-09 | 2023-01-19 |  | 2022-12-20 | 2022-12-25 |  | 2022-12-23 | 2022-12-25 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | WAITING FOR SURVEY | 2022-12-21
97 | TN | VELNP3 | VELNP1 | OK | CBE | Relocation | Ericsson | Vellanaipatti 3 | Sf.No.579/2, Post: Vellanipatti village, Taluk: Annur, District: Coimbatore, State: Tamilnadu, Pincode-641048 | Coimbatore | GBT | Survey wip, | 11.1032 | 77.0833 | 11.1032 | 77.0833 | 155-1110-32770833 | 2G+L1800+L2100+L2300+L900+TTB-A | CNIL / GTL | Indus | TAM/GBT/K/30389 | IN-3150039 |  | Done | 2022-11-02 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-02 | 2022-12-13 | SHIVA/SUMAN-INHOUSE | 2G+L1800+L2100+L2300+L900+TTB-A | L1800 | L900+L2100+L2300-TTB-A | 3 | done | 13 |  |  | Jan'23 | Jan'23 | 22517279 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-02 | SK TELECOM | 2023-01-02 | SK TELECOM |  |  |  | 2023-01-02 |  | Relocated |  | 2023-01-03 | TN/01/5177/01722/0043/04/01/17410/NS/03012023 | 2023-01-12 | SATHISH | [5 empty] | Yes | 2023-01-03 | 54 | [9 empty] | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-03
98 | TN | TPKIT2 | TPKT1 | OK | CBE | Relocation |  | Thappattaikilavanpudur 2 | Sf.No.80/1a2, Post: Thimmanguthu Village, Taluk: Pollachi, District: Coimbatore, State: Tamilnadu, Pincode-642005 | Coimbatore | GBT | Survey wip, | 10.6667 | 76.9008 | 10.6667 | 76.9008 | 155-1066-67769008 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30752 | IN-3149817 |  | Done | 2022-11-02 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-02 | 2022-11-08 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 2 | done | 6 |  |  | Feb'23 |  | 22517232 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | Workable | [20 empty] | Yes |  | 54 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
99 | TN | UMRYU2 | UMRY1 | OK | CBE | Relocation | Huawei + Ericsson | Umarediyur 2 | Sf.No.410/5, Post: Ammapettai village, Taluk: Bhavani, District: Erode, State: Tamilnadu, Pincode-638311 | Erode | GBT |  | 11.6366 | 77.7294 | 11.6366 | 77.7294 | 155-1163-67777294 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30862 | IN-3149794 |  | Done | 2022-11-02 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-02 | 2022-11-08 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 4 | done | 16 |  |  | Dec | Dec | 22323720 | 2022-12-08 | 2022-12-08 | 2022-12-09 |  | MS1 DONE | 2022-12-17 | Boss management | 2022-12-17 | BOSS MANAGEMENT |  |  |  | 2022-12-17 |  |  |  | 2022-12-20 | TN/04/5177/00491/0043/04/01/17300/NS/20122022 | 2022-12-20 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-20 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2023-01-12 | 2023-01-13 |  | 2023-01-09 | 2023-01-15 |  | 2023-01-08 | 2023-01-13 |  | 2023-01-19 | 2023-01-19 |  |  | 2022-12-27 | 2022-12-27 | Only SOFT Pending |  | Only SOFT Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-20
100 | TN | SENGP2 | SENG1 | OK | CBE | Relocation | Ericsson | Sengotipalayam 2 | No.216/A1, Post: Varadhanur Village, Taluk: Kinatthukadavu, District: Coimbatore, State: Tamilnadu, Pincode-642120 | Coimbatore | GBT | Survey wip, | 10.7189 | 77.064 | 10.7189 | 77.064 | 155-1071-89770640 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/10918 | IN-3149464 |  | Done | 2022-11-02 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-02 | 2022-11-08 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22697632 | 2023-01-20 | 2023-01-20 | 2023-01-21 |  | MS1 DONE | 2023-01-23 | Shyon Enterprises | 2023-01-23 | Shyon Enterprises |  |  |  | 2023-01-23 |  | Relocated |  | 2023-01-24 |  |  |  | 100 | Morethan 7 Days | 17 | Morethan 7 Days |  | Yes | 2023-01-24 | 54 | [12 empty] | 2023-01-30 |  |  | 2023-01-28 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-24
101 | TN | KILKT2 | KILKT1 | OK | VLR | Relocation |  | Kilkothur 2 | Sf.No.1539, S. No.64/3A1B, 94/3a1b, Post: Kilkotur village, Taluk: Anaicut, District: Vellore, State: Tamilnadu, Pincode-632103 | Vellore | GBT | Survey wip, | 12.7948 | 78.9487 | 12.7948 | 78.9487 | 155-1279-48789487 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28669 | IN-3149863 |  | Done | 2022-11-02 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-02 | 2022-12-18 | BALU/ONCALL | 2G+L1800+L2100+L2300+L900 | - | L1800+L900+L2100+L2300 | 3 | done | 12 |  |  | Feb'23 | [6 empty] | Material need to take back to Warehouse | [20 empty] | Yes |  | 54 | [21 empty] | Installation Pending |  |  |  | CNIL Free Exit Feasble Relocation | #N/A
102 | TN | AMPKM2 | AMPKM1 | OK | VLR | Relocation | Ericsson | New Anna Nagar 2 | Sf.No.380/18, 380/17, Parithi puthur, New Anna Nagar, Post: Chitheri, Taluk & District: Ranipet, State: Tamilnadu, Pincode-631003 | Vellore | GBT | Survey wip, | 13.0744 | 79.6167 | 13.0744 | 79.6167 | 155-1307-44796167 | 2G+L1800+L2100+L2300+L900 | Indus | Indus | BSTNVLR0781 | IN-3138944 |  | Done | 2022-11-03 | High Opex (Circle) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-03 | 2022-12-28 | R-WAVE TEAM | 2G+L1800+L2100+L2300+L900 | 2G+L1800 | L2100+L2300+L900(ubr) | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22609528 | 2023-01-10 | 2023-01-10 | 2023-01-10 |  | MS1 DONE | 2023-01-13 | RS Teletude | 2023-01-13 | RS Teletude |  |  |  | 2023-01-19 |  |  |  | 2023-01-18 | TN/15/5177/02014/0043/04/01/17513/NS/18012023 |  |  | 99 | Morethan 7 Days | 22 | Morethan 7 Days |  | Yes | 2023-01-19 | 53 | [21 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Field visit required for rectification | 2023-01-19
103 | TN | ANGNR2 | ANGNR1 | OK | CBE | Relocation | Huawei + Ericsson | Ananganoor 2 | Mr. Kumaresan M, S/o. Manogaran, S.No. 45/3A2, Post: Anangur Village, Taluk: Vellore SRO, District: Namakkal, State: Tamilnadu, Pincode-637213 | Namakkal | GBT | Survey wip, | 11.1178 | 77.8937 | 11.1178 | 77.8937 | 155-1111-78778937 | 2G+L1800+L2100+L900(Don’t put L900 in 270) | CNIL / GTL | ATC | TAM/GBT/K/27874 | TN/NM/AT/23409 |  | Done | 2022-11-07 | WAITING FOR SURVEY |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-06 | 2022-12-16 | DHILEEP/ONCALL | 2G+L1800+L2100+L900(Don’t put L900 in 270) | L1800 | L900+L2100 | 4 | done | 11 |  |  | Dec | Dec | [5 empty] | MS1 DONE | 2022-12-23 | Boss management | 2022-12-23 | BOSS MANAGEMENT |  |  |  | 2022-12-23 |  | Relocated |  | 2022-12-25 | TN/10/5126/00289/0043/04/01/17353/NS/25122022 | 2023-01-06 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-25 | [7 empty] | 2023-01-09 | 2023-01-13 |  | 2023-01-09 | 2023-01-13 |  | 2023-01-05 | 2023-01-10 |  | 2023-01-05 | 2023-01-19 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | WAITING FOR SURVEY | 2022-12-25
104 | TN | CHKMO2 | CHKM1 | OK | CBE | Relocation | Huawei + Ericsson | Chokkampalayam 2 | Mr. Muthusamy A, S/o. Arukutti, S.No. 628/A1, Patta No. 144, Post: Kanjappalli, Taluk: Annur, District: Coimbatore, State: Tamilnadu, Pincode-641659 | Coimbatore | GBT | Survey wip, | 11.2088 | 77.1283 | 11.2088 | 77.1283 | 155-1120-88771284 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/28138 | TN/CO/AT/23416 |  | Done | 2022-11-07 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-06 | 2022-11-19 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 8 |  |  | Jan'23 | Dec | 22472611 | 2022-12-23 | 2022-12-23 | 2022-12-23 |  | MS1 DONE | 2022-12-28 | Boss management | 2022-12-28 | BOSS MANAGEMENT |  |  |  | 2022-12-28 |  | Relocated |  | 2022-12-28 | TN/01/5126/00482/0043/04/01/17384/NS/29122022 | 2023-01-20 | E.SENTHIL | [5 empty] | Yes | 2022-12-29 | 50 | [6 empty] | 2023-01-12 | 2023-01-15 |  | 2023-01-09 | 2023-01-15 |  | 2023-01-08 | 2023-01-13 |  | 2023-01-05 | 2023-01-06 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Relocation | 2022-12-28
105 | TN | SAMPI2 | SAMPI1 | OK | TRY | Relocation | Ericsson | Sampatti 2 | Mr. Chinnappan S, S/o. Sanga Goundar, S.No. 223/1A1, Patta No. 91, Post: Sampatti Village, Taluk: Manaparai, District: Tiruchirappalli, State: Tamilnadu, Pincode-621306 | Tiruchirappalli | GBT | Survey wip, | 10.5346 | 78.4263 | 10.5346 | 78.4263 | 155-1053-47784263 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30213 | TN/TR/AT/23463 |  | Done | 2022-11-07 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-06 | 2022-12-11 |  | 2G+L1800+L2300+L900 | L1800 | L900+L2300 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22516175 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-06 | RS Teletude | 2023-01-06 | RS Teletude |  |  |  | 2023-01-06 |  | Relocated |  | 2023-01-07 | TN/13/5126/00328/0043/04/01/17446/NS/07012023 | 2023-01-25 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-07 | 50 | [9 empty] | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-07
106 | TN | MALVD2 | MALVD1 | OK | VLR | Relocation |  | Mallavadi 2 | Sf.No.64/7b2b1, Patta.no.157, Post: Pudhumallavadi, Taluk & District: Tiruvannamalai, State: Tamil Nadu, Pincode-606802 | Tiruvannamalai | GBT | Survey wip, | 12.326 | 79.0738 | 12.326 | 79.0738 | 155-1232-60790738 | 2G+L1800+L2300+L900 | Reliance | Indus | TNRRXXXXX002B | IN-3136044 |  | Done | 2022-11-07 | RELIANCE Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-07 | [8 empty] | 95 | Morethan 10 Days | Feb'23 | [6 empty] | Access issue //Mail given to toco | [20 empty] | Yes |  | 49 | [21 empty] | Installation Pending |  |  |  | RELIANCE Free Exit Feasble Relocation | #N/A
107 | TN | MRDUR2 | MRDR1 | OK | TRY | Relocation | Huawei + Ericsson | Marudhur 2 | Mr. Rajmohan, S/o. Ramaraj, Door No. 1/222, S.No. 131/8, Patta No. 403, Post: Marudhur Village, Taluk: Ilalkudi, Srirangam SRO, District: Trichy, State: Tamilnadu, Pincode-621112 | Tiruchirappalli | GBT | Survey wip, |  |  | 10.9098 | 78.7692 | 155-1090-98787692 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/11087 | TN/TR/AT/23400 |  | Done | 2022-11-09 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-09 | 2022-12-06 | Inhouse | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Dec | Dec | 22457120 | 2022-12-22 | 2022-12-22 | 2022-12-23 |  | MS1 DONE | 2022-12-23 |  | 2022-12-23 | SHAJOFONICA |  |  |  | 2022-12-23 |  | Relocated |  | 2022-12-25 | TN/13/5126/00332/0043/04/01/17354/NS/25122022 | 2023-01-03 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-25 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul |  |  |  | 2023-01-09 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-05 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-25
108 | TN | MAKRI2 | MAKI1 | OK | TRY | Relocation | Huawei + Ericsson | Maniyankurichi 2 | Mr. Rajappa P, S/o. Ponnusamy, S.No. 55/6, Post: Ammasathiram Village, Maniyankurichi Village Panchayat, Thuvarankurichi SRO, Taluk: Marungapuri, District: Tiruchirappalli, State: Tamil Nadu, Pincode-621310 | Tiruchirappalli | GBT | MS1 DONE |  |  | 10.4407 | 78.3504 | 155-1044-07783504 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/28907 | TN/TR/AT/23440 |  | Done | 2022-11-10 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-10 | 2022-11-19 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L2100+L900 | 4 | done | 16 |  |  | Dec | Dec | 22225747 | 2022-11-29 | 2022-11-29 | 2022-11-29 |  | MS1 DONE | 2022-11-29 | Shajofonica | 2022-11-29 | BOSS MANAGEMENT |  |  |  | 2022-11-30 |  | Relocated |  | 2022-12-01 | TN/13/5126/00327/0043/04/01/17205/NS/01122022 | 2022-12-02 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-01 | [6 empty] | Gnoc pending |  |  |  | 2023-01-09 |  |  | 2022-12-20 | 2022-12-25 |  | 2022-12-23 | 2022-12-25 |  |  | 2022-12-15 | 2022-12-15 | Phy & Soft AT Pending |  | Phy & Soft AT Pending |  | CNIL Free Exit Feasble Relocation | 2022-12-01
109 | TN | MELPN2 | MELPN1 | OK | TRY | Relocation | Ericsson | Melappanaiyur 2 | Mr.Sekaran,Post office street,Panayampatti,Thirumayam,Pudukottai-622406 PH:9444894853 | Pudukottai | GBT | Survey wip, |  |  | 10.314 | 78.6747 | 155-1031-40786747 | 2G+L1800+L2300+L900 | CNIL / GTL | Summit | TAM/GBT/K/28842 | I-TN-TRMY-ENB-9023 |  | Done | 2022-11-13 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-13 | 2022-12-23 | MANIKANDAN/ONCALL | 2G+L1800+L2300+L900 | 0 | 0 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22516601 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-05 | Boss Management | 2023-01-05 | BOSS MANAGEMENT |  |  |  | 2023-01-05 |  |  |  | 2023-01-08 | TN/13/5428/0194/0043/04/01/17454/NS/08012023 | 2023-02-01 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-08 | 43 | [9 empty] | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-08
110 | CHN | CWM226 | CWM107 | OK | CHN | Relocation |  | ANNA NAGAR15 | Plot No.1228/1, Door No.57/1, Old S. No.137/Part, TS No.208/2, Block No.34, 18th Main Road, Post: Anna Nagar, Taluk & District: Chennai, State: Tamilnadu, Pincode-600040 | Chennai | RTP | Survey wip, | 13.0946 | 80.2035 | 13.0946 | 80.2035 | 152-1309-46802034 | 2G+L1800+L2100+L2300+L900 | INDUS | Indus | IN-1006939 | IN-3136032 | IN-3136032 | Done | 2022-11-14 | Operation Issues |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-14 | [8 empty] | 88 | Morethan 10 Days | Feb'23 | [6 empty] | Full site materials req | [20 empty] | Yes |  | 42 | [21 empty] | Installation Pending |  |  |  | Operation Issues | #N/A
111 | TN | KUKLM2 | KUKLM1 | 1 LINK | CBE | Relocation | Ericsson | Kurkalpalayam 2 | Sf.No.121, Post: Kurkalpalayam Village, Taluk: Kangeyam, District: Tiruppur, State: Tamilnadu, Pincode-638660 | Tiruppur | GBT | Survey wip, |  |  | 10.9434 | 77.4792 | 155-1094-34774792 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28773 | IN-3149809 |  | Done | 2022-11-17 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-16 | 2022-12-19 | VICKY/ONCALL | 2G+L1800+L2300+L900 | L1800 | L2300 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22483920 | 2022-12-24 | 2022-12-24 | 2022-12-24 |  | MS1 DONE | 2023-01-04 | SK Telecom | 2023-01-04 | SK Telecom |  |  |  | 2023-01-04 |  | Relocated |  | 2023-01-05 | TN/01/5177/01729/0043/04/01/17429/NS/05012023 |  |  | 86 | Morethan 7 Days | 36 | Morethan 7 Days |  | Yes | 2023-01-05 | 40 | [6 empty] | 2023-01-16 | 2023-01-19 |  | 2023-01-15 | 2023-01-19 |  | 2023-01-12 | 2023-01-17 |  | 2023-01-06 | 2023-01-08 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-05
112 | TN | KADKI2 | KADKI1 | OK | CBE | Relocation | Ericsson | Kandyankuttai 2 | Sf.No.1557/1, Post: Aval poondurai village, Taluk: Sulur, District: Erode, State: Tamilnadu, Pincode-638115 | Erode | GBT | Survey wip, |  |  | 11.2429 | 77.7582 | 155-1124-29777582 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28588 | IN-3149504 |  | Done | 2022-11-17 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-16 | 2022-11-30 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 6194700 | 2022-12-05 | 2022-12-06 | 2022-12-08 |  | MS1 DONE | 2023-01-15 | Boss management | 2023-01-15 | BOSS MANAGEMENT |  |  |  | 2023-01-15 |  |  |  | 2023-01-14 | TN/04/5177/00480/0043/04/01/17499/NS/14012023 | 2023-01-24 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-15 | 40 |  | 2023-02-03 |  |  | 2023-02-03 |  |  |  |  | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-18 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-15
113 | TN | NALPM2 | NALPM1 | OK | CBE | Relocation | Huawei + Ericsson | Namakkal Palayam 2 | Sf.No.693/6, Post: Mukasipalayam, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638051 | Erode | GBT | MS1 DONE |  |  | 11.1804 | 77.6091 | 155-1118-04776092 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/29363 | IN-3149624 |  | Done | 2022-11-18 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-17 | 2022-11-30 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 4 | done | 16 |  |  | Dec | Dec | 6194688 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE | 2022-12-14 | Boss management | 2022-12-14 | BOSS MANAGEMENT |  |  |  | 2022-12-14 |  | Relocated |  | 2022-12-16 | TN/04/5177/00481/0043/04/01/17266/NS/16122022 | 2022-12-16 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-16 |  |  | 2023-02-03 |  |  | 2023-02-03 |  | 2022-12-22 | 2022-12-23 |  | 2023-01-09 | 2022-12-23 |  | 2022-12-18 | 2022-12-23 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-12-17
114 | TN | SLYUR2 | SLYR1 | OK | CBE | Relocation | Ericsson | Salaiyur 2 | No.55/B1, Post: Thinnapatti Village, Taluk: Udumalaipet, District: Tiruppur, State: Tamilnadu, Pincode-642132 | Tiruppur | GBT | Survey wip, |  |  | 10.5579 | 77.1421 | 155-1055-79771421 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/29644 | IN-3149786 |  | Done | 2022-11-18 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-18 | 2022-12-14 | SHIVA/SUMAN-INHOUSE | 2G+L1800+L2100+L2300+L900 | L1800 | L900+L2100+L2300 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22516192 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-03 | Boss Management | 2023-01-03 | BOSS MANAGEMENT |  |  |  | 2023-01-03 |  | Relocated |  | 2023-01-05 | TN/01/5177/01728/0043/04/01/17431/NS/05012023 |  |  | 84 | Morethan 7 Days | 36 | Morethan 7 Days |  | Yes | 2023-01-05 | 38 | [6 empty] | 2023-01-12 | 2023-01-15 |  | 2023-01-11 | 2023-01-15 |  | 2023-01-11 | 2023-01-13 |  | 2023-01-23 | 2023-01-23 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-05
115 | TN | THKUM2 | THKM1 | 1 LINK | TRY | Relocation | Ericsson | Tirunedunkulam 2 | Mr. Narayanasamy T, S/o. Thangiayan, S.No. 305/1, Old S.No. 212, Patta No. 148, Post: Tirunedunkulam Village, Taluk: Tiruverumbur, District: Tiruchirapalli, State: Tamilnadu, Pincode-620015 | Tiruchirappalli | GBT | Survey wip, |  |  | 10.7739 | 78.853 | 155-1077-39788531 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/08364 | TN/TR/AT/23392 |  | Done | 2022-11-19 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | 2022-11-23 |  | 2G+L1800+L2300+L900 | GL1800 | L2300+L900 | 3 | done | 0 |  |  | Jan'23 | Jan'23 | 22517209 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-08 | RS Teletude | 2023-01-08 | RS Teletude |  |  |  | 2023-01-08 |  | Relocated |  | 2023-01-09 | TN/13/5126/00335/0043/04/01/17461/NS/09012023 | 2023-01-19 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-09 | 37 |  | 2023-02-03 |  |  | 2023-02-03 |  | 2023-01-16 | 2023-01-19 |  | 2023-01-15 | 2023-01-19 |  | 2023-01-12 | 2023-01-17 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-09
116 | TN | PTLPT2 | PTLPT1 | OK | TRY | Relocation |  | Pathalapattai 2 | Mrs. Annie Suganya J, W/o. Jason Kennedy, S.No.142/3A2, Post: Pathalapattai Village, Taluk: Tiruverambur, District: Tiruchirapalli, State: Tamilnadu, Pincode-620013 | Tiruchirappalli | GBT | Survey wip, |  |  | 10.8019 | 78.8509 | 155-1080-19788510 | 2G+L1800+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30257 | TN/TR/AT/23466 |  | Done | 2022-11-19 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | 2022-12-06 | Inhouse | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 8 |  |  | Feb'23 |  | 22697620 | 2023-01-20 | 2023-01-20 | 2023-01-23 |  | Antenna & Power,Cpri Cables req | [20 empty] | Yes |  | 37 | [21 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
117 | TN | AVOOR4 | AVOOR2 | OK | TRY | Relocation | Huawei + Ericsson | Avoor - TNJ | Sf.No.2/41, Muslim main road, Sepparam, Post: Govindakudi, Taluk & District: Thiruvarur, State: Tamil Nadu, Pincode-612701 | Thiruvarur | GBT |  |  |  | 10.9078 | 79.3423 | 155-1090-78793423 | 2G+L1800+L2300+L900 | BSNL | Indus | 1624 | IN-3133824 |  | Done | 2022-11-21 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-21 | 2022-12-01 |  | 2G+L1800+L2300+L900 | L1800 | L2100 | 3 | done | 6 |  |  | Dec | Dec | 22271221 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE | 2022-12-17 | Boss management | 2022-12-17 | BOSS MANAGEMENT |  |  |  | 2022-12-17 |  | Relocated |  | 2022-12-22 |  | 2023-02-04 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-22 | [7 empty] | 2023-01-09 | 2023-01-13 |  | 2023-01-09 | 2023-01-13 |  | 2023-01-05 | 2023-01-10 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-12-25
118 | TN | CBE955 | CBE315 | OK | CBE | Relocation |  | Town Hall | Survey ward No.2, Block No.18, T.S.No.1004/1, 1005 Part, 1007/2, 1007/4, Post: Periyakadai veethi, Taluk & District: Coimbatore, State: Tamilnadu, Pincode-641001 | Coimbatore | RTT |  |  |  | 10.9939 | 76.964 | 155-MCBE-1132443 | 2G+L1800+L2100+L2300+L900+TTB-B | INDUS | Indus | IN-1245606 | IN-3141960 |  | Done | 2022-11-21 | High Opex (Circle) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-21 | 2023-01-21 | SK TEAM | 2G+L1800+L2100+L2300+L900+TTB-B | 2G+L1800+L2300 | L2100+L900 | 3 | done | 12 |  |  | Feb'23 | Jan'23 | [5 empty] | Survey pending | 2023-01-25 | SK Telecom | 2023-01-25 | SK Telecom |  |  |  | 2023-01-27 | [7 empty] | 81 | Morethan 7 Days | 12 | Morethan 7 Days |  | Yes | 2023-01-29 | 35 | [21 empty] | MS1 Pending |  |  |  | High Opex (Circle) | 2023-01-29
119 | TN | SULR29 | KANGY1 | OK | CBE | Relocation | Huawei | Kangayapalayam | Sf.No.3/353, Trichy Road, Post: Kangayamapalayam, Taluk: Sulur, District: Coimbatore, State: Tamilnadu, Pincode-641401 | Coimbatore | GBT | MS1 DONE |  |  | 11.0276 | 77.1532 | 155-1102-77771532 | 2G+L1800+L2100+L2300+TTB-A(Don’t put L2100 in 330) | Indus | Indus | IN-1062767 | IN-3147358 |  | Done | 2022-11-21 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-21 | 2022-11-29 | BOSS MNG |  |  |  | 4+3+4 |  | 11 |  |  | Dec | Dec | 22255358 | 2022-12-02 | 2022-12-03 | 2022-12-03 |  | MS1 DONE | 2022-12-01 | Shajofonica | 2022-12-05 | RS Teletude |  |  |  | 2022-12-05 |  | Relocated |  | 2022-12-06 | TN/01/5177/01708/0043/04/01/17235/NS/06122022 |  |  | 81 | Morethan 7 Days | 66 | Morethan 7 Days |  | Yes | 2022-12-06 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul |  |  |  | 2023-01-09 | [11 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  |  | 2022-12-06
120 | TN | ANKDN2 | ANKD1 | OK | CBE | Relocation |  | Aandi Koundanur 2 | Sf.No.904, SF No.274, Post: Andiagowndanoor, Taluk: Udumalaipet, District: Tiruppur, State: Tamilnadu, Pincode-642154 | Tiruppur | GBT |  |  |  | 10.5306 | 77.2678 | 155-MTNU-1663563 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/27779 | IN-3149762 |  | Done | 2022-11-19 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | [6 empty] | done |  | 83 | Morethan 10 Days | Feb'23 | [6 empty] | Re-Survey | [20 empty] | Yes |  | 37 | [21 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
121 | TN | THPBR2 | THPBR1 | OK | TRY | Relocation |  | Thenperambur 2 | Mr. Ambikapati M, S/o. Murugaiyan, S.No. 254/8 Presently S.No. 254/8B, Post: Thenperambur, Taluk: Kurunthankudi, District: Thanjavur, State: Tamilnadu, Pincode-613101 | Thanjavur |  |  |  |  | 10.8253 | 79.0547 | 155-MTNU-1648524 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | ATC | TAM/GBT/K/30234 | YET_TO_GENERATE |  | Done | 2022-11-23 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-23 | 2022-12-13 | MANIKANDAN/ONCALL | 2G+L1800+L2100+L2300+L900 | 2G+L1800 | L2100+L2300+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22630177 | 2023-01-09 | 2023-01-12 | 2023-01-13 |  | MS1 DONE | 2023-01-22 | Shajofonica | 2023-01-22 | Shajofonica |  |  |  | 2023-01-22 |  | Relocated |  | 2023-01-24 |  | 2023-01-31 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-24 | 33 | [15 empty] | 2023-01-28 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-24
122 | CHN | MANI22 | MANIN2 | OK | CHN | Relocation |  | Manali Indl Estae2 | No.82, SH 104, Dwaraka Nagar, Manali New Town, Post & Taluk: Manali, District: Chennai, State: Tamil Nadu, Pincode-600103 | Chennai | GBT |  |  |  | 13.1985 | 80.27 | 152-MCHN-1074455 | 2G+L1800+L2100+L2300+L900(Don’t put L2100 in 270) | Indus | Indus | IN-1006292 | TN/CH/TT/12843 | STANDARD_PRODUCT | Done | 2022-11-23 | Operation Issues |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-23 | 2023-01-08 | SETHU/ONCALL | 2G+L1800+L2100+L2300+L900(Don’t put L2100 in 270) | - | L900+UBR+L2300 | 3 | done | 12 |  |  | Feb'23 |  | 82681 | 2023-01-09 | 2023-01-10 | 2023-01-11 |  | Material transit | [20 empty] | Yes |  | 33 | [21 empty] | Installation Pending |  |  |  | Operation Issues | #N/A
123 | TN | AMNCH2 | AMNCH1 | OK | TRY | Relocation |  | AMMANICHATTIRAM 2 | Sf.No.16, Post: Ammanichatiram, Taluk & District: Thanjavur, State: Tamilnadu, Pincode-614612 | Thanjavur | GBT |  |  |  | 10.2019 | 79.2494 | 155-MTNU-403982 | 2G+L1800+L2100+L900 | Indus | Indus | IN-1069234 | IN-3138661 |  | Done | 2022-11-23 | Operation Issues |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-23 | 2023-01-21 | SATHISH/ONCALL | 2G+L1800+L2100+L900 | L1800 | L900+L2100 | 3 | done | 9 |  |  | Feb'23 | Feb'23 |  | 2023-01-21 | 2023-01-21 | 2023-01-23 |  |  | 2023-01-27 | Shajofonica | 2023-01-27 | Shajofonica |  |  |  | 2023-01-28 |  |  |  | 2023-02-03 |  | 2023-02-06 | R.MANIKANDAN | [5 empty] | Yes | 2023-02-03 | 33 | [21 empty] | MS1 Pending |  |  |  | Operation Issues | 2023-02-02
124 | TN | VMGMD2 | VMGM1 | OK | CBE | Relocation |  | Vemgamedu 2 | Sf.No.237/5B, Post: Pasuvapatti village, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638051 | Erode | GBT |  |  |  | 11.1379 | 77.6087 | 155-MTNU-1641670 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/11544 | IN-3149741 |  | Done | 2022-11-23 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-23 | 2022-11-30 | SENTHIL/SHYON | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 9 |  |  | Feb'23 |  | 22804754 | 2023-02-02 | 2023-02-03 |  |  |  | 2023-02-07 | Shyon Enterprises | 2023-02-07 | Shyon Enterprises |  |  |  | 2023-02-07 | [12 empty] | Yes |  | 33 | [21 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
125 | CH | ITC003 | ITC2 | OK | CHN | Relocation | Huawei + MW |  |  | Chennai | [6 empty] | 152-1318-46803125 | [6 empty] | Done | 2022-03-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-21 | 2022-03-28 | [9 empty] | APR | APR | 76133 | 2022-05-08 | 2022-05-09 | 2022-05-09 |  | MS1 DONE | 2022-04-03 |  | 2022-04-02 |  |  |  |  | 2022-04-03 |  | Relocated |  | 2022-04-03 |  | 2022-04-03 | [6 empty] | Yes | 2022-04-03 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-06-13 | 2022-07-08 |  | 2022-05-03 | 2022-07-08 |  | 2022-07-04 | 2022-07-08 |  | 2022-05-03 | 2022-07-08 |  | 2022-09-13 | 2022-09-02 | 2022-09-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-03
126 | CH | AYAN31 | AYANAV | OK | CHN | Relocation | Huawei + MW |  |  | Chennai | [6 empty] | 152-1309-91802304 | [6 empty] | Done | 2022-04-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-01 | 2022-04-06 | [9 empty] | APR | APR | 74608 | 2022-04-14 | 2022-04-15 | 2022-04-18 |  | MS1 DONE | 2022-04-15 |  | 2022-04-15 |  |  |  |  | 2022-04-16 |  | Relocated |  | 2022-04-16 |  | 2022-04-17 | [6 empty] | Yes | 2022-04-17 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-05-30 | 2022-07-08 |  | 2022-06-05 | 2022-07-08 |  | 2022-07-04 | 2022-07-08 |  | 2022-06-05 | 2022-07-08 |  | 2022-10-02 | 2022-09-02 | 2022-09-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-17
127 | CH | VADA12 | VADAP5 | OK | CHN | Relocation | Huawei + Ericsson + MW |  |  | Chennai | [6 empty] | 152-1305-34802159 | [6 empty] | Done | 2022-03-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-25 | 2022-04-01 |  | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | NA | RRU2219 B0*3+RRU2279*3 |  |  | APR | APR | 18480464 | 2022-04-06 | 2022-04-07 | 2022-04-08 |  | MS1 DONE | 2022-04-16 |  | 2022-04-16 |  |  |  |  | 2022-04-17 |  | Relocated |  | 2022-04-17 |  | 2022-04-17 | [6 empty] | Yes | 2022-04-17 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-07-02 | 2022-07-08 |  | 2022-06-05 | 2022-07-08 |  | 2022-06-25 | 2022-06-30 | kuldeep | 2022-04-23 | 2022-04-27 |  |  | 2022-06-30 |  | Only KPI Pending | Under_ATP | Only KPI Pending |  |  | 2022-04-17
128 | CH | PAMLP2 | PAMLPO | OK | CHN | Relocation | Huawei + Ericsson + MW |  |  | Chennai | [6 empty] | 152-1297-41801353 | [6 empty] | Done | 2022-03-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-14 | 2022-03-31 |  | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3 | NA | RRU2219 B0*3+RRU2279*3 |  |  | APR | APR | 74314 | 2022-04-04 | 2022-04-05 | 2022-04-04 |  | MS1 DONE | 2022-04-18 |  | 2022-04-18 |  |  |  |  | 2022-04-20 |  | Relocated |  | 2022-04-20 |  | 2022-04-22 | [6 empty] | Yes | 2022-04-22 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-06-18 | 2022-07-08 |  | 2022-07-28 | 2022-07-08 |  | 2022-07-01 | 2022-07-06 | kuldeep | 2022-05-13 | 2022-05-17 |  | 2022-10-02 | 2022-08-29 | 2022-09-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-22
129 | CH | TIRU43 | TIRU31 | OK | CHN | Relocation | Huawei + Ericsson + MW |  |  | Chennai | [6 empty] | 152-1312-57800420 | [6 empty] | Done | 2022-03-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-16 | 2022-03-10 |  | L900+GL1800 |  | L900+GL1800 | 4+3+3 | NA | RRU2219 B0*3+RRU2279*4 |  |  | APR | APR | 18474026 | 2022-04-05 | 2022-04-09 | 2022-04-10 |  | MS1 DONE | 2022-04-18 |  | 2022-04-19 |  |  |  |  | 2022-04-20 |  | Relocated |  | 2022-04-20 |  | 2022-04-22 | [6 empty] | Yes | 2022-04-22 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-06-25 | 2022-06-08 |  | 2022-07-25 | 2022-06-08 |  | 2022-08-14 | 2022-08-19 | kuldeep | 2022-05-02 | 2022-05-06 |  | 2022-10-02 | 2022-09-02 | 2022-09-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-22
130 | CH | RICHI8 | RICHIE | OK | CHN | Relocation | Huawei + Ericsson + MW |  |  | Chennai | [6 empty] | 152-1306-95802702 | [6 empty] | Done | 2022-04-26 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-26 | 2022-04-28 |  | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | NA | RRU2219 B0*3+RRU2279*3 |  |  | MAY | May | 75362 | 2022-05-14 | 2022-05-15 | 2022-05-15 |  | MS1 DONE | 2022-05-04 |  | 2022-05-04 |  |  |  |  | 2022-05-12 |  | Relocated |  | 2022-05-12 |  | 2022-05-27 | [6 empty] | Yes | 2022-05-27 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-07-02 | 2022-07-08 |  | 2022-07-25 | 2022-07-08 |  | 2022-07-03 | 2022-07-08 |  | 2022-05-13 | 2022-05-17 |  | 2023-01-28 | 2023-01-25 | 2023-01-25 | MS2 Done | MAPA_Done | Only KPI Pending |  |  | 2022-05-27
131 | CH | VELMA6 | VELMA2 | OK | CHN | Relocation | Ericsson + MW |  |  | Chennai | [6 empty] | 152-1298-74802225 | [6 empty] | Done | 2022-04-27 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-27 | 2022-04-29 |  | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | NA | RRU2219 B0*3+RRU2279*3 |  |  | JUN | JUN | 75272 | 2022-05-08 | 2022-05-10 | 2022-05-11 |  | MS1 DONE | 2022-05-26 |  | 2022-05-26 |  |  |  |  | 2022-06-08 |  | Relocated |  | 2022-06-08 |  | 2022-06-13 | [6 empty] | Yes | 2022-06-13 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-07-09 | 2022-07-09 |  | 2022-07-23 | 2022-07-23 |  | 2022-07-04 | 2022-07-09 | kuldeep | 2022-07-19 | 2022-07-23 |  | 2023-01-14 | 2022-11-28 | 2022-11-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-13
132 | CH | KODU36 | KODUN3 | OK | CHN | Relocation | Huawei + Ericsson + MW |  |  | Chennai | [6 empty] | 152-1313-10802518 | [6 empty] | Done | 2022-04-29 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-25 | 2022-04-30 | [9 empty] | JUN | JUN | 76134 | 2022-06-03 | 2022-06-04 | 2022-06-04 |  | MS1 DONE, New Maerial |  |  | 2022-06-15 | OWN TEAM |  |  |  | 2022-06-21 |  | Relocated |  | 2022-06-22 |  | 2022-06-23 | [6 empty] | Yes | 2022-06-23 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-28 | 2022-07-07 |  | 2022-07-25 | 2022-07-07 |  | 2022-07-03 | 2022-07-07 |  | 2022-07-25 | 2022-07-07 |  | 2022-10-02 | 2022-08-29 | 2022-09-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-23
133 | CH | CWM225 | CWM109 | OK | CHN | Relocation | Huawei + Ericsson + MW |  |  | Chennai | [6 empty] | 152-1293-39802331 | [6 empty] | Done | 2022-06-11 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-06-13 | 2022-06-14 |  | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | NA | RRU2219 B0*3+RRU2279*3 |  |  | JUN | JUN | 77762 | 2022-06-14 | 2022-06-15 | 2022-06-15 |  | MS1 DONE | 2022-06-26 |  | 2022-06-14 |  |  |  |  | 2022-06-24 |  | Relocated |  | 2022-06-25 |  | 2022-06-26 | [6 empty] | Yes | 2022-06-26 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-08-03 | 2022-08-07 |  | 2022-07-25 | 2022-08-07 |  | 2022-08-03 | 2022-08-08 | kuldeep | 2022-10-27 | 2022-10-31 |  |  |  |  | Only KPI Pending | MAPA_Done | Only KPI Pending |  |  | 2022-06-26
134 | TN | CBE901 | CBE159 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore | [6 empty] | 155-1096-75770035 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-03 | 2022-03-05 |  | L2100+L2300 |  | L2100+L2300 | 4+5 | NA | RRU4418*5+RRU2219*4 |  |  | APR | APR | 18355721 | 2022-03-14 | 2022-03-15 | 2022-03-17 |  | MS1 DONE | 2022-03-31 |  | 2022-03-30 |  |  |  |  | 2022-03-31 |  | Relocated |  | 2022-03-31 | TN/01/5428/0322/0043/04/01/15880/NS/31032022 | 2022-04-01 | [6 empty] | Yes | 2022-04-01 | [7 empty] | 2022-06-24 | 2022-06-25 |  | 2022-06-12 | 2022-06-25 |  | 2022-06-21 | 2022-06-26 | kuldeep | 2022-04-03 | 2022-04-07 |  | 2022-12-26 | 2022-12-29 | 2022-12-29 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-01
135 | TN | VKLM03 | VKLM1 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Tirunelveli | [6 empty] | 155-0879-48774084 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-25 | 2022-03-07 |  | L2100 |  | L2100 | 4 | NA | RRU2219 B1*4 |  |  | APR | APR | 18344401 | 2022-03-12 | 2022-03-13 | 2022-03-16 |  | MS1 DONE | 2022-03-31 |  | 2022-03-30 |  |  |  |  | 2022-03-31 |  | Relocated |  | 2022-03-31 | TN/12/5177/00529/0043/04/01/15877/NS/31032022 | 2022-04-01 | [6 empty] | Yes | 2022-04-01 | [7 empty] | 2022-06-04 | 2022-06-06 |  | 2022-04-27 | 2022-06-06 |  | 2022-08-09 | 2022-08-14 | kuldeep | 2022-04-05 | 2022-04-09 |  | 2022-09-08 | 2022-04-22 | 2022-04-26 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-01
136 | TN | TUT121 | TUT11 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Tutucorin | [6 empty] | 155-0878-88781325 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-04 | 2022-03-04 |  | L2100+L2300 |  | L2100+L2300 | 4+5 | NA | RRU4418*5+RRU2279*4 |  |  | APR | APR | 18344489 | 2022-03-12 | 2022-03-13 | 2022-03-15 |  | MS1 DONE | 2022-04-02 |  | 2022-04-02 |  |  |  |  | 2022-04-04 |  | Relocated |  | 2022-04-04 | TN/14/5177/1902/0043/04/01/15884/NS/04042022 | 2022-04-04 | [6 empty] | Yes | 2022-04-04 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-09-12 | 2022-09-14 |  | 2022-04-27 | 2022-09-14 |  | 2022-07-31 | 2022-08-05 | kuldeep | 2022-04-03 | 2022-04-07 |  | 2022-10-02 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-04
137 | TN | PDMUP2 | PDMUP1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Pondy | [6 empty] | 155-1338-65801109 | [6 empty] | Done | 2022-03-28 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-27 | 2022-03-29 |  | L2100+L2300 |  | L2100+L2300 | 3+4 | NA | RRU4418*4+RRU2219 B1*3 |  |  | APR | APR | 18457654 | 2022-04-02 | 2022-04-03 | 2022-04-05 |  | MS1 DONE | 2022-04-04 |  | 2022-04-03 |  |  |  |  | 2022-04-05 |  | Relocated |  | 2022-04-05 | TN/18/5177/04023/0043/04/01/15886/NS/06042022 | 2022-04-08 | [6 empty] | Yes | 2022-04-08 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-05-28 | 2022-05-31 |  | 2022-04-14 | 2022-05-31 |  | 2022-04-20 | 2022-04-25 | kuldeep | 2022-04-06 | 2022-04-10 |  | 2022-11-22 | 2022-11-11 | 2022-11-15 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-08
138 | TN | UAUNM2 | UAUNM1 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Tirunelveli | [6 empty] | 155-0871-34778084 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-23 | 2022-03-05 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | APR | APR | 18337666 | 2022-03-11 | 2022-03-12 | 2022-03-14 |  | MS1 DONE | 2022-04-08 |  | 2022-04-05 |  |  |  |  | 2022-04-06 |  | Relocated |  | 2022-04-06 | TN/12/5428/0017/0043/04/01/15887/NS/06042022 | 2022-04-08 | [6 empty] | Yes | 2022-04-08 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-06-24 | 2022-06-25 |  | 2022-04-19 | 2022-06-25 |  | 2022-07-22 | 2022-07-27 | kuldeep | 2022-05-02 | 2022-05-06 |  | 2022-07-28 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-08
139 | TN | MTHKL5 | MTHKL1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Tiruchirappalli | [6 empty] | 155-1075-50786064 | [6 empty] | Done | 2022-04-06 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-06 | 2022-04-06 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | APR | APR | 18480483 | 2022-04-06 | 2022-04-07 | 2022-04-07 |  | MS1 DONE | 2022-04-08 |  | 2022-04-06 |  |  |  |  | 2022-04-06 |  | Relocated |  | 2022-04-06 | TN/13/5428/0074/0043/04/01/15890/NS/06042022 | 2022-04-08 | [6 empty] | Yes | 2022-04-08 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-29 | 2022-08-07 |  | 2022-04-29 | 2022-08-07 |  | 2022-08-03 | 2022-08-08 | kuldeep | 2022-04-05 | 2022-04-09 |  |  | 2022-08-08 |  | Only KPI Pending | MAPA_Done | Only KPI Pending |  |  | 2022-04-08
140 | TN | DGL110 | DGL13 | OK | MDU | Relocation | Huawei + MW |  |  | Dindigul | [6 empty] | 155-1034-28779915 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-03 | 2022-03-04 | [9 empty] | APR | APR | 18297916 | 2022-03-06 | 2022-03-07 | 2022-03-08 |  | MS1 DONE | 2022-06-16 |  | 2022-04-13 |  |  |  |  | 2022-04-15 |  | Relocated |  | 2022-04-15 | TN/06/5126/0037/0043/04/01/15933/NS/15042022 | 2022-04-15 | [6 empty] | Yes | 2022-04-15 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-07-04 | 2022-07-05 |  | 2022-04-27 | 2022-07-05 |  | 2022-07-01 | 2022-07-05 |  | 2022-06-09 | 2022-06-13 |  | 2022-11-26 | 2022-11-18 | 2022-11-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-15
141 | TN | VLR235 | VLR52 | OK | VLR | Relocation | Huawei + MW |  |  | Vellore | [6 empty] | 155-1293-23791399 | [6 empty] | Done | 2022-02-20 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-24 | 2022-03-24 | [9 empty] | APR | APR | 1011542 | 2022-03-24 | 2022-03-26 | 2022-02-27 |  | MS1 DONE | 2022-04-15 |  | 2022-04-08 |  |  |  |  | 2022-04-09 |  | Relocated |  | 2022-04-09 | TN/15/5177/01984/0043/04/01/15896/NS/09042022 | 2022-04-09 | [6 empty] | Yes | 2022-04-09 | [7 empty] | 2022-06-29 | 2022-07-02 |  | 2022-04-27 | 2022-07-02 |  | 2022-06-28 | 2022-07-02 | [5 empty] | 2022-07-02 |  | Only KPI Pending | MAPA_Done | Only KPI Pending |  |  | 2022-04-09
142 | TN | PNPT15 | PNPT3 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Cuddalore | [6 empty] | 155-1148-67797561 | [6 empty] | Done | 2022-03-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-25 | 2022-03-31 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | APR | APR | 18468151 | 2022-04-04 | 2022-04-05 | 2022-04-06 |  | MS1 DONE | 2022-04-12 |  | 2022-04-11 |  |  |  |  | 2022-04-11 |  | Relocated |  | 2022-04-12 | TN/02/5177/00948/0043/04/01/15911/NS/12042022 | 2022-04-16 | [6 empty] | Yes | 2022-04-16 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-06-25 | 2022-06-27 |  | 2022-07-28 | 2022-06-27 |  | 2022-06-21 | 2022-06-26 | kuldeep | 2022-04-15 | 2022-04-19 |  | 2022-07-22 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-16
143 | TN | PCHYR2 | PCHYR1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore | [6 empty] | 155-1111-46769228 | [6 empty] | Done | 2022-02-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-27 | 2022-02-23 |  | L2100+L2300 |  | L2100+L2300 | 4 | NA | RRU4418*6+RRU2219*3 |  |  | APR | APR | 18248250 | 2022-02-24 | 2022-02-25 | 2022-02-26 |  | MS1 DONE | 2022-05-10 |  | 2022-02-28 |  |  |  |  | 2022-04-18 |  | Relocated |  | 2022-04-18 | TN/01/5177/01648/0043/04/01/15951/NS/18042022 | 2022-04-18 | [6 empty] | Yes | 2022-04-18 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-07-28 | 2022-08-11 |  | 2022-07-25 | 2022-08-11 |  | 2022-08-07 | 2022-08-12 | kuldeep | 2022-04-29 | 2022-05-03 |  | 2023-01-27 | 2023-01-27 | 2023-01-27 | All 3 Accepted | MAPA_Done | All 3 Accepted |  |  | 2022-04-18
144 | TN | COWKVP | KSVMP1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Thiruvallur | [6 empty] | 155-1332-85800720 | [6 empty] | Done | 2022-03-29 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-15 | 2022-03-29 |  | L2100+L2300 |  | L2100+L2300 | 3+3 | NA | RRU4418*3+RRU2219 B0*3 |  |  | APR | APR | 18457796 | 2022-04-02 | 2022-04-03 | 2022-04-05 |  | MS1 DONE | 2022-03-19 |  | 2022-04-09 |  |  |  |  | 2022-04-17 |  | Relocated |  | 2022-04-16 | TN/18/5177/04029/0043/04/01/15940/NS/16042022 | 2022-04-17 | [6 empty] | Yes | 2022-04-17 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-07-04 | 2022-07-05 |  | 2022-06-03 | 2022-07-05 |  | 2022-06-28 | 2022-07-03 | kuldeep | 2022-04-15 | 2022-04-19 |  | 2022-03-19 | 2022-04-18 | 2022-04-18 | MS2 Done | Cow site | All 3 Accepted |  |  | 2022-04-17
145 | TN | MTRM05 | MTRM3 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Salem |  | MS1 DONE |  |  |  |  | 155-1182-65778427 | L2300 | [5 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-03 | 2022-03-03 | [9 empty] | APR | APR | 18307859 | 2022-03-08 | 2022-03-09 | 2022-03-09 |  | MS1 DONE, New Maerial |  |  | 2022-04-06 | RS Teletude |  |  |  | 2022-04-16 |  | Relocated |  | 2022-04-16 | TN/10/5428/0007/0043/04/01/15937/NS/16042022 | 2022-04-17 | [6 empty] | Yes | 2022-04-17 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-06-18 | 2022-06-23 |  | 2023-01-20 | 2022-06-23 |  | 2022-06-19 | 2022-06-23 |  | 2022-08-31 | 2022-08-31 |  | 2022-09-13 | 2022-09-09 | 2022-04-25 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-17
146 | TN | KLNJR3 | KLNJR1 | OK | VLR | Relocation | Ericsson + MW |  |  | Vellore | [6 empty] | 155-1295-11791288 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-01 | 2022-03-08 |  | GL1800+L900 |  | GL1800+L900 | 4 | NA | RRU2279*4+RRU2219 B0*4 |  |  | APR | APR | 18400863 | 2022-03-22 | 2022-03-23 | 2022-03-25 |  | MS1 DONE | 2022-04-13 |  | 2022-04-12 |  |  |  |  | 2022-04-15 |  | Relocated |  | 2022-04-14 | TN/15/5297/0176/0043/04/01/15934/NS/15042022 | 2022-04-16 | [6 empty] | Yes | 2022-04-16 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-07-22 | 2022-07-22 |  | 2022-04-19 | 2022-04-19 |  | 2022-07-17 | 2022-07-22 | kuldeep | 2022-04-15 | 2022-04-19 |  | 2022-04-13 | 2022-12-13 | 2022-12-13 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-16
147 | TN | TKVL14 | TKVLR3 | OK | TRY | Relocation | Huawei + MW |  |  | Viluppuram | [6 empty] | 155-1196-11791905 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-26 | 2022-03-27 | [9 empty] | APR | APR | 18456127 | 2022-04-01 | 2022-04-02 | 2022-04-05 |  | MS1 DONE | 2022-04-07 |  | 2022-04-05 |  |  |  |  | 2022-04-08 |  | Relocated |  | 2022-04-08 | TN/02/5126/0025/0043/04/01/15892/NS/08042022 | 2022-04-08 | [6 empty] | Yes | 2022-04-08 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-06-29 | 2022-07-02 |  | 2022-04-27 | 2022-07-02 |  | 2022-06-28 | 2022-07-02 |  | 2022-04-27 | 2022-07-02 |  | 2022-07-22 | 2022-05-01 | 2022-05-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-08
148 | TN | PKT215 | PKT01 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Tirunelveli | [6 empty] | 155-0872-54777361 | [6 empty] | Done | 2022-03-09 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-08 | 2022-03-09 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | APR | APR | 18457711 | 2022-04-02 | 2022-04-03 | 2022-04-04 |  | MS1 DONE | 2022-04-11 |  | 2022-04-12 |  |  |  |  | 2022-04-15 |  | Relocated |  | 2022-04-15 | TN/12/5177/00530/0043/04/01/15931/NS/14042022 | 2022-04-15 | [6 empty] | Yes | 2022-04-15 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-06-13 | 2022-06-17 |  | 2022-04-28 | 2022-01-17 |  | 2022-06-26 | 2022-07-01 | kuldeep | 2022-04-15 | 2022-04-19 |  | 2022-07-22 | 2022-06-18 | 2022-06-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-15
149 | TN | TKMB18 | TKMB1 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Dindigul | [6 empty] | 155-1043-95779522 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-23 | 2022-03-03 |  | L2300+L2100 |  | L2300+L2100 | 4+3 | NA | RRU4418*4+RRU2219 B1*3 |  |  | APR | APR | 18298667 | 2022-03-06 | 2022-03-07 | 2022-03-08 |  | MS1 DONE | 2022-04-19 |  | 2022-04-18 |  |  |  |  | 2022-04-19 |  | Relocated |  | 2022-04-19 | TN/06/5177/01079/0043/04/01/15952/NS/19042022 | 2022-04-22 | [6 empty] | Yes | 2022-04-22 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-07-06 | 2022-07-07 |  | 2022-06-03 | 2022-07-07 |  | 2022-07-14 | 2022-07-19 | kuldeep | 2022-05-02 | 2022-05-06 |  | 2022-07-22 | 2022-06-18 | 2022-06-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-22
150 | TN | PRLAM3 | PRLAM1 | OK | TRY | Relocation | Ericsson + MW |  |  | Thiruvarur | [6 empty] | 155-1096-12796588 | [6 empty] | Done | 2022-03-04 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-26 | 2022-03-10 |  | GL1800 |  | GL1800 | 4+4 | NA | RRU2219 B3*4 |  |  | APR | APR | 18402800 | 2022-03-22 | 2022-03-23 | 2022-03-24 |  | MS1 DONE | 2022-05-01 |  | 2022-04-19 |  |  |  |  | 2022-04-22 |  | Relocated |  | 2022-04-22 | TN/11/5126/00077/0043/04/01/15968/NS/22042022 | 2022-04-22 | [6 empty] | Yes | 2022-04-22 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-08-23 | 2022-08-23 |  | 2022-04-27 | 2022-04-27 |  | 2022-08-18 | 2022-08-23 | kuldeep | 2022-04-23 | 2022-04-27 |  | 2022-05-01 | 2022-12-13 | 2022-12-13 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-22
151 | TN | CBE890 | CBE512 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore | [6 empty] | 155-1095-22769889 | [6 empty] | Done | 2022-03-17 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-16 | 2022-03-22 |  | L2100+L2300 |  | L2100+L2300 | 6+7 | NA | RRU4418*7+RRU2219 B1*6 |  |  | APR | APR | 18493138 | 2022-04-08 | 2022-04-09 | 2022-04-11 |  | MS1 DONE | 2022-04-21 |  | 2022-04-21 |  |  |  |  | 2022-04-23 |  | Relocated |  | 2022-04-23 | TN/01/5115/00136/0043/04/01/15978/NS/23042022 | 2022-04-25 | [6 empty] | Yes | 2022-04-25 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-08-02 | 2022-08-07 |  | 2022-06-12 | 2022-08-07 |  | 2022-08-01 | 2022-08-06 | kuldeep | 2022-04-23 | 2022-04-27 |  | 2023-01-06 | 2023-01-06 | 2023-01-06 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-25
152 | TN | TRY385 | TRY04 | OK | TRY | Relocation | Huawei + MW |  |  | Tiruchirappalli | [6 empty] | 155-1082-44786998 | [6 empty] | Done | 2022-04-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-01 | 2022-04-09 | [9 empty] | APR | APR | 18531452 | 2022-04-16 | 2022-04-17 | 2022-04-18 |  | MS1 DONE | 2022-04-21 |  | 2022-04-21 |  |  |  |  | 2022-04-25 |  | Relocated |  | 2022-04-25 | TN/13/5177/0991/0043/04/01/16004/NS/25042022 | 2022-04-25 | [6 empty] | Yes | 2022-04-25 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-07-07 | 2022-07-12 |  | 2022-07-28 | 2022-07-12 |  | 2022-07-08 | 2022-07-12 |  | 2022-07-28 | 2022-07-12 |  | 2022-07-30 | 2022-06-18 | 2022-06-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-25
153 | TN | SINGA2 | SINGA1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore | [6 empty] | 155-1061-95769617 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-01-24 | 2022-03-03 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAY | May | 18295570 | 2022-04-11 | 2022-04-12 | 2022-03-08 |  | MS1 DONE | 2022-04-27 |  | 2022-04-27 |  |  |  |  | 2022-04-30 |  | Relocated |  | 2022-04-30 | TN/01/5271/0319/0043/04/01/16007/NS/30042022 | 2022-05-05 | [6 empty] | Yes | 2022-05-05 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul |  |  |  | 2022-06-03 | 2022-06-07 |  | 2022-05-08 | 2022-05-13 |  | 2022-05-09 | 2022-05-13 |  |  | 2022-06-28 | 2022-06-28 | Only Phy Pending | Under_ATP | Only Phy Pending |  |  | 2022-05-05
154 | TN | SKGI22 | SKGI5 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Salem | [6 empty] | 155-1144-97778716 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-06 | 2022-03-06 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAY | May | 18468148 | 2022-04-04 | 2022-04-05 | 2022-04-06 |  | MS1 DONE | 2022-05-04 |  | 2022-05-04 |  |  |  |  | 2022-05-05 |  | Relocated |  | 2022-05-05 | TN/10/5177/00838/0043/04/01/16020/NS/05052022 | 2022-05-07 | [6 empty] | Yes | 2022-05-07 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-08-19 | 2022-08-23 |  | 2022-06-03 | 2022-06-07 |  | 2022-08-15 | 2022-08-20 | kuldeep | 2022-05-13 | 2022-05-17 |  | 2022-09-13 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-07
155 | TN | PDYRM2 | PDYRM1 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Tutucorin | [6 empty] | 155-0885-26781191 | [6 empty] | Done | 2022-03-10 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-10 | 2022-03-11 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | JUN | JUN | 18355881 | 2022-03-14 | 2022-03-15 | 2022-03-16 |  | MS1 DONE | 2022-06-26 |  | 2022-05-29 |  |  |  |  | 2022-05-30 |  | Relocated |  | 2022-05-31 | TN/14/5428/0144/0043/04/01/16187/NS/31052022 | 2022-06-01 | [6 empty] | Yes | 2022-06-01 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-08-09 | 2022-08-12 |  | 2022-10-19 | 2022-08-12 |  | 2022-08-13 | 2022-08-18 | kuldeep | 2022-07-02 | 2022-07-06 |  |  | 2022-10-12 | 2022-10-12 | Only SOFT Pending | Under_ATP | Only SOFT Pending |  |  | 2022-06-01
156 | TN | PKT010 | PKT02 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Tirunelveli | [6 empty] | 155-0870-07777428 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-01-22 | 2022-03-05 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | NA | RRU2219 B1*3+RRU2219 B0*4+RRU4418*4 |  |  | JUN | JUN | 1011842 | 2022-03-11 | 2022-03-14 | 2022-03-14 |  | MS1 DONE | 2022-06-15 |  | 2022-06-14 |  |  |  |  | 2022-06-19 |  | Relocated |  | 2022-06-20 | TN/12/5126/00084/0043/04/01/16288/NS/20062022 | 2022-06-21 | [6 empty] | Yes | 2022-06-21 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-08-05 | 2022-08-09 |  | 2022-07-25 | 2022-08-09 |  | 2022-08-05 | 2022-08-10 | kuldeep | 2022-09-20 | 2022-09-24 |  |  | 2022-08-10 |  | Only KPI Pending | MAPA_Done | Only KPI Pending |  |  | 2022-06-21
157 | TN | MNPTI2 | MNPTI1 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Salem | [6 empty] | 155-1171-34780337 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-01 | 2022-05-02 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | NA | RRU2219 B1*3+RRU2219 B0*4+RRU4418*4 |  |  | JUN | JUN | 19144713 | 2022-05-02 | 2022-05-03 | 2022-05-03 |  | MS1 DONE | 2022-06-28 |  | 2022-06-24 |  |  |  |  | 2022-06-28 |  | Relocated |  | 2022-06-28 | TN/14/5126/0146/0043/04/01/16358/NS/28062022 | 2022-06-30 | [6 empty] | Yes | 2022-06-30 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-08-20 | 2022-08-27 |  | 2022-07-25 | 2022-08-27 |  | 2022-08-18 | 2022-08-23 | kuldeep | 2022-12-16 | 2022-12-16 |  | 2023-01-27 | 2023-01-27 | 2023-01-27 | All 3 Accepted | MAPA_Done | All 3 Accepted |  |  | 2022-06-30
158 | TN | PPMPT3 | PPMPT1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore |  | MS1 DONE |  |  |  |  | 155-1095-71770998 | 2G+L18+ L21+L23 | [5 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-02 | 2022-03-02 |  | L2100+L2300 |  | L2100+L2300 | 3+6 | NA | RRU4418*6+RRU2219 B1*3 |  |  | July | Jul | 18298673 | 2022-03-06 | 2022-03-07 | 2022-03-08 |  | MS1 DONE | 2022-07-13 |  | 2022-07-13 |  |  |  |  | 2022-07-14 |  | Relocated |  | 2022-07-20 | TN/01/5168/0424/0043/04/01/16455/NS/16072022 | 2022-07-20 | [6 empty] | Yes | 2022-07-20 |  |  | 2022-07-20 |  |  | 2022-07-20 | Rahul | 2022-08-01 | 2022-08-19 |  | 2022-10-19 | 2022-08-19 |  | 2022-07-31 | 2022-08-05 | kuldeep | 2022-07-21 | 2022-07-25 |  |  | 2022-08-05 |  | Only KPI Pending | MAPA_Done | Only KPI Pending |  |  | 2022-07-17
159 | TN | PTTNM2 | PTTNM1 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Namakkal | [6 empty] | 155-1147-36782103 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-01-17 | 2022-03-04 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU2219 B1*5+RRU2219 B0*4 |  |  | JUN | JUN | 18612851 | 2022-05-02 | 2022-05-03 | 2022-05-04 |  | MS1 DONE | 2022-06-25 |  | 2022-06-26 |  |  |  |  | 2022-06-25 |  | Relocated |  | 2022-06-26 | TN/10/5271/0193/0043/04/01/16349/NS/26062022 | 2022-06-28 | [6 empty] | Yes | 2022-06-28 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-08-19 | 2022-08-23 |  | 2022-07-25 | 2022-07-27 |  | 2022-08-18 | 2022-08-23 | kuldeep | 2022-09-20 | 2022-09-24 |  | 2022-12-29 | 2022-12-29 | 2022-12-29 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-28
160 | TN | KLVLU3 | KLVLU1 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Madurai | [6 empty] | 155-1007-12784184 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-01-24 | 2022-03-11 |  | L2100+L2300 |  | L2100+L2300 | 3+4 | NA | RRU4418*4+RRU2219 B1*3 |  |  | MAY | May | 18468147 | 2022-04-04 | 2022-04-05 | 2022-04-06 |  | MS1 DONE | 2022-06-26 |  | 2022-05-06 |  |  |  |  | 2022-05-07 |  | Relocated |  | 2022-05-07 | TN/06/5177/01081/0043/04/01/16024/NS/07052022 | 2022-05-07 | [6 empty] | Yes | 2022-05-07 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-06-15 | 2022-06-17 |  | 2022-07-24 | 2022-06-17 |  | 2022-06-11 | 2022-06-16 | kuldeep | 2022-05-09 | 2022-05-13 |  | 2023-01-23 | 2022-11-15 | 2022-11-15 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-07
161 | TN | ELSPT2 | ELSPT1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Erode | [6 empty] | 155-1140-42776159 | [6 empty] | Done | 2022-03-24 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-24 | 2022-04-02 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAY | May | 18605497 | 2022-05-23 | 2022-05-24 | 2022-05-04 |  | MS1 DONE | 2022-07-01 |  | 2022-05-10 |  |  |  |  | 2022-05-11 |  | Relocated |  | 2022-05-11 | TN/04/5126/00132/0043/04/01/16038/NS/11052022 | 2022-05-12 | [6 empty] | Yes | 2022-05-12 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-08-05 | 2022-08-12 |  | 2022-06-07 | 2022-06-07 |  | 2022-08-03 | 2022-08-08 | kuldeep | 2022-05-12 | 2022-05-16 |  | 2022-09-13 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-12
162 | TN | KLRM02 | KLRM1 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Namakkal | [6 empty] | 155-1128-09779775 | [6 empty] | Done | 2022-03-30 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-30 | 2022-04-07 |  | L2100 |  | L2100 | 3 | NA | RRU2219 B1*3 |  |  | JUN | JUN | 75779 | 2022-05-23 | 2022-05-24 | 2022-05-25 |  | MS1 DONE | 2022-05-18 |  | 2022-06-02 |  |  |  |  | 2022-06-02 |  | Relocated |  | 2022-06-03 | TN/10/5177/00852/0043/04/01/16209/NS/03062022 | 2022-06-03 | [6 empty] | Yes | 2022-06-03 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-08-05 | 2022-08-09 |  | 2022-10-19 | 2022-08-09 |  | 2022-08-06 | 2022-08-08 | kuldeep |  |  |  |  | 2022-10-28 | 2022-10-28 | Only SOFT Pending | MAPA_Done | Only SOFT Pending |  | Field visit required for rectification | 2022-06-03
163 | TN | MURKD2 | MURKD1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Tiruchirappalli |  | MS1 DONE |  |  |  |  | 155-1094-93794522 | L1800 | [5 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-10 | 2022-03-10 |  | L2100 |  | L2100 | 3 | NA | RRU2219 B1*3 |  |  | MAY | May | 18646150 | 2022-05-07 | 2022-05-08 | 2022-05-10 |  | MS1 DONE | 2022-05-07 |  | 2022-05-11 |  |  |  |  | 2022-05-12 |  | Relocated |  | 2022-05-12 | TN/11/5428/0206/0043/04/01/16048/NS/12052022 | 2022-05-12 | [6 empty] | Yes | 2022-05-12 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-06-30 | 2022-07-02 |  | 2023-01-20 | 2022-07-02 |  | 2022-07-03 | 2022-07-08 | kuldeep | 2022-05-12 | 2022-05-16 |  | 2022-07-22 | 2022-07-01 | 2022-07-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-12
164 | TN | KTBS10 | KTBSL1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Tiruchirappalli | [6 empty] | 155-1019-07786930 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-11 | 2022-03-11 |  | L2100 |  | L2100 | 3 | NA | RRU2219 B0*3 |  |  | MAY | May | 18646151 | 2022-05-07 | 2022-05-08 | 2022-05-11 |  | MS1 DONE | 2022-05-11 |  | 2022-05-11 |  |  |  |  | 2022-05-12 |  | Relocated |  | 2022-05-12 | TN/13/5428/0439/0043/04/01/16050/NS/12052022 | 2022-05-15 | [6 empty] | Yes | 2022-05-15 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-06-27 | 2022-07-01 |  | 2022-07-24 | 2022-07-01 |  | 2022-06-27 | 2022-07-02 | kuldeep | 2022-05-12 | 2022-05-16 |  | 2022-07-22 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-15
165 | TN | AGAPM2 | AGAPM1 | OK | MDU | Relocation | Huawei + MW |  |  | Tirunelveli | [6 empty] | 155-0873-24773827 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-07 | 2022-05-08 | [9 empty] | MAY | May | 18646153 | 2022-05-07 | 2022-05-08 | 2022-05-12 |  | MS1 DONE | 2022-05-12 |  | 2022-05-13 |  |  |  |  | 2022-05-14 |  | Relocated |  | 2022-05-14 | TN/12/5177/00525/0043/04/01/16073/NS/14052022 | 2022-05-15 | [6 empty] | Yes | 2022-05-15 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-06-28 | 2022-07-02 |  | 2022-06-06 | 2022-07-02 |  | 2022-06-28 | 2022-07-02 |  | 2022-06-06 | 2022-07-02 |  | 2022-07-22 | 2022-06-18 | 2022-06-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-15
166 | TN | PMPYR4 | PMPYR1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Thanjavur | [6 empty] | 155-1092-76793556 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-08 | 2022-03-08 |  | L2300 |  | L2300 | 3 | NA | RRU4418*3 |  |  | JUN | JUN | 18958564 | 2022-06-09 | 2022-06-10 | 2022-06-10 |  | MS1 DONE | 2022-06-15 |  | 2022-06-14 |  |  |  |  | 2022-06-15 |  | Relocated |  | 2022-06-15 | TN/11/5177/0149/0043/04/01/16279/NS/15062022 | 2022-06-16 | [6 empty] | Yes | 2022-06-16 |  |  | 2022-06-14 |  |  | 2022-06-14 | Rahul | 2022-07-07 | 2022-07-12 |  | 2022-07-24 | 2022-07-12 |  | 2022-07-06 | 2022-07-11 | kuldeep | 2022-07-13 | 2022-07-17 |  | 2022-12-05 | 2022-10-24 | 2022-11-15 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-16
167 | TN | PATU15 | PATT3 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Tiruchirappalli | [6 empty] | 155-1042-68793185 | [6 empty] | Done | 2022-03-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-28 | 2022-03-02 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAY | May | 18307258 | 2022-03-08 | 2022-03-09 | 2022-03-09 |  | MS1 DONE | 2022-05-04 |  | 2022-05-04 |  |  |  |  | 2022-05-05 |  | Relocated |  | 2022-05-05 | TN/11/5113/00029/0043/04/01/16019/NS/05052022 | 2022-05-10 | [6 empty] | Yes | 2022-05-10 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-07-26 | 2022-07-30 |  | 2022-06-03 | 2022-07-30 |  | 2022-07-24 | 2022-07-29 | kuldeep | 2022-05-12 | 2022-05-16 |  | 2022-07-30 | 2022-07-16 | 2022-07-20 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-10
168 | TN | PDCRM4 | PDCRM3 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Namakkal | [6 empty] | 155-1138-27781648 | [6 empty] | Done | 2022-03-17 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-16 | 2022-05-10 |  | L900 |  | L900 | 4 | NA | RRU2219 B1*4 |  |  | JUN | JUN | 18870543 | 2022-06-03 | 2022-06-04 | 2022-06-04 |  | MS1 DONE | 2022-05-31 |  | 2022-05-31 |  |  |  |  | 2022-06-04 |  | Relocated |  | 2022-06-04 | TN/10/5428/0035/0043/04/01/16213/NS/04062022 | 2022-06-04 | [6 empty] | Yes | 2022-06-04 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-08-09 | 2022-08-12 |  | 2022-06-19 | 2022-08-12 |  | 2022-08-09 | 2022-08-14 | kuldeep | 2022-07-02 | 2022-07-06 |  | 2022-11-22 | 2022-10-24 | 2022-10-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-04
169 | TN | TIR482 | TIR49 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Tiruppur | [6 empty] | 155-1112-26773854 | [6 empty] | Done | 2022-04-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-01 | 2022-04-11 |  | L2100+L2300 |  | L2100+L2300 | 3+4 | NA | RRU4418*4+RRU2219 B1*3 |  |  | MAY | May | 18520041 | 2022-04-14 | 2022-04-15 | 2022-04-18 |  | MS1 DONE | 2022-05-26 |  | 2022-05-07 |  |  |  |  | 2022-05-07 |  | Relocated |  | 2022-05-08 | TN/01/5177/01663/0043/04/01/16026/NS/08052022 | 2022-05-10 | [6 empty] | Yes | 2022-05-10 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-08-03 | 2022-08-07 |  | 2022-06-03 | 2022-08-07 |  | 2022-07-28 | 2022-08-02 | kuldeep | 2022-05-12 | 2022-05-16 |  | 2022-08-07 | 2022-07-29 | 2022-08-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-10
170 | TN | SLM397 | SLM103 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Salem |  | MS1 DONE |  |  |  |  | 155-1165-24780956 | 2G+L1800+L2100+L2300 | [5 empty] | Done | 2022-04-13 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-12 | 2022-04-15 |  | L2100+L2300 |  | L2100+L2300 | 3+4 | NA | RRU4418*4+RRU2219 B1*3 |  |  | July | Jul | 18531469 | 2022-04-16 | 2022-04-17 | 2022-04-17 |  | MS1 DONE | 2022-04-26 |  | 2022-04-26 |  |  |  |  | 2022-05-21 |  | Relocated |  | 2022-07-04 | TN/10/0043/00028/0043/04/01/16379/NS/04072022 | 2022-07-04 | [6 empty] | Yes | 2022-07-04 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-07-26 | 2022-07-30 |  | 2022-07-25 | 2022-07-30 |  | 2022-07-22 | 2022-07-27 | kuldeep | 2022-05-20 | 2022-05-24 |  | 2022-04-26 | 2022-07-20 | 2022-07-20 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-07-04
171 | TN | STTPU7 | STTPU1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Thanjavur | [6 empty] | 155-1143-55795404 | [6 empty] | Done | 2022-04-09 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-08 | 2022-04-21 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAY | May | 18870727 | 2022-06-03 | 2022-06-04 | 2022-06-04 |  | MS1 DONE | 2022-05-13 |  | 2022-05-13 |  |  |  |  | 2022-05-16 |  | Relocated |  | 2022-05-17 | TN/02/5126/00145/0043/04/01/16097/NS/17052022 | 2022-05-27 | [6 empty] | Yes | 2022-05-27 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-07-25 | 2022-07-28 |  | 2022-06-12 | 2022-07-28 |  | 2022-08-28 | 2022-09-02 | kuldeep | 2022-05-20 | 2022-05-24 |  | 2022-09-08 | 2022-06-27 | 2022-07-01 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-17
172 | TN | MADM02 | MADM1 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Viluppuram |  | MS1 DONE |  |  |  |  | 155-1182-26793841 | 2G+L1800+L2300+L900 | [5 empty] | Done | 2022-04-15 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-15 | 2022-04-22 |  | L2100+L2300 |  | L2100+L2300 | 3+3 | NA | RRU4418*3+RRU2219 B1*3 |  |  | July | Jul | 19090929 | 2022-06-03 | 2022-06-04 | 2022-06-04 |  | MS1 DONE | 2022-07-05 |  | 2022-07-05 |  |  |  |  | 2022-07-05 |  | Relocated |  | 2022-07-06 | TN/02/5115/00146/0043/04/01/16391/NS/06072022 | 2022-07-07 | [6 empty] | Yes | 2022-07-07 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-07-23 | 2022-07-25 |  | 2022-07-25 | 2022-07-25 |  | 2022-07-20 | 2022-07-25 | kuldeep | 2022-09-20 | 2022-09-24 |  | 2022-11-22 | 2022-11-18 | 2022-10-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-07-07
173 | TN | BVGRI5 | BVGRI4 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Cuddalore | [6 empty] | 155-1144-22796422 | [6 empty] | Done | 2022-04-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-22 | 2022-05-02 |  | L2100+L2300 |  | L2100+L2300 | 4+3 | NA | RRU4418*3+RRU2219 B1*4 |  |  | MAY | May | 18748575 | 2022-05-23 | 2022-05-24 | 2022-05-25 |  | MS1 DONE | 2022-05-19 |  | 2022-05-21 |  |  |  |  | 2022-05-27 |  | Relocated |  | 2022-05-27 | TN/02/5177/00952/0043/04/01/16174/NS/27052022 | 2022-05-27 | [6 empty] | Yes | 2022-05-27 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-07-11 | 2022-07-12 |  | 2022-06-03 | 2022-07-12 |  | 2022-07-08 | 2022-07-13 | kuldeep | 2022-05-28 | 2022-06-01 |  | 2022-05-19 | 2022-10-12 | 2022-10-12 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-27
174 | TN | PNPM53 | PNPM5 | OK | CBE | Relocation | Huawei + MW |  |  | Coimbatore | [6 empty] | 155-1115-34769425 | [6 empty] | Done | 2022-04-26 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-26 | 2022-04-29 | [9 empty] | JUN | JUN | 18646160 | 2022-05-07 | 2022-05-08 | 2022-05-10 |  | MS1 DONE | 2022-06-14 |  | 2022-06-14 |  |  |  |  | 2022-06-15 |  | Relocated |  | 2022-06-15 | TN/01/5177/01673/0043/04/01/16280/NS/15062022 | 2022-06-19 | [6 empty] | Yes | 2022-06-19 |  |  | 2022-06-19 |  |  | 2022-06-19 | Rahul | 2022-08-16 | 2022-08-16 |  | 2023-01-20 | 2023-01-20 |  |  |  |  | Offered | Accepted |  | 2022-06-14 | 2022-07-16 | 2022-07-20 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-19
175 | TN | KDVAI2 | KDVAI1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore |  | MS1 DONE |  |  |  |  | 155-1094-08774393 | 2G+L1800+L2100+L2300 | [5 empty] | Done | 2022-04-26 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-26 | 2022-05-03 |  | L2100+L2300 |  | L2100+L2300 | 3+3 | NA | RRU4418*3+RRU2219 B1*3 |  |  | July | Jul | 18647573 | 2022-05-08 | 2022-05-09 | 2022-05-10 |  | MS1 DONE | 2022-07-03 |  | 2022-06-28 |  |  |  |  | 2022-07-03 |  | Relocated |  | 2022-07-04 | TN/04/5177/00460/0043/04/01/16381/NS/04072022 | 2022-07-04 | [6 empty] | Yes | 2022-07-04 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-08-17 | 2022-08-20 |  | 2022-07-25 | 2022-08-20 |  | 2022-08-19 | 2022-08-24 | kuldeep | 2022-10-27 | 2022-10-31 |  | 2022-11-26 | 2022-11-11 | 2022-11-15 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-07-04
176 | TN | CBE939 | CBE165 | OK | CBE | Relocation | Huawei + MW |  |  | Coimbatore | [6 empty] | 155-1098-96769480 | [6 empty] | Done | 2022-04-28 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-13 | 2022-04-29 | [9 empty] | MAY | May | 18646149 | 2022-05-07 | 2022-05-08 | 2022-05-25 |  | MS1 DONE | 2022-04-30 |  | 2022-04-30 |  |  |  |  | 2022-05-22 |  | Relocated |  | 2022-05-28 | TN/01/5177/1255/0043/04/01/16177/NS/28052022 | 2022-05-31 | [6 empty] | Yes | 2022-05-31 | [7 empty] | 2022-08-20 | 2022-08-23 |  | 2022-06-12 | 2022-08-23 |  | 2022-08-19 | 2022-08-23 |  | 2022-06-12 | 2022-08-23 |  | 2022-11-24 | 2022-09-25 | 2022-09-29 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-31
177 | TN | NGL141 | NGL49 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Kanniyakumari | [6 empty] | 155-0815-35774190 | [6 empty] | Done | 2022-05-18 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-20 | 2022-05-19 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | JUN | JUN | 75813 | 2022-05-26 | 2022-05-27 | 2022-05-27 |  | MS1 DONE | 2022-05-22 |  | 2022-05-22 |  |  |  |  | 2022-05-23 |  | Relocated |  | 2022-06-23 | TN/08/5126/00050/0043/04/01/16327/NS/23062022 | 2022-06-24 | [6 empty] | Yes | 2022-06-24 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-08-01 | 2022-08-05 |  | 2023-01-20 | 2023-01-20 |  | 2022-07-31 | 2022-08-05 | kuldeep | 2022-05-28 | 2022-06-01 |  | 2022-05-22 | 2022-10-24 | 2022-10-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-24
178 | TN | VSNRM2 | VSNRM1 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Namakkal | [6 empty] | 155-1120-44779868 | [6 empty] | Done | 2022-05-21 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-18 | 2022-05-24 |  | L900+L2300 |  | L900+L2300 | 3+3 | NA | RRU4418*2+RRU2219 B0*3 |  |  | JUN | JUN | 18911804 | 2022-06-07 | 2022-06-08 | 2022-06-08 |  | MS1 DONE | 2022-06-06 |  | 2022-06-06 |  |  |  |  | 2022-06-07 |  | Relocated |  | 2022-06-07 | TN/10/0043/00029/0043/04/01/16221/NS/07062022 | 2022-06-08 | [6 empty] | Yes | 2022-06-08 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-18 | 2022-06-23 |  | 2022-06-19 | 2022-06-23 |  | 2022-06-18 | 2022-06-23 |  | 2022-07-02 | 2022-07-06 |  |  | 2022-06-23 |  | Only KPI Pending | MAPA_Done | Only KPI Pending |  |  | 2022-06-08
179 | TN | MATTU3 | MATTU1 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Palani |  | MS1 DONE |  |  |  |  | 155-1047-63776189 | 2G+L1800+L2100+L2300+L900 | [5 empty] | Done | 2022-05-26 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-24 | 2022-05-28 |  | L900 |  | L900 | 3 | NA | RRU2219 B0*3 |  |  | July | Jul | 19090926 | 2022-07-01 | 2022-07-02 | 2022-07-04 |  | MS1 DONE | 2022-07-06 |  | 2022-07-07 |  |  |  |  | 2022-07-10 |  | Relocated |  | 2022-07-11 | TN/06/5177/01088/0043/04/01/16430/NS/11072022 | 2022-07-11 | [6 empty] | Yes | 2022-07-11 |  |  | 2022-07-11 |  |  | 2022-07-11 | Rahul | 2022-07-31 | 2022-08-11 |  | 2022-07-25 | 2022-08-11 |  | 2022-07-28 | 2022-08-02 | kuldeep | 2022-09-20 | 2022-09-24 |  | 2022-09-08 | 2022-07-21 | 2022-07-25 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-07-11
180 | TN | TRY382 | TRY203 | OK | TRY | Relocation | Huawei + Ericsson + MW |  |  | Tiruchirappalli | [6 empty] | 155-1082-15786981 | [6 empty] | Done | 2022-05-31 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-30 | 2022-06-01 |  | L2100+L2300 |  | L2100+L2300 | 3+3 | NA | RRU4418*3+RRU2219 B1*3 |  |  | JUN | JUN | 18911802 | 2022-06-07 | 2022-06-08 | 2022-06-08 |  | MS1 DONE | 2022-06-07 |  | 2022-06-10 |  |  |  |  | 2022-06-11 |  | Relocated |  | 2022-06-12 | TN/13/5428/0245/0043/04/01/16245/NS/12062022 | 2022-06-12 | [6 empty] | Yes | 2022-06-12 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-25 | 2022-06-27 |  | 2022-06-30 | 2022-06-27 |  | 2022-06-27 | 2022-07-02 | kuldeep | 2022-07-02 | 2022-07-06 |  | 2022-11-24 | 2022-10-08 | 2022-10-12 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-06-13
181 | TN | SLM402 | SLM128 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Salem | [6 empty] | 155-1167-22781000 | [6 empty] | Done | 2022-02-13 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-01-07 | 2022-02-15 |  | L2100+L2300 |  | L2100+L2300 | 4 | NA | RRU4418*6+RRU2219*5 |  |  | FEB | FEB | 18197047 | 2022-02-16 | 2022-02-17 | 2022-02-18 |  | MS1 DONE | 2022-02-18 |  | 2022-02-19 |  |  |  |  | 2022-02-22 |  | Relocated |  | 2022-02-22 | TN/10/5297/0122/0043/45/04/13782/NS/22022022 | 2022-03-03 | [6 empty] | Yes | 2022-02-22 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-03-05 | 2022-03-05 |  | 2022-03-10 | 2022-03-05 |  | 2022-06-23 | 2022-06-28 | kuldeep | 2022-02-22 | 2022-02-26 |  | 2022-08-09 | 2022-08-05 | 2022-08-09 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-02-22
182 | TN | VLR111 | VLR11 | OK | VLR | Relocation | Ericsson + MW |  |  | Vellore | [6 empty] | 155-1292-88791359 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-15 | 2022-03-01 |  | GL1800 |  | GL1800 | 4 | NA | RRU2279*4 |  |  | MAR | MAR | 18268721 | 2022-03-02 | 2022-03-03 | 2022-03-03 |  | MS1 DONE | 2022-03-04 |  | 2022-03-04 |  |  |  |  | 2022-03-05 |  | Relocated |  | 2022-03-05 | TN/15/5177/01982/0043/04/01/15681/NS/05032022 | 2022-03-07 | [6 empty] | Yes | 2022-03-05 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-08-25 | 2022-08-25 |  |  |  |  | 2022-08-20 | 2022-08-25 | kuldeep | 2022-04-03 | 2022-04-07 |  | 2022-03-28 | 2022-03-24 | 2022-03-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-05
183 | TN | SLM325 | SLM148 | OK | VLR | Relocation | Huawei + MW |  |  | Salem | [6 empty] | 155-1169-61780946 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2021-10-13 | 2022-02-28 | [9 empty] | MAR | MAR | 18277701 | 2022-03-02 | 2022-03-03 | 2022-03-03 |  | MS1 DONE | 2022-03-08 |  | 2022-03-08 |  |  |  |  | 2022-03-08 |  | Relocated |  | 2022-03-08 | TN/10/5428/0457/0043/04/01/15698/NS/08032022 | 2022-03-08 | [6 empty] | Yes | 2022-03-08 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-06-29 | 2022-07-02 |  | 2022-06-12 | 2022-07-02 |  | 2022-06-29 | Accepted |  | 2022-06-12 | 2022-07-02 |  | 2022-05-05 | 2022-05-01 | 2022-05-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-08
184 | TN | MLVTN4 | MLVTN1 | OK | MDU | Relocation | Huawei + Ericsson + MW |  |  | Tutucorin | [6 empty] | 155-0881-56780998 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-01-13 | 2022-03-04 |  | L900 |  | L900 | 3 | NA | RRU2219 B0*3 |  |  | MAR | MAR | 18295573 | 2022-03-05 | 2022-03-06 | 2022-03-08 |  | MS1 DONE | 2022-03-10 |  | 2022-03-10 |  |  |  |  | 2022-03-10 |  | Relocated |  | 2022-03-10 | TN/14/5177/01906/0043/04/01/15707/NS/10032022 | 2022-03-10 | [6 empty] | Yes | 2022-03-10 | [7 empty] | 2022-03-22 | 2022-03-23 |  | 2022-03-22 | 2022-03-23 |  | 2022-04-07 | 2022-04-12 | kuldeep | 2022-03-12 | 2022-03-16 |  | 2022-08-23 | 2022-08-19 | 2022-08-23 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-10
185 | TN | ISWRG4 | ISWRG1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Tiruppur | [6 empty] | 155-1115-83773004 | [6 empty] | Done | 2022-03-02 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-02 | 2022-03-04 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAR | MAR | 18297917 | 2022-03-06 | 2022-03-07 | 2022-03-08 |  | MS1 DONE | 2022-03-20 |  | 2022-03-09 |  |  |  |  | 2022-03-10 |  | Relocated |  | 2022-03-10 | TN/01/0043/00104/0043/04/01/15703/NS/09032022 | 2022-03-10 | [6 empty] | Yes | 2022-03-10 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-05-31 | 2022-06-05 |  | 2022-06-12 | 2022-06-05 |  | 2022-07-25 | 2022-07-30 | kuldeep | 2022-03-12 | 2022-03-16 |  | 2022-06-28 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-10
186 | TN | MMDUR4 | MMDUR1 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Chengalpet | [6 empty] | 155-1265-75799429 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-08 | 2022-03-03 |  | L900+L2300 |  | L900+L2300 | 3+3+4 | NA | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAR | MAR | 18295574 | 2022-03-05 | 2022-03-06 | 2022-03-07 |  | MS1 DONE | 2022-03-13 |  | 2022-03-12 |  |  |  |  | 2022-03-13 |  | Relocated |  | 2022-03-13 | TN/18/5115/00211/0043/04/01/15723/NS/13032022 | 2022-03-13 | [6 empty] | Yes | 2022-03-13 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul |  |  |  | 2022-04-06 | 2022-04-07 |  | 2022-03-17 | 2022-03-22 |  | 2022-03-18 | 2022-03-22 |  |  | 2022-10-12 | 2022-10-12 | Only Phy Pending |  | Only Phy Pending |  |  | 2022-03-13
187 | TN | SLM400 | SLM83 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Salem | [6 empty] | 155-1164-19781357 | [6 empty] | Done | 2022-03-11 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-11 | 2022-03-12 |  | L2100+L2300 |  | L2100+L2300 | 3+4 | NA | RRU4418*4+RRU2219 B1*3 |  |  | MAR | MAR | 18365599 | 2022-03-16 | 2022-03-16 | 2022-03-16 |  | MS1 DONE | 2022-02-05 |  | 2022-02-05 |  |  |  |  | 2022-03-13 |  | Relocated |  | 2022-03-13 | TN/10/5177/00839/0043/04/01/15724/NS/13032022 | 2022-03-13 | [6 empty] | Yes | 2022-03-13 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-06-28 | 2022-07-02 |  | 2022-03-21 | 2022-07-02 |  | 2022-06-26 | 2022-07-01 | kuldeep | 2022-03-18 | 2022-03-22 |  | 2022-05-05 | 2022-05-01 | 2022-05-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-13
188 | TN | KDKL45 | KDKL3 | OK | MDU | Relocation | Huawei + MW |  |  | Dindigul | [6 empty] | 155-1023-76774963 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2021-12-06 | 2022-03-05 | [9 empty] | MAR | MAR | 18337658 | 2022-03-11 | 2022-03-12 | 2022-03-14 |  | MS1 DONE | 2022-03-16 |  | 2022-03-15 |  |  |  |  | 2022-03-16 |  | Relocated |  | 2022-03-19 | TN/06/5177/01076/0043/04/01/15770/NS/16032022 | 2022-03-19 | [6 empty] | Yes | 2022-03-19 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-03-25 | 2022-03-26 |  | 2022-03-16 | 2022-03-26 |  | 2022-03-22 | 2022-03-26 | [7 empty] | Only KPI Pending |  | Only KPI Pending |  |  | 2022-03-19
189 | TN | WRGD13 | CWWRG | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Kancheepuram | [6 empty] | 155-1282-15799558 | [6 empty] | Done | 2022-02-27 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-27 | 2022-02-28 |  | L900 |  | L900 | 3 | NA | RRU2219 B0*3 |  |  | MAR | MAR | 18284917 | 2022-03-04 | 2022-03-04 | 2022-03-04 |  | MS1 DONE | 2022-03-17 |  | 2022-03-17 |  |  |  |  | 2022-03-19 |  | Relocated |  | 2022-03-19 | TN/18/5177/04010/0043/04/01/15776/NS/17032022 | 2022-03-19 | [6 empty] | Yes | 2022-03-19 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-04-14 | 2022-04-14 |  | 2022-03-21 | 2022-04-14 |  | 2022-04-09 | 2022-04-14 | kuldeep | 2022-03-18 | 2022-03-22 |  | 2022-04-26 | 2022-04-22 | 2022-04-26 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-19
190 | TN | TNPLM6 | TNPLM1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Erode | [6 empty] | 155-1150-58773860 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2021-12-03 | 2022-03-02 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+4+1 | NA | RRU4418*1+RRU2219 B1*3+RRU2219 B0*4 |  |  | MAR | MAR | 18298671 | 2022-03-06 | 2022-03-07 | 2022-03-08 |  | MS1 DONE | 2022-03-17 |  | 2022-03-15 |  |  |  |  | 2022-03-18 |  | Relocated |  | 2022-03-19 | TN/14/5177/1138/0043/04/01/15769/NS/16032022 | 2022-03-19 | [6 empty] | Yes | 2022-03-19 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-29 | 2022-07-02 |  | 2022-04-06 | 2022-07-02 |  | 2022-06-27 | 2022-07-02 |  | 2022-03-21 | 2022-03-25 |  | 2022-05-05 | 2022-05-01 | 2022-05-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-19
191 | TN | KLPTI6 | KLPTI2 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore | [6 empty] | 155-1106-69770464 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-03 | 2022-03-04 |  | L2100+L2300 |  | L2100+L2300 | 3+4 | NA | RRU4418*4+RRU2219 B1*3 |  |  | MAR | MAR | 18307259 | 2022-03-08 | 2022-03-08 | 2022-03-08 |  | MS1 DONE | 2022-03-19 |  | 2022-03-19 |  |  |  |  | 2022-03-19 |  | Relocated |  | 2022-03-19 | TN/01/5297/00699/0043/04/01/15802/NS/19032022 | 2022-03-19 | [6 empty] | Yes | 2022-03-19 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-24 | 2022-06-25 |  | 2022-03-21 | 2022-06-25 |  | 2022-05-12 | 2022-05-17 | kuldeep | 2022-05-09 | 2022-05-13 |  | 2022-05-05 | 2022-05-01 | 2022-05-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-19
192 | TN | TIPPA2 | TIPPA1 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Dharmapuri | [6 empty] | 155-1270-54778743 | [6 empty] | Done | 2022-03-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2021-08-26 | 2022-03-09 |  | L900+L2100 |  | L900+L2100 | 4+4 | NA | RRU2219 B1*4+RRU2219 B0*4 |  |  | MAR | MAR | 18364755 | 2022-03-15 | 2022-03-16 | 2022-03-18 |  | MS1 DONE | 2022-03-24 |  | 2022-03-22 |  |  |  |  | 2022-03-24 |  | Relocated |  | 2022-03-24 | TN/03/5177/00499/0043/04/01/15854/NS/23032022 | 2022-03-24 | [6 empty] | Yes | 2022-03-24 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-08-05 | 2022-08-09 |  | 2022-04-27 | 2022-08-09 |  | 2022-08-28 | 2022-09-02 | kuldeep | 2022-03-27 | 2022-03-31 |  |  | 2022-09-02 | 2023-02-01 | Only KPI Pending |  | Only KPI Pending |  |  | 2022-03-24
193 | TN | KMNPM3 | KMNPM1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Coimbatore | [6 empty] | 155-1089-58772077 | [6 empty] | Done | 2022-03-04 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-03 | 2022-03-15 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | NA | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3 |  |  | MAR | MAR | 18344501 | 2022-03-12 | 2022-03-13 | 2022-03-16 |  | MS1 DONE | 2022-03-23 |  | 2022-03-23 |  |  |  |  | 2022-03-24 |  | Relocated |  | 2022-03-24 | TN/01/5177/01657/0043/04/01/15856/NS/24032022 | 2022-03-24 | [6 empty] | Yes | 2022-03-24 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-28 | 2022-07-02 |  | 2022-04-13 | 2022-07-02 |  | 2022-08-01 | 2022-08-06 | kuldeep | 2022-03-27 | 2022-03-31 |  | 2022-12-09 | 2022-11-06 | 2022-11-10 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-24
194 | TN | KLMBD4 | KLMBD1 | OK | VLR | Relocation | Huawei + MW |  |  | Kancheepuram | [6 empty] | 155-1299-29798494 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-11 | 2022-03-09 | [9 empty] | MAR | MAR | 18400839 | 2022-03-22 | 2022-03-23 | 2022-03-24 |  | MS1 DONE | 2022-03-25 |  | 2022-03-25 |  |  |  |  | 2022-03-25 |  | Relocated |  | 2022-03-25 | TN/18/5177/04020/0043/04/01/15865/NS/25032022 | 2022-03-25 | [6 empty] | Yes | 2022-03-25 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-05-31 | 2022-06-05 |  | 2022-07-01 | 2022-07-05 |  | 2022-07-01 | 2022-07-05 |  | 2022-07-01 | 2022-07-05 |  | 2022-05-05 | 2022-05-01 | 2022-05-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-25
195 | TN | VENGA5 | VENGA1 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Erode | [6 empty] | 155-1110-46778776 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2021-12-08 | 2022-03-03 |  | L900+L2300 |  | L900+L2300 | 3+3 | NA | RRU4418*3+RRU2219 B0*3 |  |  | MAR | MAR | 18284918 | 2022-03-04 | 2022-03-05 | 2022-03-07 |  | MS1 DONE | 2022-04-14 |  | 2022-03-26 |  |  |  |  | 2022-03-26 |  | Relocated |  | 2022-03-26 | TN/04/5177/00453/0043/04/01/15867/NS/26032022 | 2022-03-26 | [6 empty] | Yes | 2022-03-26 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-06-21 | 2022-06-23 |  | 2022-04-27 | 2022-06-23 |  | 2022-07-21 | 2022-07-26 | kuldeep | 2022-03-27 | 2022-03-31 |  | 2022-11-26 | 2022-09-25 | 2022-09-29 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-03-26
196 | TN | IPYRN4 | IPYRN1 | OK | MDU | Relocation | Huawei + MW |  |  | Tutucorin | [6 empty] | 155-0918-56778904 | [6 empty] | Done | 2022-02-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-01-20 | 2022-03-07 | [9 empty] | MAR | MAR | 18344437 | 2022-03-12 | 2022-03-13 | 2022-03-15 |  | MS1 DONE | 2022-03-28 |  | 2022-03-26 |  |  |  |  | 2022-03-26 |  | Relocated |  | 2022-03-26 | TN/14/5177/0429/0043/04/01/15868/NS/26032022 | 2022-03-26 | [6 empty] | Yes | 2022-03-26 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-05-02 |  |  | 2022-05-03 | 2022-05-03 | [8 empty] | 2022-06-14 | 2022-06-14 | Only Phy Pending |  | Only Phy Pending |  |  | 2022-03-26
197 | TN | TIR355 | TIR44 | OK | CBE | Relocation | Huawei + Ericsson + MW |  |  | Tiruppur | [6 empty] | 155-1113-60773127 | [6 empty] | Done | 2022-03-04 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-09 | 2022-03-08 |  | L2100+L2300 |  | L2100+L2300 | 3+5 | NA | RRU4418*5+RRU2219*3 |  |  | MAR | MAR | 18434821 | 2022-03-28 | 2022-03-29 | 2022-03-29 |  | MS1 DONE | 2022-03-31 |  | 2022-03-29 |  |  |  |  | 2022-03-30 |  | Relocated |  | 2022-03-30 | TN/01/0043/00102/0043/04/01/15876/NS/30032022 | 2022-03-31 | [6 empty] | Yes | 2022-03-31 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-12-13 | 2022-07-02 |  | 2022-04-14 | 2022-07-02 |  | 2022-12-22 | 2022-12-27 |  | 2022-04-03 | 2022-04-07 |  |  | 2022-12-29 | 2022-12-29 | Only Phy Pending | MAPA_Done | Only Phy Pending |  |  | 2022-03-31
198 | TN | SLM378 | SLM134 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Salem | [6 empty] | 155-1166-51782191 | [6 empty] | Done | 2022-02-26 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-26 | 2022-02-27 |  | L900 |  | L900 | 3 | NA | RRU2219 B0*3 |  |  | APR | APR | 18280631 | 2022-03-03 | 2022-03-04 | 2022-03-04 |  | MS1 DONE | 2022-03-30 |  | 2022-03-30 |  |  |  |  | 2022-04-01 |  | Relocated |  | 2022-04-01 | TN/10/5177/00845/0043/04/01/15878/NS/31032022 | 2022-04-01 | [6 empty] | Yes | 2022-04-01 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-04-08 | 2022-04-10 |  | 2022-04-14 | 2022-04-10 |  | 2022-03-18 | 2022-03-23 | kuldeep | 2022-04-05 | 2022-04-09 |  | 2022-05-05 | 2022-05-01 | 2022-05-05 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-01
199 | TN | VADUG4 | VADUG1 | OK | VLR | Relocation | Ericsson + MW |  |  | Vellore | [6 empty] | 155-1296-21790163 | [6 empty] | Done | 2022-04-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-03 | 2022-04-04 |  | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | NA | RRU2219 B0*3+RRU2279*3 |  |  | APR | APR | 18493152 | 2022-04-08 | 2022-04-09 | 2022-04-09 |  | MS1 DONE | 2022-04-08 |  | 2022-04-08 |  |  |  |  | 2022-04-16 |  | Relocated |  | 2022-04-16 | TN/15/5428/0356/0043/04/01/15923/NS/14042022 | 2022-04-16 | [6 empty] | Yes | 2022-04-16 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-06-19 | 2022-06-19 |  |  |  |  | 2022-06-14 | 2022-06-19 | kuldeep | 2022-04-15 | 2022-04-19 |  | 2022-06-28 | 2022-06-24 | 2022-06-28 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-16
200 | TN | NRMPM3 | NRMPM1 | OK | MDU | Relocation | Huawei + MW |  |  | Tirunelveli | [6 empty] | 155-0876-00777383 | [6 empty] | Done | 2022-05-29 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-05-29 | 2022-05-30 | [9 empty] | APR | APR | 18870424 | 2022-06-03 | 2022-06-04 | 2022-06-04 |  | MS1 DONE | 2022-04-08 |  | 2022-04-08 |  |  |  |  | 2022-04-25 |  | Relocated |  | 2022-04-25 | TN/12/5177/00524/0043/04/01/16003/NS/25042022 | 2022-04-25 | [6 empty] | Yes | 2022-04-25 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-05-27 | 2022-05-30 |  | 2022-06-06 | 2022-05-30 |  | 2022-05-27 | Accepted |  | 2022-06-06 | 2022-05-30 |  | 2022-06-22 | 2022-06-18 | 2022-06-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-04-25
201 | TN | KDVPT2 | KDVPT1 | OK | MDU | Relocation | Ericsson + MW |  |  | Theni |  | MS1 DONE |  |  |  |  | 155-0997-03774900 | 2G+L1800+L2100+L2300+L900 | [5 empty] | Done | 2022-02-28 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-28 | 2022-03-01 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | NA | RRU2219 B1*3+RRU2219 B0*4+RRU4418*4 |  |  | July | Jul | 18295571 | 2022-03-05 | 2022-03-07 | 2022-03-07 |  | MS1 DONE | 2022-08-26 |  | 2022-08-26 |  |  |  |  | 2022-07-20 |  | Relocated |  | 2022-07-19 | TN/06/5297/0086/0043/04/01/16466/NS/19072022 | 2022-07-20 | [6 empty] | Yes | 2022-07-20 |  |  | 2022-07-20 |  |  | 2022-07-20 | Rahul | 2022-11-11 | 2022-11-11 |  | 2023-01-20 | 2022-10-31 |  | 2022-11-06 | 2022-11-11 | kuldeep | 2022-10-27 | 2022-10-31 |  |  | 2022-11-11 |  | Only KPI Pending |  | Only KPI Pending |  |  | 2022-07-20
202 | TN | KCP135 | KCPM5 | OK | VLR | Relocation | Huawei + Ericsson + MW |  |  | Kancheepuram | [6 empty] | 155-1282-25796988 | [6 empty] | Done | 2022-03-14 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-14 | 2022-03-21 |  | L2100+L2300 |  | L2100+L2300 | 3+6 | NA | RRU4418*6+RRU2219 B1*3 |  |  | MAY | May | 18468143 | 2022-04-21 | 2022-04-27 | 2022-04-28 |  | MS1 DONE | 2022-04-29 |  | 2022-04-29 |  |  |  |  | 2022-05-03 |  | Relocated |  | 2022-05-01 | TN/18/5177/04034/0043/04/01/16009/NS/01052022 | 2022-05-03 | [6 empty] | Yes | 2022-05-03 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-08-06 | 2022-08-15 |  | 2022-06-03 | 2022-08-15 |  | 2022-08-05 | 2022-08-10 | kuldeep | 2022-04-29 | 2022-05-03 |  | 2022-12-09 | 2022-10-08 | 2022-10-12 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-03
203 | TN | KKVDI2 | KKVDI1 | OK | MDU | Relocation | Huawei + MW |  |  | Virudhunagar | [6 empty] | 155-0940-39777207 | [6 empty] | Done | 2022-03-07 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-03-07 | 2022-03-08 | [9 empty] | MAY | May | 18344451 | 2022-03-12 | 2022-03-14 | 2022-03-14 |  | MS1 DONE | 2022-05-05 |  | 2022-05-05 |  |  |  |  | 2022-05-07 |  | Relocated |  | 2022-05-07 | TN/16/5177/00327/0043/04/01/16021/NS/06052022 | 2022-05-07 | [6 empty] | Yes | 2022-05-07 |  |  | 2022-06-15 |  |  | 2022-06-15 | Rahul | 2022-06-30 | 2022-07-02 |  | 2022-06-03 | 2022-07-02 |  | 2022-06-30 | Accepted |  | 2022-06-03 | 2022-07-02 |  | 2022-06-22 | 2022-06-18 | 2022-06-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-07
204 | TN | NKDYR5 | NKDYR1 | OK | CBE | Relocation | Huawei + MW |  |  | Tiruppur | [6 empty] | 155-1108-53776594 | [6 empty] | Done | 2022-04-24 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-24 | 2022-04-25 | [9 empty] | MAY | May | 18605740 | 2022-04-29 | 2022-05-03 | 2022-05-03 |  | MS1 DONE | 2022-04-26 |  | 2022-04-26 |  |  |  |  | 2022-05-03 |  | Relocated |  | 2022-05-03 | TN/01/5177/01662/0043/04/01/16010/NS/01052022 | 2022-05-03 | [6 empty] | Yes | 2022-05-03 |  |  | 2022-06-23 |  |  | 2022-06-23 | Rahul | 2022-06-28 | 2022-07-02 |  | 2022-06-06 | 2022-07-02 |  | 2022-06-28 | Accepted |  | 2022-06-06 | 2022-07-02 |  | 2022-06-22 | 2022-06-18 | 2022-06-22 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-05-03
205 | TN | DGL111 | DGL10 | OK | MDU | Relocation | Huawei + Ericsson |  |  | Dindigul |  | MS1 DONE |  |  |  |  | 155-1036-56779732 | 2G+L1800+L2100+L2300+L900 | [5 empty] | Done | 2022-07-07 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-07-07 | 2022-07-08 |  | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+6 | NA | RRU2219 B1*3+RRU2219 B0*3+RRU4418*6 |  |  | Aug | Jul | 19516315 | 2022-07-12 | 2022-07-12 | 2022-07-12 |  | MS1 DONE | 2022-07-21 |  | 2022-07-21 |  |  |  |  | 2022-07-26 |  | Relocated |  | 2022-07-18 | TN/06/5168/0007/0043/04/01/16462/NS/18072022 | 2022-07-26 | [6 empty] | Yes | 2022-07-26 |  |  | 2022-04-29 |  |  | 2022-04-29 | Rahul | 2022-08-21 | 2022-08-23 |  | 2022-07-26 | 2022-07-26 |  | 2022-08-27 | 2022-09-01 | kuldeep | 2022-07-22 | 2022-07-26 |  |  | 2022-09-01 |  | Only KPI Pending |  | Only KPI Pending |  |  | 2022-07-26
206 | TN | PRDI57 | PRDI4 | OK | CBE | Relocation | Huawei + MW |  |  | Erode | [6 empty] | 155-1127-84775880 | [6 empty] | Done | 2022-02-28 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-02-28 | 2022-03-01 | [9 empty] | MAR | MAR | 18295576 | 2022-03-05 | 2022-03-07 | 2022-03-07 |  | MS1 DONE | 2022-03-12 |  | 2022-03-12 |  |  |  |  | 2022-03-19 |  | Relocated |  | 2022-03-19 | TN/04/5177/00454/0043/04/01/15742/NS/15032022 | 2022-03-19 | [6 empty] | Yes | 2022-03-19 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul | 2022-05-28 | 2022-05-31 |  | 2022-03-21 | 2022-05-31 |  | 2022-05-28 | Accepted |  | 2022-03-21 | 2022-05-31 |  | 2022-08-02 | 2022-08-02 | 2022-08-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | #N/A
207 | TN | AYGDP2 | AYGD1 | OK | CBE | Relocation | Ericsson | Ayigoundanpalayam 2 | Sf.No.88/8a, Post: Ayikavundanpalayam Village, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638057 | Erode | GBT |  |  |  | 11.2812 | 77.528 | 155-1128-12775280 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Indus | CNIL / GTL | IN-3149540 |  | Done | 2022-11-24 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-24 | 2022-11-30 |  | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22517390 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-03 | Boss Management | 2023-01-03 | BOSS MANAGEMENT |  |  |  | 2023-01-03 |  | Relocated |  | 2023-01-07 | TN/04/5177/00495/0043/04/01/17447/NS/07012023 | 2023-02-07 | E.SENTHIL | [5 empty] | Yes | 2023-01-07 | 32 | [9 empty] | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  | 2023-01-19 | 2023-01-19 | Phy & Soft AT Pending |  | Phy & Soft AT Pending |  | CNIL Relocation | 2023-01-07
208 | TN | MUDPL2 | MUDL1 | OK | CBE | Relocation | Ericsson | Mudalipalayam 2 | Sf.No.427/2, Post: Mudalipalayam Village, Taluk: Vijaypuram, District: Tiruppur, State: Tamilnadu, Pincode-641606 | Tiruppur | GBT |  |  |  | 11.1077 | 77.4239 | 155-1110-77774239 | 2G+L1800+L2100+L2300+L900+TTB-B | CNIL / GTL | Indus | CNIL / GTL | IN-3149841 |  | Done | 2022-11-24 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-24 | 2022-12-08 | RS TELE | 2G+L1800+L2100+L2300+L900+TTB-B | 2G+L1800 | L2100+L2300+L900+TTB-B | 3 | done | 13 |  |  | Jan'23 | Jan'23 | 22517449 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-20 | Boss Management | 2023-01-20 | BOSS MANAGEMENT |  |  |  | 2023-01-22 |  |  |  | 2023-01-22 | TN/01/5177/01737/0043/04/01/17539/NS/22012023 | 2023-02-04 | E.SENTHIL | [5 empty] | Yes | 2023-01-22 | 32 | [12 empty] | 2023-01-30 |  |  | 2023-01-23 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-23
209 | TN | KRPUR2 | KRPUR2 | OK | VLR | Relocation |  | Karuppur 2 | Mr. Tharunvel, S/o. Vetrivel, Old S.No. 62/6, R.S.No. 62/6, present S.No. 283/13, Post: Karuppur Village, Taluk: Omalur, District: Salem, State: Tamilnadu, Pincode-636012 | Salem | GBT |  |  |  | 11.717 | 78.0927 | 155-1171-70780927 | 2G+L1800+L2100+L2300+L900+TTB-C | CNIL / GTL | ATC | CNIL / GTL | TN/SA/AT/23420 |  | Done | 2022-11-25 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2023-01-31 | SHYON | L2300+L2100+L1800+L900 | L1800 | L2100+L2300+L900 | 3 | done | 13 |  |  | Feb'23 | [6 empty] | Antenna & Power,Cpri Cables req | [20 empty] | Yes |  | 31 | [21 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
210 | TN | GUMNR2 | GUMNR1 | OK | VLR | Relocation | Ericsson | Gummanur 2 | Mr.Ramamoorthy, S.No. 174/2A & 2B, Post: Gummanur Village, Taluk: Rayakottai, District: Krishnagiri, State: Tamilnadu, Pinocde-635116 | Dharmapuri | GBT |  |  |  | 12.4491 | 78.0145 | 155-1244-91780145 | 2G+L1800+L2100+L900 | CNIL / GTL | ATC | CNIL / GTL | TN/DH/AT/23422 |  | Done | 2022-11-25 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2022-12-14 | ASHOK TEAM /ONCALL | 2G+L1800+L2100+L900 | 0 | 2G+L1800+L2100+L900 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22517417 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2023-01-09 | Boss Management | 2023-01-09 | BOSS MANAGEMENT |  |  |  | 2023-01-09 |  |  |  | 2023-01-12 | TN/03/5126/00150/0043/04/01/17484/NS/12012023 |  |  | 77 | Morethan 7 Days | 28 | Morethan 7 Days |  | Yes | 2023-01-13 | 31 |  | 2023-02-03 |  |  | 2023-02-03 |  |  |  |  | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-18 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-13
211 | CHN | VALU12 | VALU12 | OK | CHN | Relocation |  | #N/A | #N/A | Chennai | #N/A | [5 empty] | 152-1305-31802427 | 2G+L1800+L2100+L2300+L900(Don’t put L2100&L900 in 180) | INDUS | IN-1044332 | INDUS |  |  | Done | 2022-11-25 | High Opex (Circle) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2023-01-21 | SANJAY /ONCALL | 2G+L1800+L2100+L2300+L900(Don’t put L2100&L900 in 180) | - | UBR+L2300 | 3 | done | 6 |  |  | Feb'23 | [6 empty] | Survey Completed | [20 empty] | Yes |  | 31 | [21 empty] | Installation Pending |  |  |  | High Opex (Circle) | #N/A
212 | TN | SLM392 | SLM159 | OK | VLR | Relocation | Huawei | Uthukadu | Sf.No.70/4, Kumaran Nagar 1st St, Post: Dadagapatty, Taluk & District: Salem, State: Tamil Nadu, Pincode-636006 | Salem | GBT |  |  |  | 11.6371 | 78.1533 | 155-1163-71781533 | 2G+L1800+L2100+L2300 | BSNL | Indus | BSNL | IN-3133835 |  | Done | 2022-11-25 | BSNL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2022-12-01 |  | L2300+L2100+L1800 | L2300+L2100+L1800 | 0 | 3 | done | 9 |  |  | Jan'23 | Dec | 22460249 | 2022-12-22 | 2022-12-22 | 2022-12-23 |  | MS1 DONE | 2022-12-28 | Boss management | 2022-12-28 | BOSS MANAGEMENT |  |  |  | 2022-12-28 |  | Relocated |  | 2022-12-29 | TN/10/5177/00883/0043/04/01/17385/NS/29122022 |  |  | 77 | Morethan 7 Days | 43 | Morethan 7 Days |  | Yes | 2022-12-29 | 31 | [6 empty] | 2023-01-06 | 2023-01-09 |  | 2023-01-09 | 2023-01-09 | [10 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | BSNL Relocation | 2022-12-28
213 | TN | SLM419 | SLM419 | OK | VLR | Relocation |  | S.Nattamangalam post | Patta no.649, SF no. 54/1c, Nattamangalam Main Rd, P M P Nagar, Post: Kondalampatti, Taluk & District: Salem, State: Tamil Nadu, Pincode-636010 | Salem | GBT |  |  |  | 11.6206 | 78.1294 | 155-1162-06781294 | 2G+L1800+L2100+L2300+L900(Don’t put L2100 in 50) | Reliance | Indus | Reliance | IN-3152150 |  | Done | 2022-11-25 | Others |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2023-01-13 | Dhileep/Oncall | 2G+L1800+L2100+L2300+L900 | 2G+L1800+L2300 | L2100+L900 | 4 | done | 15 |  |  | Feb'23 | Jan'23 | 22643633 | 2023-01-13 | 2023-01-13 | 2023-01-14 |  |  | 2023-01-27 | Shyon Enterprises | 2023-01-27 | Shyon Enterprises |  |  |  | 2023-01-28 | [7 empty] | 77 | Morethan 7 Days | 12 | Morethan 7 Days |  | Yes | 2023-01-29 | 31 | [21 empty] | MS1 Pending |  |  |  | Others | 2023-01-29
214 | TN | SMUUR2 | SMUUR1 | OK | CBE | Relocation | Huawei + Ericsson | Semur 2 | Sf.No.75/1, No.188/A2, A3, Post: Semur village, Taluk: Avalpudurai, District: Erode, State: Tamilnadu, Pincode-638115 | Erode | GBT |  |  |  | 11.214 | 77.7567 | 155-1121-40777568 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | CNIL / GTL | IN-3149750 |  | Done | 2022-11-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2022-11-30 |  | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 9 |  |  | Dec | Dec | 22337871 | 2022-12-10 | 2022-12-10 | 2022-12-11 |  | MS1 DONE | 2022-12-17 | Boss management | 2022-12-17 | BOSS MANAGEMENT |  |  |  | 2022-12-17 |  |  |  | 2022-12-20 | TN/04/5177/00489/0043/04/01/17301/NS/20122022 | 2022-12-20 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-20 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2022-12-23 | 2022-12-25 |  | 2023-01-09 | 2022-12-25 |  | 2022-12-22 | 2022-12-27 |  | 2022-12-23 | 2022-12-25 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-12-20
215 | TN | KRVAM2 | KRVAM1 | OK | CBE | Relocation | Huawei + Ericsson | Koranvanpalayam 2 | Sf.No.270/2, 1186, Post: Nagadevampalayam Village, Taluk: Gopichettipalayam, District: Erode, State: Tamilnadu, Pincode-638476 | Erode | GBT | MS1 DONE |  |  | 11.4072 | 77.4698 | 155-MTNU-1677433 | 2G+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28711 | IN-3149771 |  | Done | 2022-11-27 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-28 | 2022-11-30 |  | 2G+L1800+L2300+L900 | L2300+L1800 | L900 | 3 | done | 9 |  |  | Dec | Dec | [5 empty] | MS1 DONE | 2022-12-04 | Shajofonica | 2022-12-05 | BOSS MANAGEMENT |  |  |  | 2022-12-05 |  | Relocated |  | 2022-12-06 | TN/04/5177/00478/0043/04/01/17233/NS/06122022 | 2022-12-06 | E.SENTHIL | [5 empty] | Yes | 2022-12-06 |  |  | 2022-12-29 |  |  | 2022-12-29 | Rahul | 2022-12-19 | 2022-12-23 |  | 2022-12-14 | 2022-12-23 |  | 2022-12-14 | 2022-12-19 |  | 2022-12-12 | 2022-12-16 |  | 2023-01-14 | 2022-12-15 | 2022-12-15 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-12-06
216 | TN | ACHNP2 | ACHNP1 | Link | MDU | Relocation |  | #N/A | #N/A | Thoothukkudi | GBT | [5 empty] | 155-0882-69778474 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Ascend | TAM/GBT/K/30900 | YET_TO_GENERATE |  | Done | 2022-11-29 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-27 | 2022-12-13 | ASHOK TEAM /ONCALL | 2G+L1800+L2100+L2300+L900 | L1800 | L2100+L2300+L900 | 3 | done | 12 |  |  | Feb'23 |  | 22568130 | 2023-01-05 | 2023-01-05 | 2023-01-05 |  | Workable | [20 empty] | Yes |  | 29 | [21 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
217 | TN | VLR135 | VLR73 | OK | VLR | Relocation | Huawei + Ericsson | Sathuvachrei - Anbu Nagar | Venkatesan, No.72, Piramana street, Post: Sathuvachari, Taluk & District: Vellore, State: Tamilnadu, Pincode-632009 | Vellore | GBT |  |  |  | 12.9402 | 79.1557 | 155-1294-02791557 | 2G+L1800+L2100+L2300+L900 | BSNL | TVI | 295 | - |  | Done | 2022-11-30 | Others |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-30 | 2022-11-30 |  | L2100+L2300 | 0 | L2100+L2300 | 3 | done | 4 |  |  | Jan'23 | Jan'23 | 22271207 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE | 2022-12-13 | RS Teletude | 2022-12-13 | RS Teletude |  |  |  | 2022-12-13 |  | Relocated |  | 2023-01-06 | TN/15/5113/00082/0043/04/01/17437/NS/06012023 |  |  | 72 | Morethan 7 Days | 34 | Morethan 7 Days |  | Yes | 2023-01-07 | 26 | [9 empty] | 2023-01-20 |  |  | 2023-01-09 | 2023-01-10 | [7 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Field visit required for rectification | 2023-01-07
218 | TN | SLM395 | SLM129 | OK | VLR | Relocation |  | Salem-Asthampatty | No.58/10, Seerangapalayam Road, Post: Kumarasamipatti, Taluk & District: Salem, State: Tamilnadu, Pincode-636007 | Salem | GBT |  |  |  | 11.6713 | 78.1544 | 155-1167-13781544 | 2G+L1800+L2100+L2300 | BSNL | TVI | 5491 | - |  | Done | 2022-11-30 | Others |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-30 | 2022-11-30 |  | 2G+L1800+L2100+L2300 | L1800+L2100+L2300 | - | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22271211 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE | 2023-01-04 | Shyon Enterprises | 2023-01-04 | Shyon Enterprises |  |  |  | 2023-01-04 |  | Relocated |  | 2023-01-05 | TN/10/5113/00115/0043/04/01/17430/NS/05012023 | 2023-01-22 | SATHISH | [5 empty] | Yes | 2023-01-05 | 26 | [6 empty] | 2023-01-23 | 2023-01-25 | [13 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Others | 2023-01-05
219 | TN | RSPM15 | RSPM5 | OK | VLR | Relocation | Huawei + Ericsson | Raalingam St, Rasipuram | Mrs. Sivakami J, Door No. 34/2, TS No 102, Paachi Street, Post & Taluk: Rasipuram, District: Namakkal, State: Tamilnadu, Pincode-637408 | Namakkal | RTT | MS1 DONE |  |  | 11.4605 | 78.1902 | 155-1146-05781902 | 2G+L1800+L2100+L2300+L900+TTB-A | BSNL | TVI | 2605 | - |  | Done | 2022-11-30 | BSNL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-30 | 2022-12-01 |  | L2300+L2100+L1800+L900 | L2300+L2100+L1800 | L900 | 3 | done | 12 |  |  | Dec | Dec | 22270989 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE | 2022-12-07 | Shajofonica | 2022-12-08 | BOSS MANAGEMENT |  |  |  | 2022-12-08 |  | Relocated |  | 2022-12-11 | TN/10/5113/00114/0043/04/01/17249/NS/11122022 | 2022-12-15 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-11 | [7 empty] | 2022-12-19 | 2022-12-23 |  | 2022-12-19 | 2022-12-23 |  | 2022-12-14 | 2022-12-19 |  | 2022-12-16 | 2022-12-20 |  | 2023-01-14 | 2022-12-13 | 2022-12-13 | MS2 Done | MAPA_Done | All 3 Accepted |  | BSNL Relocation | 2022-12-11
220 | TN | GUNDU3 | - | OK | TRY | NEW SITE | Huawei | Gundur | Sf.No.187/2a, Ayanpudur, Post: Gundur, Taluk & District: Trichy, State: Tamilnadu, Pincode-620007 | Tiruchirappalli | GBT | MS1 DONE | 10.7221 | 78.7355 | 10.7221 | 78.7355 | 155-1072-21787355 | 2G+L1800 | - | Indus | - | IN-3114578 | ECO | Done | 2022-11-01 | MS1 Done |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-01 | 2022-11-01 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 21854262 | 2022-11-03 | 2022-11-04 | 2022-11-05 |  | MS1 DONE |  |  | 2022-11-05 | BOSS MANAGEMENT |  |  |  | 2022-11-17 |  |  |  | 2022-11-18 |  | 2022-11-21 | E.SENTHIL | [5 empty] | Yes | 2022-11-18 | [7 empty] | 2022-11-23 | 2022-11-26 |  | 2022-11-22 | 2022-11-26 |  | 2022-11-22 | 2022-11-26 | [5 empty] | 2023-01-09 | 2023-01-09 | Only SOFT Pending |  | Only SOFT Pending |  | MS1 Done | 2022-11-18
221 | TN | KPNM06 | - | OK | VLR | NEW SITE | Huawei | KAVERI PATTINAM 6 | Sf.No.551/1a2, Post & Taluk: Kaveripattinam, District: Krishnagiri, State: Tamilnadu, Pincode-635112 | Krishnagiri | GBT | MS1 DONE |  |  | 12.4199 | 78.2218 | 155-1241-99782218 | 2G+L1800 | - | Indus |  | IN-3148266 | STANDARD_PRODUCT | Done | 2022-11-18 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-18 | 2022-11-18 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 22119677 | 2022-11-18 | 2022-11-19 | 2022-11-20 |  | MS1 DONE |  |  | 2022-11-21 | BOSS MANAGEMENT |  |  |  | 2022-11-25 |  |  |  | 2022-11-25 |  | 2023-01-22 | R.MANIKANDAN | [5 empty] | Yes | 2022-11-25 | [7 empty] | 2022-12-15 | 2022-12-04 |  | 2022-11-30 | 2022-12-04 |  | 2022-11-30 | 2022-12-04 | [7 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-11-25
222 | TN | MULKT2 | - | OK | VLR | NEW SITE | Huawei | Mullikulathur 2 | No.208, Sadras Main Road, Post: Anupuram, Taluk & District: Kanchipuram, State: Tamil Nadu, Pincode-603109 | Kancheepuram | GBT | MS1 DONE |  |  | 12.5751 | 80.1034 | 155-1257-51801033 | 2G+L1800 | - | Summit |  | I-TN-TRKD-ENB-9008 | STANDARD_PRODUCT | Done | 2022-11-19 | MS1 Done |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | 2022-11-19 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 22118645 | 2022-11-18 | 2022-11-19 | 2022-11-20 |  | MS1 DONE |  |  | 2022-11-21 | RS Teletude |  |  |  | 2022-11-24 |  |  |  | 2022-11-24 |  | 2022-11-29 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-24 | [7 empty] | 2022-12-01 | 2022-12-04 |  | 2022-12-17 | 2022-12-20 |  | 2022-11-30 | 2022-12-04 |  |  |  |  | 2023-01-28 | 2023-01-09 | 2023-01-09 | All 3 Accepted |  | All 3 Accepted |  | MS1 Done | 2022-11-24
223 | TN | STIRI2 | - | OK | TRY | NEW SITE | Huawei | Sathirai 2 | No.92, PT Rd, Post: Satharai, Taluk & District: Tiruvallur, State: Tamil Nadu, Pincode-631203 | Thiruvallur | GBT | MS1 DONE |  |  | 13.0567 | 79.8425 | 155-1305-67798424 | 2G+L1800 | - | Summit |  | I-TN-TVLR-ENB-9081 | Normal DG site | Done | 2022-11-19 | MS1 Done |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | 2022-11-19 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 22118693 | 2022-11-18 | 2022-11-19 | 2022-11-20 |  | MS1 DONE |  |  | 2022-11-21 | RS Teletude |  |  |  | 2022-11-24 |  |  |  | 2022-11-24 |  | 2022-11-30 | V.SIVA | [5 empty] | Yes | 2022-11-24 | [7 empty] | 2022-12-05 | 2022-12-09 |  | 2022-12-29 | 2022-12-30 |  | 2022-12-05 | 2022-12-09 |  | Offered | Accepted |  | 2023-01-14 | 2022-12-13 | 2022-12-13 | MS2 Done | MAPA_Done | All 3 Accepted |  | MS1 Done | 2022-11-24
224 | TN | PKT228 | - | OK | MDU | NEW SITE | Huawei | Nellai Nagaram | Mr.Govindarajulu,No.159, Nethaji Road, Thondarsannathi stop, Post: Lalugapuram, Nellai Nagaram, Taluk & District: Tirunelveli, State: Tamil Nadu, Pincode-627006,Ph-9942096178 | Tirunelveli | GBT |  |  |  | 8.7337 | 77.6869 | 155-0873-27776862 | 2G+L1800 | - | Ascend |  |  | ECO | Done | 2022-11-04 | - |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-04 | 2022-11-05 |  |  | GL1800 |  | 3 |  | 3 |  |  | Feb'23 |  | 21918807 | 2022-11-08 | 2022-11-08 | 2022-11-09 |  | Alarm/1 sec down, Public Issues |  |  | 2022-11-10 | BOSS MANAGEMENT |  |  |  | 2022-11-18 | [12 empty] | Yes |  | 52 | [21 empty] | MS1 Pending |  |  |  |  | #N/A
225 | TN | CBE658 | - | OK | CBE | NEW SITE | Huawei | Vadavalli | Mr.P.K.Haridas, No.486/2, Dr.sir.R.K.Shanmugam, CBR Nagar, Post: Vadavalli, Taluk & District: Coimbatore, State: Tamilnadu, Pincode-641007,Ph-9500233537 | Coimbatore | RTT | MS1 DONE |  |  | 11.0161 | 76.8852 | 155-1101-61768858 | 2G+L1800 | - | Ascend |  |  | Lite + | Done | 2022-11-18 | MS1 Done |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-18 | 2022-11-19 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 22118597 | 2022-11-18 | 2022-11-19 | 2022-11-20 |  | MS1 DONE |  |  | 2022-11-20 | BOSS MANAGEMENT |  |  |  | 2022-11-21 |  |  |  | 2022-11-23 |  | 2022-12-07 | E.SENTHIL | [5 empty] | Yes | 2022-11-23 |  | 2022-11-24 | [5 empty] | 2022-11-24 | 2022-11-27 |  | 2022-11-23 | 2022-11-27 |  | 2022-11-23 | 2022-11-27 | [5 empty] | 2022-12-13 | 2022-12-13 | Only SOFT Pending |  | Only SOFT Pending |  | MS1 Done | 2022-11-23
226 | TN | ILPUR4 | - | OK | TRY | NEW SITE | Huawei | Iluppur 4 | Mrs.V.Geetha, Sf.No.123/8-5, Sowrashtra, 3rd Street, Post: Illuppur, Taluk & District: Pudukkottai-622102,Ph-8883936890 | Pudukottai | GBT | MS1 DONE |  |  | 10.5206 | 78.6206 | 155-1052-06786206 | 2G+L1800 | - | Ascend |  |  | ECO | Done | 2022-11-04 | MS1 Done |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-04 | 2022-11-04 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 21938332 | 2022-11-08 | 2022-11-08 | 2022-11-09 |  | MS1 DONE |  |  | 2022-11-10 | BOSS MANAGEMENT |  |  |  | 2022-11-24 |  |  |  | 2022-11-24 |  | 2022-11-29 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-24 |  | 2022-11-24 | [5 empty] | 2022-11-28 | 2022-11-29 |  | 2023-01-20 |  |  | 2022-11-25 | 2022-11-29 | [5 empty] | 2022-12-13 | 2022-12-13 | Only SOFT Pending |  | Only SOFT Pending |  | MS1 Done | 2022-11-24
227 | TN | ATPLM2 | - | OK | VLR | NEW SITE | Huawei | Athipalaiyam 2 | Sf.No.80/3, Athipalayam village, Post: Sirumolasi, Taluk: Tiruchengode, District: Namakkal, State: Tamil Nadu, Pinocde-637214 | Namakkal | GBT | MS1 DONE |  |  | 11.336 | 77.8885 | 155-1133-60778885 | 2G+L1800 | - | Indus |  | IN-3152445 | ECO | Done | 2022-11-04 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-04 | 2022-11-04 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 22137659 | 2022-11-20 | 2022-11-20 | 2022-11-21 |  | MS1 DONE |  |  | 2022-11-22 | RS Teletude |  |  |  | 2022-11-25 |  |  |  | 2022-11-25 |  | 2022-12-26 | SATHISH | [5 empty] | Yes | 2022-11-25 | [7 empty] | 2022-12-27 | 2022-12-30 |  | 2022-12-29 | 2022-12-30 | [7 empty] | 2023-01-28 | 2022-12-13 | 2022-12-13 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-11-25
228 | TN | MYVAD2 | - | OK | CBE | NEW SITE | Huawei | Myvadi 2 | Mr. Kumar N, S/o. Nallamuthu, S.No. 140/7, as per Patta No. 2729 S.No. 140/7D, Post: Myvadi Village, Taluk: Madathukulam, District: Tiruppur, State: Tamilnadu, Pincode-642203 | Tiruppur | GBT | MS1 DONE |  |  | 10.5966 | 77.3161 | 155-1059-66773161 | 2G+L1800 | - | ATC |  | TN/TI/AT/23153 | CONTEMPORARY_LITE_PLUS | Done | 2022-11-19 | MS1 Done |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | 2022-11-19 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 22112880 | 2022-11-18 | 2022-11-19 | 2022-11-20 |  | MS1 DONE |  |  | 2022-11-21 | BOSS MANAGEMENT |  |  |  | 2022-11-24 |  |  |  | 2022-11-24 |  | 2022-12-14 | R.MANIKANDAN | [5 empty] | Yes | 2022-11-24 | [10 empty] | 2022-12-29 | 2022-12-30 | [8 empty] | 2022-12-13 | 2022-12-13 | Only Phy Pending |  | Only Phy Pending |  | MS1 Done | 2022-11-24
229 | TN | ADMBI3 | - | OK | TRY | NEW SITE | Huawei | Adambai South | Mr.V. Shanmugasundaram, Sf.No.22/3, East street, Post: Adambai south, Taluk: Pattukottai, District: Thanjavur, State: Tamilnadu, Pincode-614602,Ph-9786810657 | Thanjavur | GBT | MS1 DONE |  |  | 10.4468 | 79.2594 | 155-1044-68792594 | 2G+L1800 | - | Ascend |  |  | ECO | Done | 2022-11-19 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | 2022-11-20 |  |  | GL1800 |  | 3 |  | 3 |  |  | Nov | Nov | 22137084 | 2022-11-20 | 2022-11-20 | 2022-11-21 |  | MS1 DONE |  |  | 2022-11-21 | BOSS MANAGEMENT |  |  |  | 2022-11-25 |  |  |  | 2022-11-25 |  | 2022-11-30 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-25 | [7 empty] | 2022-12-01 | 2022-12-04 |  | 2022-12-29 | 2022-12-04 |  | 2022-11-30 | 2022-12-04 | [5 empty] | 2022-12-15 | 2022-12-15 | Only SOFT Pending |  | Only SOFT Pending |  |  | 2022-11-25
230 | TN | MNGLP2 | - | OK | VLR | NEW SITE | Huawei | Mogallipalli Gate | Mugalapalli, Post: Thummanapalli, Taluk: Hosur, District: Krishnagiri, State: Tamilnadu, Pincode-635105 | Krishnagiri | GBT | MS1 DONE |  |  | 12.8169 | 77.9172 | 155-1281-69779172 | 2G+L1800 | - | ATC |  | TN6029 | Sharing | Done | 2022-11-19 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-19 | 2022-11-20 |  |  | GL1800 |  | 4 |  | 4 |  |  | Dec | Nov | 22137235 | 2022-11-20 | 2022-11-20 | 2022-11-21 |  | MS1 DONE |  |  | 2022-11-27 | BOSS MANAGEMENT |  |  |  | 2022-11-27 |  |  |  | 2022-11-28 |  | 2022-12-08 | R.MANIKANDAN | [5 empty] | Yes | 2022-11-28 | [10 empty] | 2022-12-17 | 2022-12-20 | [8 empty] | 2022-12-20 |  | Phy & Soft & KPI AT Pending |  | Phy & KPI AT Pending |  |  | 2022-11-28
231 | TN | RSPM16 | - | OK | VLR | NEW SITE | Huawei | Pattanam 16 | Kolandayee W/o kailasan, Door no: 1/14, Pattanathar thottam, Post: Goundampalayam, Taluk: Rasipuram, District: Namakkal, State: Tamilnadu, Pincode-637408. Cnt no: 7904898355 | Namakkal | GBT | MS1 DONE |  |  | 11.4483 | 78.1704 | 155-1144-83781704 | 2G+L1800 | - | Summit |  | I-TN-RAZS-ENB-9002 | STANDARD_PRODUCT | Done | 2022-11-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-22 | 2022-11-22 |  |  | GL1800 |  | 4 |  | 4 |  |  | Nov | Nov | 22157433 | 2022-11-22 | 2022-11-23 | 2022-11-24 |  | MS1 DONE |  |  | 2022-11-25 | BOSS MANAGEMENT |  |  |  | 2022-11-25 |  |  |  | 2022-11-25 |  | 2022-12-06 | V.MANIKANDAN | [5 empty] | Yes | 2022-11-25 | [10 empty] | 2022-12-17 | 2022-12-20 | [8 empty] | 2022-12-06 | 2022-12-06 | Phy & Soft AT Pending |  | Only Phy Pending |  |  | 2022-11-25
232 | TN | MDKI24 | - | OK | CBE | NEW SITE | Huawei | Madukkarai 24 | Mr.Rakesh, No.12/314, Perumal Koil Street, Post: Madukarai, Taluk & District: Coimbatore, State: Tamilnadu, Pincode-641105. 96984-90903 | Coimbatore | GBT | MS1 DONE |  |  | 10.9109 | 76.9682 | 155-1091-09769682 | 2G+L1800 | - | Summit |  | I-TN-CMBR-ENB-0528 | STANDARD_PRODUCT | Done | 2022-11-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-22 | 2022-11-23 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22157052 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | MS1 DONE |  |  | 2022-11-25 | RS Teletude |  |  |  | 2022-12-16 |  |  |  | 2022-12-18 |  | 2023-01-03 | SATHISH | [5 empty] | Yes | 2022-12-18 | [7 empty] | 2023-01-09 | 2023-01-13 |  | 2023-01-09 | 2023-01-13 | [8 empty] | 2023-01-10 | 2023-01-10 | Only SOFT Pending |  | Only SOFT Pending |  |  | 2022-12-18
233 | TN | KURUV2 | - | OK | TRY | NEW SITE | Huawei | Kuruvadipatti | Sf.No.69/5, 69/6, Post: Kuruvadipatti village, Taluk & District: Thanjavur, State: Tamilnadu, Pincode-613601 | Thanjavur | GBT | MS1 DONE |  |  | 10.7528 | 79.0369 | 155-1075-28790369 | 2G+L1800 | - | Indus |  | IN-3132301 | ECO | Done | 2022-11-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-22 | 2022-11-23 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Nov | 22154111 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | MS1 DONE |  |  | 2022-11-24 | BOSS MANAGEMENT |  |  |  | 2022-11-25 |  |  |  | 2022-11-28 |  | 2022-12-12 | R.MANIKANDAN | [5 empty] | Yes | 2022-11-25 | [7 empty] | 2022-12-28 | 2023-01-01 |  | 2022-12-28 | 2023-01-01 | [10 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-11-29
234 | TN | TIR515 | - | OK | CBE | NEW SITE | Huawei | Kulathupalayam | Sf.No.180/2b, Post: Pazhangarai Village, Taluk: Avinashi, District: Tiruppur, State: Tamilnadu, Pincode-641652 | Tiruppur | GBT | MS1 DONE |  |  | 11.1814 | 77.3082 | 155-1118-13773082 | 2G+L1800 | - | Indus |  | IN-3146895 | ECO | Done | 2022-11-22 | - |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-22 | 2022-11-23 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22154129 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | MS1 DONE | 2022-11-27 | Shajofonica | 2022-11-27 | BOSS MANAGEMENT |  |  |  | 2022-12-12 |  | Relocated |  | 2022-12-12 |  | 2023-01-18 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-12 | [10 empty] | 2023-01-09 | [11 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  |  | 2022-12-12
235 | TN | VDSN10 | - | OK | MDU | NEW SITE | Huawei | Vedasandur 10 | Sf.No.1285/1b, Post & Taluk: Vedasanthur, District: Dindigul, State: Tamilnadu, Pincode-624710 | Dindigul | GBT | MS1 DONE |  |  | 10.5198 | 77.9434 | 155-1051-98779434 | 2G+L1800 | - | Indus |  | IN-3152807 | ECO | Done | 2022-11-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-22 | 2022-11-23 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22154138 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | MS1 DONE |  |  | 2022-11-25 | BOSS MANAGEMENT |  |  |  | 2022-12-16 |  |  |  | 2022-12-16 |  | 2023-01-27 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-16 | [7 empty] | 2022-12-27 | 2022-12-30 |  | 2023-01-09 | 2022-12-30 | [10 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-12-17
236 | TN | KRMDA2 | - | OK | CBE | NEW SITE | Huawei | Karamada 2 | Sf.No.996/5B1, Post: Marudur, Taluk: Mettupalayam, District: Coimbatore, State: Tamilnadu, Pincode-641104 | Coimbatore | GBT | MS1 DONE |  |  | 11.2376 | 76.9432 | 155-1123-76769431 | 2G+L1800 | - | Indus |  | IN-3152498 | ECO | Done | 2022-11-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-22 | 2022-11-23 |  |  | GL1800 |  | 4 |  | 4 |  |  | Dec | Nov | 22154091 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | MS1 DONE |  |  | 2022-11-27 | BOSS MANAGEMENT |  |  |  | 2022-11-27 |  |  |  | 2022-11-28 |  | 2022-12-07 | E.SENTHIL | [5 empty] | Yes | 2022-11-28 | [7 empty] | 2023-01-02 | 2023-01-03 |  | 2022-12-17 | 2022-12-20 | [7 empty] | 2023-01-28 | 2022-12-15 | 2022-12-15 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-11-28
237 | TN | CHNPK2 | - | OK | CBE | NEW SITE | Huawei | CN palayam | MR.SUBRAMANIYAN S/O.MR.RAMASAMY, SOUTH STREET, POST: PATEESWARAN, TALUK: CHENNAPPANAYAKKANPALAYAM, DISTRICT: CUDDALORE, STATE: TAMILNADU, PINCODE-607102. Ph-9952760050 | Erode | GBT | MS1 DONE |  |  | 11.7331 | 79.6027 | 155-1173-31796027 | 2G+L1800+L2300 | - | Ascend |  |  | ECO | Done | 2022-11-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2022-11-25 |  |  |  |  | 3 |  | 3 |  |  | Nov | Nov | 6144105 | 2022-11-21 | 2022-11-22 | 2022-11-22 |  | MS1 DONE |  |  | 2022-11-23 | BOSS MANAGEMENT |  |  |  | 2022-11-25 |  |  |  | 2022-11-25 |  | 2022-12-02 | V.SIVA | [5 empty] | Yes | 2022-11-25 | [7 empty] | 2022-12-05 | 2022-12-09 |  | 2022-12-17 | 2022-12-20 |  | 2022-12-05 | 2022-12-09 |  |  |  |  | 2023-01-28 | 2023-01-25 | 2023-01-25 | All 3 Accepted |  | All 3 Accepted |  |  | 2022-11-25
238 | TN | PDIRS2 | - | OK | CBE | NEW SITE | Huawei | Vadamugam | Sf.No.67/2, Post: Vadamugam Vellodu village, Taluk: Perundurai, Distirct: Erode, State: Tamilnadu, Pincode-638052 | Erode | GBT | MS1 DONE |  |  | 11.266 | 77.6119 | 155-1126-60776119 | 2G+L1800 | - | Indus |  | IN-3152251 | ECO | Done | 2022-11-22 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-22 | 2022-11-23 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22154115 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  | MS1 DONE |  |  | 2022-11-29 | RS Teletude |  |  |  | 2022-11-29 |  | Completed |  | 2022-12-01 |  | 2022-12-26 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-01 | [7 empty] | 2022-12-19 | 2022-12-23 |  | 2022-12-29 | 2022-12-30 |  |  |  |  | Offered | Accepted |  | 2023-01-14 | 2023-01-04 | 2023-01-04 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-12-01
239 | TN | ORND06 | - | OK | TRY | NEW SITE | Huawei | Orathanadu 6 | Mr. Nehru U S/o Uthirapathy, Sy No.415/3A, 415/3B, site No.19, Venkatarathinam Nagar, Post: Pudur Village, Taluk: Orathanadu, District: Thanjavur, State: Tamilnadu, Pincode-614625 | Thanjavur | GBT | MS1 DONE |  |  | 10.6202 | 79.2468 | 155-0991-40781331 | 2G+L1800 | - | ATC | - | TN/TA/AT/23543 | Contemporary lite Plus | Done | 2022-11-25 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-25 | 2022-11-26 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22231828 | 2022-11-29 | 2022-11-30 | 2022-11-30 |  | MS1 DONE |  |  | 2022-12-04 | BOSS MANAGEMENT |  |  |  | 2022-12-13 |  |  |  | 2022-12-13 |  | 2022-12-14 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-13 | [7 empty] | 2022-12-15 | 2022-12-18 |  | 2023-01-09 | 2022-12-18 | [8 empty] | 2023-01-09 | 2023-01-09 | Only SOFT Pending |  | Only SOFT Pending |  |  | 2022-12-14
240 | TN | MMPYM2 | - | OK | CBE | NEW SITE | Huawei | SRB | Mr.Moorthy, No:445, Ayyapalli, Post: Gangapuram, Taluk: Chithode, District: Erode, State: Tamilnadu, Pincode-638102. 85260-62224 | Coimbatore | GBT |  |  |  | 11.3703 | 77.6765 | 155-1137-03776765 | 2G+L1800 | - | Summit |  | I-TN-EROD-ENB-9092 | STANDARD_PRODUCT | Done | 2022-12-02 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-02 | 2022-12-03 | RS TELE |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22263003 | 2022-12-03 | 2022-12-03 | 2022-12-03 |  | MS1 DONE |  |  | 2022-12-05 | RS Teletude |  |  |  | 2022-12-19 |  |  |  | 2022-12-20 |  | 2023-01-21 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-20 | [7 empty] | 2022-12-27 | 2022-12-30 |  | 2023-01-09 | 2022-12-30 | [7 empty] | 2023-01-28 | 2023-01-25 | 2023-01-25 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-12-20
241 | TN | IDPD14 | - | OK | VLR | NEW SITE | Huawei | Saravana Tv Service Center | Mr.T.Ponnuvel, Amman Traders cement shop, Kattu valavu street, Post & Taluk: Idappadi, District: Salem, State: Tamilnadu, Pincode-637101. Ph-9842687178 | Salem | GBT |  |  |  | 11.5812 | 77.8308 | 155-1158-10778322 | 2G+L1800 | - | Ascend |  | IN-3153345 | ECO | Done | 2022-11-04 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-04 | 2022-11-05 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22281705 / 22281711 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE |  |  | 2022-12-13 | BOSS MANAGEMENT |  |  |  | 2022-12-19 |  |  |  | 2022-12-22 |  | 2023-01-09 | SATHISH | [5 empty] | Yes | 2022-12-22 | [10 empty] | 2023-01-09 | [11 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  |  | 2022-12-23
242 | TN | KUNTR2 | - | OK | VLR | NEW SITE | Huawei | agrapalayam 2 | Sf.No.17/3a, Post: Sevur Village, Taluk: Arani, District: Tiruvannamalai, State: Tamilnadu, Pincode-632314 | Tiruvannamalai | GBT | MS1 DONE |  |  | 12.691 | 79.2542 | 155-1269-09792541 | 2G+L1800 | - | Indus |  | IN-3153345 | ECO | Done | 2022-11-04 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-11-04 | 2022-11-05 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22281690 /22281699 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE |  |  | 2022-12-10 | RS Teletude |  |  |  | 2022-12-16 |  |  |  | 2022-12-18 |  | 2023-01-13 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-18 | [10 empty] | 2023-01-09 | [9 empty] | 2023-01-25 | 2023-01-25 | Phy & Soft AT Pending |  | Phy & Soft AT Pending |  |  | 2022-12-18
243 | TN | TMPKM2 | - | OK | CHN | NEW SITE | Huawei | Thamaaraipakkam 2 | No.455, Bharathi Nagar, Post: Edamedu, Taluk: Velliyur, District: Thiruvallur, State: Tamilnadu, Pincode-631561 | Thiruvallur | GBT |  |  |  | 13.2142 | 80.0193 | 155-1321-42800193 | 2G+L1800 | - | Summit |  | I-TN-TMPK-ENB-9002 | STANDARD_PRODUCT | Done | 2022-12-03 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-03 | 2022-12-04 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22282622 / 22282627 | 2022-12-05 | 2022-12-06 | 2022-12-06 |  | MS1 DONE |  |  | 2022-12-10 | RS Teletude |  |  |  | 2022-12-19 |  |  |  | 2022-12-22 |  |  |  | 69 | Morethan 7 Days | 50 | Morethan 7 Days |  | Yes | 2022-12-22 | [7 empty] | 2022-12-28 | 2023-01-01 |  | 2023-01-09 | 2023-01-01 | [10 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-12-23
244 | TN | CNPTU2 | CNPTU1 | OK | CBE | Relocation | Ericsson | Chinnapapanuthu 2 | Sf.No.1244, 200/2, Post: Periapappanuthu, Taluk: Udumalaipettai, District: Tiruppur, State: Tamil Nadu, Pincode-642132 | Tiruppur | GBT |  |  |  | 10.5654 | 77.1602 | 155-1056-54771602 | L900+L1800+L2100+TD | CNIL / GTL | Indus | TAM/GBT/K/31075 | YET_TO_GENERATE |  | Done | 2022-12-07 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-07 | 2022-12-19 | VICKY/ONCALL | 2G+L1800+L2100+L2300+L900 | 0 | 0 | 3 | done | 12 |  |  | Jan'23 | Jan'23 | 22686131 | 2023-01-19 | 2023-01-19 | 2023-01-19 |  | MS1 DONE | 2023-01-05 | SK Telecom | 2023-01-05 | SK Telecom |  |  |  | 2023-01-05 |  |  |  | 2023-01-08 | TN/01/5177/01731/0043/04/01/17457/NS/08012023 | 2023-02-05 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-08 | 19 |  | 2023-02-03 |  |  | 2023-02-03 |  | 2023-01-17 | 2023-01-22 |  | 2023-01-20 | 2023-01-22 |  | 2023-01-19 | 2023-01-24 |  | 2023-01-23 | 2023-01-23 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-08
245 | TN | UCHPT2 | - | OK | MDU | NEW SITE | Huawei |  |  |  |  | MS1 DONE |  |  |  |  | 155-0985-82780116 | GL1800 |  | Indus |  | - |  | Done | 2022-10-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | #N/A | 2022-10-05 |  |  |  |  | 3 |  |  |  |  | Oct | Oct | 21492920 | 2022-10-18 | 2022-10-18 | 2022-10-19 |  | MS1 DONE |  |  | 2022-10-19 | BOSS MANAGEMENT |  |  |  | 2022-10-25 |  |  |  | 2022-10-25 |  | 2022-10-27 | V.MANIKANDAN | [5 empty] | Yes | 2022-10-25 | [7 empty] | 2022-10-31 | 2022-11-04 |  | 2022-12-29 | 2022-12-30 |  | 2022-10-31 | 2022-11-04 |  | Offered | Accepted |  | 2023-01-14 | 2022-11-10 | 2022-11-10 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-10-25
246 | TN | KCP133 | - | OK | VLR | NEW SITE | Huawei |  |  |  |  | MS1 DONE |  |  |  |  | 155-1286-26796676 | G1800+L1800+L2300+L900 |  | Indus |  | IN-3127032 |  | Done | 2022-07-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | #N/A | 2022-07-01 | [9 empty] | July | Jul | 19348952 | 2022-07-02 | 2022-07-02 | 2022-07-03 |  | MS1 DONE |  |  | 2022-07-03 |  |  |  |  | 2022-07-07 |  |  |  | 2022-07-07 |  | 2022-07-07 | [6 empty] | Yes | 2022-07-07 | [7 empty] | 2022-07-18 | 2022-07-19 |  | 2022-08-08 | 2022-08-08 |  | 2022-08-08 | 2022-08-08 |  | Offered | Accepted |  | 2022-07-19 | 2022-07-18 | 2022-07-18 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-07-07
247 | TN | DGL120 | - | OK | MDU | NEW SITE | Huawei |  |  |  |  | MS1 DONE |  |  |  |  | 155-1038-76780058 | G1800+L1800+L2300+L900 |  | ATC |  | TN/DI/AT/23146 |  | Done | 2022-07-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | #N/A | 2022-07-01 | [9 empty] | July | Jul | 19348959 | 2022-07-02 | 2022-07-02 | 2022-07-03 |  | MS1 DONE |  |  | 2022-07-03 |  |  |  |  | 2022-07-11 |  |  |  | 2022-07-09 |  | 2022-07-11 | [6 empty] | Yes | 2022-07-11 | [7 empty] | 2022-10-12 | 2022-10-16 |  | 2022-08-02 | 2022-08-03 |  | 2022-10-12 | 2022-10-16 |  | 2022-07-30 | 2022-08-03 |  | 2022-12-24 | 2022-07-16 | 2022-07-20 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-07-11
248 | TN | MPRI25 | - | OK | TRY | NEW SITE | Huawei |  |  |  |  | MS1 DONE |  |  |  |  | 155-1061-33784077 | G1800+L1800+L2300+L900 |  | Indus |  | IN-3132383 |  | Done | 2022-07-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | #N/A | 2022-07-01 | [9 empty] | July | Jul | 19348968 | 2022-07-02 | 2022-07-02 | 2022-07-03 |  | MS1 DONE |  |  | 2022-07-03 |  |  |  |  | 2022-07-16 |  |  |  | 2022-07-16 |  | 2022-07-16 | [6 empty] | Yes | 2022-07-16 | [7 empty] | 2022-07-21 | 2022-07-25 |  | 2022-08-02 | 2022-08-03 |  | 2022-07-21 | 2022-07-25 |  | 2022-07-30 | 2022-08-03 |  | 2022-12-24 | 2022-07-29 | 2022-08-02 | MS2 Done | MAPA_Done | All 3 Accepted |  |  | 2022-07-16
249 | TN | TIR501 | - | OK | CBE | NEW SITE | Huawei |  |  | Tiruppur |  | MS1 DONE |  |  |  |  | 155-1111-72773052 | G1800+L1800+L2300+L900 |  | Indus |  | - |  | Done | 2022-07-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | #N/A | 2022-07-01 | [9 empty] | July | Jul | 19612957 | 2022-07-16 | 2022-07-16 | 2022-07-18 |  | MS1 DONE |  |  | 2022-07-18 | STCS |  |  |  | 2022-07-20 |  |  |  | 2022-07-19 |  | 2022-07-20 | [6 empty] | Yes | 2022-07-20 | [10 empty] | 2022-08-02 | 2022-08-03 | [8 empty] | 2022-10-12 | 2022-10-12 | Only Phy Pending |  | Only Phy Pending |  |  | 2022-07-20
250 | TN | NSNP6 | COW | Ok | CBE | Relocation | MW |  |  | Coimbatore | [6 empty] | 155-MTNU-1607201 | [6 empty] | Done | 2022-04-01 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-04-01 | 2022-04-03 | [9 empty] | APR | APR |  | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | MS1 DONE | 2022-04-12 | Shajofonica | 2022-04-13 | OWN TEAM |  |  |  | 2022-04-13 |  | Pending |  | 2022-04-13 |  | 2022-04-13 | [6 empty] | Yes | 2022-04-13 |  |  | 2022-07-18 |  |  | 2022-07-18 | Rahul |  |  |  | 2023-01-20 | [11 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  |  | #N/A
251 | TN | NLGDM2 | NLGDM1 | Ok | CBE | Relocation | Ericsson | Nalligoundam 2 | SF.No: 63, New:53/1-A, Post: Nalligoundenpalayam Village, Taluk: Uthukuli, Distirct: Tiruppur, State: Tamilnadu, Pincode-638110 | Tiruppur | GBT |  |  |  | 11.3159 | 77.3753 | 155-1131-59773753 | G1800+L1800+L2100+L900 | CNIL / GTL | Indus |  | IN-3149864 |  | Done | 2022-12-12 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-15 | 2022-12-18 | DHILEEP/ONCALL | 2G+L1800+L2100+L900 | L1800 | L900+L2100 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22517462 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2022-12-31 | Boss management | 2022-12-31 | BOSS MANAGEMENT |  |  |  | 2022-12-31 |  | Relocated |  | 2023-01-05 | TN/01/5177/01725/0043/04/01/17419/NS/04012023 | 2023-01-21 | SATHISH | [5 empty] | Yes | 2023-01-05 | [7 empty] | 2023-01-16 | 2023-01-19 |  | 2023-01-15 | 2023-01-19 |  | 2023-01-05 | 2023-01-10 |  | 2023-01-06 | 2023-01-08 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-05
252 | TN | SMJLM2 | SMJLM1 | Ok | CBE | Relocation | Huawei + Ericsson | Samrajpalayam 2 | Sf.No.173/1, Post: Vadamugam Kangayapalayam, Uthukuli, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638812 | Tiruppur | GBT |  |  |  | 11.2107 | 77.4549 | 155-1121-07774549 | G1800+L1800+L2300+L900 | CNIL / GTL | Indus |  | IN-3149814 |  | Done | 2022-12-12 | CNIL Free Exit Feasble Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-15 | 2022-12-18 | DHILEEP/ONCALL | 2G+L1800+L2300+L900 | L1800+L2300 | L900 | 2 | done | 6 |  |  | Jan'23 | Jan'23 | 22517485 | 2022-12-28 | 2022-12-28 | 2022-12-29 |  | MS1 DONE | 2022-12-30 | Boss management | 2022-12-30 | BOSS MANAGEMENT |  |  |  | 2022-12-30 |  | Relocated |  | 2023-01-01 | TN/04/5177/00492/0043/04/01/17398/NS/01012023 | 2023-01-07 | E.SENTHIL | [5 empty] | Yes | 2023-01-01 | [7 empty] | 2023-01-12 | 2023-01-15 |  | 2023-01-09 | 2023-01-15 |  | 2023-01-07 | 2023-01-12 |  | 2023-01-05 | 2023-01-06 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Free Exit Feasble Relocation | 2023-01-01
253 | TN | ARGI22 | - | Ok | TRY | NEW SITE | Huawei | Manamelkudi Road Aranthangi | Mrs.Mumthaj.A , D/o.Syed Mohamed, S.F.No.6/5, Post & Taluk: Aranthangi, District: Pudukottait, State: Tamilnadu, Pincode-614616 | Pudukottai | GBT |  |  |  | 10.1623 | 78.9878 | 155-1016-41789886 | 2G+L1800 | - | ATC |  | TN/PU/AT/22618 |  | Done | 2022-12-16 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-16 | 2022-12-16 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22371445/22368877 | 2022-12-14 | 2022-12-14 | 2022-12-16 |  | MS1 DONE |  |  | 2022-12-19 | BOSS MANAGEMENT |  |  |  | 2022-12-19 |  |  |  | 2022-12-21 |  | 2023-01-10 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-21 | [7 empty] | 2023-01-01 | 2023-01-02 |  | 2023-01-09 | 2023-01-02 | [8 empty] | 2022-12-27 | 2022-12-27 | Only SOFT Pending |  | Only SOFT Pending |  |  | 2022-12-21
254 | TN | PDY355 | PDY137 | Ok | TRY | Relocation |  | Bungalow street | Mrs .M.Anandhi - 9940667572, No.3, Kamaraj Salai, Post: Ilango Nagar, Taluk & District: Puducherry, State: Tamilnadu, Pincode-605001 | Pondy | RTT |  |  |  | 11.937 | 79.8242 | 15534-1193-70798242 | L900+L1800+L2100+TD | BSNL | Airtel | 527 |  |  | Done | 2022-12-15 | Operation Issues |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-15 | 2022-12-17 | R-WAVE TEAM |  |  |  |  | done |  |  |  | Feb'23 | [6 empty] | Full site materials req | [20 empty] | Yes | [23 empty] | Installation Pending |  |  |  | Operation Issues | #N/A
255 | TN | ARIUR2 | ARIUR2 | Ok | TRY | Relocation |  | ARIUR2 | Sf.No.126, 2nd Cross st, Post: Ariyur village, Taluk & District: Puducherry, State: Tamilnadu, Pincode-605110 | Pondy | GBT |  |  |  | 11.9067 | 79.7006 | 15534-1190-67797006 | L900+L1800+L2100+TD | Reliance | Indus | TN_PONDY_16 |  |  | Done | 2022-12-15 | Others |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-15 | 2022-12-17 | R-WAVE TEAM | 2G+L1800+L2100+L2300+L900 | L1800 | L900+L2100+L2300 | 4 | done | 14 |  |  | Feb'23 |  | 1003706 | 2023-01-19 | 2023-01-19 | 2023-01-19 |  | Antenna & Power,Cpri Cables req | [20 empty] | Yes | [23 empty] | Installation Pending |  |  |  | Others | #N/A
256 | TN | KUKLT2 | KUKLT2 | Ok | CBE | Relocation | Huawei + Ericsson | Kuralkottai 2 | Patta no.109, Post: Kurukalkuttai Village, Taluk: Udumalpet, District: Tiruppur, State: Tamilnadu, Pincode-642154 | Tiruppur | GBT |  |  |  | 10.5442 | 77.25 | 155-1054-42772500 | G1800+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/28767 |  |  | Done | 2022-12-16 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-16 | 2022-12-19 | VICKY/ONCALL | 2G+L1800+L2300+L900 | L1800 | L2300+L900 | 3 | done | 9 |  |  | Jan'23 | Dec | Done | Done | Done | Done |  | MS1 DONE | 2022-12-26 | Boss management | 2022-12-26 | BOSS MANAGEMENT |  |  |  | 2022-12-26 |  | Relocated |  | 2022-12-28 | TN/01/5177/01719/0043/04/01/17372/NS/27122022 | 2023-01-04 | SATHISH | [5 empty] | Yes | 2022-12-27 |  |  | 2023-02-03 |  |  | 2023-02-03 |  |  |  |  | 2023-01-09 | 2023-01-25 |  | 2023-01-01 | 2023-01-06 |  | 2023-01-05 | 2023-01-06 |  |  |  |  | Phy & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2022-12-26
257 | TN | CBE909 | - | Ok | CBE | NEW SITE | Huawei | #N/A | #N/A | Coimbatore | #N/A | [5 empty] | 155-1101-99770564 | G1800+L1800+L2300+L900 |  | ATC |  | TN/CO/AT/22984 |  | Done | 2022-12-18 | - |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-18 | 2022-12-10 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22392385 | 2022-12-16 | 2022-12-16 | 2022-12-19 |  | MS1 DONE |  |  | 2022-12-19 | RS Teletude |  |  |  | 2022-12-22 |  | Relocated |  | 2022-12-25 |  | 2023-01-13 | V.MANIKANDAN | [5 empty] | Yes | 2022-12-25 | [7 empty] | 2022-12-28 | 2023-01-01 |  | 2023-01-09 | 2023-01-01 | [10 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-12-25
258 | TN | GOBI43 | - | Ok | CBE | NEW SITE | Huawei | Gobichettipalayam 43 | Mr.Paramasivam, Manikarar thottam, Kollampalayam, Post: Kalikam, Taluk: Gobichettipalayam, District: Erode, State: Tamilnadu, Pincode-638452 | Erode | GBT |  |  |  | 11.443 | 77.4141 | 155-1144-30774141 | 2G+L1800 |  | Summit |  | I-TN-GBPM-ENB-0015 |  | Done | 2022-12-18 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-18 | 2022-12-18 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22419575/22419585 | 2022-12-19 | 2022-12-19 | 2022-12-20 |  | MS1 DONE |  |  | 2022-12-20 | BOSS MANAGEMENT |  |  |  | 2022-12-24 |  |  |  | 2022-12-24 |  | 2022-12-30 | SATHISH | [5 empty] | Yes | 2022-12-24 | [7 empty] | 2022-12-27 | 2022-12-30 |  | 2023-01-09 | 2022-12-30 | [7 empty] | 2023-01-28 | 2023-01-09 | 2023-01-09 | MS2 Done | MAPA_Done | Only KPI Pending |  |  | 2022-12-24
259 | TN | THOZR3 | - | Ok | VLR | NEW SITE | Huawei | Thottikalai 3 | Mrs.S.SELVI, SF.No: 50/7 D.No:114, Chelliamman Nagar, Post: Aiyathoor,VEPPAMPATTU, District: Thiruvallur, State: Tamilnadu, Pincode-602024. Ph-9790863881,6369004711 | Thiruvallur | GBT |  |  |  | 13.1464 | 79.9855 | 155-1314-64799855 | 2G+L1800 |  | Ascend |  |  |  | Done | 2022-12-18 | - |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-18 | 2022-12-18 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22420346/22420344 | 2022-12-19 | 2022-12-19 | 2022-12-20 |  | MS1 DONE |  |  | 2022-12-20 | R WAVE |  |  |  | 2022-12-25 |  | Relocated |  | 2022-12-25 |  |  |  | 54 | Morethan 7 Days | 47 | Morethan 7 Days |  | Yes | 2022-12-25 | [10 empty] | 2023-01-09 | [11 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  |  | 2022-12-25
260 | TN | SLM376 | - | Ok | VLR | NEW SITE | Huawei | Narasothipatti | Mr. Rathinam P S/o Perumal, Sy.No.36/6, Post: Narasothipatti Village, Taluk: Sooramangalam SRO, District: Salem, State: Tamilnadu, Pincode-636004 | Salem | GBT |  |  |  | 11.6903 | 78.1325 | 155-1169-03781326 | 2G+L1800 |  | ATC |  | TN/SA/AT/23064 | CONTEMPORARY_LITE_PLUS | Done | 2022-12-19 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-19 | 2022-12-19 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22419575 | 2022-12-19 | 2022-12-20 | 2022-12-21 |  | MS1 DONE |  |  | 2022-12-22 | BOSS MANAGEMENT |  |  |  | 2022-12-24 |  |  |  | 2022-12-24 |  | 2023-01-06 | SATHISH | [5 empty] | Yes | 2022-12-24 | [10 empty] | 2023-01-09 | [9 empty] | 2023-01-19 | 2023-01-19 | Phy & Soft AT Pending |  | Phy & Soft AT Pending |  |  | 2022-12-24
261 | TN | ARNI15 |  | Ok | VLR | NEW SITE | Huawei | AraniPalayam | Mr.M.Gunalan S/O Mr.Jayavelu, No.13/47, Police station Street, Arani Palayam, Post & Taluk: Arani, District: Tiruvannamalai, State: Tamil Nadu, Pincode-632301 | Tiruvannamalai | GBT |  |  |  | 12.6732 | 79.289 | 155-1267-38792894 | 2G+L1800 |  | Ascend |  |  | Lite + | Done | 2022-12-19 | - |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-19 | 2022-12-19 |  |  | GL1800 |  | 3 | done | 3 |  |  | Jan'23 | Jan'23 | 22432572/22432575 | 2022-12-19 | 2022-12-20 | 2022-12-21 |  | MS1 DONE |  |  | 2022-12-22 | R WAVE |  |  |  | 2022-12-27 |  | Relocated |  | 2022-12-27 |  | 2022-12-30 | V.SIVA | [5 empty] | Yes | 2022-12-27 | [10 empty] | 2023-01-09 | 2023-01-25 | [8 empty] | 2023-01-19 | 2023-01-19 | Phy & KPI AT Pending |  | Phy & KPI AT Pending |  |  | 2022-12-25
262 | TN | VLLUR9 | - | Ok | CBE | NEW SITE | Huawei | Kanjikonaampalayam | SF No:265, Item No:3, Vellalore, Post: Kanjikonaampalayam, Taluk & District: Coimbatore, State: Tamil Nadu, Pincode-641016 | Coimbatore | GBT |  |  |  | 10.968 | 77.0259 | 155-1096-80770259 | 2G+L1800 |  | Indus |  | IN-3152390 |  | Done | 2022-12-19 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-19 | 2022-12-19 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22350295 | 2022-12-14 | 2022-12-14 | 2022-12-16 |  | MS1 DONE |  |  | 2022-12-19 | RS Teletude |  |  |  | 2022-12-19 |  |  |  | 2022-12-21 |  | 2023-01-21 | E.SENTHIL | [5 empty] | Yes | 2022-12-21 | [7 empty] | 2023-01-02 | 2023-01-03 |  | 2023-01-09 | 2023-01-03 | [8 empty] | 2023-01-09 | 2023-01-09 | Only SOFT Pending |  | Only SOFT Pending |  |  | 2022-12-21
263 | TN | ILUPR2 | - | Ok | TRY | NEW SITE | Huawei | Iluppur 2 | Sf.No.54/9, Plot Nos.27 and 28, Post: Punginipatti Village, Taluk: Annavasal, District: Pudukottai, State: Tamilnadu, Pincode-622102 | Pudukottai | GBT |  |  |  | 10.5204 | 78.633 | 155-1052-04786330 | 2G+L1800 |  | Indus |  | IN-3152810 |  | Done | 2022-12-19 | - |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-20 | 2022-12-20 |  |  | GL1800 |  | 3 |  | 3 |  |  | Dec | Dec | 22442850/22442867 | 2022-12-20 | 2022-12-21 | 2022-12-21 |  | MS1 DONE |  |  | 2022-12-22 | BOSS MANAGEMENT |  |  |  | 2022-12-25 |  | Relocated |  | 2022-12-25 |  | 2023-01-14 | R.MANIKANDAN | [5 empty] | Yes | 2022-12-25 | [7 empty] | 2023-01-07 | 2023-01-08 |  | 2023-01-09 | 2023-01-08 | [10 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2022-12-25
264 | TN | ASUR14 |  | Ok | CBE | NEW SITE | Huawei | Arasur To Annur Link Rd | Mr.S.Palanisamy,S/o.Subbana Gounder, No:57/1, Post: Karungadu, Annur Main Road, Arasur East, Taluk & District: Coimbatore, State: Tamilnadu, Pincode-641401. 93624-70384 | Coimbatore | GBT |  |  |  | 11.0941 | 77.1244 | 155-1109-41771244 | 2G+L1800 |  | Summit |  | I-TN-CMBR-ENB-0611 |  | Done | 2022-12-19 | - |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-20 | 2022-12-20 |  | 0 | GL1800 | 0 | 3 | done | 3 |  |  | Jan'23 | Jan'23 | 22442813/22442829 | 2022-12-20 | 2022-12-21 | 2022-12-24 |  | MS1 DONE |  |  | 2022-12-24 | BOSS MANAGEMENT |  |  |  | 2023-01-10 |  |  |  | 2023-01-11 |  | 2023-01-21 | E.SENTHIL | [5 empty] | Yes | 2023-01-11 | [7 empty] | 2023-01-17 | 2023-01-22 |  | 2023-01-20 | 2023-01-22 | [10 empty] | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  |  | 2023-01-11
265 | TN | KANUR2 | KANR1 | Ok | TRY | Relocation | Ericsson | #N/A | #N/A | Cuddalore | #N/A | [5 empty] | 155-1139-86794691 | G1800+L1800+L2300+L900 | CNIL / GTL | Ascend |  | - |  | Done | 2022-12-17 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-17 | 2022-12-30 | ANAND/ONCALL | 2G+L1800+L2300+L900 | GL1800 | L2300+L900 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22249079 | 2022-12-02 | 2022-12-02 | 2022-11-29 |  | MS1 DONE | 2023-01-08 | Shajofonica | 2023-01-08 | Shajofonica |  |  |  | 2023-01-08 |  |  |  | 2023-01-09 | TN/02/5115/00168/0043/04/01/17462/NS/09012023 | 2023-02-02 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-09 | [7 empty] | 2023-01-23 | 2023-01-25 |  | 2023-01-20 |  |  | 2023-01-12 | 2023-01-17 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-09
266 | TN | PALTU3 | PALTU1 | OK | CBE | Relocation | Ericsson | Palliuthu 3 | No.981/2A, Palliyuthu main st, Post: Avalpoondurai Village, Taluk & District: Erode, State: Tamilnadu, Pincode-638101 | Erode | GBT |  |  |  | 11.1943 | 77.7036 | 155-1119-43777037 | G1800+L1800+L2300+L900 | CNIL / GTL | Indus | TAM/GBT/K/30170 | IN-3149845 |  | Done | 2022-12-18 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-18 | 2022-12-27 | O&M/ONCALL | 2G+L1800+L2300+L900 | L1800 | L900+L2300 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | [5 empty] | MS1 DONE | 2023-01-04 | Boss Management | 2023-01-04 | BOSS MANAGEMENT |  |  |  | 2023-01-04 |  | Relocated |  | 2023-01-06 | TN/04/5177/00498/0043/04/01/17436/NS/06012023 | 2023-01-20 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-07 | [7 empty] | 2023-01-17 | 2023-01-22 |  | 2023-01-20 | 2023-01-22 |  | 2023-01-14 | 2023-01-19 |  | 2023-01-19 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-07
267 | TN | GRYNR2 | GRYNR1 | OK | CBE | Relocation | Ericsson | Gray Nagar 2 | Sf.No.180, 45/1, Post: Karandipalayam Village, Taluk: Perundurai, District: Erode, State: Tamilnadu, Pincode-638057 | Erode | GBT |  |  |  | 11.2843 | 77.4886 | 155-1128-44774886 | L900+L1800+L2100+TD | GTL | Indus | TAM/GBT/K/28343 | IN-3149494 |  | Done | 2022-12-19 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-19 | 2022-12-27 | O&M/ONCALL | 2G+L1800+L2100+L2300+L900 | L1800 | L2300+L2100+L900 | 3 | done | 11 |  |  | Jan'23 | Jan'23 | 22588437 | 2023-01-07 | 2023-01-07 | 2023-01-09 |  | MS1 DONE | 2023-01-10 | Shyon Enterprises | 2023-01-10 | Shyon Enterprises |  |  |  | 2023-01-10 |  |  |  | 2023-01-12 | TN/04/5177/00500/0043/04/01/17485/NS/12012023 | 2023-01-22 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-13 |  |  | 2023-02-03 |  |  | 2023-02-03 |  |  |  |  | 2023-01-20 |  |  | 2023-01-14 | 2023-01-19 |  | 2023-01-18 | 2023-01-19 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | CNIL Relocation | 2023-01-13
268 | TN | TKREC2 | TKREC1 |  | CBE | Relocation | Ericsson | T.K.Raja Educational institues | Sf.No.801/4, 222, Post: Adhiyur Village, Taluk & District: Tirupathur, State: Tamilnadu, Pincode-635602 | Vellore | GBT |  |  |  | 12.4645 | 78.5666 | 155-1246-45785666 | L900+L1800+L2100+TD | INDUS | Indus |  | IN-3153666 |  | Done | 2022-12-19 | Operation Issues |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-19 | 2023-01-03 | GOPI/INHOUSE | 2G+L1800+L2100+L2300+L900 | NA | L900+UBR+L2300 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22588536 | 2023-01-06 | 2023-01-06 | 2023-01-10 |  | MS1 DONE | 2023-01-11 | RS Teletude | 2023-01-11 | RS Teletude |  |  |  | 2023-01-15 |  |  |  | 2023-01-14 | TN/15/5177/02013/0043/04/01/17501/NS/14012023 |  |  | 53 | Morethan 7 Days | 26 | Morethan 7 Days |  | Yes | 2023-01-15 |  |  | 2023-02-03 |  |  | 2023-02-03 |  |  |  |  | 2023-01-20 | [5 empty] | 2023-01-23 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Operation Issues | 2023-01-15
269 | TN | RMPUR2 | RMPR1 |  | CBE | Relocation |  | R.M.Pudur 2 | No.146/2, No. 89, Post: Thensangampalayam Village, Taluk: Pollachi, District: Coimbatore, State: Tamilnadu, Pincode-642134 | Coimbatore | GBT |  |  |  | 10.5563 | 76.9675 | 155-1055-63769675 | G1800+L1800+L2300+L900 | GTL | Indus |  | IN-3149812 |  | Done | 2022-12-20 | CNIL Relocation | [6 empty] | Yes | Yes | Yes | 2022-12-20 | 2023-01-24 | SK TEAM | 2G+L1800+L2300+L900 | L1800 | L900+L2300 | 3 | done | 9 |  |  | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
270 | TN | SHPDU2 | SHPD1 |  | CBE | Relocation | Ericsson | Shellappagoundanvalasu 2 | Sf.No.114/2 and 3, Post: Sellappagoundenvalasu, Pethampalayam, Taluk: Perundurai, District: Erode, State: Tamil Nadu, Pincode-638052 | Erode | GBT |  |  |  | 11.3268 | 77.5901 | 155-1132-68775901 | G1800+L1800+L2300+L900 | GTL | Indus |  | IN-3149840 |  | Done | 2022-12-21 | CNIL Relocation | [6 empty] | Yes | Yes | Yes | 2022-12-21 | 2022-12-28 | SANTHOSH/ONCALL | 2G+L1800+L2300+L900 | 2G+L1800 | L2300+L900 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22627326 | 2023-01-12 | 2023-01-12 | 2023-01-12 |  | MS1 DONE | 2023-01-19 | Shyon Enterprises | 2023-01-19 | Shyon Enterprises |  |  |  | 2023-01-22 |  |  |  | 2023-01-20 | TN/04/5177/00502/0043/04/01/17520/NS/20012023 | 2023-02-06 | E.SENTHIL | [5 empty] | Yes | 2023-01-22 |  |  | 2023-02-03 |  |  | 2023-02-03 | [16 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Need to check for offering | 2023-01-22
271 | TN | NMKL63 | NKL23 | OK | CBE | Relocation | Ericsson | Near Golden Palace | Mrs.Saranya.KS W/o.Balasubramanian, Sy.No.6/391, Post: Andavar Nagar, Taluk & District: Namakkal, State: Tamil Nadu, Pincode-637002 | Namakkal | RTT |  |  |  | 11.2104 | 78.1817 | 155-1121-04781817 |  | BSNL | ATC | 2595 |  |  | Done | 2022-12-24 | Others |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-24 | 2022-12-28 | DHILEEP/ONCALL | 2G+L1800+L2100+L2300+L900+FSA+TSA | L1800+L2100+L2300 | L900 | 3 | done | 15 |  |  | Jan'23 | Jan'23 | Done | Done | Done | Done |  | MS1 DONE | 2022-12-31 | BOSS MANAGEMENT | 2022-12-31 | BOSS MANAGEMENT |  |  |  | 2022-12-31 |  | Relocated |  | 2023-01-05 | TN/10/5126/00292/0043/04/01/17414/NS/04012023 | 2023-01-03 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-05 | [10 empty] | 2023-01-20 |  |  | 2023-01-03 | 2023-01-08 |  | 2023-01-06 | 2023-01-08 |  |  | 2023-01-08 | 2023-01-08 | Phy AT Pending |  | Phy & Soft AT Pending |  | Others | 2023-01-05
272 | TN | KGRI44 | KGRI13 | Ok | VLR | Relocation |  | NewPet,Krishnagiri | S.F.No.934/1B2A1A , Old sub jail road, Post: Boganapalli, Taluk & District: Krishangiri, State: Tamilnadu, Pincode-635001 | Krishnagiri |  |  |  |  | 11.1943 | 77.7036 | 155-1251-52782219 | L900+L1800+L2100+TD | Indus | Indus | IN-1246241 |  |  | Done | 2022-12-24 | Operation Issues |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-24 | 2023-01-03 | GOPI/INHOUSE |  |  |  |  | done |  |  |  | Feb'23 |  | 22803726 | 2023-02-02 | 2023-02-03 |  |  | Full site materials req | [20 empty] | Yes | [23 empty] | Installation Pending |  |  |  | Operation Issues | #N/A
273 | TN | CBE866 | CWPSG | Ok | CBE | Relocation |  | P.S.G.Science and Arts College | No.482/1a, Kalapatti village, Krishnanmoorthy nagar, Post: Civilaerodam, Taluk: Pelamedu, District: coimbatore, State: Tamilnadu, Pincode-641014 | Coimbatore | GBT |  |  |  | 11.0311 | 77.0366 | 155-1103-11770366 | G1800+L1800+L2300 | Indus | Indus | IN-1377579 |  |  | Done | 2022-12-24 | Operation Issues |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-25 | 2022-12-28 | MADHAN PONDY/ONCALL | 2G+L1800+L2100+L2300 | L1800 | L2100+L2300 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 6346859 | 2023-01-13 | 2023-01-13 | 2023-01-14 |  | MS1 DONE | 2023-01-06 | SK Telecom | 2023-01-06 | SK Telecom |  |  |  | 2023-01-06 |  | Relocated |  | 2023-01-07 | TN/01/5177/01730/0043/04/01/17449/NS/07012023 |  |  | 47 | Morethan 7 Days | 34 | Morethan 7 Days |  | Yes | 2023-01-07 | [10 empty] | 2023-01-20 | [11 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Operation Issues | 2023-01-07
274 | TN | TNJ364 | TNJ43 | ok | TRY | Relocation | Ericsson | East ram park st | TS Nos.1308, 1309 and 1310, No.33, S Main St, Post: Rajakrisnapuram, Taluk & District: Thanjavur, State: Tamil Nadu, Pincode-613001 | Thanjavur | RTT |  |  |  | 10.7887 | 79.138 | 155-1078-87791380 | G1800+L1800+L2100+L2300 | BSNL | Indus | 215 |  |  | Done | 2022-12-24 | BSNL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-25 | 2022-12-28 | MANIKANDAN/ONCALL | 2G+L1800+L2100+L2300+TTB-B+FSA+TSA | L1800 | L2100+L2300 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22534964 | 2022-12-30 | 2022-12-30 | 2022-12-30 |  | MS1 DONE | 2023-01-02 | Boss Management | 2023-01-02 | BOSS MANAGEMENT |  |  |  | 2023-01-02 |  | Relocated |  | 2023-01-05 | TN/11/5177/00307/0043/04/01/17423/NS/05012023 | 2023-01-09 | R.MANIKANDAN | [5 empty] | Yes | 2023-01-05 | [7 empty] | 2023-01-17 | 2023-01-22 |  | 2023-01-20 | 2023-01-22 |  | 2023-01-03 | 2023-01-08 |  | 2023-01-06 | 2023-01-08 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | BSNL Relocation | 2023-01-05
275 | CHN | JEWEL6 | JEWEL | ok | CHN | Relocation |  |  |  | Chennai | [6 empty] | 152-1308-91802786 | G1800+L1800+L2100+L2300 | INDUS | Indus | IN-1006787 |  |  | Done | 2022-12-24 | High Opex (Circle) |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-25 | 2023-01-21 | SANJAY /ONCALL | 2G+L1800+L2100+L2300+L900 | L2300 | 2G+L1800+L2100 | 3 | done | 6 |  |  | Jan'23 | Jan'23 | 83104 | 2023-01-25 | 2023-01-25 | 2023-01-27 |  | MS1 DONE | 2023-01-24 | Boss Management | 2023-01-24 | BOSS MANAGEMENT |  |  |  | 2023-01-25 |  |  |  | 2023-01-25 |  |  |  | 47 | Morethan 7 Days | 16 | Morethan 7 Days |  | Yes | 2023-01-25 | [16 empty] | 2023-01-28 | 2023-01-28 |  |  |  |  | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | High Opex (Circle) | 2023-01-25
276 | TN | MELR22 | MELR10 | ok | MDU | Relocation |  | Surakkundu | S. No.164/5A, Ward No.27, E, Block No.1, Survey Field No.10/10C, Thiruvadhavur road, Post & Taluk: Melur, District: Madurai, State: Tamilnadu, Pincode-625106 | Madurai | GBT |  |  |  | 10.0175 | 78.3355 | 155-1001-75783355 | L900+L1800+L2100+TD | Reliance | Indus | TN6MDRAI0047G |  |  | Done | 2022-12-24 | Others | [6 empty] | Yes | Yes | Yes | 2022-12-25 | 2022-12-30 | SUMAN/INHOUSE | 2G+L1800+L2100+L2300 | 2G+L1800+L2300 | L2100 | 3 | done | 9 |  |  | Jan'23 | Jan'23 | 22588472 | 2023-01-06 | 2023-01-07 | 2023-01-09 |  | MS1 DONE | 2023-01-25 | Shyon Enterprises | 2023-01-25 | Shyon Enterprises |  |  |  | 2023-01-25 |  |  |  | 2023-01-25 |  | 2023-01-31 | V.MANIKANDAN | [5 empty] | Yes | 2023-01-25 | [22 empty] | Phy & Soft & KPI AT Pending |  | Phy & Soft & KPI AT Pending |  | Field visit required for rectification | 2023-01-25
277 | TN | PLMPM6 | PLMPM1 | ok | CBE | Relocation |  | Palampalayam | SF No:327/2, Post: Pallapalayam, Taluk: Kannampalayam, District: Coimbatore, State: Tamil Nadu, Pincode-641402 | Coimbatore | GBT |  |  |  | 10.9931 | 77.0865 | 155-1099-32770865 | L900+L1800+L2100+TD | Indus | Indus | IN-1062787 |  |  | Done | 2022-12-24 | Unsafe |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2022-12-25 | 2023-01-02 | SATHISH/ONCALL | 2G+L1800+L2100+L2300+L900+FTB-B+TTB-A,B,D(Don’t put L2100 in 210) | L1800 | L900+L2100+L230 | 3 | done | 19 |  |  | Feb'23 | [6 empty] | Antenna & Power,Cpri Cables req(14) | [20 empty] | Yes | [23 empty] | Installation Pending |  |  |  | Unsafe | #N/A
278 | TN | SHSUM2 | SHSUM1 | ok | MDU | Relocation |  | Shanmugasundarapuram 2 | Mr.Raju, Theni mai raod, Post: Kanavilakku, Taluk & District: Theni, State: Tamilnadu, Pincode-625562. 9087684122 | Theni | GBT |  |  |  | 10.0068 | 77.5615 | 155-0888-10774530 | L900+L1800+L2100+TD | CNIL / GTL | Summit | TAM/GBT/K/27765 | I-TN-BDKK-ENB-9012 |  | Done | 2023-01-10 | CNIL Relocation |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2023-01-10 | 2023-01-25 | ANAND/ONCALL | 2G+L1800+L2100+L2300+L900 | L1800 | L900+L2100+L2300 | 3 | done | 12 |  |  | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
279 | TN | TIR431 | - | ok | CBE | NEW SITE |  |  |  | Tiruppur | [6 empty] | 155-1106-55773613 | 2G+L1800+L2100+L2300 | - | ATC | - |  |  | Done | 2022-12-23 |  |  |  | Yes | Yes |  |  |  | Yes | Yes | 2022-12-23 |  |  | 2G+L1800+L2100+L2300 | [5 empty] | 49 | Morethan 10 Days | Feb'23 | [18 empty] | 2023-01-11 | TN/01/5126/00480/0043/04/01/17471/NS/11012023 | [7 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
280 | TN | KMPTU2 | KMPTU1 | ok | TRY | Relocation |  | Kampattu |  | Viluppuram |  |  |  |  | 11.7461 | 79.2592 | 155-1174-51792622 | 2G+L1800+L2100+L2300+L900 | CNIL / GTL | Ascend | TAM/GBT/K/28575 |  |  | Done | 2023-01-03 | CNIL Relocation |  |  | Yes | Yes |  |  |  | Yes | Yes | 2023-01-03 | 2023-01-05 | MADHAN PONDY/ONCALL | 2G+L1800+L2100+L2300+L900 | [7 empty] | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  | CNIL Relocation | #N/A
281 | TN | KTRPU2 | KTRPU1 | ok | MDU | Relocation |  |  |  | Sivaganga | [7 empty] | L900+L1800+L2100+TD | INDUS | Indus | IN-1107015 |  |  | Done | 2023-01-13 |  |  |  | Yes | Yes |  |  |  | Yes | Yes | 2023-01-13 | 2023-01-26 | SHIVA INHOUSE TEAM | 2G+L1800+L2100+L2300+L900 | L1800 | L900+L2100+L2300 | 3 | done | 12 |  |  | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
282 | CHN | MMIN18 | MMIN13 | ok | CHN | Relocation |  |  |  | Chennai | [13 empty] | Done | 2023-01-21 |  |  |  | Yes | Yes | [5 empty] | 2023-01-21 | 2023-01-29 | MANIKANDAN/ONCALL | 2G+L1800+L2100+L2300+L900+FTB-A+TTB-A,B,C | - | L900+UBR+L2300 | 3 | done | 12 |  |  | Feb'23 | [8 empty] | Boss Management |  | Boss Management | [16 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
283 | TN | SPLKT2 | SPLKT1 | ok | MDU | Relocation |  |  |  | Theni | [13 empty] | Done | 2023-01-21 |  |  |  | Yes | Yes | [5 empty] | 2023-01-21 | 2023-01-25 | ANAND/ONCALL |  |  |  |  | done |  |  |  | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
284 | TN | MDU557 | - | ok | MDU | NEW SITE |  |  |  | Madurai | [9 empty] | Indus |  |  |  | Done | 2023-01-25 |  |  |  | Yes | Yes | [5 empty] | 2023-01-25 | [8 empty] | 16 | Morethan 10 Days | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
285 | TN | ARGI25 | - | ok | TRY | NEW SITE |  |  |  | Pudukkottai | [9 empty] | Ascend |  |  |  | Done | 2023-01-25 |  |  |  | Yes | Yes | [5 empty] | 2023-01-25 | [8 empty] | 16 | Morethan 10 Days | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
286 | TN | MOPRI2 | - | ok | CBE | NEW SITE |  |  |  | Coimbatore | [9 empty] | Indus |  |  |  | Done | 2023-01-25 |  |  |  | Yes | Yes | [5 empty] | 2023-01-25 | [8 empty] | 16 | Morethan 10 Days | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
287 | TN | MUPAT4 | - | ok | CBE | NEW SITE |  |  |  | Tiruppur | [9 empty] | Indus |  |  |  | Done | 2023-01-25 |  |  |  | Yes | Yes | [5 empty] | 2023-01-25 | [8 empty] | 16 | Morethan 10 Days | Feb'23 | [27 empty] | Yes | [23 empty] | Installation Pending |  |  |  |  | #N/A
288 | TN | NDMZR6 | NDMZR2 | ok | TRY | Relocation |  |  |  | Viluppuram | [8 empty] | CNIL / GTL | Ascend | TAM/GBT/K/29406 |  |  | Done | 2023-01-27 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2023-01-27 | 2023-01-31 | RS TELE | 2G+L1800+L2100+L2300+L900 | L1800 | L900+L2100+L2300 | 3 | done | 12 |  |  | Feb'23 | [6 empty] | Material return to ware house | [20 empty] | Yes | [28 empty] | #N/A
289 | TN | TTMDM2 | TTMDM1 | ok | MDU | Relocation |  |  |  | Thoothukkudi | [8 empty] | CNIL / GTL | Ascend | TAM/GBT/K/28585 |  |  | Done | 2023-01-27 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2023-01-27 | 2023-01-28 | PERFECT WELL | 2G+L1800+L2100+L2300+L900 | L1800 | L900+L2100+L2300 | 4 | done | 14 |  |  | Feb'23 |  | 22815161 | 2023-02-04 | 2023-02-04 | 2023-02-04 | [22 empty] | Yes | [28 empty] | #N/A
290 | TN | EMPKE2 | EMKE1 | ok | TRY | Relocation |  |  |  | Viluppuram | [8 empty] | CNIL / GTL | Ascend | TAM/GBT/K/28247 |  |  | Done | 2023-01-27 |  |  |  | Yes | Yes | NA | NA | Yes | Yes | Yes | 2023-01-27 | 2023-01-28 | RS TELE | 2G+L1800+L2100+L2300+L900 | L1800 | L900+L2100+L2300 | 3 | done | 12 |  |  | Feb'23 |  | 22840190 | 2023-02-07 | 2023-02-07 | 2023-02-07 | [22 empty] | Yes | [28 empty] | #N/A
291 | TN | PATHR2 | PATHR1 | ok | TRY | Relocation |  | Pallathur/Aladikadu |  | Thanjavur |  |  |  |  | 10.3261 | 79.3019 |  |  | CNIL / GTL | Ascend | TAM/GBT/K/27753 |  |  | Done | 2023-02-04 | [10 empty] | 2023-02-04 | [8 empty] | 6 | 6 to 10 Days | Feb'23 | [56 empty] | #N/A
Formulas:
Ageing - Survey vs RFAI = IF([Survey Completed]>0,"",TODAY()-[Site Allocated])
Ageing - SCFT vs RFAI = IF([MS1 Date]="","",IF([SCFT]>0,"",TODAY()-[Site Allocated]))
Ageing - MS1 vs SCFT = IF([MS1 Date]="","",IF([SCFT]>0,"",TODAY()-[MS1 Date]))
AGEING = IF([MS1 Date]>0,"",TODAY()-[Site Allocated])
Soft AT Offer = [MW Soft AT]

## Config
New Site ID | Old Site ID | FD Site | Zone | NEW / RELOCATION | OEM | Config Tech | Huawei Curr. Config | Eric Curr. Config | Sec Count | Total Radio Count
KLKLU2 | KLKLU1 | Ok | TRY | RELOCATION | Ericsson | L900+L2300 |  | L900+L2300 | 3+4 | RRU2219 B0*3+RRU4418*2
VDATL2 | VDATL1 | Ok | VLR | RELOCATION | Ericsson | L2300 +L2100 |  | L2300 +L2100 | 3+3 | RRU2219B1*3
SARKR2 | SARKR1 | Ok | CBE | RELOCATION | Ericsson | L900+L2300 +L2100 |  | L900+L2300 +L2100 | 4+4+4 | RRU2219B0*4
CENYH2 | CENYH1 | Ok | VLR | RELOCATION | Ericsson | L900 |  | L900 | 3 | 2219B0*3
MANVL2 | MANVLl | LINK | TRY | RELOCATION | Ericsson | L2300 |  | L2300 | 3 | RRU4418*3
GVPTI4 | GVPTI2 | FD | MDU | RELOCATION | Ericsson | L900+L2300 +L2100 |  | L900+L2300 +L2100 | 4+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*4
TRY403 | TRY66 | FD | TRY | RELOCATION | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | 4418 B40T*4 2219 B1*2 2219 B0A*3
ERD247 | ERD60 | Ok | CBE | RELOCATION | Ericsson | L900+L2100 |  | L900+L2100 | 3+3 | 2219B1*3+2219B0*3
KDKL46 | KDKL14 | OK | MDU | RELOCATION | Ericsson | L900+L2300 |  | L900+L2300 | 3+3 | 4418 B40T*2 2219 B0A*3
NLGRI4 | NLGR1 | OK | TRY | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 4+4+4 | RRU4418*4+RRU2219 B1*4+RRU2219 B0*4
DGL123 | DGL38 | OK | MDU | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
PDY391 | PDY04 | FD | TRY | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 4+4+4 | RRU4418*4+RRU2219 B1*4+RRU2219 B0*4
VNDNI3 | VNDNI1 | OK | MDU | RELOCATION | Ericsson | L2100 |  | L2100 | 3 | 2219 B1*3
ASHO23 | ASHOK | FD | CHN | RELOCATION | Ericsson | L900+L1800+L2300+G1800 |  | L900+L1800+L2300+G1800 | 3+3+3+10Trx | RRU2219 B0*3+RRU2279*3
TECGE3 | TECGE1 | ok | TRY | RELOCATION | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+3 | 2219B1*3 4418B40T*2
NSNP17 | NSNP6 | Ok | CBE | RELOCATION | Ericsson | L2300 |  | L2300 | 4 | RRU4418*4
UDYPT3 | UDYPT2 | Ok | TRY | RELOCATION | Ericsson | L900+L2300 +L2100 |  | L900+L2300 +L2100 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
CBE948 | CBE253 | Ok | CBE | RELOCATION | Ericsson | L900+L2300 +L2100 |  | L900+L2300 +L2100 | 3+4+6 | RRU4418*6+RRU2219 B1*4+RRU2219 B0*3
VDGPI2 | VDGPI1 | Ok | CBE | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
DGL122 | DGL18 | Ok | MDU | RELOCATION | Ericsson | L2100 +L2300 |  | L2100 +L2300 | 4+5 | RRU4418*5+RRU2219 B1*4
KPTKR2 | KPKTR1 | Ok | TRY | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
MOGW31 | MOGWE7 | Ok | CHN | RELOCATION | Ericsson | GL1800+L900+L2100 |  | GL1800+L900+L2100 | 3+3+3 | RRU2219 B0A*4 + RRU227922 B122 B3C*4
VYMDU2 | VYMDU1 | Ok | TRY | RELOCATION | Ericsson | L2100 |  | L2100 | 3 | 2219B1*3
KLPVR6 | KLPVR2 | Ok | MDU | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 4+3+5 | RRU4418*5+RRU2219 B1*3+RRU2219 B0*4
VAND31 | VANDA3 | Ok | CHN | RELOCATION | Ericsson | GL1800+L900+L2100 |  | GL1800+L900+L2100 | 4+4+3 | RRU2219 B0A*4 + RRU2279*3+RRU2219 B3*1
TARA33 | TARA16 | Ok | CHN | RELOCATION | Ericsson | GL1800+L900+L2100 |  | GL1800+L900+L2100 | 3+4+5+16 trx | RRU2219 B1*5+RRU2219 B0*3+RRU2219 B3*4
ANNA25 | ANNA11 | FD | CHN | RELOCATION | Ericsson | GL1800+L2100 |  | GL1800+L2100 | 4+4 | RRU2279*4
KLVNG2 | KLVN1 | Ok | VLR | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
ATRPL2 | ATRPL1 | ok | MDU | RELOCATION | Ericsson | L900+L2100 |  | L900+L2100 | 3+3 | RRU2219 B1*3+RRU2219 B0*3
TRY410 | TRY195 | OK | TRY | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
CBE954 | CBE865 | OK | CBE | RELOCATION | Ericsson | L900+L2100 |  | L900+L2100 | 4+4 | RRU2219 B1*4+RRU2219 B0*4
SNTKD2 | SNTKD1 | OK | MDU | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 2+2+3 | RRU2219 B1*2+RRU2219 B0*2+RRU8863*1
SLM420 | SLM157 | OK | VLR | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
INDNR2 | INDNR1 | OK | CBE | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
OTNGP2 | OTNGP1 | OK | MDU | RELOCATION | Ericsson | L900+L2300 |  | L900+L2300 | 3+3 | RRU4418*3+RRU2219 B0*3
VAGIK2 | VAGIK1 | OK | MDU | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
KAPLM2 | KAPLM1 | OK | CBE | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
VLYNK2 | VLYN1 | OK | MDU | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
GOVTC3 | GOVTC1 | OK | MDU | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
KGVLU2 | KGVLU1 | OK | CBE | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
MAKRI2 | MAKI1 | OK | TRY | RELOCATION | Ericsson | L900+L2100 +L2300 |  | L900+L2100 +L2300 | 4+4+4 | RRU4418*4+RRU2219 B1*4+RRU2219 B0*4
VADA12 | VADAP5 | OK | CHN | Relocation | Ericsson | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | RRU2219 B0*3+RRU2279*3
PAMLP2 | PAMLPO | OK | CHN | Relocation | Ericsson | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3 | RRU2219 B0*3+RRU2279*3
TIRU43 | TIRU31 | OK | CHN | Relocation | Ericsson | L900+GL1800 |  | L900+GL1800 | 4+3+3 | RRU2219 B0*3+RRU2279*4
RICHI8 | RICHIE | OK | CHN | Relocation | Ericsson | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | RRU2219 B0*3+RRU2279*3
VELMA6 | VELMA2 | OK | CHN | Relocation | Ericsson | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | RRU2219 B0*3+RRU2279*3
CWM225 | CWM109 | OK | CHN | Relocation | Ericsson | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | RRU2219 B0*3+RRU2279*3
CBE901 | CBE159 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 4+5 | RRU4418*5+RRU2219*4
VKLM03 | VKLM1 | OK | MDU | Relocation | Ericsson | L2100 |  | L2100 | 4 | RRU2219 B1*4
TUT121 | TUT11 | OK | Tutucorin | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 4+5 | RRU4418*5+RRU2279*4
PDMUP2 | PDMUP1 | OK | TRY | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+4 | RRU4418*4+RRU2219 B1*3
UAUNM2 | UAUNM1 | OK | MDU | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
MTHKL5 | MTHKL1 | OK | TRY | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
PNPT15 | PNPT3 | OK | VLR | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
PCHYR2 | PCHYR1 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 4 | RRU4418*6+RRU2219*3
COWKVP | KSVMP1 | OK | TRY | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+3 | RRU4418*3+RRU2219 B0*3
KLNJR3 | KLNJR1 | OK | VLR | Relocation | Ericsson | GL1800+L900 |  | GL1800+L900 | 4 | RRU2279*4+RRU2219 B0*4
PKT215 | PKT01 | OK | MDU | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
TKMB18 | TKMB1 | OK | MDU | Relocation | Ericsson | L2300+L2100 |  | L2300+L2100 | 4+3 | RRU4418*4+RRU2219 B1*3
PRLAM3 | PRLAM1 | OK | TRY | Relocation | Ericsson | GL1800 |  | GL1800 | 4+4 | RRU2219 B3*4
CBE890 | CBE512 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 6+7 | RRU4418*7+RRU2219 B1*6
SINGA2 | SINGA1 | OK | CBE | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
SKGI22 | SKGI5 | OK | VLR | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
PDYRM2 | PDYRM1 | OK | Tutucorin | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
PKT010 | PKT02 | OK | MDU | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | RRU2219 B1*3+RRU2219 B0*4+RRU4418*4
MNPTI2 | MNPTI1 | OK | VLR | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | RRU2219 B1*3+RRU2219 B0*4+RRU4418*4
PPMPT3 | PPMPT1 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+6 | RRU4418*6+RRU2219 B1*3
PTTNM2 | PTTNM1 | OK | VLR | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU2219 B1*5+RRU2219 B0*4
KLVLU3 | KLVLU1 | OK | MDU | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+4 | RRU4418*4+RRU2219 B1*3
ELSPT2 | ELSPT1 | OK | CBE | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
KLRM02 | KLRM1 | OK | VLR | Relocation | Ericsson | L2100 |  | L2100 | 3 | RRU2219 B1*3
MURKD2 | MURKD1 | OK | TRY | Relocation | Ericsson | L2100 |  | L2100 | 3 | RRU2219 B1*3
KTBS10 | KTBSL1 | OK | TRY | Relocation | Ericsson | L2100 |  | L2100 | 3 | RRU2219 B0*3
PMPYR4 | PMPYR1 | OK | TRY | Relocation | Ericsson | L2300 |  | L2300 | 3 | RRU4418*3
PATU15 | PATT3 | OK | TRY | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
PDCRM4 | PDCRM3 | OK | VLR | Relocation | Ericsson | L900 |  | L900 | 4 | RRU2219 B1*4
TIR482 | TIR49 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+4 | RRU4418*4+RRU2219 B1*3
SLM397 | SLM103 | OK | VLR | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+4 | RRU4418*4+RRU2219 B1*3
STTPU7 | STTPU1 | OK | TRY | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
MADM02 | MADM1 | OK | TRY | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+3 | RRU4418*3+RRU2219 B1*3
BVGRI5 | BVGRI4 | OK | VLR | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 4+3 | RRU4418*3+RRU2219 B1*4
KDVAI2 | KDVAI1 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+3 | RRU4418*3+RRU2219 B1*3
NGL141 | NGL49 | OK | Kanniyakumari | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+3 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
VSNRM2 | VSNRM1 | OK | VLR | Relocation | Ericsson | L900+L2300 |  | L900+L2300 | 3+3 | RRU4418*2+RRU2219 B0*3
MATTU3 | MATTU1 | OK | Palani | Relocation | Ericsson | L900 |  | L900 | 3 | RRU2219 B0*3
TRY382 | TRY203 | OK | TRY | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+3 | RRU4418*3+RRU2219 B1*3
SLM402 | SLM128 | OK | VLR | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 4 | RRU4418*6+RRU2219*5
VLR111 | VLR11 | OK | VLR | Relocation | Ericsson | GL1800 |  | GL1800 | 4 | RRU2279*4
MLVTN4 | MLVTN1 | OK | Tutucorin | Relocation | Ericsson | L900 |  | L900 | 3 | RRU2219 B0*3
ISWRG4 | ISWRG1 | OK | CBE | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
MMDUR4 | MMDUR1 | OK | Chengalpet | Relocation | Ericsson | L900+L2300 |  | L900+L2300 | 3+3+4 | RRU4418*3+RRU2219 B1*3+RRU2219 B0*3
SLM400 | SLM83 | OK | VLR | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+4 | RRU4418*4+RRU2219 B1*3
WRGD13 | CWWRG | OK | VLR | Relocation | Ericsson | L900 |  | L900 | 3 | RRU2219 B0*3
TNPLM6 | TNPLM1 | OK | CBE | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+4+1 | RRU4418*1+RRU2219 B1*3+RRU2219 B0*4
KLPTI6 | KLPTI2 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+4 | RRU4418*4+RRU2219 B1*3
TIPPA2 | TIPPA1 | OK | VLR | Relocation | Ericsson | L900+L2100 |  | L900+L2100 | 4+4 | RRU2219 B1*4+RRU2219 B0*4
KMNPM3 | KMNPM1 | OK | CBE | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+4 | RRU4418*4+RRU2219 B1*3+RRU2219 B0*3
VENGA5 | VENGA1 | OK | CBE | Relocation | Ericsson | L900+L2300 |  | L900+L2300 | 3+3 | RRU4418*3+RRU2219 B0*3
TIR355 | TIR44 | OK | CBE | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+5 | RRU4418*5+RRU2219*3
SLM378 | SLM134 | OK | VLR | Relocation | Ericsson | L900 |  | L900 | 3 | RRU2219 B0*3
VADUG4 | VADUG1 | OK | VLR | Relocation | Ericsson | L900+GL1800+L2100 |  | L900+GL1800+L2100 | 3+3+3+3 | RRU2219 B0*3+RRU2279*3
KDVPT2 | KDVPT1 | OK | MDU | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 4+3+4 | RRU2219 B1*3+RRU2219 B0*4+RRU4418*4
KCP135 | KCPM5 | OK | VLR | Relocation | Ericsson | L2100+L2300 |  | L2100+L2300 | 3+6 | RRU4418*6+RRU2219 B1*3
DGL111 | DGL10 | OK | MDU | Relocation | Ericsson | L900+L2100+L2300 |  | L900+L2100+L2300 | 3+3+6 | RRU2219 B1*3+RRU2219 B0*3+RRU4418*6
KRVAM2 | KRVAM1 | OK | CBE | RELOCATION | Ericsson | L900 |  | L900 | 3 | 2219B0*3
RSPM15 | RSPM5 | OK | VLR | RELOCATION | Ericsson | L900+L2100 |  | L900+L2100 | 3+3 | RRU2219 B1*3+RRU2219 B0*3

## SACFA & WPC
S.No | SiteID | New 6 Digit ID | District | Zone |  | Circle | TOCO | TOCO ID | RL No. | Workable/NON Workable | SR Status | SO Date | L1800 | L900 | L2100 | TD | Tech | SACFA Status | Remarks | 900 SACFA ID | SACFA Date | WPC ID | WPC Data | 1800 SACFA ID | SACFA Date | WPC ID | WPC Data | 2100 SACFA ID | SACFA Date | WPC ID | WPC Data | 2300 SACFA ID | SACFA Date | WPC ID | WPC Data | remarks for So withraw | SiteID
1 | CBE737 | CBE737 | Coimbatore | Coimbatore |  | ROTN | Airtel | CBE737 | - | Nominals with issues |  | 2019-08-27 | CBE737 | 4G_FD900_CBE737 | 4G_FD2100_CBE737 | 4G_TD_CBE737 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361918 | 2021-06-25 | P/FVC/MDS/1049910/2021 | 2021-08-09 | ST202011135696 | 2020-11-05 | P/FVC/MDS/1006069/2020 | 2020-11-18 | ST202212857092 | 2022-12-27 | 0 |  | ST202011140461 | 2020-11-08 | P/FBW/MDS/1006181/2020 | 2020-11-18 | Partof461sitesSyamaMay'30 | CBE737
2 | KGRI33 | KGRI33 | Krishnagiri | Vellore |  | ROTN | Airtel | KGRI33 | - | Nominals with issues | SR | 2019-08-27 | KGRI33 | 4G_FD900_KGRI33 | 4G_FD2100_KGRI33 | 4G_TD_KGRI33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364349 | 2021-06-28 | P/FVC/MDS/1050267/2021 | 2021-08-09 | ST202011135697 | 2020-11-05 | P/FVC/MDS/1006070/2020 | 2020-11-18 |  |  |  |  | ST202011140462 | 2020-11-08 | P/FBW/MDS/1006182/2020 | 2020-11-18 | Partof461sitesSyamaMay'30 | KGRI33
3 | KOMANG | KOMANG | Cuddalore | Trichy |  | ROTN | Indus | IN-1434861 | R/NN-469562 | Nominals with issues | Dropped-Canb. | 2020-10-15 | KOMANG | 4G_FD900_KOMANG | 4G_FD2100_KOMANG | 4G_TD_KOMANG | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106362325 | 2021-06-25 | P/FVC/MDS/1049971/2021 | 2021-08-09 | ST202011135655 | 2020-11-05 | P/FVC/MDS/1006057/2020 | 2020-11-18 | ST202011138095 | 2020-11-06 | P/FVC/MDS/1006029/2020 | 2020-11-18 |  |  |  |  | 0 | KOMANG
4 | MPRI14 | MPRI14 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-1428515 | R/NN-469226 | Nominals with issues | Dropped-Canb. | 2020-10-20 | MPRI14 | 4G_FD900_MPRI14 | 4G_FD2100_MPRI14 | 4G_TD_MPRI14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362632 | 2021-06-26 | P/FVC/MDS/1049995/2021 | 2021-08-09 |  |  | P/FVC/MDS/1006082/2020 | 2020-11-18 |  |  |  |  | ST202011140481 | 2020-11-08 | P/FBW/MDS/1006193/2020 | 2020-11-18 | 0 | MPRI14
5 | MTR25 | MTR025 | Salem | Vellore |  | ROTN | Indus | IN-1430048 | R/NN-469278 | Nominals with issues | On Air | 2020-10-23 | MTR025 | 4G_FD900_MTR025 | 4G_FD2100_MTR025 | 4G_TD_MTR025 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202201008776 | 2022-01-12 | P/FVC/MDS/1071717/2022 | 2022-01-20 | ST202201022638 | 2022-01-28 | P/FVC/MDS/1072960/2022 | 2022-02-04 |  |  |  |  | ST202201008953 | 2022-01-13 | P/FBW/MDS/1071557/2022 | 2022-01-20 | 0 | MTR25
6 | PNKLM4 | PNKLM4 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22181 | T20TN06525 | Nominals with issues | On Air | 2020-10-23 | PNKLM4 | 4G_FD900_PNKLM4 | 4G_FD2100_PNKLM4 | 4G_TD_PNKLM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362751 | 2021-06-26 | P/FVC/MDS/1050024/2021 | 2021-08-09 | ST202011140391 | 2020-11-08 | P/FVC/MDS/1006131/2020 | 2020-11-18 | ST202011152156 | 2020-11-20 | P/FVC/MDS/1006532/2020 | 2020-11-28 | ST202011140498 | 2020-11-08 | P/FBW/MDS/1006210/2020 | 2020-11-18 | 0 | PNKLM4
7 | TRVRB3 | TRVRB3 | Kanniyakumari | Madurai |  | ROTN | Summit | TN/KN/AT/22174 | T20TN06518 | Nominals with issues | On Air | 2020-10-23 | TRVRB3 | 4G_FD900_TRVRB3 | 4G_FD2100_TRVRB3 | 4G_TD_TRVRB3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363073 | 2021-12-10 | P/FVC/MDS/1069082/2021 | 2021-12-17 | ST202112604903 | 2021-12-07 | P/FVC/MDS/1068828/2021 | 2021-12-15 | ST202102042708 | 2021-02-02 | P/FVC/MDS/1011204/2021 | 2021-03-01 | ST202112609415 | 2021-12-10 | P/FBW/MDS/1068792/2021 | 2021-12-15 | 0 | TRVRB3
8 | TVPM12 | TVPM12 | Tiruvannamalai | Vellore |  | ROTN | Indus |  | R/NN-469538 | Nominals with issues | Dropped-Canb. | 2020-10-15 | TVPM12 | 4G_FD900_TVPM12 | 4G_FD2100_TVPM12 | 4G_TD_TVPM12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363123 | 2021-06-26 | P/FVC/MDS/1050100/2021 | 2021-08-09 | ST202011135654 | 2020-11-05 | P/FVC/MDS/1006056/2020 | 2020-11-18 |  |  |  |  | ST202011140451 | 2020-11-08 | P/FBW/MDS/1006176/2020 | 2020-11-18 | SO Hold R/NN-469538 Canceled by Indus Nitin on Feb 22021 As per Indus 15-Apr mail Site ll be RFAI may 1st week | TVPM12
9 | ARNI26 | ARNI26 | Tiruvannamalai | Vellore |  | ROTN | Ascend | 0 | - | Nominals with issues | Dropped-Canb. | 2021-03-25 | ARNI26 | 4G_FD900_ARNI26 | 4G_FD2100_ARNI26 | 4G_TD_ARNI26 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361842 | 2021-06-25 | P/FVC/MDS/1049903/2021 | 2021-08-09 | ST202104126200 | 2021-04-06 | P/FVC/MDS/1017818/2021 | 2021-05-15 |  |  |  |  | ST202104119667 | 2021-04-03 | P/FBW/MDS/1020259/2021 | 2021-05-23 | 0 | ARNI26
10 | CBE827 | CBE827 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1448589 | R/NN-470168 | Nominals with issues | Dropped-Canb. | 2021-03-16 | CBE827 | 4G_FD900_CBE827 | 4G_FD2100_CBE827 | 4G_TD_CBE827 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361961 | 2021-06-25 | P/FVC/MDS/1049919/2021 | 2021-08-09 | ST202103105177 | 2021-03-25 | P/FVC/MDS/1017943/2021 | 2021-05-15 |  |  |  |  | ST202103105753 | 2021-03-25 | P/FBW/MDS/1020103/2021 | 2021-05-22 | 0 | CBE827
11 | ERD159 | ERD159 | Erode | Coimbatore |  | ROTN | Indus | 0 | R/NN-567828 | Nominals with issues | Dropped-Canb. | 2021-03-16 | ERD159 | 4G_FD900_ERD159 | 4G_FD2100_ERD159 | 4G_TD_ERD159 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362267 | 2021-06-25 | P/FVC/MDS/1049940/2021 | 2021-08-09 | ST202103105243 | 2021-03-25 | P/FVC/MDS/1017950/2021 | 2021-05-15 |  |  |  |  | ST202103105838 | 2021-03-25 | P/FBW/MDS/1020110/2021 | 2021-05-22 | Partof461sitesSyamaMay'30 | ERD159
12 | ERD163 | ERD163 | Erode | Coimbatore |  | ROTN | Indus | IN-1806088 | R/NN-567364 | Nominals with issues | Dropped-Canb. | 2021-03-19 | ERD163 | 4G_FD900_ERD163 | 4G_FD2100_ERD163 | 4G_TD_ERD163 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362268 | 2021-06-25 | P/FVC/MDS/1049941/2021 | 2021-08-09 | ST202103105240 | 2021-03-25 | P/FVC/MDS/1017947/2021 | 2021-05-15 |  |  |  |  | ST202103105835 | 2021-03-25 | P/FBW/MDS/1020107/2021 | 2021-05-22 | Partof461sitesSyamaMay'30.MuthusirproposedATCsurrenderonAug8&giventoOwn | ERD163
13 | GUNDPP | GUNDPP | Cuddalore | Trichy |  | ROTN | ATC | TN/CU/AT/22337 | T20TN08645 | Nominals with issues | On Air | 2021-03-24 | GUNDPP | 4G_FD900_GUNDPP | 4G_FD2100_GUNDPP | 4G_TD_GUNDPP | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202109522080 | 2021-09-16 | P/FVC/MDS/1062418/2021 | 2021-09-23 | ST202109522207 | 2021-09-16 | P/FVC/MDS/1062465/2021 | 2021-09-23 | ST202109530015 | 2021-09-24 | P/FVC/MDS/1063001/2021 | 2021-10-01 | ST202109522262 | 2021-09-16 | P/FBW/MDS/1062513/2021 | 2021-09-23 | 0 | GUNDPP
14 | HSR153 | HSR153 | Krishnagiri | Vellore |  | ROTN | Indus | IN-1878750 | R/NN-569398 | Nominal WIP | Dropped-Canb. | 2021-04-10 | HSR153 | 4G_FD900_HSR153 | 4G_FD2100_HSR153 | 4G_TD_HSR153 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362289 | 2021-06-25 | P/FVC/MDS/1049950/2021 | 2021-08-09 | ST202104148121 | 2021-04-15 | P/FVC/MDS/1018027/2021 | 2021-05-15 |  |  |  |  | ST202104148952 | 2021-04-15 | P/FBW/MDS/1018085/2021 | 2021-05-16 | Priority Working by Indus + ATC - 1-Apr-21 | HSR153
15 | KLPVR5 | KLPVR5 | Tirunelveli | Madurai |  | ROTN | Ascend | 0 | - | Nominal WIP | SR | 2021-03-23 | KLPVR5 | 4G_FD900_KLPVR5 | 4G_FD2100_KLPVR5 | 4G_TD_KLPVR5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362312 | 2021-06-25 | P/FVC/MDS/1049964/2021 | 2021-08-09 | ST202104125407 | 2021-04-05 | P/FVC/MDS/1017797/2021 | 2021-05-15 |  |  |  |  | ST202104119377 | 2021-04-03 | P/FBW/MDS/1020238/2021 | 2021-05-23 | 0 | KLPVR5
16 | KOVI24 | KOVI24 | Chennai | Chennai |  | CHN | Indus | IN-1719031 | R/NN-568054 | Nominal WIP | Dropped | 2021-03-15 | KOVI24 | 4G_FD900_KOVI24 | 4G_FD2100_KOVI24 | 4G_TD_KOVI24 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202104130192 | 2021-04-07 | P/FVC/MDS/1017841/2021 | 2021-05-15 | ST202104130300 | 2021-04-07 | P/FVC/MDS/1017851/2021 | 2021-05-15 | ST202106358253 | 2021-06-23 | P/FVC/MDS/1055853/2021 | 2021-09-04 | ST202104119154 | 2021-04-03 | P/FBW/MDS/1020281/2021 | 2021-05-23 | SO R/NN-403884 terminated by Indus and repunched on Feb 12, 2021. SP R/NN-568054 rejected. SP R/NN-565036 rejected on Mar 10, 2021 due to delay in product confirnmation from Indus | KOVI24
17 | KRPT3 | KRPT03 | Virudhunagar | Madurai |  | ROTN | ATC | TN3134 |  | Nominal WIP | Dropped-Canb. | 2021-03-27 | KRPT03 | 4G_FD900_KRPT03 | 4G_FD2100_KRPT03 | 4G_TD_KRPT03 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362332 | 2021-06-25 | P/FVC/MDS/1049974/2021 | 2021-08-09 | ST202104126222 | 2021-04-06 | P/FVC/MDS/1017825/2021 | 2021-05-15 |  |  |  |  | ST202104119674 | 2021-04-03 | P/FBW/MDS/1020267/2021 | 2021-05-23 | 0 | KRPT3
18 | MGDI20 | MGDI20 | Thiruvarur | Trichy |  | ROTN | Indus | IN-1385437 | R/NN-446941 | Nominals with issues | Dropped-Canb. | 2021-03-16 | MGDI20 | 4G_FD900_MGDI20 | 4G_FD2100_MGDI20 | 4G_TD_MGDI20 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362389 | 2021-06-25 | P/FVC/MDS/1049992/2021 | 2021-08-09 | ST202103105176 | 2021-03-25 | P/FVC/MDS/1017942/2021 | 2021-05-15 |  |  |  |  | ST202103105752 | 2021-03-25 | P/FBW/MDS/1020102/2021 | 2021-05-22 | 20-20-TopTowns0.8Validation/R/NN-391616/SRwithdrwanduetoDAY1TDDandrepunched | MGDI20
19 | PRNI6 | PRNI06 | Thanjavur | Trichy |  | ROTN | TVI | 0 | - | Nominal WIP | On Air | 2021-03-27 | PRNI06 | 4G_FD900_PRNI06 | 4G_FD2100_PRNI06 | 4G_TD_PRNI06 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362759 | 2021-06-26 | P/FVC/MDS/1050030/2021 | 2021-08-09 | ST202104126225 | 2021-04-06 | P/FVC/MDS/1017828/2021 | 2021-05-15 |  |  |  |  | ST202104119876 | 2021-04-03 | P/FBW/MDS/1020270/2021 | 2021-05-23 | SO has been issued to TVI , as per mail from kamal SO Surrender by TOCO on 26-may due to LL backed out | PRNI6
20 | SEHUR3 | SEHUR3 | Virudhunagar | Madurai |  | ROTN | Indus | IN-1385568 | R/NN-440033 | Nominals with issues | On Air | 2021-03-11 | SEHUR3 | 4G_FD900_SEHUR3 | 4G_FD2100_SEHUR3 | 4G_TD_SEHUR3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202111585032 | 2021-11-09 | P/FVC/MDS/1068090/2021 | 2021-12-08 | ST202111585346 | 2021-11-09 | P/FVC/MDS/1068127/2021 | 2021-12-08 |  |  |  |  | ST202111582611 | 2021-11-06 | P/FBW/MDS/1068064/2021 | 2021-12-08 | 20-20-RestofUrban/R/NN-385736SRWithdrwanandindussharing2/5/2020/R/NN-418595/SRwithdrwanduetoDAY1TDDandrepunched | SEHUR3
21 | SLM365 | SLM365 | Salem | Vellore |  | ROTN | Indus | IN-1448592 | R/NN-470193 | Nominals with issues | Dropped-Canb. | 2021-03-11 | SLM365 | 4G_FD900_SLM365 | 4G_FD2100_SLM365 | 4G_TD_SLM365 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362785 | 2021-06-26 | P/FVC/MDS/1050045/2021 | 2021-08-09 | ST202103105005 | 2021-03-25 | P/FVC/MDS/1017915/2021 | 2021-05-15 |  |  |  |  | ST202103099317 | 2021-03-22 | P/FBW/MDS/1019979/2021 | 2021-05-22 | 0 | SLM365
22 | TARA23 | TARA23 | Chennai | Chennai |  | CHN | Indus | IN-1782875 | R/NN-567135 | Nominal WIP | Dropped | 2021-03-09 | TARA23 | 4G_FD900_TARA23 | 4G_FD2100_TARA23 | 4G_TD_TARA23 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202103105908 | 2021-03-25 | P/FVC/MDS/1017323/2021 | 2021-05-12 | ST202103106150 | 2021-03-25 | P/FVC/MDS/1017771/2021 | 2021-05-15 | ST202106358290 | 2021-06-23 | P/FVC/MDS/1055872/2021 | 2021-09-04 | ST202103099690 | 2021-03-22 | P/FBW/MDS/1020021/2021 | 2021-05-22 | Surrendered by Own on July 7, 2020, surrendered by Ascend on Aug 10 and allotted to Own (Ar) | TARA23
23 | TIR395 | TIR395 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1386564 | R/NN-457588 | Nominals with issues | On Air | 2021-03-23 | TIR395 | 4G_FD900_TIR395 | 4G_FD2100_TIR395 | 4G_TD_TIR395 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362804 | 2021-06-26 | P/FVC/MDS/1050064/2021 | 2021-08-09 | ST202104126137 | 2021-04-06 | P/FVC/MDS/1017802/2021 | 2021-05-15 |  |  |  |  | ST202104119415 | 2021-04-03 | P/FBW/MDS/1020243/2021 | 2021-05-23 | TocochangedfromATCtoinuds6/22/2020 | TIR395
24 | TNJ88 | TNJ088 | Thanjavur | Trichy |  | ROTN | Ascend |  |  | Nominals with issues | RFAI | 2021-03-25 | TNJ088 | 4G_FD900_TNJ088 | 4G_FD2100_TNJ088 | 4G_TD_TNJ088 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362866 | 2021-06-26 | P/FVC/MDS/1050078/2021 | 2021-08-09 | ST202104126201 | 2021-04-06 | P/FVC/MDS/1017819/2021 | 2021-05-15 |  |  |  |  | ST202104119668 | 2021-04-03 | P/FBW/MDS/1020260/2021 | 2021-05-23 | TocoChangedFromATC(95)ToIndusConfirmedBySyama1/17/2019/R/NN-319197BookedAs30MtrGBTODSiteRequestWithdwanandRebookedasLiteplusAsperSyamaConfirmationR/NN-321181Bookedliteplusthenwithdwanandrebookedastrasitionalbasisonjawhar2/20/2019R/NN-323121InduscanceledSOonAug22/OwnStatusChangedfromSOtoSRbasisonsentamil8/26/2019 | TNJ88
25 | TNV77 | TNV077 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1736293 | R/NN-562588 | Nominals with issues | Drop | 2021-03-11 | TNV077 | 4G_FD900_TNV077 | 4G_FD2100_TNV077 | 4G_TD_TNV077 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362879 | 2021-06-26 | P/FVC/MDS/1050080/2021 | 2021-08-09 | ST202103104953 | 2021-03-25 | P/FVC/MDS/1017912/2021 | 2021-05-15 |  |  |  |  | ST202103099300 | 2021-03-22 | P/FBW/MDS/1019976/2021 | 2021-05-22 | R/NN-464126 withdrawn and repositioned with deviation basis discussion with Ratna | TNV77
26 | TRY272 | TRY272 | Tiruchirappalli | Trichy |  | ROTN | Ascend |  |  | Nominal WIP | Dropped-Canb. | 2021-03-20 | TRY272 | 4G_FD900_TRY272 | 4G_FD2100_TRY272 | 4G_TD_TRY272 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363074 | 2021-06-26 | P/FVC/MDS/1050084/2021 | 2021-08-09 | ST202104125399 | 2021-04-05 | P/FVC/MDS/1017789/2021 | 2021-05-15 |  |  |  |  | ST202103105957 | 2021-03-25 | P/FBW/MDS/1018706/2021 | 2021-05-21 | SOSurrenderedbyATCbasisonsyama9/30/2019/TVIreturnednominalonOct25/R/NN-375047SRWithdrwanandalocatedtoown2/18/2020 | TRY272
27 | TVLR72 | TVLR72 | Thiruvallur | Chennai |  | ROTN | Ascend | 0 | - | Nominal WIP | SP | 2021-03-20 | TVLR72 | 4G_FD900_TVLR72 | 4G_FD2100_TVLR72 | 4G_TD_TVLR72 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363108 | 2021-06-26 | P/FVC/MDS/1050099/2021 | 2021-08-09 | ST202104125400 | 2021-04-05 | P/FVC/MDS/1017790/2021 | 2021-05-15 |  |  |  |  | ST202104119378 | 2021-04-03 | P/FBW/MDS/1020239/2021 | 2021-05-23 | Dropped-Can on 2 Jul , Indus Provided new SP post SO Released | TVLR72
28 | UMKDI4 | UMKDI4 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-1794201 | R/NN-567468 | Nominal WIP | On Air | 2021-03-16 | UMKDI4 | 4G_FD900_UMKDI4 | 4G_FD2100_UMKDI4 | 4G_TD_UMKDI4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363131 | 2021-06-26 | P/FVC/MDS/1050102/2021 | 2021-08-09 | ST202103105242 | 2021-03-25 | P/FVC/MDS/1017949/2021 | 2021-05-15 |  |  |  |  | ST202103105837 | 2021-03-25 | P/FBW/MDS/1020109/2021 | 2021-05-22 | Partof461sitesSyamaMay'30.MuthusirproposedATCsurrenderonAug8&giventoOwn | UMKDI4
29 | VAND30 | VAND30 | Chennai | Chennai |  | CHN | Indus | IN-1388286 | R/NN-464712 | Nominal WIP | SR | 2021-03-09 | VAND30 | 4G_FD900_VAND30 | 4G_FD2100_VAND30 | 4G_TD_VAND30 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202103105888 | 2021-03-25 | P/FVC/MDS/1017321/2021 | 2021-05-12 | ST202103106127 | 2021-03-25 | P/FVC/MDS/1017769/2021 | 2021-05-15 | ST202106358305 | 2021-06-23 | P/FVC/MDS/1055878/2021 | 2021-09-04 | ST202103099688 | 2021-03-22 | P/FBW/MDS/1020019/2021 | 2021-05-22 | 0 | VAND30
30 | ANJGM7 | ANJGM7 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22393 | T21TN00765 | Nominals with issues | Dropped-Canb. | 2021-03-10 | ANJGM7 | 4G_FD900_ANJGM7 | 4G_FD2100_ANJGM7 | 4G_TD_ANJGM7 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364102 | 2021-06-28 | P/FVC/MDS/1050131/2021 | 2021-08-09 | ST202103106338 | 2021-03-25 | P/FVC/MDS/1017985/2021 | 2021-05-15 |  |  |  |  | ST202103099296 | 2021-03-22 | P/FBW/MDS/1019972/2021 | 2021-05-22 | 0 | ANJGM7
31 | GMPD27 | GMPD27 | Thiruvallur | Chennai |  | ROTN | ATC | TN/TU/AT/22451 | T21TN01788 | Nominals with issues | Dropped-Canb. | 2021-03-24 | GMPD27 | 4G_FD900_GMPD27 | 4G_FD2100_GMPD27 | 4G_TD_GMPD27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364117 | 2021-06-28 | P/FVC/MDS/1050143/2021 | 2021-08-09 | ST202104126198 | 2021-04-06 | P/FVC/MDS/1017816/2021 | 2021-05-15 |  |  |  |  | ST202104119525 | 2021-04-03 | P/FBW/MDS/1020257/2021 | 2021-05-23 | 0 | GMPD27
32 | PTNSCB | PTNSCB | Chennai | Chennai |  | CHN | TVI |  |  | Nominal WIP | SRB(Surrender) | 2021-03-26 | PTNSCB | 4G_FD900_PTNSCB | 4G_FD2100_PTNSCB | 4G_TD_PTNSCB | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202104130219 | 2021-04-07 | P/FVC/MDS/1017850/2021 | 2021-05-15 | ST202104130432 | 2021-04-07 | P/FVC/MDS/1017862/2021 | 2021-05-15 | ST202106358312 | 2021-06-23 | P/FVC/MDS/1055880/2021 | 2021-09-04 | ST202104119189 | 2021-04-03 | P/FBW/MDS/1020290/2021 | 2021-05-23 | 0 | PTNSCB
33 | KDKL21 | KDKL21 | Dindigul | Coimbatore |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2021-03-11 | KDKL21 | 4G_FD900_KDKL21 | 4G_FD2100_KDKL21 | 4G_TD_KDKL21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364120 | 2021-06-28 | P/FVC/MDS/1050146/2021 | 2021-08-09 | ST202104126141 | 2021-04-06 | P/FVC/MDS/1017806/2021 | 2021-05-15 |  |  |  |  | ST202104119419 | 2021-04-03 | P/FBW/MDS/1020247/2021 | 2021-05-23 | Earliercheck,nowP0/P1/R/NN-322987/SRwithdrwanduetoDAY1TDDandrepunched/R/NN-431484Withdrwanduetop15/19/2020 | KDKL21
34 | TRY259 | TRY259 | Tiruchirappalli | Trichy |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2021-03-13 | TRY259 | 4G_FD900_TRY259 | 4G_FD2100_TRY259 | 4G_TD_TRY259 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364121 | 2021-06-28 | P/FVC/MDS/1050147/2021 | 2021-08-09 | ST202104126168 | 2021-04-06 | P/FVC/MDS/1017810/2021 | 2021-05-15 |  |  |  |  | ST202104119519 | 2021-04-03 | P/FBW/MDS/1020251/2021 | 2021-05-23 | /R/NN-323046/SRwithdrwanduetoDAY1TDDandrepunched | TRY259
35 | CDLR77 | CDLR77 | Cuddalore | Trichy |  | ROTN | Indus |  |  | Nominal WIP | Dropped-Canb. | 2021-03-16 | CDLR77 | 4G_FD900_CDLR77 | 4G_FD2100_CDLR77 | 4G_TD_CDLR77 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364370 | 2021-06-28 | P/FVC/MDS/1050275/2021 | 2021-08-09 | ST202103105241 | 2021-03-25 | P/FVC/MDS/1017948/2021 | 2021-05-15 |  |  |  |  | ST202103105836 | 2021-03-25 | P/FBW/MDS/1020108/2021 | 2021-05-22 | Partof461sitesSyamaMay'30.MuthusirproposedATCsurrenderonAug8&giventoOwn | CDLR77
36 | PATU38 | PATU38 | Thanjavur | Trichy |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2021-03-13 | PATU38 | 4G_FD900_PATU38 | 4G_FD2100_PATU38 | 4G_TD_PATU38 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364371 | 2021-06-28 | P/FVC/MDS/1050276/2021 | 2021-08-09 | ST202104126167 | 2021-04-06 | P/FVC/MDS/1017809/2021 | 2021-05-15 |  |  |  |  | ST202104119422 | 2021-04-03 | P/FBW/MDS/1020250/2021 | 2021-05-23 | 20-20-TopTowns0.8Validation/R/NN-385744/SRwithdrwanduetoDAY1TDDandrepunched | PATU38
37 | HSR152 | HSR152 | Krishnagiri | Vellore |  | ROTN | TVI |  |  | Nominal WIP | On Air | 2021-03-10 | HSR152 | 4G_FD900_HSR152 | 4G_FD2100_HSR152 | 4G_TD_HSR152 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363686 | 2021-06-28 | P/FVC/MDS/1050261/2021 | 2021-08-09 | ST202103105174 | 2021-03-25 | P/FVC/MDS/1017940/2021 | 2021-05-15 | ST202210538400 | 2022-10-08 | P/FVC/MDS/1113905/2022 | 2022-10-21 | ST202103105750 | 2021-03-25 | P/FBW/MDS/1020100/2021 | 2021-05-22 | 0 | HSR152
38 | NGL123 | NGL123 | Kanniyakumari | Madurai |  | ROTN | INDUS |  |  | Nominal WIP | On Air | 2021-03-04 | NGL123 | 4G_FD900_NGL123 | 4G_FD2100_NGL123 | 4G_TD_NGL123 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363669 | 2021-06-28 | P/FVC/MDS/1050244/2021 | 2021-08-09 | ST202103105009 | 2021-03-25 | P/FVC/MDS/1017919/2021 | 2021-05-15 |  |  |  |  | ST202103099321 | 2021-03-22 | P/FBW/MDS/1019983/2021 | 2021-05-22 | 0 | NGL123
39 | ZOHOBS | ZOHOBS | Chennai | Chennai |  | CHN | Airtel |  |  | Nominal WIP | On air |  | ZOHOBS | 4G_FD900_ZOHOBS | 4G_FD2100_ZOHOBS | 4G_TD_ZOHOBS | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202103105913 | 2021-03-25 | P/FVC/MDS/1017766/2021 | 2021-05-15 | ST202103106181 | 2021-03-25 | P/FVC/MDS/1017776/2021 | 2021-05-15 | ST202107388495 | 2021-07-19 | P/FVC/MDS/1056680/2021 | 2021-09-08 | ST202107389822 | 2021-07-20 | P/FBW/MDS/1056638/2021 | 2021-09-08 | 0
40 | NANG28 | NANG28 | Chennai | Chennai |  | CHN | indus | R/NN-417567 | 0 | Nominal WIP |  | 2021-03-08 | NANG28 | 4G_FD900_NANG28 | 4G_FD2100_NANG28 | 4G_TD_NANG28 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202104130191 | 2021-04-07 | P/FVC/MDS/1017840/2021 | 2021-05-15 | ST202104130299 | 2021-04-07 | P/FVC/MDS/1017854/2021 | 2021-05-15 | ST202104130434 | 2021-04-07 | P/FVC/MDS/1017864/2021 | 2021-05-15 | ST202104119153 | 2021-04-03 | P/FBW/MDS/1020280/2021 | 2021-05-23 |  | NANG28
41 | HSR127 | HSR127 |  |  |  | ROTN | Indus | R/NN-479007 |  |  |  | 2021-03-23 | HSR127 | 4G_FD900_HSR127 | 4G_FD2100_HSR127 | 4G_TD_HSR127 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498645 | 2021-08-31 | P/FVC/MDS/1060436/2021 | 2021-09-13 | ST202104125402 | 2021-04-05 | P/FVC/MDS/1017792/2021 | 2021-05-15 | ST202104126271 | 2021-04-06 | P/FVC/MDS/1017831/2021 | 2021-05-15 | ST202104119372 | 2021-04-03 | P/FBW/MDS/1020232/2021 | 2021-05-23 |  | HSR127
42 | PDY326 | PDY326 |  |  |  | ROTN | Indus | R/NN-562123 |  |  |  | 2021-03-08 | PDY326 | 4G_FD900_PDY326 | 4G_FD2100_PDY326 | 4G_TD_PDY326 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498656 | 2021-08-31 | P/FVC/MDS/1060446/2021 | 2021-09-13 | ST202103105116 | 2021-03-25 | P/FVC/MDS/1017932/2021 | 2021-05-15 | ST202103106238 | 2021-03-25 | P/FVC/MDS/1017966/2021 | 2021-05-15 | ST202103105621 | 2021-03-25 | P/FBW/MDS/1020093/2021 | 2021-05-22 |  | PDY326
43 | KPVLS4 | KPVLS4 |  |  |  | ROTN | Indus | R/NN-564513 |  |  |  | 2021-03-11 | KPVLS4 | 4G_FD900_KPVLS4 | 4G_FD2100_KPVLS4 | 4G_TD_KPVLS4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498659 | 2021-08-31 | P/FVC/MDS/1060448/2021 | 2021-09-13 | ST202103105115 | 2021-03-25 | P/FVC/MDS/1017931/2021 | 2021-05-15 | ST202103106236 | 2021-03-25 | P/FVC/MDS/1017964/2021 | 2021-05-15 | ST202103099336 | 2021-03-22 | P/FBW/MDS/1019994/2021 | 2021-05-22 |  | KPVLS4
44 | MMNA12 | MMNA12 | Chennai | Chennai |  | CHN | Ascend | ENQTN/000197/2021 | - | Nominals with issues | On air | 2020-10-05 | MMNA12 | 4G_FD900_MMNA12 | 4G_FD2100_MMNA12 | 4G_TD_MMNA12 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202010117245 | 2020-10-21 | P/FVC/MDS/1005856/2020 | 2020-11-10 | ST202010117457 | 2020-10-21 | P/FVC/MDS/1005846/2020 | 2020-11-10 | ST202106358262 | 2021-06-23 | P/FVC/MDS/1055859/2021 | 2021-09-04 | ST202010118823 | 2020-10-22 | P/FBW/MDS/1005939/2020 | 2020-11-10 | SR STATUS CHANGED TO SP AS PER CHARAN TOLD// Toco Changed ASCEND to Own Surrendered by Own on July 7, 2020 and changed to Ascend | MMNA12
45 | CBE730 | CBE730 | Coimbatore | Coimbatore |  | ROTN | Airtel | CBE730 | - | Nominal WIP | Dropped-Canb. | 2021-04-24 | CBE730 | 4G_FD900_CBE730 | 4G_FD2100_CBE730 | 4G_TD_CBE730 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371787 | 2021-07-03 | P/FVC/MDS/1051772/2021 | 2021-08-15 | ST202105295911 | 2021-05-25 | P/FVC/MDS/1045099/2021 | 2021-07-28 |  |  |  |  | ST202106325384 | 2021-06-05 | P/FVC/MDS/1036551/2021 | 2021-06-23 | Partof461sitesSyamaMay'30/TocoChangedtoownbysomasundar2/18/2020 | CBE730
46 | CBE781 | CBE781 | Coimbatore | Coimbatore |  | ROTN | Airtel |  |  | Nominal WIP | Dropped-Canb. | 2021-04-24 | CBE781 | 4G_FD900_CBE781 | 4G_FD2100_CBE781 | 4G_TD_CBE781 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371790 | 2021-07-03 | P/FVC/MDS/1051773/2021 | 2021-08-15 | ST202105295912 | 2021-05-25 | P/FVC/MDS/1045100/2021 | 2021-07-28 |  |  |  |  | ST202106325422 | 2021-06-05 | P/FVC/MDS/1036552/2021 | 2021-06-23 | Jan'20Capacity SR withdraw from Indus on 17-Apr'21 to maintain 1 toco/Site | CBE781
47 | CDBM33 | CDBM33 | Cuddalore | Trichy |  | ROTN | Indus | IN-1543076 | R/NN-559802 | Nominal WIP | On Air | 2021-04-24 | CDBM33 | 4G_FD900_CDBM33 | 4G_FD2100_CDBM33 | 4G_TD_CDBM33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361968 | 2021-06-25 | P/FVC/MDS/1049922/2021 | 2021-08-09 | ST202105295907 | 2021-05-25 | P/FVC/MDS/1045031/2021 | 2021-07-28 |  |  |  |  | ST202105224846 | 2021-05-04 | P/FBW/MDS/1020350/2021 | 2021-05-23 | /R/NN-312158BookedAs30MtrGBTODSiteRequestWithdwanandRebookedasLiteplusAsperSyamaConfirmationR/NN-321218Withdrwanandrebokedastransitionalbasisonjawhar5/15/2019R/NN-336800SPRejectedduetoRentnegoitionthrnbookedas30MGBTMay'29/R/NN-339164SOWithdrwanduetoindussurrendered2/14/2020 | CDBM33
48 | KDKL40 | KDKL40 | Dindigul | Coimbatore |  | ROTN | Indus | IN-1788809 | R/NN-567285 | Nominal WIP | On Air | 2021-03-31 | KDKL40 | 4G_FD900_KDKL40 | 4G_FD2100_KDKL40 | 4G_TD_KDKL40 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371796 | 2021-07-03 | P/FVC/MDS/1051778/2021 | 2021-08-15 | ST202110560207 | 2021-10-14 | P/FVC/MDS/1063712/2021 | 2021-10-22 |  |  |  |  | ST202109499928 | 2021-09-01 | P/FBW/MDS/1060674/2021 | 2021-09-13 | 0 | KDKL40
49 | MDTI35 | MDTI35 | Nagapattinam | Trichy |  | ROTN | Airtel | MDTI35 | - | Nominal WIP | SO | 2021-04-24 | MDTI35 | 4G_FD900_MDTI35 | 4G_FD2100_MDTI35 | 4G_TD_MDTI35 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362361 | 2021-06-25 | P/FVC/MDS/1049981/2021 | 2021-08-09 | ST202105295914 | 2021-05-25 | P/FVC/MDS/1045102/2021 | 2021-07-28 |  |  |  |  | ST202106325424 | 2021-06-05 | P/FVC/MDS/1036554/2021 | 2021-06-23 | SR No R/NN-438713 withdrawn on Dec 10, 2020 and Alloted to Own basis Arvind's mail | MDTI35
50 | MDU443 | MDU443 | Madurai | Madurai |  | ROTN | Airtel | MDU443 | - | Nominal WIP | Dropped-Canb. | 2021-04-24 | MDU443 | 4G_FD900_MDU443 | 4G_FD2100_MDU443 | 4G_TD_MDU443 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371802 | 2021-07-03 | P/FVC/MDS/1051781/2021 | 2021-08-15 | ST202105295913 | 2021-05-25 | P/FVC/MDS/1045101/2021 | 2021-07-28 |  |  |  |  | ST202106325423 | 2021-06-05 | P/FVC/MDS/1036553/2021 | 2021-06-23 | 0 | MDU443
51 | NBLOCK | NBLOCK | Chennai | Chennai |  | CHN | Airtel | NBLOCK | - | Nominal WIP | Dropped | 2021-04-24 | NBLOCK | 4G_FD900_NBLOCK | 4G_FD2100_NBLOCK | 4G_TD_NBLOCK | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106325016 | 2021-06-05 | P/FVC/MDS/1036782/2021 | 2021-06-24 | ST202105295927 | 2021-05-25 | P/FVC/MDS/1045111/2021 | 2021-07-28 | ST202105295025 | 2021-05-25 | P/FVC/MDS/1036495/2021 | 2021-06-23 | ST202106325376 | 2021-06-05 | P/FVC/MDS/1036542/2021 | 2021-06-23 | 0 | NBLOCK
52 | THRVOY | THRVOY | Thiruvallur | Chennai |  | ROTN | Indus | IN-1389291 | R/NN-466105 | Nominal WIP | On Air | 2021-04-26 | THRVOY | 4G_FD900_THRVOY | 4G_FD2100_THRVOY | 4G_TD_THRVOY | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202107371816 | 2021-07-03 | P/FVC/MDS/1051789/2021 | 2021-08-15 | ST202105296015 | 2021-05-25 | P/FVC/MDS/1045131/2021 | 2021-07-28 | ST202105295066 | 2021-05-25 | P/FVC/MDS/1036503/2021 | 2021-06-23 | ST202107389830 | 2021-07-20 | P/FBW/MDS/1056646/2021 | 2021-09-08 | 0 | THRVOY
53 | TIRU38 | TIRU38 | Chennai | Chennai |  | CHN | Airtel | TIRU38 |  | Nominals with issues | Dropped-Canb. | 2021-03-04 | TIRU38 | 4G_FD900_TIRU38 | 4G_FD2100_TIRU38 | 4G_TD_TIRU38 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106325018 | 2021-06-05 | P/FVC/MDS/1036784/2021 | 2021-06-24 | ST202105295928 | 2021-05-25 | P/FVC/MDS/1045112/2021 | 2021-07-28 | ST202105295026 | 2021-05-25 | P/FVC/MDS/1036497/2021 | 2021-06-23 | ST202106325378 | 2021-06-05 | P/FVC/MDS/1036545/2021 | 2021-06-23 | 0 | TIRU38
54 | TRY357 | TRY357 | Tiruchirappalli | Trichy |  | ROTN | Airtel | TRY357 | - | Nominal WIP | Dropped-Canb. | 2021-04-24 | TRY357 | 4G_FD900_TRY357 | 4G_FD2100_TRY357 | 4G_TD_TRY357 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371821 | 2021-07-03 | P/FVC/MDS/1051792/2021 | 2021-08-15 | ST202105295917 | 2021-05-25 | P/FVC/MDS/1045103/2021 | 2021-07-28 |  |  |  |  | ST202106325425 | 2021-06-05 | P/FVC/MDS/1036555/2021 | 2021-06-23 | 0 | TRY357
55 | NGL131 | NGL131 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-1928620 | R/NN-617710 | Nominal WIP | On Air | 2021-05-10 | NGL131 | 4G_FD900_NGL131 | 4G_FD2100_NGL131 | 4G_TD_NGL131 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371838 | 2021-07-03 | P/FVC/MDS/1051803/2021 | 2021-08-15 | ST202105295959 | 2021-05-25 | P/FVC/MDS/1045124/2021 | 2021-07-28 | ST202103087017 | 2020-07-01 | P/FVC/MDS/1014387/2021 | 2021-04-06 | ST202106325484 | 2021-06-05 | P/FVC/MDS/1036566/2021 | 2021-06-23 | 0 | NGL131
56 | SRIDMA | SRIDMA | Tiruchirappalli | Trichy |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2021-04-26 | SRIDMA | 4G_FD900_SRIDMA | 4G_FD2100_SRIDMA | 4G_TD_SRIDMA | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202108498669 | 2021-08-31 | P/FVC/MDS/1060457/2021 | 2021-09-13 | ST202108498292 | 2021-08-31 | P/FVC/MDS/1060501/2021 | 2021-09-13 | ST202007021615 | 2020-07-09 | P/FVC/MDS/1000527/2020 | 2020-07-18 | ST202109499933 | 2021-09-01 | P/FBW/MDS/1060679/2021 | 2021-09-13 | SOCanceledbyATConOct15,2020 | SRIDMA
57 | RIVIE1 | RIVIE1 | Chennai | Chennai |  | CHN | Airtel | 0 | 0 | Nominal WIP |  | 2021-05-06 | RIVIE1 | 4G_FD900_RIVIE1 | 4G_FD2100_RIVIE1 | 4G_TD_RIVIE1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106325020 | 2021-06-05 | P/FVC/MDS/1036786/2021 | 2021-06-24 | ST202105295931 | 2021-05-25 | P/FVC/MDS/1045114/2021 | 2021-07-28 | ST202105295028 | 2021-05-25 | P/FVC/MDS/1036499/2021 | 2021-06-23 | ST202106325380 | 2021-06-05 | P/FVC/MDS/1036547/2021 | 2021-06-23 |  | RIVIE1
58 | SLM366 | SLM366 |  |  |  | ROTN | INDUS | R/NN-470302 |  |  |  | 2021-04-29 | SLM366 | 4G_FD900_SLM366 | 4G_FD2100_SLM366 | 4G_TD_SLM366 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498651 | 2021-08-31 | P/FVC/MDS/1060441/2021 | 2021-09-13 | ST202105295922 | 2021-05-25 | P/FVC/MDS/1045108/2021 | 2021-07-28 | ST202105295005 | 2021-05-25 | P/FVC/MDS/1036491/2021 | 2021-06-23 | ST202106326247 | 2021-06-06 | P/FVC/MDS/1036848/2021 | 2021-06-24 |  | SLM366
59 | TVLR75 | TVLR75 |  |  |  | ROTN | Indus | IN-1867364 | R/NN-569197 |  |  | 2021-04-15 | TVLR75 | 4G_FD900_TVLR75 | 4G_FD2100_TVLR75 | 4G_TD_TVLR75 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106329348 | 2021-06-07 | P/FVC/MDS/1036809/2021 | 2021-06-24 | ST202105296034 | 2021-05-25 | P/FVC/MDS/1045138/2021 | 2021-07-28 | ST202105295088 | 2021-05-25 | P/FVC/MDS/1036508/2021 | 2021-06-23 | ST202106326220 | 2021-06-06 | P/FVC/MDS/1036577/2021 | 2021-06-23
60 | BRGR4 | BRGR04 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/22315 | T20TN08264 | Nominal WIP | On Air | 2021-04-21 | BRGR04 | 4G_FD900_BRGR04 | 4G_FD2100_BRGR04 | 4G_TD_BRGR04 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371786 | 2021-07-03 | P/FVC/MDS/1050306/2021 | 2021-08-11 | ST202105294096 | 2021-05-25 | P/FVC/MDS/1036623/2021 | 2021-06-23 |  |  |  |  | ST202105228454 | 2021-05-04 | P/FBW/MDS/1020364/2021 | 2021-05-23 | Punched to Indus on 13-Apr'21 Paralel SR withdraw from Indus on 17-Apr'21 to maintain 1 toco/Site Indus SP also rejected COW - 17-Apr'21 against ATC providing RTT option near to Nominal | BRGR4
61 | HRUR7 | HRUR07 | Dharmapuri | Vellore |  | ROTN | Indus | IN-1882708 | R/NN-569385 | Nominal WIP | SR | 2021-04-19 | HRUR07 | 4G_FD900_HRUR07 | 4G_FD2100_HRUR07 | 4G_TD_HRUR07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371793 | 2021-07-03 | P/FVC/MDS/1051775/2021 | 2021-08-15 | ST202105293996 | 2021-05-25 | P/FVC/MDS/1036617/2021 | 2021-06-23 |  |  |  |  | ST202105228457 | 2021-05-04 | P/FBW/MDS/1020367/2021 | 2021-05-23 | Indus SR R/NN-439855 withdrawn to reposition | HRUR7
62 | HSR155 | HSR155 | Krishnagiri | Vellore |  | ROTN | Indus | IN-1909517 | R/NN-570182 | Nominal WIP | On Air | 2021-04-17 | HSR155 | 4G_FD900_HSR155 | 4G_FD2100_HSR155 | 4G_TD_HSR155 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371794 | 2021-07-03 | P/FVC/MDS/1051776/2021 | 2021-08-15 | ST202105293997 | 2021-05-25 | P/FVC/MDS/1036618/2021 | 2021-06-23 | ST202210548815 | 2022-10-11 | P/FVC/MDS/1113946/2022 | 2022-10-21 | ST202105228512 | 2021-05-04 | P/FBW/MDS/1020369/2021 | 2021-05-23 | Nominal withdrawan from TVI , 9-Apr | HSR155
63 | ILNGD6 | ILNGD6 | Chennai | Chennai |  | CHN | Indus | IN-1924617 | R/NN-617458 | Nominal WIP | On air | 2021-04-15 | ILNGD6 | 4G_FD900_ILNGD6 | 4G_FD2100_ILNGD6 | 4G_TD_ILNGD6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106325010 | 2021-06-05 | P/FVC/MDS/1036776/2021 | 2021-06-24 | ST202105293328 | 2021-05-25 | P/FVC/MDS/1036590/2021 | 2021-06-23 | ST202105294813 | 2021-05-25 | P/FVC/MDS/1036474/2021 | 2021-06-23 | ST202106325320 | 2021-06-05 | P/FVC/MDS/1036534/2021 | 2021-06-23 | Indus SR R/NN-320581 withdrawn on Dec 21 and realloted to Ascend basis Muthu sir's/Jawahar's DTA response on Dec 17, 2020 SR Withdrawal done by Mistake , Punched again on 12-Apr'21 | ILNGD6
64 | KOTTAI | KOTTAI | Thiruvallur | Chennai |  | ROTN | Ascend | 0 | - | Nominals with issues | Dropped-Canb. | 2021-04-10 | KOTTAI | 4G_FD900_KOTTAI | 4G_FD2100_KOTTAI | 4G_TD_KOTTAI | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371797 | 2021-07-03 | P/FVC/MDS/1051779/2021 | 2021-08-15 | ST202105293416 | 2021-05-25 | P/FVC/MDS/1036596/2021 | 2021-06-23 |  |  |  |  | ST202105228550 | 2021-05-04 | P/FBW/MDS/1020377/2021 | 2021-05-23 | 0 | Kottai
65 | KRKL21 | KRKL21 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1385505 | R/NN-430878 | Nominal WIP | SO | 2021-04-22 | KRKL21 | 4G_FD900_KRKL21 | 4G_FD2100_KRKL21 | 4G_TD_KRKL21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371801 | 2021-07-03 | P/FVC/MDS/1051780/2021 | 2021-08-15 | ST202105294179 | 2021-05-25 | P/FVC/MDS/1036628/2021 | 2021-06-23 | ST202211684511 | 2022-11-05 | P/FVC/MDS/1114592/2022 | 2022-11-15 | ST202105224819 | 2021-05-04 | P/FBW/MDS/1020341/2021 | 2021-05-23 | AmendedSOGivenduetoAGLconversionconfirmedbysyama3/4/2019/SOSurrenderedbyArulWithdrwanbySCMOct18th/ATCsurrenderedonOct29/R/NN-373664SPRejectedduetooptionnotok/R/NN-424288/SRwithdrwanduetoDAY1TDDandrepunched | KRKL21
66 | MHNR5 | MHNR05 | Namakkal | Coimbatore |  | ROTN | Indus | IN-1924264 | R/NN-617436 | Nominal WIP | On Air | 2021-04-19 | MHNR05 | 4G_FD900_MHNR05 | 4G_FD2100_MHNR05 | 4G_TD_MHNR05 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202107371804 | 2021-07-03 | P/FVC/MDS/1051782/2021 | 2021-08-15 | ST202105294034 | 2021-05-25 | P/FVC/MDS/1036621/2021 | 2021-06-23 | ST202105294955 | 2021-05-25 | P/FVC/MDS/1036488/2021 | 2021-06-23 | ST202106359627 | 2021-06-24 | P/FBW/MDS/1051747/2021 | 2021-08-15 | 0 | MHNR5
67 | NGL117 | NGL117 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22517 |  | Nominal WIP | On Air | 2021-04-21 | NGL117 | 4G_FD900_NGL117 | 4G_FD2100_NGL117 | 4G_TD_NGL117 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371805 | 2021-07-03 | P/FVC/MDS/1051784/2021 | 2021-08-15 | ST202105294098 | 2021-05-25 | P/FVC/MDS/1036625/2021 | 2021-06-23 |  |  |  |  | ST202105224478 | 2021-05-04 | P/FBW/MDS/1020321/2021 | 2021-05-23 | 0 | NGL117
68 | PLCH49 | PLCH49 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1924116 | R/NN-617429 | Nominal WIP | Dropped | 2021-04-19 | PLCH49 | 4G_FD900_PLCH49 | 4G_FD2100_PLCH49 | 4G_TD_PLCH49 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371806 | 2021-07-03 | P/FVC/MDS/1051785/2021 | 2021-08-15 | ST202105294033 | 2021-05-25 | P/FVC/MDS/1036620/2021 | 2021-06-23 |  |  |  |  | ST202105224840 | 2021-05-04 | P/FBW/MDS/1020344/2021 | 2021-05-23 | SR withdrawn from current TOCO and realloted to ATC on Mar 28, 2021 Punched to Indus on 13-Apr'21 Paralel SR withdraw from ATC on 17-Apr'21 to maintain 1 toco/Site | PLCH49
69 | PNKLM2 | PNKLM2 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-1794190 | R/NN-567467 | Nominals with issues | On Air | 2021-03-16 | PNKLM2 | 4G_FD900_PNKLM2 | 4G_FD2100_PNKLM2 | 4G_TD_PNKLM2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371809 | 2021-07-03 | P/FVC/MDS/1051786/2021 | 2021-08-15 | ST202105293417 | 2021-05-25 | P/FVC/MDS/1036597/2021 | 2021-06-23 |  |  |  |  | ST202105224480 | 2021-05-04 | P/FBW/MDS/1020323/2021 | 2021-05-23 | 20-20-RestofUrban | PNKLM2
70 | PNPM47 | PNPM47 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22533 | T21TN02824 | Nominal WIP | On Air | 2021-04-13 | PNPM47 | 4G_FD900_PNPM47 | 4G_FD2100_PNPM47 | 4G_TD_PNPM47 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202112627241 | 2021-12-24 | P/FVC/MDS/1070574/2022 | 2022-01-03 | ST202112604973 | 2021-12-07 | P/FVC/MDS/1068842/2021 | 2021-12-15 | ST202212811931 | 2022-12-14 | P/FVC/MDS/1119364/2022 | 2022-12-20 | ST202112627263 | 2021-12-24 | P/FBW/MDS/1070564/2022 | 2022-01-03 | 0 | PNPM47
71 | RAJAK6 | RAJAK6 | Chennai | Chennai |  | CHN | Indus | IN-1789232 | R/NN-567335 | Nominal WIP | On air | 2021-04-15 | RAJAK6 | 4G_FD900_RAJAK6 | 4G_FD2100_RAJAK6 | 4G_TD_RAJAK6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106325008 | 2021-06-05 | P/FVC/MDS/1036774/2021 | 2021-06-24 | ST202105293326 | 2021-05-25 | P/FVC/MDS/1036588/2021 | 2021-06-23 | ST202105294777 | 2021-05-25 | P/FVC/MDS/1036470/2021 | 2021-06-23 | ST202106325284 | 2021-06-05 | P/FVC/MDS/1036532/2021 | 2021-06-23 | Ascend surrendered SR on Dec 7, 2020 and realloted to Airtel | RAJAK6
72 | TVML68 | TVML68 | Tiruvannamalai | Vellore |  | ROTN | Indus | IN-1882712 | R/NN-569487 | Nominal WIP | Dropped-Canb. | 2021-04-15 | TVML68 | 4G_FD900_TVML68 | 4G_FD2100_TVML68 | 4G_TD_TVML68 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371824 | 2021-07-03 | P/FVC/MDS/1051794/2021 | 2021-08-15 | ST202105293644 | 2021-05-25 | P/FVC/MDS/1036609/2021 | 2021-06-23 |  |  |  |  | ST202105228516 | 2021-05-04 | P/FBW/MDS/1020373/2021 | 2021-05-23 | Priority Working by Indus + ATC - 1-Apr-21 | TVML68
73 | UDGDI6 | UDGDI6 | Thoothukkudi | Madurai |  | ROTN | ATC | TN/TH/AT/22257 | T20TN07272 | Nominal WIP | Dropped-Canb. | 2021-04-13 | UDGDI6 | 4G_FD900_UDGDI6 | 4G_FD2100_UDGDI6 | 4G_TD_UDGDI6 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371825 | 2021-07-03 | P/FVC/MDS/1051795/2021 | 2021-08-15 | ST202105293418 | 2021-05-25 | P/FVC/MDS/1036598/2021 | 2021-06-23 |  |  |  |  | ST202105224484 | 2021-05-04 | P/FBW/MDS/1020327/2021 | 2021-05-23 | 0 | UDGDI6
74 | TVTY33 | TVTY33 | Chennai | Chennai |  | CHN | ATC | TN/CH/AT/22464 |  | Nominal WIP | Dropped-Canb. | 2021-04-21 | TVTY33 | 4G_FD900_TVTY33 | 4G_FD2100_TVTY33 | 4G_TD_TVTY33 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106325013 | 2021-06-05 | P/FVC/MDS/1036779/2021 | 2021-06-24 | ST202105293330 | 2021-05-25 | P/FVC/MDS/1036592/2021 | 2021-06-23 | ST202105294815 | 2021-05-25 | P/FVC/MDS/1036477/2021 | 2021-06-23 | ST202106325323 | 2021-06-05 | P/FVC/MDS/1036538/2021 | 2021-06-23 | Owner Backout due to Public Issue - Arul mail 3-may'21 SO Surrender | TVTY33
75 | PRNI8 | PRNI08 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/22443 | T21TN01780 | Nominal WIP | SO | 2021-04-13 | PRNI08 | 4G_FD900_PRNI08 | 4G_FD2100_PRNI08 | 4G_TD_PRNI08 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202112627231 | 2021-12-24 | P/FVC/MDS/1070566/2022 | 2022-01-03 | ST202112627245 | 2021-12-24 | P/FVC/MDS/1070546/2022 | 2022-01-03 | ST202105294865 | 2021-05-25 | P/FVC/MDS/1036482/2021 | 2021-06-23 | ST202112627255 | 2021-12-24 | P/FBW/MDS/1070556/2022 | 2022-01-03 | 0 | PRNI8
76 | AGDI8 | AGDI08 | Pudukkottai | Trichy |  | ROTN | ATC | TN/PU/AT/22477 | T21TN02472 | Nominal WIP | Dropped-Canb. | 2021-04-21 | AGDI08 | 4G_FD900_AGDI08 | 4G_FD2100_AGDI08 | 4G_TD_AGDI08 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371842 | 2021-07-03 | P/FVC/MDS/1051804/2021 | 2021-08-15 | ST202105294097 | 2021-05-25 | P/FVC/MDS/1036624/2021 | 2021-06-23 |  |  |  |  | ST202105224816 | 2021-05-04 | P/FBW/MDS/1020338/2021 | 2021-05-23 | 0 | AGDI8
77 | SIGRI3 | SIGRI3 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/22591 | T21TN03074 | Nominal WIP | On Air | 2021-04-13 | SIGRI3 | 4G_FD900_SIGRI3 | 4G_FD2100_SIGRI3 | 4G_TD_SIGRI3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371849 | 2021-07-03 | P/FVC/MDS/1051807/2021 | 2021-08-15 | ST202105293602 | 2021-05-25 | P/FVC/MDS/1036601/2021 | 2021-06-23 |  |  |  |  | ST202105224814 | 2021-05-04 | P/FBW/MDS/1020336/2021 | 2021-05-23 | 0 | SIGRI3
78 | TUT139 | TUT139 | Thoothukkudi | Madurai |  | ROTN | INDUS |  |  |  | On Air | 2021-07-09 | TUT139 | 4G_FD900_TUT139 | 4G_FD2100_TUT139 | 4G_TD_TUT139 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107386750 | 2021-07-17 | P/FVC/MDS/1051577/2021 | 2021-08-14 | ST202105293980 | 2021-05-25 | P/FVC/MDS/1036613/2021 | 2021-06-23 |  |  |  |  | ST202105224482 | 2021-05-04 | P/FBW/MDS/1020325/2021 | 2021-05-23 | SR withdrawn from current TOCO and realloted to ATC on Mar 28, 2021 SO Issued R/NN-570156 withdrawn by indus as owner backed out Jawahar mail 25-Apr'21 New Indus SR Punched on 26-Apr'21 | TUT139
79 | MRCNA3 | MRCNA3 | Chennai | Chennai |  | CHN | Srigom | - | 0 | Nominal WIP | On air | 2021-04-26 | MRCNA3 | 4G_FD900_MRCNA3 | 4G_FD2100_MRCNA3 | 4G_TD_MRCNA3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106364545 | 2021-06-28 | P/FVC/MDS/1050304/2021 | 2021-08-09 | ST202106357454 | 2021-06-23 | P/FVC/MDS/1060952/2021 | 2021-09-14 | ST202107369683 | 2021-07-01 | P/FVC/MDS/1056084/2021 | 2021-09-07 | ST202106325324 | 2021-06-05 | P/FVC/MDS/1036539/2021 | 2021-06-23 |  | MRCNA3
80 | CBE862 | CBE862 |  |  |  | ROTN | Indus | R/NN-562079 |  |  |  | 2021-04-07 | CBE862 | 4G_FD900_CBE862 | 4G_FD2100_CBE862 | 4G_TD_CBE862 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498655 | 2021-08-31 | P/FVC/MDS/1060445/2021 | 2021-09-13 | ST202105293251 | 2021-05-25 | P/FVC/MDS/1036579/2021 | 2021-06-23 | ST202104150103 | 2021-04-16 | P/FVC/MDS/1018120/2021 | 2021-05-16 | ST202105224844 | 2021-05-04 | P/FBW/MDS/1020348/2021 | 2021-05-23 |  | CBE862
81 | CBE864 | CBE864 |  |  |  | ROTN | Indus | R/NN-562251 |  |  |  | 2021-04-07 | CBE864 | 4G_FD900_CBE864 | 4G_FD2100_CBE864 | 4G_TD_CBE864 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498658 | 2021-08-31 | P/FVC/MDS/1060447/2021 | 2021-09-13 | ST202105293252 | 2021-05-25 | P/FVC/MDS/1036580/2021 | 2021-06-23 | ST202104150104 | 2021-04-16 | P/FVC/MDS/1018121/2021 | 2021-05-16 | ST202105224845 | 2021-05-04 | P/FBW/MDS/1020349/2021 | 2021-05-23 |  | CBE864
82 | UPPUP1 | UPPUP1 |  |  |  | ROTN |  |  |  |  | On Air |  | UPPUP1 | 4G_FD900_UPPUP1 | 4G_FD2100_UPPUP1 | 4G_TD_UPPUP1 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371829 | 2021-07-03 | P/FVC/MDS/1051797/2021 | 2021-08-15 | ST202105293995 | 2021-05-25 | P/FVC/MDS/1036616/2021 | 2021-06-23 | ST202105294913 | 2021-05-25 | P/FVC/MDS/1036487/2021 | 2021-06-23 | ST202108430517 | 2021-08-17 | P/FBW/MDS/1056075/2021 | 2021-09-07 | 0
83 | IYAP31 | IYAP31 | Chennai | Chennai |  | CHN | Ascend | 108 | - | Nominal WIP | SO | 2021-04-03 | IYAP31 | 4G_FD900_IYAP31 | 4G_FD2100_IYAP31 | 4G_TD_IYAP31 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106324992 | 2021-06-05 | P/FVC/MDS/1036760/2021 | 2021-06-24 | ST202105293276 | 2021-05-25 | P/FVC/MDS/1036585/2021 | 2021-06-23 | ST202105294748 | 2021-05-25 | P/FVC/MDS/1036466/2021 | 2021-06-23 | ST202105224268 | 2021-05-04 | P/FBW/MDS/1020297/2021 | 2021-05-23 | 0 | IYAP31
84 | MTGPT4 | MTGPT4 | Namakkal | Coimbatore |  | ROTN | Ascend |  |  | Nominal WIP |  | 2021-04-10 | MTGPT4 | 4G_FD900_MTGPT4 | 4G_FD2100_MTGPT4 | 4G_TD_MTGPT4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362636 | 2021-06-26 | P/FVC/MDS/1049997/2021 | 2021-08-09 | ST202104148069 | 2021-04-15 | P/FVC/MDS/1018017/2021 | 2021-05-15 |  |  |  |  | ST202104148902 | 2021-04-15 | P/FBW/MDS/1018075/2021 | 2021-05-16 | 0 | MTGPT4
85 | TUT141 | TUT141 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-1878805 | R/NN-569404 | Nominal WIP | Dropped-Canb. | 2021-04-10 | TUT141 | 4G_FD900_TUT141 | 4G_FD2100_TUT141 | 4G_TD_TUT141 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202106363097 | 2021-06-26 | P/FVC/MDS/1050096/2021 | 2021-08-09 | ST202104148124 | 2021-04-15 | P/FVC/MDS/1018030/2021 | 2021-05-15 | ST202104151709 | 2021-04-17 | P/FVC/MDS/1017576/2021 | 2021-05-13 | ST202105224483 | 2021-05-04 | P/FBW/MDS/1020326/2021 | 2021-05-23 | Priority Working by Indus + ATC - 1-Apr-21 | TUT141
86 | SNKT11 | SNKT11 | Tirunelveli | Madurai |  | ROTN | Ascend |  |  | Nominals with issues | SR | 2021-03-31 | SNKT11 | 4G_FD900_SNKT11 | 4G_FD2100_SNKT11 | 4G_TD_SNKT11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364112 | 2021-06-28 | P/FVC/MDS/1050138/2021 | 2021-08-09 | ST202104147716 | 2021-04-15 | P/FVC/MDS/1017994/2021 | 2021-05-15 |  |  |  |  | ST202104148721 | 2021-04-15 | P/FBW/MDS/1018054/2021 | 2021-05-16 | SP R/NN-565164 Rejected on Mar 10, 2021 due to Low AGL | SNKT11
87 | SPKL13 | SPKL13 | Chennai | Chennai |  | CHN | Ascend |  |  | Nominal WIP | On air | 2021-04-10 | SPKL13 | 4G_FD900_SPKL13 | 4G_FD2100_SPKL13 | 4G_TD_SPKL13 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202104149038 | 2021-04-15 | P/FVC/MDS/1017877/2021 | 2021-05-15 | ST202104149074 | 2021-04-15 | P/FVC/MDS/1017888/2021 | 2021-05-15 | ST202104149158 | 2021-04-15 | P/FVC/MDS/1017905/2021 | 2021-05-15 | ST202104149635 | 2021-04-16 | P/FBW/MDS/1018097/2021 | 2021-05-16 | SO Surrendered by Ascend on Dec 28, 2020 and SCM Canceled on Jan 2, 2021 | SPKL13
88 | TPTR22 | TPTR22 | Vellore | Vellore |  | ROTN | INDUS |  |  | Nominal WIP | Dropped | 2021-03-22 | TPTR22 | 4G_FD900_TPTR22 | 4G_FD2100_TPTR22 | 4G_TD_TPTR22 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364352 | 2021-06-28 | P/FVC/MDS/1050270/2021 | 2021-08-09 | ST202104147717 | 2021-04-15 | P/FVC/MDS/1017995/2021 | 2021-05-15 |  |  |  |  | ST202104148722 | 2021-04-15 | P/FBW/MDS/1018055/2021 | 2021-05-16 | Partof461sitesSyamaMay'30 | TPTR22
89 | TPTR23 | TPTR23 | Vellore | Vellore |  | ROTN | INDUS |  |  | Nominal WIP | Dropped | 2021-04-08 | TPTR23 | 4G_FD900_TPTR23 | 4G_FD2100_TPTR23 | 4G_TD_TPTR23 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202106364353 | 2021-06-28 | P/FVC/MDS/1050271/2021 | 2021-08-09 | ST202104148125 | 2021-04-15 | P/FVC/MDS/1018031/2021 | 2021-05-15 | ST202104150498 | 2021-04-16 | P/FVC/MDS/1017531/2021 | 2021-05-13 | ST202105228515 | 2021-05-04 | P/FBW/MDS/1020372/2021 | 2021-05-23 | Partof461sitesSyamaMay'30 | TPTR23
90 | NGPT5 | NGPT05 | Namakkal | Coimbatore |  | ROTN | INDUS |  |  | Nominal WIP | On Air | 2021-04-01 | NGPT05 | 4G_FD900_NGPT05 | 4G_FD2100_NGPT05 | 4G_TD_NGPT05 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364408 | 2021-06-28 | P/FVC/MDS/1050278/2021 | 2021-08-09 | ST202104148020 | 2021-04-15 | P/FVC/MDS/1018008/2021 | 2021-05-15 |  |  |  |  | ST202104148895 | 2021-04-15 | P/FBW/MDS/1018068/2021 | 2021-05-16 | 20-20-RestofUrban/R/NN-391636SOsurrenederdbyindusMani6/13/2020. SR repunched on Feb 8, 2021 basis repositioning suggested by Judah | NGPT5
91 | CNPT9 | CNPT09 | Dindigul | Coimbatore |  | ROTN | Indus |  |  | Nominal WIP | Drop | 2021-03-24 | CNPT09 | 4G_FD900_CNPT09 | 4G_FD2100_CNPT09 | 4G_TD_CNPT09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364412 | 2021-06-28 | P/FVC/MDS/1050282/2021 | 2021-08-09 | ST202104147711 | 2021-04-15 | P/FVC/MDS/1017989/2021 | 2021-05-15 |  |  |  |  | ST202104148716 | 2021-04-15 | P/FBW/MDS/1018049/2021 | 2021-05-16 | SOCanceledbyATConSep12,2020(Muthusir/Arulmail)andgiventoowntoco | CNPT9
92 | HSR141 | HSR141 | Krishnagiri | Vellore |  | ROTN | INDUS |  |  | Nominal WIP | SRB(Surrender) | 2021-03-26 | HSR141 | 4G_FD900_HSR141 | 4G_FD2100_HSR141 | 4G_TD_HSR141 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364414 | 2021-06-28 | P/FVC/MDS/1050284/2021 | 2021-08-09 | ST202104148009 | 2021-04-15 | P/FVC/MDS/1018003/2021 | 2021-05-15 |  |  |  |  | ST202104148813 | 2021-04-15 | P/FBW/MDS/1018063/2021 | 2021-05-16 | 0 | HSR141
93 | CNGM10 | CNGM10 | Tiruvannamalai | Vellore |  | ROTN | Ascend |  |  | Nominal WIP | On Air | 2021-04-08 | CNGM10 | 4G_FD900_CNGM10 | 4G_FD2100_CNGM10 | 4G_TD_CNGM10 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202108430715 | 2021-08-17 | P/FVC/MDS/1059667/2021 | 2021-09-12 | ST202108498215 | 2021-08-31 | P/FVC/MDS/1060462/2021 | 2021-09-13 |  |  |  |  | ST202108430503 | 2021-08-17 | P/FBW/MDS/1056061/2021 | 2021-09-07 | Nominal pulled from TVI by deployment on Dec 29 and reallotted to Ascend on Dec 30 | CNGM10
94 | KARNAP | KARNAP | Vellore | Vellore |  | ROTN | INDUS |  |  | Nominal WIP | On Air | 2021-04-01 | KARNAP | 4G_FD900_KARNAP | 4G_FD2100_KARNAP | 4G_TD_KARNAP | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106364509 | 2021-06-28 | P/FVC/MDS/1050295/2021 | 2021-08-09 | ST202104148023 | 2021-04-15 | P/FVC/MDS/1018011/2021 | 2021-05-15 | ST202104150497 | 2021-04-16 | P/FVC/MDS/1017530/2021 | 2021-05-13 | ST202107389828 | 2021-07-20 | P/FBW/MDS/1056644/2021 | 2021-09-08 | SP R/NN-567497 on Mar 19, 2021 due to low agl pushed by Indus against ask | KARNAP
95 | GDLR13 | GDLR13 | The Nilgiris | Coimbatore |  | ROTN | INDUS |  |  | Nominal WIP | SR | 2021-04-01 | GDLR13 | 4G_FD900_GDLR13 | 4G_FD2100_GDLR13 | 4G_TD_GDLR13 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366831 | 2021-06-30 | P/FVC/MDS/1050179/2021 | 2021-08-09 | ST202104148068 | 2021-04-15 | P/FVC/MDS/1018016/2021 | 2021-05-15 |  |  |  |  | ST202104148901 | 2021-04-15 | P/FBW/MDS/1018074/2021 | 2021-05-16 | BSNL confirmed not possible and realloted to Indus on Mar 29, 2021 | GDLR13
96 | TUT132 | TUT132 | Thoothukkudi | Madurai |  | ROTN | Indus |  |  | Nominal WIP | Dropped-Canb. | 2021-04-21 | TUT132 | 4G_FD900_TUT132 | 4G_FD2100_TUT132 | 4G_TD_TUT132 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366905 | 2021-06-30 | P/FVC/MDS/1050207/2021 | 2021-08-09 | ST202104148122 | 2021-04-15 | P/FVC/MDS/1018028/2021 | 2021-05-15 |  |  |  |  | ST202104148953 | 2021-04-15 | P/FBW/MDS/1018086/2021 | 2021-05-16 | Priority Working by Indus + ATC - 1-Apr-21 R/NN-560363 - SO SR was not active , Indus Jawahr mail 15-May'21 | TUT132
97 | KUMB74 | KUMB74 | Thanjavur | Trichy |  | ROTN | INDUS |  |  | Nominal WIP | On Air | 2021-04-01 | KUMB74 | 4G_FD900_KUMB74 | 4G_FD2100_KUMB74 | 4G_TD_KUMB74 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363682 | 2021-06-28 | P/FVC/MDS/1050257/2021 | 2021-08-09 | ST202104148026 | 2021-04-15 | P/FVC/MDS/1018014/2021 | 2021-05-15 |  |  |  |  | ST202104148899 | 2021-04-15 | P/FBW/MDS/1018072/2021 | 2021-05-16 | 0 | KUMB74
98 | ERPUR1 | ERPUR1 | Thanjavur | Trichy |  | ROTN | Indus |  |  | Nominal WIP |  | 2021-04-03 | ERPUR1 | 4G_FD900_ERPUR1 | 4G_FD2100_ERPUR1 | 4G_TD_ERPUR1 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363670 | 2021-06-28 | P/FVC/MDS/1050245/2021 | 2021-08-09 | ST202104148071 | 2021-04-15 | P/FVC/MDS/1018019/2021 | 2021-05-15 |  |  |  |  | ST202104148944 | 2021-04-15 | P/FBW/MDS/1018077/2021 | 2021-05-16 | 0 | ERPUR1
99 | VENCD2 | VENCD2 | Kanniyakumari | Madurai |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2021-03-25 | VENCD2 | 4G_FD900_VENCD2 | 4G_FD2100_VENCD2 | 4G_TD_VENCD2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363658 | 2021-06-28 | P/FVC/MDS/1050233/2021 | 2021-08-09 | ST202104147718 | 2021-04-15 | P/FVC/MDS/1017996/2021 | 2021-05-15 |  |  |  |  | ST202104148806 | 2021-04-15 | P/FBW/MDS/1018056/2021 | 2021-05-16 | 0 | VENCD2
100 | KODKZ | KODKZ0 | Kanniyakumari | Madurai |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2021-04-05 | KODKZ0 | 4G_FD900_KODKZ0 | 4G_FD2100_KODKZ0 | 4G_TD_KODKZ0 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202108498668 | 2021-08-31 | P/FVC/MDS/1060456/2021 | 2021-09-13 | ST202108498291 | 2021-08-31 | P/FVC/MDS/1060500/2021 | 2021-09-13 | ST202109499808 | 2021-09-01 | P/FVC/MDS/1060722/2021 | 2021-09-13 | ST202109499932 | 2021-09-01 | P/FBW/MDS/1060678/2021 | 2021-09-13 | 0 | KODKZ
101 | VPTO13 | VPTO13 | Chennai | Chennai |  | CHN | Indus | R/NN-568591 | 0 | Nominal WIP |  | 2021-04-08 | VPTO13 | 4G_FD900_VPTO13 | 4G_FD2100_VPTO13 | 4G_TD_VPTO13 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202104149037 | 2021-04-15 | P/FVC/MDS/1017876/2021 | 2021-05-15 | ST202104149079 | 2021-04-15 | P/FVC/MDS/1017893/2021 | 2021-05-15 | ST202104149157 | 2021-04-15 | P/FVC/MDS/1017904/2021 | 2021-05-15 | ST202104149634 | 2021-04-16 | P/FBW/MDS/1018096/2021 | 2021-05-16 |  | VPTO13
102 | MDU494 | MDU494 |  |  |  | ROTN | Indus | R/NN-568011 |  |  |  | 2021-04-07 | MDU494 | 4G_FD900_MDU494 | 4G_FD2100_MDU494 | 4G_TD_MDU494 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202107386765 | 2021-07-17 | P/FVC/MDS/1051583/2021 | 2021-08-14 | ST202104148162 | 2021-04-15 | P/FVC/MDS/1018035/2021 | 2021-05-15 | ST202104151115 | 2021-04-17 | P/FVC/MDS/1017541/2021 | 2021-05-13 | ST202105224511 | 2021-05-04 | P/FBW/MDS/1020332/2021 | 2021-05-23 |  | MDU494
103 | SLM350 | SLM350 | Salem | Vellore |  | ROTN | Indus | IN-1727048 | R/NN-565469 | Nominal WIP |  | 2021-03-09 | SLM350 | 4G_FD900_SLM350 | 4G_FD2100_SLM350 | 4G_TD_SLM350 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362780 | 2021-06-26 | P/FVC/MDS/1050042/2021 | 2021-08-09 | ST202008040365 | 2020-08-09 | P/FVC/MDS/1001563/2020 | 2020-08-14 |  |  |  |  | ST202008040407 | 2020-08-09 | P/FBW/MDS/1001593/2020 | 2020-08-14 | SO Hold R/NN-456963 Canceled by Indus Nitin on Feb 22021 | SLM350
104 | ARLR12 | ARLR12 | Ariyalur | Trichy |  | ROTN | Ascend | 0 | - | Nominals with issues | Drop | 2021-03-02 | ARLR12 | 4G_FD900_ARLR12 | 4G_FD2100_ARLR12 | 4G_TD_ARLR12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361836 | 2021-06-25 | P/FVC/MDS/1049899/2021 | 2021-08-09 | ST202103097862 | 2021-03-22 | P/FVC/MDS/1016810/2021 | 2021-04-12 |  |  |  |  | ST202103099145 | 2021-03-21 | P/FBW/MDS/1016936/2021 | 2021-04-12 | Partof461sitesSyamaMay'30/SOSurrenderedbyATCconfirmedbysyama10/4/2019/Earliercheck,nowP0/P1/TocochangedtoAscend7/8/2020.AscendsurrenderedonAug10&giventoown | ARLR12
105 | KKD38 | KKD038 | Sivaganga | Madurai |  | ROTN | Indus | IN-1386409 | R/NN-456802 | Nominals with issues |  | 2021-02-21 | KKD038 | 4G_FD900_KKD038 | 4G_FD2100_KKD038 | 4G_TD_KKD038 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362308 | 2021-06-25 | P/FVC/MDS/1049960/2021 | 2021-08-09 | ST202103097322 | 2021-03-22 | P/FVC/MDS/1016794/2021 | 2021-04-12 |  |  |  |  | ST202103099130 | 2021-03-21 | P/FBW/MDS/1016921/2021 | 2021-04-12 | TocoChangedFromATC(95)ToIndusConfirmedBySyama1/17/2019R/NN-319736Bookedliteplusthenwithdwanandrebookedastrasitionalbasisonjawhar2/20/2019/R/NN-323133SOalreadywithdrawn&RebookingtobedoneasODGBT30Mbasisonjawhar7/8/2019R/NN-350019SOSurrenderedbyjawharconfirmedbysyama9/6/2019/R/NN-375017SOsurrenederdbyindusMani6/13/2020 | KKD38
106 | KMPM24 | KMPM24 | Namakkal | Coimbatore |  | ROTN | Indus | IN-1736290 | R/NN-497329 | Nominals with issues | Drop | 2021-03-09 | KMPM24 | 4G_FD900_KMPM24 | 4G_FD2100_KMPM24 | 4G_TD_KMPM24 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362322 | 2021-06-25 | P/FVC/MDS/1049968/2021 | 2021-08-09 | ST202103098660 | 2021-03-22 | P/FVC/MDS/1016832/2021 | 2021-04-12 |  |  |  |  | ST202103099279 | 2021-03-22 | P/FBW/MDS/1019966/2021 | 2021-05-22 | 20-20-TopTowns0.8Validation/R/NN-391217/SRwithdrwanduetoDAY1TDDandrepunched | KMPM24
107 | KRR84 | KRR084 | Karur | Coimbatore |  | ROTN | Ascend | 0 | - | Nominals with issues |  | 2021-03-06 | KRR084 | 4G_FD900_KRR084 | 4G_FD2100_KRR084 | 4G_TD_KRR084 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362339 | 2021-06-25 | P/FVC/MDS/1046130/2021 | 2021-08-03 | ST202103097996 | 2021-03-22 | P/FVC/MDS/1016823/2021 | 2021-04-12 |  |  |  |  | ST202103099257 | 2021-03-22 | P/FBW/MDS/1019958/2021 | 2021-05-22 | Partof461sitesSyamaMay'30.MuthusirproposedATCsurrenderonAug8&giventoOwn | KRR84
108 | KRR88 | KRR088 | Karur | Coimbatore |  | ROTN | ATC | TN/KU/AT/22378 | T21TN00367 | Nominals with issues | Dropped-Canb. | 2021-03-10 | KRR088 | 4G_FD900_KRR088 | 4G_FD2100_KRR088 | 4G_TD_KRR088 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362340 | 2021-06-25 | P/FVC/MDS/1046131/2021 | 2021-08-03 | ST202103098662 | 2021-03-22 | P/FVC/MDS/1016834/2021 | 2021-04-12 |  |  |  |  | ST202103099281 | 2021-03-22 | P/FBW/MDS/1019968/2021 | 2021-05-22 | 0 | KRR88
109 | PNPT14 | PNPT14 | Cuddalore | Trichy |  | ROTN | Ascend |  |  | Nominals with issues | SR | 2021-02-27 | PNPT14 | 4G_FD900_PNPT14 | 4G_FD2100_PNPT14 | 4G_TD_PNPT14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362752 | 2021-06-26 | P/FVC/MDS/1050025/2021 | 2021-08-09 | ST202103097826 | 2021-03-22 | P/FVC/MDS/1016803/2021 | 2021-04-12 |  |  |  |  | ST202103099139 | 2021-03-21 | P/FBW/MDS/1016930/2021 | 2021-04-12 | 0 | PNPT14
110 | TTYM9 | TTYM09 | Tiruchirappalli | Trichy |  | ROTN | Ascend | 0 | - | Nominal WIP | SP | 2021-03-02 | TTYM09 | 4G_FD900_TTYM09 | 4G_FD2100_TTYM09 | 4G_TD_TTYM09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363085 | 2021-06-26 | P/FVC/MDS/1050091/2021 | 2021-08-09 | ST202103097863 | 2021-03-22 | P/FVC/MDS/1016811/2021 | 2021-04-12 |  |  |  |  | ST202103099208 | 2021-03-21 | P/FBW/MDS/1016937/2021 | 2021-04-12 | 0 | TTYM9
111 | VLR231 | VLR231 | Vellore | Vellore |  | ROTN | TVI | 0 | - | Nominal WIP | SR | 2021-03-08 | VLR231 | 4G_FD900_VLR231 | 4G_FD2100_VLR231 | 4G_TD_VLR231 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363203 | 2021-06-26 | P/FVC/MDS/1050117/2021 | 2021-08-09 | ST202103098000 | 2021-03-22 | P/FVC/MDS/1016827/2021 | 2021-04-12 |  |  |  |  | ST202103099261 | 2021-03-22 | P/FBW/MDS/1019962/2021 | 2021-05-22 | 0 | VLR231
112 | PRNP16 | PRNP16 | Vellore | Vellore |  | ROTN | Indus | IN-1721603 | R/NN-565199 | Nominals with issues | On Air | 2021-02-21 | PRNP16 | 4G_FD900_PRNP16 | 4G_FD2100_PRNP16 | 4G_TD_PRNP16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364113 | 2021-06-28 | P/FVC/MDS/1050139/2021 | 2021-08-09 | ST202103097823 | 2021-03-22 | P/FVC/MDS/1016800/2021 | 2021-04-12 |  |  |  |  | ST202103099136 | 2021-03-21 | P/FBW/MDS/1016927/2021 | 2021-04-12 | 0 | PRNP16
113 | TIR316 | TIR316 | Tiruppur | Coimbatore |  | ROTN | BSNL |  |  | Nominal WIP | Dropped-Canb. | 2021-03-02 | TIR316 | 4G_FD900_TIR316 | 4G_FD2100_TIR316 | 4G_TD_TIR316 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366842 | 2021-06-30 | P/FVC/MDS/1050189/2021 | 2021-08-09 | ST202103098002 | 2021-03-22 | P/FVC/MDS/1016829/2021 | 2021-04-12 |  |  |  |  | ST202103099276 | 2021-03-22 | P/FBW/MDS/1019963/2021 | 2021-05-22 | 0 | TIR316
114 | TIR313 | TIR313 | Tiruppur | Coimbatore |  | ROTN | Indus |  |  | Nominal WIP | Dropped | 2021-02-22 | TIR313 | 4G_FD900_TIR313 | 4G_FD2100_TIR313 | 4G_TD_TIR313 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366845 | 2021-06-30 | P/FVC/MDS/1050192/2021 | 2021-08-09 | ST202103097317 | 2021-03-22 | P/FVC/MDS/1016789/2021 | 2021-04-12 |  |  |  |  | ST202103099125 | 2021-03-21 | P/FBW/MDS/1016916/2021 | 2021-04-12 | 0 | TIR313
115 | NMBYR2 | NMBYR2 | Erode | Coimbatore |  | ROTN | Ascend |  |  | Nominal WIP | Dropped-Canb. | 2021-02-23 | NMBYR2 | 4G_FD900_NMBYR2 | 4G_FD2100_NMBYR2 | 4G_TD_NMBYR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366902 | 2021-06-30 | P/FVC/MDS/1050204/2021 | 2021-08-09 | ST202103097904 | 2021-03-22 | P/FVC/MDS/1016820/2021 | 2021-04-12 |  |  |  |  | ST202103099254 | 2021-03-22 | P/FBW/MDS/1019955/2021 | 2021-05-22 | 0 | NMBYR2
116 | KALKUL | KALKUL | Kanniyakumari | Madurai |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2021-03-03 | KALKUL | 4G_FD900_KALKUL | 4G_FD2100_KALKUL | 4G_TD_KALKUL | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363665 | 2021-06-28 | P/FVC/MDS/1050240/2021 | 2021-08-09 | ST202103098664 | 2021-03-22 | P/FVC/MDS/1016836/2021 | 2021-04-12 |  |  |  |  | ST202103099283 | 2021-03-22 | P/FBW/MDS/1019970/2021 | 2021-05-22 | 0 | KALKUL
117 | VLR232 | VLR232 | Vellore | Vellore |  | ROTN | TVI |  |  | Nominal WIP | RFAI | 2021-02-26 | VLR232 | 4G_FD900_VLR232 | 4G_FD2100_VLR232 | 4G_TD_VLR232 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363663 | 2021-06-28 | P/FVC/MDS/1050238/2021 | 2021-08-09 | ST202103097999 | 2021-03-22 | P/FVC/MDS/1016826/2021 | 2021-04-12 | ST202205124700 | 2022-05-02 | P/FVC/MDS/1079511/2022 | 2022-05-16 | ST202103099260 | 2021-03-22 | P/FBW/MDS/1019961/2021 | 2021-05-22 | 0 | VLR232
118 | PALLGH | PALLGH | Thanjavur | Trichy |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2021-02-21 | PALLGH | 4G_FD900_PALLGH | 4G_FD2100_PALLGH | 4G_TD_PALLGH | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363654 | 2021-06-28 | P/FVC/MDS/1050229/2021 | 2021-08-09 | ST202103097822 | 2021-03-22 | P/FVC/MDS/1016799/2021 | 2021-04-12 |  |  |  |  | ST202103099135 | 2021-03-21 | P/FBW/MDS/1016926/2021 | 2021-04-12 | 0 | PALLGH
119 | DGL92 | DGL092 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/22331 | - |  | On Air | 2021-03-11 | DGL092 | 4G_FD900_DGL092 | 4G_FD2100_DGL092 | 4G_TD_DGL092 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574106 | 2021-10-28 | P/FVC/MDS/1065845/2021 | 2021-11-16 | ST202110573017 | 2021-10-27 | P/FVC/MDS/1065716/2021 | 2021-11-16 |  |  |  |  | ST202110572486 | 2021-10-27 | P/FBW/MDS/1067897/2021 | 2021-12-08 |  | DGL92
120 | TVTY30 | TVTY30 | Chennai | Chennai |  | CHN | Summit |  |  | Nominal WIP | On air | 2021-02-24 | TVTY30 | 4G_FD900_TVTY30 | 4G_FD2100_TVTY30 | 4G_TD_TVTY30 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202103088450 | 2021-03-12 | P/FVC/MDS/1014466/2021 | 2021-04-06 | ST202103088420 | 2021-03-12 | P/FVC/MDS/1014459/2021 | 2021-04-06 | ST202107369636 | 2021-07-01 | P/FVC/MDS/1056079/2021 | 2021-09-07 | ST202103087556 | 2021-03-11 | P/FBW/MDS/1014452/2021 | 2021-04-06 | Ascend surrendered SR on Dec 7, 2020 and realloted to Airtel. Realloted to Ascend on Feb 8, 2021 basis Muthu sir mail on Non patta | TVTY30
121 | TIR446 | TIR446 | Tiruppur | Coimbatore |  | ROTN | Indus |  |  | Nominal WIP | Dropped | 2021-04-19 | TIR446 | 4G_FD900_TIR446 | 4G_FD2100_TIR446 | 4G_TD_TIR446 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363684 | 2021-06-28 | P/FVC/MDS/1050259/2021 | 2021-08-09 | ST202103088422 | 2021-03-12 | P/FVC/MDS/1014461/2021 | 2021-04-06 |  |  |  |  | ST202103087561 | 2021-03-11 | P/FBW/MDS/1014453/2021 | 2021-04-06 | SR withdrawn from current TOCO and realloted to ATC on Mar 28, 2021 Punched to Indus on 13-Apr'21 Paralel SR withdraw from ATC on 17-Apr'21 to maintain 1 toco/Site | TIR446
122 | PATU44 | PATU44 | Thanjavur | Trichy |  | ROTN | Indus | IN-1662167 | R/NN-563379 | Nominal WIP | On Air | 2021-04-24 | PATU44 | 4G_FD900_PATU44 | 4G_FD2100_PATU44 | 4G_TD_PATU44 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202112610872 | 2021-12-10 | P/FVC/MDS/1069078/2021 | 2021-12-17 | ST202112604888 | 2021-12-07 | P/FVC/MDS/1068824/2021 | 2021-12-15 | ST202103087029 | 2021-03-10 | P/FVC/MDS/1014399/2021 | 2021-04-06 | ST202112609407 | 2021-12-10 | P/FBW/MDS/1068788/2021 | 2021-12-15 | 0 | PATU44
123 | PMKD22 | PMKD22 | Ramanathapuram | Madurai |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2021-04-21 | PMKD22 | 4G_FD900_PMKD22 | 4G_FD2100_PMKD22 | 4G_TD_PMKD22 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366828 | 2021-06-30 | P/FVC/MDS/1050178/2021 | 2021-08-09 | ST202105295906 | 2021-05-25 | P/FVC/MDS/1045030/2021 | 2021-07-28 | ST202103087028 | 2021-03-10 | P/FVC/MDS/1014398/2021 | 2021-04-06 | ST202105224513 | 2021-05-04 | P/FBW/MDS/1020334/2021 | 2021-05-23 | 0 | PMKD22
124 | TIR455 | TIR455 | Tiruppur | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2021-04-05 | TIR455 | 4G_FD900_TIR455 | 4G_FD2100_TIR455 | 4G_TD_TIR455 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363627 | 2021-06-27 | P/FVC/MDS/1050222/2021 | 2021-08-09 | ST202104148119 | 2021-04-15 | P/FVC/MDS/1018025/2021 | 2021-05-15 | ST202103087039 | 2021-03-10 | P/FVC/MDS/1014409/2021 | 2021-04-06 | ST202104148950 | 2021-04-15 | P/FBW/MDS/1018083/2021 | 2021-05-16 | 0 | TIR455
125 | TIR456 | TIR456 | Tiruppur | Coimbatore |  | ROTN | Ascend |  |  | Nominal WIP | On Air | 2021-04-20 | TIR456 | 4G_FD900_TIR456 | 4G_FD2100_TIR456 | 4G_TD_TIR456 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363626 | 2021-06-27 | P/FVC/MDS/1050221/2021 | 2021-08-09 | ST202104147715 | 2021-04-15 | P/FVC/MDS/1017993/2021 | 2021-05-15 | ST202103087042 | 2021-03-10 | P/FVC/MDS/1014412/2021 | 2021-04-06 | ST202104148720 | 2021-04-15 | P/FBW/MDS/1018053/2021 | 2021-05-16 | Ascend Surrender SO due to Public Issue-LL backout on 20-Apr'21 , Provided New SP | TIR456
126 | TNV79 | TNV079 | Tirunelveli | Madurai |  | ROTN | ATC |  |  |  | On Air | 2021-07-12 | TNV079 | 4G_FD900_TNV079 | 4G_FD2100_TNV079 | 4G_TD_TNV079 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396900 | 2021-07-26 | P/FVC/MDS/1052720/2021 | 2021-08-20 | ST202107393927 | 2021-07-23 | P/FVC/MDS/1056740/2021 | 2021-09-09 | ST202107393752 | 2021-07-23 | P/FVC/MDS/1057234/2021 | 2021-09-09 | ST202107393396 | 2021-07-23 | P/FBW/MDS/1056707/2021 | 2021-09-08 | 0
127 | GDHM31 | GDHM31 | Vellore | Vellore |  | ROTN | AIRTEL |  |  | Nominal WIP | Drop-Consolidated |  | GDHM31 | 4G_FD900_GDHM31 | 4G_FD2100_GDHM31 | 4G_TD_GDHM31 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364544 | 2021-06-28 | P/FVC/MDS/1050303/2021 | 2021-08-09 | ST202105295934 | 2021-05-25 | P/FVC/MDS/1045117/2021 | 2021-07-28 |  |  |  |  | ST202106325429 | 2021-06-05 | P/FVC/MDS/1036559/2021 | 2021-06-23 | SR Surrendered by ATC on Dec 9, 2020 | GDHM31
128 | VLR211 | VLR211 | Vellore | Vellore |  | ROTN | AIRTEL |  |  | Nominal WIP | Dropped-Canb. |  | VLR211 | 4G_FD900_VLR211 | 4G_FD2100_VLR211 | 4G_TD_VLR211 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366791 | 2021-06-30 | P/FVC/MDS/1046137/2021 | 2021-08-03 | ST202105295938 | 2021-05-25 | P/FVC/MDS/1045119/2021 | 2021-07-28 |  |  |  |  | ST202107389812 | 2021-07-20 | P/FBW/MDS/1056628/2021 | 2021-09-08 | SR Surrendered by ATC on Dec 9, 2020 | VLR211
129 | TRY367 | TRY367 |  |  |  | ROTN | Indus | - | R/NN-564314 |  |  | 2021-02-11 | TRY367 | 4G_FD900_TRY367 | 4G_FD2100_TRY367 | 4G_TD_TRY367 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504498 | 2021-09-02 | P/FVC/MDS/1058584/2021 | 2021-09-10 | ST202103082654 | 2021-03-06 | P/FVC/MDS/1013448/2021 | 2021-03-17 | ST202103106216 | 2021-03-25 | P/FVC/MDS/1017961/2021 | 2021-05-15 | ST202103082324 | 2021-03-06 | P/FBW/MDS/1013417/2021 | 2021-03-17
130 | HSR147 | HSR147 | Krishnagiri | Vellore |  | ROTN | Airtel |  |  | Nominals with issues | Dropped-Canb. |  | HSR147 | 4G_FD900_HSR147 | 4G_FD2100_HSR147 | 4G_TD_HSR147 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362288 | 2021-06-25 | P/FVC/MDS/1049949/2021 | 2021-08-09 | ST202103073541 | 2021-03-01 | P/FVC/MDS/1012419/2021 | 2021-03-13 |  |  |  |  | ST202102071678 | 2021-02-27 | P/FBW/MDS/1012269/2021 | 2021-03-13 | Priority Working by Indus + ATC - 1-Apr-21 SR withdraw from Indus on 17-Apr'21 to maintain 1 toco/Site
131 | MGDI27 | MGDI27 | Thiruvarur | Trichy |  | ROTN | Indus | IN-1430003 | R/NN-469257 | Nominals with issues | On Air | 2021-02-15 | MGDI27 | 4G_FD900_MGDI27 | 4G_FD2100_MGDI27 | 4G_TD_MGDI27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362393 | 2021-06-25 | P/FVC/MDS/1049993/2021 | 2021-08-09 | ST202102034637 | 2021-02-02 | P/FVC/MDS/1013136/2021 | 2021-03-16 | ST202209487725 | 2022-09-28 | P/FVC/MDS/1101351/2022 | 2022-10-10 | ST202102035423 | 2021-02-02 | P/FBW/MDS/1013217/2021 | 2021-03-17 | 0 | MGDI27
132 | TCGD48 | TCGD48 | Namakkal | Coimbatore |  | ROTN | Indus | IN-1541488 | R/NN-470249 | Nominals with issues | Dropped-Canb. | 2021-02-09 | TCGD48 | 4G_FD900_TCGD48 | 4G_FD2100_TCGD48 | 4G_TD_TCGD48 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362800 | 2021-06-26 | P/FVC/MDS/1050060/2021 | 2021-08-09 | ST202102034729 | 2021-02-02 | P/FVC/MDS/1013156/2021 | 2021-03-16 |  |  |  |  | ST202102035491 | 2021-02-02 | P/FBW/MDS/1013236/2021 | 2021-03-17 | 0 | TCGD48
133 | NGOR8 | NGOR08 | Nagapattinam | Trichy |  | ROTN | Summit |  |  | Nominal WIP | SR | 2021-02-15 | NGOR08 | 4G_FD900_NGOR08 | 4G_FD2100_NGOR08 | 4G_TD_NGOR08 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364160 | 2021-06-28 | P/FVC/MDS/1050164/2021 | 2021-08-09 | ST202102034643 | 2021-02-02 | P/FVC/MDS/1013142/2021 | 2021-03-16 |  |  |  |  | ST202102035429 | 2021-02-02 | P/FBW/MDS/1013223/2021 | 2021-03-17 | Partof461sitesSyamaMay'30/FreshSRWithdrawnbyATC8/22/2019/R/NN-365884/SRwithdrwanduetoDAY1TDDandrepunched | NGOR8
134 | MTPM25 | MTPM25 | Coimbatore | Coimbatore |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2021-02-22 | MTPM25 | 4G_FD900_MTPM25 | 4G_FD2100_MTPM25 | 4G_TD_MTPM25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364206 | 2021-06-28 | P/FVC/MDS/1050167/2021 | 2021-08-09 | ST202102034636 | 2021-02-02 | P/FVC/MDS/1013135/2021 | 2021-03-16 |  |  |  |  | ST202102035422 | 2021-02-02 | P/FBW/MDS/1013216/2021 | 2021-03-17 | Partof461sitesSyamaMay'30/MTPM23ToMTPM25siteidchangedduetoduplicate/R/NN-348256SoWithdrwanconfirmedbyscmNov'4/R/NN-375087/SRwithdrwanduetoDAY1TDDandrepunched | MTPM25
135 | VMBD33 | VMBD33 | Vellore | Vellore |  | ROTN | Indus |  |  | Nominal WIP | Dropped | 2021-04-13 | VMBD33 | 4G_FD900_VMBD33 | 4G_FD2100_VMBD33 | 4G_TD_VMBD33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364474 | 2021-06-28 | P/FVC/MDS/1050291/2021 | 2021-08-09 | ST202105293645 | 2021-05-25 | P/FVC/MDS/1036610/2021 | 2021-06-23 |  |  |  |  | ST202105228519 | 2021-05-04 | P/FBW/MDS/1020376/2021 | 2021-05-23 | Nominal pulled from TVI by deployment on Dec 29 and reallotted to Ascend on Dec 30 Priority Working by Indus + ATC - 1-Apr-21 | VMBD33
136 | VLRM57 | VLRM57 | Viluppuram | Trichy |  | ROTN | Summit |  |  | Nominal WIP | SO | 2021-02-15 | VLRM57 | 4G_FD900_VLRM57 | 4G_FD2100_VLRM57 | 4G_TD_VLRM57 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364527 | 2021-06-28 | P/FVC/MDS/1050298/2021 | 2021-08-09 | ST202102035014 | 2021-02-02 | P/FVC/MDS/1013175/2021 | 2021-03-16 |  |  |  |  | ST202102035833 | 2021-02-02 | P/FBW/MDS/1010791/2021 | 2021-02-23 | SR Surrendered by ATC on Dec 9, 2020 | VLRM57
137 | KRKTI3 | KRKTI3 | Thiruvarur | Trichy |  | ROTN | ATC |  |  | Nominal WIP | RFAI | 2021-01-19 | KRKTI3 | 4G_FD900_KRKTI3 | 4G_FD2100_KRKTI3 | 4G_TD_KRKTI3 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202201000635 | 2022-01-03 | P/FVC/MDS/1071062/2022 | 2022-01-10 | ST202201000172 | 2022-01-06 | P/FVC/MDS/1071052/2022 | 2022-01-10 | ST202201000635 | 2022-01-03 | P/FVC/MDS/1071062/2022 | 2022-01-10 | ST202201000692 | 2022-01-03 | P/FBW/MDS/1071072/2022 | 2022-01-10 |  | KRKTI3
138 | KCPM88 | KCPM88 | Kancheepuram | Chennai |  | ROTN | Ascend |  |  |  | On Air | 2021-07-05 | KCPM88 | 4G_FD900_KCPM88 | 4G_FD2100_KCPM88 | 4G_TD_KCPM88 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107379962 | 2021-07-10 | P/FVC/MDS/1051823/2021 | 2021-08-15 | ST202108498239 | 2021-08-31 | P/FVC/MDS/1060477/2021 | 2021-09-13 | ST202107388477 | 2021-07-19 | P/FVC/MDS/1056664/2021 | 2021-09-08 | ST202107389801 | 2021-07-20 | P/FBW/MDS/1055995/2021 | 2021-09-06 | 0 | KCPM88
139 | IDKK2 | IDKK02 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1582764 | R/NN-561028 | Nominals with issues | On Air | 2021-02-18 | IDKK02 | 4G_FD900_IDKK02 | 4G_FD2100_IDKK02 | 4G_TD_IDKK02 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362296 | 2021-06-25 | P/FVC/MDS/1049951/2021 | 2021-08-09 | ST202103073675 | 2021-03-01 | P/FVC/MDS/1012450/2021 | 2021-03-13 |  |  |  |  | ST202102071562 | 2021-02-27 | P/FBW/MDS/1012225/2021 | 2021-03-13 | 0 | IDKK2
140 | KARA17 | KARA17 | Chennai | Chennai |  | CHN | TVI | 0 | - | Nominal WIP | On air | 2021-02-20 | KARA17 | 4G_FD900_KARA17 | 4G_FD2100_KARA17 | 4G_TD_KARA17 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202102071755 | 2021-02-27 | P/FVC/MDS/1012331/2021 | 2021-03-13 | ST202102071772 | 2021-02-27 | P/FVC/MDS/1012348/2021 | 2021-03-13 | ST202106358247 | 2021-06-23 | P/FVC/MDS/1055850/2021 | 2021-09-04 | ST202103072966 | 2021-03-01 | P/FBW/MDS/1012388/2021 | 2021-03-13 | Indus SR R/NN-333961 withdrawn on Dec 21 and realloted to Ascend basis Muthu sir's/Jawahar's DTA response on Dec 17, 2020 | KARA17
141 | KATP16 | KATP16 | Chennai | Chennai |  | CHN | Indus | IN-1468037 | R/NN-499770 | Nominals with issues | On air | 2021-02-20 | KATP16 | 4G_FD900_KATP16 | 4G_FD2100_KATP16 | 4G_TD_KATP16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202102071748 | 2021-02-27 | P/FVC/MDS/1012329/2021 | 2021-03-13 | ST202102071770 | 2021-02-27 | P/FVC/MDS/1012346/2021 | 2021-03-13 | ST202106358251 | 2021-06-23 | P/FVC/MDS/1055851/2021 | 2021-09-04 | ST202103072964 | 2021-03-01 | P/FBW/MDS/1012386/2021 | 2021-03-13 | TDD added after Syama confirmation. SO Withdrawn after acceptance . | KATP16
142 | KATUU1 | KATUU1 | Thiruvarur | Trichy |  | ROTN | Indus | IN-1718663 | R/NN-565004 | Nominals with issues | Dropped | 2021-02-16 | KATUU1 | 4G_FD900_KATUU1 | 4G_FD2100_KATUU1 | 4G_TD_KATUU1 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362303 | 2021-06-25 | P/FVC/MDS/1049955/2021 | 2021-08-09 | ST202103073672 | 2021-03-01 | P/FVC/MDS/1012447/2021 | 2021-03-13 | ST202103075655 | 2021-03-02 | P/FVC/MDS/1012493/2021 | 2021-03-13 | ST202103075107 | 2021-03-02 | P/FBW/MDS/1012488/2021 | 2021-03-13 | SO R/NN-469561 terminated by Indus and rebooked on Feb 12, 2021 basis request from Jawahar | KATUU1
143 | KRIP12 | KRIP12 | Chennai | Chennai |  | CHN | Indus | IN-1727519 | R/NN-565502 | Nominals with issues | Dropped | 2021-02-16 | KRIP12 | 4G_FD900_KRIP12 | 4G_FD2100_KRIP12 | 4G_TD_KRIP12 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202102071741 | 2021-02-27 | P/FVC/MDS/1012324/2021 | 2021-03-13 | ST202102071765 | 2021-02-27 | P/FVC/MDS/1012341/2021 | 2021-03-13 | ST202106358256 | 2021-06-23 | P/FVC/MDS/1055854/2021 | 2021-09-04 | 2019442328 | 2019-12-18 | P/FVC/MDS/5931492/2020 | 2020-01-01 | SO R/NN-369112 terminated by Indus and rebooked | KRIP12
144 | NGL129 | NGL129 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-1691102 | R/NN-564288 | Nominals with issues |  | 2021-02-16 | NGL129 | 4G_FD900_NGL129 | 4G_FD2100_NGL129 | 4G_TD_NGL129 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362644 | 2021-06-26 | P/FVC/MDS/1050004/2021 | 2021-08-09 | ST202103073690 | 2021-03-01 | P/FVC/MDS/1012464/2021 | 2021-03-13 |  |  |  |  | ST202102071584 | 2021-02-27 | P/FBW/MDS/1012243/2021 | 2021-03-13 | SO Surrendered by ATC and canceled by SCM on Dec 10, 2020. To be realloted to Indus | NGL129
145 | PLDM14 | PLDM14 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1385196 | R/NN-430892 | Nominals with issues | On Air | 2021-02-18 | PLDM14 | 4G_FD900_PLDM14 | 4G_FD2100_PLDM14 | 4G_TD_PLDM14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362749 | 2021-06-26 | P/FVC/MDS/1046132/2021 | 2021-08-03 | ST202103073676 | 2021-03-01 | P/FVC/MDS/1012451/2021 | 2021-03-13 |  |  |  |  | ST202102071563 | 2021-02-27 | P/FBW/MDS/1012226/2021 | 2021-03-13 | ATCsurrenderedSOsonSep20/R/NN-370183/SRwithdrwanduetoDAY1TDDandrepunched/PrioritychangedfromP1toP07/14/2020 | PLDM14
146 | SATH24 | SATH24 | Erode | Coimbatore |  | ROTN | Indus | IN-1650264 | R/NN-562787 | Nominals with issues | SO-Hold | 2021-02-10 | SATH24 | 4G_FD900_SATH24 | 4G_FD2100_SATH24 | 4G_TD_SATH24 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362769 | 2021-06-26 | P/FVC/MDS/1050035/2021 | 2021-08-09 | ST202107380613 | 2021-07-10 | P/FVC/MDS/1055988/2021 | 2021-09-06 | ST202107369694 | 2021-07-01 | P/FVC/MDS/1056087/2021 | 2021-09-07 | ST202107380621 | 2021-07-10 | P/FBW/MDS/1056002/2021 | 2021-09-06 | SO R/NN-339167 Canceled by Indus on Jan 13, 2021 and ID changed and rebooked | SATH24
147 | SATTA6 | SATTA6 | Chennai | Chennai |  | CHN | Indus | IN-1383635 | R/NN-422510 | Nominals with issues | SR | 2021-02-16 | SATTA6 | 4G_FD900_SATTA6 | 4G_FD2100_SATTA6 | 4G_TD_SATTA6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202102071745 | 2021-02-27 | P/FVC/MDS/1012326/2021 | 2021-03-13 | ST202102071767 | 2021-02-27 | P/FVC/MDS/1012343/2021 | 2021-03-13 | ST202106358279 | 2021-06-23 | P/FVC/MDS/1055869/2021 | 2021-09-04 | ST202103072961 | 2021-03-01 | P/FBW/MDS/1012383/2021 | 2021-03-13 | TDD added after Syama confirmation SO Withdrawn from Indus end ,Mail from Mani - 2 Jun'21 - - given to ascend | SATTA6
148 | TIR425 | TIR425 | Tiruppur | Coimbatore |  | ROTN | Ascend | 0 | - | Nominals with issues | Dropped-Canb. | 2021-02-19 | TIR425 | 4G_FD900_TIR425 | 4G_FD2100_TIR425 | 4G_TD_TIR425 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362805 | 2021-06-26 | P/FVC/MDS/1050065/2021 | 2021-08-09 | ST202103073456 | 2021-03-01 | P/FVC/MDS/1012406/2021 | 2021-03-13 |  |  |  |  | ST202102071670 | 2021-02-27 | P/FBW/MDS/1012261/2021 | 2021-03-13 |  | TIR425
149 | TIVR31 | TIVR31 | Thiruvarur | Trichy |  | ROTN | Indus | IN-1449126 | R/NN-472594 | Nominals with issues | Dropped-Canb. | 2021-02-16 | TIVR31 | 4G_FD900_TIVR31 | 4G_FD2100_TIVR31 | 4G_TD_TIVR31 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362814 | 2021-06-26 | P/FVC/MDS/1050069/2021 | 2021-08-09 | ST202103073695 | 2021-03-01 | P/FVC/MDS/1012469/2021 | 2021-03-13 |  |  |  |  | ST202102071599 | 2021-02-27 | P/FBW/MDS/1012248/2021 | 2021-03-13 | 0 | TIVR31
150 | KLAKU3 | KLAKU3 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22387 | T21TN00759 | Nominals with issues | SR | 2021-02-19 | KLAKU3 | 4G_FD900_KLAKU3 | 4G_FD2100_KLAKU3 | 4G_TD_KLAKU3 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106363272 | 2021-06-26 | P/FVC/MDS/1050129/2021 | 2021-08-09 | ST202103073519 | 2021-03-01 | P/FVC/MDS/1012411/2021 | 2021-03-13 | ST202103075680 | 2021-03-02 | P/FVC/MDS/1012504/2021 | 2021-03-13 |  |  |  |  | 0 | KLAKU3
151 | THENNR | THENNR | Ariyalur | Trichy |  | ROTN | Ascend |  |  | Nominals with issues | On Air | 2021-02-19 | THENNR | 4G_FD900_THENNR | 4G_FD2100_THENNR | 4G_TD_THENNR | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364109 | 2021-06-28 | P/FVC/MDS/1050135/2021 | 2021-08-09 | ST202111585344 | 2021-11-09 | P/FVC/MDS/1068125/2021 | 2021-12-08 |  |  |  |  | ST202111582610 | 2021-11-06 | P/FBW/MDS/1068063/2021 | 2021-12-08 | 0 | THENNR
152 | PATT29 | PATT29 | Chennai | Chennai |  | CHN | Airtel |  |  | Nominal WIP | Dropped-Canb. | - | PATT29 | 4G_FD900_PATT29 | 4G_FD2100_PATT29 | 4G_TD_PATT29 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202103082547 | 2021-03-06 | P/FVC/MDS/1013463/2021 | 2021-03-18 | ST202102071780 | 2021-02-27 | P/FVC/MDS/1012356/2021 | 2021-03-13 | ST202107369682 | 2021-07-01 | P/FVC/MDS/1056083/2021 | 2021-09-07 | ST202103082378 | 2021-03-06 | P/FBW/MDS/1013389/2021 | 2021-03-17 | 0
153 | HSR134 | HSR134 | Krishnagiri | Vellore |  | ROTN | Airtel |  |  | Nominal WIP | RFAI | 2021-05-10 | HSR134 | 4G_FD900_HSR134 | 4G_FD2100_HSR134 | 4G_TD_HSR134 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364367 | 2021-06-28 | P/FVC/MDS/1050272/2021 | 2021-08-09 | ST202104148011 | 2021-04-15 | P/FVC/MDS/1018005/2021 | 2021-05-15 |  |  |  |  | ST202104148892 | 2021-04-15 | P/FBW/MDS/1018065/2021 | 2021-05-16 | Partof461sitesSyamaMay'30 | HSR134
154 | TMGM16 | TMGM16 | Madurai | Madurai |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2021-02-15 | TMGM16 | 4G_FD900_TMGM16 | 4G_FD2100_TMGM16 | 4G_TD_TMGM16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366827 | 2021-06-30 | P/FVC/MDS/1050177/2021 | 2021-08-09 | ST202107380612 | 2021-07-10 | P/FVC/MDS/1055987/2021 | 2021-09-06 | ST202107369693 | 2021-07-01 | P/FVC/MDS/1056086/2021 | 2021-09-07 | ST202107379960 | 2021-07-10 | P/FBW/MDS/1057142/2021 | 2021-09-09 | 0 | TMGM16
155 | PMKD23 | PMKD23 | Ramanathapuram | Madurai |  | ROTN | Summit |  |  | Nominal WIP | On Air | 2021-02-18 | PMKD23 | 4G_FD900_PMKD23 | 4G_FD2100_PMKD23 | 4G_TD_PMKD23 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202201014691 | 2022-01-20 | P/FVC/MDS/1072395/2022 | 2022-01-31 | ST202201014763 | 2022-01-20 | P/FVC/MDS/1072366/2022 | 2022-01-31 |  |  |  |  | ST202201014810 | 2022-01-20 | P/FBW/MDS/1072337/2022 | 2022-01-31 | 0 | PMKD23
156 | TRY353 | TRY353 | Tiruchirappalli | Trichy |  | ROTN | Summit |  |  | Nominal WIP | SP | 2021-02-18 | TRY353 | 4G_FD900_TRY353 | 4G_FD2100_TRY353 | 4G_TD_TRY353 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366838 | 2021-06-30 | P/FVC/MDS/1050185/2021 | 2021-08-09 | ST202103073705 | 2021-03-01 | P/FVC/MDS/1012479/2021 | 2021-03-13 |  |  |  |  | ST202102071667 | 2021-02-27 | P/FBW/MDS/1012258/2021 | 2021-03-13 | 0 | TRY353
157 | CBE839 | CBE839 | Coimbatore | Coimbatore |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2021-02-18 | CBE839 | 4G_FD900_CBE839 | 4G_FD2100_CBE839 | 4G_TD_CBE839 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366846 | 2021-06-30 | P/FVC/MDS/1050193/2021 | 2021-08-09 | ST202103073702 | 2021-03-01 | P/FVC/MDS/1012476/2021 | 2021-03-13 |  |  |  |  | ST202102071664 | 2021-02-27 | P/FBW/MDS/1012255/2021 | 2021-03-13 | 0 | CBE839
158 | PKT199 | PKT199 | Tirunelveli | Madurai |  | ROTN | Summit |  |  | Nominal WIP | On Air | 2021-02-18 | PKT199 | 4G_FD900_PKT199 | 4G_FD2100_PKT199 | 4G_TD_PKT199 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202110573619 | 2021-10-27 | P/FVC/MDS/1065760/2021 | 2021-11-16 | ST202110574136 | 2021-10-28 | P/FVC/MDS/1065820/2021 | 2021-11-16 | ST202210548461 | 2022-10-11 | P/FVC/MDS/1113921/2022 | 2022-10-21 | ST202110572529 | 2021-10-27 | P/FBW/MDS/1066532/2021 | 2021-11-19 | 0 | PKT199
159 | MTPM27 | MTPM27 | Coimbatore | Coimbatore |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2021-02-18 | MTPM27 | 4G_FD900_MTPM27 | 4G_FD2100_MTPM27 | 4G_TD_MTPM27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366909 | 2021-06-30 | P/FVC/MDS/1050211/2021 | 2021-08-09 | ST202103073700 | 2021-03-01 | P/FVC/MDS/1012474/2021 | 2021-03-13 |  |  |  |  | ST202102071662 | 2021-02-27 | P/FBW/MDS/1012253/2021 | 2021-03-13 | 0 | MTPM27
160 | MDU481 | MDU481 | Madurai | Madurai |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2021-02-18 | MDU481 | 4G_FD900_MDU481 | 4G_FD2100_MDU481 | 4G_TD_MDU481 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363683 | 2021-06-28 | P/FVC/MDS/1050258/2021 | 2021-08-09 | ST202103073699 | 2021-03-01 | P/FVC/MDS/1012473/2021 | 2021-03-13 |  |  |  |  | ST202102071603 | 2021-02-27 | P/FBW/MDS/1012252/2021 | 2021-03-13 | 0 | MDU481
161 | KLKC27 | KLKC27 | Viluppuram | Trichy |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2021-02-11 | KLKC27 | 4G_FD900_KLKC27 | 4G_FD2100_KLKC27 | 4G_TD_KLKC27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363664 | 2021-06-28 | P/FVC/MDS/1050239/2021 | 2021-08-09 | ST202103073537 | 2021-03-01 | P/FVC/MDS/1012415/2021 | 2021-03-13 |  |  |  |  | ST202102071675 | 2021-02-27 | P/FBW/MDS/1012266/2021 | 2021-03-13 | 0 | KLKC27
162 | TVKND3 | TVKND3 | Kanniyakumari | Madurai |  | ROTN | ATC |  |  | Nominal WIP |  | 2021-02-11 | TVKND3 | 4G_FD900_TVKND3 | 4G_FD2100_TVKND3 | 4G_TD_TVKND3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202110553067 | 2021-10-07 | P/FVC/MDS/1063633/2021 | 2021-10-22 | ST202110554054 | 2021-10-08 | P/FVC/MDS/1063597/2021 | 2021-10-20 | ST202110560494 | 2021-10-14 | P/FVC/MDS/1063756/2021 | 2021-10-22 | ST202110555489 | 2021-10-09 | P/FBW/MDS/1063606/2021 | 2021-10-20 |  | TVKND3
163 | MUDSAO | MUDSAO | Cuddalore | Trichy |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2021-02-11 | MUDSAO | 4G_FD900_MUDSAO | 4G_FD2100_MUDSAO | 4G_TD_MUDSAO | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000638 | 2022-01-03 | P/FVC/MDS/1071065/2022 | 2022-01-10 | ST202201000662 | 2022-01-06 | P/FVC/MDS/1071058/2022 | 2022-01-10 |  |  |  |  | ST202201000695 | 2022-01-03 | P/FBW/MDS/1071075/2022 | 2022-01-10 | 0 | MUDSAO
164 | CBE785 | CBE785 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1718941 | R/NN-565027 | Nominals with issues | SO | 2021-02-15 | CBE785 | 4G_FD900_CBE785 | 4G_FD2100_CBE785 | 4G_TD_CBE785 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361945 | 2021-06-25 | P/FVC/MDS/1049914/2021 | 2021-08-09 | ST202102054073 | 2021-02-10 | P/FBW/MDS/1011843/2021 | 2021-03-09 | ST202212780721 | 2022-12-02 | P/FVC/MDS/1118292/2022 | 2022-12-07 | ST202102053644 | 2021-02-15 | P/FBW/MDS/1012750/2021 | 2021-03-13 | SP R/NN-439826 terminated by Indus and rebooked on Feb 12, 2021 basis request from Jawahar | CBE785
165 | GERU39 | GERU39 | Chennai | Chennai |  | CHN | Indus | R/NN-478883 | 0 | Nominal WIP |  | 2021-02-13 | GERU39 | 4G_FD900_GERU39 | 4G_FD2100_GERU39 | 4G_TD_GERU39 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108410819 | 2021-08-06 | P/FVC/MDS/1052891/2021 | 2021-08-20 | ST202102054595 | 2021-02-16 | P/FVC/MDS/1011786/2021 | 2021-03-09 | ST202102054289 | 2021-02-16 | P/FVC/MDS/1011746/2021 | 2021-03-09 | ST202102054939 | 2021-02-16 | P/FBW/MDS/1011797/2021 | 2021-03-09 |  | GERU39
166 | ARNI22 | ARNI22 | Tiruvannamalai | Vellore |  | ROTN | Indus | IN-1543151 | R/NN-559814 | Nominals with issues | Dropped | 2021-01-19 | ARNI22 | 4G_FD900_ARNI22 | 4G_FD2100_ARNI22 | 4G_TD_ARNI22 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361840 | 2021-06-25 | P/FVC/MDS/1049901/2021 | 2021-08-09 | ST202102032298 | 2021-02-01 | P/FVC/MDS/1011686/2021 | 2021-03-05 |  |  |  |  | ST202101027833 | 2021-01-29 | P/FBW/MDS/1010937/2021 | 2021-02-24 | 20-20-TopTowns0.8Validation | ARNI22
167 | AVNI28 | AVNI28 | Tiruppur | Coimbatore |  | ROTN | ATC | TN/TI/AT/22298 | T20TN07643 | Nominals with issues | SR | 2021-01-20 | AVNI28 | 4G_FD900_AVNI28 | 4G_FD2100_AVNI28 | 4G_TD_AVNI28 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361906 | 2021-06-25 | P/FVC/MDS/1049905/2021 | 2021-08-09 | ST202102032441 | 2021-02-01 | P/FVC/MDS/1011710/2021 | 2021-03-05 |  |  |  |  | ST202101028311 | 2021-01-29 | P/FBW/MDS/1011071/2021 | 2021-02-25 | 0 | AVNI28
168 | KAPT4 | KAPT04 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/22368 | T21TN00357 | Nominals with issues | SRB(Surrender) | 2021-01-21 | KAPT04 | 4G_FD900_KAPT04 | 4G_FD2100_KAPT04 | 4G_TD_KAPT04 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362302 | 2021-06-25 | P/FVC/MDS/1049954/2021 | 2021-08-09 | ST202102032487 | 2021-02-01 | P/FVC/MDS/1011727/2021 | 2021-03-05 |  |  |  |  | ST202102037962 | 2021-02-04 | P/FBW/MDS/1010698/2021 | 2021-02-23 | 0 | KAPT4
169 | KMKL12 | KMKL12 | Cuddalore | Trichy |  | ROTN | Indus | IN-1632573 | R/NN-562218 | Nominals with issues | On Air | 2021-01-19 | KMKL12 | 4G_FD900_KMKL12 | 4G_FD2100_KMKL12 | 4G_TD_KMKL12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202109522076 | 2021-09-16 | P/FVC/MDS/1062414/2021 | 2021-09-23 | ST202109522204 | 2021-09-16 | P/FVC/MDS/1062462/2021 | 2021-09-23 | ST202109530293 | 2021-09-24 | P/FVC/MDS/1063053/2021 | 2021-10-01 | ST202109522259 | 2021-09-16 | P/FBW/MDS/1062510/2021 | 2021-09-23 | Location changed , Old location 11.292408 79.558611 - 4 Jun'21 | KMKL12
170 | MCMPTI | MCMPTI | Thanjavur | Trichy |  | ROTN | Indus | IN-1398604 | R/NN-466949 | Nominals with issues | On Air | 2021-02-11 | MCMPTI | 4G_FD900_MCMPTI | 4G_FD2100_MCMPTI | 4G_TD_MCMPTI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000636 | 2022-01-03 | P/FVC/MDS/1071063/2022 | 2022-01-10 | ST202201000173 | 2022-01-06 | P/FVC/MDS/1071053/2022 | 2022-01-10 |  |  |  |  | ST202201000693 | 2022-01-03 | P/FBW/MDS/1071073/2022 | 2022-01-10 | Location changed , Old location 10.849655/78.969213 - 4 Jun'21 | MCMPTI
171 | MGDI80 | MGDI80 | Thiruvarur | Trichy |  | ROTN | Indus | IN-1690411 | R/NN-564295 | Nominals with issues | Dropped | 2021-02-08 | MGDI80 | 4G_FD900_MGDI80 | 4G_FD2100_MGDI80 | 4G_TD_MGDI80 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362394 | 2021-06-25 | P/FVC/MDS/1049994/2021 | 2021-08-09 | ST202102055207 | 2021-02-16 | P/FVC/MDS/1011534/2021 | 2021-03-05 |  |  |  |  | ST202102053931 | 2021-02-16 | P/FBW/MDS/1011854/2021 | 2021-03-09 | Old SO R/NN-469260 terminated by Indus and repunched on Jan 29, 2021 | MGDI80
172 | MUKDL3 | MUKDL3 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/22347 | T20TN08655 | Nominals with issues | SO | 2021-01-13 | MUKDL3 | 4G_FD900_MUKDL3 | 4G_FD2100_MUKDL3 | 4G_TD_MUKDL3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362639 | 2021-06-26 | P/FVC/MDS/1050000/2021 | 2021-08-09 | ST202102032239 | 2021-02-01 | P/FVC/MDS/1011664/2021 | 2021-03-05 |  |  |  |  | ST202101027727 | 2021-01-29 | P/FBW/MDS/1011096/2021 | 2021-02-25 | 0 | MUKDL3
173 | PDKT57 | PDKT57 | Pudukkottai | Trichy |  | ROTN | Indus | IN-1451083 | R/NN-469392 | Nominals with issues | Dropped-Canb. | 2021-02-13 | PDKT57 | 4G_FD900_PDKT57 | 4G_FD2100_PDKT57 | 4G_TD_PDKT57 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362723 | 2021-06-26 | P/FVC/MDS/1050013/2021 | 2021-08-09 | ST202102055614 | 2021-02-16 | P/FVC/MDS/1011562/2021 | 2021-03-05 |  |  |  |  | ST202102053637 | 2021-02-15 | P/FBW/MDS/1012748/2021 | 2021-03-13 | 0 | PDKT57
174 | PKT198 | PKT198 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1450841 | R/NN-473060 | Nominals with issues | Dropped-Canb. | 2021-02-03 | PKT198 | 4G_FD900_PKT198 | 4G_FD2100_PKT198 | 4G_TD_PKT198 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362736 | 2021-06-26 | P/FVC/MDS/1050021/2021 | 2021-08-09 | ST202102047142 | 2021-02-10 | P/FVC/MDS/1011469/2021 | 2021-03-05 |  |  |  |  | ST202102049133 | 2021-02-10 | P/FBW/MDS/1011509/2021 | 2021-03-05 |  | PKT198
175 | PLCH44 | PLCH44 | Coimbatore | Coimbatore |  | ROTN | Ascend | 0 | - | Nominals with issues | Dropped-Canb. | 2021-01-12 | PLCH44 | 4G_FD900_PLCH44 | 4G_FD2100_PLCH44 | 4G_TD_PLCH44 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362739 | 2021-06-26 | P/FVC/MDS/1050023/2021 | 2021-08-09 | ST202102032429 | 2021-02-01 | P/FVC/MDS/1011703/2021 | 2021-03-05 |  |  |  |  | ST202101027492 | 2021-01-29 | P/FBW/MDS/1011077/2021 | 2021-02-25 | As per Pandian Mail SO has been surrender by Ascend as LL backedout due to public issue, mail of 27-ma7'21 | PLCH44
176 | PRNI5 | PRNI05 | Thanjavur | Trichy |  | ROTN | Indus | IN-1385384 | R/NN-439877 | Nominals with issues | On Air | 2021-02-13 | PRNI05 | 4G_FD900_PRNI05 | 4G_FD2100_PRNI05 | 4G_TD_PRNI05 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362757 | 2021-06-26 | P/FVC/MDS/1050029/2021 | 2021-08-09 | ST202102055594 | 2021-02-16 | P/FVC/MDS/1011561/2021 | 2021-03-05 |  |  |  |  | ST202102053636 | 2021-02-15 | P/FBW/MDS/1012747/2021 | 2021-03-13 | 20-20-RestofUrban/ATCsurrenderedonfeb6thandalocatedtoindusbysyama2/11/2020/R/NN-395891/SRwithdrwanduetoDAY1TDDandrepunched | PRNI5
177 | SBKL7 | SBKL09 | Nagapattinam | Trichy |  | ROTN | Ascend |  |  | Nominals with issues | Dropped-Canb. | 2021-02-16 | SBKL09 | 4G_FD900_SBKL09 | 4G_FD2100_SBKL09 | 4G_TD_SBKL09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362770 | 2021-06-26 | P/FVC/MDS/1050036/2021 | 2021-08-09 | ST202102055280 | 2021-02-16 | P/FVC/MDS/1011550/2021 | 2021-03-05 |  |  |  |  | ST202102053976 | 2021-02-16 | P/FBW/MDS/1011869/2021 | 2021-03-09 | 0 | SBKL7
178 | SITKU2 | SITKU2 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1632496 | R/NN-562205 | Nominals with issues |  | 2021-02-08 | SITKU2 | 4G_FD900_SITKU2 | 4G_FD2100_SITKU2 | 4G_TD_SITKU2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362772 | 2021-06-26 | P/FVC/MDS/1050038/2021 | 2021-08-09 | ST202102055099 | 2021-02-16 | P/FVC/MDS/1011531/2021 | 2021-03-05 |  |  |  |  | ST202102053930 | 2021-02-16 | P/FBW/MDS/1011853/2021 | 2021-03-09 | SO R/NN-469396 Canceled by Indus Lat long changed - Old 11.089178/79.613622 4 Jun'21 | SITKU2
179 | SLMLI3 | SLMLI3 | Theni | Madurai |  | ROTN | Indus | IN-1582884 | R/NN-561056 | Nominals with issues | On Air | 2021-02-11 | SLMLI3 | 4G_FD900_SLMLI3 | 4G_FD2100_SLMLI3 | 4G_TD_SLMLI3 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202111585095 | 2021-11-09 | P/FVC/MDS/1068096/2021 | 2021-12-08 | ST202111585312 | 2021-11-09 | P/FVC/MDS/1068114/2021 | 2021-12-08 | ST202102054007 | 2021-02-10 | P/FBW/MDS/1011822/2021 | 2021-03-09 | ST202111584787 | 2021-11-09 | P/FBW/MDS/1068070/2021 | 2021-12-08 | 0 | SLMLI3
180 | SMNR7 | SMNR07 | Coimbatore | Coimbatore |  | ROTN | Ascend | 0 | - | Nominals with issues | On Air | 2021-01-15 | SMNR07 | 4G_FD900_SMNR07 | 4G_FD2100_SMNR07 | 4G_TD_SMNR07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362787 | 2021-06-26 | P/FVC/MDS/1050047/2021 | 2021-08-09 | ST202102032443 | 2021-02-01 | P/FVC/MDS/1011712/2021 | 2021-03-05 |  |  |  |  | ST202101027828 | 2021-01-29 | P/FBW/MDS/1010932/2021 | 2021-02-24 | 0 | SMNR7
181 | SVGI20 | SVGI20 | Sivaganga | Madurai |  | ROTN | Indus | IN-1434853 | R/NN-469560 | Nominals with issues | On Air | 2021-01-15 | SVGI20 | 4G_FD900_SVGI20 | 4G_FD2100_SVGI20 | 4G_TD_SVGI20 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362793 | 2021-06-26 | P/FVC/MDS/1050053/2021 | 2021-08-09 | ST202102032259 | 2021-02-01 | P/FVC/MDS/1011678/2021 | 2021-03-05 |  |  |  |  | ST202101027829 | 2021-01-29 | P/FBW/MDS/1010933/2021 | 2021-02-24 | 0 | SVGI20
182 | SVGI26 | SVGI26 | Sivaganga | Madurai |  | ROTN | Indus | IN-1691103 | R/NN-564310 | Nominals with issues | Dropped-Canb. | 2021-02-08 | SVGI26 | 4G_FD900_SVGI26 | 4G_FD2100_SVGI26 | 4G_TD_SVGI26 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362794 | 2021-06-26 | P/FVC/MDS/1050054/2021 | 2021-08-09 | ST202102055212 | 2021-02-16 | P/FVC/MDS/1011539/2021 | 2021-03-05 |  |  |  |  | ST202102053936 | 2021-02-16 | P/FBW/MDS/1011859/2021 | 2021-03-09 | Old SO R/NN-470241 terminated by Indus and repunched on Jan 29, 2021 | SVGI26
183 | SVTRM3 | SVTRM3 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1582795 | R/NN-561037 | Nominals with issues | On Air | 2021-02-08 | SVTRM3 | 4G_FD900_SVTRM3 | 4G_FD2100_SVTRM3 | 4G_TD_SVTRM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202203064640 | 2022-03-07 | P/FVC/MDS/1076941/2022 | 2022-03-23 | ST202203064594 | 2022-03-07 | P/FVC/MDS/1076914/2022 | 2022-03-23 |  |  |  |  | ST202203064532 | 2022-03-07 | P/FBW/MDS/1076883/2022 | 2022-03-23 | 0 | SVTRM3
184 | TNJ130 | TNJ130 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/22223 | T20TN07113 | Nominals with issues | Dropped-Canb. | 2021-01-12 | TNJ130 | 4G_FD900_TNJ130 | 4G_FD2100_TNJ130 | 4G_TD_TNJ130 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362858 | 2021-06-26 | P/FVC/MDS/1050074/2021 | 2021-08-09 | ST202102032254 | 2021-02-01 | P/FVC/MDS/1011673/2021 | 2021-03-05 |  |  |  |  | ST202101027720 | 2021-01-29 | P/FBW/MDS/1011088/2021 | 2021-02-25 | 0 | TNJ130
185 | TNJ167 | TNJ167 | Thanjavur | Trichy |  | ROTN | Indus | IN-1645403 | R/NN-562649 | Nominals with issues |  | 2021-01-15 | TNJ167 | 4G_FD900_TNJ167 | 4G_FD2100_TNJ167 | 4G_TD_TNJ167 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362863 | 2021-06-26 | P/FVC/MDS/1050077/2021 | 2021-08-09 | ST202102032238 | 2021-02-01 | P/FVC/MDS/1011663/2021 | 2021-03-05 |  |  |  |  | ST202101027832 | 2021-01-29 | P/FBW/MDS/1010936/2021 | 2021-02-24 | Partof461sitesSyamaMay'30/Tcocchangedfromowntoindus8/5/2019/R/NN-361838SOSurrenderedbyindus1/13/2020/R/NN-392550/SRwithdrwanduetoDAY1TDDandrepunched | TNJ167
186 | TRY364 | TRY364 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-1690716 | R/NN-564307 | Nominals with issues | SR | 2021-02-05 | TRY364 | 4G_FD900_TRY364 | 4G_FD2100_TRY364 | 4G_TD_TRY364 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363077 | 2021-06-26 | P/FVC/MDS/1050087/2021 | 2021-08-09 | ST202102047448 | 2021-02-10 | P/FVC/MDS/1011478/2021 | 2021-03-05 |  |  |  |  | ST202102049139 | 2021-02-10 | P/FBW/MDS/1011515/2021 | 2021-03-05 | Old SO R/NN-468986 terminated by Indus and repunched on Jan 29, 2021 | TRY364
187 | TUT131 | TUT131 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-1622429 | R/NN-561944 | Nominals with issues | SO | 2021-02-11 | TUT131 | 4G_FD900_TUT131 | 4G_FD2100_TUT131 | 4G_TD_TUT131 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363094 | 2021-06-26 | P/FVC/MDS/1050095/2021 | 2021-08-09 | ST202102055244 | 2021-02-16 | P/FVC/MDS/1011547/2021 | 2021-03-05 |  |  |  |  | ST202102053974 | 2021-02-16 | P/FBW/MDS/1011867/2021 | 2021-03-09 | 0 | TUT131
188 | VENGPT | VENGPT | Tirunelveli | Madurai |  | ROTN | Indus | IN-1512642 | R/NN-558925 | Nominals with issues | On Air | 2021-02-05 | VENGPT | 4G_FD900_VENGPT | 4G_FD2100_VENGPT | 4G_TD_VENGPT | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202109515580 | 2021-09-09 | P/FVC/MDS/1060954/2021 | 2021-09-14 | ST202110574116 | 2021-10-28 | P/FVC/MDS/1065815/2021 | 2021-11-16 | ST202109515206 | 2021-09-09 | P/FVC/MDS/1062188/2021 | 2021-09-20 | ST202108430478 | 2021-08-17 | P/FBW/MDS/1056038/2021 | 2021-09-07 | 0 | VENGPT
189 | VLKL8 | VLKL08 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1644691 | R/NN-562632 | Nominals with issues | On Air | 2021-01-19 | VLKL08 | 4G_FD900_VLKL08 | 4G_FD2100_VLKL08 | 4G_TD_VLKL08 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202108430703 | 2021-08-17 | P/FVC/MDS/1059657/2021 | 2021-09-12 | ST202109511387 | 2021-09-07 | P/FVC/MDS/1061434/2021 | 2021-09-15 |  |  |  |  | ST202108430493 | 2021-08-17 | P/FBW/MDS/1056051/2021 | 2021-09-07 | NoResponsefromBSNL.HenceTOCOchangedtoIndusonFeb8,2019R/NN-323047Withdrwanandrebokedastransitionalbasisonjawhar5/15/2019/R/NN-336805SOsurrenderedbyindusyjawhar11/22/2019/R/NN-382679/SRwithdrwanduetoDAY1TDDandrepunched | VLKL8
190 | KDKLM8 | KDKLM8 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1687991 | R/NN-563434 | Nominals with issues | Dropped-Canb. | 2021-02-03 | KDKLM8 | 4G_FD900_KDKLM8 | 4G_FD2100_KDKLM8 | 4G_TD_KDKLM8 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363262 | 2021-06-26 | P/FVC/MDS/1050126/2021 | 2021-08-09 | ST202102047257 | 2021-02-10 | P/FVC/MDS/1011472/2021 | 2021-03-05 |  |  |  |  | ST202102049136 | 2021-02-10 | P/FBW/MDS/1011512/2021 | 2021-03-05 | 0 | KDKLM8
191 | PVLR9 | PVLR09 | Namakkal | Coimbatore |  | ROTN | Indus | IN-1722085 | R/NN-565168 | Nominals with issues | Dropped-Canb. | 2021-02-18 | PVLR09 | 4G_FD900_PVLR09 | 4G_FD2100_PVLR09 | 4G_TD_PVLR09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364111 | 2021-06-28 | P/FVC/MDS/1050137/2021 | 2021-08-09 | ST202102055618 | 2021-02-16 | P/FVC/MDS/1011566/2021 | 2021-03-05 |  |  |  |  | ST202102053646 | 2021-02-15 | P/FBW/MDS/1012752/2021 | 2021-03-13 | 0 | PVLR9
192 | TCDR10 | TCDR10 | Thoothukkudi | Madurai |  | ROTN | Summit |  |  | Nominal WIP | SO | 2021-02-15 | TCDR10 | 4G_FD900_TCDR10 | 4G_FD2100_TCDR10 | 4G_TD_TCDR10 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364149 | 2021-06-28 | P/FVC/MDS/1050153/2021 | 2021-08-09 | ST202102047461 | 2021-02-10 | P/FVC/MDS/1011491/2021 | 2021-03-05 | ST202102047598 | 2021-02-10 | P/FVC/MDS/1011235/2021 | 2021-03-03 | ST202102049212 | 2021-02-10 | P/FBW/MDS/1013112/2021 | 2021-03-16 | SOCanceledbyATConSep12,2020(Muthusir/Arulmail)andgiventoowntoco | TCDR10
193 | SVPT19 | SVPT19 | Virudhunagar | Madurai |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. |  | SVPT19 | 4G_FD900_SVPT19 | 4G_FD2100_SVPT19 | 4G_TD_SVPT19 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364150 | 2021-06-28 | P/FVC/MDS/1050154/2021 | 2021-08-09 | ST202110577686 | 2021-10-30 | P/FVC/MDS/1065915/2021 | 2021-11-16 | ST202107388491 | 2021-07-19 | P/FVC/MDS/1056676/2021 | 2021-09-08 | ST202107389819 | 2021-07-20 | P/FBW/MDS/1056635/2021 | 2021-09-08 | SO Hold R/NN-320151 Canceled by Indus Nitin on Feb 22021 SR Terminated by Indus 15-Apr'21 | SVPT19
194 | APKT29 | APKT29 | Virudhunagar | Madurai |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2021-02-22 | APKT29 | 4G_FD900_APKT29 | 4G_FD2100_APKT29 | 4G_TD_APKT29 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364156 | 2021-06-28 | P/FVC/MDS/1050160/2021 | 2021-08-09 | ST202102047457 | 2021-02-10 | P/FVC/MDS/1011487/2021 | 2021-03-05 | ST202102047595 | 2021-02-10 | P/FVC/MDS/1011232/2021 | 2021-03-03 | ST202102049209 | 2021-02-10 | P/FBW/MDS/1013109/2021 | 2021-03-16 | Partof461sitesSyamaMay'30 | APKT29
195 | TUT125 | TUT125 | Thoothukkudi | Madurai |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2021-02-22 | TUT125 | 4G_FD900_TUT125 | 4G_FD2100_TUT125 | 4G_TD_TUT125 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364516 | 2021-06-28 | P/FVC/MDS/1050296/2021 | 2021-08-09 | ST202102047462 | 2021-02-10 | P/FVC/MDS/1011492/2021 | 2021-03-05 |  |  |  |  | ST202102049213 | 2021-02-10 | P/FBW/MDS/1013113/2021 | 2021-03-16 | 0 | TUT125
196 | NGL113 | NGL113 | Kanniyakumari | Madurai |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2021-01-13 | NGL113 | 4G_FD900_NGL113 | 4G_FD2100_NGL113 | 4G_TD_NGL113 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366809 | 2021-06-30 | P/FVC/MDS/1050175/2021 | 2021-08-09 | ST202107380611 | 2021-07-10 | P/FVC/MDS/1055986/2021 | 2021-09-06 | ST202107369684 | 2021-07-01 | P/FVC/MDS/1056085/2021 | 2021-09-07 | ST202107379959 | 2021-07-10 | P/FBW/MDS/1057141/2021 | 2021-09-09 | SP R/NN-469236 Rejected on Dec 7, 2020 due to Low AGL Than Booking & RF Clearance | NGL113
197 | MDKLR2 | MDKLR2 | Ramanathapuram | Madurai |  | ROTN | ATC |  |  | Nominal WIP | SR | 2021-01-11 | MDKLR2 | 4G_FD900_MDKLR2 | 4G_FD2100_MDKLR2 | 4G_TD_MDKLR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366853 | 2021-06-30 | P/FVC/MDS/1050199/2021 | 2021-08-09 | ST202102032232 | 2021-02-01 | P/FVC/MDS/1011656/2021 | 2021-03-05 |  |  |  |  | ST202101027725 | 2021-01-29 | P/FBW/MDS/1011093/2021 | 2021-02-25 | 0 | MDKLR2
198 | SOMNT1 | SOMNT1 | Sivaganga | Madurai |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2021-01-07 | SOMNT1 | 4G_FD900_SOMNT1 | 4G_FD2100_SOMNT1 | 4G_TD_SOMNT1 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366906 | 2021-06-30 | P/FVC/MDS/1050208/2021 | 2021-08-09 | ST202102032257 | 2021-02-01 | P/FVC/MDS/1011676/2021 | 2021-03-05 |  |  |  |  | ST202101027497 | 2021-01-29 | P/FBW/MDS/1011082/2021 | 2021-02-25 | 0 | SOMNT1
199 | MDU480 | MDU480 | Madurai | Madurai |  | ROTN | ATC |  |  | Nominal WIP | SR | 2021-01-07 | MDU480 | 4G_FD900_MDU480 | 4G_FD2100_MDU480 | 4G_TD_MDU480 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363689 | 2021-06-28 | P/FVC/MDS/1050264/2021 | 2021-08-09 | ST202102032361 | 2021-02-01 | P/FVC/MDS/1011689/2021 | 2021-03-05 |  |  |  |  | ST202101027496 | 2021-01-29 | P/FBW/MDS/1011081/2021 | 2021-02-25 |  | MDU480
200 | OKDI7 | OKDI07 | Madurai | Madurai |  | ROTN | ATC |  |  | Nominal WIP |  | 2021-01-18 | OKDI07 | 4G_FD900_OKDI07 | 4G_FD2100_OKDI07 | 4G_TD_OKDI07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363688 | 2021-06-28 | P/FVC/MDS/1050263/2021 | 2021-08-09 | ST202102032296 | 2021-02-01 | P/FVC/MDS/1011684/2021 | 2021-03-05 |  |  |  |  | ST202101028313 | 2021-01-29 | P/FBW/MDS/1011073/2021 | 2021-02-25 | 0 | OKDI7
201 | PDPTR3 | PDPTR3 | Thoothukkudi | Madurai |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2021-01-19 | PDPTR3 | 4G_FD900_PDPTR3 | 4G_FD2100_PDPTR3 | 4G_TD_PDPTR3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363673 | 2021-06-28 | P/FVC/MDS/1050248/2021 | 2021-08-09 | ST202102032488 | 2021-02-01 | P/FVC/MDS/1011728/2021 | 2021-03-05 |  |  |  |  | ST202102037956 | 2021-02-04 | P/FBW/MDS/1010692/2021 | 2021-02-23 | 0 | PDPTR3
202 | PUZH14 | PUZH14 | Chennai | Chennai |  | CHN | Indus | R/NN-478927 | 0 | Nominal WIP |  | 2021-01-19 | PUZH14 | 4G_FD900_PUZH14 | 4G_FD2100_PUZH14 | 4G_TD_PUZH14 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109533399 | 2021-09-25 | P/FVC/MDS/1062984/2021 | 2021-10-01 | ST202109532046 | 2021-09-24 | P/FVC/MDS/1062906/2021 | 2021-10-01 | ST202109530307 | 2021-09-24 | P/FVC/MDS/1063067/2021 | 2021-10-01 | ST202109533087 | 2021-09-25 | P/FVC/MDS/1062843/2021 | 2021-10-01
203 | ATHGA4 | ATHGA4 |  |  |  | ROTN | Indus | R/NN-564312 |  |  |  | 2021-02-15 | ATHGA4 | 4G_FD900_ATHGA4 | 4G_FD2100_ATHGA4 | 4G_TD_ATHGA4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498661 | 2021-08-31 | P/FVC/MDS/1060450/2021 | 2021-09-13 | ST202102055616 | 2021-02-16 | P/FVC/MDS/1011564/2021 | 2021-03-05 | ST202102054009 | 2021-02-10 | P/FBW/MDS/1011824/2021 | 2021-03-09 | ST202102053655 | 2021-02-15 | P/FBW/MDS/1012756/2021 | 2021-03-13 |  | ATHGA4
204 | TKSI25 | TKSI25 | Tirunelveli | Madurai |  | ROTN | Ascend |  |  | Nominals with issues | On Air | 2021-01-27 | TKSI25 | 4G_FD900_TKSI25 | 4G_FD2100_TKSI25 | 4G_TD_TKSI25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362852 | 2021-06-26 | P/FVC/MDS/1046134/2021 | 2021-08-03 | ST202102042163 | 2021-02-08 | P/FVC/MDS/1010870/2021 | 2021-02-24 |  |  |  |  | ST202102037953 | 2021-02-04 | P/FBW/MDS/1010689/2021 | 2021-02-23 | 0 | TKSI25
205 | TRPTM4 | TRPTM4 | Nagapattinam | Trichy |  | ROTN | Ascend |  |  | Nominals with issues | SO | 2021-01-28 | TRPTM4 | 4G_FD900_TRPTM4 | 4G_FD2100_TRPTM4 | 4G_TD_TRPTM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363072 | 2021-06-26 | P/FVC/MDS/1050082/2021 | 2021-08-09 | ST202102042169 | 2021-02-08 | P/FVC/MDS/1010876/2021 | 2021-02-24 |  |  |  |  | ST202102037980 | 2021-02-04 | P/FBW/MDS/1010702/2021 | 2021-02-23 | 0 | TRPTM4
206 | VDLR18 | VDLR18 | Cuddalore | Trichy |  | ROTN | Indus | IN-1662225 | R/NN-563387 | Nominals with issues | On Air | 2021-01-29 | VDLR18 | 4G_FD900_VDLR18 | 4G_FD2100_VDLR18 | 4G_TD_VDLR18 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202112610818 | 2021-12-10 | P/FVC/MDS/1069074/2021 | 2021-12-17 | ST202112604359 | 2021-12-07 | P/FVC/MDS/1068752/2021 | 2021-12-15 |  |  |  |  | ST202112608811 | 2021-12-09 | P/FBW/MDS/1068856/2021 | 2021-12-15 | 0 | VDLR18
207 | KPMPT4 | KPMPT4 | Tiruchirappalli | Trichy |  | ROTN | ATC |  |  | Nominal WIP |  | 2021-01-23 | KPMPT4 | 4G_FD900_KPMPT4 | 4G_FD2100_KPMPT4 | 4G_TD_KPMPT4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202109527655 | 2021-09-22 | P/FVC/MDS/1062546/2021 | 2021-09-27 | ST202109522210 | 2021-09-16 | P/FVC/MDS/1062468/2021 | 2021-09-23 | ST202109530018 | 2021-09-24 | P/FVC/MDS/1063004/2021 | 2021-10-01 | ST202109522264 | 2021-09-16 | P/FBW/MDS/1062515/2021 | 2021-09-23 |  | KPMPT4
208 | PJPT8 | PJPT08 | Erode | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2021-01-23 | PJPT08 | 4G_FD900_PJPT08 | 4G_FD2100_PJPT08 | 4G_TD_PJPT08 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363674 | 2021-06-28 | P/FVC/MDS/1050249/2021 | 2021-08-09 | ST202102042285 | 2021-02-08 | P/FVC/MDS/1010891/2021 | 2021-02-24 | ST202102042724 | 2021-02-02 | P/FVC/MDS/1011210/2021 | 2021-03-01 | ST202102038516 | 2021-02-04 | P/FBW/MDS/1010731/2021 | 2021-02-23 | 0 | PJPT8
209 | DGL105 | DGL105 | Dindigul | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2021-01-23 | DGL105 | 4G_FD900_DGL105 | 4G_FD2100_DGL105 | 4G_TD_DGL105 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363672 | 2021-06-28 | P/FVC/MDS/1050247/2021 | 2021-08-09 | ST202102042260 | 2021-02-08 | P/FVC/MDS/1010881/2021 | 2021-02-24 |  |  |  |  | ST202102038135 | 2021-02-04 | P/FBW/MDS/1010712/2021 | 2021-02-23 | 0 | DGL105
210 | TVML78 | TVML78 | Tiruvannamalai | Vellore |  | ROTN | INDUS |  |  | Nominal WIP | Dropped-Canb. | 2021-04-12 | TVML78 | 4G_FD900_TVML78 | 4G_FD2100_TVML78 | 4G_TD_TVML78 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363671 | 2021-06-28 | P/FVC/MDS/1050246/2021 | 2021-08-09 | ST202105293419 | 2021-05-25 | P/FVC/MDS/1036599/2021 | 2021-06-23 |  |  |  |  | ST202105228517 | 2021-05-04 | P/FBW/MDS/1020374/2021 | 2021-05-23 | Under Project Vellore , AT wont able to RFI - SO withdrawan and given to Indus | TVML78
211 | APTNM4 | APTNM4 |  |  |  | ROTN | Indus | R/NN-430625 |  |  |  | 2021-01-29 | APTNM4 | 4G_FD900_APTNM4 | 4G_FD2100_APTNM4 | 4G_TD_APTNM4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108410887 | 2021-08-06 | P/FVC/MDS/1052918/2021 | 2021-08-20 | ST202102042266 | 2021-02-08 | P/FVC/MDS/1010888/2021 | 2021-02-24 | ST202102042714 | 2021-02-02 | P/FVC/MDS/1011208/2021 | 2021-03-01 | ST202102038491 | 2021-02-04 | P/FBW/MDS/1010722/2021 | 2021-02-23 |  | APTNM4
212 | CBE841 | CBE841 | Coimbatore | Coimbatore |  | ROTN | Ascend | 0011080 | - | Nominals with issues | Dropped-Canb. | 2021-01-02 | CBE841 | 4G_FD900_CBE841 | 4G_FD2100_CBE841 | 4G_TD_CBE841 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361962 | 2021-06-25 | P/FVC/MDS/1049920/2021 | 2021-08-09 | ST202101023193 | 2021-01-25 | P/FVC/MDS/1010759/2021 | 2021-02-23 |  |  |  |  | ST202101024842 | 2021-01-26 | P/FBW/MDS/1010983/2021 | 2021-02-24 | 0 | CBE841
213 | CDBM55 | CDBM55 | Cuddalore | Trichy |  | ROTN | Indus | IN-1583121 | R/NN-561101 | Nominals with issues | SO | 2021-02-08 | CDBM55 | 4G_FD900_CDBM55 | 4G_FD2100_CDBM55 | 4G_TD_CDBM55 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361976 | 2021-06-25 | P/FVC/MDS/1049926/2021 | 2021-08-09 | ST202101023312 | 2021-01-25 | P/FVC/MDS/1010782/2021 | 2021-02-23 |  |  |  |  | ST202101024887 | 2021-01-26 | P/FBW/MDS/1011000/2021 | 2021-02-24 | 0 | CDBM55
214 | CMGM7 | CMGM07 | Namakkal | Coimbatore |  | ROTN | Ascend | 0011091 | - | Nominals with issues |  | 2021-01-06 | CMGM07 | 4G_FD900_CMGM07 | 4G_FD2100_CMGM07 | 4G_TD_CMGM07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362084 | 2021-06-25 | P/FVC/MDS/1049929/2021 | 2021-08-09 | ST202101023203 | 2021-01-25 | P/FVC/MDS/1010769/2021 | 2021-02-23 |  |  |  |  | ST202101024849 | 2021-01-26 | P/FBW/MDS/1010990/2021 | 2021-02-24 |  | CMGM7
215 | PMKD21 | PMKD21 | Ramanathapuram | Madurai |  | ROTN | Ascend | 0 | - | Nominal WIP | SR | 2021-01-08 | PMKD21 | 4G_FD900_PMKD21 | 4G_FD2100_PMKD21 | 4G_TD_PMKD21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362750 | 2021-06-26 | P/FVC/MDS/1046133/2021 | 2021-08-03 | ST202101023207 | 2021-01-25 | P/FVC/MDS/1010773/2021 | 2021-02-23 |  |  |  |  | ST202101024850 | 2021-01-26 | P/FBW/MDS/1010991/2021 | 2021-02-24 | 20-20-TopTowns0.8Validation/R/NN-384765/SRwithdrwanduetoDAY1TDDandrepunched Indus SR R/NN-438254 Withdrawn on Dec 21 and realloted to Ascend basis Indus DTA Mail from Muthu sir/Jawahar on Dec 17, 2020 | PMKD21
216 | PYKLI4 | PYKLI4 | Kanniyakumari | Madurai |  | ROTN | Ascend |  |  | Nominal WIP | On Air | 2021-04-03 | PYKLI4 | 4G_FD900_PYKLI4 | 4G_FD2100_PYKLI4 | 4G_TD_PYKLI4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202201000637 | 2022-01-03 | P/FVC/MDS/1071064/2022 | 2022-01-10 | ST202201000661 | 2022-01-06 | P/FVC/MDS/1071057/2022 | 2022-01-10 |  |  |  |  | ST202201000694 | 2022-01-03 | P/FBW/MDS/1071074/2022 | 2022-01-10 | 2121 Not Feasible, By BSNL - Suresh mail 27-May'21 - Location also changed , Old Location-8.206238,77.330552 | PYKLI4
217 | CBE844 | CBE844 | Coimbatore | Coimbatore |  | ROTN | Indus |  |  |  |  | 2021-07-09 | CBE844 | 4G_FD900_CBE844 | 4G_FD2100_CBE844 | 4G_TD_CBE844 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107386789 | 2021-07-17 | P/FVC/MDS/1051593/2021 | 2021-08-14 | ST202101023208 | 2021-01-25 | P/FVC/MDS/1010774/2021 | 2021-02-23 |  |  |  |  | ST202101024851 | 2021-01-26 | P/FBW/MDS/1010992/2021 | 2021-02-24 | New SR punched on 10-Apr'21 to Indus | CBE844
218 | CHPT44 | CHPT44 | Kancheepuram | Chennai |  | ROTN | Indus | IN-1386733 | R/NN-457560 | Nominals with issues | Dropped-Canb. | 2021-01-04 | CHPT44 | 4G_FD900_CHPT44 | 4G_FD2100_CHPT44 | 4G_TD_CHPT44 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362083 | 2021-06-25 | P/FVC/MDS/1049928/2021 | 2021-08-09 | ST202101009923 | 2021-01-13 | P/FVC/MDS/1009729/2021 | 2021-01-24 |  |  |  |  | ST202101019543 | 2021-01-25 | P/FBW/MDS/1010955/2021 | 2021-02-24 | Partof461sitesSyamaMay'30/Earliercheck,nowP0/P1/TocochangedfromATCtoinuds6/22/2020 | CHPT44
219 | KKD66 | KKD066 | Sivaganga | Madurai |  | ROTN | Indus | IN-1426784 | R/NN-468959 | Nominals with issues | Dropped-Canb. | 2020-12-21 | KKD066 | 4G_FD900_KKD066 | 4G_FD2100_KKD066 | 4G_TD_KKD066 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362309 | 2021-06-25 | P/FVC/MDS/1049961/2021 | 2021-08-09 | ST202101010090 | 2021-01-13 | P/FVC/MDS/1009751/2021 | 2021-01-24 |  |  |  |  | ST202101010537 | 2021-01-13 | P/FBW/MDS/1009763/2021 | 2021-01-24 | 0 | KKD66
220 | SEERPL1 | SEERPL1 | Namakkal | Coimbatore |  | ROTN | Indus |  |  | Nominal WIP |  | 2020-12-12 | SEERPL1 | 4G_FD900_SEERPL1 | 4G_FD2100_SEERPL1 | 4G_TD_SEERPL1 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364540 | 2021-06-28 | P/FVC/MDS/1050300/2021 | 2021-08-09 | ST202101010022 | 2021-01-13 | P/FVC/MDS/1009741/2021 | 2021-01-24 | ST202101010092 | 2021-01-13 | P/FVC/MDS/1009752/2021 | 2021-01-24 | ST202103082325 | 2021-03-06 | P/FBW/MDS/1013418/2021 | 2021-03-17 |  | SEERPL
221 | PKGD11 | PKGD11 | Tirunelveli | Madurai |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-12-28 | PKGD11 | 4G_FD900_PKGD11 | 4G_FD2100_PKGD11 | 4G_TD_PKGD11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366835 | 2021-06-30 | P/FVC/MDS/1050181/2021 | 2021-08-09 | ST202101009972 | 2021-01-13 | P/FVC/MDS/1009733/2021 | 2021-01-24 |  |  |  |  | ST202101010549 | 2021-01-13 | P/FBW/MDS/1009770/2021 | 2021-01-24 | 0 | PKGD11
222 | PDY224 | PDY224 | Puducherry | Trichy |  | ROTN | Indus | IN-1403446 | R/NN-466226 | Nominals with issues | SR | 2020-12-18 | PDY224 | 4G_FD900_PDY224 | 4G_FD2100_PDY224 | 4G_TD_PDY224 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362727 | 2021-06-26 | P/FVC/MDS/1050016/2021 | 2021-08-09 | ST202101005283 | 2021-01-08 | P/FVC/MDS/1009082/2021 | 2021-01-17 |  |  |  |  | ST202101005615 | 2021-01-08 | P/FBW/MDS/1009690/2021 | 2021-01-24 | SocanceledbyAcendMay7'19andtocochangedtoATCmay7'19/SRwithdrawnbyATC7/27/2020 New SR Punched to Indus on 17-Apr'21,Old Planned coordinate was11.9181,79.8061 | PDY224
223 | TNJ137 | TNJ137 | Thanjavur | Trichy |  | ROTN | Indus | IN-1492631 | R/NN-544518 | Nominals with issues | SR | 2020-12-17 | TNJ137 | 4G_FD900_TNJ137 | 4G_FD2100_TNJ137 | 4G_TD_TNJ137 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362862 | 2021-06-26 | P/FVC/MDS/1050076/2021 | 2021-08-09 | ST202101005279 | 2021-01-08 | P/FVC/MDS/1009078/2021 | 2021-01-17 |  |  |  |  | ST202101005652 | 2021-01-08 | P/FBW/MDS/1009700/2021 | 2021-01-24 | 0 | TNJ137
224 | VACHPT | VACHPT | Virudhunagar | Madurai |  | ROTN | Indus | IN-1436229 | R/NN-469621 | Nominals with issues | Dropped | 2020-12-17 | VACHPT | 4G_FD900_VACHPT | 4G_FD2100_VACHPT | 4G_TD_VACHPT | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106363156 | 2021-06-26 | P/FVC/MDS/1050108/2021 | 2021-08-09 | ST202101005282 | 2021-01-08 | P/FVC/MDS/1009081/2021 | 2021-01-17 | ST202101005339 | 2021-01-08 | P/FVC/MDS/1009117/2021 | 2021-01-17 | ST202108430476 | 2021-08-17 | P/FBW/MDS/1056036/2021 | 2021-09-07 | 0 | VACHPT
225 | SMGI7 | SMGI07 | Coimbatore | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2020-12-09 | SMGI07 | 4G_FD900_SMGI07 | 4G_FD2100_SMGI07 | 4G_TD_SMGI07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366852 | 2021-06-30 | P/FVC/MDS/1050198/2021 | 2021-08-09 | ST202101005292 | 2021-01-08 | P/FVC/MDS/1009088/2021 | 2021-01-17 | ST202101005353 | 2021-01-08 | P/FVC/MDS/1009120/2021 | 2021-01-17 | ST202103075091 | 2021-03-02 | P/FBW/MDS/1012481/2021 | 2021-03-13 | Changed from L21 to L23 basis discussion with CEO - Mar 1, 2021 | SMGI7
226 | AVNI27 | AVNI27 | Tiruppur | Coimbatore |  | ROTN | ATC | TN/TI/AT/22297 | T20TN07642 | Nominals with issues | Dropped-Canb. | 2020-12-24 | AVNI27 | 4G_FD900_AVNI27 | 4G_FD2100_AVNI27 | 4G_TD_AVNI27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361843 | 2021-06-25 | P/FVC/MDS/1049904/2021 | 2021-08-09 | ST202101001424 | 2021-01-04 | P/FVC/MDS/1009043/2021 | 2021-01-16 |  |  |  |  | ST202101001177 | 2021-01-04 | P/FBW/MDS/1008974/2021 | 2021-01-16 | 0 | AVNI27
227 | DVKT36 | DVKT36 | Sivaganga | Madurai |  | ROTN | Ascend | 0011038 | - | Nominals with issues | Drop | 2020-12-28 | DVKT36 | 4G_FD900_DVKT36 | 4G_FD2100_DVKT36 | 4G_TD_DVKT36 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362261 | 2021-06-25 | P/FVC/MDS/1049936/2021 | 2021-08-09 | ST202101001399 | 2021-01-04 | P/FVC/MDS/1009029/2021 | 2021-01-16 |  |  |  |  | ST202101001165 | 2021-01-04 | P/FBW/MDS/1008962/2021 | 2021-01-16 | 0 | DVKT36
228 | GOBI32 | GOBI32 | Erode | Coimbatore |  | ROTN | Airtel | GOBI32 | - | Nominals with issues | Dropped-Canb. | 2020-12-30 | GOBI32 | 4G_FD900_GOBI32 | 4G_FD2100_GOBI32 | 4G_TD_GOBI32 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362280 | 2021-06-25 | P/FVC/MDS/1049946/2021 | 2021-08-09 | ST202101001457 | 2021-01-04 | P/FVC/MDS/1009059/2021 | 2021-01-16 | ST202104150507 | 2021-04-16 | P/FVC/MDS/1017536/2021 | 2021-05-13 | ST202101001188 | 2021-01-04 | P/FBW/MDS/1008985/2021 | 2021-01-16 | Partof461sitesSyamaMay'30/Earliercheck,nowP0/P1/changesP1syama2/10/2020
229 | NGPM16 | NGPM16 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1399511 | R/NN-466230 | Nominals with issues | Dropped | 2020-12-21 | NGPM16 | 4G_FD900_NGPM16 | 4G_FD2100_NGPM16 | 4G_TD_NGPM16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362648 | 2021-06-26 | P/FVC/MDS/1050006/2021 | 2021-08-09 | ST202101001410 | 2021-01-04 | P/FVC/MDS/1009036/2021 | 2021-01-16 |  |  |  |  | ST202101010539 | 2021-01-13 | P/FBW/MDS/1009765/2021 | 2021-01-24 | Partof461sitesSyamaMay'30/SOSurrenderedbyATCconfirmedbysyama10/4/2019/SRwithdrawnbyATC7/27/2020 | NGPM16
230 | VDRNM4 | VDRNM4 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1387747 | R/NN-463671 | Nominals with issues | On Air | 2020-12-22 | VDRNM4 | 4G_FD900_VDRNM4 | 4G_FD2100_VDRNM4 | 4G_TD_VDRNM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363195 | 2021-06-26 | P/FVC/MDS/1050111/2021 | 2021-08-09 | ST202101001409 | 2021-01-04 | P/FVC/MDS/1009035/2021 | 2021-01-16 |  |  |  |  | ST202101010538 | 2021-01-13 | P/FBW/MDS/1009764/2021 | 2021-01-24 | 0 | VDRNM4
231 | PLCH46 | PLCH46 | Coimbatore | Coimbatore |  | ROTN | Indus |  |  | Nominal WIP | SRB(Surrender) | 2021-04-19 | PLCH46 | 4G_FD900_PLCH46 | 4G_FD2100_PLCH46 | 4G_TD_PLCH46 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363690 | 2021-06-28 | P/FVC/MDS/1050265/2021 | 2021-08-09 | ST202105294032 | 2021-05-25 | P/FVC/MDS/1036619/2021 | 2021-06-23 |  |  |  |  | ST202105224839 | 2021-05-04 | P/FBW/MDS/1020343/2021 | 2021-05-23 | Ascend surrendered SO on Jan 22, 2021 basis which SCM canceled SO on Jan 25, 2022 | PLCH46
232 | VDGPM2 | VDGPM2 |  |  |  | ROTN | Indus | R/NN-559100 |  |  |  | 2020-12-21 | VDGPM2 | 4G_FD900_VDGPM2 | 4G_FD2100_VDGPM2 | 4G_TD_VDGPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108410913 | 2021-08-06 | P/FVC/MDS/1052919/2021 | 2021-08-20 | ST202101001447 | 2021-01-04 | P/FVC/MDS/1009055/2021 | 2021-01-16 | ST202101007490 | 2021-01-10 | P/FVC/MDS/1009652/2021 | 2021-01-17 | ST202101001186 | 2021-01-04 | P/FBW/MDS/1008983/2021 | 2021-01-16 |  | VDGPM2
233 | ARCT28 | ARCT28 | Vellore | Vellore |  | ROTN | Indus | IN-1388996 | R/NN-464144 | Nominals with issues | SO | 2020-12-31 | ARCT28 | 4G_FD900_ARCT28 | 4G_FD2100_ARCT28 | 4G_TD_ARCT28 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361834 | 2021-06-25 | P/FVC/MDS/1049897/2021 | 2021-08-09 | ST202101001554 | 2021-01-04 | P/FVC/MDS/1008735/2021 | 2021-01-15 |  |  |  |  | ST202101001283 | 2021-01-04 | P/FBW/MDS/1008950/2021 | 2021-01-16 | 0 | ARCT28
234 | CANAL6 | CANAL6 | Chennai | Chennai |  | CHN | Airtel | CANAL6 | - | Nominals with issues | SO | 2020-12-01 | CANAL6 | 4G_FD900_CANAL6 | 4G_FD2100_CANAL6 | 4G_TD_CANAL6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202101000636 | 2021-01-02 | P/FVC/MDS/1008808/2021 | 2021-01-15 | ST202101000750 | 2021-01-02 | P/FVC/MDS/1008829/2021 | 2021-01-15 | ST202106358167 | 2021-06-23 | P/FVC/MDS/1055848/2021 | 2021-09-04 | ST202101001113 | 2021-01-04 | P/FBW/MDS/1008910/2021 | 2021-01-16 | 0
235 | DVKT33 | DVKT33 | Sivaganga | Madurai |  | ROTN | Ascend | 0011086 | - | Nominals with issues | On Air | 2021-01-04 | DVKT33 | 4G_FD900_DVKT33 | 4G_FD2100_DVKT33 | 4G_TD_DVKT33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202203074022 | 2022-03-16 | P/FVC/MDS/1077180/2022 | 2022-03-30 | ST202203073642 | 2022-03-16 | P/FVC/MDS/1077132/2022 | 2022-03-30 |  |  |  |  | ST202203072994 | 2022-03-15 | P/FBW/MDS/1077085/2022 | 2022-03-30 | 0 | DVKT33
236 | KTP23 | KTP023 | Vellore | Vellore |  | ROTN | TVI | Yet to be generated | - | Nominals with issues | On Air | 2020-12-30 | KTP023 | 4G_FD900_KTP023 | 4G_FD2100_KTP023 | 4G_TD_KTP023 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202202048188 | 2022-02-18 | P/FVC/MDS/1075002/2022 | 2022-02-28 | ST202202049432 | 2022-02-19 | P/FVC/MDS/1074947/2022 | 2022-02-28 |  |  |  |  | ST202202048683 | 2022-02-18 | P/FBW/MDS/1074889/2022 | 2022-02-28 | 0 | KTP23
237 | MANG20 | MANG20 | Chennai | Chennai |  | CHN | Ascend | 0 | - | Nominals with issues | SR | 2020-12-31 | MANG20 | 4G_FD900_MANG20 | 4G_FD2100_MANG20 | 4G_TD_MANG20 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202101000659 | 2021-01-02 | P/FVC/MDS/1008824/2021 | 2021-01-15 | ST202101000770 | 2021-01-02 | P/FVC/MDS/1008849/2021 | 2021-01-15 | ST202106358260 | 2021-06-23 | P/FVC/MDS/1055857/2021 | 2021-09-04 | ST202101001103 | 2021-01-04 | P/FBW/MDS/1008940/2021 | 2021-01-16 | 0 | MANG20
238 | MTR28 | MTR028 | Salem | Vellore |  | ROTN | Indus | IN-1565730 | R/NN-560607 | Nominals with issues | Dropped-Canb. | 2021-01-25 | MTR028 | 4G_FD900_MTR028 | 4G_FD2100_MTR028 | 4G_TD_MTR028 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362638 | 2021-06-26 | P/FVC/MDS/1049999/2021 | 2021-08-09 | ST202101001551 | 2021-01-04 | P/FVC/MDS/1008732/2021 | 2021-01-15 |  |  |  |  | ST202101001266 | 2021-01-04 | P/FBW/MDS/1009018/2021 | 2021-01-16 | Old SO R/NN-385780 Canceled by indus and rebooked | MTR28
239 | NLKP9 | NLKP09 | Cuddalore | Trichy |  | ROTN | Indus | IN-1583131 | R/NN-561102 | Nominals with issues | On Air | 2020-12-31 | NLKP09 | 4G_FD900_NLKP09 | 4G_FD2100_NLKP09 | 4G_TD_NLKP09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362650 | 2021-06-26 | P/FVC/MDS/1050008/2021 | 2021-08-09 | ST202101001562 | 2021-01-04 | P/FVC/MDS/1008743/2021 | 2021-01-15 | ST202210548840 | 2022-10-11 | P/FVC/MDS/1113949/2022 | 2022-10-21 | ST202101001286 | 2021-01-04 | P/FBW/MDS/1008953/2021 | 2021-01-16 | 0 | NLKP9
240 | VLUR11 | VLUR11 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/22251 | T20TN07230 | Nominals with issues | Dropped-Canb. | 2021-01-12 | VLUR11 | 4G_FD900_VLUR11 | 4G_FD2100_VLUR11 | 4G_TD_VLUR11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363243 | 2021-06-26 | P/FVC/MDS/1046135/2021 | 2021-08-03 | ST202101001514 | 2021-01-04 | P/FVC/MDS/1008766/2021 | 2021-01-15 |  |  |  |  | ST202101001259 | 2021-01-04 | P/FBW/MDS/1009011/2021 | 2021-01-16 | 0 | VLUR11
241 | KMBLM4 | KMBLM4 | Coimbatore | Coimbatore |  | ROTN | TVI |  |  | Nominal WIP | Dropped | 2020-12-14 | KMBLM4 | 4G_FD900_KMBLM4 | 4G_FD2100_KMBLM4 | 4G_TD_KMBLM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364148 | 2021-06-28 | P/FVC/MDS/1050152/2021 | 2021-08-09 | ST202101001563 | 2021-01-04 | P/FVC/MDS/1008744/2021 | 2021-01-15 |  |  |  |  | ST202101001287 | 2021-01-04 | P/FBW/MDS/1008954/2021 | 2021-01-16 | Surrenderedbyown-MuthusirMailAug9 | KMBLM4
242 | ERD207 | ERD207 | Erode | Coimbatore |  | ROTN | Ascend |  |  | Nominal WIP | On Air | 2020-12-28 | ERD207 | 4G_FD900_ERD207 | 4G_FD2100_ERD207 | 4G_TD_ERD207 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366849 | 2021-06-30 | P/FVC/MDS/1050195/2021 | 2021-08-09 | ST202101001496 | 2021-01-04 | P/FVC/MDS/1008751/2021 | 2021-01-15 |  |  |  |  | ST202101001225 | 2021-01-04 | P/FBW/MDS/1009000/2021 | 2021-01-16 | 0 | ERD207
243 | NKPTY2 | NKPTY2 | Dindigul | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-12-28 | NKPTY2 | 4G_FD900_NKPTY2 | 4G_FD2100_NKPTY2 | 4G_TD_NKPTY2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366908 | 2021-06-30 | P/FVC/MDS/1050210/2021 | 2021-08-09 | ST202101001511 | 2021-01-04 | P/FVC/MDS/1008763/2021 | 2021-01-15 |  |  |  |  | ST202101001257 | 2021-01-04 | P/FBW/MDS/1009009/2021 | 2021-01-16 | 0 | NKPTY2
244 | MELPTT | MELPTT | Cuddalore | Trichy |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2020-12-28 | MELPTT | 4G_FD900_MELPTT | 4G_FD2100_MELPTT | 4G_TD_MELPTT | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366910 | 2021-06-30 | P/FVC/MDS/1050212/2021 | 2021-08-09 | ST202101001510 | 2021-01-04 | P/FVC/MDS/1008762/2021 | 2021-01-15 |  |  |  |  | ST202101001256 | 2021-01-04 | P/FBW/MDS/1009008/2021 | 2021-01-16 | 0 | MELPTT
245 | MENA13 | MENA13 | Chennai | Chennai |  | CHN | Indus | R/NN-478875 | 0 | Nominal WIP |  | 2020-12-19 | MENA13 | 4G_FD900_MENA13 | 4G_FD2100_MENA13 | 4G_TD_MENA13 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202101000640 | 2021-01-02 | P/FVC/MDS/1008812/2021 | 2021-01-15 | ST202101000755 | 2021-01-02 | P/FVC/MDS/1008834/2021 | 2021-01-15 | ST202101000788 | 2021-01-02 | P/FVC/MDS/1008868/2021 | 2021-01-16 | ST202101001120 | 2021-01-04 | P/FBW/MDS/1008917/2021 | 2021-01-16 |  | MENA13
246 | ALGPM2 | ALGPM2 |  |  |  | ROTN | Indus | R/NN-558984 |  |  |  | 2021-01-25 | ALGPM2 | 4G_FD900_ALGPM2 | 4G_FD2100_ALGPM2 | 4G_TD_ALGPM2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202108410880 | 2021-08-06 | P/FVC/MDS/1052911/2021 | 2021-08-20 | ST202101001515 | 2021-01-04 | P/FVC/MDS/1008768/2021 | 2021-01-15 | ST202101001047 | 2021-01-04 | P/FVC/MDS/1008883/2021 | 2021-01-16 | ST202101001260 | 2021-01-04 | P/FBW/MDS/1009012/2021 | 2021-01-16 |  | ALGPM2
247 | AZADN9 | AZADN9 | Chennai | Chennai |  | CHN | Airtel | [5 empty] | AZADN9 | 4G_FD900_AZADN9 | 4G_FD2100_AZADN9 | 4G_TD_AZADN9 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202101000642 | 2021-01-02 | P/FVC/MDS/1008814/2021 | 2021-01-15 | ST202101000759 | 2021-01-02 | P/FVC/MDS/1008838/2021 | 2021-01-15 | ST202101006443 | 2021-01-08 | P/FVC/MDS/1009159/2021 | 2021-01-17 | ST202101001146 | 2021-01-04 | P/FBW/MDS/1008929/2021 | 2021-01-16
248 | APTN10 | APTN10 | Thanjavur | Trichy |  | ROTN | Indus | IN-3010631 | R/NN-626415 |  | On Air | 2021-08-10 | APTN10 | 4G_FD900_APTN10 | 4G_FD2100_APTN10 | 4G_TD_APTN10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430710 | 2021-08-17 | P/FVC/MDS/1059662/2021 | 2021-09-12 | ST202108498210 | 2021-08-31 | P/FVC/MDS/1058567/2021 | 2021-09-10 |  |  |  |  | ST202108430498 | 2021-08-17 | P/FBW/MDS/1056056/2021 | 2021-09-07
249 | JKMPT2 | JKMPT2 | Theni | Madurai |  | ROTN | Indus | IN-1385539 | R/NN-442706 | Nominals with issues | Dropped-Canb. | 2020-12-13 | JKMPT2 | 4G_FD900_JKMPT2 | 4G_FD2100_JKMPT2 | 4G_TD_JKMPT2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362297 | 2021-06-25 | P/FVC/MDS/1049952/2021 | 2021-08-09 | ST202012177333 | 2020-12-18 | P/FVC/MDS/1008597/2021 | 2021-01-14 |  |  |  |  | ST202012176613 | 2020-12-17 | P/FBW/MDS/1007855/2020 | 2020-12-29 | 20-20-RestofUrban/R/NN-384772/SRwithdrwanduetoDAY1TDDandrepunched | JKMPT2
250 | MDTI39 | MDTI39 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1431642 | R/NN-469388 | Nominals with issues | On Air | 2020-12-08 | MDTI39 | 4G_FD900_MDTI39 | 4G_FD2100_MDTI39 | 4G_TD_MDTI39 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202112610909 | 2021-12-10 | P/FVC/MDS/1069089/2021 | 2021-12-17 | ST202012177355 | 2020-12-18 | P/FVC/MDS/1008605/2021 | 2021-01-14 |  |  |  |  | ST202012176601 | 2020-12-17 | P/FBW/MDS/1007848/2020 | 2020-12-29 | 0 | MDTI39
251 | TIR314 | TIR314 | Tiruppur | Coimbatore |  | ROTN | Ascend | 0 | - | Nominals with issues | On Air | 2020-11-30 | TIR314 | 4G_FD900_TIR314 | 4G_FD2100_TIR314 | 4G_TD_TIR314 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362803 | 2021-06-26 | P/FVC/MDS/1050063/2021 | 2021-08-09 | ST202012177315 | 2020-12-18 | P/FVC/MDS/1008582/2021 | 2021-01-14 |  |  |  |  | ST202012176579 | 2020-12-17 | P/FBW/MDS/1007843/2020 | 2020-12-29 | 0 | TIR314
252 | NAGPK1 | NAGPK1 | Madurai | Madurai |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2020-12-08 | NAGPK1 | 4G_FD900_NAGPK1 | 4G_FD2100_NAGPK1 | 4G_TD_NAGPK1 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366907 | 2021-06-30 | P/FVC/MDS/1050209/2021 | 2021-08-09 | ST202012177323 | 2020-12-18 | P/FVC/MDS/1008588/2021 | 2021-01-14 |  |  |  |  | ST202012176600 | 2020-12-17 | P/FBW/MDS/1007847/2020 | 2020-12-29 | 0 | NAGPK1
253 | MANG19 | MANG19 | Chennai | Chennai |  | CHN | Ascend | 0 | - | Nominals with issues | Dropped-Canb. | 2021-01-02 | MANG19 | 4G_FD900_MANG19 | 4G_FD2100_MANG19 | 4G_TD_MANG19 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202012176725 | 2020-12-17 | P/FVC/MDS/1007790/2020 | 2020-12-28 | ST202012176774 | 2020-12-17 | P/FVC/MDS/1007798/2020 | 2020-12-28 | ST202106358259 | 2021-06-23 | P/FVC/MDS/1055856/2021 | 2021-09-04 | ST202012176697 | 2020-12-17 | P/FBW/MDS/1007832/2020 | 2020-12-29 | SO Surrendered by Ascend on Dec 28, 2020 and SCM Canceled on Jan 2, 2021 | MANG19
254 | WABCO2 | WABCO2 | Chennai | Chennai |  | CHN | Airtel |  |  | Nominal WIP | On air |  | WABCO2 | 4G_FD900_WABCO2 | 4G_FD2100_WABCO2 | 4G_TD_WABCO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202012176723 | 2020-12-17 | P/FVC/MDS/1007788/2020 | 2020-12-28 | ST202012176772 | 2020-12-17 | P/FVC/MDS/1007796/2020 | 2020-12-28 |  |  |  |  | ST202012176695 | 2020-12-17 | P/FBW/MDS/1007830/2020 | 2020-12-29 | 0
255 | KSVMP2 | KSVMP2 |  |  |  | ROTN | Indus | R/NN-478914 |  |  |  | 2020-11-16 | KSVMP2 | 4G_FD900_KSVMP2 | 4G_FD2100_KSVMP2 | 4G_TD_KSVMP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201008746 | 2022-01-12 | P/FVC/MDS/1071699/2022 | 2022-01-20 | ST202201008645 | 2022-01-12 | P/FVC/MDS/1071624/2022 | 2022-01-20 | ST202201008989 | 2022-01-13 | P/FVC/MDS/1071731/2022 | 2022-01-20 | ST202201008804 | 2022-01-12 | P/FBW/MDS/1071539/2022 | 2022-01-20 | Old SO Withdrawan | KSVMP2
256 | MDPM3 | MDPM03 |  |  |  | ROTN | Indus | IN-3000750 | R/NN-620000 |  |  | 2021-08-03 | MDPM03 | 4G_FD900_MDPM03 | 4G_FD2100_MDPM03 | 4G_TD_MDPM03 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108430687 | 2021-08-17 | P/FVC/MDS/1059642/2021 | 2021-09-12 | ST202012163742 | 2020-12-02 | P/FVC/MDS/1007202/2020 | 2020-12-11 | ST202012163755 | 2020-12-02 | P/FVC/MDS/1007211/2020 | 2020-12-11 | ST202012163697 | 2020-12-02 | P/FBW/MDS/1007184/2020 | 2020-12-11
257 | KILABM | KILABM | Thiruvallur | Chennai |  | ROTN | ATC | TN/TU/AT/22614 | - |  | On Air | 2021-08-10 | KILABM | 4G_FD900_KILABM | 4G_FD2100_KILABM | 4G_TD_KILABM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497389 | 2021-08-30 | P/FVC/MDS/1060362/2021 | 2021-09-13 | ST202012163744 | 2020-12-02 | P/FVC/MDS/1007204/2020 | 2020-12-11 | ST202012163760 | 2020-12-02 | P/FVC/MDS/1007213/2020 | 2020-12-11 | ST202108493650 | 2021-08-27 | P/FBW/MDS/1060221/2021 | 2021-09-13 | 0
258 | CBE754 | CBE754 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1385193 | R/NN-430849 | Nominals with issues | Dropped-Canb. | 2020-11-16 | CBE754 | 4G_FD900_CBE754 | 4G_FD2100_CBE754 | 4G_TD_CBE754 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361933 | 2021-06-25 | P/FVC/MDS/1049912/2021 | 2021-08-09 | ST202012161518 | 2020-12-01 | P/FVC/MDS/1006971/2020 | 2020-12-06 |  |  |  |  | ST202012163370 | 2020-12-02 | P/FBW/MDS/1007076/2020 | 2020-12-11 | Partof461sitesSyamaMay'30/ATCsurrenderedonOct29//R/NN-373712SOSurrenderedbyindus1/13/2020/R/NN-392556/SRwithdrwanduetoDAY1TDDandrepunched | CBE754
259 | CDBM50 | CDBM50 | Cuddalore | Trichy |  | ROTN | Indus | IN-1428711 | R/NN-469253 | Nominals with issues | Drop | 2020-11-07 | CDBM50 | 4G_FD900_CDBM50 | 4G_FD2100_CDBM50 | 4G_TD_CDBM50 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361975 | 2021-06-25 | P/FVC/MDS/1049925/2021 | 2021-08-09 | ST202011154508 | 2020-11-23 | P/FVC/MDS/1006755/2020 | 2020-12-06 |  |  |  |  | ST202011155051 | 2020-11-24 | P/FBW/MDS/1006799/2020 | 2020-12-06 | 0 | CDBM50
260 | CNPT11 | CNPT11 | Dindigul | Coimbatore |  | ROTN | Indus | IN-1389280 | R/NN-464133 | Nominals with issues | SO | 2020-11-25 | CNPT11 | 4G_FD900_CNPT11 | 4G_FD2100_CNPT11 | 4G_TD_CNPT11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362085 | 2021-06-25 | P/FVC/MDS/1049930/2021 | 2021-08-09 | ST202012161520 | 2020-12-01 | P/FVC/MDS/1006973/2020 | 2020-12-06 |  |  |  |  | ST202012161909 | 2020-12-01 | P/FBW/MDS/1007050/2020 | 2020-12-11 | 0 | CNPT11
261 | CONR15 | CONR15 | The Nilgiris | Coimbatore |  | ROTN | Indus | IN-1385233 | R/NN-431540 | Nominals with issues |  | 2020-11-23 | CONR15 | 4G_FD900_CONR15 | 4G_FD2100_CONR15 | 4G_TD_CONR15 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362255 | 2021-06-25 | P/FVC/MDS/1049931/2021 | 2021-08-09 | ST202012161404 | 2020-12-01 | P/FVC/MDS/1006929/2020 | 2020-12-06 | ST202012175944 | 2020-12-17 | P/FVC/MDS/1007885/2020 | 2020-12-29 | ST202012163410 | 2020-12-02 | P/FBW/MDS/1007098/2020 | 2020-12-11 | ATCsurrenderedonOct29TH.Re-allottedtoIndus/TVIon30th/R/NN-373659/SRwithdrwanduetoDAY1TDDandrepunched | CONR15
262 | KLTPM3 | KLTPM3 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1466803 | R/NN-497310 | Nominals with issues | On Air | 2020-11-04 | KLTPM3 | 4G_FD900_KLTPM3 | 4G_FD2100_KLTPM3 | 4G_TD_KLTPM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362313 | 2021-06-25 | P/FVC/MDS/1049965/2021 | 2021-08-09 | ST202011154495 | 2020-11-23 | P/FVC/MDS/1006748/2020 | 2020-12-06 |  |  |  |  | ST202011155039 | 2020-11-24 | P/FBW/MDS/1006793/2020 | 2020-12-06 | /R/NN-406351/SRwithdrwanduetoDAY1TDDandrepunched | KLTPM3
263 | PDKT58 | PDKT58 | Pudukkottai | Trichy |  | ROTN | Indus | IN-1448604 | R/NN-470243 | Nominals with issues | Dropped-Canb. | 2020-11-16 | PDKT58 | 4G_FD900_PDKT58 | 4G_FD2100_PDKT58 | 4G_TD_PDKT58 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362724 | 2021-06-26 | P/FVC/MDS/1050014/2021 | 2021-08-09 | ST202012161507 | 2020-12-01 | P/FVC/MDS/1006967/2020 | 2020-12-06 |  |  |  |  | ST202012163364 | 2020-12-02 | P/FBW/MDS/1007074/2020 | 2020-12-11 | 0 | PDKT58
264 | PDY310 | PDY310 | Puducherry | Trichy |  | ROTN | Indus | IN-1512853 | R/NN-558937 | Nominals with issues | SO | 2020-11-25 | PDY310 | 4G_FD900_PDY310 | 4G_FD2100_PDY310 | 4G_TD_PDY310 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362730 | 2021-06-26 | P/FVC/MDS/1050017/2021 | 2021-08-09 | ST202012161437 | 2020-12-01 | P/FVC/MDS/1006952/2020 | 2020-12-06 |  |  |  |  | ST202012163431 | 2020-12-02 | P/FBW/MDS/1007114/2020 | 2020-12-11 | 20-20-RestofUrban/ATCsurrenderedonfeb6thandalocatedtoindusbysyama2/11/2020 | PDY310
265 | PNRT20 | PNRT20 | Cuddalore | Trichy |  | ROTN | Indus | IN-1632467 | R/NN-562202 | Nominals with issues | On Air | 2021-01-15 | PNRT20 | 4G_FD900_PNRT20 | 4G_FD2100_PNRT20 | 4G_TD_PNRT20 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362754 | 2021-06-26 | P/FVC/MDS/1050027/2021 | 2021-08-09 | ST202012161460 | 2020-12-01 | P/FVC/MDS/1006915/2020 | 2020-12-06 |  |  |  |  | ST202012163397 | 2020-12-02 | P/FBW/MDS/1007085/2020 | 2020-12-11 | SO R/NN-469399 Canceled by Indus on Dec 22-23 Location change, Old location 11.781034-79.54158 - 4 Jun'21 | PNRT20
266 | PTPLM4 | PTPLM4 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22232 | T20TN07156 | Nominals with issues | Dropped-Canb. | 2020-11-23 | PTPLM4 | 4G_FD900_PTPLM4 | 4G_FD2100_PTPLM4 | 4G_TD_PTPLM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362761 | 2021-06-26 | P/FVC/MDS/1050032/2021 | 2021-08-09 | ST202012161423 | 2020-12-01 | P/FVC/MDS/1006942/2020 | 2020-12-06 | ST202012163603 | 2020-12-02 | P/FVC/MDS/1007148/2020 | 2020-12-11 | ST202102039300 | 2021-02-04 | P/FBW/MDS/1011410/2021 | 2021-03-05 | 0 | PTPLM4
267 | PULI16 | PULI16 | Chennai | Chennai |  | CHN | Indus | IN-1383845 | R/NN-428121 | Nominals with issues | Drop | 2020-11-07 | PULI16 | 4G_FD900_PULI16 | 4G_FD2100_PULI16 | 4G_TD_PULI16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202011154343 | 2020-11-23 | P/FVC/MDS/1006712/2020 | 2020-12-06 | ST202011154384 | 2020-11-23 | P/FVC/MDS/1006722/2020 | 2020-12-06 | ST202106358273 | 2021-06-23 | P/FVC/MDS/1055867/2021 | 2021-09-04 | ST202011154294 | 2020-11-23 | P/FBW/MDS/1006701/2020 | 2020-12-06 | 0 | PULI16
268 | TLKM13 | TLKM13 | Kancheepuram | Chennai |  | ROTN | Ascend | 0 | - | Nominals with issues | On Air | 2020-11-11 | TLKM13 | 4G_FD900_TLKM13 | 4G_FD2100_TLKM13 | 4G_TD_TLKM13 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362853 | 2021-06-26 | P/FVC/MDS/1050072/2021 | 2021-08-09 | ST202011154454 | 2020-11-23 | P/FVC/MDS/1006729/2020 | 2020-12-06 |  |  |  |  | ST202011154300 | 2020-11-23 | P/FBW/MDS/1006706/2020 | 2020-12-06 | 0 | TLKM13
269 | TPTR26 | TPTR26 | Vellore | Vellore |  | ROTN | Indus | IN-1650227 | R/NN-562780 | Nominals with issues | On Air | 2021-01-19 | TPTR26 | 4G_FD900_TPTR26 | 4G_FD2100_TPTR26 | 4G_TD_TPTR26 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362880 | 2021-06-26 | P/FVC/MDS/1050081/2021 | 2021-08-09 | ST202012161510 | 2020-12-01 | P/FVC/MDS/1006970/2020 | 2020-12-06 | ST202012163591 | 2020-12-02 | P/FVC/MDS/1007136/2020 | 2020-12-11 | ST202102049102 | 2021-02-10 | P/FBW/MDS/1011496/2021 | 2021-03-05 | SO R/NN-464924 Canceled by Indus on Jan 13, 2021 and ID changed and rebooked | TPTR26
270 | TUT126 | TUT126 | Thoothukkudi | Madurai |  | ROTN | ATC | TN/TH/AT/22081 | T20TN05717 | Nominals with issues | SO | 2020-11-12 | TUT126 | 4G_FD900_TUT126 | 4G_FD2100_TUT126 | 4G_TD_TUT126 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363093 | 2021-06-26 | P/FVC/MDS/1050094/2021 | 2021-08-09 | ST202011155002 | 2020-11-24 | P/FVC/MDS/1006778/2020 | 2020-12-06 | ST202212858183 | 2022-12-27 | 0 |  | ST202011155183 | 2020-11-24 | P/FBW/MDS/1006819/2020 | 2020-12-06 | 0 | TUT126
271 | VELLU2 | VELLU2 | Virudhunagar | Madurai |  | ROTN | Indus | IN-1450899 | R/NN-473096 | Nominals with issues | On Air | 2020-11-16 | VELLU2 | 4G_FD900_VELLU2 | 4G_FD2100_VELLU2 | 4G_TD_VELLU2 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106363198 | 2021-06-26 | P/FVC/MDS/1050113/2021 | 2021-08-09 | ST202012161447 | 2020-12-01 | P/FVC/MDS/1006905/2020 | 2020-12-06 | ST202008045761 | 2020-08-17 | P/FVC/MDS/1001938/2020 | 2020-08-22 | ST202204119446 | 2022-04-26 | P/FBW/MDS/1079262/2022 | 2022-05-13 | 0 | VELLU2
272 | VISH12 | VISH12 | Vellore | Vellore |  | ROTN | Indus | IN-1488405 | R/NN-536733 | Nominals with issues | On Air | 2020-11-25 | VISH12 | 4G_FD900_VISH12 | 4G_FD2100_VISH12 | 4G_TD_VISH12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363201 | 2021-06-26 | P/FVC/MDS/1050115/2021 | 2021-08-09 | ST202012161436 | 2020-12-01 | P/FVC/MDS/1006951/2020 | 2020-12-06 |  |  |  |  | ST202012163430 | 2020-12-02 | P/FBW/MDS/1007113/2020 | 2020-12-11 | 0 | VISH12
273 | VLUR10 | VLUR10 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1448600 | R/NN-470224 | Nominals with issues | Dropped | 2020-11-16 | VLUR10 | 4G_FD900_VLUR10 | 4G_FD2100_VLUR10 | 4G_TD_VLUR10 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363214 | 2021-06-26 | P/FVC/MDS/1050120/2021 | 2021-08-09 | ST202012161503 | 2020-12-01 | P/FVC/MDS/1006965/2020 | 2020-12-06 |  |  |  |  | ST202012163362 | 2020-12-02 | P/FBW/MDS/1007072/2020 | 2020-12-11 | 0 | VLUR10
274 | VRCM31 | VRCM31 | Cuddalore | Trichy |  | ROTN | Indus | IN-1565785 | R/NN-560618 | Nominals with issues | Dropped-Canb. | 2020-12-18 | VRCM31 | 4G_FD900_VRCM31 | 4G_FD2100_VRCM31 | 4G_TD_VRCM31 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363244 | 2021-06-26 | P/FVC/MDS/1046136/2021 | 2021-08-03 | ST202011154991 | 2020-11-24 | P/FVC/MDS/1006768/2020 | 2020-12-06 |  |  |  |  | ST202011155174 | 2020-11-24 | P/FBW/MDS/1006810/2020 | 2020-12-06 | SO r/nn-469558 Issued on Nov 11 canceled and issued again | VRCM31
275 | VRPNT2 | VRPNT2 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-1488413 | R/NN-536759 | Nominals with issues | On Air | 2020-11-12 | VRPNT2 | 4G_FD900_VRPNT2 | 4G_FD2100_VRPNT2 | 4G_TD_VRPNT2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202112610880 | 2021-12-10 | P/FVC/MDS/1069081/2021 | 2021-12-17 | ST202011155001 | 2020-11-24 | P/FVC/MDS/1006777/2020 | 2020-12-06 | ST202102042710 | 2021-02-02 | P/FVC/MDS/1011212/2021 | 2021-03-01 | ST202011155182 | 2020-11-24 | P/FBW/MDS/1006818/2020 | 2020-12-06 | 0 | VRPNT2
276 | NJKTI3 | NJKTI3 | Thanjavur | Trichy |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2020-02-10 | NJKTI3 | 4G_FD900_NJKTI3 | 4G_FD2100_NJKTI3 | 4G_TD_NJKTI3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364124 | 2021-06-28 | P/FVC/MDS/1050150/2021 | 2021-08-09 | ST202011154489 | 2020-11-23 | P/FVC/MDS/1006744/2020 | 2020-12-06 |  |  |  |  | ST202011155029 | 2020-11-24 | P/FBW/MDS/1006789/2020 | 2020-12-06 | SOSurrenderedbyATCconfirmedbysyama10/4/2019.SOsurrenderedagainTN/TA/AT/21845 | NJKTI3
277 | TNV44 | TNV044 | Tirunelveli | Madurai |  | ROTN | ATC |  |  | Nominal WIP | SO | 2020-11-25 | TNV044 | 4G_FD900_TNV044 | 4G_FD2100_TNV044 | 4G_TD_TNV044 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366847 | 2021-06-30 | P/FVC/MDS/1050194/2021 | 2021-08-09 | ST202012161431 | 2020-12-01 | P/FVC/MDS/1006946/2020 | 2020-12-06 |  |  |  |  | ST202012163424 | 2020-12-02 | P/FBW/MDS/1007109/2020 | 2020-12-11 | 0 | TNV44
278 | SMGI6 | SMGI06 | Coimbatore | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | SO | 2020-11-25 | SMGI06 | 4G_FD900_SMGI06 | 4G_FD2100_SMGI06 | 4G_TD_SMGI06 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366851 | 2021-06-30 | P/FVC/MDS/1050197/2021 | 2021-08-09 | ST202012161432 | 2020-12-01 | P/FVC/MDS/1006947/2020 | 2020-12-06 |  |  |  |  | ST202012163427 | 2020-12-02 | P/FBW/MDS/1007110/2020 | 2020-12-11 | 0 | SMGI6
279 | VRCM29 | VRCM29 |  |  |  | ROTN | Indus | R/NN-467034 |  |  |  | 2020-11-04 | VRCM29 | 4G_FD900_VRCM29 | 4G_FD2100_VRCM29 | 4G_TD_VRCM29 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498649 | 2021-08-31 | P/FVC/MDS/1060440/2021 | 2021-09-13 | ST202011155011 | 2020-11-24 | P/FVC/MDS/1006782/2020 | 2020-12-06 | ST202011155391 | 2020-11-24 | P/FVC/MDS/1006859/2020 | 2020-12-06 | ST202011155186 | 2020-11-24 | P/FBW/MDS/1006822/2020 | 2020-12-06 |  | VRCM29
280 | CBE824 | CBE824 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22168 | T20TN05989 | Nominals with issues | Dropped-Canb. | 2020-10-12 | CBE824 | 4G_FD900_CBE824 | 4G_FD2100_CBE824 | 4G_TD_CBE824 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361956 | 2021-06-25 | P/FVC/MDS/1049918/2021 | 2021-08-09 | ST202011134950 | 2020-11-04 | P/FVC/MDS/1006374/2020 | 2020-11-28 |  |  |  |  | ST202011140422 | 2020-11-08 | P/FBW/MDS/1006152/2020 | 2020-11-18 | 0 | CBE824
281 | ERD202 | ERD202 | Erode | Coimbatore |  | ROTN | Indus | IN-1407507 | R/NN-467518 | Nominals with issues | On Air | 2020-10-12 | ERD202 | 4G_FD900_ERD202 | 4G_FD2100_ERD202 | 4G_TD_ERD202 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202108497376 | 2021-08-30 | P/FVC/MDS/1060349/2021 | 2021-09-13 | ST202011134978 | 2020-11-04 | P/FVC/MDS/1006385/2020 | 2020-11-28 | ST202108493804 | 2021-08-27 | P/FVC/MDS/1060255/2021 | 2021-09-13 | ST202011140430 | 2020-11-08 | P/FBW/MDS/1006160/2020 | 2020-11-18 | 0 | ERD202
282 | KLPVR4 | KLPVR4 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1408181 | R/NN-467536 | Nominals with issues | On Air | 2020-10-13 | KLPVR4 | 4G_FD900_KLPVR4 | 4G_FD2100_KLPVR4 | 4G_TD_KLPVR4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362311 | 2021-06-25 | P/FVC/MDS/1049963/2021 | 2021-08-09 | ST202011134925 | 2020-11-04 | P/FVC/MDS/1006364/2020 | 2020-11-28 |  |  |  |  | ST202011140415 | 2020-11-08 | P/FBW/MDS/1006145/2020 | 2020-11-18 | 0 | KLPVR4
283 | KRR71 | KRR071 | Karur | Coimbatore |  | ROTN | Indus | IN-1460953 | R/NN-488369 | Nominals with issues | SO | 2020-10-29 | KRR071 | 4G_FD900_KRR071 | 4G_FD2100_KRR071 | 4G_TD_KRR071 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362333 | 2021-06-25 | P/FVC/MDS/1049975/2021 | 2021-08-09 | ST202011152122 | 2020-11-20 | P/FVC/MDS/1006508/2020 | 2020-11-28 | ST202211758108 | 2022-11-22 | P/FVC/MDS/1116782/2022 | 2022-11-29 | ST202011152429 | 2020-11-21 | P/FBW/MDS/1006542/2020 | 2020-11-28 | Partof461sitesSyamaMay'30/SOcanceledbyindus10/19/2020 | KRR71
284 | SNDI6 | SNDI06 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1398042 | R/NN-466970 | Nominals with issues | Dropped-Canb. | 2020-10-14 | SNDI06 | 4G_FD900_SNDI06 | 4G_FD2100_SNDI06 | 4G_TD_SNDI06 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202112610917 | 2021-12-10 | P/FVC/MDS/1069092/2021 | 2021-12-17 | ST202011134965 | 2020-11-04 | P/FVC/MDS/1006380/2020 | 2020-11-28 |  |  |  |  | ST202011140426 | 2020-11-08 | P/FBW/MDS/1006156/2020 | 2020-11-18 | 0 | SNDI6
285 | TRY349 | TRY349 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-1428136 | R/NN-469012 | Nominals with issues | Dropped-Canb. | 2020-10-29 | TRY349 | 4G_FD900_TRY349 | 4G_FD2100_TRY349 | 4G_TD_TRY349 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363078 | 2021-06-26 | P/FVC/MDS/1050088/2021 | 2021-08-09 | ST202011152119 | 2020-11-20 | P/FVC/MDS/1006505/2020 | 2020-11-28 |  |  |  |  | ST202011152428 | 2020-11-21 | P/FBW/MDS/1006541/2020 | 2020-11-28 | 0 | TRY349
286 | VLRM58 | VLRM58 | Viluppuram | Trichy |  | ROTN | Indus | IN-1398057 | R/NN-466967 | Nominals with issues | SR | 2020-10-14 | VLRM58 | 4G_FD900_VLRM58 | 4G_FD2100_VLRM58 | 4G_TD_VLRM58 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363211 | 2021-06-26 | P/FVC/MDS/1050119/2021 | 2021-08-09 | ST202011135017 | 2020-11-04 | P/FVC/MDS/1006386/2020 | 2020-11-28 |  |  |  |  | ST202011140431 | 2020-11-08 | P/FBW/MDS/1006161/2020 | 2020-11-18 | 0 | VLRM58
287 | PVCRM3 | PVCRM3 | Tirunelveli | Madurai |  | ROTN | ATC |  |  | Nominal WIP | SO |  | PVCRM3 | 4G_FD900_PVCRM3 | 4G_FD2100_PVCRM3 | 4G_TD_PVCRM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202108430714 | 2021-08-17 | P/FVC/MDS/1059666/2021 | 2021-09-12 | ST202011135046 | 2020-11-04 | P/FVC/MDS/1006393/2020 | 2020-11-28 |  |  |  |  | ST202011140443 | 2020-11-08 | P/FBW/MDS/1006168/2020 | 2020-11-18 | 0 | PVCRM3
288 | TIR406 | TIR406 | Tiruppur | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | SR | 2020-10-15 | TIR406 | 4G_FD900_TIR406 | 4G_FD2100_TIR406 | 4G_TD_TIR406 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366793 | 2021-06-30 | P/FVC/MDS/1050169/2021 | 2021-08-09 | ST202011135048 | 2020-11-04 | P/FVC/MDS/1006395/2020 | 2020-11-28 |  |  |  |  | ST202011140445 | 2020-11-08 | P/FBW/MDS/1006170/2020 | 2020-11-18 | 0 | TIR406
289 | ERD203 | ERD203 | Erode | Coimbatore |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2020-10-12 | ERD203 | 4G_FD900_ERD203 | 4G_FD2100_ERD203 | 4G_TD_ERD203 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366802 | 2021-06-30 | P/FVC/MDS/1050172/2021 | 2021-08-09 | ST202011134930 | 2020-11-04 | P/FVC/MDS/1006369/2020 | 2020-11-28 |  |  |  |  | ST202011140419 | 2020-11-08 | P/FBW/MDS/1006149/2020 | 2020-11-18 | ATC Canceled SO Hold on Jan 13, 2021 (Mail shared by Arvind on Feb 3, 2021) | ERD203
290 | VLR214 | VLR214 | Vellore | Vellore |  | ROTN | Airtel |  |  | Nominal WIP | Dropped-Canb. |  | VLR214 | 4G_FD900_VLR214 | 4G_FD2100_VLR214 | 4G_TD_VLR214 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106366917 | 2021-06-30 | P/FVC/MDS/1050217/2021 | 2021-08-09 | ST202011152133 | 2020-11-20 | P/FVC/MDS/1006519/2020 | 2020-11-28 |  |  |  |  | ST202011152448 | 2020-11-21 | P/FBW/MDS/1006561/2020 | 2020-11-28 | 0
291 | DGL82 | DGL082 | Dindigul | Coimbatore |  | ROTN | Summit |  |  | Nominal WIP |  | 2020-10-24 | DGL082 | 4G_FD900_DGL082 | 4G_FD2100_DGL082 | 4G_TD_DGL082 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364348 | 2021-06-28 | P/FVC/MDS/1046140/2021 | 2021-08-03 | ST202011140385 | 2020-11-08 | P/FVC/MDS/1006125/2020 | 2020-11-18 |  |  |  |  | ST202011140495 | 2020-11-08 | P/FBW/MDS/1006207/2020 | 2020-11-18 | ATC Canceled SO Hold on Jan 13, 2021 (Mail shared by Arvind on Feb 3, 2021) | DGL82
292 | PMTPM2 | PMTPM2 | Erode | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-10-24 | PMTPM2 | 4G_FD900_PMTPM2 | 4G_FD2100_PMTPM2 | 4G_TD_PMTPM2 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106366792 | 2021-06-30 | P/FVC/MDS/1046138/2021 | 2021-08-03 | ST202011140388 | 2020-11-08 | P/FVC/MDS/1006128/2020 | 2020-11-18 | ST202011140379 | 2020-11-08 | P/FVC/MDS/1006119/2020 | 2020-11-18 |  |  |  |  | 0 | PMTPM2
293 | KOZHIK | KOZHIK | Madurai | Madurai |  | ROTN | Summit |  |  | Nominal WIP | Dropped-Canb. | 2020-10-15 | KOZHIK | 4G_FD900_KOZHIK | 4G_FD2100_KOZHIK | 4G_TD_KOZHIK | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106366801 | 2021-06-30 | P/FVC/MDS/1050171/2021 | 2021-08-09 | ST202011135673 | 2020-11-05 | P/FVC/MDS/1006064/2020 | 2020-11-18 | ST202011138122 | 2020-11-06 | P/FVC/MDS/1006033/2020 | 2020-11-18 |  |  |  |  | ATC Canceled SO Hold on Jan 13, 2021 (Mail shared by Arvind on Feb 3, 2021) | KOZHIK
294 | ANNA29 | ANNA29 | Chennai | Chennai |  | CHN | indus | R/NN-419120 | 0 | Nominal WIP |  | 2020-10-06 | ANNA29 | 4G_FD900_ANNA29 | 4G_FD2100_ANNA29 | 4G_TD_ANNA29 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202010104158 | 2020-10-12 | P/FVC/MDS/1005201/2020 | 2020-10-18 | ST202010104344 | 2020-10-12 | P/FVC/MDS/1005830/2020 | 2020-11-09 | ST202010109690 | 2020-10-15 | P/FVC/MDS/1005362/2020 | 2020-10-31 | ST202010104479 | 2020-10-12 | P/FBW/MDS/1005276/2020 | 2020-10-27 |  | ANNA29
295 | AMAPT3 | AMAPT3 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/22092 | T20TN05728 | Nominals with issues | On Air | 2020-09-28 | AMAPT3 | 4G_FD900_AMAPT3 | 4G_FD2100_AMAPT3 | 4G_TD_AMAPT3 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202108497362 | 2021-08-30 | P/FVC/MDS/1060339/2021 | 2021-09-13 | ST202010117693 | 2020-10-21 | P/FVC/MDS/1005563/2020 | 2020-11-08 | ST202010119074 | 2020-10-23 | P/FVC/MDS/1005666/2020 | 2020-11-09 | ST202108493619 | 2021-08-27 | P/FBW/MDS/1060198/2021 | 2021-09-13 | ATCSOSurrenderedonNov18thduetoLLBackout.NewOptionSOreleased | AMAPT3
296 | ARGI12 | ARGI12 | Pudukkottai | Trichy |  | ROTN | ATC | TN/PU/AT/22105 | T20TN05907 | Nominals with issues | On Air | 2020-10-06 | ARGI12 | 4G_FD900_ARGI12 | 4G_FD2100_ARGI12 | 4G_TD_ARGI12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361835 | 2021-06-25 | P/FVC/MDS/1049898/2021 | 2021-08-09 | ST202010117561 | 2020-10-21 | P/FVC/MDS/1005528/2020 | 2020-11-08 |  |  |  |  | ST202010118946 | 2020-10-22 | P/FBW/MDS/1005600/2020 | 2020-11-09 | SOCanceledbyATConOct15,2020 | ARGI12
297 | MDU431 | MDU431 | Madurai | Madurai |  | ROTN | Indus | IN-1387817 | R/NN-463872 | Nominals with issues | On Air | 2020-10-03 | MDU431 | 4G_FD900_MDU431 | 4G_FD2100_MDU431 | 4G_TD_MDU431 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362376 | 2021-06-25 | P/FVC/MDS/1049986/2021 | 2021-08-09 | ST202010117557 | 2020-10-21 | P/FVC/MDS/1005527/2020 | 2020-11-08 |  |  |  |  | ST202010118916 | 2020-10-22 | P/FBW/MDS/1005591/2020 | 2020-11-09 | 0 | MDU431
298 | TUT119 | TUT119 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-1409856 | R/NN-467555 | Nominals with issues | Dropped-Canb. | 2020-09-30 | TUT119 | 4G_FD900_TUT119 | 4G_FD2100_TUT119 | 4G_TD_TUT119 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363092 | 2021-06-26 | P/FVC/MDS/1050093/2021 | 2021-08-09 | ST202010117713 | 2020-10-21 | P/FVC/MDS/1005565/2020 | 2020-11-08 |  |  |  |  | ST202010118875 | 2020-10-22 | P/FBW/MDS/1005586/2020 | 2020-11-09 | 0 | TUT119
299 | NRPCL4 | NRPCL4 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1385394 | R/NN-442737 | Nominals with issues | Dropped-Canb. | 2020-09-21 | NRPCL4 | 4G_FD900_NRPCL4 | 4G_FD2100_NRPCL4 | 4G_TD_NRPCL4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362652 | 2021-06-26 | P/FVC/MDS/1050009/2021 | 2021-08-09 | ST202010104187 | 2020-10-12 | P/FVC/MDS/1005219/2020 | 2020-10-19 |  |  |  |  | ST202010104420 | 2020-10-12 | P/FBW/MDS/1005249/2020 | 2020-10-27 | 20-20-RestofUrban/R/NN-385059/SRwithdrwanduetoDAY1TDDandrepunched | NRPCL4
300 | CBE808 | CBE808 | Coimbatore | Coimbatore |  | ROTN | Ascend | ENQTN/000224/2021 | - | Nominals with issues | SO | 2020-10-05 | CBE808 | 4G_FD900_CBE808 | 4G_FD2100_CBE808 | 4G_TD_CBE808 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361950 | 2021-06-25 | P/FVC/MDS/1049915/2021 | 2021-08-09 | ST202010100429 | 2020-10-07 | P/FVC/MDS/1005063/2020 | 2020-10-18 |  |  |  |  | ST202010100457 | 2020-10-07 | P/FBW/MDS/1005069/2020 | 2020-10-18 | 0 | CBE808
301 | CBE811 | CBE811 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1387543 | R/NN-462098 | Nominals with issues | Dropped-Canb. | 2020-09-15 | CBE811 | 4G_FD900_CBE811 | 4G_FD2100_CBE811 | 4G_TD_CBE811 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361955 | 2021-06-25 | P/FVC/MDS/1049917/2021 | 2021-08-09 | ST202010101053 | 2020-10-08 | P/FVC/MDS/1005100/2020 | 2020-10-18 |  |  |  |  | ST202010100220 | 2020-10-07 | P/FBW/MDS/1005023/2020 | 2020-10-18 | 0 | CBE811
302 | CDLR68 | CDLR68 | Cuddalore | Trichy |  | ROTN | Indus | IN-1385515 | R/NN-440332 | Nominals with issues | Dropped-Canb. | 2020-09-12 | CDLR68 | 4G_FD900_CDLR68 | 4G_FD2100_CDLR68 | 4G_TD_CDLR68 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362049 | 2021-06-25 | P/FVC/MDS/1046128/2021 | 2021-08-03 | ST202010101046 | 2020-10-08 | P/FVC/MDS/1005093/2020 | 2020-10-18 |  |  |  |  | ST202010100214 | 2020-10-07 | P/FBW/MDS/1005017/2020 | 2020-10-18 | 20-20-TopTowns0.8Validation/ATCsurrenderedonfeb6thandalocatedtoindusbysyama2/11/2020/R/NN-395880/SRwithdrwanduetoDAY1TDDandrepunched | CDLR68
303 | KTLI7 | KTLI07 | Karur | Coimbatore |  | ROTN | Indus | IN-1385412 | R/NN-442875 | Nominals with issues | Dropped-Canb. | 2020-09-18 | KTLI07 | 4G_FD900_KTLI07 | 4G_FD2100_KTLI07 | 4G_TD_KTLI07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362341 | 2021-06-25 | P/FVC/MDS/1049976/2021 | 2021-08-09 | ST202010101142 | 2020-10-08 | P/FVC/MDS/1005130/2020 | 2020-10-18 |  |  |  |  | ST202010100274 | 2020-10-07 | P/FBW/MDS/1005037/2020 | 2020-10-18 | 20-20-RestofUrban/R/NN-391621/SRwithdrwanduetoDAY1TDDandrepunched | KTLI7
304 | PDKT33 | PDKT33 | Pudukkottai | Trichy |  | ROTN | Indus | IN-1385207 | R/NN-430920 | Nominals with issues | On Air | 2020-09-15 | PDKT33 | 4G_FD900_PDKT33 | 4G_FD2100_PDKT33 | 4G_TD_PDKT33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362657 | 2021-06-26 | P/FVC/MDS/1050012/2021 | 2021-08-09 | ST202010101050 | 2020-10-08 | P/FVC/MDS/1005097/2020 | 2020-10-18 |  |  |  |  | ST202010100218 | 2020-10-07 | P/FBW/MDS/1005021/2020 | 2020-10-18 | R/NN-320160SOWithdrwanandrebokedbasisonjawhar8/2/2019/R/NN-357351SPRejectedduetooptionnotok/SOWithdrwanbyscmOct'5/R/NN-375211SOSurrenderedbyindus1/13/2020/R/NN-392179/SRwithdrwanduetoDAY1TDDandrepunched | PDKT33
305 | TKSI15 | TKSI15 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1393247 | R/NN-466097 | Nominals with issues |  | 2020-09-15 | TKSI15 | 4G_FD900_TKSI15 | 4G_FD2100_TKSI15 | 4G_TD_TKSI15 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362816 | 2021-06-26 | P/FVC/MDS/1050071/2021 | 2021-08-09 | ST202010101049 | 2020-10-08 | P/FVC/MDS/1005096/2020 | 2020-10-18 |  |  |  |  | ST202010100217 | 2020-10-07 | P/FBW/MDS/1005020/2020 | 2020-10-18 | Partof461sitesSyamaMay'30/R/NN-346047/SRwithdrwanduetoDAY1TDDandrepunched/TocochangedfromindustoAscend8/4/2020 | TKSI15
306 | KARA30 | KARA30 | Chennai | Chennai |  | CHN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-09-17 | KARA30 | 4G_FD900_KARA30 | 4G_FD2100_KARA30 | 4G_TD_KARA30 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202010100036 | 2020-10-06 | P/FVC/MDS/1004997/2020 | 2020-10-17 | ST202010101155 | 2020-10-08 | P/FVC/MDS/1005140/2020 | 2020-10-18 | ST202106358373 | 2021-06-23 | P/FVC/MDS/1055890/2021 | 2021-09-04 | ST202010100058 | 2020-10-07 | P/FBW/MDS/1005007/2020 | 2020-10-17 | R/NN-464452 Indus SP Rejected | KARA30
307 | TSVL9 | TSVL09 | Tirunelveli | Madurai |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-10-24 | TSVL09 | 4G_FD900_TSVL09 | 4G_FD2100_TSVL09 | 4G_TD_TSVL09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364469 | 2021-06-28 | P/FVC/MDS/1050286/2021 | 2021-08-09 | ST202010101141 | 2020-10-08 | P/FVC/MDS/1005129/2020 | 2020-10-18 |  |  |  |  | ST202010100273 | 2020-10-07 | P/FBW/MDS/1005036/2020 | 2020-10-18 | 0 | TSVL9
308 | TIVR33 | TIVR33 | Thiruvarur | Trichy |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-09-17 | TIVR33 | 4G_FD900_TIVR33 | 4G_FD2100_TIVR33 | 4G_TD_TIVR33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364472 | 2021-06-28 | P/FVC/MDS/1050289/2021 | 2021-08-09 | ST202010101134 | 2020-10-08 | P/FVC/MDS/1005122/2020 | 2020-10-18 |  |  |  |  | ST202010100253 | 2020-10-07 | P/FBW/MDS/1005032/2020 | 2020-10-18 | 0 | TIVR33
309 | CBE810 | CBE810 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1387544 | R/NN-462097 | Nominals with issues |  | 2020-08-31 | CBE810 | 4G_FD900_CBE810 | 4G_FD2100_CBE810 | 4G_TD_CBE810 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361951 | 2021-06-25 | P/FVC/MDS/1049916/2021 | 2021-08-09 | ST202009093033 | 2020-09-29 | P/FVC/MDS/1004665/2020 | 2020-10-12 |  |  |  |  | ST202010098561 | 2020-10-06 | P/FBW/MDS/1004885/2020 | 2020-10-17 | 0 | CBE810
310 | KNGM12 | KNGM12 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1385395 | R/NN-442741 | Nominals with issues | Dropped-Canb. | 2020-09-08 | KNGM12 | 4G_FD900_KNGM12 | 4G_FD2100_KNGM12 | 4G_TD_KNGM12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362323 | 2021-06-25 | P/FVC/MDS/1049969/2021 | 2021-08-09 | ST202009093201 | 2020-09-29 | P/FVC/MDS/1004715/2020 | 2020-10-12 |  |  |  |  | ST202010098648 | 2020-10-06 | P/FBW/MDS/1004909/2020 | 2020-10-17 | 20-20-RestofUrban/R/NN-391624/SRwithdrwanduetoDAY1TDDandrepunched | KNGM12
311 | KPUYM1 | KPUYM1 | Namakkal | Coimbatore |  | ROTN | Indus | IN-1386342 | R/NN-456720 | Nominals with issues | SR | 2020-09-01 | KPUYM1 | 4G_FD900_KPUYM1 | 4G_FD2100_KPUYM1 | 4G_TD_KPUYM1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014681 | 2022-01-20 | P/FVC/MDS/1072390/2022 | 2022-01-31 | ST202201014752 | 2022-01-20 | P/FVC/MDS/1072361/2022 | 2022-01-31 |  |  |  |  | ST202201014801 | 2022-01-20 | P/FBW/MDS/1072332/2022 | 2022-01-31 | Tocochangedtoindus6/22/2020 | KPUYM1
312 | MGDI19 | MGDI19 | Thiruvarur | Trichy |  | ROTN | Indus | IN-1385524 | R/NN-446936 | Nominals with issues | Dropped-Canb. | 2020-09-08 | MGDI19 | 4G_FD900_MGDI19 | 4G_FD2100_MGDI19 | 4G_TD_MGDI19 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362388 | 2021-06-25 | P/FVC/MDS/1049991/2021 | 2021-08-09 | ST202009093202 | 2020-09-29 | P/FVC/MDS/1004716/2020 | 2020-10-12 |  |  |  |  | ST202010098649 | 2020-10-06 | P/FBW/MDS/1004910/2020 | 2020-10-17 | 20-20-TopTowns0.8Validation/R/NN-385750/SRwithdrwanduetoDAY1TDDandrepunched | MGDI19
313 | SLM253 | SLM253 | Salem | Vellore |  | ROTN | Airtel | SLM253 | - | Nominals with issues | SO | 2019-05-31 | SLM253 | 4G_FD900_SLM253 | 4G_FD2100_SLM253 | 4G_TD_SLM253 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362773 | 2021-06-26 | P/FVC/MDS/1050039/2021 | 2021-08-09 | ST202009092980 | 2020-09-29 | P/FVC/MDS/1004655/2020 | 2020-10-12 |  |  |  |  | ST202010098866 | 2020-10-06 | P/FBW/MDS/1004981/2020 | 2020-10-17 | TocochangedFromBSNLToATCBycharan10/4/2018/tocochangedtoownbasisionsentamil3/13/2019/SOCanceledbyownconfirmedbysentamilnov28th | SLM253
314 | SLM323 | SLM323 | Salem | Vellore |  | ROTN | Indus | IN-1389250 | R/NN-464411 | Nominals with issues | Dropped-Canb. | 2020-09-07 | SLM323 | 4G_FD900_SLM323 | 4G_FD2100_SLM323 | 4G_TD_SLM323 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362775 | 2021-06-26 | P/FVC/MDS/1050041/2021 | 2021-08-09 | ST202009093181 | 2020-09-29 | P/FVC/MDS/1004710/2020 | 2020-10-12 |  |  |  |  | ST202010098604 | 2020-10-06 | P/FBW/MDS/1004895/2020 | 2020-10-17 | Partof461sitesSyamaMay'30/ATCsurrenderedSOsonSep20/R/NN-370180SPRejectedduetonoRFNov'29th/R/NN-382687/SRwithdrwanduetoDAY1TDDandrepunched/SRwithdrwanandshifted7/24/2020 | SLM323
315 | SLM355 | SLM355 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22038 | T20TN04038 | Nominals with issues | Dropped-Canb. | 2020-08-26 | SLM355 | 4G_FD900_SLM355 | 4G_FD2100_SLM355 | 4G_TD_SLM355 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362781 | 2021-06-26 | P/FVC/MDS/1050043/2021 | 2021-08-09 | ST202009093069 | 2020-09-29 | P/FVC/MDS/1004671/2020 | 2020-10-12 |  |  |  |  | ST202010098870 | 2020-10-06 | P/FBW/MDS/1004985/2020 | 2020-10-17 | 0 | SLM355
316 | MRKT6 | MRKT06 |  |  |  | ROTN | Indus | R/NN-464556 |  |  |  | 2020-08-26 | MRKT06 | 4G_FD900_MRKT06 | 4G_FD2100_MRKT06 | 4G_TD_MRKT06 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498648 | 2021-08-31 | P/FVC/MDS/1060439/2021 | 2021-09-13 | ST202009093237 | 2020-09-29 | P/FVC/MDS/1004722/2020 | 2020-10-12 | ST202010098262 | 2020-10-05 | P/FVC/MDS/1004857/2020 | 2020-10-17 | ST202010098725 | 2020-10-06 | P/FBW/MDS/1004941/2020 | 2020-10-17 |  | MRKT6
317 | SNDI5 | SNDI05 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1386799 | R/NN-440828 | Nominals with issues | SO | 2020-08-10 | SNDI05 | 4G_FD900_SNDI05 | 4G_FD2100_SNDI05 | 4G_TD_SNDI05 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362789 | 2021-06-26 | P/FVC/MDS/1050049/2021 | 2021-08-09 | ST202009067413 | 2020-09-14 | P/FVC/MDS/1003007/2020 | 2020-09-19 |  |  |  |  | ST202009067548 | 2020-09-14 | P/FBW/MDS/1003074/2020 | 2020-09-19 | 20-20-RestofUrban/R/NN-391255/SRwithdrwanduetoDAY1TDDandrepunched | SNDI5
318 | VELC18 | VELC18 | Chennai | Chennai |  | CHN | Indus | IN-1387986 | R/NN-464335 | Nominals with issues | Dropped-Canb. | 2020-08-14 | VELC18 | 4G_FD900_VELC18 | 4G_FD2100_VELC18 | 4G_TD_VELC18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202009067383 | 2020-09-14 | P/FVC/MDS/1003133/2020 | 2020-09-19 | ST202009067444 | 2020-09-14 | P/FVC/MDS/1003030/2020 | 2020-09-19 | ST202106358306 | 2021-06-23 | P/FVC/MDS/1055879/2021 | 2021-09-04 | ST202009067574 | 2020-09-14 | P/FBW/MDS/1003095/2020 | 2020-09-19 | Surrendered by Own on July 7, 2020 and changed to Ascend | VELC18
319 | VLRM54 | VLRM54 | Viluppuram | Trichy |  | ROTN | Indus | IN-1388224 | R/NN-464554 | Nominals with issues | On Air | 2020-08-13 | VLRM54 | 4G_FD900_VLRM54 | 4G_FD2100_VLRM54 | 4G_TD_VLRM54 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363210 | 2021-06-26 | P/FVC/MDS/1050118/2021 | 2021-08-09 | ST202009067449 | 2020-09-14 | P/FVC/MDS/1003034/2020 | 2020-09-19 |  |  |  |  | ST202009067575 | 2020-09-14 | P/FBW/MDS/1003096/2020 | 2020-09-19 | ATCcanceledSOonAug6andchangedtoIndus | VLRM54
320 | MDU433 | MDU433 | Madurai | Madurai |  | ROTN | Indus | IN-1387818 | R/NN-463906 | Nominals with issues |  | 2020-08-13 | MDU433 | 4G_FD900_MDU433 | 4G_FD2100_MDU433 | 4G_TD_MDU433 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362377 | 2021-06-25 | P/FVC/MDS/1049987/2021 | 2021-08-09 | ST202009061558 | 2020-09-07 | P/FVC/MDS/1002846/2020 | 2020-09-15 |  |  |  |  | ST202009061454 | 2020-09-06 | P/FBW/MDS/1002801/2020 | 2020-09-15 | 0 | MDU433
321 | VYASA7 | VYASA7 | Chennai | Chennai |  | CHN | Indus |  |  | Nominal WIP | RFAI | 2019-09-11 | VYASA7 | 4G_FD900_VYASA7 | 4G_FD2100_VYASA7 | 4G_TD_VYASA7 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202007023045 | 2020-07-09 | P/FVC/MDS/1000588/2020 | 2020-07-18 | ST202009061544 | 2020-09-07 | P/FVC/MDS/1002832/2020 | 2020-09-15 | ST202106358360 | 2021-06-23 | P/FVC/MDS/1055888/2021 | 2021-09-04 | ST202007023056 | 2020-07-13 | P/FBW/MDS/1000634/2020 | 2020-07-18 | TDD added after Syama confirmation | VYASA7
322 | POLR7 | POLR07 | Tiruvannamalai | Vellore |  | ROTN | Indus |  |  | Nominal WIP | Dropped-L900 | 2020-08-13 | POLR07 | 4G_FD900_POLR07 | 4G_FD2100_POLR07 | 4G_TD_POLR07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364411 | 2021-06-28 | P/FVC/MDS/1050281/2021 | 2021-08-09 | ST202009061580 | 2020-09-07 | P/FVC/MDS/1002865/2020 | 2020-09-15 |  |  |  |  | ST202009061502 | 2020-09-06 | P/FBW/MDS/1002818/2020 | 2020-09-15 | 20-20-RestofUrban/ATCsurrenderedonfeb6thandalocatedtoindusbysyama2/11/2020/R/NN-395904/SRwithdrwanduetoDAY1TDDandrepunched | POLR7
323 | PKT177 | PKT177 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1030572 | R/RES-423638 | Nominals with issues | Dropped-Canb. | 2020-02-24 | PKT177 | 4G_FD900_PKT177 | 4G_FD2100_PKT177 | 4G_TD_PKT177 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362733 | 2021-06-26 | P/FVC/MDS/1050019/2021 | 2021-08-09 | ST202009059807 | 2020-09-04 | P/FVC/MDS/1002755/2020 | 2020-09-14 |  |  |  |  | ST202009059261 | 2020-09-03 | P/FBW/MDS/1002685/2020 | 2020-09-14 | 0 | PKT177
324 | KPAD13 | KPAD13 | Chennai | Chennai |  | CHN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-08-22 | KPAD13 | 4G_FD900_KPAD13 | 4G_FD2100_KPAD13 | 4G_TD_KPAD13 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202009059079 | 2020-09-03 | P/FVC/MDS/1002648/2020 | 2020-09-14 | ST202009059690 | 2020-09-04 | P/FVC/MDS/1002741/2020 | 2020-09-14 | ST202107369635 | 2021-07-01 | P/FVC/MDS/1055143/2021 | 2021-09-03 | ST202009059233 | 2020-09-03 | P/FBW/MDS/1002679/2020 | 2020-09-14 | 0 | KPAD13
325 | MDTI30 | MDTI30 | Nagapattinam | Trichy |  | ROTN | Indus |  |  | Nominal WIP | Dropped-L900 | 2019-06-18 | MDTI30 | 4G_FD900_MDTI30 | 4G_FD2100_MDTI30 | 4G_TD_MDTI30 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364161 | 2021-06-28 | P/FVC/MDS/1050165/2021 | 2021-08-09 | ST202009059659 | 2020-09-04 | P/FVC/MDS/1002713/2020 | 2020-09-14 |  |  |  |  | ST202007023166 | 2020-07-13 | P/FBW/MDS/1000624/2020 | 2020-07-18 | Partof461sitesSyamaMay'30 | MDTI30
326 | PNRT14 | PNRT14 | Cuddalore | Trichy |  | ROTN | Indus | IN-1385235 | R/NN-431498 | Nominals with issues | SR | 2020-08-04 | PNRT14 | 4G_FD900_PNRT14 | 4G_FD2100_PNRT14 | 4G_TD_PNRT14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202201000640 | 2022-01-03 | P/FVC/MDS/1071067/2022 | 2022-01-10 | ST202201000666 | 2022-01-06 | P/FVC/MDS/1071060/2022 | 2022-01-10 |  |  |  |  | ST202201000696 | 2022-01-03 | P/FBW/MDS/1071076/2022 | 2022-01-10 | LiteplusSRwithdrawnR/NN-337821andpunchedasTransitionalR/NN-337821SOSurrenderedbyjawharconfirmedbysyama9/6/2019/Earliercheck,nowP0/P1/R/NN-392165/SRwithdrwanduetoDAY1TDDandrepunched | PNRT14
327 | ANAUNI | ANAUNI | Chennai | Chennai |  | CHN | BSNL |  |  | Nominal WIP | Dropped-Canb. | 2020-07-30 | ANAUNI | 4G_FD900_ANAUNI | 4G_FD2100_ANAUNI | 4G_TD_ANAUNI | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202008045532 | 2020-08-17 | P/FVC/MDS/1001842/2020 | 2020-08-22 | ST202008045594 | 2020-08-17 | P/FVC/MDS/1001867/2020 | 2020-08-22 | ST202106358313 | 2021-06-23 | P/FVC/MDS/1055881/2021 | 2021-09-04 | ST202008046024 | 2020-08-17 | P/FBW/MDS/1002004/2020 | 2020-08-24 | TDD added after Syama confirmation
328 | PDY311 | PDY311 | Puducherry | Trichy |  | ROTN | ATC |  |  | Nominal WIP | On Air |  | PDY311 | 4G_FD900_PDY311 | 4G_FD2100_PDY311 | 4G_TD_PDY311 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364410 | 2021-06-28 | P/FVC/MDS/1050280/2021 | 2021-08-09 | ST202008040363 | 2020-08-09 | P/FVC/MDS/1001558/2020 | 2020-08-14 | ST202207228632 | 2022-07-07 | P/FVC/MDS/1087979/2022 | 2022-07-18 | ST202008040405 | 2020-08-09 | P/FBW/MDS/1001591/2020 | 2020-08-14 | Indus SO R/NN-439883 terminated by Indus and realloted to ATC on Feb 13, 2021 | PDY311
329 | KGRI39 | KGRI39 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/21937 | T20TN02590 | Nominals with issues | Dropped-Canb. | 2020-07-16 | KGRI39 | 4G_FD900_KGRI39 | 4G_FD2100_KGRI39 | 4G_TD_KGRI39 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362306 | 2021-06-25 | P/FVC/MDS/1049958/2021 | 2021-08-09 | ST202008037529 | 2020-08-06 | P/FVC/MDS/1001288/2020 | 2020-08-12 |  |  |  |  | ST202007033338 | 2020-07-31 | P/FBW/MDS/1001068/2020 | 2020-08-07 | Partof461sitesSyamaMay'30/TocoChangedfromOwntoATCBysyamaNov'7/Earliercheck,nowP0/P1 | KGRI39
330 | TKSI14 | TKSI14 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1385536 | R/NN-430871 | Nominals with issues | Dropped-Canb. | 2020-07-04 | TKSI14 | 4G_FD900_TKSI14 | 4G_FD2100_TKSI14 | 4G_TD_TKSI14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362815 | 2021-06-26 | P/FVC/MDS/1050070/2021 | 2021-08-09 | ST202008037525 | 2020-08-06 | P/FVC/MDS/1001285/2020 | 2020-08-12 |  |  |  |  | ST202007033334 | 2020-07-31 | P/FBW/MDS/1001066/2020 | 2020-08-07 | Partof461sitesSyamaMay'30/R/NN-347747/SRwithdrwanduetoDAY1TDDandrepunched | TKSI14
331 | IDPD8 | IDPD08 | Salem | Vellore |  | ROTN | Indus |  |  | Nominal WIP | On Air | 2020-06-30 | IDPD08 | 4G_FD900_IDPD08 | 4G_FD2100_IDPD08 | 4G_TD_IDPD08 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364409 | 2021-06-28 | P/FVC/MDS/1050279/2021 | 2021-08-09 | ST202008037476 | 2020-08-06 | P/FVC/MDS/1001275/2020 | 2020-08-12 |  |  |  |  | ST202007033327 | 2020-07-31 | P/FBW/MDS/1001059/2020 | 2020-08-07 | 20-20-RestofUrban/R/NN-384803SPRejectedduetoNoRF3/2/2020/ R/NN-384803Withdrwan/R/NN-424370/SRwithdrwanduetoDAY1TDDandrepunched | IDPD8
332 | NAKKS2 | NAKKS2 | Perambalur | Trichy |  | ROTN | INDUS |  |  | Nominal WIP | SO | 2021-02-15 | NAKKS2 | 4G_FD900_NAKKS2 | 4G_FD2100_NAKKS2 | 4G_TD_NAKKS2 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106364413 | 2021-06-28 | P/FVC/MDS/1050283/2021 | 2021-08-09 | ST202008037471 | 2020-08-06 | P/FVC/MDS/1001266/2020 | 2020-08-12 | ST202008039026 | 2020-08-07 | P/FVC/MDS/1001331/2020 | 2020-08-13 | ST202107389829 | 2021-07-20 | P/FBW/MDS/1056645/2021 | 2021-09-08 | SO R/NN-430558 terminated by Indus and repunched | NAKKS2
333 | ACODE2 | ACODE2 |  |  |  | ROTN | Indus | R/NN-420647 |  |  |  | 2020-07-06 | ACODE2 | 4G_FD900_ACODE2 | 4G_FD2100_ACODE2 | 4G_TD_ACODE2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498646 | 2021-08-31 | P/FVC/MDS/1060437/2021 | 2021-09-13 | ST202008037558 | 2020-08-06 | P/FVC/MDS/1001297/2020 | 2020-08-12 | ST202008039067 | 2020-08-07 | P/FVC/MDS/1001342/2020 | 2020-08-13 | ST202007033345 | 2020-07-31 | P/FBW/MDS/1001075/2020 | 2020-08-07 |  | ACODE2
334 | KLCL11 | KLCL11 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/21780 | T20TN00207 | Nominals with issues | On Air | 2020-02-25 | KLCL11 | 4G_FD900_KLCL11 | 4G_FD2100_KLCL11 | 4G_TD_KLCL11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362310 | 2021-06-25 | P/FVC/MDS/1049962/2021 | 2021-08-09 | ST202007022832 | 2020-07-09 | P/FVC/MDS/1000572/2020 | 2020-07-18 |  |  |  |  | ST202007023147 | 2020-07-13 | P/FBW/MDS/1000605/2020 | 2020-07-18 | 20-20-RestofUrban | KLCL11
335 | USPT10 | USPT10 | Madurai | Madurai |  | ROTN | Indus | IN-1385540 | R/NN-442721 | Nominals with issues | Dropped-Canb. | 2020-06-20 | USPT10 | 4G_FD900_USPT10 | 4G_FD2100_USPT10 | 4G_TD_USPT10 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363155 | 2021-06-26 | P/FVC/MDS/1050107/2021 | 2021-08-09 | ST202007022821 | 2020-07-09 | P/FVC/MDS/1000561/2020 | 2020-07-18 |  |  |  |  | ST202007023130 | 2020-07-13 | P/FBW/MDS/1000590/2020 | 2020-07-18 | 20-20-RestofUrban/TocochangedfromATCtoindus2/14/2020/R/NN-403685/SRwithdrwanduetoDAY1TDDandrepunched | USPT10
336 | ARAK26 | ARAK26 | Vellore | Vellore |  | ROTN | Ascend | 10474 | - | Nominals with issues | Dropped-Canb. | 2020-06-10 | ARAK26 | 4G_FD900_ARAK26 | 4G_FD2100_ARAK26 | 4G_TD_ARAK26 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361833 | 2021-06-25 | P/FVC/MDS/1049896/2021 | 2021-08-09 | ST202006017060 | 2020-06-30 | P/FVC/MDS/1000319/2020 | 2020-07-05 |  |  |  |  | ST202007017688 | 2020-07-02 | P/FBW/MDS/1000456/2020 | 2020-07-09 | Partof461sitesSyamaMay'30/SOSurrenderedbyArulWithdrwanbySCMOct18th/Earliercheck,nowP0/P1 | ARAK26
337 | ECHNKR | ECHNKR | Kancheepuram | Chennai |  | ROTN | Indus | IN-1386694 | R/NN-458378 | Nominals with issues | On Air | 2020-07-06 | ECHNKR | 4G_FD900_ECHNKR | 4G_FD2100_ECHNKR | 4G_TD_ECHNKR | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202106364350 | 2021-06-28 | P/FVC/MDS/1050268/2021 | 2021-08-09 | ST202006016982 | 2020-06-30 | P/FVC/MDS/1000292/2020 | 2020-07-05 | ST202006017453 | 2020-07-01 | P/FVC/MDS/1000406/2020 | 2020-07-08 | ST202108430490 | 2021-08-17 | P/FBW/MDS/1056048/2021 | 2021-09-07 | 0 | ECHNKR
338 | JBES29 | JBES29 | Chennai | Chennai |  | CHN | TVI | ATTNCHN2021 | - | Nominals with issues | On air | 2020-06-22 | JBES29 | 4G_FD900_JBES29 | 4G_FD2100_JBES29 | 4G_TD_JBES29 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202006016773 | 2020-06-28 | P/FVC/MDS/1000284/2020 | 2020-07-04 | ST202006017151 | 2020-06-30 | P/FVC/MDS/1000358/2020 | 2020-07-05 | ST202106358246 | 2021-06-23 | P/FVC/MDS/1055849/2021 | 2021-09-04 | ST202007017708 | 2020-07-02 | P/FBW/MDS/1000475/2020 | 2020-07-09 | 0 | JBES29
339 | PATT18 | PATT18 | Chennai | Chennai |  | CHN | Indus | IN-1377593 | R/NN-396273 | Nominals with issues | SO | 2020-05-20 | PATT18 | 4G_FD900_PATT18 | 4G_FD2100_PATT18 | 4G_TD_PATT18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202006016767 | 2020-06-28 | P/FVC/MDS/1000278/2020 | 2020-07-04 | ST202006017137 | 2020-06-30 | P/FVC/MDS/1000352/2020 | 2020-07-05 | ST202106358267 | 2021-06-23 | P/FVC/MDS/1055864/2021 | 2021-09-04 | ST202007017702 | 2020-07-02 | P/FBW/MDS/1000469/2020 | 2020-07-09 | SO Withdrawn from Indus end ,Mail from Mani - 2 Jun'21 - given to ascend | PATT18
340 | CDLR61 | CDLR61 | Cuddalore | Trichy |  | ROTN | Ascend |  |  | Nominal WIP | Dropped-Canb. | 2021-01-04 | CDLR61 | 4G_FD900_CDLR61 | 4G_FD2100_CDLR61 | 4G_TD_CDLR61 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364207 | 2021-06-28 | P/FVC/MDS/1050168/2021 | 2021-08-09 | ST202006017131 | 2020-06-30 | P/FVC/MDS/1000346/2020 | 2020-07-05 |  |  |  |  | ST202007017695 | 2020-07-02 | P/FBW/MDS/1000463/2020 | 2020-07-09 | Partof461sitesSyamaMay'30/SOSurrenderedbyATCconfirmedbysyama10/4/2019/Earliercheck,nowP0/P1/TocochangedfromATCtoAscend6/16/2020 | CDLR61
341 | PNRI22 | PNRI22 | Thiruvallur | Chennai |  | ROTN | Indus |  |  | Nominal WIP | SO | 2020-06-11 | PNRI22 | 4G_FD900_PNRI22 | 4G_FD2100_PNRI22 | 4G_TD_PNRI22 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364368 | 2021-06-28 | P/FVC/MDS/1050273/2021 | 2021-08-09 | ST202006017070 | 2020-06-30 | P/FVC/MDS/1000323/2020 | 2020-07-05 |  |  |  |  | ST202007017692 | 2020-07-02 | P/FBW/MDS/1000460/2020 | 2020-07-09 | Partof461sitesSyamaMay'30/Earliercheck,nowP0/P1/TocochangedfomATCtoindusconfirmedbysyamaoraly3/11/2020/R/NN-404851/SRwithdrwanduetoDAY1TDDandrepunched/R/NN-404851SPRejectedduetop15/19/2020 | PNRI22
342 | BVNI16 | BVNI16 | Erode | Coimbatore |  | ROTN | Indus | IN-1375688 | R/NN-382668 | Nominals with issues | Drop | 2020-02-21 | BVNI16 | 4G_FD900_BVNI16 | 4G_FD2100_BVNI16 | 4G_TD_BVNI16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361912 | 2021-06-25 | P/FVC/MDS/1049908/2021 | 2021-08-09 | 2020397988 | 2020-03-06 | P/FVC/MDS/6102488/2020 | 2020-06-19 |  |  |  |  | 2020398043 | 2020-03-06 | P/FBW/MDS/6102460/2020 | 2020-06-19 | Partof461sitesSyamaMay'30/R/NN-346060Withdrwanthenbokedasliteplusbasisonjawhar6/24/2019/R/NN-347934SOSurenedredbyindusJawhar12/12/2019 | BVNI16
343 | KGRI36 | KGRI36 | Krishnagiri | Vellore |  | ROTN | Indus | IN-1376277 | R/NN-384035 | Nominals with issues | Dropped-Canb. | 2020-03-09 | KGRI36 | 4G_FD900_KGRI36 | 4G_FD2100_KGRI36 | 4G_TD_KGRI36 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362305 | 2021-06-25 | P/FVC/MDS/1049957/2021 | 2021-08-09 | 2020523163 | 2020-04-03 | P/FBW/MDS/6098892/2020 | 2020-06-19 |  |  |  |  | 2020523164 | 2020-04-03 | P/FBW/MDS/6098893/2020 | 2020-06-19 | 20-20-TopTowns0.8Validation | KGRI36
344 | NGL107 | NGL107 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/21759 | T20TN00186 | Nominals with issues | Dropped-Canb. | 2020-03-04 | NGL107 | 4G_FD900_NGL107 | 4G_FD2100_NGL107 | 4G_TD_NGL107 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362643 | 2021-06-26 | P/FVC/MDS/1050003/2021 | 2021-08-09 | 2020398001 | 2020-03-06 | P/FVC/MDS/6102501/2020 | 2020-06-19 |  |  |  |  | 2020398057 | 2020-03-06 | P/FBW/MDS/6102471/2020 | 2020-06-19 | 20-20-TopTowns0.8Validation | NGL107
345 | SVKI53 | SVKI53 | Virudhunagar | Madurai |  | ROTN | Indus | IN-1366357 | R/NN-350010 | Nominals with issues | SR | 2019-07-12 | SVKI53 | 4G_FD900_SVKI53 | 4G_FD2100_SVKI53 | 4G_TD_SVKI53 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362795 | 2021-06-26 | P/FVC/MDS/1050055/2021 | 2021-08-09 | 2020520906 | 2020-04-03 | P/FVC/MDS/6099498/2020 | 2020-06-19 |  |  |  |  | 2020520917 | 2020-04-03 | P/FBW/MDS/6099509/2020 | 2020-06-19 | R/NN-315348withdrawn&RebookingtobedoneasODGBT30Mbasisonjawhar7/8/2019 | SVKI53
346 | TRY320 | TRY320 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-1372417 | R/NN-373711 | Nominals with issues | SR | 2020-03-21 | TRY320 | 4G_FD900_TRY320 | 4G_FD2100_TRY320 | 4G_TD_TRY320 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363075 | 2021-06-26 | P/FVC/MDS/1050085/2021 | 2021-08-09 | 2020525439 | 2020-04-03 | P/FVC/MDS/6098767/2020 | 2020-06-19 |  |  |  |  | 2020525492 | 2020-04-03 | P/FBW/MDS/6098820/2020 | 2020-06-19 | Partof461sitesSyamaMay'30/ATCsurrenderedonOct29/ | TRY320
347 | URAP10 | URAP10 | Chennai | Chennai |  | CHN | Indus |  |  | Nominal WIP | On air | 2020-03-25 | URAP10 | 4G_FD900_URAP10 | 4G_FD2100_URAP10 | 4G_TD_URAP10 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020523228 | 2020-04-03 | P/FVC/MDS/6098957/2020 | 2020-06-19 | 2020523229 | 2020-04-03 | P/FVC/MDS/6098958/2020 | 2020-06-19 | ST202106358332 | 2021-06-23 | P/FVC/MDS/1055884/2021 | 2021-09-04 | 2020523230 | 2020-04-03 | P/FBW/MDS/6098959/2020 | 2020-06-19 | 0 | URAP10
348 | KOLP13 | KOLP13 | Chennai |  |  | CHN |  |  |  | Nominal WIP | On air | 2021-07-07 | KOLP13 | 4G_FD900_KOLP13 | 4G_FD2100_KOLP13 | 4G_TD_KOLP13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107371989 | 2021-07-03 | P/FVC/MDS/1051643/2021 | 2021-08-14 | 2020525421 | 2020-04-03 | P/FVC/MDS/6099918/2020 | 2020-06-19 | ST202107393764 | 2021-07-23 | P/FVC/MDS/1057245/2021 | 2021-09-09 | ST202107393410 | 2021-07-23 | P/FBW/MDS/1056717/2021 | 2021-09-08 | 0 | KOLP13
349 | THOUS4 | THOUS4 | Chennai | Chennai |  | CHN | Indus | R/RES-414364 | 0 | Nominal WIP |  | 2020-03-12 | THOUS4 | 4G_FD900_THOUS4 | 4G_FD2100_THOUS4 | 4G_TD_THOUS4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020520950 | 2020-04-03 | P/FVC/MDS/6099542/2020 | 2020-06-19 | 2020520951 | 2020-04-03 | P/FVC/MDS/6099543/2020 | 2020-06-19 | ST202108413667 | 2021-08-09 | P/FVC/MDS/1055940/2021 | 2021-09-05 | 2020520952 | 2020-04-03 | P/FBW/MDS/6099544/2020 | 2020-06-19 |  | THOUS4
350 | PLCH36 | PLCH36 |  |  |  | ROTN | ATC | - |  |  |  | 2020-03-20 | PLCH36 | 4G_FD900_PLCH36 | 4G_FD2100_PLCH36 | 4G_TD_PLCH36 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109533383 | 2021-09-25 | P/FVC/MDS/1062982/2021 | 2021-10-01 | 2020525456 | 2020-04-03 | P/FVC/MDS/6098784/2020 | 2020-06-19 | 2020525531 | 2020-04-03 | P/FVC/MDS/6098759/2020 | 2020-06-19 | 2020525509 | 2020-04-03 | P/FBW/MDS/6098837/2020 | 2020-06-19 |  | PLCH36
351 | SLGR8 | SLGR08 |  |  |  | ROTN | Indus | - | R/NN-402582 |  |  | 2020-03-13 | SLGR08 | 4G_FD900_SLGR08 | 4G_FD2100_SLGR08 | 4G_TD_SLGR08 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109533382 | 2021-09-25 | P/FVC/MDS/1062981/2021 | 2021-10-01 | 2020525443 | 2020-04-03 | P/FVC/MDS/6098771/2020 | 2020-06-19 | 2020525518 | 2020-04-03 | P/FVC/MDS/6098746/2020 | 2020-06-19 | 2020525496 | 2020-04-03 | P/FBW/MDS/6098824/2020 | 2020-06-19
352 | CBE761 | CBE761 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1372405 | R/NN-373757 | Nominals with issues | Dropped | 2020-01-22 | CBE761 | 4G_FD900_CBE761 | 4G_FD2100_CBE761 | 4G_TD_CBE761 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361944 | 2021-06-25 | P/FVC/MDS/1049913/2021 | 2021-08-09 | 2020346385 | 2020-02-04 | P/FVC/MDS/6085683/2020 | 2020-06-11 |  |  |  |  | 2020346435 | 2020-02-04 | P/FBW/MDS/6085733/2020 | 2020-06-11 | ATCsurrenderedonOct29TH.Re-allottedtoIndus/TVIon30th | CBE761
353 | CDLR70 | CDLR70 | Cuddalore | Trichy |  | ROTN | ATC | TN/CU/AT/21771 | T20TN00198 | Nominals with issues | Dropped-Canb. | 2020-02-19 | CDLR70 | 4G_FD900_CDLR70 | 4G_FD2100_CDLR70 | 4G_TD_CDLR70 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362050 | 2021-06-25 | P/FVC/MDS/1046129/2021 | 2021-08-03 | 2020383700 | 2020-02-24 | P/FVC/DBR/6086428/2020 | 2020-06-11 |  |  |  |  | 2020383744 | 2020-02-24 | P/FBW/MDS/6086552/2020 | 2020-06-11 | 20-20-TopTowns0.8Validation/productchangedfromliteanchortostandard4/6/2020 | CDLR70
354 | TVMYR4 | TVMYR4 | Chennai | Chennai |  | CHN | Railtel | - | - | Nominals with issues | Dropped-Canb. | 2020-01-21 | TVMYR4 | 4G_FD900_TVMYR4 | 4G_FD2100_TVMYR4 | 4G_TD_TVMYR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020346369 |  | P/FVC/MDS/6085667/2020 | 2020-06-11 | 2020346391 | 2020-02-04 | P/FVC/MDS/6085689/2020 | 2020-06-11 | ST202106358300 | 2021-06-23 | P/FVC/MDS/1055876/2021 | 2021-09-04 | 2020346420 | 2020-02-04 | P/FBW/MDS/6085718/2020 | 2020-06-11 | 0 | TVMYR4
355 | VEERA5 | VEERA5 | Chennai | Chennai |  | CHN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-01-23 | VEERA5 | 4G_FD900_VEERA5 | 4G_FD2100_VEERA5 | 4G_TD_VEERA5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020346376 |  | P/FVC/MDS/6085674/2020 | 2020-06-11 | 2020346398 | 2020-02-04 | P/FVC/MDS/6085696/2020 | 2020-06-11 | ST202106358374 | 2021-06-23 | P/FVC/MDS/1055891/2021 | 2021-09-04 | 2020346427 | 2020-02-04 | P/FBW/MDS/6085725/2020 | 2020-06-11 | 0 | VEERA5
356 | TIVM27 | TIVM27 | Viluppuram | Trichy |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-01-16 | TIVM27 | 4G_FD900_TIVM27 | 4G_FD2100_TIVM27 | 4G_TD_TIVM27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371882 | 2021-07-03 | P/FVC/MDS/1051816/2021 | 2021-08-15 | 2020346386 | 2020-02-04 | P/FVC/MDS/6085684/2020 | 2020-06-11 |  |  |  |  | ST202106359690 | 2021-06-24 | P/FBW/MDS/1051756/2021 | 2021-08-15 | 0 | TIVM27
357 | PRNG28 | PRNG28 | Chennai | Chennai |  | CHN | indus | R/NN-383250 | 0 | Nominal WIP |  | 2020-01-27 | PRNG28 | 4G_FD900_PRNG28 | 4G_FD2100_PRNG28 | 4G_TD_PRNG28 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020346371 |  | P/FVC/MDS/6085669/2020 | 2020-06-11 | 2020346393 | 2020-02-04 | P/FVC/MDS/6085691/2020 | 2020-06-11 | ST202008045729 | 2020-08-17 | P/FVC/MDS/1001931/2020 | 2020-08-22 | 2020346422 | 2020-02-04 | P/FBW/MDS/6085720/2020 | 2020-06-11 |  | PRNG28
358 | CNMCM2 | CNMCM2 |  |  |  | ROTN | CNIL | - |  |  |  | 2020-01-27 | CNMCM2 | 4G_FD900_CNMCM2 | 4G_FD2100_CNMCM2 | 4G_TD_CNMCM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109533381 | 2021-09-25 | P/FVC/MDS/1062980/2021 | 2021-10-01 | 2020346486 | 2020-02-04 | P/FVC/MDS/6085782/2020 | 2020-06-11 | 2020346512 | 2020-02-04 | P/FVC/MDS/6085808/2020 | 2020-06-11 | 2020346505 | 2020-02-04 | P/FBW/MDS/6085801/2020 | 2020-06-11 |  | CNMCM2
359 | LALPT3 | LALPT3 | Cuddalore | Trichy |  | ROTN | Indus | IN-1376956 | R/NN-392122 | Nominals with issues | SO | 2020-02-17 | LALPT3 | 4G_FD900_LALPT3 | 4G_FD2100_LALPT3 | 4G_TD_LALPT3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362358 | 2021-06-25 | P/FVC/MDS/1049979/2021 | 2021-08-09 | 2020368243 | 2020-02-13 | P/FVC/MDS/6084190/2020 | 2020-06-04 |  |  |  |  | 2020368295 | 2020-02-13 | P/FBW/MDS/6084242/2020 | 2020-06-04 | TocoChangedFromATC(95)ToIndusConfirmedBySyama1/17/2019/R/NN-319250BookedAs30MtrGBTODSiteRequestWithdwanandRebookedasLiteplusAsperSyamaConfirmation/R/NN-321183SOWithdrwanduetoindussurrenedred1/30/2020 | LALPT3
360 | MDU274 | MDU274 | Madurai | Madurai |  | ROTN | Airtel | MDU274 | - | Nominals with issues | SR | 2020-10-07 | MDU274 | 4G_FD900_MDU274 | 4G_FD2100_MDU274 | 4G_TD_MDU274 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362363 | 2021-06-25 | P/FVC/MDS/1049983/2021 | 2021-08-09 | 2020368303 | 2020-02-13 | P/FVC/MDS/6084250/2020 | 2020-06-04 |  |  |  |  | 2019409656 | 2019-12-09 | P/FBW/MDS/6046233/2020 | 2020-05-19 | SocanceledbyAcendMay7'19andtocochangedtoATCmay7'19/chnagedtoP1bysyama2/10/2020/TocoChangedtoownbysomasundar2/18/2020
361 | PATU39 | PATU39 | Thanjavur | Trichy |  | ROTN | Airtel | PATU39 | - | Nominals with issues | Dropped-Canb. | 2020-02-24 | PATU39 | 4G_FD900_PATU39 | 4G_FD2100_PATU39 | 4G_TD_PATU39 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362653 | 2021-06-26 | P/FVC/MDS/1050010/2021 | 2021-08-09 | 2020368312 | 2020-02-13 | P/FVC/MDS/6084259/2020 | 2020-06-04 |  |  |  |  | 2020368342 | 2020-02-13 | P/FBW/MDS/6084289/2020 | 2020-06-04 | Partof461sitesSyamaMay'30/TAM/RTT/K/08654TocoChangedfromCNILtoATCConfirmedbycharan7/5/2019/FreshSRwithdrwanbyATC8/22/2019 | PATU39
362 | CBE780 | CBE780 | Coimbatore | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-02-06 | CBE780 | 4G_FD900_CBE780 | 4G_FD2100_CBE780 | 4G_TD_CBE780 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371962 | 2021-07-03 | P/FVC/MDS/1051616/2021 | 2021-08-14 | 2020368236 | 2020-02-13 | P/FVC/MDS/6084183/2020 | 2020-06-04 |  |  |  |  | ST202106359726 | 2021-06-24 | P/FBW/MDS/1051763/2021 | 2021-08-15 | 0 | CBE780
363 | PKGD9 | PKGD09 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1376595 | R/NN-391631 | Nominals with issues | Dropped-Canb. | 2020-02-18 | PKGD09 | 4G_FD900_PKGD09 | 4G_FD2100_PKGD09 | 4G_TD_PKGD09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362731 | 2021-06-26 | P/FVC/MDS/1050018/2021 | 2021-08-09 | 2020397111 | 2020-03-06 | P/FVC/MDS/6071271/2020 | 2020-05-29 |  |  |  |  | 2020397190 | 2020-03-06 | P/FBW/MDS/6071155/2020 | 2020-05-29 | 20-20-RestofUrban | PKGD9
364 | VSDLR2 | VSDLR2 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1376447 | R/NN-391233 | Nominals with issues | On Air | 2020-02-18 | VSDLR2 | 4G_FD900_VSDLR2 | 4G_FD2100_VSDLR2 | 4G_TD_VSDLR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363250 | 2021-06-26 | P/FVC/MDS/1050122/2021 | 2021-08-09 | 2020397110 | 2020-03-06 | P/FVC/MDS/6071270/2020 | 2020-05-29 |  |  |  |  | 2020397189 | 2020-03-06 | P/FBW/MDS/6071154/2020 | 2020-05-29 | 20-20-RestofUrban | VSDLR2
365 | TIRV15 | TIRV15 | Chennai | Chennai |  | CHN | Indus |  |  | Nominal WIP | On air | 2019-08-16 | TIRV15 | 4G_FD900_TIRV15 | 4G_FD2100_TIRV15 | 4G_TD_TIRV15 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020397092 |  | P/FVC/MDS/6071252/2020 | 2020-05-29 | 2020397159 | 2020-03-06 | P/FVC/MDS/6071129/2020 | 2020-05-29 | ST202106358333 | 2021-06-23 | P/FVC/MDS/1055885/2021 | 2021-09-04 | 2020397176 | 2020-03-06 | P/FBW/MDS/6071146/2020 | 2020-05-29 | 0 | TIRV15
366 | ABSM7 | ABSM07 | Tirunelveli | Madurai |  | ROTN | Indus | IN-1376103 | R/NN-385066 | Nominals with issues | Dropped-Canb. | 2020-01-29 | ABSM07 | 4G_FD900_ABSM07 | 4G_FD2100_ABSM07 | 4G_TD_ABSM07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106360478 | 2021-06-24 | P/FVC/MDS/1049889/2021 | 2021-08-09 | 2020360232 | 2020-02-10 | P/FVC/MDS/6051088/2020 | 2020-05-19 |  |  |  |  | 2020360281 | 2020-02-10 | P/FBW/MDS/6051137/2020 | 2020-05-19 | 20-20-RestofUrban | ABSM7
367 | AMBR49 | AMBR49 | Vellore | Vellore |  | ROTN | Indus | IN-1369405 | R/NN-366251 | Nominals with issues | Drop | 2020-02-03 | AMBR49 | 4G_FD900_AMBR49 | 4G_FD2100_AMBR49 | 4G_TD_AMBR49 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106360484 | 2021-06-24 | P/FVC/MDS/1049893/2021 | 2021-08-09 | 2020332481 | 2020-01-24 | P/FVC/MDS/6049223/2020 | 2020-05-19 |  |  |  |  | 2020332563 | 2020-01-24 | P/FBW/MDS/6049293/2020 | 2020-05-19 | Partof461sitesSyamaMay'30/SRSurrenderedbyAscendconfirmedbysyama8/27/2019 | AMBR49
368 | AMNR7 | AMNR07 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-1376286 | R/NN-385758 | Nominals with issues | SR | 2020-02-05 | AMNR07 | 4G_FD900_AMNR07 | 4G_FD2100_AMNR07 | 4G_TD_AMNR07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361824 | 2021-06-25 | P/FVC/MDS/1049894/2021 | 2021-08-09 | 2020360263 | 2020-02-10 | P/FVC/MDS/6051119/2020 | 2020-05-19 |  |  |  |  | 2020360390 | 2020-02-10 | P/FBW/MDS/6051210/2020 | 2020-05-19 | 20-20-RestofUrban | AMNR7
369 | CBE748 | CBE748 | Coimbatore | Coimbatore |  | ROTN | Airtel | CBE748 | - | Nominals with issues | SP | 2020-01-06 | CBE748 | 4G_FD900_CBE748 | 4G_FD2100_CBE748 | 4G_TD_CBE748 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361932 | 2021-06-25 | P/FVC/MDS/1049911/2021 | 2021-08-09 | 2020361006 | 2020-02-10 | P/FVC/MDS/6051286/2020 | 2020-05-19 |  |  |  |  | 2020361229 | 2020-02-10 | P/FBW/MDS/6050927/2020 | 2020-05-19 | Partof461sitesSyamaMay'30
370 | CDBM41 | CDBM41 | Cuddalore | Trichy |  | ROTN | Indus | IN-1369996 | R/NN-367415 | Nominals with issues | On Air | 2019-11-20 | CDBM41 | 4G_FD900_CDBM41 | 4G_FD2100_CDBM41 | 4G_TD_CDBM41 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361972 | 2021-06-25 | P/FVC/MDS/1049923/2021 | 2021-08-09 | 2019402412 | 2020-01-02 | P/FBW/MDS/6047688/2020 | 2020-05-19 |  |  |  |  | 2019402430 | 2020-01-02 | P/FBW/MDS/6047706/2020 | 2020-05-19 | Partof461sitesSyamaMay'30/SRSurrenderedbyAscendconfirmedbysyama8/27/2019/Tocochangedfromatctoindusbasisonsyama/jawhar9/10/2019/PrioritychangedfromP1toP07/14/2020 Location changed on 4 Jun'21 - Old location 11.405434/79.688258 SO Withdrawn from Indus end ,Mail from Mani - 2 Jun'21 - alocated to Ascend | CDBM41
371 | CDBM43 | CDBM43 | Cuddalore | Trichy |  | ROTN | Indus | IN-1376419 | R/NN-383980 | Nominals with issues | Dropped-Canb. | 2020-02-08 | CDBM43 | 4G_FD900_CDBM43 | 4G_FD2100_CDBM43 | 4G_TD_CDBM43 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361973 | 2021-06-25 | P/FVC/MDS/1049924/2021 | 2021-08-09 | 2020360261 | 2020-02-10 | P/FVC/MDS/6051117/2020 | 2020-05-19 |  |  |  |  | 2020360387 | 2020-02-10 | P/FBW/MDS/6051207/2020 | 2020-05-19 | 20-20-TopTowns0.8Validation | CDBM43
372 | ELGD9 | ELGD09 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/21751 | T20TN00178 | Nominals with issues | Dropped-Canb. | 2020-02-08 | ELGD09 | 4G_FD900_ELGD09 | 4G_FD2100_ELGD09 | 4G_TD_ELGD09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362262 | 2021-06-25 | P/FVC/MDS/1049937/2021 | 2021-08-09 | 2020360247 | 2020-02-10 | P/FVC/MDS/6051103/2020 | 2020-05-19 |  |  |  |  | 2020360296 | 2020-02-10 | P/FBW/MDS/6051152/2020 | 2020-05-19 | 20-20-TopTowns0.8Validation | ELGD9
373 | ERD138 | ERD138 | Erode | Coimbatore |  | ROTN | Indus | IN-1375283 | R/NN-382172 | Nominals with issues | Dropped-Canb. | 2020-01-20 | ERD138 | 4G_FD900_ERD138 | 4G_FD2100_ERD138 | 4G_TD_ERD138 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362264 | 2021-06-25 | P/FVC/MDS/1049938/2021 | 2021-08-09 | 2020332480 | 2020-01-24 | P/FVC/MDS/6049222/2020 | 2020-05-19 |  |  |  |  | 2020332562 | 2020-01-24 | P/FBW/MDS/6049292/2020 | 2020-05-19 | Partof461sitesSyamaMay'30/SOSurrenderedbyATCconfirmedbysyama10/4/2019 | ERD138
374 | JOLR16 | JOLR16 | Vellore | Vellore |  | ROTN | Indus | IN-1369388 | R/NN-366238 | Nominals with issues |  | 2020-01-09 | JOLR16 | 4G_FD900_JOLR16 | 4G_FD2100_JOLR16 | 4G_TD_JOLR16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362298 | 2021-06-25 | P/FVC/MDS/1049953/2021 | 2021-08-09 | 2020328003 | 2020-01-16 | P/FVC/MDS/6049391/2020 | 2020-05-19 |  |  |  |  | 2020328177 | 2020-01-16 | P/FBW/MDS/6049509/2020 | 2020-05-19 | Partof461sitesSyamaMay'30/SRSurrenderedbyAscendconfirmedbysyama8/27/2019 | JOLR16
375 | KMBM12 | KMBM12 | Theni | Madurai |  | ROTN | Indus | IN-1372407 | R/NN-373759 | Nominals with issues | Dropped-Canb. | 2020-01-09 | KMBM12 | 4G_FD900_KMBM12 | 4G_FD2100_KMBM12 | 4G_TD_KMBM12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362314 | 2021-06-25 | P/FVC/MDS/1049966/2021 | 2021-08-09 | 2020328007 | 2020-01-16 | P/FVC/MDS/6049395/2020 | 2020-05-19 |  |  |  |  | 2020328181 | 2020-01-16 | P/FBW/MDS/6049513/2020 | 2020-05-19 | Partof461sitesSyamaMay'30/ATCsurrenderedonOct29/ | KMBM12
376 | KOLA43 | KOLA43 | Chennai | Chennai |  | CHN | ATC | TN/CH/AT/21697 | T19TN11249 | Nominals with issues | Dropped-Canb. | 2020-01-31 | KOLA43 | 4G_FD900_KOLA43 | 4G_FD2100_KOLA43 | 4G_TD_KOLA43 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020360224 | 2020360224 | P/FVC/MDS/6051080/2020 | 2020-05-19 | 2020360271 | 2020-02-10 | P/FVC/MDS/6051127/2020 | 2020-05-19 | ST202106358252 | 2021-06-23 | P/FVC/MDS/1055852/2021 | 2021-09-04 | 2020360309 | 2020-02-10 | P/FBW/MDS/6051165/2020 | 2020-05-19 | 0 | KOLA43
377 | MADH29 | MADH29 | Chennai | Chennai |  | CHN | Indus | IN-1371540 | R/NN-372487 | Nominals with issues | SR | 2019-11-04 | MADH29 | 4G_FD900_MADH29 | 4G_FD2100_MADH29 | 4G_TD_MADH29 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2019647434 |  | P/FVC/MDS/6047622/2020 | 2020-05-19 | 2019647439 | 2020-01-02 | P/FVC/MDS/6047627/2020 | 2020-05-19 | ST202106358257 | 2021-06-23 | P/FVC/MDS/1055855/2021 | 2021-09-04 | 2019647444 | 2020-01-02 | P/FBW/MDS/6047632/2020 | 2020-05-19 | 0 | MADH29
378 | MDU385 | MDU385 | Madurai | Madurai |  | ROTN | Indus | IN-1370176 | R/NN-367957 | Nominals with issues | Dropped-Canb. | 2019-10-14 | MDU385 | 4G_FD900_MDU385 | 4G_FD2100_MDU385 | 4G_TD_MDU385 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362369 | 2021-06-25 | P/FVC/MDS/1049984/2021 | 2021-08-09 | 2020328048 | 2020-01-16 | P/FVC/MDS/6049336/2020 | 2020-05-19 |  |  |  |  | 2019617863 | 2019-12-03 | P/FBW/MDS/5893748/2019 | 2019-12-10 | Partof461sitesSyamaMay'30R/NN-346103SOSurrenderedbyjawharconfirmedbysyama9/6/2019 | MDU385
379 | NGL94 | NGL094 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/21755 | T20TN00182 | Nominals with issues | Dropped-Canb. | 2020-02-08 | NGL094 | 4G_FD900_NGL094 | 4G_FD2100_NGL094 | 4G_TD_NGL094 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362647 | 2021-06-26 | P/FVC/MDS/1050005/2021 | 2021-08-09 | 2020360246 | 2020-02-10 | P/FVC/MDS/6051102/2020 | 2020-05-19 |  |  |  |  | 2020360295 | 2020-02-10 | P/FBW/MDS/6051151/2020 | 2020-05-19 | 20-20-TopTowns0.8Validation | NGL94
380 | NLKP6 | NLKP06 | Cuddalore | Trichy |  | ROTN | Indus | IN-1370911 | R/NN-369697 | Nominals with issues | Dropped-Canb. | 2019-10-29 | NLKP06 | 4G_FD900_NLKP06 | 4G_FD2100_NLKP06 | 4G_TD_NLKP06 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362649 | 2021-06-26 | P/FVC/MDS/1050007/2021 | 2021-08-09 | 2019647093 | 2020-01-02 | P/FVC/MDS/6047281/2020 | 2020-05-19 |  |  |  |  | ST202012176569 | 2020-12-17 | P/FBW/MDS/1007836/2020 | 2020-12-29 | TocoChangedfromowntoindusconfirmedbysyama8/29/2019/SPRejectedrebokedbasisonjawhar9/17/2019/R/NN-368220SPRejectedandreapply | NLKP6
381 | PSMUR8 | PSMUR8 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/21744 | T20TN00171 | Nominals with issues | Dropped-Canb. | 2020-01-29 | PSMUR8 | 4G_FD900_PSMUR8 | 4G_FD2100_PSMUR8 | 4G_TD_PSMUR8 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362760 | 2021-06-26 | P/FVC/MDS/1050031/2021 | 2021-08-09 | 2020360239 | 2020-02-10 | P/FVC/MDS/6051095/2020 | 2020-05-19 |  |  |  |  | 2020360288 | 2020-02-10 | P/FBW/MDS/6051144/2020 | 2020-05-19 | 20-20-TopTowns0.8Validation | PSMUR8
382 | SVKI67 | SVKI67 | Virudhunagar | Madurai |  | ROTN | Indus | IN-1375998 | R/NN-384082 | Nominals with issues | Dropped-Canb. | 2020-01-29 | SVKI67 | 4G_FD900_SVKI67 | 4G_FD2100_SVKI67 | 4G_TD_SVKI67 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362797 | 2021-06-26 | P/FVC/MDS/1050057/2021 | 2021-08-09 | 2020360233 | 2020-02-10 | P/FVC/MDS/6051089/2020 | 2020-05-19 |  |  |  |  | 2020360282 | 2020-02-10 | P/FBW/MDS/6051138/2020 | 2020-05-19 | 20-20-TopTowns0.8Validation | SVKI67
383 | SVPT17 | SVPT17 | Virudhunagar | Madurai |  | ROTN | Indus | IN-1372670 | R/NN-375030 | Nominals with issues | Dropped-Canb. | 2020-01-13 | SVPT17 | 4G_FD900_SVPT17 | 4G_FD2100_SVPT17 | 4G_TD_SVPT17 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362798 | 2021-06-26 | P/FVC/MDS/1050058/2021 | 2021-08-09 | 2020360421 | 2020-02-10 | P/FVC/MDS/6051327/2020 | 2020-05-19 |  |  |  |  | 2020360433 | 2020-02-10 | P/FBW/MDS/6051339/2020 | 2020-05-19 | SOSurrenderedbyATCbasisonsyama9/4/2019 Location changed - Old 4Jun'21 | SVPT17
384 | TARA27 | TARA27 | Chennai | Chennai |  | CHN | TVI | ATTNCHN1996 | - | Nominals with issues | Dropped-Canb. | 2019-10-14 | TARA27 | 4G_FD900_TARA27 | 4G_FD2100_TARA27 | 4G_TD_TARA27 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020360929 | 2020360929 | P/FVC/MDS/6051391/2020 | 2020-05-19 | 2020361104 | 2020-02-10 | P/FVC/MDS/6050734/2020 | 2020-05-19 | ST202106358291 | 2021-06-23 | P/FVC/MDS/1055873/2021 | 2021-09-04 | 2020361299 | 2020-02-10 | P/FBW/MDS/6050986/2020 | 2020-05-19 | TDD added after Syama confirmation Toco Chnged from ATC to Srigom confirmed by syama 5/8/2019/ TOCO Chamged Confirmed by syama TVI Surrender SO , mail from Antony - 2-Jun'21 | TARA27
385 | TRUMA9 | TRUMA9 | Chennai | Chennai |  | CHN | TVI | ATTNCHN2005 | - | Nominals with issues | On air | 2019-12-31 | TRUMA9 | 4G_FD900_TRUMA9 | 4G_FD2100_TRUMA9 | 4G_TD_TRUMA9 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020360936 | 2020360936 | P/FVC/MDS/6051398/2020 | 2020-05-19 | 2020361206 | 2020-02-10 | P/FVC/MDS/6050904/2020 | 2020-05-19 | ST202106358297 | 2021-06-23 | P/FVC/MDS/1055875/2021 | 2021-09-04 | 2020361401 | 2020-02-10 | P/FBW/MDS/6130430/2020 | 2020-09-18 | 0 | TRUMA9
386 | TVLR51 | TVLR51 | Thiruvallur | Chennai |  | ROTN | Indus | IN-1369733 | R/NN-366791 | Nominals with issues | Dropped | 2019-09-27 | TVLR51 | 4G_FD900_TVLR51 | 4G_FD2100_TVLR51 | 4G_TD_TVLR51 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363107 | 2021-06-26 | P/FVC/MDS/1050098/2021 | 2021-08-09 | 2020361553 | 2020-02-10 | P/FVC/MDS/6050837/2020 | 2020-05-19 |  |  |  |  | 2020361352 | 2020-02-10 | P/FBW/MDS/6051039/2020 | 2020-05-19 | LiteplusSRwithdrawnandpunchedasTransitional/R/NN-339682SOwithdrwalduetoindusnotaquiredbyjawhar8/27/2019/TocoChangedfromatctoindusconfirmedbysyama9/5/2019 | TVLR51
387 | UMPT21 | UMPT21 | Tiruppur | Coimbatore |  | ROTN | ATC | TN/CO/AT/21610 | T19TN08586 | Nominals with issues | Dropped-Canb. | 2020-01-23 | UMPT21 | 4G_FD900_UMPT21 | 4G_FD2100_UMPT21 | 4G_TD_UMPT21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363132 | 2021-06-26 | P/FVC/MDS/1050103/2021 | 2021-08-09 | 2020361559 | 2020-02-10 | P/FVC/MDS/6050839/2020 | 2020-05-19 |  |  |  |  | 2020361340 | 2020-02-10 | P/FBW/MDS/6051027/2020 | 2020-05-19 | ATTNTPR1981soWithdrwanbyTVIanalocatedtoatccomfirmedbysyama8/21/2019 | UMPT21
388 | UMPT24 | UMPT24 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1371162 | R/NN-370188 | Nominals with issues | SR | 2019-11-14 | UMPT24 | 4G_FD900_UMPT24 | 4G_FD2100_UMPT24 | 4G_TD_UMPT24 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363145 | 2021-06-26 | P/FVC/MDS/1050105/2021 | 2021-08-09 | 2020328042 | 2020-01-16 | P/FVC/MDS/6049430/2020 | 2020-05-19 |  |  |  |  | 2020328216 | 2020-01-16 | P/FBW/MDS/6049548/2020 | 2020-05-19 | AmendedSOGivenduetoAGLconversionconfirmedbysyama3/4/2019/ATCsurrenderedSOsonSep20 | UMPT24
389 | HAST14 | HAST14 | Chennai | Chennai |  | CHN | Airtel |  |  | Nominal WIP | Dropped-Canb. | - | HAST14 | 4G_FD900_HAST14 | 4G_FD2100_HAST14 | 4G_TD_HAST14 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202102071739 | 2021-02-27 | P/FVC/MDS/1012322/2021 | 2021-03-13 | 2020328165 | 2020-01-16 | P/FVC/MDS/6049497/2020 | 2020-05-19 | ST202106358314 | 2021-06-23 | P/FVC/MDS/1055882/2021 | 2021-09-04 | 2020328251 | 2020-01-16 | P/FBW/MDS/6049583/2020 | 2020-05-19 | SO Surrendered by ATC and canceled by SCM on Dec 10, 2020
390 | WOODLD | WOODLD | Chennai | Chennai |  | CHN | Airtel |  |  | Nominal WIP | Dropped-Not Req. Bsns | - | WOODLD | 4G_FD900_WOODLD | 4G_FD2100_WOODLD | 4G_TD_WOODLD | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020360225 | 2020360225 | P/FVC/MDS/6051081/2020 | 2020-05-19 | 2020360272 | 2020-02-10 | P/FVC/MDS/6051128/2020 | 2020-05-19 | ST202106358361 | 2021-06-23 | P/FVC/MDS/1055889/2021 | 2021-09-04 | 2020360310 | 2020-02-10 | P/FBW/MDS/6051166/2020 | 2020-05-19 | Tagged from SO to SR as per Sathish Mail - 2Jul21 | WOODLD
391 | CMCHN2 | CMCHN2 | Vellore | Vellore |  | ROTN | Indus |  |  | Nominal WIP | On Air |  | CMCHN2 | 4G_FD900_CMCHN2 | 4G_FD2100_CMCHN2 | 4G_TD_CMCHN2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371893 | 2021-07-03 | P/FVC/MDS/1051819/2021 | 2021-08-15 | 2020329902 | 2020-01-24 | P/FVC/MDS/6049078/2020 | 2020-05-19 | ST202206156716 | 2022-06-02 | P/FVC/MDS/1082480/2022 | 2022-06-14 | ST202106359713 | 2021-06-24 | P/FBW/MDS/1051759/2021 | 2021-08-15 | 0
392 | DGL78 | DGL078 | Dindigul | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | SR | 2020-02-02 | DGL078 | 4G_FD900_DGL078 | 4G_FD2100_DGL078 | 4G_TD_DGL078 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371894 | 2021-07-03 | P/FVC/MDS/1051820/2021 | 2021-08-15 | 2020360400 | 2020-02-10 | P/FVC/MDS/6051220/2020 | 2020-05-19 |  |  |  |  | 2020360410 | 2020-02-10 | P/FBW/MDS/6051230/2020 | 2020-05-19 | 20-20-TopTowns0.8Validation | DGL78
393 | MUSI8 | MUSI08 | Tiruchirappalli | Trichy |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2020-02-02 | MUSI08 | 4G_FD900_MUSI08 | 4G_FD2100_MUSI08 | 4G_TD_MUSI08 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371961 | 2021-03-07 | P/FVC/MDS/1051615/2021 | 2021-08-14 | 2020360399 | 2020-02-10 | P/FVC/MDS/6051219/2020 | 2020-05-19 |  |  |  |  | 2020360409 | 2020-02-10 | P/FBW/MDS/6051229/2020 | 2020-05-19 | 20-20-RestofUrban/PrioritychangedfromP1toP07/14/2020 | MUSI8
394 | MLKCL5 | MLKCL5 | Chennai | Chennai |  | CHN | Indus | R/RES-418865 | 0 | Nominal WIP |  | 2019-11-22 | MLKCL5 | 4G_FD900_MLKCL5 | 4G_FD2100_MLKCL5 | 4G_TD_MLKCL5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2019402477 |  | P/FBW/MDS/6047753/2020 | 2020-05-19 | 2019402485 | 2020-01-02 | P/FBW/MDS/6047761/2020 | 2020-05-19 | 2019402481 | 2020-01-02 | P/FBW/MDS/6047757/2020 | 2020-05-19 | 2019402489 | 2020-01-02 | P/FBW/MDS/6047765/2020 | 2020-05-19 |  | MLKCL5
395 | PADI14 | PADI14 | Chennai | Chennai |  | CHN | CNIL | 0 | 0 | Nominal WIP |  | 2019-11-19 | PADI14 | 4G_FD900_PADI14 | 4G_FD2100_PADI14 | 4G_TD_PADI14 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2019402479 |  | P/FBW/MDS/6047755/2020 | 2020-05-19 | 2019402487 | 2020-01-02 | P/FBW/MDS/6047763/2020 | 2020-05-19 | 2019402483 | 2020-01-02 | P/FBW/MDS/6047759/2020 | 2020-05-19 | 2019402491 | 2020-01-02 | P/FBW/MDS/6047767/2020 | 2020-05-19 |  | PADI14
396 | ANNA28 | ANNA28 | Chennai | Chennai |  | CHN | Indus | R/NN-379142 | 0 | Nominal WIP |  | 2019-12-23 | ANNA28 | 4G_FD900_ANNA28 | 4G_FD2100_ANNA28 | 4G_TD_ANNA28 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020329887 |  | P/FVC/MDS/6049063/2020 | 2020-05-19 | 2020329932 | 2020-01-24 | P/FVC/MDS/6049108/2020 | 2020-05-19 | 2020329915 | 2020-01-24 | P/FVC/MDS/6049091/2020 | 2020-05-19 | 2020329968 | 2020-01-24 | P/FBW/MDS/6049144/2020 | 2020-05-19 |  | ANNA28
397 | VEERA4 | VEERA4 | Chennai | Chennai |  | CHN | Indus | R/RES-421605 | 0 | Nominal WIP |  | 2020-03-20 | VEERA4 | 4G_FD900_VEERA4 | 4G_FD2100_VEERA4 | 4G_TD_VEERA4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020383762 |  | P/FVC/MDS/6086570/2020 | 2020-06-11 | 2020329949 | 2020-01-24 | P/FVC/MDS/6049125/2020 | 2020-05-19 | 2020383797 | 2020-02-24 | P/FVC/MDS/6086485/2020 | 2020-06-11 | 2020329987 | 2020-01-24 | P/FBW/MDS/6049163/2020 | 2020-05-19 |  | VEERA4
398 | SLM339 | SLM339 |  |  |  | ROTN | Indus | R/NN-369149 |  |  |  | 2019-10-22 | SLM339 | 4G_FD900_SLM339 | 4G_FD2100_SLM339 | 4G_TD_SLM339 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108410881 | 2021-08-06 | P/FVC/MDS/1052912/2021 | 2021-08-20 | 2019647131 | 2020-01-02 | P/FVC/MDS/6047319/2020 | 2020-05-19 | 2019647153 | 2020-01-02 | P/FVC/MDS/6047341/2020 | 2020-05-19 | 2019647317 | 2020-01-02 | P/FBW/MDS/6047405/2020 | 2020-05-19 |  | SLM339
399 | MDU413 | MDU413 |  |  |  | ROTN | Indus | R/NN-383244 |  |  |  | 2020-01-21 | MDU413 | 4G_FD900_MDU413 | 4G_FD2100_MDU413 | 4G_TD_MDU413 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533380 | 2021-09-25 | P/FVC/MDS/1062979/2021 | 2021-10-01 | 2020332485 | 2020-01-24 | P/FVC/MDS/6049227/2020 | 2020-05-19 | 2020332589 | 2020-01-24 | P/FVC/MDS/6049331/2020 | 2020-05-19 | 2020332567 | 2020-01-24 | P/FBW/MDS/6049309/2020 | 2020-05-19 |  | MDU413
400 | DPI36 | DPI036 | Dharmapuri | Vellore |  | ROTN | ATC | TN/DH/AT/20730 | T18TN06092 | Nominals with issues | Dropped-Canb. | 2019-10-24 | DPI036 | 4G_FD900_DPI036 | 4G_FD2100_DPI036 | 4G_TD_DPI036 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362257 | 2021-06-25 | P/FVC/MDS/1049933/2021 | 2021-08-09 | 2019693920 | 2019-11-28 | P/FBW/MDS/5913351/2019 | 2019-12-18 |  |  |  |  | 2019693932 | 2019-11-28 | P/FBW/MDS/5913263/2019 | 2019-12-18 | 0 | DPI36
401 | ANAK15 | ANAK15 | Chennai | Chennai |  | CHN | ATC | TN/CH/AT/20848 | T19TN02884 | Nominals with issues | Dropped-Canb. | 2019-09-24 | ANAK15 | 4G_FD900_ANAK15 | 4G_FD2100_ANAK15 | 4G_TD_ANAK15 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2020383763 |  | P/FVC/MDS/6086571/2020 | 2020-06-11 | 2019617505 | 2019-12-03 | P/FVC/MDS/5893364/2019 | 2019-12-10 | ST202106358153 | 2021-06-23 | P/FVC/MDS/1055845/2021 | 2021-09-04 | 2019617664 | 2019-12-03 | P/FBW/MDS/5893514/2019 | 2019-12-10 | TDD added after Syama confirmation | ANAK15
402 | CDLR63 | CDLR63 | Cuddalore | Trichy |  | ROTN | Indus | IN-1388152 | R/NN-464553 | Nominals with issues | SO | 2020-08-16 | CDLR63 | 4G_FD900_CDLR63 | 4G_FD2100_CDLR63 | 4G_TD_CDLR63 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361980 | 2021-06-25 | P/FVC/MDS/1049927/2021 | 2021-08-09 | 2019617476 | 2019-12-03 | P/FVC/MDS/5893335/2019 | 2019-12-10 |  |  |  |  | 2019617896 | 2019-12-03 | P/FBW/MDS/5893681/2019 | 2019-12-10 | Partof461sitesSyamaMay'30/ATCcanceledSOonAug6andchangedtoIndus | CDLR63
403 | MUGA16 | MUGA16 | Chennai | Chennai |  | CHN | Airtel | MUGA16 | - | Nominals with issues | Dropped-Canb. | 2021-02-18 | MUGA16 | 4G_FD900_MUGA16 | 4G_FD2100_MUGA16 | 4G_TD_MUGA16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2019617419 |  | P/FVC/MDS/5893274/2019 | 2019-12-10 | 2019617543 | 2019-12-03 | P/FVC/MDS/5893393/2019 | 2019-12-10 | ST202106358263 | 2021-06-23 | P/FVC/MDS/1055860/2021 | 2021-09-04 | 2019617809 | 2019-12-03 | P/FBW/MDS/5893659/2019 | 2019-12-10 | Surrendered by Own on July 7, 2020 and changed to Ascend. Changed from Ascend to Own on Dec 10 basis Arvind's confirmation
404 | NEEL31 | NEEL31 | Chennai | Chennai |  | CHN | TVI | ATTNCHN1995 | - | Nominals with issues | SO | 2019-10-09 | NEEL31 | 4G_FD900_NEEL31 | 4G_FD2100_NEEL31 | 4G_TD_NEEL31 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2019617414 |  | P/FVC/MDS/5893277/2019 | 2019-12-10 | 2019617538 | 2019-12-03 | P/FVC/MDS/5893388/2019 | 2019-12-10 | ST202106358264 | 2021-06-23 | P/FVC/MDS/1055861/2021 | 2021-09-04 | 2019617804 | 2019-12-03 | P/FBW/MDS/5893654/2019 | 2019-12-10 | TDD added after Syama confirmation | NEEL31
405 | SLM273 | SLM273 | Salem | Vellore |  | ROTN | Airtel | SLM273 | - | Nominals with issues | Dropped-Canb. | 2019-09-19 | SLM273 | 4G_FD900_SLM273 | 4G_FD2100_SLM273 | 4G_TD_SLM273 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362774 | 2021-06-26 | P/FVC/MDS/1050040/2021 | 2021-08-09 | 2019617429 | 2019-12-03 | P/FVC/MDS/5893288/2019 | 2019-12-10 |  |  |  |  | 2019617700 | 2019-12-03 | P/FBW/MDS/5893550/2019 | 2019-12-10 | R/NN-322997withdrwanandbookedastransitionalbasisionjawhar3/27/2019//TransitionaSR-R/NN-328781withdrawnandbookedasLiteplus/R/NN-347073SRWithdrwanTocoChangedfromindustoownbasisonsentamil9/19/2019/SRtoSOconfirmedbysentamil10/11/2019/PrioritychangedfromP1toP07/14/2020 | SLM273
406 | TIVR27 | TIVR27 | Thiruvarur | Trichy |  | ROTN | Indus | IN-1369376 | R/NN-365887 | Nominals with issues | SR | 2019-10-14 | TIVR27 | 4G_FD900_TIVR27 | 4G_FD2100_TIVR27 | 4G_TD_TIVR27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362810 | 2021-06-26 | P/FVC/MDS/1050067/2021 | 2021-08-09 | 2019664241 | 2019-12-03 | P/FVC/MDS/5894357/2019 | 2019-12-10 |  |  |  |  | 2019647045 | 2020-01-02 | P/FBW/MDS/6048078/2020 | 2020-05-19 | FreshSRWithdrawnbyATC8/22/2019 | TIVR27
407 | CIMR5 | CIMR05 | Theni | Madurai |  | ROTN | ATC |  |  | Nominal WIP | On Air | 2019-09-14 | CIMR05 | 4G_FD900_CIMR05 | 4G_FD2100_CIMR05 | 4G_TD_CIMR05 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202110553066 | 2021-10-07 | P/FVC/MDS/1063632/2021 | 2021-10-22 | 2019617480 | 2019-12-03 | P/FVC/MDS/5893339/2019 | 2019-12-10 | 2020361019 | 2020-02-10 | P/FVC/MDS/6050889/2020 | 2020-05-19 | 2019617900 | 2019-12-03 | P/FBW/MDS/5893685/2019 | 2019-12-10 | MDUZone-List2/Changedfromp2top1basismarketingconfirmationonJun21st'19 | CIMR5
408 | SVKI58 | SVKI58 | Virudhunagar | Sivakasi |  | ROTN | Airtel |  |  | Nominal WIP | On Air | 2019-09-19 | SVKI58 | 4G_FD900_SVKI58 | 4G_FD2100_SVKI58 | 4G_TD_SVKI58 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585119 | 2021-11-09 | P/FVC/MDS/1068100/2021 | 2021-12-08 | 2019617447 | 2019-12-03 | P/FVC/MDS/5893306/2019 | 2019-12-10 |  |  |  |  | ST202011141292 | 2020-11-09 | P/FBW/MDS/1006423/2020 | 2020-11-28 | Partof461sitesSyamaMay'30 | SVKI58
409 | MUPET4 | MUPET4 |  |  |  | ROTN | Indus | R/RES-418210 |  |  |  | 2019-11-11 | MUPET4 | 4G_FD900_MUPET4 | 4G_FD2100_MUPET4 | 4G_TD_MUPET4 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202110559380 | 2021-10-14 | P/FVC/MDS/1063730/2021 | 2021-10-22 | 2019664347 | 2019-12-03 | P/FVC/MDS/5894446/2019 | 2019-12-10 | 2019664377 | 2019-12-03 | P/FVC/MDS/5894476/2019 | 2019-12-10 | 2020397253 | 2020-03-06 | P/FBW/MDS/6071319/2020 | 2020-05-29 |  | MUPET4
410 | MDU389 | MDU389 | Madurai | Madurai |  | ROTN | Indus | IN-1367655 | R/NN-357354 | Nominals with issues | Dropped-Canb. | 2019-08-24 | MDU389 | 4G_FD900_MDU389 | 4G_FD2100_MDU389 | 4G_TD_MDU389 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362370 | 2021-06-25 | P/FVC/MDS/1049985/2021 | 2021-08-09 | 2019892280 | 2019-08-30 | P/FVC/MDS/5826812/2019 | 2019-10-03 |  |  |  |  | 2019617866 | 2019-12-03 | P/FBW/MDS/5893751/2019 | 2019-12-10 | Partof461sitesSyamaMay'30/R/NN-346181SRWithdrwanandrebokedbasisonjawhar8/2/2019 | MDU389
411 | RMPM27 | RMPM27 | Ramanathapuram | Madurai |  | ROTN | Indus | IN-1366152 | R/NN-347761 | Nominals with issues | SR | 2019-07-25 | RMPM27 | 4G_FD900_RMPM27 | 4G_FD2100_RMPM27 | 4G_TD_RMPM27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362768 | 2021-06-26 | P/FVC/MDS/1050034/2021 | 2021-08-09 | 2019843315 | 2019-07-29 | P/FVC/MDS/5793716/2019 | 2019-08-29 |  |  |  |  | ST202102037959 | 2021-02-04 | P/FBW/MDS/1010695/2021 | 2021-02-23 | Partof461sitesSyamaMay'30/PrioritychangedfromP1toP07/14/2020 | RMPM27
412 | PERYA8 | PERYA8 | Chennai | Chennai |  | CHN | Indus | IN-1365598 | R/NN-347701 | Nominals with issues | Dropped-Canb. | 2019-07-09 | PERYA8 | 4G_FD900_PERYA8 | 4G_FD2100_PERYA8 | 4G_TD_PERYA8 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2019820111 |  | P/FVC/MDS/5790948/2019 | 2019-08-28 | 2019821009 | 2019-07-10 | P/FVC/MDS/5790983/2019 | 2019-08-28 | ST202106358268 | 2021-06-23 | P/FVC/MDS/1055865/2021 | 2021-09-04 | 2019821081 | 2019-07-10 | P/FBW/MDS/5790976/2019 | 2019-08-28 | 0 | PERYA8
413 | TNV33 | TNV033 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/21264 | T19TN04496 | Nominals with issues | Dropped-Canb. | 2019-07-18 | TNV033 | 4G_FD900_TNV033 | 4G_FD2100_TNV033 | 4G_TD_TNV033 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362867 | 2021-06-26 | P/FVC/MDS/1050079/2021 | 2021-08-09 | 2019834328 | 2019-07-24 | P/FVC/BGL/5780881/2019 | 2019-08-23 |  |  |  |  | 2019123501 | 2019-07-24 | P/AVC/BGL/5780881/2019 | 2019-08-23 | Partof461sitesSyamaMay'30 | TNV33
414 | UMPT33 | UMPT33 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1364735 | R/NN-344906 | Nominals with issues | Dropped-Canb. | 2019-06-27 | UMPT33 | 4G_FD900_UMPT33 | 4G_FD2100_UMPT33 | 4G_TD_UMPT33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363146 | 2021-06-26 | P/FVC/MDS/1050106/2021 | 2021-08-09 | 2019997994 | 2019-06-27 | P/FVC/MDS/5728014/2019 | 2019-07-22 |  |  |  |  | ST202102037983 | 2021-02-04 | P/FBW/MDS/1010705/2021 | 2021-02-23 | Partof461sitesSyamaMay'30 | UMPT33
415 | ARAK54 | ARAK54 |  |  |  | ROTN | ATC | - |  |  |  | 24/5/2019 | ARAK54 | 4G_FD900_ARAK54 | 4G_FD2100_ARAK54 | 4G_TD_ARAK54 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2019998306 |  | P/FVC/MDS/5728080/2019 | 2019-07-22 | 2019998306 | 2019-06-27 | P/FVC/MDS/5728080/2019 | 2019-07-22 | 2019998488 | 2019-07-01 | P/FVC/MDS/5728084/2019 | 2019-07-22 | 2019999325 | 2019-07-02 | P/FBW/MDS/5750575/2019 | 2019-07-31 |  | ARAK54
416 | TNJ105 | TNJ105 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/21320 | T19TN04552 | Nominals with issues | On Air | 2019-06-12 | TNJ105 | 4G_FD900_TNJ105 | 4G_FD2100_TNJ105 | 4G_TD_TNJ105 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362857 | 2021-06-26 | P/FVC/MDS/1050073/2021 | 2021-08-09 | 2019972308 | 2019-06-13 | P/FVC/MDS/5720314/2019 | 2019-07-18 |  |  |  |  | ST202007023171 | 2020-07-13 | P/FBW/MDS/1000629/2020 | 2020-07-18 | Partof461sitesSyamaMay'30 | TNJ105
417 | TTPTU2 | TTPTU2 | Cuddalore | Trichy |  | ROTN | Indus | IN-1363771 | R/NN-337819 | Nominals with issues |  | 2019-06-12 | TTPTU2 | 4G_FD900_TTPTU2 | 4G_FD2100_TTPTU2 | 4G_TD_TTPTU2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371822 | 2021-07-03 | P/FVC/MDS/1051793/2021 | 2021-08-15 | 2019969302 | 2019-06-11 | P/FVC/MDS/5720319/2019 | 2019-07-18 |  |  |  |  | ST202106359632 | 2021-06-24 | P/FBW/MDS/1051749/2021 | 2021-08-15 | 0 | TTPTU2
418 | TVLR49 | TVLR49 | Thiruvallur | Chennai |  | ROTN | Indus | IN-1361404 | R/NN-331466 | Nominals with issues |  | 2019-05-02 | TVLR49 | 4G_FD900_TVLR49 | 4G_FD2100_TVLR49 | 4G_TD_TVLR49 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106363098 | 2021-06-26 | P/FVC/MDS/1050097/2021 | 2021-08-09 | 2019905131 | 2019-05-02 | P/FVC/MDS/5652737/2019 | 2019-06-13 |  |  |  |  | ST202007023054 | 2020-07-13 | P/FBW/MDS/1000632/2020 | 2020-07-18 | R/NN-321317withdrwanandbokkedastransitinalbasisonjawhar3/18/2019/R/NN-326886SPrejectedbookedas30Mbasisonjawhar4/11/2019 | TVLR49
419 | PLCH33 | PLCH33 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/20912 | T19TN02948 | Nominals with issues | On Air | 2019-05-13 | PLCH33 | 4G_FD900_PLCH33 | 4G_FD2100_PLCH33 | 4G_TD_PLCH33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362737 | 2021-06-26 | P/FVC/MDS/1050022/2021 | 2021-08-09 | 2019928066 | 2019-05-14 | P/FVC/MDS/5646902/2019 | 2019-06-10 |  |  |  |  | ST202102037984 | 2021-02-04 | P/FBW/MDS/1010706/2021 | 2021-02-23 | 0 | PLCH33
420 | RJPM40 | RJPM40 | Virudhunagar | Madurai |  | ROTN | Airtel | RJPM40 | - | Nominals with issues | SO | 2019-04-24 | RJPM40 | 4G_FD900_RJPM40 | 4G_FD2100_RJPM40 | 4G_TD_RJPM40 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362767 | 2021-06-26 | P/FVC/MDS/1050033/2021 | 2021-08-09 | 2019797746 | 2019-04-30 | P/FVC/MDS/5643250/2019 | 2019-06-07 |  |  |  |  | ST202012176642 | 2020-12-17 | P/FBW/MDS/1007862/2020 | 2020-12-29 | SOCanceledbyATConSep12,2020(Muthusir/Arulmail)andgiventoowntoco
421 | TIVR14 | TIVR14 | Thiruvarur | Thiruvarur |  | ROTN | ATC |  |  | Nominal WIP | Dropped | 2019-04-09 | TIVR14 | 4G_FD900_TIVR14 | 4G_FD2100_TIVR14 | 4G_TD_TIVR14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107371971 | 2021-07-03 | P/FVC/MDS/1051625/2021 | 2021-08-14 | 2019757047 | 2019-04-16 | P/FBW/MDS/5602260/2019 | 2019-05-20 | ST202107388492 | 2021-07-19 | P/FVC/MDS/1056677/2021 | 2021-09-08 | ST202007023170 | 2020-07-13 | P/FBW/MDS/1000628/2020 | 2020-07-18 | 0 | TIVR14
422 | ANNA22 | ANNA22 | Chennai | Chennai |  | CHN | Indus | IN-1305398 | R/RES-411690 | Nominals with issues | Dropped-Canb. | 2019-05-03 | ANNA22 | 4G_FD900_ANNA22 | 4G_FD2100_ANNA22 | 4G_TD_ANNA22 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202107396920 | 2021-07-26 | P/FVC/MDS/1052735/2021 | 2021-08-20 | 2019587023 | 2019-03-11 | P/FBW/MDS/5541753/2019 | 2019-04-23 | ST202106358166 | 2021-06-23 | P/FVC/MDS/1055846/2021 | 2021-09-04 | 2019584400 | 2019-03-08 | P/FBW/MDS/5544680/2019 | 2019-04-23 | 0 | ANNA22
423 | KDKL25 | KDKL25 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/20674 | T18TN06036 | Nominals with issues | On Air | 2019-02-20 | KDKL25 | 4G_FD900_KDKL25 | 4G_FD2100_KDKL25 | 4G_TD_KDKL25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362304 | 2021-06-25 | P/FVC/MDS/1049956/2021 | 2021-08-09 | 2019300834 | 2019-01-02 | P/FVC/MDS/5432027/2019 | 2019-03-05 |  |  |  |  | ST202102038130 | 2021-02-04 | P/FBW/MDS/1010707/2021 | 2021-02-23 | 0 | KDKL25
424 | ERD96 | ERD096 |  |  |  | ROTN | ATC | TPS |  |  |  | 2016-08-25 | ERD096 | 4G_FD900_ERD096 | 4G_FD2100_ERD096 | 4G_TD_ERD096 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | 2016655777 |  | P/FVC/MDS/3650861/2016 | 2016-11-25 | 2018439962 | 2018-10-23 | P/FBW/MDS/5235388/2018 | 2018-12-05 | 2019303192 | 2019-01-03 | P/FVC/MDS/5329977/2019 | 2019-01-22 | 2019315794 | 2019-01-07 | P/FBW/MDS/5391379/2019 | 2019-02-18 |  | ERD96
425 | TIR337 | TIR337 | Tiruppur | Coimbatore |  | ROTN | ATC |  |  | Nominal WIP | Dropped-Canb. | 2018-09-28 | TIR337 | 4G_FD900_TIR337 | 4G_FD2100_TIR337 | 4G_TD_TIR337 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371874 | 2021-07-03 | P/FVC/MDS/1051813/2021 | 2021-08-15 | 2018416234 | 2018-10-09 | P/FBW/MDS/5226961/2018 | 2018-11-28 | ST202101005327 | 2021-01-08 | P/FVC/MDS/1009111/2021 | 2021-01-17 | ST202106359672 | 2021-06-24 | P/FBW/MDS/1051753/2021 | 2021-08-15 | 0 | TIR337
426 | LBROA5 | LBROA5 | Chennai | Chennai |  | CHN | Indus | R/RES-373354 | 0 | Nominal WIP |  | 2017-09-15 | LBROA5 | 4G_FD900_LBROA5 | 4G_FD2100_LBROA5 | 4G_TD_LBROA5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498643 | 2021-08-31 | P/FVC/MDS/1060434/2021 | 2021-09-13 | 2018558248 | 2018-02-28 | P/FBW/MDS/4735460/2018 | 2018-03-22 | ST202108413666 | 2021-08-09 | P/FVC/MDS/1055939/2021 | 2021-09-05 | 2017252172 | 2017-12-01 | P/FBW/MDS/4530195/2017 | 2017-12-19 |  | LBROA5
427 | TNV50 | TNV050 |  |  |  | ROTN | Indus | R/RES-382175 |  |  |  | 2017-11-22 | TNV050 | 4G_FD900_TNV050 | 4G_FD2100_TNV050 | 4G_TD_TNV050 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2017280405 |  | P/FBW/MDS/4553842/2018 | 2018-01-04 | 2017280585 | 2017-12-15 | P/FBW/MDS/4553901/2018 | 2018-01-04 | 2017280530 | 2017-12-15 | P/FBW/MDS/4553859/2018 | 2018-01-04 | 2019317073 | 2019-01-07 | P/FBW/MDS/5391415/2019 | 2019-02-18 |  | TNV50
428 | KMGLM3 | KMGLM3 |  |  |  | ROTN | Indus | R/NN-270683 |  |  |  | 2017-07-10 | KMGLM3 | 4G_FD900_KMGLM3 | 4G_FD2100_KMGLM3 | 4G_TD_KMGLM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2017633252 |  | P/FVC/MDS/4224922/2017 | 2017-07-28 | 2017670034 | 2017-08-02 | P/FBW/MDS/4268780/2017 | 2017-08-24 | 2017669342 | 2017-08-01 | P/FVC/MDS/4657990/2018 | 2018-02-23 | 2017252332 | 2017-12-01 | P/FBW/MDS/4525827/2017 | 2017-12-19
429 | ONGUR2 | ONGUR2 |  |  |  | ROTN | Indus | R/RES-369709 |  |  |  | 2017-06-22 | ONGUR2 | 4G_FD900_ONGUR2 | 4G_FD2100_ONGUR2 | 4G_TD_ONGUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2017633170 |  | P/FVC/MDS/4224813/2017 | 2017-07-28 | 2017670169 | 2017-08-02 | P/FBW/MDS/4268785/2017 | 2017-08-24 | 2017669364 | 2017-08-01 | P/FBC/MDS/4657995/2018 | 2018-02-23 | 2017252318 | 2017-12-01 | P/FBW/MDS/4525824/2017 | 2017-12-19
430 | TKPLI2 | TKPLI2 |  |  |  | ROTN | Indus | R/RES-369687 |  |  |  | 2017-06-22 | TKPLI2 | 4G_FD900_TKPLI2 | 4G_FD2100_TKPLI2 | 4G_TD_TKPLI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2017633108 |  | P/FBC/MDS/4224705/2017 | 2017-07-28 | 2017670603 | 2017-08-02 | P/FBW/MDS/4269527/2017 | 2017-08-24 | 2017669403 | 2017-08-01 | P/FVC/MDS/4658004/2018 | 2018-02-23 | 2017252302 | 2017-12-01 | P/FBW/MDS/4525821/2017 | 2017-12-19
431 | AWKCI2 | AWKCI2 |  |  |  | ROTN | Indus | R/NN-260968 |  |  |  | 2017-01-31 | AWKCI2 | 4G_FD900_AWKCI2 | 4G_FD2100_AWKCI2 | 4G_TD_AWKCI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2016609519 |  | P/FVC/MDS/3555417/2016 | 2016-10-17 | 2017362604 | 2017-01-27 | P/FBW/MDS/3895359/2017 | 2017-03-27 | 2016617068 | 2016-09-23 | P/FVC/MDS/3614531/2016 | 2016-11-08 | 2019315817 | 2019-01-07 | P/FBW/MDS/5391446/2019 | 2019-02-18 |  | AWKCI2
432 | MANPA8 | MANPA8 | Chennai | Chennai |  | CHN | Ascend | 0 | 0 | Nominal WIP |  | 2016-03-07 | MANPA8 | 4G_FD900_MANPA8 | 4G_FD2100_MANPA8 | 4G_TD_MANPA8 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | 2016843551 |  | P/FVC/MDS/3515717/2016 | 2016-09-20 | 2016656097 | 2016-10-15 | P/FBW/MDS/3618388/2016 | 2016-11-09 |  |  |  |  | 2019758122 | 2019-04-16 | P/FBW/MDS/5584451/2019 | 2019-05-15
433 | MDU267 | MDU267 |  |  |  | ROTN | ATC | TPS |  |  |  | 2015-06-10 | MDU267 | 4G_FD900_MDU267 | 4G_FD2100_MDU267 | 4G_TD_MDU267 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2016945675 |  | P/FVC/MDS/3473703/2016 | 2016-08-24 | 2016657417 | 2016-10-15 | P/FBW/MDS/3618083/2016 | 2016-11-09 | 2016946405 | 2016-07-06 | P/FVC/MDS/3473743/2016 | 2016-08-24 | 2019316977 | 2019-01-07 | P/FBW/MDS/5391450/2019 | 2019-02-18 |  | MDU267
434 | SLM140 | SLM140 |  |  |  | ROTN | Indus | R/RES-186058 |  |  |  | 2011-11-16 | SLM140 | 4G_FD900_SLM140 | 4G_FD2100_SLM140 | 4G_TD_SLM140 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2012561666 |  | P/FVC/MDS/1860812/2012 | 2012-08-22 | 2016656528 | 2016-10-15 | P/FBW/MDS/3618425/2016 | 2016-11-09 | 2011762606 | 2011-12-11 | P/FVC/MDS/1703656/2011 | 2011-12-14 | 2017256456 | 2017-12-05 | P/FBW/MDS/4531926/2017 | 2017-12-20 |  | SLM140
435 | VILLI9 | VILLI9 | Chennai | Chennai |  | CHN | Indus | R/NN-212122 | 0 | Nominal WIP |  | 2013-11-22 | VILLI9 | 4G_FD900_VILLI9 | 4G_FD2100_VILLI9 | 4G_TD_VILLI9 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2013904553 |  | P/FVC/MDS/2246199/2014 | 2014-01-27 | 2016999639 | 2016-07-21 | P/FBW/MDS/3494896/2016 | 2016-09-06 | 2013904553 | 2013-12-13 | P/FVC/MDS/2246199/2014 | 2014-01-27 | 2017259206 | 2017-12-06 | P/FBW/MDS/4542453/2017 | 2017-12-26
436 | KANVKM | KANVKM | Chennai | Chennai |  | CHN | ATC | TN/KA/AT/22065 |  |  | On air | 2021-07-27 | KANVKM | 4G_FD900_KANVKM | 4G_FD2100_KANVKM | 4G_TD_KANVKM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404983 | 2021-08-02 | P/FVC/MDS/1052802/2021 | 2021-08-20 | ST202108407508 | 2021-08-03 | P/FVC/MDS/1056756/2021 | 2021-09-09 | ST202108413635 | 2021-08-09 | P/FVC/MDS/1055908/2021 | 2021-09-05 | ST202108407158 | 2021-08-03 | P/FBW/MDS/1052844/2021 | 2021-08-20
437 | VILLKR | VILLKR | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3000753 | R/NN-620004 |  |  | 2021-08-09 | VILLKR | 4G_FD900_VILLKR | 4G_FD2100_VILLKR | 4G_TD_VILLKR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430697 | 2021-08-17 | P/FVC/MDS/1059652/2021 | 2021-09-12 | ST202109511386 | 2021-09-07 | P/FVC/MDS/1061433/2021 | 2021-09-15 |  |  |  |  | ST202108430470 | 2021-08-17 | P/FBW/MDS/1056030/2021 | 2021-09-07 | 0
438 | VEMBNR | VEMBNR | Salem | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2021-08-10 | VEMBNR | 4G_FD900_VEMBNR | 4G_FD2100_VEMBNR | 4G_TD_VEMBNR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430733 | 2021-08-17 | P/FVC/MDS/1059679/2021 | 2021-09-12 | ST202108498237 | 2021-08-31 | P/FVC/MDS/1060475/2021 | 2021-09-13 | ST202109512025 | 2021-09-07 | P/FVC/MDS/1061770/2021 | 2021-09-16 | ST202108430515 | 2021-08-17 | P/FBW/MDS/1056073/2021 | 2021-09-07 | 0
439 | PNVAI6 | PNVAI6 | Pudukkottai | Trichy |  | ROTN | ATC |  |  |  | On Air |  | PNVAI6 | 4G_FD900_PNVAI6 | 4G_FD2100_PNVAI6 | 4G_TD_PNVAI6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512245 | 2021-09-07 | P/FVC/MDS/1061437/2021 | 2021-09-15 | ST202109511389 | 2021-09-07 | P/FVC/MDS/1061772/2021 | 2021-09-16 | ST202109530031 | 2021-09-24 | P/FVC/MDS/1063012/2021 | 2021-10-01 | ST202109499943 | 2021-09-01 | P/FBW/MDS/1060688/2021 | 2021-09-13
440 | CHPT54 | CHPT54 | Kancheepuram | Chennai |  | ROTN | Indus | IN-3009971 | R/NN-626479 |  |  | 2021-08-23 | CHPT54 | 4G_FD900_CHPT54 | 4G_FD2100_CHPT54 | 4G_TD_CHPT54 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512246 | 2021-09-07 | P/FVC/MDS/1061696/2021 | 2021-09-16 | ST202109511390 | 2021-09-07 | P/FVC/MDS/1061773/2021 | 2021-09-16 |  |  |  |  | ST202109499944 | 2021-09-01 | P/FBW/MDS/1060689/2021 | 2021-09-13
441 | KEELYR | KEELYR | Thiruvarur | Trichy |  | ROTN | Indus | IN-3007559 | R/NN-626220 |  | On Air | 2021-08-23 | KEELYR | 4G_FD900_KEELYR | 4G_FD2100_KEELYR | 4G_TD_KEELYR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512247 | 2021-09-07 | P/FVC/MDS/1061697/2021 | 2021-09-16 | ST202109511391 | 2021-09-07 | P/FVC/MDS/1061774/2021 | 2021-09-16 |  |  |  |  | ST202109499945 | 2021-09-01 | P/FBW/MDS/1060690/2021 | 2021-09-13
442 | AGLM10 | AGLM10 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3021186 | R/NN-627499 |  | On Air | 2021-08-26 | AGLM10 | 4G_FD900_AGLM10 | 4G_FD2100_AGLM10 | 4G_TD_AGLM10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512248 | 2021-09-07 | P/FVC/MDS/1061698/2021 | 2021-09-16 | ST202109511392 | 2021-09-07 | P/FVC/MDS/1061775/2021 | 2021-09-16 |  |  |  |  | ST202109499946 | 2021-09-01 | P/FBW/MDS/1060691/2021 | 2021-09-13
443 | TIR473 | TIR473 |  |  |  | ROTN | Indus | IN-3000297 | R/NN-618714 |  |  | 2021-08-26 | TIR473 | 4G_FD900_TIR473 | 4G_FD2100_TIR473 | 4G_TD_TIR473 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504532 | 2021-09-02 | P/FVC/MDS/1060763/2021 | 2021-09-13 | ST202109511412 | 2021-09-07 | P/FVC/MDS/1061795/2021 | 2021-09-16 | ST202109511999 | 2021-09-07 | P/FVC/MDS/1061742/2021 | 2021-09-16 | ST202109513233 | 2021-09-08 | P/FBW/MDS/1061659/2021 | 2021-09-16
444 | AREVA4 | AREVA4 |  |  |  | ROTN | Indus | IN-3021737 | R/NN-627501 |  |  | 2021-08-26 | AREVA4 | 4G_FD900_AREVA4 | 4G_FD2100_AREVA4 | 4G_TD_AREVA4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504533 | 2021-09-02 | P/FVC/MDS/1060764/2021 | 2021-09-13 | ST202109511413 | 2021-09-07 | P/FVC/MDS/1061796/2021 | 2021-09-16 | ST202109512000 | 2021-09-07 | P/FVC/MDS/1061743/2021 | 2021-09-16 | ST202109513234 | 2021-09-08 | P/FBW/MDS/1061660/2021 | 2021-09-16
445 | TNJ121 | TNJ121 | Thanjavur | Trichy |  | ROTN | Indus | IN-3000981 | R/NN-619987 |  | On Air | 2021-08-31 | TNJ121 | 4G_FD900_TNJ121 | 4G_FD2100_TNJ121 | 4G_TD_TNJ121 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512249 | 2021-09-07 | P/FVC/MDS/1061699/2021 | 2021-09-16 | ST202109511393 | 2021-09-07 | P/FVC/MDS/1061776/2021 | 2021-09-16 |  |  |  |  | ST202109499947 | 2021-09-01 | P/FBW/MDS/1060692/2021 | 2021-09-13
446 | MDU474 | MDU474 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/22536 | - |  | On Air | 2021-08-31 | MDU474 | 4G_FD900_MDU474 | 4G_FD2100_MDU474 | 4G_TD_MDU474 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512251 | 2021-09-07 | P/FVC/MDS/1061701/2021 | 2021-09-16 | ST202109511395 | 2021-09-07 | P/FVC/MDS/1061778/2021 | 2021-09-16 | ST202212826860 | 2022-12-16 | P/AFC/MDS/1119536/2022 | 2022-12-22 | ST202109499950 | 2021-09-01 | P/FBW/MDS/1060694/2021 | 2021-09-13
447 | TLNYR3 | TLNYR3 | Nagapattinam | Trichy |  | ROTN | ATC | TN/NA/AT/22700 | - |  | On Air | 2021-08-31 | TLNYR3 | 4G_FD900_TLNYR3 | 4G_FD2100_TLNYR3 | 4G_TD_TLNYR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109504514 | 2021-09-02 | P/FVC/MDS/1060751/2021 | 2021-09-13 | ST202109511400 | 2021-09-07 | P/FVC/MDS/1061783/2021 | 2021-09-16 |  |  |  |  | ST202109513221 | 2021-09-08 | P/FBW/MDS/1061439/2021 | 2021-09-15
448 | SPD107 | SPD107 | Kancheepuram | Chennai |  | ROTN | ATC | TN/KA/AT/22717 | - |  | On Air | 2021-09-03 | SPD107 | 4G_FD900_SPD107 | 4G_FD2100_SPD107 | 4G_TD_SPD107 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512254 | 2021-09-07 | P/FVC/MDS/1061704/2021 | 2021-09-16 | ST202109511447 | 2021-09-07 | P/FVC/MDS/1061802/2021 | 2021-09-16 | ST202109512005 | 2021-09-07 | P/FVC/MDS/1061749/2021 | 2021-09-16 | ST202109513243 | 2021-09-08 | P/FBW/MDS/1061669/2021 | 2021-09-16
449 | THRYAL | THRYAL | Thiruvallur | Chennai |  | ROTN | Indus | IN-3007547 | R/NN-626213 |  | On Air | 2021-08-31 | THRYAL | 4G_FD900_THRYAL | 4G_FD2100_THRYAL | 4G_TD_THRYAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610916 | 2021-12-10 | P/FVC/MDS/1069091/2021 | 2021-12-17 | ST202112604926 | 2021-12-07 | P/FVC/MDS/1068836/2021 | 2021-12-15 |  |  |  |  | ST202112609822 | 2021-12-10 | P/FBW/MDS/1068801/2021 | 2021-12-15
450 | MEYYUR | MEYYUR | Thiruvallur | Chennai |  | ROTN | Indus | IN-3008831 | R/NN-626272 |  | On Air | 2021-09-04 | MEYYUR | 4G_FD900_MEYYUR | 4G_FD2100_MEYYUR | 4G_TD_MEYYUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512258 | 2021-09-07 | P/FVC/MDS/1061708/2021 | 2021-09-16 | ST202109511453 | 2021-09-07 | P/FVC/MDS/1061808/2021 | 2021-09-16 | ST202109512009 | 2021-09-07 | P/FVC/MDS/1061753/2021 | 2021-09-16 | ST202109513247 | 2021-09-08 | P/FBW/MDS/1061673/2021 | 2021-09-16
451 | KEELAP | KEELAP | Madurai | Madurai |  | ROTN | Indus | IN-3021090 | R/NN-627477 |  | On Air | 2021-09-04 | KEELAP | 4G_FD900_KEELAP | 4G_FD2100_KEELAP | 4G_TD_KEELAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201013791 | 2022-01-19 | P/FVC/MDS/1071779/2022 | 2022-01-21 | ST202201013814 | 2022-01-19 | P/FVC/MDS/1071794/2022 | 2022-01-24 | ST202109512011 | 2021-09-07 | P/FVC/MDS/1061755/2021 | 2021-09-16 | ST202109513249 | 2021-09-08 | P/FBW/MDS/1061675/2021 | 2021-09-16
452 | MADPAT | MADPAT | Virudhunagar | Madurai |  | ROTN | Indus | IN-3021108 | R/NN-627483 |  | On Air | 2021-09-04 | MADPAT | 4G_FD900_MADPAT | 4G_FD2100_MADPAT | 4G_TD_MADPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512261 | 2021-09-07 | P/FVC/MDS/1061711/2021 | 2021-09-16 | ST202109511456 | 2021-09-07 | P/FVC/MDS/1061811/2021 | 2021-09-16 | ST202109512012 | 2021-09-07 | P/FVC/MDS/1061756/2021 | 2021-09-16 | ST202109513250 | 2021-09-08 | P/FBW/MDS/1061676/2021 | 2021-09-16
453 | PONGA1 | PONGA1 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3021148 | R/NN-627493 |  | On Air | 2021-08-31 | PONGA1 | 4G_FD900_PONGA1 | 4G_FD2100_PONGA1 | 4G_TD_PONGA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109504511 | 2021-09-02 | P/FVC/MDS/1060749/2021 | 2021-09-13 | ST202109511398 | 2021-09-07 | P/FVC/MDS/1061781/2021 | 2021-09-16 |  |  |  |  | ST202109499953 | 2021-09-01 | P/FBW/MDS/1060697/2021 | 2021-09-13
454 | PBLR21 | PBLR21 | Perambalur | Trichy |  | ROTN | Indus | IN-3020051 | R/NN-627440 |  | On Air | 2021-08-31 | PBLR21 | 4G_FD900_PBLR21 | 4G_FD2100_PBLR21 | 4G_TD_PBLR21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512253 | 2021-09-07 | P/FVC/MDS/1061703/2021 | 2021-09-16 | ST202110574100 | 2021-10-28 | P/FVC/MDS/1065814/2021 | 2021-11-16 | ST202109515207 | 2021-09-09 | P/FVC/MDS/1062233/2021 | 2021-09-20 | ST202109499952 | 2021-09-01 | P/FBW/MDS/1060696/2021 | 2021-09-13
455 | RANPR1 | RANPR1 | Viluppuram | Trichy |  | ROTN | Indus | IN-3020040 | R/NN-627438 |  | On Air | 2021-09-03 | RANPR1 | 4G_FD900_RANPR1 | 4G_FD2100_RANPR1 | 4G_TD_RANPR1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512256 | 2021-09-07 | P/FVC/MDS/1061706/2021 | 2021-09-16 | ST202109511451 | 2021-09-07 | P/FVC/MDS/1061806/2021 | 2021-09-16 | ST202109512007 | 2021-09-07 | P/FVC/MDS/1061751/2021 | 2021-09-16 | ST202109513245 | 2021-09-08 | P/FBW/MDS/1061671/2021 | 2021-09-16
456 | PUTHUR | PUTHUR | The Nilgiris | Coimbatore |  | ROTN | Indus | IN-3020032 | R/NN-627436 |  | SO | 2021-08-31 | PUTHUR | 4G_FD900_PUTHUR | 4G_FD2100_PUTHUR | 4G_TD_PUTHUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512252 | 2021-09-07 | P/FVC/MDS/1061702/2021 | 2021-09-16 | ST202109511396 | 2021-09-07 | P/FVC/MDS/1061779/2021 | 2021-09-16 |  |  |  |  | ST202109499951 | 2021-09-01 | P/FBW/MDS/1060695/2021 | 2021-09-13
457 | SHEVAR | SHEVAR | Salem | Vellore |  | ROTN | Airtel | - | - |  | On Air | 2021-09-03 | SHEVAR | 4G_FD900_SHEVAR | 4G_FD2100_SHEVAR | 4G_TD_SHEVAR | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202109512257 | 2021-09-07 | P/FVC/MDS/1061707/2021 | 2021-09-16 | ST202109511452 | 2021-09-07 | P/FVC/MDS/1061807/2021 | 2021-09-16 | ST202109512008 | 2021-09-07 | P/FVC/MDS/1061752/2021 | 2021-09-16 | ST202109513246 | 2021-09-08 | P/FBW/MDS/1061672/2021 | 2021-09-16
458 | AGSTM3 | AGSTM3 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-1531820 | R/NN-559539 | Nominal WIP | SO | 2021-05-21 | AGSTM3 | 4G_FD900_AGSTM3 | 4G_FD2100_AGSTM3 | 4G_TD_AGSTM3 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202107386733 | 2021-07-17 | P/FVC/MDS/1051571/2021 | 2021-08-14 | ST202106333418 | 2021-06-09 | P/FVC/MDS/1060858/2021 | 2021-09-13 | ST202106331618 | 2021-06-08 | P/FVC/MDS/1051505/2021 | 2021-08-14 | ST202106332011 | 2021-06-08 | P/FVC/MDS/1045065/2021 | 2021-07-28 | 0 | AGSTM3
459 | AGSTM4 | AGSTM4 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-1531837 | R/NN-559540 | Nominal WIP | On Air | 2021-05-21 | AGSTM4 | 4G_FD900_AGSTM4 | 4G_FD2100_AGSTM4 | 4G_TD_AGSTM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107386734 | 2021-07-17 | P/FVC/MDS/1051572/2021 | 2021-08-14 | ST202106333520 | 2021-06-09 | P/FVC/MDS/1060874/2021 | 2021-09-13 | ST202106331619 | 2021-06-08 | P/FVC/MDS/1051506/2021 | 2021-08-14 | ST202106332012 | 2021-06-08 | P/FVC/MDS/1045066/2021 | 2021-07-28 | 0 | AGSTM4
460 | CBE822 | CBE822 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1969690 | R/NN-618616 | Nominal WIP |  | 2021-05-21 | CBE822 | 4G_FD900_CBE822 | 4G_FD2100_CBE822 | 4G_TD_CBE822 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371791 | 2021-07-03 | P/FVC/MDS/1051774/2021 | 2021-08-15 | ST202106333521 | 2021-06-09 | P/FVC/MDS/1060875/2021 | 2021-09-13 |  |  |  |  | ST202106332025 | 2021-06-08 | P/FVC/MDS/1045067/2021 | 2021-07-28 | 0 | CBE822
461 | MANI16 | MANI16 | Chennai | Chennai |  | CHN | Indus | IN-1386001 | R/NN-456063 | Nominals with issues | On air | 2020-06-20 | MANI16 | 4G_FD900_MANI16 | 4G_FD2100_MANI16 | 4G_TD_MANI16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201022521 | 2022-01-28 | P/FVC/MDS/1072928/2022 | 2022-02-04 | ST202201022642 | 2022-01-28 | P/FVC/MDS/1072961/2022 | 2022-02-04 | ST202201022916 | 2022-01-28 | P/FVC/MDS/1073030/2022 | 2022-02-04 | ST202201022819 | 2022-01-28 | P/FBW/MDS/1072988/2022 | 2022-02-04 | 0 | MANI16
462 | TRY292 | TRY292 | Tiruchirappalli | Trichy |  | ROTN | ATC | TN/TR/AT/21239 | T19TN04471 | Nominals with issues | On Air | 2019-08-30 | TRY292 | 4G_FD900_TRY292 | 4G_FD2100_TRY292 | 4G_TD_TRY292 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371818 | 2021-07-03 | P/FVC/MDS/1051791/2021 | 2021-08-15 | 2019610473 | 2019-09-07 | P/FVC/MDS/1094333/2022 | 2022-08-25 |  |  |  |  | 2019615031 | 2019-09-19 | P/FBW/MDS/6049921/2020 | 2020-05-19 | TRYZone-TopComplaints | TRY292
463 | UMPT31 | UMPT31 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-1368602 | R/NN-364159 | Nominals with issues | Dropped-Canb. | 2019-09-07 | UMPT31 | 4G_FD900_UMPT31 | 4G_FD2100_UMPT31 | 4G_TD_UMPT31 | G1800+L1800+L2300 | deviation Approval Available |  | ST202107371826 | 2021-07-03 | P/FVC/MDS/1051796/2021 | 2021-08-15 | 2019609901 | 2019-09-11 | diviation recived | 2019-10-18 |  |  |  |  | ST202007023055 | 2020-07-13 | P/FBW/MDS/1000633/2020 | 2020-07-18 | Partof461sitesSyamaMay'30/R/NN-346243bewithdrawn&RebookingtobedoneasLiteplusbasisonjawhar7/8/2019/R/NN-350048SPRejectedandalocatedtoCNIL7/23/2019/TAM/GBT/K/27875notfeasibileconfimredbypramoth7/29/2019andTVIsharingoutoftheclutter | UMPT31
464 | JSWSTL | JSWSTL | Salem | Vellore |  | ROTN | Airtel | - |  | Nominal WIP | On Air | 2021-04-28 | JSWSTL | 4G_FD900_JSWSTL | 4G_FD2100_JSWSTL | 4G_TD_JSWSTL | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371850 | 2021-07-03 | P/FVC/MDS/1051808/2021 | 2021-08-15 | ST202106333512 | 2021-06-09 | P/FVC/MDS/1060871/2021 | 2021-09-13 |  |  |  |  | ST202106331998 | 2021-06-08 | P/FVC/MDS/1045063/2021 | 2021-07-28 | 0 | JSWSTL
465 | REDH30 | REDH30 | Chennai | Chennai |  | CHN | INDUS |  |  | Nominal WIP | Dropped-L900 | 2021-03-15 | REDH30 | 4G_FD900_REDH30 | 4G_FD2100_REDH30 | 4G_TD_REDH30 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202107396921 | 2021-07-26 | P/FVC/MDS/1052736/2021 | 2021-08-20 | ST202106333514 | 2021-06-09 | P/FVC/MDS/1060873/2021 | 2021-09-13 | ST202010118816 | 2020-10-22 | P/FVC/MDS/1005875/2020 | 2020-11-10 | ST202106359634 | 2021-06-24 | P/FBW/MDS/1051751/2021 | 2021-08-15 | 0 | REDH30
466 | MMNA28 | MMNA28 | Chennai | Chennai |  | CHN | Airtel |  |  | Nominal WIP | On air | - | MMNA28 | 4G_FD900_MMNA28 | 4G_FD2100_MMNA28 | 4G_TD_MMNA28 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108410818 | 2021-08-06 | P/FVC/MDS/1052890/2021 | 2021-08-20 | ST202108414441 | 2021-08-10 | P/FVC/MDS/1055961/2021 | 2021-09-05 | ST202108413664 | 2021-08-09 | P/FVC/MDS/1055937/2021 | 2021-09-05 | ST202108424139 | 2021-08-11 | P/FBW/MDS/1055981/2021 | 2021-09-05 | SR Surrendered by ATC on Dec 9, 2020 and alloted to Own | MMNA28
467 | NYLI59 | NYLI59 | Cuddalore | Trichy |  | ROTN | Ascend |  |  | Nominal WIP | On Air | 2021-06-07 | NYLI59 | 4G_FD900_NYLI59 | 4G_FD2100_NYLI59 | 4G_TD_NYLI59 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106335533 | 2021-06-09 | P/FVC/MDS/1045058/2021 | 2021-07-28 | ST202106335581 | 2021-06-09 | P/FVC/MDS/1060894/2021 | 2021-09-13 |  |  |  |  | ST202106335607 | 2021-06-08 | P/FVC/MDS/1045095/2021 | 2021-07-28 | 0 | NYLI59
468 | NADOOR | NADOOR | Dharmapuri | Vellore |  | ROTN | Ascend |  |  | Nominal WIP | On Air | 2021-06-07 | NADOOR | 4G_FD900_NADOOR | 4G_FD2100_NADOOR | 4G_TD_NADOOR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106335532 | 2021-06-09 | P/FVC/MDS/1045057/2021 | 2021-07-28 | ST202106335580 | 2021-06-09 | P/FVC/MDS/1060893/2021 | 2021-09-13 |  |  |  |  | ST202106332057 | 2021-06-08 | P/FVC/MDS/1045079/2021 | 2021-07-28 | 0 | NADOOR
469 | SPD110 | SPD110 | Kancheepuram | Vellore |  | ROTN | Ascend |  |  | Nominal WIP | On Air | 2021-06-04 | SPD110 | 4G_FD900_SPD110 | 4G_FD2100_SPD110 | 4G_TD_SPD110 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522075 | 2021-09-16 | P/FVC/MDS/1062413/2021 | 2021-09-23 | ST202109522203 | 2021-09-16 | P/FVC/MDS/1062461/2021 | 2021-09-23 | ST202109530292 | 2021-09-24 | P/FVC/MDS/1063052/2021 | 2021-10-01 | ST202109522258 | 2021-09-16 | P/FBW/MDS/1062509/2021 | 2021-09-23 | 0 | SPD110
470 | HSR170 | HSR170 | Krishnagiri | Vellore |  | ROTN | Airtel |  |  | Nominal WIP | On Air | 2021-05-29 | HSR170 | 4G_FD900_HSR170 | 4G_FD2100_HSR170 | 4G_TD_HSR170 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371968 | 2021-07-03 | P/FVC/MDS/1051622/2021 | 2021-08-14 | ST202106333524 | 2021-06-09 | P/FVC/MDS/1060877/2021 | 2021-09-13 | ST202210548119 | 2022-10-11 | P/FVC/MDS/1113907/2022 | 2022-10-21 | ST202106332027 | 2021-06-08 | P/FVC/MDS/1045070/2021 | 2021-07-28 | 0 | HSR170
471 | HSR171 | HSR171 | Krishnagiri | Vellore |  | ROTN | Airtel |  |  | Nominal WIP | On Air | 2021-05-29 | HSR171 | 4G_FD900_HSR171 | 4G_FD2100_HSR171 | 4G_TD_HSR171 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371969 | 2021-07-03 | P/FVC/MDS/1051623/2021 | 2021-08-14 | ST202106333525 | 2021-06-09 | P/FVC/MDS/1060878/2021 | 2021-09-13 |  |  |  |  | ST202106332028 | 2021-06-08 | P/FVC/MDS/1045071/2021 | 2021-07-28 | 0 | HSR171
472 | GMPD29 | GMPD29 | Thiruvallur | Chennai |  | ROTN | Airtel |  |  | Nominal WIP | On Air | 2021-05-29 | GMPD29 | 4G_FD900_GMPD29 | 4G_FD2100_GMPD29 | 4G_TD_GMPD29 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371970 | 2021-07-03 | P/FVC/MDS/1051624/2021 | 2021-08-14 | ST202106333526 | 2021-06-09 | P/FVC/MDS/1060879/2021 | 2021-09-13 |  |  |  |  | ST202106332029 | 2021-06-08 | P/FVC/MDS/1045072/2021 | 2021-07-28 | 0 | GMPD29
473 | VDKRI3 | VDKRI3 | Tirunelveli | Tirunelveli |  | ROTN | Indus |  |  |  | On Air | 2021-07-02 | VDKRI3 | 4G_FD900_VDKRI3 | 4G_FD2100_VDKRI3 | 4G_TD_VDKRI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107371982 | 2021-07-03 | P/FVC/MDS/1051636/2021 | 2021-08-14 | ST202107393907 | 2021-07-23 | P/FVC/MDS/1055992/2021 | 2021-09-06 | ST202107378046 | 2021-07-08 | P/FVC/MDS/1056094/2021 | 2021-09-07 | ST202107380629 | 2021-07-10 | P/FBW/MDS/1057197/2021 | 2021-09-09 | 0 | VDKRI3
474 | CBE831 | CBE831 | Coimbatore | Coimbatore |  | ROTN | Indus |  |  |  | On Air | 2021-06-29 | CBE831 | 4G_FD900_CBE831 | 4G_FD2100_CBE831 | 4G_TD_CBE831 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107371978 | 2021-07-03 | P/FVC/MDS/1051632/2021 | 2021-08-14 | ST202107380618 | 2021-07-10 | P/FVC/MDS/1056620/2021 | 2021-09-08 | ST202107378040 | 2021-07-08 | P/FVC/MDS/1056091/2021 | 2021-09-07 | ST202107380625 | 2021-07-10 | P/FBW/MDS/1057193/2021 | 2021-09-09 | 0 | CBE831
475 | CBE886 | CBE886 | Coimbatore | Coimbatore |  | ROTN | Indus |  |  |  | On Air | 2021-07-09 | CBE886 | 4G_FD900_CBE886 | 4G_FD2100_CBE886 | 4G_TD_CBE886 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559325 | 2021-10-14 | P/FVC/MDS/1063725/2021 | 2021-10-22 | ST202110554053 | 2021-10-08 | P/FVC/MDS/1063596/2021 | 2021-10-20 | ST202212826761 | 2022-12-16 | P/AFC/MDS/1119524/2022 | 2022-12-22 | ST202110554912 | 2021-10-08 | P/FBW/MDS/1063680/2021 | 2021-10-22 | 0 | CBE832
476 | HSR151 | HSR151 | Krishnagiri | Vellore |  | ROTN | Indus |  |  |  | On Air | 2021-07-09 | HSR151 | 4G_FD900_HSR151 | 4G_FD2100_HSR151 | 4G_TD_HSR151 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396919 | 2021-07-26 | P/FVC/MDS/1052734/2021 | 2021-08-20 | ST202108414435 | 2021-08-10 | P/FVC/MDS/1055955/2021 | 2021-09-05 | ST202210538399 | 2022-10-08 | P/FVC/MDS/1113904/2022 | 2022-10-21 | ST202107393411 | 2021-07-23 | P/FBW/MDS/1056718/2021 | 2021-09-08 | 0 | HSR151
477 | PERMLP | PERMLP | Vellore | Vellore |  | ROTN | Ascend |  |  |  | On Air | 2021-06-29 | PERMLP | 4G_FD900_PERMLP | 4G_FD2100_PERMLP | 4G_TD_PERMLP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107371977 | 2021-07-03 | P/FVC/MDS/1051631/2021 | 2021-08-14 | ST202107380617 | 2021-07-10 | P/FVC/MDS/1056619/2021 | 2021-09-08 | ST202107378039 | 2021-07-08 | P/FVC/MDS/1056090/2021 | 2021-09-07 | ST202107380624 | 2021-07-10 | P/FBW/MDS/1057192/2021 | 2021-09-09 | 0 | PERMLP
478 | KRKL26 | KRKL26 | Nagapattinam | Trichy |  | ROTN | BSNL |  |  |  | On Air | 2021-07-20 | KRKL26 | 4G_FD900_KRKL26 | 4G_FD2100_KRKL26 | 4G_TD_KRKL26 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404986 | 2021-08-02 | P/FVC/MDS/1052805/2021 | 2021-08-20 | ST202108407511 | 2021-08-03 | P/FVC/MDS/1056759/2021 | 2021-09-09 |  |  |  |  | ST202108407161 | 2021-08-03 | P/FBW/MDS/1052847/2021 | 2021-08-20 | 0 | KRKL26
479 | CKLAM2 | CKLAM2 | Tirunelveli | Madurai |  | ROTN | ATC |  |  |  | On Air | 2021-07-16 | CKLAM2 | 4G_FD900_CKLAM2 | 4G_FD2100_CKLAM2 | 4G_TD_CKLAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396904 | 2021-07-26 | P/FVC/MDS/1052724/2021 | 2021-08-20 | ST202107393931 | 2021-07-23 | P/FVC/MDS/1056744/2021 | 2021-09-09 | ST202107393756 | 2021-07-23 | P/FVC/MDS/1057238/2021 | 2021-09-09 | ST202107393403 | 2021-07-23 | P/FBW/MDS/1056710/2021 | 2021-09-08 | 0 | CKLAM2
480 | KNKI15 | KNKI15 | Kanniyakumari | Madurai |  | ROTN | BSNL |  |  |  | SO | 2021-07-22 | KNKI15 | 4G_FD900_KNKI15 | 4G_FD2100_KNKI15 | 4G_TD_KNKI15 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404994 | 2021-08-02 | P/FVC/MDS/1052813/2021 | 2021-08-20 | ST202108407519 | 2021-08-03 | P/FVC/MDS/1056767/2021 | 2021-09-09 |  |  |  |  | ST202108407169 | 2021-08-03 | P/FBW/MDS/1052855/2021 | 2021-08-20 | 0 | KNKI15
481 | ARUMNY | ARUMNY | Kanniyakumari | Madurai |  | ROTN | BSNL |  |  |  | SR | 2021-07-20 | ARUMNY | 4G_FD900_ARUMNY | 4G_FD2100_ARUMNY | 4G_TD_ARUMNY | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404987 | 2021-08-02 | P/FVC/MDS/1052806/2021 | 2021-08-20 | ST202108407512 | 2021-08-03 | P/FVC/MDS/1056760/2021 | 2021-09-09 | ST202008045762 | 2020-08-17 | P/FVC/MDS/1001939/2020 | 2020-08-22 | ST202108407162 | 2021-08-03 | P/FBW/MDS/1052848/2021 | 2021-08-20 | 0 | ARUMNY
482 | DKPYAM | DKPYAM | Tiruppur | Coimbatore |  | ROTN | ATC |  |  |  | On Air | 2021-07-22 | DKPYAM | 4G_FD900_DKPYAM | 4G_FD2100_DKPYAM | 4G_TD_DKPYAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404991 | 2021-08-02 | P/FVC/MDS/1052810/2021 | 2021-08-20 | ST202108407516 | 2021-08-03 | P/FVC/MDS/1056764/2021 | 2021-09-09 | ST202012163602 | 2020-12-02 | P/FVC/MDS/1007147/2020 | 2020-12-11 | ST202108407166 | 2021-08-03 | P/FBW/MDS/1052852/2021 | 2021-08-20 | 0 | DKPYAM
483 | PILLNL | PILLNL | Namakkal | Coimbatore |  | ROTN | ATC |  |  |  | On Air | 2021-07-22 | PILLNL | 4G_FD900_PILLNL | 4G_FD2100_PILLNL | 4G_TD_PILLNL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404992 | 2021-08-02 | P/FVC/MDS/1052811/2021 | 2021-08-20 | ST202108407517 | 2021-08-03 | P/FVC/MDS/1056765/2021 | 2021-09-09 |  |  |  |  | ST202108407167 | 2021-08-03 | P/FBW/MDS/1052853/2021 | 2021-08-20 | 0 | PILLNL
484 | PDY325 | PDY325 | Puducherry | Trichy |  | ROTN | ATC |  |  |  | On Air | 2021-07-13 | PDY325 | 4G_FD900_PDY325 | 4G_FD2100_PDY325 | 4G_TD_PDY325 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396901 | 2021-07-26 | P/FVC/MDS/1052721/2021 | 2021-08-20 | ST202107393928 | 2021-07-23 | P/FVC/MDS/1056741/2021 | 2021-09-09 | ST202107393753 | 2021-07-23 | P/FVC/MDS/1057235/2021 | 2021-09-09 | ST202107393397 | 2021-07-23 | P/FBW/MDS/1056708/2021 | 2021-09-08 | 0 | PDY325
485 | MDU483 | MDU483 | Madurai | Madurai |  | ROTN | ATC |  |  |  | On Air | 2021-07-22 | MDU483 | 4G_FD900_MDU483 | 4G_FD2100_MDU483 | 4G_TD_MDU483 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404989 | 2021-08-02 | P/FVC/MDS/1052808/2021 | 2021-08-20 | ST202108407514 | 2021-08-03 | P/FVC/MDS/1056762/2021 | 2021-09-09 |  |  |  |  | ST202108407164 | 2021-08-03 | P/FBW/MDS/1052850/2021 | 2021-08-20 | 0 | MDU483
486 | KCP127 | KCP127 | Kancheepuram | Chennai |  | ROTN | ATC |  |  |  | On Air | 2021-07-22 | KCP127 | 4G_FD900_KCP127 | 4G_FD2100_KCP127 | 4G_TD_KCP127 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108405000 | 2021-08-02 | P/FVC/MDS/1052819/2021 | 2021-08-20 | ST202108407526 | 2021-08-03 | P/FVC/MDS/1056774/2021 | 2021-09-09 |  |  |  |  | ST202108407176 | 2021-08-03 | P/FBW/MDS/1052862/2021 | 2021-08-20 | 0 | KCP127
487 | KARUGL | KARUGL | Tirunelveli | Madurai |  | ROTN | ATC |  |  |  | On Air | 2021-07-12 | KARUGL | 4G_FD900_KARUGL | 4G_FD2100_KARUGL | 4G_TD_KARUGL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396899 | 2021-07-26 | P/FVC/MDS/1052719/2021 | 2021-08-20 | ST202107393926 | 2021-07-23 | P/FVC/MDS/1056739/2021 | 2021-09-09 | ST202107393751 | 2021-07-23 | P/FVC/MDS/1057233/2021 | 2021-09-09 | ST202107393395 | 2021-07-23 | P/FBW/MDS/1056705/2021 | 2021-09-08 | 0 | KARUGL
488 | VLNMD3 | VLNMD3 | Tiruchirappalli | Trichy |  | ROTN | ATC |  |  |  | On Air | 2021-07-16 | VLNMD3 | 4G_FD900_VLNMD3 | 4G_FD2100_VLNMD3 | 4G_TD_VLNMD3 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202107396903 | 2021-07-26 | P/FVC/MDS/1052723/2021 | 2021-08-20 | ST202107393930 | 2021-07-23 | P/FVC/MDS/1056743/2021 | 2021-09-09 | ST202107393755 | 2021-07-23 | P/FVC/MDS/1057237/2021 | 2021-09-09 | ST202107393398 | 2021-07-23 | P/FBW/MDS/1056709/2021 | 2021-09-08 | 0 | VLNMD3
489 | PDY328 | PDY328 | Puducherry | Trichy |  | ROTN | Indus |  |  |  |  | 2021-07-22 | PDY328 | 4G_FD900_PDY328 | 4G_FD2100_PDY328 | 4G_TD_PDY328 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404970 | 2021-08-02 | P/FVC/MDS/1052791/2021 | 2021-08-20 | ST202108407522 | 2021-08-03 | P/FVC/MDS/1056770/2021 | 2021-09-09 |  |  |  |  | ST202108407172 | 2021-08-03 | P/FBW/MDS/1052858/2021 | 2021-08-20 | 0 | PDY328
490 | HATSN1 | HATSN1 | Tiruppur | Coimbatore |  | ROTN | Airtel |  |  |  | On Air | 2021-07-22 | HATSN1 | 4G_FD900_HATSN1 | 4G_FD2100_HATSN1 | 4G_TD_HATSN1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404997 | 2021-08-02 | P/FVC/MDS/1052816/2021 | 2021-08-20 | ST202108407523 | 2021-08-03 | P/FVC/MDS/1056771/2021 | 2021-09-09 |  |  |  |  | ST202108407173 | 2021-08-03 | P/FBW/MDS/1052859/2021 | 2021-08-20 | 0 | HATSN1
491 | MOOKK1 | MOOKK1 | Pudukkottai | Trichy |  | ROTN | ATC |  |  |  | On Air | 2021-07-20 | MOOKK1 | 4G_FD900_MOOKK1 | 4G_FD2100_MOOKK1 | 4G_TD_MOOKK1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404985 | 2021-08-02 | P/FVC/MDS/1052804/2021 | 2021-08-20 | ST202108407510 | 2021-08-03 | P/FVC/MDS/1056758/2021 | 2021-09-09 |  |  |  |  | ST202108407160 | 2021-08-03 | P/FBW/MDS/1052846/2021 | 2021-08-20 | 0 | MOOKK1
492 | PKT207 | PKT207 | Tirunelveli | Madurai |  | ROTN | INDUS |  |  |  | On Air | 2021-07-12 | PKT207 | 4G_FD900_PKT207 | 4G_FD2100_PKT207 | 4G_TD_PKT207 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107386796 | 2021-07-17 | P/FVC/MDS/1051594/2021 | 2021-08-14 | ST202107393919 | 2021-07-23 | P/FVC/MDS/1056734/2021 | 2021-09-09 | ST202107393746 | 2021-07-23 | P/FVC/MDS/1057228/2021 | 2021-09-09 | ST202107393390 | 2021-07-23 | P/FBW/MDS/1056699/2021 | 2021-09-08 | 0 | PKT207
493 | GDLR15 | GDLR15 | The Nilgiris | Coimbatore |  | ROTN | ATC |  |  |  | On Air | 2021-07-22 | GDLR15 | 4G_FD900_GDLR15 | 4G_FD2100_GDLR15 | 4G_TD_GDLR15 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404996 | 2021-08-02 | P/FVC/MDS/1052815/2021 | 2021-08-20 | ST202108407521 | 2021-08-03 | P/FVC/MDS/1056769/2021 | 2021-09-09 |  |  |  |  | ST202108407171 | 2021-08-03 | P/FBW/MDS/1052857/2021 | 2021-08-20 | 0 | GDLR15
494 | SAPPNP | SAPPNP | Krishnagiri | Vellore |  | ROTN | TVI |  |  |  | On Air | 2021-07-12 | SAPPNP | 4G_FD900_SAPPNP | 4G_FD2100_SAPPNP | 4G_TD_SAPPNP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396898 | 2021-07-26 | P/FVC/MDS/1052718/2021 | 2021-08-20 | ST202107393923 | 2021-07-23 | P/FVC/MDS/1056736/2021 | 2021-09-09 | ST202107393748 | 2021-07-23 | P/FVC/MDS/1057230/2021 | 2021-09-09 | ST202107393392 | 2021-07-23 | P/FBW/MDS/1056702/2021 | 2021-09-08 | 0 | SAPPNP
495 | ALAPRM | ALAPRM | Dharmapuri | Vellore |  | ROTN | TVI |  |  |  | On Air | 2021-07-12 | ALAPRM | 4G_FD900_ALAPRM | 4G_FD2100_ALAPRM | 4G_TD_ALAPRM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108410883 | 2021-08-06 | P/FVC/MDS/1052914/2021 | 2021-08-20 | ST202107393925 | 2021-07-23 | P/FVC/MDS/1056738/2021 | 2021-09-09 | ST202107393750 | 2021-07-23 | P/FVC/MDS/1057232/2021 | 2021-09-09 | ST202107393394 | 2021-07-23 | P/FBW/MDS/1056704/2021 | 2021-09-08 | 0 | ALAPRM
496 | SLM380 | SLM380 | Salem | Vellore |  | ROTN | Airtel |  |  |  | On Air | 2021-07-22 | SLM380 | 4G_FD900_SLM380 | 4G_FD2100_SLM380 | 4G_TD_SLM380 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404998 | 2021-08-02 | P/FVC/MDS/1052817/2021 | 2021-08-20 | ST202108407524 | 2021-08-03 | P/FVC/MDS/1056772/2021 | 2021-09-09 |  |  |  |  | ST202108407174 | 2021-08-03 | P/FBW/MDS/1052860/2021 | 2021-08-20 | 0 | SLM380
497 | ASUR13 | ASUR13 | Coimbatore | Coimbatore |  | ROTN | Ascend |  |  |  | On Air | 2021-07-12 | ASUR13 | 4G_FD900_ASUR13 | 4G_FD2100_ASUR13 | 4G_TD_ASUR13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108410882 | 2021-08-06 | P/FVC/MDS/1052913/2021 | 2021-08-20 | ST202107393924 | 2021-07-23 | P/FVC/MDS/1056737/2021 | 2021-09-09 | ST202107393749 | 2021-07-23 | P/FVC/MDS/1057231/2021 | 2021-09-09 | ST202107393393 | 2021-07-23 | P/FBW/MDS/1056703/2021 | 2021-09-08 | 0 | ASUR13
498 | KISKI8 | KISKI8 | Chennai |  |  | CHN |  |  |  | Nominal WIP | On air | 2021-07-16 | KISKI8 | 4G_FD900_KISKI8 | 4G_FD2100_KISKI8 | 4G_TD_KISKI8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396910 | 2021-07-26 | P/FVC/MDS/1052730/2021 | 2021-08-20 | ST202107393908 | 2021-07-23 | P/FVC/MDS/1056723/2021 | 2021-09-09 | ST202107393745 | 2021-07-23 | P/FVC/MDS/1057227/2021 | 2021-09-09 | ST202107393409 | 2021-07-23 | P/FBW/MDS/1056716/2021 | 2021-09-08 | 0 | KISKI8
499 | MUDI22 | MUDI22 | Chennai | Chennai |  | CHN | Indus | R/NN-568578 | 0 | Nominal WIP |  | 2021-06-30 | MUDI22 | 4G_FD900_MUDI22 | 4G_FD2100_MUDI22 | 4G_TD_MUDI22 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202107371987 | 2021-07-03 | P/FVC/MDS/1051641/2021 | 2021-08-14 | ST202107393910 | 2021-07-23 | P/FVC/MDS/1056725/2021 | 2021-09-09 | ST202107388479 | 2021-07-19 | P/FVC/MDS/1056666/2021 | 2021-09-08 | ST202106357033 | 2021-06-22 | P/FBW/MDS/1060899/2021 | 2021-09-13 | 0 | MUDI22
500 | TOND29 | TOND29 | Chennai | Chennai |  | CHN | Indus | R/NN-620762 | 0 | Nominal WIP |  | 2021-07-22 | TOND29 | 4G_FD900_TOND29 | 4G_FD2100_TOND29 | 4G_TD_TOND29 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108404980 | 2021-08-02 | P/FVC/MDS/1052800/2021 | 2021-08-20 | ST202108406886 | 2021-08-03 | P/FVC/MDS/1056753/2021 | 2021-09-09 | ST202107393743 | 2021-07-23 | P/FVC/MDS/1057225/2021 | 2021-09-09 | ST202108407154 | 2021-08-03 | P/FBW/MDS/1052841/2021 | 2021-08-20 | 0 | TOND29
501 | PDY282 | PDY282 | Puducherry | Trichy |  | ROTN | Indus | IN-1936725 | R/NN-618044 |  | Dropped | 2021-04-27 | PDY282 | 4G_FD900_PDY282 | 4G_FD2100_PDY282 | 4G_TD_PDY282 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108405001 | 2021-08-02 | P/FVC/MDS/1052820/2021 | 2021-08-20 | ST202108407529 | 2021-08-03 | P/FVC/MDS/1056775/2021 | 2021-09-09 |  |  |  |  | 2019617850 | 2019-12-03 | P/FBW/MDS/5893735/2019 | 2019-12-10 |  | PDY282
502 | VDLR17 | VDLR17 | Cuddalore | Trichy |  | ROTN | Indus | IN-3004978 | R/NN-625893 |  | On Air | 2021-04-27 | VDLR17 | 4G_FD900_VDLR17 | 4G_FD2100_VDLR17 | 4G_TD_VDLR17 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108405003 | 2021-08-02 | P/FVC/MDS/1052822/2021 | 2021-08-20 | ST202108407531 | 2021-08-03 | P/FVC/MDS/1056777/2021 | 2021-09-09 |  |  |  |  | ST202108407179 | 2021-08-03 | P/FBW/MDS/1052865/2021 | 2021-08-20 | 0 | VDLR17
503 | CBE591 | CBE591 |  |  |  | ROTN | Indus | R/RES-501951 |  |  |  | 2021-06-18 | CBE591 | 4G_FD900_CBE591 | 4G_FD2100_CBE591 | 4G_TD_CBE591 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106354515 | 2021-06-21 | P/FVC/MDS/1051704/2021 | 2021-08-14 | ST202106357036 | 2021-06-22 | P/FVC/MDS/1060932/2021 | 2021-09-14 | ST202106356484 | 2021-06-22 | P/FVC/MDS/1061407/2021 | 2021-09-15 | ST202106357091 | 2021-06-22 | P/FBW/MDS/1060909/2021 | 2021-09-13 | 0 | CBE591
504 | TENI30 | TENI30 |  |  |  | ROTN | Indus | R/NN-618687 |  |  |  | 2021-06-18 | TENI30 | 4G_FD900_TENI30 | 4G_FD2100_TENI30 | 4G_TD_TENI30 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106354577 | 2021-06-21 | P/FVC/MDS/1051717/2021 | 2021-08-14 | ST202106357424 | 2021-06-23 | P/FVC/MDS/1060945/2021 | 2021-09-14 | ST202106356500 | 2021-06-22 | P/FVC/MDS/1061420/2021 | 2021-09-15 | ST202106360051 | 2021-06-24 | P/FBW/MDS/1060922/2021 | 2021-09-13 | 0 | TENI30
505 | MUPET6 | MUPET6 |  |  |  | ROTN | Indus | R/NN-569204 |  |  |  | 2021-06-21 | MUPET6 | 4G_FD900_MUPET6 | 4G_FD2100_MUPET6 | 4G_TD_MUPET6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202107386719 | 2021-07-17 | P/FVC/MDS/1051565/2021 | 2021-08-14 | ST202107380141 | 2021-07-10 | P/FVC/MDS/1055147/2021 | 2021-09-03 | ST202107388459 | 2021-07-19 | P/FVC/MDS/1055994/2021 | 2021-09-06 | ST202107379913 | 2021-07-10 | P/FBW/MDS/1057095/2021 | 2021-09-09 | 0 | MUPET6
506 | TUT148 | TUT148 |  |  |  | ROTN | Indus | R/NN-619619 |  |  |  | 2021-07-20 | TUT148 | 4G_FD900_TUT148 | 4G_FD2100_TUT148 | 4G_TD_TUT148 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108404968 | 2021-08-02 | P/FVC/MDS/1052789/2021 | 2021-08-20 | ST202108407533 | 2021-08-03 | P/FVC/MDS/1056779/2021 | 2021-09-09 | ST202108413638 | 2021-08-09 | P/FVC/MDS/1055911/2021 | 2021-09-05 | ST202108407181 | 2021-08-03 | P/FBW/MDS/1052867/2021 | 2021-08-20 | 0 | TUT148
507 | CWSLSP | CWSLSP |  |  |  | ROTN | Airtel |  |  |  |  | 2021-05-29 | CWSLSP | 4G_FD900_CWSLSP | 4G_FD2100_CWSLSP | 4G_TD_CWSLSP | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106331859 | 2021-06-08 | P/FVC/MDS/1045046/2021 | 2021-07-28 | ST202106333532 | 2021-06-09 | P/FVC/MDS/1060882/2021 | 2021-09-13 | ST202106331666 | 2021-06-08 | P/FVC/MDS/1051519/2021 | 2021-08-14 | ST202106332050 | 2021-06-08 | P/FVC/MDS/1045075/2021 | 2021-07-28 |  | CWSLSP
508 | SWMLI3 | SWMLI3 |  |  |  | ROTN | ATC | - |  |  |  | 2021-05-04 | SWMLI3 | 4G_FD900_SWMLI3 | 4G_FD2100_SWMLI3 | 4G_TD_SWMLI3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201025220 | 2022-01-31 | P/FVC/MDS/1074457/2022 | 2022-02-22 | ST202201025328 | 2022-01-31 | P/FVC/MDS/1074400/2022 | 2022-02-22 | ST202201025473 | 2022-01-31 | P/FVC/MDS/1074512/2022 | 2022-02-22 | ST202201025398 | 2022-01-31 | P/FBW/MDS/1074340/2022 | 2022-02-22 |  | SWMLI3
509 | TNJ154 | TNJ154 |  |  |  | ROTN | ATC | - |  |  |  | 2021-05-10 | TNJ154 | 4G_FD900_TNJ154 | 4G_FD2100_TNJ154 | 4G_TD_TNJ154 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498663 | 2021-08-31 | P/FVC/MDS/1060452/2021 | 2021-09-13 | ST202106333404 | 2021-06-09 | P/FVC/MDS/1060853/2021 | 2021-09-13 | ST202105295218 | 2021-05-25 | P/FVC/MDS/1036520/2021 | 2021-06-23 | ST202106326254 | 2021-06-06 | P/FVC/MDS/1036853/2021 | 2021-06-24 |  | TNJ154
510 | PATWM3 | PATWM3 |  |  |  | ROTN | Indus | R/NN-617791 |  |  |  | 2021-07-07 | PATWM3 | 4G_FD900_PATWM3 | 4G_FD2100_PATWM3 | 4G_TD_PATWM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202107371990 | 2021-07-03 | P/FVC/MDS/1051645/2021 | 2021-08-14 | ST202108414440 | 2021-08-10 | P/FVC/MDS/1055960/2021 | 2021-09-05 | ST202108413663 | 2021-08-09 | P/FVC/MDS/1055936/2021 | 2021-09-05 | ST202108424137 | 2021-08-11 | P/FBW/MDS/1055979/2021 | 2021-09-05 | 0 | PATWM3
511 | MNLGD3 | MNLGD3 |  |  |  | ROTN | Indus | R/NN-618679 |  |  |  | 2021-06-30 | MNLGD3 | 4G_FD900_MNLGD3 | 4G_FD2100_MNLGD3 | 4G_TD_MNLGD3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202107379964 | 2021-07-10 | P/FVC/MDS/1051825/2021 | 2021-08-15 | ST202107380145 | 2021-07-10 | P/FVC/MDS/1056100/2021 | 2021-09-07 | ST202107388463 | 2021-07-19 | P/FVC/MDS/1056651/2021 | 2021-09-08 | ST202107379917 | 2021-07-10 | P/FBW/MDS/1057099/2021 | 2021-09-09 | 0 | MNLGD3
512 | CBE874 | CBE874 |  |  |  | ROTN | Indus | R/NN-618674 |  |  |  | 2021-07-09 | CBE874 | 4G_FD900_CBE874 | 4G_FD2100_CBE874 | 4G_TD_CBE874 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107396909 | 2021-07-26 | P/FVC/MDS/1052729/2021 | 2021-08-20 | ST202107393935 | 2021-07-23 | P/FVC/MDS/1056748/2021 | 2021-09-09 | ST202107393762 | 2021-07-23 | P/FVC/MDS/1057243/2021 | 2021-09-09 | ST202107393408 | 2021-07-23 | P/FBW/MDS/1056715/2021 | 2021-09-08 | 0 | CBE874
513 | OVGDU3 | OVGDU3 |  |  |  | ROTN | GTL | - |  |  |  | 2021-05-19 | OVGDU3 | 4G_FD900_OVGDU3 | 4G_FD2100_OVGDU3 | 4G_TD_OVGDU3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504494 | 2021-09-02 | P/FVC/MDS/1058581/2021 | 2021-09-10 | ST202106333417 | 2021-06-09 | P/FVC/MDS/1060857/2021 | 2021-09-13 | ST202106331606 | 2021-06-08 | P/FVC/MDS/1051504/2021 | 2021-08-14 | ST202108424138 | 2021-08-11 | P/FBW/MDS/1055980/2021 | 2021-09-05 | 0 | OVGDU3
514 | NKDYR4 | NKDYR4 |  |  |  | ROTN | Indus | R/RES-502368 |  |  |  | 2021-06-18 | NKDYR4 | 4G_FD900_NKDYR4 | 4G_FD2100_NKDYR4 | 4G_TD_NKDYR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106354516 | 2021-06-21 | P/FVC/MDS/1051705/2021 | 2021-08-14 | ST202106357037 | 2021-06-22 | P/FVC/MDS/1060933/2021 | 2021-09-14 | ST202106356485 | 2021-06-22 | P/FVC/MDS/1061408/2021 | 2021-09-15 | ST202106359400 | 2021-06-24 | P/FBW/MDS/1060910/2021 | 2021-09-13 | 0 | NKDYR4
515 | KONASM | KONASM | Salem | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2021-08-03 | KONASM | 4G_FD900_KONASM | 4G_FD2100_KONASM | 4G_TD_KONASM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430679 | 2021-08-17 | P/FVC/MDS/1059634/2021 | 2021-09-12 | ST202108414422 | 2021-08-10 | P/FVC/MDS/1055943/2021 | 2021-09-05 |  |  |  |  | ST202108424121 | 2021-08-11 | P/FBW/MDS/1055965/2021 | 2021-09-05 | 0
516 | SPD111 | SPD111 | Kancheepuram | Chennai |  | ROTN | Airtel | - | - |  | On Air | 2021-08-07 | SPD111 | 4G_FD900_SPD111 | 4G_FD2100_SPD111 | 4G_TD_SPD111 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430694 | 2021-08-17 | P/FVC/MDS/1059649/2021 | 2021-09-12 | ST202109501776 | 2021-09-02 | P/FVC/MDS/1058578/2021 | 2021-09-10 | ST202210548816 | 2022-10-11 | P/FVC/MDS/1113947/2022 | 2022-10-21 | ST202108430492 | 2021-08-17 | P/FBW/MDS/1056050/2021 | 2021-09-07 | 0
517 | MDPM04 | MDPM04 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3002112 | R/NN-625475 |  | On Air | 2021-08-03 | MDPM04 | 4G_FD900_MDPM04 | 4G_FD2100_MDPM04 | 4G_TD_MDPM04 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430681 | 2021-08-17 | P/FVC/MDS/1059636/2021 | 2021-09-12 | ST202108414424 | 2021-08-10 | P/FVC/MDS/1055945/2021 | 2021-09-05 | ST202210548372 | 2022-10-11 | P/FVC/MDS/1113912/2022 | 2022-10-21 | ST202108424123 | 2021-08-11 | P/FBW/MDS/1055967/2021 | 2021-09-05 | 0
518 | KARADI | KARADI | Tiruvannamalai | Vellore |  | ROTN | CNIL | TAM/GBT/K/09033 | - |  | On Air | 2021-08-03 | KARADI | 4G_FD900_KARADI | 4G_FD2100_KARADI | 4G_TD_KARADI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430682 | 2021-08-17 | P/FVC/MDS/1059637/2021 | 2021-09-12 | ST202108414425 | 2021-08-10 | P/FVC/MDS/1055946/2021 | 2021-09-05 |  |  |  |  | ST202108424124 | 2021-08-11 | P/FBW/MDS/1055968/2021 | 2021-09-05 | 0
519 | OLAFCW | OLAFCW | Krishnagiri | Vellore |  | ROTN | Airtel | - | - |  | On Air |  | OLAFCW | 4G_FD900_OLAFCW | 4G_FD2100_OLAFCW | 4G_TD_OLAFCW | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202108404976 | 2021-08-02 | P/FVC/MDS/1052796/2021 | 2021-08-20 | ST202108407553 | 2021-08-03 | P/FVC/MDS/1056797/2021 | 2021-09-09 | ST202108413656 | 2021-08-09 | P/FVC/MDS/1055929/2021 | 2021-09-05 | ST202108407200 | 2021-08-03 | P/FBW/MDS/1052937/2021 | 2021-08-20 | 0
520 | NGL83 | NGL083 |  |  |  | ROTN | Indus | IN-3000984 | R/NN-620050 |  |  | 2021-06-18 | NGL083 | 4G_FD900_NGL083 | 4G_FD2100_NGL083 | 4G_TD_NGL083 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202106354574 | 2021-06-21 | P/FVC/MDS/1051714/2021 | 2021-08-14 | ST202106357409 | 2021-06-23 | P/FVC/MDS/1060942/2021 | 2021-09-14 | ST202106356488 | 2021-06-22 | P/FVC/MDS/1061411/2021 | 2021-09-15 | ST202106360045 | 2021-06-24 | P/FBW/MDS/1060919/2021 | 2021-09-13
521 | KRR98 | KRR098 |  |  |  | ROTN | Indus | IN-3000698 | R/NN-619777 |  |  | 2021-08-03 | KRR098 | 4G_FD900_KRR098 | 4G_FD2100_KRR098 | 4G_TD_KRR098 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108430683 | 2021-08-17 | P/FVC/MDS/1059638/2021 | 2021-09-12 | ST202108414426 | 2021-08-10 | P/FVC/MDS/1055947/2021 | 2021-09-05 | ST202108413611 | 2021-08-09 | P/FVC/MDS/1055894/2021 | 2021-09-05 | ST202108424125 | 2021-08-11 | P/FBW/MDS/1055969/2021 | 2021-09-05
522 | NLMBR6 | NLMBR6 |  |  |  | ROTN | Indus | IN-3002381 | R/NN-625560 |  |  | 2021-08-03 | NLMBR6 | 4G_FD900_NLMBR6 | 4G_FD2100_NLMBR6 | 4G_TD_NLMBR6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108430685 | 2021-08-17 | P/FVC/MDS/1059640/2021 | 2021-09-12 | ST202110560206 | 2021-10-14 | P/FVC/MDS/1063711/2021 | 2021-10-22 | ST202110560499 | 2021-10-14 | P/FVC/MDS/1063761/2021 | 2021-10-22 | ST202108424127 | 2021-08-11 | P/FBW/MDS/1055971/2021 | 2021-09-05 | 0
523 | IYAP27 | IYAP27 | Chennai | Chennai |  | CHN | Indus | IN-3002924 | R/NN-625713 |  | On air | 2021-08-07 | IYAP27 | 4G_FD900_IYAP27 | 4G_FD2100_IYAP27 | 4G_TD_IYAP27 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430692 | 2021-08-17 | P/FVC/MDS/1059647/2021 | 2021-09-12 | ST202108414443 | 2021-08-10 | P/FVC/MDS/1055963/2021 | 2021-09-05 |  |  |  |  | ST202108424141 | 2021-08-11 | P/FBW/MDS/1055983/2021 | 2021-09-05 | 0
524 | SPKL15 | SPKL15 | Chennai | Chennai |  | CHN | Airtel | - | - |  | SO | 2021-08-07 | SPKL15 | 4G_FD900_SPKL15 | 4G_FD2100_SPKL15 | 4G_TD_SPKL15 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430691 | 2021-08-17 | P/FVC/MDS/1059646/2021 | 2021-09-12 | ST202108414442 | 2021-08-10 | P/FVC/MDS/1055962/2021 | 2021-09-05 | ST202204095110 | 2022-04-08 | P/FVC/MDS/1078401/2022 | 2022-04-21 | ST202108424140 | 2021-08-11 | P/FBW/MDS/1055982/2021 | 2021-09-05 | 0
525 | TEMPM3 | TEMPM3 | Chennai | Chennai |  | CHN | Indus | IN-3003828 | R/NN-620858 |  |  | 2021-07-29 | TEMPM3 | 4G_FD900_TEMPM3 | 4G_FD2100_TEMPM3 | 4G_TD_TEMPM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108404984 | 2021-08-02 | P/FVC/MDS/1052803/2021 | 2021-08-20 | ST202108407509 | 2021-08-03 | P/FVC/MDS/1056757/2021 | 2021-09-09 | ST202108413636 | 2021-08-09 | P/FVC/MDS/1055909/2021 | 2021-09-05 | ST202108407159 | 2021-08-03 | P/FBW/MDS/1052845/2021 | 2021-08-20 | 0
526 | NALLOO | NALLOO | Kanniyakumari | Madurai |  | ROTN | Indus | IN-1531934 | R/NN-559553 |  | SRB(Surrender) | 2021-08-09 | NALLOO | 4G_FD900_NALLOO | 4G_FD2100_NALLOO | 4G_TD_NALLOO | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430695 | 2021-08-17 | P/FVC/MDS/1059650/2021 | 2021-09-12 | ST202109501777 | 2021-09-02 | P/FVC/MDS/1058579/2021 | 2021-09-10 |  |  |  |  | ST202108430468 | 2021-08-17 | P/FBW/MDS/1055144/2021 | 2021-09-03 | 0
527 | MAMSAP | MAMSAP | Virudhunagar | Madurai |  | ROTN | Indus | IN-1622439 | R/NN-561945 |  | On Air | 2021-08-09 | MAMSAP | 4G_FD900_MAMSAP | 4G_FD2100_MAMSAP | 4G_TD_MAMSAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430696 | 2021-08-17 | P/FVC/MDS/1059651/2021 | 2021-09-12 | ST202109501778 | 2021-09-02 | P/FVC/MDS/1058580/2021 | 2021-09-10 |  |  |  |  | ST202108430469 | 2021-08-17 | P/FBW/MDS/1055145/2021 | 2021-09-03 | 0
528 | ULLKT5 | ULLKT5 | Thiruvarur | Trichy |  | ROTN | ATC | TN/TI/AT/22353 | - |  | On Air | 2021-08-10 | ULLKT5 | 4G_FD900_ULLKT5 | 4G_FD2100_ULLKT5 | 4G_TD_ULLKT5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014701 | 2022-01-20 | P/FVC/MDS/1072397/2022 | 2022-01-31 | ST202201014769 | 2022-01-20 | P/FVC/MDS/1072368/2022 | 2022-01-31 |  |  |  |  | ST202201014784 | 2022-01-20 | P/FBW/MDS/1072319/2022 | 2022-01-31 | 0
529 | SEGMD1 | SEGMD1 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2021-08-13 | SEGMD1 | 4G_FD900_SEGMD1 | 4G_FD2100_SEGMD1 | 4G_TD_SEGMD1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430718 | 2021-08-17 | P/FVC/MDS/1059670/2021 | 2021-09-12 | ST202108498228 | 2021-08-31 | P/FVC/MDS/1060465/2021 | 2021-09-13 |  |  |  |  | ST202108430506 | 2021-08-17 | P/FBW/MDS/1056064/2021 | 2021-09-07 | 0
530 | PTVPT5 | PTVPT5 | Dindigul | Coimbatore |  | ROTN | Indus | IN-3000757 | R/NN-620008 |  | On Air | 2021-08-09 | PTVPT5 | 4G_FD900_PTVPT5 | 4G_FD2100_PTVPT5 | 4G_TD_PTVPT5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430699 | 2021-08-17 | P/FVC/MDS/1059653/2021 | 2021-09-12 | ST202109501779 | 2021-09-02 | P/FVC/MDS/1060725/2021 | 2021-09-13 |  |  |  |  | ST202108430471 | 2021-08-17 | P/FBW/MDS/1056031/2021 | 2021-09-07 | 0
531 | VAIYAV | VAIYAV | Kancheepuram | Chennai |  | ROTN | ATC | TN/KA/AT/22652 | - |  | On Air | 2021-08-13 | VAIYAV | 4G_FD900_VAIYAV | 4G_FD2100_VAIYAV | 4G_TD_VAIYAV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430719 | 2021-08-17 | P/FVC/MDS/1059671/2021 | 2021-09-12 | ST202108498229 | 2021-08-31 | P/FVC/MDS/1060466/2021 | 2021-09-13 |  |  |  |  | ST202108430507 | 2021-08-17 | P/FBW/MDS/1056065/2021 | 2021-09-07 | 0
532 | NARPAT | NARPAT | Dindigul | Coimbatore |  | ROTN | Indus | IN-3007550 | R/NN-626215 |  | On Air | 2021-08-13 | NARPAT | 4G_FD900_NARPAT | 4G_FD2100_NARPAT | 4G_TD_NARPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430711 | 2021-08-17 | P/FVC/MDS/1059663/2021 | 2021-09-12 | ST202108498211 | 2021-08-31 | P/FVC/MDS/1058568/2021 | 2021-09-10 |  |  |  |  | ST202108430499 | 2021-08-17 | P/FBW/MDS/1056057/2021 | 2021-09-07 | 0
533 | ABSHGP | ABSHGP | Puducherry | Trichy |  | ROTN | Indus | IN-3007553 | R/NN-626219 |  | On Air | 2021-08-13 | ABSHGP | 4G_FD900_ABSHGP | 4G_FD2100_ABSHGP | 4G_TD_ABSHGP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430712 | 2021-08-17 | P/FVC/MDS/1059664/2021 | 2021-09-12 | ST202108498212 | 2021-08-31 | P/FVC/MDS/1060459/2021 | 2021-09-13 |  |  |  |  | ST202108430500 | 2021-08-17 | P/FBW/MDS/1056058/2021 | 2021-09-07 | 0
534 | KALPET | KALPET | Puducherry | Trichy |  | ROTN | Indus | IN-3007902 | R/NN-626240 |  | On Air | 2021-08-10 | KALPET | 4G_FD900_KALPET | 4G_FD2100_KALPET | 4G_TD_KALPET | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430709 | 2021-08-17 | P/FVC/MDS/1059661/2021 | 2021-09-12 | ST202108498209 | 2021-08-31 | P/FVC/MDS/1058566/2021 | 2021-09-10 |  |  |  |  | ST202108430497 | 2021-08-17 | P/FBW/MDS/1056055/2021 | 2021-09-07 | 0
535 | NOKAMI | NOKAMI | Tiruvannamalai | Vellore |  | ROTN | Indus | IN-3007911 | R/NN-626243 |  | On Air | 2021-08-13 | NOKAMI | 4G_FD900_NOKAMI | 4G_FD2100_NOKAMI | 4G_TD_NOKAMI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430713 | 2021-08-17 | P/FVC/MDS/1059665/2021 | 2021-09-12 | ST202108498213 | 2021-08-31 | P/FVC/MDS/1060460/2021 | 2021-09-13 |  |  |  |  | ST202108430501 | 2021-08-17 | P/FBW/MDS/1056059/2021 | 2021-09-07 | 0
536 | ERAL02 | ERAL2 |  |  |  | ROTN | Indus | IN-1030643 | R/RES-502389 |  |  | 2021-08-10 | ERAL2 | 4G_FD900_ERAL2 | 4G_FD2100_ERAL2 | 4G_TD_ERAL2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202104209745 | 2021-04-30 | P/AFC/MDS/1019160/2021 | 2021-05-21 | ST202108498233 | 2021-08-31 | P/FVC/MDS/1060470/2021 | 2021-09-13 | ST202109499797 | 2021-09-01 | P/FVC/MDS/1060712/2021 | 2021-09-13 | ST202108430511 | 2021-08-17 | P/FBW/MDS/1056069/2021 | 2021-09-07
537 | MDTI36 | MDTI36 |  |  |  | ROTN | Indus | IN-3000694 | R/NN-619773 |  |  | 2021-08-13 | MDTI36 | 4G_FD900_MDTI36 | 4G_FD2100_MDTI36 | 4G_TD_MDTI36 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108430723 | 2021-08-17 | P/FVC/MDS/1059675/2021 | 2021-09-12 | ST202108498233 | 2021-08-31 | P/FVC/MDS/1060470/2021 | 2021-09-13 | ST202109512022 | 2021-09-07 | P/FVC/MDS/1061767/2021 | 2021-09-16 | ST202109513260 | 2021-09-08 | P/FBW/MDS/1061686/2021 | 2021-09-16 | 0
538 | HSR178 | HSR178 |  |  |  | ROTN | Indus | IN-3000579 | R/NN-619705 |  |  | 2021-08-13 | HSR178 | 4G_FD900_HSR178 | 4G_FD2100_HSR178 | 4G_TD_HSR178 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108430732 | 2021-08-17 | P/FVC/MDS/1059678/2021 | 2021-09-12 | ST202108498236 | 2021-08-31 | P/FVC/MDS/1060474/2021 | 2021-09-13 | ST202109512024 | 2021-09-07 | P/FVC/MDS/1061769/2021 | 2021-09-16 | ST202108430514 | 2021-08-17 | P/FBW/MDS/1056071/2021 | 2021-09-07 | 0
539 | MDU520 | MDU520 | Madurai | Madurai |  | ROTN | Indus | IN-3013604 | R/NN-626771 |  | On Air | 2021-08-17 | MDU520 | 4G_FD900_MDU520 | 4G_FD2100_MDU520 | 4G_TD_MDU520 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498624 | 2021-08-31 | P/FVC/MDS/1060416/2021 | 2021-09-13 | ST202108498270 | 2021-08-31 | P/FVC/MDS/1060484/2021 | 2021-09-13 | ST202212826797 | 2022-12-16 | P/AFC/MDS/1119528/2022 | 2022-12-22 | ST202109499902 | 2021-09-01 | P/FBW/MDS/1058574/2021 | 2021-09-10
540 | TIR400 | TIR400 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3009955 | R/NN-626476 |  | On Air | 2021-08-19 | TIR400 | 4G_FD900_TIR400 | 4G_FD2100_TIR400 | 4G_TD_TIR400 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498631 | 2021-08-31 | P/FVC/MDS/1060423/2021 | 2021-09-13 | ST202108498277 | 2021-08-31 | P/FVC/MDS/1060491/2021 | 2021-09-13 | ST202101007493 | 2021-01-10 | P/FVC/MDS/1009655/2021 | 2021-01-17 | ST202109499909 | 2021-09-01 | P/FBW/MDS/1060657/2021 | 2021-09-13
541 | MDRKR1 | MDRKR1 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3009996 | R/NN-626489 |  |  | 2021-08-19 | MDRKR1 | 4G_FD900_MDRKR1 | 4G_FD2100_MDRKR1 | 4G_TD_MDRKR1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498632 | 2021-08-31 | P/FVC/MDS/1060424/2021 | 2021-09-13 | ST202108498278 | 2021-08-31 | P/FVC/MDS/1060492/2021 | 2021-09-13 | ST202109511764 | 2021-09-07 | P/FVC/MDS/1061721/2021 | 2021-09-16 | ST202109499910 | 2021-09-01 | P/FBW/MDS/1060658/2021 | 2021-09-13
542 | PAKYKL | PAKYKL | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-TLVL-ENB-9029 | SR-TN000259 |  | On Air | 2021-08-19 | PAKYKL | 4G_FD900_PAKYKL | 4G_FD2100_PAKYKL | 4G_TD_PAKYKL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497387 | 2021-08-30 | P/FVC/MDS/1060360/2021 | 2021-09-13 | ST202108494562 | 2021-08-27 | P/FVC/MDS/1060313/2021 | 2021-09-13 | ST202108493816 | 2021-08-27 | P/FVC/MDS/1060266/2021 | 2021-09-13 | ST202108493648 | 2021-08-27 | P/FBW/MDS/1060219/2021 | 2021-09-13
543 | PAMAN1 | PAMAN1 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TTPN-ENB-9027 | SR-TN000258 |  | On Air | 2021-08-19 | PAMAN1 | 4G_FD900_PAMAN1 | 4G_FD2100_PAMAN1 | 4G_TD_PAMAN1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497388 | 2021-08-30 | P/FVC/MDS/1060361/2021 | 2021-09-13 | ST202108494563 | 2021-08-27 | P/FVC/MDS/1060314/2021 | 2021-09-13 | ST202108493817 | 2021-08-27 | P/FVC/MDS/1060267/2021 | 2021-09-13 | ST202108493649 | 2021-08-27 | P/FBW/MDS/1060220/2021 | 2021-09-13
544 | KCP126 | KCP126 | Kancheepuram | Chennai |  | ROTN | Airtel | - | - |  | SO | 2021-08-17 | KCP126 | 4G_FD900_KCP126 | 4G_FD2100_KCP126 | 4G_TD_KCP126 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498625 | 2021-08-31 | P/FVC/MDS/1060417/2021 | 2021-09-13 | ST202108498271 | 2021-08-31 | P/FVC/MDS/1060485/2021 | 2021-09-13 | ST202212811916 | 2022-12-14 | P/FVC/MDS/1119356/2022 | 2022-12-20 | ST202109499903 | 2021-09-01 | P/FBW/MDS/1060651/2021 | 2021-09-13
545 | VELLR4 | VELLR4 | Madurai | Madurai |  | ROTN | Indus | IN-3012380 | R/NN-626672 |  | On Air | 2021-08-19 | VELLR4 | 4G_FD900_VELLR4 | 4G_FD2100_VELLR4 | 4G_TD_VELLR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498635 | 2021-08-31 | P/FVC/MDS/1060426/2021 | 2021-09-13 | ST202108498288 | 2021-08-31 | P/FVC/MDS/1060497/2021 | 2021-09-13 | ST202109511765 | 2021-09-07 | P/FVC/MDS/1061722/2021 | 2021-09-16 | ST202109499912 | 2021-09-01 | P/FBW/MDS/1060660/2021 | 2021-09-13
546 | KYPT11 | KYPT11 | Thoothukkudi | Madurai |  | ROTN | ATC | TN/TH/AT/22701 | - |  | On Air | 2021-08-17 | KYPT11 | 4G_FD900_KYPT11 | 4G_FD2100_KYPT11 | 4G_TD_KYPT11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498627 | 2021-08-31 | P/FVC/MDS/1060419/2021 | 2021-09-13 | ST202108498273 | 2021-08-31 | P/FVC/MDS/1060487/2021 | 2021-09-13 |  |  |  |  | ST202109499905 | 2021-09-01 | P/FBW/MDS/1060653/2021 | 2021-09-13
547 | KRPNI7 | KRPNI7 | Madurai | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2021-08-17 | KRPNI7 | 4G_FD900_KRPNI7 | 4G_FD2100_KRPNI7 | 4G_TD_KRPNI7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498626 | 2021-08-31 | P/FVC/MDS/1060418/2021 | 2021-09-13 | ST202108498272 | 2021-08-31 | P/FVC/MDS/1060486/2021 | 2021-09-13 |  |  |  |  | ST202109499904 | 2021-09-01 | P/FBW/MDS/1060652/2021 | 2021-09-13
548 | MALAVT | MALAVT | Viluppuram | Trichy |  | ROTN | Indus | IN-3007554 | R/NN-626217 |  | On Air | 2021-08-17 | MALAVT | 4G_FD900_MALAVT | 4G_FD2100_MALAVT | 4G_TD_MALAVT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498619 | 2021-08-31 | P/FVC/MDS/1060414/2021 | 2021-09-13 | ST202108498263 | 2021-08-31 | P/FVC/MDS/1060482/2021 | 2021-09-13 |  |  |  |  | ST202109499900 | 2021-09-01 | P/FBW/MDS/1058572/2021 | 2021-09-10
549 | KRKDL4 | KRKDL4 | Puducherry | Trichy |  | ROTN | Indus | IN-3007565 | R/NN-626222 |  | On Air | 2021-08-17 | KRKDL4 | 4G_FD900_KRKDL4 | 4G_FD2100_KRKDL4 | 4G_TD_KRKDL4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498620 | 2021-08-31 | P/FVC/MDS/1060415/2021 | 2021-09-13 | ST202108498264 | 2021-08-31 | P/FVC/MDS/1060483/2021 | 2021-09-13 |  |  |  |  | ST202109499901 | 2021-09-01 | P/FBW/MDS/1058573/2021 | 2021-09-10
550 | KEZHAH | KEZHAH | Puducherry | Trichy |  | ROTN | Indus | IN-3007899 | R/NN-626239 |  | On Air | 2021-08-19 | KEZHAH | 4G_FD900_KEZHAH | 4G_FD2100_KEZHAH | 4G_TD_KEZHAH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498629 | 2021-08-31 | P/FVC/MDS/1060421/2021 | 2021-09-13 | ST202108498275 | 2021-08-31 | P/FVC/MDS/1060489/2021 | 2021-09-13 |  |  |  |  | ST202109499907 | 2021-09-01 | P/FBW/MDS/1060655/2021 | 2021-09-13
551 | PALPAT | PALPAT | Tiruvannamalai | Vellore |  | ROTN | Indus | IN-3008838 | R/NN-626273 |  | On Air | 2021-08-19 | PALPAT | 4G_FD900_PALPAT | 4G_FD2100_PALPAT | 4G_TD_PALPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498630 | 2021-08-31 | P/FVC/MDS/1060422/2021 | 2021-09-13 | ST202108498276 | 2021-08-31 | P/FVC/MDS/1060490/2021 | 2021-09-13 |  |  |  |  | ST202109499908 | 2021-09-01 | P/FBW/MDS/1060656/2021 | 2021-09-13
552 | MELAUR | MELAUR | Thoothukkudi | Madurai |  | ROTN | ATC | TN/TR/TT/15395 | - |  | On Air | 2021-08-17 | MELAUR | 4G_FD900_MELAUR | 4G_FD2100_MELAUR | 4G_TD_MELAUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498628 | 2021-08-31 | P/FVC/MDS/1060420/2021 | 2021-09-13 | ST202109501786 | 2021-09-02 | P/FVC/MDS/1060730/2021 | 2021-09-13 |  |  |  |  | ST202109499906 | 2021-09-01 | P/FBW/MDS/1060654/2021 | 2021-09-13
553 | FOXCN5 | FOXCN5 | Kancheepuram | Chennai |  | ROTN | Airtel | - | - |  | On Air |  | FOXCN5 | 4G_FD900_FOXCN5 | 4G_FD2100_FOXCN5 | 4G_TD_FOXCN5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202108498617 | 2021-08-31 | P/FVC/MDS/1060412/2021 | 2021-09-13 | ST202108498240 | 2021-08-31 | P/FVC/MDS/1060478/2021 | 2021-09-13 | ST202109499789 | 2021-09-01 | P/FVC/MDS/1060708/2021 | 2021-09-13 | ST202109499919 | 2021-09-01 | P/FBW/MDS/1060666/2021 | 2021-09-13
554 | KGPTI1 | KGPTI1 |  |  |  | ROTN | Indus | IN-1804221 | R/NN-564734 |  |  | 2021-08-17 | KGPTI1 | 4G_FD900_KGPTI1 | 4G_FD2100_KGPTI1 | 4G_TD_KGPTI1 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498638 | 2021-08-31 | P/FVC/MDS/1060429/2021 | 2021-09-13 | ST202109501788 | 2021-09-02 | P/FVC/MDS/1060731/2021 | 2021-09-13 | ST202109511766 | 2021-09-07 | P/FVC/MDS/1061723/2021 | 2021-09-16 | ST202109499914 | 2021-09-01 | P/FBW/MDS/1060661/2021 | 2021-09-13
555 | MDU84 | MDU84 |  |  |  | ROTN | Indus | IN-1746390 | R/NN-564566 |  |  | 2021-07-29 | MDU84 | 4G_FD900_MDU84 | 4G_FD2100_MDU84 | 4G_TD_MDU84 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504502 | 2021-09-02 | P/FVC/MDS/1060743/2021 | 2021-09-13 | ST202108498295 | 2021-08-31 | P/FVC/MDS/1060504/2021 | 2021-09-13 | ST202109511768 | 2021-09-07 | P/FVC/MDS/1061725/2021 | 2021-09-16 | ST202109499922 | 2021-09-01 | P/FBW/MDS/1060669/2021 | 2021-09-13
556 | TKLRR1 | TKLRR1 |  |  |  | ROTN | Indus | IN-1804220 | R/NN-564733 |  |  |  | TKLRR1 | 4G_FD900_TKLRR1 | 4G_FD2100_TKLRR1 | 4G_TD_TKLRR1 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504503 | 2021-09-02 | P/FVC/MDS/1060744/2021 | 2021-09-13 | ST202108498296 | 2021-08-31 | P/FVC/MDS/1060505/2021 | 2021-09-13 | ST202109511770 | 2021-09-07 | P/FVC/MDS/1061726/2021 | 2021-09-16 | ST202109499924 | 2021-09-01 | P/FBW/MDS/1060670/2021 | 2021-09-13
557 | MLVTN1 | MLVTN1 |  |  |  | ROTN | Indus | IN-3019929 | R/NN-627407 |  |  | 2021-08-19 | MLVTN1 | 4G_FD900_MLVTN1 | 4G_FD2100_MLVTN1 | 4G_TD_MLVTN1 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498641 | 2021-08-31 | P/FVC/MDS/1060432/2021 | 2021-09-13 | ST202109501790 | 2021-09-02 | P/FVC/MDS/1060733/2021 | 2021-09-13 | ST202109499787 | 2021-09-01 | P/FVC/MDS/1060706/2021 | 2021-09-13 | ST202109499917 | 2021-09-01 | P/FBW/MDS/1060664/2021 | 2021-09-13
558 | CHMPDA | CHMPDA |  |  |  | ROTN |  |  |  |  | On air |  | CHMPDA | 4G_FD900_CHMPDA | 4G_FD2100_CHMPDA | 4G_TD_CHMPDA | l900+L2300 | WPC ID Available L900+L2300 |  | ST202108498618 | 2021-08-31 | P/FVC/MDS/1060413/2021 | 2021-09-13 | ST202108498260 | 2021-08-31 | P/FVC/MDS/1060480/2021 | 2021-09-13 | ST202109499791 | 2021-09-01 | P/FVC/MDS/1060710/2021 | 2021-09-13 | ST202109499921 | 2021-09-01 | P/FBW/MDS/1060668/2021 | 2021-09-13
559 | SUNDT2 | SUNDT2 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBS-ENB-0011 | SR-TN000251 |  | On Air | 2021-08-23 | SUNDT2 | 4G_FD900_SUNDT2 | 4G_FD2100_SUNDT2 | 4G_TD_SUNDT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497369 | 2021-08-30 | P/FVC/MDS/1060345/2021 | 2021-09-13 | ST202108494508 | 2021-08-27 | P/FVC/MDS/1060298/2021 | 2021-09-13 | ST202108493800 | 2021-08-27 | P/FVC/MDS/1060251/2021 | 2021-09-13 | ST202108493625 | 2021-08-27 | P/FBW/MDS/1060204/2021 | 2021-09-13
560 | KYNGR2 | KYNGR2 | Salem | Vellore |  | ROTN | Summit | I-TN-ATTR-ENB-9070 | SR-TN000254 |  | On Air | 2021-08-26 | KYNGR2 | 4G_FD900_KYNGR2 | 4G_FD2100_KYNGR2 | 4G_TD_KYNGR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497363 | 2021-08-30 | P/FVC/MDS/1060340/2021 | 2021-09-13 | ST202108494503 | 2021-08-27 | P/FVC/MDS/1060293/2021 | 2021-09-13 | ST202108493784 | 2021-08-27 | P/FVC/MDS/1060246/2021 | 2021-09-13 | ST202109513240 | 2021-09-08 | P/FBW/MDS/1061666/2021 | 2021-09-16
561 | ANIPAT | ANIPAT | Madurai | Madurai |  | ROTN | Summit | I-TN-PRYU-ENB-9034 | SR-TN000267 |  | On Air | 2021-08-26 | ANIPAT | 4G_FD900_ANIPAT | 4G_FD2100_ANIPAT | 4G_TD_ANIPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497384 | 2021-08-30 | P/FVC/MDS/1060357/2021 | 2021-09-13 | ST202108494559 | 2021-08-27 | P/FVC/MDS/1060310/2021 | 2021-09-13 | ST202108493812 | 2021-08-27 | P/FVC/MDS/1060263/2021 | 2021-09-13 | ST202108493640 | 2021-08-27 | P/FBW/MDS/1060216/2021 | 2021-09-13
562 | THEROR | THEROR | Kanniyakumari | Madurai |  | ROTN | Summit | I-TN-AGST-ENB-9036 | SR-TN000271 |  | On Air | 2021-08-26 | THEROR | 4G_FD900_THEROR | 4G_FD2100_THEROR | 4G_TD_THEROR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497361 | 2021-08-30 | P/FVC/MDS/1060338/2021 | 2021-09-13 | ST202108494501 | 2021-08-27 | P/FVC/MDS/1060291/2021 | 2021-09-13 | ST202108493782 | 2021-08-27 | P/FVC/MDS/1060244/2021 | 2021-09-13 | ST202108493618 | 2021-08-27 | P/FBW/MDS/1060197/2021 | 2021-09-13
563 | PALYAM | PALYAM | Erode | Coimbatore |  | ROTN | Summit | I-TN-GBPM-ENB-9059 | SR-TN000274 |  | On Air | 2021-08-26 | PALYAM | 4G_FD900_PALYAM | 4G_FD2100_PALYAM | 4G_TD_PALYAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497377 | 2021-08-30 | P/FVC/MDS/1060350/2021 | 2021-09-13 | ST202108494552 | 2021-08-27 | P/FVC/MDS/1060303/2021 | 2021-09-13 | ST202108493805 | 2021-08-27 | P/FVC/MDS/1060256/2021 | 2021-09-13 | ST202108493633 | 2021-08-27 | P/FBW/MDS/1060209/2021 | 2021-09-13
564 | KAVAL2 | KAVAL2 | Dindigul | Coimbatore |  | ROTN | Summit | I-TN-ODCT-ENB-9047 | SR-TN000272 |  | On Air | 2021-08-26 | KAVAL2 | 4G_FD900_KAVAL2 | 4G_FD2100_KAVAL2 | 4G_TD_KAVAL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497383 | 2021-08-30 | P/FVC/MDS/1060356/2021 | 2021-09-13 | ST202108494558 | 2021-08-27 | P/FVC/MDS/1060309/2021 | 2021-09-13 | ST202108493811 | 2021-08-27 | P/FVC/MDS/1060262/2021 | 2021-09-13 | ST202108493639 | 2021-08-27 | P/FBW/MDS/1060215/2021 | 2021-09-13
565 | MINKAL | MINKAL | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TYMA-ENB-9004 | SR-TN000273 |  | On Air | 2021-08-26 | MINKAL | 4G_FD900_MINKAL | 4G_FD2100_MINKAL | 4G_TD_MINKAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497390 | 2021-08-30 | P/FVC/MDS/1060363/2021 | 2021-09-13 | ST202108494565 | 2021-08-27 | P/FVC/MDS/1060316/2021 | 2021-09-13 | ST202108493819 | 2021-08-27 | P/FVC/MDS/1060269/2021 | 2021-09-13 | ST202108493651 | 2021-08-27 | P/FBW/MDS/1060222/2021 | 2021-09-13
566 | CHETT2 | CHETT2 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBR-ENB-0584 | SR-TN000279 |  | On Air | 2021-08-26 | CHETT2 | 4G_FD900_CHETT2 | 4G_FD2100_CHETT2 | 4G_TD_CHETT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497368 | 2021-08-30 | P/FVC/MDS/1060344/2021 | 2021-09-13 | ST202108494507 | 2021-08-27 | P/FVC/MDS/1060297/2021 | 2021-09-13 | ST202108493788 | 2021-08-27 | P/FVC/MDS/1060250/2021 | 2021-09-13 | ST202108493624 | 2021-08-27 | P/FBW/MDS/1060203/2021 | 2021-09-13
567 | VELKAN | VELKAN | Tiruchirappalli | Trichy |  | ROTN | Summit | I-TN-MUSR-ENB-9057 | SR-TN000277 |  | On Air | 2021-08-26 | VELKAN | 4G_FD900_VELKAN | 4G_FD2100_VELKAN | 4G_TD_VELKAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497380 | 2021-08-30 | P/FVC/MDS/1060353/2021 | 2021-09-13 | ST202108494555 | 2021-08-27 | P/FVC/MDS/1060306/2021 | 2021-09-13 | ST202108493808 | 2021-08-27 | P/FVC/MDS/1060259/2021 | 2021-09-13 | ST202108493636 | 2021-08-27 | P/FBW/MDS/1060212/2021 | 2021-09-13
568 | MDU479 | MDU479 | Madurai | Madurai |  | ROTN | Summit | I-TN-NMDK-ENB-9002 |  |  | On Air |  | MDU479 | 4G_FD900_MDU479 | 4G_FD2100_MDU479 | 4G_TD_MDU479 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109527660 | 2021-09-22 | P/FVC/MDS/1062662/2021 | 2021-09-29 | ST202109526856 | 2021-09-21 | P/FVC/MDS/1062609/2021 | 2021-09-29 | ST202108493810 | 2021-08-27 | P/FVC/MDS/1060261/2021 | 2021-09-13 | ST202109527549 | 2021-09-22 | P/FBW/MDS/1062553/2021 | 2021-09-27
569 | VGPTI2 | VGPTI2 | Theni | Madurai |  | ROTN | Summit | I-TN-VDGP-ENB-9002 | SR-TN000255 |  | On Air |  | VGPTI2 | 4G_FD900_VGPTI2 | 4G_FD2100_VGPTI2 | 4G_TD_VGPTI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497391 | 2021-08-30 | P/FVC/MDS/1060364/2021 | 2021-09-13 | ST202108494566 | 2021-08-27 | P/FVC/MDS/1060317/2021 | 2021-09-13 | ST202108493820 | 2021-08-27 | P/FVC/MDS/1060270/2021 | 2021-09-13 | ST202108493652 | 2021-08-27 | P/FBW/MDS/1060223/2021 | 2021-09-13
570 | PAYNAM | PAYNAM | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-SVUR-ENB-9042 | SR-TN000269 |  | On Air |  | PAYNAM | 4G_FD900_PAYNAM | 4G_FD2100_PAYNAM | 4G_TD_PAYNAM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497386 | 2021-08-30 | P/FVC/MDS/1060359/2021 | 2021-09-13 | ST202108494561 | 2021-08-27 | P/FVC/MDS/1060312/2021 | 2021-09-13 | ST202108493815 | 2021-08-27 | P/FVC/MDS/1060265/2021 | 2021-09-13 | ST202108493642 | 2021-08-27 | P/FBW/MDS/1060218/2021 | 2021-09-13
571 | PAKANA | PAKANA | The Nilgiris | Coimbatore |  | ROTN | Summit | I-TN-PTLR-ENB-9020 | SR-TN000266 |  | On Air |  | PAKANA | 4G_FD900_PAKANA | 4G_FD2100_PAKANA | 4G_TD_PAKANA | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497385 | 2021-08-30 | P/FVC/MDS/1060358/2021 | 2021-09-13 | ST202108494560 | 2021-08-27 | P/FVC/MDS/1060311/2021 | 2021-09-13 | ST202108493813 | 2021-08-27 | P/FVC/MDS/1060264/2021 | 2021-09-13 | ST202108493641 | 2021-08-27 | P/FBW/MDS/1060217/2021 | 2021-09-13
572 | KIRUSH | KIRUSH | Erode | Coimbatore |  | ROTN | Summit | I-TN-BHVN-ENB-9053 | SR-TN000275 |  | On Air |  | KIRUSH | 4G_FD900_KIRUSH | 4G_FD2100_KIRUSH | 4G_TD_KIRUSH | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497366 | 2021-08-30 | P/FVC/MDS/1060342/2021 | 2021-09-13 | ST202108494505 | 2021-08-27 | P/FVC/MDS/1060295/2021 | 2021-09-13 | ST202108493786 | 2021-08-27 | P/FVC/MDS/1060248/2021 | 2021-09-13 | ST202108493622 | 2021-08-27 | P/FBW/MDS/1060201/2021 | 2021-09-13
573 | MADKAR | MADKAR | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBS-ENB-9041 | SR-TN000268 |  | On Air |  | MADKAR | 4G_FD900_MADKAR | 4G_FD2100_MADKAR | 4G_TD_MADKAR | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497373 | 2021-08-30 | P/FVC/MDS/1060346/2021 | 2021-09-13 | ST202108494509 | 2021-08-27 | P/FVC/MDS/1060299/2021 | 2021-09-13 | ST202108493801 | 2021-08-27 | P/FVC/MDS/1060252/2021 | 2021-09-13 | ST202108493626 | 2021-08-27 | P/FBW/MDS/1060205/2021 | 2021-09-13
574 | SRIMAD | SRIMAD | The Nilgiris | Coimbatore |  | ROTN | Summit | I-TN-GDLR-ENB-9022 | SR-TN000270 |  | On Air |  | SRIMAD | 4G_FD900_SRIMAD | 4G_FD2100_SRIMAD | 4G_TD_SRIMAD | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498666 | 2021-08-31 | P/FVC/MDS/1060454/2021 | 2021-09-13 | ST202108498274 | 2021-08-31 | P/FVC/MDS/1060488/2021 | 2021-09-13 | ST202109499800 | 2021-09-01 | P/FVC/MDS/1060715/2021 | 2021-09-13 | ST202109499929 | 2021-09-01 | P/FBW/MDS/1060675/2021 | 2021-09-13
575 | AMERI2 | AMERI2 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-VDCM-ENB-9074 | SR-TN000286 |  | On Air |  | AMERI2 | 4G_FD900_AMERI2 | 4G_FD2100_AMERI2 | 4G_TD_AMERI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497336 | 2021-08-30 | P/FVC/MDS/1060319/2021 | 2021-09-13 | ST202108494306 | 2021-08-27 | P/FVC/MDS/1060272/2021 | 2021-09-13 | ST202108493758 | 2021-08-27 | P/FVC/MDS/1060225/2021 | 2021-09-13 | ST202108493597 | 2021-08-27 | P/FBW/MDS/1060178/2021 | 2021-09-13
576 | KULYAN | KULYAN | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-VKMP-ENB-9022 | SR-TN000299 |  | On Air |  | KULYAN | 4G_FD900_KULYAN | 4G_FD2100_KULYAN | 4G_TD_KULYAN | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497340 | 2021-08-30 | P/FVC/MDS/1060323/2021 | 2021-09-13 | ST202108494314 | 2021-08-27 | P/FVC/MDS/1060276/2021 | 2021-09-13 | ST202108493762 | 2021-08-27 | P/FVC/MDS/1060229/2021 | 2021-09-13 | ST202108493601 | 2021-08-27 | P/FBW/MDS/1060182/2021 | 2021-09-13
577 | SHARAM | SHARAM | Theni | Madurai |  | ROTN | Summit | I-TN-ADPJ-ENB-9040 | SR-TN000300 |  | On Air |  | SHARAM | 4G_FD900_SHARAM | 4G_FD2100_SHARAM | 4G_TD_SHARAM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497355 | 2021-08-30 | P/FVC/MDS/1060333/2021 | 2021-09-13 | ST202108494496 | 2021-08-27 | P/FVC/MDS/1060286/2021 | 2021-09-13 | ST202108493774 | 2021-08-27 | P/FVC/MDS/1060239/2021 | 2021-09-13 | ST202108493611 | 2021-08-27 | P/FBW/MDS/1060192/2021 | 2021-09-13
578 | VIRSAN | VIRSAN | Madurai | Madurai |  | ROTN | Summit | I-TN-MDUR-ENB-9028 | SR-TN000293 |  | On Air |  | VIRSAN | 4G_FD900_VIRSAN | 4G_FD2100_VIRSAN | 4G_TD_VIRSAN | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497332 | 2021-08-30 | P/FVC/MDS/1058516/2021 | 2021-09-10 | ST202108494302 | 2021-08-27 | P/FVC/MDS/1058513/2021 | 2021-09-10 | ST202108493754 | 2021-08-27 | P/FVC/MDS/1058510/2021 | 2021-09-10 | ST202108493593 | 2021-08-27 | P/FBW/MDS/1058507/2021 | 2021-09-10
579 | TCGD47 | TCGD47 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9042 | SR-TN000285 |  | On Air |  | TCGD47 | 4G_FD900_TCGD47 | 4G_FD2100_TCGD47 | 4G_TD_TCGD47 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497351 | 2021-08-30 | P/FVC/MDS/1060329/2021 | 2021-09-13 | ST202108494491 | 2021-08-27 | P/FVC/MDS/1060282/2021 | 2021-09-13 | ST202108493770 | 2021-08-27 | P/FVC/MDS/1060235/2021 | 2021-09-13 | ST202108493607 | 2021-08-27 | P/FBW/MDS/1060188/2021 | 2021-09-13
580 | KADIOR | KADIOR | Salem | Vellore |  | ROTN | Summit | I-TN-OMLR-ENB-9073 | SR-TN000303 |  | On Air |  | KADIOR | 4G_FD900_KADIOR | 4G_FD2100_KADIOR | 4G_TD_KADIOR | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497352 | 2021-08-30 | P/FVC/MDS/1060330/2021 | 2021-09-13 | ST202108494492 | 2021-08-27 | P/FVC/MDS/1060283/2021 | 2021-09-13 | ST202108493771 | 2021-08-27 | P/FVC/MDS/1060236/2021 | 2021-09-13 | ST202108493608 | 2021-08-27 | P/FBW/MDS/1060189/2021 | 2021-09-13
581 | KOTDUR | KOTDUR | Viluppuram | Trichy |  | ROTN | Summit | I-TN-TRKY-ENB-9070 | SR-TN000291 |  | On Air |  | KOTDUR | 4G_FD900_KOTDUR | 4G_FD2100_KOTDUR | 4G_TD_KOTDUR | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497354 | 2021-08-30 | P/FVC/MDS/1060332/2021 | 2021-09-13 | ST202108494495 | 2021-08-27 | P/FVC/MDS/1060285/2021 | 2021-09-13 | ST202108493773 | 2021-08-27 | P/FVC/MDS/1060238/2021 | 2021-09-13 | ST202108493610 | 2021-08-27 | P/FBW/MDS/1060191/2021 | 2021-09-13
582 | NATPAM | NATPAM | Vellore | Vellore |  | ROTN | Summit | I-TN-VMBD-ENB-9049 | SR-TN000294 |  | On Air |  | NATPAM | 4G_FD900_NATPAM | 4G_FD2100_NATPAM | 4G_TD_NATPAM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497333 | 2021-08-30 | P/FVC/MDS/1058517/2021 | 2021-09-10 | ST202108494303 | 2021-08-27 | P/FVC/MDS/1058514/2021 | 2021-09-10 | ST202108493755 | 2021-08-27 | P/FVC/MDS/1058511/2021 | 2021-09-10 | ST202108493594 | 2021-08-27 | P/FBW/MDS/1058508/2021 | 2021-09-10
583 | KANSAM | KANSAM | Theni | Madurai |  | ROTN | Summit | I-TN-UTMP-ENB-9050 | SR-TN000297 |  | On Air |  | KANSAM | 4G_FD900_KANSAM | 4G_FD2100_KANSAM | 4G_TD_KANSAM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497357 | 2021-08-30 | P/FVC/MDS/1060334/2021 | 2021-09-13 | ST202108494497 | 2021-08-27 | P/FVC/MDS/1060287/2021 | 2021-09-13 | ST202108493775 | 2021-08-27 | P/FVC/MDS/1060240/2021 | 2021-09-13 | ST202108493612 | 2021-08-27 | P/FBW/MDS/1060193/2021 | 2021-09-13
584 | MUNIYA | MUNIYA | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9054 | SR-TN000302 |  | On Air |  | MUNIYA | 4G_FD900_MUNIYA | 4G_FD2100_MUNIYA | 4G_TD_MUNIYA | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497358 | 2021-08-30 | P/FVC/MDS/1060335/2021 | 2021-09-13 | ST202108494498 | 2021-08-27 | P/FVC/MDS/1060288/2021 | 2021-09-13 | ST202108493776 | 2021-08-27 | P/FVC/MDS/1060241/2021 | 2021-09-13 | ST202108493613 | 2021-08-27 | P/FBW/MDS/1060194/2021 | 2021-09-13
585 | VALYAM | VALYAM | Salem | Vellore |  | ROTN | Summit | I-TN-GGVL-ENB-9010 | SR-TN000296 |  | On Air |  | VALYAM | 4G_FD900_VALYAM | 4G_FD2100_VALYAM | 4G_TD_VALYAM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497359 | 2021-08-30 | P/FVC/MDS/1060336/2021 | 2021-09-13 | ST202108494499 | 2021-08-27 | P/FVC/MDS/1060289/2021 | 2021-09-13 | ST202108493777 | 2021-08-27 | P/FVC/MDS/1060242/2021 | 2021-09-13 | ST202108493616 | 2021-08-27 | P/FBW/MDS/1060195/2021 | 2021-09-13
586 | SAMRAM | SAMRAM | Salem | Vellore |  | ROTN | Summit | I-TN-EDPD-ENB-9030 | SR-TN000298 |  | On Air |  | SAMRAM | 4G_FD900_SAMRAM | 4G_FD2100_SAMRAM | 4G_TD_SAMRAM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497349 | 2021-08-30 | P/FVC/MDS/1060327/2021 | 2021-09-13 | ST202108494487 | 2021-08-27 | P/FVC/MDS/1060280/2021 | 2021-09-13 | ST202108493768 | 2021-08-27 | P/FVC/MDS/1060233/2021 | 2021-09-13 | ST202108493605 | 2021-08-27 | P/FBW/MDS/1060186/2021 | 2021-09-13
587 | BAGUTH | BAGUTH | Erode | Coimbatore |  | ROTN | Summit | I-TN-SMNG-ENB-9057 | SR-TN000289 |  | On Air |  | BAGUTH | 4G_FD900_BAGUTH | 4G_FD2100_BAGUTH | 4G_TD_BAGUTH | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497337 | 2021-08-30 | P/FVC/MDS/1060320/2021 | 2021-09-13 | ST202108494307 | 2021-08-27 | P/FVC/MDS/1060273/2021 | 2021-09-13 | ST202108493759 | 2021-08-27 | P/FVC/MDS/1060226/2021 | 2021-09-13 | ST202108493598 | 2021-08-27 | P/FBW/MDS/1060179/2021 | 2021-09-13
588 | VALPAT | VALPAT | Vellore | Vellore |  | ROTN | Summit | I-TN-VMBD-ENB-9059 | SR-TN000284 |  | On Air |  | VALPAT | 4G_FD900_VALPAT | 4G_FD2100_VALPAT | 4G_TD_VALPAT | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497353 | 2021-08-30 | P/FVC/MDS/1060331/2021 | 2021-09-13 | ST202108494494 | 2021-08-27 | P/FVC/MDS/1060284/2021 | 2021-09-13 | ST202108493772 | 2021-08-27 | P/FVC/MDS/1060237/2021 | 2021-09-13 | ST202108493609 | 2021-08-27 | P/FBW/MDS/1060190/2021 | 2021-09-13
589 | CHIMAL | CHIMAL | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-KGRI-ENB-9115 | SR-TN000301 |  | On Air |  | CHIMAL | 4G_FD900_CHIMAL | 4G_FD2100_CHIMAL | 4G_TD_CHIMAL | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497350 | 2021-08-30 | P/FVC/MDS/1060328/2021 | 2021-09-13 | ST202108494490 | 2021-08-27 | P/FVC/MDS/1060281/2021 | 2021-09-13 | ST202108493769 | 2021-08-27 | P/FVC/MDS/1060234/2021 | 2021-09-13 | ST202108493606 | 2021-08-27 | P/FBW/MDS/1060187/2021 | 2021-09-13
590 | VILVAM | VILVAM | Thoothukkudi | Madurai |  | ROTN | Summit | I-TN-VLTK-ENB-9048 | SR-TN000295 |  | On Air |  | VILVAM | 4G_FD900_VILVAM | 4G_FD2100_VILVAM | 4G_TD_VILVAM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497335 | 2021-08-30 | P/FVC/MDS/1060318/2021 | 2021-09-13 | ST202108494305 | 2021-08-27 | P/FVC/MDS/1060271/2021 | 2021-09-13 | ST202108493757 | 2021-08-27 | P/FVC/MDS/1060224/2021 | 2021-09-13 | ST202108493596 | 2021-08-27 | P/FBW/MDS/1060177/2021 | 2021-09-13
591 | KARALA | KARALA | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TVLR-ENB-9116 | SR-TN000290 |  | On Air |  | KARALA | 4G_FD900_KARALA | 4G_FD2100_KARALA | 4G_TD_KARALA | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201014702 | 2022-01-20 | P/FVC/MDS/1072398/2022 | 2022-01-31 | ST202108494311 | 2021-08-27 | P/FVC/MDS/1060274/2021 | 2021-09-13 | ST202108493760 | 2021-08-27 | P/FVC/MDS/1060227/2021 | 2021-09-13 | ST202108493599 | 2021-08-27 | P/FBW/MDS/1060180/2021 | 2021-09-13
592 | ARURPT | ARURPT | Salem | Vellore |  | ROTN | Summit | I-TN-OMLR-ENB-9082 | SR-TN000287 |  | On Air |  | ARURPT | 4G_FD900_ARURPT | 4G_FD2100_ARURPT | 4G_TD_ARURPT | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497341 | 2021-08-30 | P/FVC/MDS/1060324/2021 | 2021-09-13 | ST202108494315 | 2021-08-27 | P/FVC/MDS/1060277/2021 | 2021-09-13 | ST202108493763 | 2021-08-27 | P/FVC/MDS/1060230/2021 | 2021-09-13 | ST202108493602 | 2021-08-27 | P/FBW/MDS/1060183/2021 | 2021-09-13
593 | THENKR | THENKR | Viluppuram | Trichy |  | ROTN | Summit | I-TN-KLKC-ENB-9084 | SR-TN000288 |  | On Air |  | THENKR | 4G_FD900_THENKR | 4G_FD2100_THENKR | 4G_TD_THENKR | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497360 | 2021-08-30 | P/FVC/MDS/1060337/2021 | 2021-09-13 | ST202108494500 | 2021-08-27 | P/FVC/MDS/1060290/2021 | 2021-09-13 | ST202108493781 | 2021-08-27 | P/FVC/MDS/1060243/2021 | 2021-09-13 | ST202108493617 | 2021-08-27 | P/FBW/MDS/1060196/2021 | 2021-09-13
594 | MANGA2 | MANGA2 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TTPN-ENB-9045 | SR-TN000292 |  | On Air |  | MANGA2 | 4G_FD900_MANGA2 | 4G_FD2100_MANGA2 | 4G_TD_MANGA2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108497339 | 2021-08-30 | P/FVC/MDS/1060322/2021 | 2021-09-13 | ST202108494312 | 2021-08-27 | P/FVC/MDS/1060275/2021 | 2021-09-13 | ST202108493761 | 2021-08-27 | P/FVC/MDS/1060228/2021 | 2021-09-13 | ST202108493600 | 2021-08-27 | P/FBW/MDS/1060181/2021 | 2021-09-13
595 | VDSRM6 | VDSRM6 | Dindigul | Coimbatore |  | ROTN | Summit | I-TN-VDSD-ENB-9066 | - |  | On Air |  | VDSRM6 | 4G_FD900_VDSRM6 | 4G_FD2100_VDSRM6 | 4G_TD_VDSRM6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504559 | 2021-09-02 | P/FVC/MDS/1060780/2021 | 2021-09-13 | ST202109501792 | 2021-09-02 | P/FVC/MDS/1060735/2021 | 2021-09-13 | ST202109499776 | 2021-09-01 | P/FVC/MDS/1058575/2021 | 2021-09-10 | ST202109499935 | 2021-09-01 | P/FBW/MDS/1060681/2021 | 2021-09-13
596 | TEPPAT | TEPPAT | Salem | Vellore |  | ROTN | Summit | I-TN-VLPD-ENB-9039 | - |  | On Air |  | TEPPAT | 4G_FD900_TEPPAT | 4G_FD2100_TEPPAT | 4G_TD_TEPPAT | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504560 | 2021-09-02 | P/FVC/MDS/1060781/2021 | 2021-09-13 | ST202109501794 | 2021-09-02 | P/FVC/MDS/1060736/2021 | 2021-09-13 | ST202109499777 | 2021-09-01 | P/FVC/MDS/1058576/2021 | 2021-09-10 | ST202109499937 | 2021-09-01 | P/FBW/MDS/1060682/2021 | 2021-09-13
597 | PANDI3 | PANDI3 | Tiruvannamalai | Vellore |  | ROTN | Summit | I-TN-TVML-ENB-9072 | - |  | On Air |  | PANDI3 | 4G_FD900_PANDI3 | 4G_FD2100_PANDI3 | 4G_TD_PANDI3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504561 | 2021-09-02 | P/FVC/MDS/1060782/2021 | 2021-09-13 | ST202109501795 | 2021-09-02 | P/FVC/MDS/1060737/2021 | 2021-09-13 | ST202109499778 | 2021-09-01 | P/FVC/MDS/1058577/2021 | 2021-09-10 | ST202109499938 | 2021-09-01 | P/FBW/MDS/1060683/2021 | 2021-09-13
598 | TENKAR | TENKAR | Tiruvannamalai | Vellore |  | ROTN | Summit | I-TN-TDMT-ENB-9038 | - |  | On Air |  | TENKAR | 4G_FD900_TENKAR | 4G_FD2100_TENKAR | 4G_TD_TENKAR | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504562 | 2021-09-02 | P/FVC/MDS/1060783/2021 | 2021-09-13 | ST202109501796 | 2021-09-02 | P/FVC/MDS/1060738/2021 | 2021-09-13 | ST202109499781 | 2021-09-01 | P/FVC/MDS/1060700/2021 | 2021-09-13 | ST202109499939 | 2021-09-01 | P/FBW/MDS/1060684/2021 | 2021-09-13
599 | KOTTAN | KOTTAN | Salem | Vellore |  | ROTN | Summit | I-TN-SLEM-ENB-9037 | - |  | On Air |  | KOTTAN | 4G_FD900_KOTTAN | 4G_FD2100_KOTTAN | 4G_TD_KOTTAN | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504563 | 2021-09-02 | P/FVC/MDS/1060784/2021 | 2021-09-13 | ST202109501820 | 2021-09-02 | P/FVC/MDS/1060739/2021 | 2021-09-13 | ST202109499783 | 2021-09-01 | P/FVC/MDS/1060702/2021 | 2021-09-13 | ST202109499940 | 2021-09-01 | P/FBW/MDS/1060685/2021 | 2021-09-13
600 | SEMPAT | SEMPAT | Madurai | Madurai |  | ROTN | Summit | I-TN-VDPT-ENB-0001 | - |  | On Air |  | SEMPAT | 4G_FD900_SEMPAT | 4G_FD2100_SEMPAT | 4G_TD_SEMPAT | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504569 | 2021-09-02 | P/FVC/MDS/1060787/2021 | 2021-09-13 | ST202109501821 | 2021-09-02 | P/FVC/MDS/1060740/2021 | 2021-09-13 | ST202109499784 | 2021-09-01 | P/FVC/MDS/1060703/2021 | 2021-09-13 | ST202109499941 | 2021-09-01 | P/FBW/MDS/1060686/2021 | 2021-09-13
601 | PUTHUM | PUTHUM | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-RDHP-ENB-9064 | - |  | On Air |  | PUTHUM | 4G_FD900_PUTHUM | 4G_FD2100_PUTHUM | 4G_TD_PUTHUM | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109504509 | 2021-09-02 | P/FVC/MDS/1060748/2021 | 2021-09-13 | ST202109501822 | 2021-09-02 | P/FVC/MDS/1060741/2021 | 2021-09-13 | ST202109499785 | 2021-09-01 | P/FVC/MDS/1060704/2021 | 2021-09-13 | ST202109499942 | 2021-09-01 | P/FBW/MDS/1060687/2021 | 2021-09-13
602 | KURGUL | KURGUL | Thanjavur | Trichy |  | ROTN | Summit | I-TN-TJVR-ENB-9042 | - |  | On Air |  | KURGUL | 4G_FD900_KURGUL | 4G_FD2100_KURGUL | 4G_TD_KURGUL | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202108498670 | 2021-08-31 | P/FVC/MDS/1060458/2021 | 2021-09-13 | ST202108498285 | 2021-08-31 | P/FVC/MDS/1060494/2021 | 2021-09-13 | ST202109499810 | 2021-09-01 | P/FVC/MDS/1060724/2021 | 2021-09-13 | ST202109499934 | 2021-09-01 | P/FBW/MDS/1060680/2021 | 2021-09-13
603 | RTHPM4 | RTHPM4 |  |  |  | ROTN | Indus | IN-3003832 | R/NN-620879 |  |  | 2021-09-04 | RTHPM4 | 4G_FD900_RTHPM4 | 4G_FD2100_RTHPM4 | 4G_TD_RTHPM4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109512267 | 2021-09-07 | P/FVC/MDS/1061717/2021 | 2021-09-16 | ST202109526841 | 2021-09-21 | P/FVC/MDS/1062602/2021 | 2021-09-29 | ST202109512018 | 2021-09-07 | P/FVC/MDS/1061762/2021 | 2021-09-16 | ST202109513256 | 2021-09-08 | P/FBW/MDS/1061682/2021 | 2021-09-16
604 | ADMGM2 | ADMGM2 |  |  |  | ROTN | Indus | IN-3005045 | R/NN-625908 |  |  | 2021-09-04 | ADMGM2 | 4G_FD900_ADMGM2 | 4G_FD2100_ADMGM2 | 4G_TD_ADMGM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109512268 | 2021-09-07 | P/FVC/MDS/1061718/2021 | 2021-09-16 | ST202109526850 | 2021-09-21 | P/FVC/MDS/1062603/2021 | 2021-09-29 | ST202109512019 | 2021-09-07 | P/FVC/MDS/1061763/2021 | 2021-09-16 | ST202109513257 | 2021-09-08 | P/FBW/MDS/1061683/2021 | 2021-09-16
605 | MUKADU | MUKADU | Pudukkottai | Trichy |  | ROTN | Indus | IN-3021158 | R/NN-627495 |  | On Air | 2021-09-04 | MUKADU | 4G_FD900_MUKADU | 4G_FD2100_MUKADU | 4G_TD_MUKADU | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512262 | 2021-09-07 | P/FVC/MDS/1061712/2021 | 2021-09-16 | ST202109522198 | 2021-09-16 | P/FVC/MDS/1062456/2021 | 2021-09-23 | ST202109512013 | 2021-09-07 | P/FVC/MDS/1061757/2021 | 2021-09-16 | ST202109513251 | 2021-09-08 | P/FBW/MDS/1061677/2021 | 2021-09-16
606 | PUDPET | PUDPET | Cuddalore | Trichy |  | ROTN | ATC | TN/PO/TT/15153 | - |  | On Air | 2021-09-04 | PUDPET | 4G_FD900_PUDPET | 4G_FD2100_PUDPET | 4G_TD_PUDPET | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497334 | 2021-08-30 | P/FVC/MDS/1058518/2021 | 2021-09-10 | ST202108494304 | 2021-08-27 | P/FVC/MDS/1058515/2021 | 2021-09-10 | ST202108493756 | 2021-08-27 | P/FVC/MDS/1058512/2021 | 2021-09-10 | ST202108493595 | 2021-08-27 | P/FBW/MDS/1058509/2021 | 2021-09-10
607 | PARMTV | PARMTV | Namakkal | Coimbatore |  | ROTN | Indus | IN-3025967 | R/NN-627762 |  | On Air | 2021-09-04 | PARMTV | 4G_FD900_PARMTV | 4G_FD2100_PARMTV | 4G_TD_PARMTV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109512263 | 2021-09-07 | P/FVC/MDS/1061713/2021 | 2021-09-16 | ST202109522199 | 2021-09-16 | P/FVC/MDS/1062457/2021 | 2021-09-23 | ST202109512014 | 2021-09-07 | P/FVC/MDS/1061758/2021 | 2021-09-16 | ST202109513252 | 2021-09-08 | P/FBW/MDS/1061678/2021 | 2021-09-16
608 | TAMBW7 | TAMBW7 | chennai | chennai |  | CHN | Indus | IN-3025346 | R/NN-619680 |  | On air | 2021-09-09 | TAMBW7 | 4G_FD900_TAMBW7 | 4G_FD2100_TAMBW7 | 4G_TD_TAMBW7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522084 | 2021-09-16 | P/FVC/MDS/1062422/2021 | 2021-09-23 | ST202109522211 | 2021-09-16 | P/FVC/MDS/1062469/2021 | 2021-09-23 | ST202109530019 | 2021-09-24 | P/FVC/MDS/1063005/2021 | 2021-10-01 | ST202109522265 | 2021-09-16 | P/FBW/MDS/1062516/2021 | 2021-09-23
609 | BHAR16 | BHAR16 | chennai | chennai |  | CHN | Indus | IN-3003846 | R/NN-621174 |  |  | 2021-09-04 | BHAR16 | 4G_FD900_BHAR16 | 4G_FD2100_BHAR16 | 4G_TD_BHAR16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110567676 | 2021-10-22 | P/FVC/MDS/1066517/2021 | 2021-11-19 | ST202102036297 | 2021-02-03 | P/FVC/MDS/1013040/2021 | 2021-03-16 | ST202102042365 | 2021-02-08 | P/FVC/MDS/1013261/2021 | 2021-03-17 | ST202109536995 | 2021-09-28 | P/FBW/MDS/1063178/2021 | 2021-10-05
610 | ERPUR2 | ERPUR2 | Thanjavur | Trichy |  | ROTN | Indus | IN-3030274 | R/NN-628171 |  | SO | 2021-09-09 | ERPUR2 | 4G_FD900_ERPUR2 | 4G_FD2100_ERPUR2 | 4G_TD_ERPUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527657 | 2021-09-22 | P/FVC/MDS/1062659/2021 | 2021-09-29 | ST202109526853 | 2021-09-21 | P/FVC/MDS/1062606/2021 | 2021-09-29 | ST202109530022 | 2021-09-24 | P/FVC/MDS/1063008/2021 | 2021-10-01 | ST202109522267 | 2021-09-16 | P/FBW/MDS/1062518/2021 | 2021-09-23
611 | VALVAI | VALVAI | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3021085 | R/NN-627476 |  |  | 2021-09-09 | VALVAI | 4G_FD900_VALVAI | 4G_FD2100_VALVAI | 4G_TD_VALVAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522082 | 2021-09-16 | P/FVC/MDS/1062420/2021 | 2021-09-23 | ST202109522209 | 2021-09-16 | P/FVC/MDS/1062467/2021 | 2021-09-23 | ST202109530017 | 2021-09-24 | P/FVC/MDS/1063003/2021 | 2021-10-01 | ST202109522263 | 2021-09-16 | P/FBW/MDS/1062514/2021 | 2021-09-23
612 | VETTAN | VETTAN | Pudukkottai | Trichy |  | ROTN | Indus | IN-3026513 | R/NN-627446 |  |  | 2021-09-09 | VETTAN | 4G_FD900_VETTAN | 4G_FD2100_VETTAN | 4G_TD_VETTAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522085 | 2021-09-16 | P/FVC/MDS/1062423/2021 | 2021-09-23 | ST202109522213 | 2021-09-16 | P/FVC/MDS/1062471/2021 | 2021-09-23 | ST202109530020 | 2021-09-24 | P/FVC/MDS/1063006/2021 | 2021-10-01 | ST202109522266 | 2021-09-16 | P/FBW/MDS/1062517/2021 | 2021-09-23
613 | KALDAI | KALDAI | Tirunelveli | Madurai |  | ROTN | Indus | IN-3020054 | R/NN-627441 |  | On Air | 2021-09-09 | KALDAI | 4G_FD900_KALDAI | 4G_FD2100_KALDAI | 4G_TD_KALDAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522079 | 2021-09-16 | P/FVC/MDS/1062417/2021 | 2021-09-23 | ST202109526851 | 2021-09-21 | P/FVC/MDS/1062604/2021 | 2021-09-29 | ST202109530004 | 2021-09-24 | P/FVC/MDS/1062805/2021 | 2021-10-01 | ST202109513269 | 2021-09-08 | P/FBW/MDS/1061695/2021 | 2021-09-16
614 | BAKKAM | BAKKAM | Kancheepuram | Chennai |  | ROTN | Indus | IN-3025954 | R/NN-627759 |  | On Air | 2021-09-09 | BAKKAM | 4G_FD900_BAKKAM | 4G_FD2100_BAKKAM | 4G_TD_BAKKAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527656 | 2021-09-22 | P/FVC/MDS/1062547/2021 | 2021-09-27 | ST202109526852 | 2021-09-21 | P/FVC/MDS/1062605/2021 | 2021-09-29 | ST202109530021 | 2021-09-24 | P/FVC/MDS/1063007/2021 | 2021-10-01 | ST202109527547 | 2021-09-22 | P/FBW/MDS/1062551/2021 | 2021-09-27
615 | PDY343 | PDY343 |  |  |  | ROTN | BSNL | 1510 | - |  |  | 2021-09-11 | PDY343 | 4G_FD900_PDY343 | 4G_FD2100_PDY343 | 4G_TD_PDY343 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109527662 | 2021-09-22 | P/FVC/MDS/1062664/2021 | 2021-09-29 | ST202109526858 | 2021-09-21 | P/FVC/MDS/1062611/2021 | 2021-09-29 | ST202109530030 | 2021-09-24 | P/FVC/MDS/1063011/2021 | 2021-10-01 | ST202109527551 | 2021-09-22 | P/FBW/MDS/1062575/2021 | 2021-09-29
616 | PATWM4 | PATWM4 |  |  |  | ROTN | Indus | IN-3030892 | R/NN-628172 |  |  | 2021-09-09 | PATWM4 | 4G_FD900_PATWM4 | 4G_FD2100_PATWM4 | 4G_TD_PATWM4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109527658 | 2021-09-22 | P/FVC/MDS/1062660/2021 | 2021-09-29 | ST202109526854 | 2021-09-21 | P/FVC/MDS/1062607/2021 | 2021-09-29 | ST202109530023 | 2021-09-24 | P/FVC/MDS/1063009/2021 | 2021-10-01 | ST202109522268 | 2021-09-16 | P/FBW/MDS/1062519/2021 | 2021-09-23
617 | TANK5 | TANK05 |  |  |  | CHN | Indus | IN-1905207 | R/NN-569866 |  |  | 2021-09-14 | TANK05 | 4G_FD900_TANK05 | 4G_FD2100_TANK05 | 4G_TD_TANK05 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109522073 | 2021-09-16 | P/FVC/MDS/1062411/2021 | 2021-09-23 | ST202109522201 | 2021-09-16 | P/FVC/MDS/1062459/2021 | 2021-09-23 | ST202109530290 | 2021-09-24 | P/FVC/MDS/1063050/2021 | 2021-10-01 | ST202109522256 | 2021-09-16 | P/FBW/MDS/1062507/2021 | 2021-09-23
618 | CONR24 | CONR24 | The Nilgiris | Coimbatore |  | ROTN | Ascend |  |  |  | SO |  | CONR24 | 4G_FD900_CONR24 | 4G_FD2100_CONR24 | 4G_TD_CONR24 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537933 | 2021-09-29 | P/FVC/MDS/1063346/2021 | 2021-10-11 | ST202109538170 | 2021-09-29 | P/FVC/MDS/1063368/2021 | 2021-10-11 | ST202109538725 | 2021-09-29 | P/FVC/MDS/1063385/2021 | 2021-10-11 | ST202109538563 | 2021-09-29 | P/FBW/MDS/1063313/2021 | 2021-10-11
619 | IRGR11 | IRGR11 | Coimbatore | Coimbatore |  | ROTN | Airtel | - | - |  | On Air | 2021-09-20 | IRGR11 | 4G_FD900_IRGR11 | 4G_FD2100_IRGR11 | 4G_TD_IRGR11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527675 | 2021-09-22 | P/FVC/MDS/1062677/2021 | 2021-09-29 | ST202109526887 | 2021-09-21 | P/FVC/MDS/1062624/2021 | 2021-09-29 | ST202210548127 | 2022-10-11 | P/FVC/MDS/1113908/2022 | 2022-10-21 | ST202109527564 | 2021-09-22 | P/FBW/MDS/1062588/2021 | 2021-09-29
620 | KPAPPM | KPAPPM | Madurai | Madurai |  | ROTN | Indus |  | R/NN-626494 |  | On Air |  | KPAPPM | 4G_FD900_KPAPPM | 4G_FD2100_KPAPPM | 4G_TD_KPAPPM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537934 | 2021-09-29 | P/FVC/MDS/1063347/2021 | 2021-10-11 | ST202109538171 | 2021-09-29 | P/FVC/MDS/1063369/2021 | 2021-10-11 | ST202109538726 | 2021-09-29 | P/FVC/MDS/1063386/2021 | 2021-10-11 | ST202109538564 | 2021-09-29 | P/FBW/MDS/1063314/2021 | 2021-10-11
621 | PDY358 | PDY358 | Puducherry | Trichy |  | ROTN | Indus |  | R/NN-628122 |  |  | 2021-07-22 | PDY358 | 4G_FD900_PDY358 | 4G_FD2100_PDY358 | 4G_TD_PDY358 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537929 | 2021-09-29 | P/FVC/MDS/1063343/2021 | 2021-10-11 | ST202109538167 | 2021-09-29 | P/FVC/MDS/1063365/2021 | 2021-10-11 | ST202109538722 | 2021-09-29 | P/FVC/MDS/1063382/2021 | 2021-10-11 | ST202109538560 | 2021-09-29 | P/FBW/MDS/1063310/2021 | 2021-10-11
622 | KKGNKM | KKGNKM | Cuddalore | Trichy |  | ROTN | Indus | - | R/NN-627468 |  | On Air |  | KKGNKM | 4G_FD900_KKGNKM | 4G_FD2100_KKGNKM | 4G_TD_KKGNKM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537930 | 2021-09-29 | P/FVC/MDS/1063344/2021 | 2021-10-11 | ST202109538168 | 2021-09-29 | P/FVC/MDS/1063366/2021 | 2021-10-11 | ST202109538723 | 2021-09-29 | P/FVC/MDS/1063383/2021 | 2021-10-11 | ST202109538561 | 2021-09-29 | P/FBW/MDS/1063311/2021 | 2021-10-11
623 | KARBAN | KARBAN | Tirunelveli | Madurai |  | ROTN | Indus | IN-3021078 | R/NN-627475 |  | On Air | 2021-09-17 | KARBAN | 4G_FD900_KARBAN | 4G_FD2100_KARBAN | 4G_TD_KARBAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527665 | 2021-09-22 | P/FVC/MDS/1062667/2021 | 2021-09-29 | ST202109526861 | 2021-09-21 | P/FVC/MDS/1062614/2021 | 2021-09-29 |  |  |  |  | ST202109527554 | 2021-09-22 | P/FBW/MDS/1062578/2021 | 2021-09-29
624 | VALGOS | VALGOS | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3021153 | R/NN-627494 |  |  | 2021-09-17 | VALGOS | 4G_FD900_VALGOS | 4G_FD2100_VALGOS | 4G_TD_VALGOS | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527667 | 2021-09-22 | P/FVC/MDS/1062669/2021 | 2021-09-29 | ST202109526863 | 2021-09-21 | P/FVC/MDS/1062616/2021 | 2021-09-29 |  |  |  |  | ST202109527556 | 2021-09-22 | P/FBW/MDS/1062580/2021 | 2021-09-29
625 | PNVAI7 | PNVAI7 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3021175 | R/NN-627496 |  |  | 2021-09-20 | PNVAI7 | 4G_FD900_PNVAI7 | 4G_FD2100_PNVAI7 | 4G_TD_PNVAI7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527671 | 2021-09-22 | P/FVC/MDS/1062673/2021 | 2021-09-29 | ST202109526883 | 2021-09-21 | P/FVC/MDS/1062620/2021 | 2021-09-29 |  |  |  |  | ST202109527560 | 2021-09-22 | P/FBW/MDS/1062584/2021 | 2021-09-29
626 | NAPGAI | NAPGAI | Pudukkottai | Trichy |  | ROTN | Indus | IN-3020067 | R/NN-627445 |  | On Air | 2021-09-20 | NAPGAI | 4G_FD900_NAPGAI | 4G_FD2100_NAPGAI | 4G_TD_NAPGAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527670 | 2021-09-22 | P/FVC/MDS/1062672/2021 | 2021-09-29 | ST202109526867 | 2021-09-21 | P/FVC/MDS/1062619/2021 | 2021-09-29 |  |  |  |  | ST202109527559 | 2021-09-22 | P/FBW/MDS/1062583/2021 | 2021-09-29
627 | AGRAHR | AGRAHR | Tiruppur | Coimbatore |  | ROTN | Indus | - | R/NN-627444 |  | On Air |  | AGRAHR | 4G_FD900_AGRAHR | 4G_FD2100_AGRAHR | 4G_TD_AGRAHR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537931 | 2021-09-29 | P/FVC/MDS/1063345/2021 | 2021-10-11 | ST202109538169 | 2021-09-29 | P/FVC/MDS/1063367/2021 | 2021-10-11 | ST202109538724 | 2021-09-29 | P/FVC/MDS/1063384/2021 | 2021-10-11 | ST202109538562 | 2021-09-29 | P/FBW/MDS/1063312/2021 | 2021-10-11
628 | NAMBU5 | NAMBU5 | Erode | Coimbatore |  | ROTN | Indus | - | R/NN-627437 |  | On Air |  | NAMBU5 | 4G_FD900_NAMBU5 | 4G_FD2100_NAMBU5 | 4G_TD_NAMBU5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537928 | 2021-09-29 | P/FVC/MDS/1063342/2021 | 2021-10-11 | ST202109538166 | 2021-09-29 | P/FVC/MDS/1063364/2021 | 2021-10-11 | ST202109538721 | 2021-09-29 | P/FVC/MDS/1063381/2021 | 2021-10-11 | ST202109538558 | 2021-09-29 | P/FBW/MDS/1063309/2021 | 2021-10-11
629 | THICHY | THICHY | Kanniyakumari | Madurai |  | ROTN | CNIL/GTL | TAM/GBT/K/09982 | - |  | On Air |  | THICHY | 4G_FD900_THICHY | 4G_FD2100_THICHY | 4G_TD_THICHY | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497348 | 2021-08-30 | P/FVC/MDS/1060326/2021 | 2021-09-13 | ST202108494486 | 2021-08-27 | P/FVC/MDS/1060279/2021 | 2021-09-13 | ST202108493765 | 2021-08-27 | P/FVC/MDS/1060232/2021 | 2021-09-13 | ST202108493604 | 2021-08-27 | P/FBW/MDS/1060185/2021 | 2021-09-13
630 | ULUNDA | ULUNDA | Thiruvallur | Chennai |  | ROTN | Indus | IN-3025257 | R/NN-627688 |  | On Air | 2021-09-17 | ULUNDA | 4G_FD900_ULUNDA | 4G_FD2100_ULUNDA | 4G_TD_ULUNDA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527666 | 2021-09-22 | P/FVC/MDS/1062668/2021 | 2021-09-29 | ST202109526862 | 2021-09-21 | P/FVC/MDS/1062615/2021 | 2021-09-29 |  |  |  |  | ST202109527555 | 2021-09-22 | P/FBW/MDS/1062579/2021 | 2021-09-29
631 | SNYPT2 | SNYPT2 | Erode | Coimbatore |  | ROTN | Indus | IN-3025262 | R/NN-627691 |  | SR | 2021-09-20 | SNYPT2 | 4G_FD900_SNYPT2 | 4G_FD2100_SNYPT2 | 4G_TD_SNYPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527673 | 2021-09-22 | P/FVC/MDS/1062675/2021 | 2021-09-29 | ST202109526885 | 2021-09-21 | P/FVC/MDS/1062622/2021 | 2021-09-29 |  |  |  |  | ST202109527562 | 2021-09-22 | P/FBW/MDS/1062586/2021 | 2021-09-29
632 | MELAKL | MELAKL | Cuddalore | Trichy |  | ROTN | Indus | IN-3025284 | R/NN-627697 |  | On Air | 2021-09-20 | MELAKL | 4G_FD900_MELAKL | 4G_FD2100_MELAKL | 4G_TD_MELAKL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527674 | 2021-09-22 | P/FVC/MDS/1062676/2021 | 2021-09-29 | ST202109526886 | 2021-09-21 | P/FVC/MDS/1062623/2021 | 2021-09-29 |  |  |  |  | ST202109527563 | 2021-09-22 | P/FBW/MDS/1062587/2021 | 2021-09-29
633 | PERCHI | PERCHI | Vellore | Vellore |  | ROTN | Indus | IN-3027810 | R/NN-628040 |  | On Air | 2021-09-20 | PERCHI | 4G_FD900_PERCHI | 4G_FD2100_PERCHI | 4G_TD_PERCHI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527672 | 2021-09-22 | P/FVC/MDS/1062674/2021 | 2021-09-29 | ST202109526884 | 2021-09-21 | P/FVC/MDS/1062621/2021 | 2021-09-29 |  |  |  |  | ST202109527561 | 2021-09-22 | P/FBW/MDS/1062585/2021 | 2021-09-29
634 | UTKTI6 | UTKTI6 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3027820 | R/NN-628041 |  | On Air | 2021-09-17 | UTKTI6 | 4G_FD900_UTKTI6 | 4G_FD2100_UTKTI6 | 4G_TD_UTKTI6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527668 | 2021-09-22 | P/FVC/MDS/1062670/2021 | 2021-09-29 | ST202109526865 | 2021-09-21 | P/FVC/MDS/1062617/2021 | 2021-09-29 |  |  |  |  | ST202109527557 | 2021-09-22 | P/FBW/MDS/1062581/2021 | 2021-09-29
635 | KDPTM3 | KDPTM3 |  |  |  | ROTN | Indus | IN-3035026 | R/NN-628590 |  |  | 2021-09-17 | KDPTM3 | 4G_FD900_KDPTM3 | 4G_FD2100_KDPTM3 | 4G_TD_KDPTM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109527679 | 2021-09-22 | P/FVC/MDS/1062681/2021 | 2021-09-29 | ST202109526891 | 2021-09-21 | P/FVC/MDS/1062628/2021 | 2021-09-29 | ST202109530299 | 2021-09-24 | P/FVC/MDS/1063059/2021 | 2021-10-01 | ST202109527568 | 2021-09-22 | P/FBW/MDS/1062592/2021 | 2021-09-29
636 | RJPM47 | RJPM47 | Virudhunagar | Madurai |  | ROTN | TVI | - | - |  | On Air | 2021-10-04 | RJPM47 | 4G_FD900_RJPM47 | 4G_FD2100_RJPM47 | 4G_TD_RJPM47 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550032 | 2021-10-05 | P/FVC/MDS/1063545/2021 | 2021-10-20 | ST202110554018 | 2021-10-08 | P/FVC/MDS/1063528/2021 | 2021-10-18 |  |  |  |  | ST202110554210 | 2021-10-08 | P/FBW/MDS/1063654/2021 | 2021-10-22
637 | MGDI13 | MGDI13 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-MRGD-ENB-0036 | SR-TN000349 |  | On Air | 2021-09-27 | MGDI13 | 4G_FD900_MGDI13 | 4G_FD2100_MGDI13 | 4G_TD_MGDI13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522072 | 2021-09-16 | P/FVC/MDS/1062410/2021 | 2021-09-23 | ST202109522200 | 2021-09-16 | P/FVC/MDS/1062458/2021 | 2021-09-23 | ST202109530289 | 2021-09-24 | P/FVC/MDS/1063049/2021 | 2021-10-01 | ST202109522255 | 2021-09-16 | P/FBW/MDS/1062506/2021 | 2021-09-23
638 | VRCM14 | VRCM14 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-VDCM-ENB-0018 | SR-TN000341 |  | On Air | 2021-09-27 | VRCM14 | 4G_FD900_VRCM14 | 4G_FD2100_VRCM14 | 4G_TD_VRCM14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522077 | 2021-09-16 | P/FVC/MDS/1062415/2021 | 2021-09-23 | ST202109522205 | 2021-09-16 | P/FVC/MDS/1062463/2021 | 2021-09-23 | ST202109530294 | 2021-09-24 | P/FVC/MDS/1063054/2021 | 2021-10-01 | ST202109522260 | 2021-09-16 | P/FBW/MDS/1062511/2021 | 2021-09-23
639 | IDPD9 | IDPD09 | Salem | Vellore |  | ROTN | Indus | IN-3000673 | R/NN-619902 |  | On Air | 2021-10-01 | IDPD09 | 4G_FD900_IDPD09 | 4G_FD2100_IDPD09 | 4G_TD_IDPD09 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550039 | 2021-10-05 | P/FVC/MDS/1063552/2021 | 2021-10-20 | ST202110554026 | 2021-10-08 | P/FVC/MDS/1063577/2021 | 2021-10-20 |  |  |  |  | ST202110554219 | 2021-10-08 | P/FBW/MDS/1063661/2021 | 2021-10-22
640 | PKT193 | PKT193 | Tirunelveli | Madurai |  | ROTN | AIRTEL |  |  |  | Dropped |  | PKT193 | 4G_FD900_PKT193 | 4G_FD2100_PKT193 | 4G_TD_PKT193 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202107371976 | 2021-07-03 | P/FVC/MDS/1051630/2021 | 2021-08-14 | ST202110560199 | 2021-10-14 | P/FVC/MDS/1063704/2021 | 2021-10-22 | ST202107377427 | 2021-07-07 | P/FVC/MDS/1056089/2021 | 2021-09-07 | ST202106357001 | 2021-06-22 | P/FBW/MDS/1058588/2021 | 2021-09-10
641 | NYLI50 | NYLI50 | Cuddalore | Trichy |  | ROTN | ATC | TN/CU/AT/22572 | - |  | On Air | 2021-09-27 | NYLI50 | 4G_FD900_NYLI50 | 4G_FD2100_NYLI50 | 4G_TD_NYLI50 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537839 | 2021-09-29 | P/FVC/MDS/1063329/2021 | 2021-10-11 | ST202109538153 | 2021-09-29 | P/FVC/MDS/1063351/2021 | 2021-10-11 | ST202109530337 | 2021-09-24 | P/FVC/MDS/1063097/2021 | 2021-10-01 | ST202109533212 | 2021-09-25 | P/FVC/MDS/1062833/2021 | 2021-10-01
642 | INUNGR | INUNGR | Karur | Coimbatore |  | ROTN | ATC | TN/KU/AT/22441 | - |  | On Air | 2021-09-27 | INUNGR | 4G_FD900_INUNGR | 4G_FD2100_INUNGR | 4G_TD_INUNGR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537840 | 2021-09-29 | P/FVC/MDS/1063330/2021 | 2021-10-11 | ST202109538154 | 2021-09-29 | P/FVC/MDS/1063352/2021 | 2021-10-11 | ST202109530338 | 2021-09-24 | P/FVC/MDS/1063098/2021 | 2021-10-01 | ST202109533213 | 2021-09-25 | P/FVC/MDS/1062834/2021 | 2021-10-01
643 | MDU513 | MDU513 | Madurai | Madurai |  | ROTN | Summit | I-TN-MDUR-ENB-0291 | SR-TN000332 |  | On Air | 2021-09-27 | MDU513 | 4G_FD900_MDU513 | 4G_FD2100_MDU513 | 4G_TD_MDU513 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109515592 | 2021-09-09 | P/FVC/MDS/1061430/2021 | 2021-09-15 | ST202109511461 | 2021-09-07 | P/FVC/MDS/1061816/2021 | 2021-09-16 | ST202109515213 | 2021-09-09 | P/FVC/MDS/1062238/2021 | 2021-09-20 | ST202109513265 | 2021-09-08 | P/FBW/MDS/1061691/2021 | 2021-09-16
644 | THAIYR | THAIYR | Thanjavur | Trichy |  | ROTN | Summit | I-TN-PTKT-ENB-9020 | SR-TN000327 |  | On Air | 2021-09-27 | THAIYR | 4G_FD900_THAIYR | 4G_FD2100_THAIYR | 4G_TD_THAIYR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109515593 | 2021-09-09 | P/FVC/MDS/1061431/2021 | 2021-09-15 | ST202109511462 | 2021-09-07 | P/FVC/MDS/1061817/2021 | 2021-09-16 | ST202109515215 | 2021-09-09 | P/FVC/MDS/1062239/2021 | 2021-09-20 | ST202109513266 | 2021-09-08 | P/FBW/MDS/1061692/2021 | 2021-09-16
645 | VALVA1 | VALVA1 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3042037 | R/NN-629575 |  |  | 2021-10-01 | VALVA1 | 4G_FD900_VALVA1 | 4G_FD2100_VALVA1 | 4G_TD_VALVA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550213 | 2021-10-05 | P/FVC/MDS/1063555/2021 | 2021-10-20 | ST202110554029 | 2021-10-08 | P/FVC/MDS/1063580/2021 | 2021-10-20 |  |  |  |  | ST202110554222 | 2021-10-08 | P/FBW/MDS/1063664/2021 | 2021-10-22
646 | KARVAN | KARVAN | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-SKKL-ENB-9061 | SR-TN000329 |  | On Air | 2021-09-27 | KARVAN | 4G_FD900_KARVAN | 4G_FD2100_KARVAN | 4G_TD_KARVAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109515589 | 2021-09-09 | P/FVC/MDS/1061428/2021 | 2021-09-15 | ST202109511459 | 2021-09-07 | P/FVC/MDS/1061814/2021 | 2021-09-16 | ST202109515211 | 2021-09-09 | P/FVC/MDS/1062236/2021 | 2021-09-20 | ST202109513263 | 2021-09-08 | P/FBW/MDS/1061689/2021 | 2021-09-16
647 | PPSM11 | PPSM11 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-VLGM-ENB-9017 | SR-TN000333 |  | On Air | 2021-09-27 | PPSM11 | 4G_FD900_PPSM11 | 4G_FD2100_PPSM11 | 4G_TD_PPSM11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109515594 | 2021-09-09 | P/FVC/MDS/1061432/2021 | 2021-09-15 | ST202109511463 | 2021-09-07 | P/FVC/MDS/1061818/2021 | 2021-09-16 | ST202109515216 | 2021-09-09 | P/FVC/MDS/1062240/2021 | 2021-09-20 | ST202109513267 | 2021-09-08 | P/FBW/MDS/1061693/2021 | 2021-09-16
648 | KMORUR | KMORUR | Salem | Vellore |  | ROTN | Indus | IN-1246791 | R/RES-505900 |  | On Air | 2021-10-01 | KMORUR | 4G_FD900_KMORUR | 4G_FD2100_KMORUR | 4G_TD_KMORUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550211 | 2021-10-05 | P/FVC/MDS/1063553/2021 | 2021-10-20 | ST202110554027 | 2021-10-08 | P/FVC/MDS/1063578/2021 | 2021-10-20 |  |  |  |  | ST202110554220 | 2021-10-08 | P/FBW/MDS/1063662/2021 | 2021-10-22
649 | TEKKAL | TEKKAL | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-TAVF-ENB-9004 | SR-TN000361 |  | On Air | 2021-09-27 | TEKKAL | 4G_FD900_TEKKAL | 4G_FD2100_TEKKAL | 4G_TD_TEKKAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527663 | 2021-09-22 | P/FVC/MDS/1062665/2021 | 2021-09-29 | ST202109526859 | 2021-09-21 | P/FVC/MDS/1062612/2021 | 2021-09-29 |  |  |  |  | ST202109527552 | 2021-09-22 | P/FBW/MDS/1062576/2021 | 2021-09-29
650 | MUTHUK | MUTHUK | Ramanathapuram | Madurai |  | ROTN | Summit | I-TN-MDKL-ENB-9035 | SR-TN000345 |  | On Air | 2021-09-27 | MUTHUK | 4G_FD900_MUTHUK | 4G_FD2100_MUTHUK | 4G_TD_MUTHUK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522078 | 2021-09-16 | P/FVC/MDS/1062416/2021 | 2021-09-23 | ST202109522206 | 2021-09-16 | P/FVC/MDS/1062464/2021 | 2021-09-23 | ST202109530295 | 2021-09-24 | P/FVC/MDS/1063055/2021 | 2021-10-01 | ST202109522261 | 2021-09-16 | P/FBW/MDS/1062512/2021 | 2021-09-23
651 | VELPUR | VELPUR | Namakkal | Coimbatore |  | ROTN | Indus | IN-1129809 | R/RES-506155 |  | On Air | 2021-10-01 | VELPUR | 4G_FD900_VELPUR | 4G_FD2100_VELPUR | 4G_TD_VELPUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550216 | 2021-10-05 | P/FVC/MDS/1063558/2021 | 2021-10-20 | ST202110554032 | 2021-10-08 | P/FVC/MDS/1063583/2021 | 2021-10-20 |  |  |  |  | ST202110554226 | 2021-10-08 | P/FBW/MDS/1063667/2021 | 2021-10-22
652 | GANGAT | GANGAT | Krishnagiri | Vellore |  | ROTN | Indus | IN-1245463 | R/RES-506159 |  | On Air | 2021-10-01 | GANGAT | 4G_FD900_GANGAT | 4G_FD2100_GANGAT | 4G_TD_GANGAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550215 | 2021-10-05 | P/FVC/MDS/1063557/2021 | 2021-10-20 | ST202110554031 | 2021-10-08 | P/FVC/MDS/1063582/2021 | 2021-10-20 |  |  |  |  | ST202110554225 | 2021-10-08 | P/FBW/MDS/1063666/2021 | 2021-10-22
653 | SELVAP | SELVAP | Coimbatore | Coimbatore |  | ROTN | CNIL | TAM/GBT/K/29639 | - |  | On Air | 2021-10-04 | SELVAP | 4G_FD900_SELVAP | 4G_FD2100_SELVAP | 4G_TD_SELVAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522049 | 2021-09-16 | P/FVC/MDS/1062387/2021 | 2021-09-23 | ST202109522179 | 2021-09-16 | P/FVC/MDS/1062437/2021 | 2021-09-23 | ST202109530268 | 2021-09-24 | P/FVC/MDS/1063027/2021 | 2021-10-01 | ST202109522234 | 2021-09-16 | P/FBW/MDS/1062485/2021 | 2021-09-23
654 | KAMPAT | KAMPAT | Dindigul | Coimbatore |  | ROTN | CNIL | TAM/GBT/K/28567 | - |  | On Air | 2021-10-04 | KAMPAT | 4G_FD900_KAMPAT | 4G_FD2100_KAMPAT | 4G_TD_KAMPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533277 | 2021-09-25 | P/FVC/MDS/1062999/2021 | 2021-10-01 | ST202109531905 | 2021-09-24 | P/FVC/MDS/1062944/2021 | 2021-10-01 |  |  |  |  | ST202109533044 | 2021-09-25 | P/FVC/MDS/1062859/2021 | 2021-10-01
655 | CHATHI | CHATHI | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2021-10-04 | CHATHI | 4G_FD900_CHATHI | 4G_FD2100_CHATHI | 4G_TD_CHATHI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550034 | 2021-10-05 | P/FVC/MDS/1063547/2021 | 2021-10-20 | ST202110554021 | 2021-10-08 | P/FVC/MDS/1063572/2021 | 2021-10-20 |  |  |  |  | ST202110554212 | 2021-10-08 | P/FBW/MDS/1063656/2021 | 2021-10-22
656 | KKD070 | KKD070 |  |  |  | ROTN | Indus | IN-3040716 | R/NN-629174 |  |  | 2021-10-04 | KKD070 | 4G_FD900_KKD070 | 4G_FD2100_KKD070 | 4G_TD_KKD070 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202048187 | 2022-02-18 | P/FVC/MDS/1075001/2022 | 2022-02-28 | ST202202049431 | 2022-02-19 | P/FVC/MDS/1074946/2022 | 2022-02-28 | ST202202049477 | 2022-02-19 | P/FVC/MDS/1074795/2022 | 2022-02-25 | ST202202048682 | 2022-02-18 | P/FBW/MDS/1074888/2022 | 2022-02-28
657 | NANG27 | NANG27 |  |  |  | CHN | indus | IN-3030883 | R/NN-628178 |  |  | 2021-09-24 | NANG27 | 4G_FD900_NANG27 | 4G_FD2100_NANG27 | 4G_TD_NANG27 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109537935 | 2021-09-29 | P/FVC/MDS/1063348/2021 | 2021-10-11 | ST202109538177 | 2021-09-29 | P/FVC/MDS/1063370/2021 | 2021-10-11 | ST202109538727 | 2021-09-29 | P/FVC/MDS/1063387/2021 | 2021-10-11 | ST202109538565 | 2021-09-29 | P/FBW/MDS/1063315/2021 | 2021-10-11
658 | PDY305 | PDY305 | Puducherry | Trichy |  | ROTN | Indus | IN-3029636 | R/NN-628112 |  | SO |  | PDY305 | 4G_FD900_PDY305 | 4G_FD2100_PDY305 | 4G_TD_PDY305 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110560525 | 2021-10-14 | P/FVC/MDS/1063753/2021 | 2021-10-22 | ST202110554919 | 2021-10-08 | P/FVC/MDS/1063767/2021 | 2021-10-22 |  |  |  |  | ST202110563764 | 2021-10-19 | P/FVC/MDS/1065415/2021 | 2021-10-28
659 | MDRKR2 | MDRKR2 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3048854 | R/NN-632187 |  | On Air | 2021-10-09 | MDRKR2 | 4G_FD900_MDRKR2 | 4G_FD2100_MDRKR2 | 4G_TD_MDRKR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110560524 | 2021-10-14 | P/FVC/MDS/1063752/2021 | 2021-10-22 | ST202110554918 | 2021-10-08 | P/FVC/MDS/1063766/2021 | 2021-10-22 |  |  |  |  | ST202110563763 | 2021-10-19 | P/FVC/MDS/1065414/2021 | 2021-10-28
660 | SEERP1 | SEERP1 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-SERP-ENB-9001 | SR-TN000334 |  | On Air | 2021-10-08 | SEERP1 | 4G_FD900_SEERP1 | 4G_FD2100_SEERP1 | 4G_TD_SEERP1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522067 | 2021-09-16 | P/FVC/MDS/1062405/2021 | 2021-09-23 | ST202109520100 | 2021-09-14 | P/FVC/MDS/1061590/2021 | 2021-09-16 |  |  |  |  | ST202109522220 | 2021-09-16 | P/FBW/MDS/1062373/2021 | 2021-09-23
661 | ANJGM4 | ANJGM4 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3012343 | R/NN-626664 |  | On Air | 2021-10-07 | ANJGM4 | 4G_FD900_ANJGM4 | 4G_FD2100_ANJGM4 | 4G_TD_ANJGM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537925 | 2021-09-29 | P/FVC/MDS/1063339/2021 | 2021-10-11 | ST202109538163 | 2021-09-29 | P/FVC/MDS/1063361/2021 | 2021-10-11 | ST202109538718 | 2021-09-29 | P/FVC/MDS/1063378/2021 | 2021-10-11 | ST202109538554 | 2021-09-29 | P/FBW/MDS/1063305/2021 | 2021-10-11
662 | KALPRP | KALPRP | Salem | Vellore |  | ROTN | Summit | I-TN-KLRP-ENB-9001 | SR-TN000326 |  | On Air | 2021-10-08 | KALPRP | 4G_FD900_KALPRP | 4G_FD2100_KALPRP | 4G_TD_KALPRP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109515590 | 2021-09-09 | P/FVC/MDS/1061429/2021 | 2021-09-15 | ST202109511460 | 2021-09-07 | P/FVC/MDS/1061815/2021 | 2021-09-16 | ST202109515212 | 2021-09-09 | P/FVC/MDS/1062237/2021 | 2021-09-20 | ST202109513264 | 2021-09-08 | P/FBW/MDS/1061690/2021 | 2021-09-16
663 | PELLAM | PELLAM | Salem | Vellore |  | ROTN | Summit | I-TN-SLEM-ENB-9024 | SR-TN000331 |  | On Air | 2021-10-08 | PELLAM | 4G_FD900_PELLAM | 4G_FD2100_PELLAM | 4G_TD_PELLAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109515584 | 2021-09-09 | P/FVC/MDS/1060956/2021 | 2021-09-14 | ST202109511457 | 2021-09-07 | P/FVC/MDS/1061812/2021 | 2021-09-16 | ST202109515208 | 2021-09-09 | P/FVC/MDS/1062234/2021 | 2021-09-20 | ST202109513261 | 2021-09-08 | P/FBW/MDS/1061687/2021 | 2021-09-16
664 | VETTA1 | VETTA1 | Pudukkottai | Trichy |  | ROTN | Indus | IN-1123155 | R/RES-506225 |  | On Air | 2021-10-06 | VETTA1 | 4G_FD900_VETTA1 | 4G_FD2100_VETTA1 | 4G_TD_VETTA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572129 | 2021-10-27 | P/FVC/MDS/1065684/2021 | 2021-11-16 | ST202110574117 | 2021-10-28 | P/FVC/MDS/1065816/2021 | 2021-11-16 | ST202110573929 | 2021-10-28 | P/FVC/MDS/1065781/2021 | 2021-11-16 | ST202110550864 | 2021-10-06 | P/FBW/MDS/1063539/2021 | 2021-10-20
665 | VPANDI | VPANDI | Coimbatore | Coimbatore |  | ROTN | Indus | IN-1245260 | R/RES-506166 |  | On Air | 2021-10-04 | VPANDI | 4G_FD900_VPANDI | 4G_FD2100_VPANDI | 4G_TD_VPANDI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109521903 | 2021-09-16 | P/FVC/MDS/1062368/2021 | 2021-09-23 | ST202109522161 | 2021-09-16 | P/FVC/MDS/1062424/2021 | 2021-09-23 | ST202109530033 | 2021-09-24 | P/FVC/MDS/1063014/2021 | 2021-10-01 | ST202109522221 | 2021-09-16 | P/FBW/MDS/1062472/2021 | 2021-09-23
666 | KONGAN | KONGAN | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-PLLC-ENB-9113 | SR-TN000403 |  | On Air | 2021-10-06 | KONGAN | 4G_FD900_KONGAN | 4G_FD2100_KONGAN | 4G_TD_KONGAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527761 | 2021-09-22 | P/FVC/MDS/1062708/2021 | 2021-09-29 | ST202109526974 | 2021-09-21 | P/FVC/MDS/1062654/2021 | 2021-09-29 |  |  |  |  | ST202109527035 | 2021-09-21 | P/FBW/MDS/1062523/2021 | 2021-09-24
667 | ADHNUR | ADHNUR | Perambalur | Trichy |  | ROTN | Indus | IN-1139129 | R/RES-506157 |  | On Air | 2021-10-04 | ADHNUR | 4G_FD900_ADHNUR | 4G_FD2100_ADHNUR | 4G_TD_ADHNUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522045 | 2021-09-16 | P/FVC/MDS/1062383/2021 | 2021-09-23 | ST202109522170 | 2021-09-16 | P/FVC/MDS/1062433/2021 | 2021-09-23 |  |  |  |  | ST202109522230 | 2021-09-16 | P/FBW/MDS/1062481/2021 | 2021-09-23
668 | KOLKAN | KOLKAN | Perambalur | Trichy |  | ROTN | Indus | IN-1386025 | R/RES-506163 |  | On Air | 2021-10-04 | KOLKAN | 4G_FD900_KOLKAN | 4G_FD2100_KOLKAN | 4G_TD_KOLKAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522047 | 2021-09-16 | P/FVC/MDS/1062385/2021 | 2021-09-23 | ST202109522172 | 2021-09-16 | P/FVC/MDS/1062435/2021 | 2021-09-23 |  |  |  |  | ST202109522232 | 2021-09-16 | P/FBW/MDS/1062483/2021 | 2021-09-23
669 | KIRKOT | KIRKOT | Sivaganga | Madurai |  | ROTN | Summit | I-TN-TPTI-ENB-9058 | SR-TN000384 |  | On Air | 2021-10-06 | KIRKOT | 4G_FD900_KIRKOT | 4G_FD2100_KIRKOT | 4G_TD_KIRKOT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527756 | 2021-09-22 | P/FVC/MDS/1062703/2021 | 2021-09-29 | ST202109526969 | 2021-09-21 | P/FVC/MDS/1062649/2021 | 2021-09-29 |  |  |  |  | ST202109528891 | 2021-09-23 | P/FBW/MDS/1062888/2021 | 2021-10-01
670 | SITHUV | SITHUV | Dindigul | Coimbatore |  | ROTN | Summit | I-TN-VDSD-ENB-9075 | SR-TN000387 |  | On Air | 2021-10-06 | SITHUV | 4G_FD900_SITHUV | 4G_FD2100_SITHUV | 4G_TD_SITHUV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527757 | 2021-09-22 | P/FVC/MDS/1062704/2021 | 2021-09-29 | ST202109526970 | 2021-09-21 | P/FVC/MDS/1062650/2021 | 2021-09-29 |  |  |  |  | ST202109528892 | 2021-09-23 | P/FBW/MDS/1062889/2021 | 2021-10-01
671 | CHIPAL | CHIPAL | Vellore | Vellore |  | ROTN | Summit | I-TN-GDTM-ENB-9060 | SR-TN000390 |  | On Air | 2021-10-06 | CHIPAL | 4G_FD900_CHIPAL | 4G_FD2100_CHIPAL | 4G_TD_CHIPAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522052 | 2021-09-16 | P/FVC/MDS/1062390/2021 | 2021-09-23 | ST202109522182 | 2021-09-16 | P/FVC/MDS/1062440/2021 | 2021-09-23 |  |  |  |  | ST202109522237 | 2021-09-16 | P/FBW/MDS/1062488/2021 | 2021-09-23
672 | VPUDUR | VPUDUR | Thoothukkudi | Madurai |  | ROTN | Summit | I-TN-VLTK-ENB-9046 | SR-TN000388 |  | On Air | 2021-10-06 | VPUDUR | 4G_FD900_VPUDUR | 4G_FD2100_VPUDUR | 4G_TD_VPUDUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522053 | 2021-09-16 | P/FVC/MDS/1062391/2021 | 2021-09-23 | ST202109522183 | 2021-09-16 | P/FVC/MDS/1062441/2021 | 2021-09-23 |  |  |  |  | ST202109522238 | 2021-09-16 | P/FBW/MDS/1062489/2021 | 2021-09-23
673 | SRIDAN | SRIDAN | Viluppuram | Trichy |  | ROTN | Summit | I-TN-TRKY-ENB-9064 | SR-TN000393 |  | On Air | 2021-10-06 | SRIDAN | 4G_FD900_SRIDAN | 4G_FD2100_SRIDAN | 4G_TD_SRIDAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522054 | 2021-09-16 | P/FVC/MDS/1062392/2021 | 2021-09-23 | ST202109522184 | 2021-09-16 | P/FVC/MDS/1062442/2021 | 2021-09-23 |  |  |  |  | ST202109522239 | 2021-09-16 | P/FBW/MDS/1062490/2021 | 2021-09-23
674 | VICHU1 | VICHU1 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-URMR-ENB-9046 | SR-TN000391 |  | On Air | 2021-10-06 | VICHU1 | 4G_FD900_VICHU1 | 4G_FD2100_VICHU1 | 4G_TD_VICHU1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522055 | 2021-09-16 | P/FVC/MDS/1062393/2021 | 2021-09-23 | ST202109522185 | 2021-09-16 | P/FVC/MDS/1062443/2021 | 2021-09-23 |  |  |  |  | ST202109522240 | 2021-09-16 | P/FBW/MDS/1062491/2021 | 2021-09-23
675 | SURYAM | SURYAM | Erode | Coimbatore |  | ROTN | Summit | I-TN-SRYP-ENB-9001 | SR-TN000394 |  | On Air | 2021-10-06 | SURYAM | 4G_FD900_SURYAM | 4G_FD2100_SURYAM | 4G_TD_SURYAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527758 | 2021-09-22 | P/FVC/MDS/1062705/2021 | 2021-09-29 | ST202109526971 | 2021-09-21 | P/FVC/MDS/1062651/2021 | 2021-09-29 |  |  |  |  | ST202109528893 | 2021-09-23 | P/FBW/MDS/1062890/2021 | 2021-10-01
676 | PUTMAN | PUTMAN | Thanjavur | Trichy |  | ROTN | Summit | I-TN-TVDD-ENB-9041 | SR-TN000392 |  | On Air | 2021-10-06 | PUTMAN | 4G_FD900_PUTMAN | 4G_FD2100_PUTMAN | 4G_TD_PUTMAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522058 | 2021-09-16 | P/FVC/MDS/1062396/2021 | 2021-09-23 | ST202109522188 | 2021-09-16 | P/FVC/MDS/1062446/2021 | 2021-09-23 |  |  |  |  | ST202109522243 | 2021-09-16 | P/FBW/MDS/1062494/2021 | 2021-09-23
677 | SOWLUR | SOWLUR | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-KGRI-ENB-9109 | SR-TN000402 |  | On Air | 2021-10-06 | SOWLUR | 4G_FD900_SOWLUR | 4G_FD2100_SOWLUR | 4G_TD_SOWLUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522071 | 2021-09-16 | P/FVC/MDS/1062409/2021 | 2021-09-23 | ST202109520099 | 2021-09-14 | P/FVC/MDS/1061589/2021 | 2021-09-16 |  |  |  |  | ST202109522254 | 2021-09-16 | P/FBW/MDS/1062505/2021 | 2021-09-23
678 | RARAMI | RARAMI | Thanjavur | Trichy |  | ROTN | Summit | I-TN-PNSM-ENB-9038 | SR-TN000441 |  | On Air | 2021-10-06 | RARAMI | 4G_FD900_RARAMI | 4G_FD2100_RARAMI | 4G_TD_RARAMI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533278 | 2021-09-25 | P/FVC/MDS/1063000/2021 | 2021-10-01 | ST202109531906 | 2021-09-24 | P/FVC/MDS/1062945/2021 | 2021-10-01 |  |  |  |  | ST202109533045 | 2021-09-25 | P/FVC/MDS/1062860/2021 | 2021-10-01
679 | TIRMAL | TIRMAL | Sivaganga | Madurai |  | ROTN | Summit | I-TN-SVGG-ENB-9082 | SR-TN000452 |  | On Air | 2021-10-06 | TIRMAL | 4G_FD900_TIRMAL | 4G_FD2100_TIRMAL | 4G_TD_TIRMAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537843 | 2021-09-29 | P/FVC/MDS/1063331/2021 | 2021-10-11 | ST202109538155 | 2021-09-29 | P/FVC/MDS/1063353/2021 | 2021-10-11 | ST202109530339 | 2021-09-24 | P/FVC/MDS/1063099/2021 | 2021-10-01 | ST202109533214 | 2021-09-25 | P/FVC/MDS/1062835/2021 | 2021-10-01
680 | AYAKAR | AYAKAR | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-VDRY-ENB-9037 | SR-TN000446 |  | On Air | 2021-10-06 | AYAKAR | 4G_FD900_AYAKAR | 4G_FD2100_AYAKAR | 4G_TD_AYAKAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533310 | 2021-09-25 | P/FVC/MDS/1062809/2021 | 2021-10-01 | ST202109531907 | 2021-09-24 | P/FVC/MDS/1062946/2021 | 2021-10-01 |  |  |  |  | ST202109533046 | 2021-09-25 | P/FVC/MDS/1062861/2021 | 2021-10-01
681 | VALPUR | VALPUR | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-TRKD-ENB-9046 | SR-TN000431 |  | On Air | 2021-10-06 | VALPUR | 4G_FD900_VALPUR | 4G_FD2100_VALPUR | 4G_TD_VALPUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527744 | 2021-09-22 | P/FVC/MDS/1062691/2021 | 2021-09-29 | ST202109526957 | 2021-09-21 | P/FVC/MDS/1062637/2021 | 2021-09-29 |  |  |  |  | ST202109528879 | 2021-09-23 | P/FBW/MDS/1062876/2021 | 2021-10-01
682 | KRAYAP | KRAYAP | Sivaganga | Madurai |  | ROTN | Summit | I-TN-TRMY-ENB-9050 | SR-TN000442 |  | On Air | 2021-10-06 | KRAYAP | 4G_FD900_KRAYAP | 4G_FD2100_KRAYAP | 4G_TD_KRAYAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537895 | 2021-09-29 | P/FVC/MDS/1063336/2021 | 2021-10-11 | ST202109538160 | 2021-09-29 | P/FVC/MDS/1063358/2021 | 2021-10-11 | ST202109538715 | 2021-09-29 | P/FVC/MDS/1063299/2021 | 2021-10-11 | ST202109538551 | 2021-09-29 | P/FBW/MDS/1063302/2021 | 2021-10-11
683 | POMYUR | POMYUR | Viluppuram | Trichy |  | ROTN | Summit | I-TN-TRKY-ENB-9073 | SR-TN000433 |  | On Air | 2021-10-06 | POMYUR | 4G_FD900_POMYUR | 4G_FD2100_POMYUR | 4G_TD_POMYUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533429 | 2021-09-25 | P/FVC/MDS/1062971/2021 | 2021-10-01 | ST202109532050 | 2021-09-24 | P/FVC/MDS/1062910/2021 | 2021-10-01 | ST202109530311 | 2021-09-24 | P/FVC/MDS/1063071/2021 | 2021-10-01 | ST202109533091 | 2021-09-25 | P/FVC/MDS/1062847/2021 | 2021-10-01
684 | PERCHE | PERCHE | Tiruvannamalai | Vellore |  | ROTN | Summit | I-TN-TRVT-ENB-9077 | SR-TN000434 |  | On Air | 2021-10-06 | PERCHE | 4G_FD900_PERCHE | 4G_FD2100_PERCHE | 4G_TD_PERCHE | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537923 | 2021-09-29 | P/FVC/MDS/1063337/2021 | 2021-10-11 | ST202109538161 | 2021-09-29 | P/FVC/MDS/1063359/2021 | 2021-10-11 | ST202109538716 | 2021-09-29 | P/FVC/MDS/1063376/2021 | 2021-10-11 | ST202109538552 | 2021-09-29 | P/FBW/MDS/1063303/2021 | 2021-10-11
685 | TAKKA1 | TAKKA1 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-ULND-ENB-9069 | SR-TN000448 |  | On Air | 2021-10-06 | TAKKA1 | 4G_FD900_TAKKA1 | 4G_FD2100_TAKKA1 | 4G_TD_TAKKA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533431 | 2021-09-25 | P/FVC/MDS/1062973/2021 | 2021-10-01 | ST202109532052 | 2021-09-24 | P/FVC/MDS/1062912/2021 | 2021-10-01 | ST202109530313 | 2021-09-24 | P/FVC/MDS/1063073/2021 | 2021-10-01 | ST202109533093 | 2021-09-25 | P/FVC/MDS/1062849/2021 | 2021-10-01
686 | VALSAI | VALSAI | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TVLR-ENB-9096 | SR-TN000453 |  | On Air | 2021-10-06 | VALSAI | 4G_FD900_VALSAI | 4G_FD2100_VALSAI | 4G_TD_VALSAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527682 | 2021-09-22 | P/FVC/MDS/1062684/2021 | 2021-09-29 | ST202109526948 | 2021-09-21 | P/FVC/MDS/1062549/2021 | 2021-09-27 |  |  |  |  | ST202109527571 | 2021-09-22 | P/FBW/MDS/1062595/2021 | 2021-09-29
687 | NEMA23 | NEMA23 | Sivaganga | Madurai |  | ROTN | Summit | I-TN-TPTI-ENB-9068 | SR-TN000443 |  | On Air | 2021-10-06 | NEMA23 | 4G_FD900_NEMA23 | 4G_FD2100_NEMA23 | 4G_TD_NEMA23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537894 | 2021-09-29 | P/FVC/MDS/1063335/2021 | 2021-10-11 | ST202109538159 | 2021-09-29 | P/FVC/MDS/1063357/2021 | 2021-10-11 | ST202109538714 | 2021-09-29 | P/FVC/MDS/1063298/2021 | 2021-10-11 | ST202109538550 | 2021-09-29 | P/FBW/MDS/1063301/2021 | 2021-10-11
688 | KOSAP1 | KOSAP1 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-TTKD-ENB-9063 | SR-TN000451 |  | On Air | 2021-10-06 | KOSAP1 | 4G_FD900_KOSAP1 | 4G_FD2100_KOSAP1 | 4G_TD_KOSAP1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533434 | 2021-09-25 | P/FVC/MDS/1062976/2021 | 2021-10-01 | ST202109532055 | 2021-09-24 | P/FVC/MDS/1062915/2021 | 2021-10-01 | ST202109530316 | 2021-09-24 | P/FVC/MDS/1063076/2021 | 2021-10-01 | ST202109533096 | 2021-09-25 | P/FVC/MDS/1062852/2021 | 2021-10-01
689 | NADKUD | NADKUD | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-SVKS-ENB-9050 | SR-TN000449 |  | On Air | 2021-10-06 | NADKUD | 4G_FD900_NADKUD | 4G_FD2100_NADKUD | 4G_TD_NADKUD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537924 | 2021-09-29 | P/FVC/MDS/1063338/2021 | 2021-10-11 | ST202109538162 | 2021-09-29 | P/FVC/MDS/1063360/2021 | 2021-10-11 | ST202109538717 | 2021-09-29 | P/FVC/MDS/1063377/2021 | 2021-10-11 | ST202109538553 | 2021-09-29 | P/FBW/MDS/1063304/2021 | 2021-10-11
690 | NARYAN | NARYAN | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-PLCD-ENB-9072 | SR-TN000435 |  | On Air | 2021-10-06 | NARYAN | 4G_FD900_NARYAN | 4G_FD2100_NARYAN | 4G_TD_NARYAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537844 | 2021-09-29 | P/FVC/MDS/1063332/2021 | 2021-10-11 | ST202109538156 | 2021-09-29 | P/FVC/MDS/1063354/2021 | 2021-10-11 | ST202109530340 | 2021-09-24 | P/FVC/MDS/1063100/2021 | 2021-10-01 | ST202109533215 | 2021-09-25 | P/FVC/MDS/1062836/2021 | 2021-10-01
691 | GUJPAT | GUJPAT | Tiruchirappalli | Trichy |  | ROTN | Summit | I-TN-SRGM-ENB-9045 | SR-TN000439 |  | On Air | 2021-10-06 | GUJPAT | 4G_FD900_GUJPAT | 4G_FD2100_GUJPAT | 4G_TD_GUJPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533428 | 2021-09-25 | P/FVC/MDS/1062970/2021 | 2021-10-01 | ST202109532049 | 2021-09-24 | P/FVC/MDS/1062909/2021 | 2021-10-01 | ST202109530310 | 2021-09-24 | P/FVC/MDS/1063070/2021 | 2021-10-01 | ST202109533090 | 2021-09-25 | P/FVC/MDS/1062846/2021 | 2021-10-01
692 | ANGBAK | ANGBAK | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-URMR-ENB-9042 | SR-TN000445 |  | On Air | 2021-10-06 | ANGBAK | 4G_FD900_ANGBAK | 4G_FD2100_ANGBAK | 4G_TD_ANGBAK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527767 | 2021-09-22 | P/FVC/MDS/1062714/2021 | 2021-09-29 | ST202109531894 | 2021-09-24 | P/FVC/MDS/1062932/2021 | 2021-10-01 |  |  |  |  | ST202109528899 | 2021-09-23 | P/FBW/MDS/1062896/2021 | 2021-10-01
693 | MALTHR | MALTHR | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-UKTI-ENB-9024 | SR-TN000438 |  | On Air | 2021-10-06 | MALTHR | 4G_FD900_MALTHR | 4G_FD2100_MALTHR | 4G_TD_MALTHR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527684 | 2021-09-22 | P/FVC/MDS/1062686/2021 | 2021-09-29 | ST202109526950 | 2021-09-21 | P/FVC/MDS/1062631/2021 | 2021-09-29 |  |  |  |  | ST202109527573 | 2021-09-22 | P/FBW/MDS/1062597/2021 | 2021-09-29
694 | PARTH1 | PARTH1 | Salem | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2021-10-04 | PARTH1 | 4G_FD900_PARTH1 | 4G_FD2100_PARTH1 | 4G_TD_PARTH1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008767 | 2022-01-12 | P/FVC/MDS/1071712/2022 | 2022-01-20 | ST202201008675 | 2022-01-12 | P/FVC/MDS/1071637/2022 | 2022-01-20 |  |  |  |  | ST202201008944 | 2022-01-13 | P/FBW/MDS/1071552/2022 | 2022-01-20
695 | SAKOT4 | SAKOT4 |  | rotn |  | ROTN | Summit |  |  |  |  | 2021-10-04 | SAKOT4 | 4G_FD900_SAKOT4 | 4G_FD2100_SAKOT4 | 4G_TD_SAKOT4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109533455 | 2021-09-25 | P/FVC/MDS/1062795/2021 | 2021-10-01 | ST202109532057 | 2021-09-24 | P/FVC/MDS/1062917/2021 | 2021-10-01 | ST202109530318 | 2021-09-24 | P/FVC/MDS/1063078/2021 | 2021-10-01 | ST202109533098 | 2021-09-25 | P/FVC/MDS/1062854/2021 | 2021-10-01
696 | VLUTR6 | VLUTR6 |  |  |  | ROTN | Summit |  |  |  |  | 2021-10-04 | VLUTR6 | 4G_FD900_VLUTR6 | 4G_FD2100_VLUTR6 | 4G_TD_VLUTR6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109533478 | 2021-09-25 | P/FVC/MDS/1062969/2021 | 2021-10-01 | ST202109532066 | 2021-09-24 | P/FVC/MDS/1062927/2021 | 2021-10-01 | ST202109530327 | 2021-09-24 | P/FVC/MDS/1063087/2021 | 2021-10-01 | ST202109533146 | 2021-09-25 | P/FVC/MDS/1062824/2021 | 2021-10-01
697 | NBOAG5 | NBOAG5 |  |  |  | ROTN | Indus |  |  |  |  | 2021-10-06 | NBOAG5 | 4G_FD900_NBOAG5 | 4G_FD2100_NBOAG5 | 4G_TD_NBOAG5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109537927 | 2021-09-29 | P/FVC/MDS/1063341/2021 | 2021-10-11 | ST202109538165 | 2021-09-29 | P/FVC/MDS/1063363/2021 | 2021-10-11 | ST202109538720 | 2021-09-29 | P/FVC/MDS/1063380/2021 | 2021-10-11 | ST202109538556 | 2021-09-29 | P/FBW/MDS/1063308/2021 | 2021-10-11
698 | PDY216 | PDY216 | Puducherry | Trichy |  | ROTN | Indus | IN-3030886 | R/NN-628109 |  | SO | 2021-10-14 | PDY216 | 4G_FD900_PDY216 | 4G_FD2100_PDY216 | 4G_TD_PDY216 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110553084 | 2021-10-07 | P/FVC/MDS/1063651/2021 | 2021-10-22 | ST202110568083 | 2021-10-22 | P/FVC/MDS/1065670/2021 | 2021-11-16 | ST202110563967 | 2021-10-19 | P/FVC/MDS/1065441/2021 | 2021-10-28 | ST202110563774 | 2021-10-19 | P/FVC/MDS/1065425/2021 | 2021-10-28
699 | HSR142 | HSR142 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3043977 | R/NN-630147 |  |  | 2021-10-13 | HSR142 | 4G_FD900_HSR142 | 4G_FD2100_HSR142 | 4G_TD_HSR142 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559327 | 2021-10-14 | P/FVC/MDS/1063727/2021 | 2021-10-22 | ST202110560202 | 2021-10-14 | P/FVC/MDS/1063707/2021 | 2021-10-22 |  |  |  |  | ST202110555484 | 2021-10-09 | P/FBW/MDS/1063601/2021 | 2021-10-20
700 | THANER | THANER | Erode | Coimbatore |  | ROTN | Summit | I-TN-PJPM-ENB-9005 | SR-TN000404 |  | On Air | 2021-10-13 | THANER | 4G_FD900_THANER | 4G_FD2100_THANER | 4G_TD_THANER | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109521904 | 2021-09-16 | P/FVC/MDS/1062369/2021 | 2021-09-23 | ST202109522162 | 2021-09-16 | P/FVC/MDS/1062425/2021 | 2021-09-23 |  |  |  |  | ST202109522222 | 2021-09-16 | P/FBW/MDS/1062473/2021 | 2021-09-23
701 | MOTHAL | MOTHAL | Tiruvannamalai | Vellore |  | ROTN | Indus | IN-1386908 | R/RES-506299 |  | On Air | 2021-10-14 | MOTHAL | 4G_FD900_MOTHAL | 4G_FD2100_MOTHAL | 4G_TD_MOTHAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559418 | 2021-10-14 | P/FVC/MDS/1063740/2021 | 2021-10-22 | ST202110560210 | 2021-10-14 | P/FVC/MDS/1063715/2021 | 2021-10-22 | ST202110563934 | 2021-10-19 | P/FVC/MDS/1065436/2021 | 2021-10-28 | ST202110560329 | 2021-10-14 | P/FVC/MDS/1063690/2021 | 2021-10-22
702 | MOOKAN | MOOKAN | Dharmapuri | Vellore |  | ROTN | BSNL | 5814 | - |  | On Air | 2021-10-13 | MOOKAN | 4G_FD900_MOOKAN | 4G_FD2100_MOOKAN | 4G_TD_MOOKAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522051 | 2021-09-16 | P/FVC/MDS/1062389/2021 | 2021-09-23 | ST202109522181 | 2021-09-16 | P/FVC/MDS/1062439/2021 | 2021-09-23 |  |  |  |  | ST202109522236 | 2021-09-16 | P/FBW/MDS/1062487/2021 | 2021-09-23
703 | THAGUR | THAGUR | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-VDRY-ENB-9051 | SR-TN000395 |  | On Air | 2021-10-13 | THAGUR | 4G_FD900_THAGUR | 4G_FD2100_THAGUR | 4G_TD_THAGUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522060 | 2021-09-16 | P/FVC/MDS/1062398/2021 | 2021-09-23 | ST202109522190 | 2021-09-16 | P/FVC/MDS/1062448/2021 | 2021-09-23 |  |  |  |  | ST202109522245 | 2021-09-16 | P/FBW/MDS/1062496/2021 | 2021-09-23
704 | KRINAP | KRINAP | Thanjavur | Trichy |  | ROTN | Summit | I-TN-PTKT-ENB-9077 | SR-TN000400 |  | On Air | 2021-10-13 | KRINAP | 4G_FD900_KRINAP | 4G_FD2100_KRINAP | 4G_TD_KRINAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522069 | 2021-09-16 | P/FVC/MDS/1062407/2021 | 2021-09-23 | ST202109520097 | 2021-09-14 | P/FVC/MDS/1061587/2021 | 2021-09-16 |  |  |  |  | ST202109522252 | 2021-09-16 | P/FBW/MDS/1062503/2021 | 2021-09-23
705 | KOOKUD | KOOKUD | Cuddalore | Trichy |  | ROTN | Summit | I-TN-KMRK-ENB-9041 | SR-TN000398 |  | On Air | 2021-10-13 | KOOKUD | 4G_FD900_KOOKUD | 4G_FD2100_KOOKUD | 4G_TD_KOOKUD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522070 | 2021-09-16 | P/FVC/MDS/1062408/2021 | 2021-09-23 | ST202109520098 | 2021-09-14 | P/FVC/MDS/1061588/2021 | 2021-09-16 |  |  |  |  | ST202109522253 | 2021-09-16 | P/FBW/MDS/1062504/2021 | 2021-09-23
706 | KPUDUR | KPUDUR | Erode | Coimbatore |  | ROTN | Summit | I-TN-BHVN-ENB-9031 | SR-TN000432 |  | On Air | 2021-10-13 | KPUDUR | 4G_FD900_KPUDUR | 4G_FD2100_KPUDUR | 4G_TD_KPUDUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527766 | 2021-09-22 | P/FVC/MDS/1062713/2021 | 2021-09-29 | ST202109531893 | 2021-09-24 | P/FVC/MDS/1062797/2021 | 2021-10-01 |  |  |  |  | ST202109528898 | 2021-09-23 | P/FBW/MDS/1062895/2021 | 2021-10-01
707 | UTHAPM | UTHAPM | Madurai | Madurai |  | ROTN | Summit | I-TN-PRYU-ENB-9042 | SR-TN000444 |  | On Air | 2021-10-13 | UTHAPM | 4G_FD900_UTHAPM | 4G_FD2100_UTHAPM | 4G_TD_UTHAPM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533433 | 2021-09-25 | P/FVC/MDS/1062975/2021 | 2021-10-01 | ST202109532054 | 2021-09-24 | P/FVC/MDS/1062914/2021 | 2021-10-01 | ST202109530315 | 2021-09-24 | P/FVC/MDS/1063075/2021 | 2021-10-01 | ST202109533095 | 2021-09-25 | P/FVC/MDS/1062851/2021 | 2021-10-01
708 | APAYAN | APAYAN | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-SVKS-ENB-9022 | SR-TN000436 |  | On Air | 2021-10-13 | APAYAN | 4G_FD900_APAYAN | 4G_FD2100_APAYAN | 4G_TD_APAYAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550217 | 2021-10-05 | P/FVC/MDS/1063559/2021 | 2021-10-20 | ST202110554033 | 2021-10-08 | P/FVC/MDS/1063584/2021 | 2021-10-20 |  |  |  |  | ST202110554227 | 2021-10-08 | P/FBW/MDS/1063668/2021 | 2021-10-22
709 | TNNRI2 | TNNRI2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-WLJB-ENB-9007 | SR-TN000467 |  | On Air | 2021-10-13 | TNNRI2 | 4G_FD900_TNNRI2 | 4G_FD2100_TNNRI2 | 4G_TD_TNNRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533276 | 2021-09-25 | P/FVC/MDS/1062998/2021 | 2021-10-01 | ST202109531903 | 2021-09-24 | P/FVC/MDS/1062942/2021 | 2021-10-01 |  |  |  |  | ST202109533042 | 2021-09-25 | P/FVC/MDS/1062857/2021 | 2021-10-01
710 | MUKSAT | MUKSAT | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TTPN-ENB-9051 | SR-TN000481 |  | On Air | 2021-10-13 | MUKSAT | 4G_FD900_MUKSAT | 4G_FD2100_MUKSAT | 4G_TD_MUKSAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527768 | 2021-09-22 | P/FVC/MDS/1062715/2021 | 2021-09-29 | ST202109531895 | 2021-09-24 | P/FVC/MDS/1062933/2021 | 2021-10-01 |  |  |  |  | ST202109528900 | 2021-09-23 | P/FBW/MDS/1062897/2021 | 2021-10-01
711 | NAIKAN | NAIKAN | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-NARD-ENB-9001 | SR-TN000461 |  | On Air | 2021-10-13 | NAIKAN | 4G_FD900_NAIKAN | 4G_FD2100_NAIKAN | 4G_TD_NAIKAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533312 | 2021-09-25 | P/FVC/MDS/1062986/2021 | 2021-10-01 | ST202109531909 | 2021-09-24 | P/FVC/MDS/1062948/2021 | 2021-10-01 |  |  |  |  | ST202109533048 | 2021-09-25 | P/FVC/MDS/1062863/2021 | 2021-10-01
712 | VETTUV | VETTUV | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-KBKD-ENB-9019 | SR-TN000465 |  | On Air | 2021-10-13 | VETTUV | 4G_FD900_VETTUV | 4G_FD2100_VETTUV | 4G_TD_VETTUV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533275 | 2021-09-25 | P/FVC/MDS/1062997/2021 | 2021-10-01 | ST202109531902 | 2021-09-24 | P/FVC/MDS/1062941/2021 | 2021-10-01 |  |  |  |  | ST202109533041 | 2021-09-25 | P/FVC/MDS/1062790/2021 | 2021-10-01
713 | THIRUP | THIRUP | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-KLVR-ENB-9022 | SR-TN000456 |  | On Air | 2021-10-13 | THIRUP | 4G_FD900_THIRUP | 4G_FD2100_THIRUP | 4G_TD_THIRUP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533313 | 2021-09-25 | P/FVC/MDS/1062987/2021 | 2021-10-01 | ST202109531910 | 2021-09-24 | P/FVC/MDS/1062949/2021 | 2021-10-01 |  |  |  |  | ST202109533049 | 2021-09-25 | P/FVC/MDS/1062864/2021 | 2021-10-01
714 | VIRINI | VIRINI | Vellore | Vellore |  | ROTN | Summit | I-TN-VLLR-ENB-9083 | SR-TN000464 |  | On Air | 2021-10-13 | VIRINI | 4G_FD900_VIRINI | 4G_FD2100_VIRINI | 4G_TD_VIRINI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533430 | 2021-09-25 | P/FVC/MDS/1062972/2021 | 2021-10-01 | ST202109532051 | 2021-09-24 | P/FVC/MDS/1062911/2021 | 2021-10-01 | ST202109530312 | 2021-09-24 | P/FVC/MDS/1063072/2021 | 2021-10-01 | ST202109533092 | 2021-09-25 | P/FVC/MDS/1062848/2021 | 2021-10-01
715 | AVANAM | AVANAM | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-KDVS-ENB-9030 | SR-TN000460 |  | On Air | 2021-10-13 | AVANAM | 4G_FD900_AVANAM | 4G_FD2100_AVANAM | 4G_TD_AVANAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527742 | 2021-09-22 | P/FVC/MDS/1062688/2021 | 2021-09-29 | ST202109526955 | 2021-09-21 | P/FVC/MDS/1062635/2021 | 2021-09-29 |  |  |  |  | ST202109528877 | 2021-09-23 | P/FBW/MDS/1062792/2021 | 2021-10-01
716 | NADLUR | NADLUR | Tiruvannamalai | Vellore |  | ROTN | Summit | I-TN-PLUR-ENB-9086 | SR-TN000463 |  | On Air | 2021-10-13 | NADLUR | 4G_FD900_NADLUR | 4G_FD2100_NADLUR | 4G_TD_NADLUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533273 | 2021-09-25 | P/FVC/MDS/1062995/2021 | 2021-10-01 | ST202109531900 | 2021-09-24 | P/FVC/MDS/1062939/2021 | 2021-10-01 |  |  |  |  | ST202109528905 | 2021-09-23 | P/FBW/MDS/1062902/2021 | 2021-10-01
717 | PUDKUD | PUDKUD | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-KDVS-ENB-9028 | SR-TN000462 |  | On Air | 2021-10-13 | PUDKUD | 4G_FD900_PUDKUD | 4G_FD2100_PUDKUD | 4G_TD_PUDKUD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527745 | 2021-09-22 | P/FVC/MDS/1062692/2021 | 2021-09-29 | ST202109526958 | 2021-09-21 | P/FVC/MDS/1062638/2021 | 2021-09-29 |  |  |  |  | ST202109528880 | 2021-09-23 | P/FBW/MDS/1062877/2021 | 2021-10-01
718 | ARIGIL | ARIGIL | Vellore | Vellore |  | ROTN | Summit | I-TN-ARKM-ENB-9062 | SR-TN000454 |  | On Air | 2021-10-13 | ARIGIL | 4G_FD900_ARIGIL | 4G_FD2100_ARIGIL | 4G_TD_ARIGIL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527740 | 2021-09-22 | P/FVC/MDS/1062545/2021 | 2021-09-27 | ST202109526952 | 2021-09-21 | P/FVC/MDS/1062633/2021 | 2021-09-29 |  |  |  |  | ST202109527575 | 2021-09-22 | P/FBW/MDS/1062599/2021 | 2021-09-29
719 | KAPPAR | KAPPAR | Salem | Vellore |  | ROTN | Summit | I-TN-DRMG-ENB-9001 | SR-TN000457 |  | On Air | 2021-10-13 | KAPPAR | 4G_FD900_KAPPAR | 4G_FD2100_KAPPAR | 4G_TD_KAPPAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533376 | 2021-09-25 | P/FVC/MDS/1062800/2021 | 2021-10-01 | ST202109531918 | 2021-09-24 | P/FVC/MDS/1062957/2021 | 2021-10-01 |  |  |  |  | ST202109533057 | 2021-09-25 | P/FVC/MDS/1062872/2021 | 2021-10-01
720 | VENGAN | VENGAN | Perambalur | Trichy |  | ROTN | Summit | I-TN-GGVL-ENB-9034 | SR-TN000472 |  | On Air | 2021-10-13 | VENGAN | 4G_FD900_VENGAN | 4G_FD2100_VENGAN | 4G_TD_VENGAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527746 | 2021-09-22 | P/FVC/MDS/1062693/2021 | 2021-09-29 | ST202109526959 | 2021-09-21 | P/FVC/MDS/1062639/2021 | 2021-09-29 |  |  |  |  | ST202109528881 | 2021-09-23 | P/FBW/MDS/1062878/2021 | 2021-10-01
721 | KALLAK | KALLAK | Tiruchirappalli | Trichy |  | ROTN | Summit | I-TN-KLKU-ENB-9002 | SR-TN000480 |  | On Air | 2021-10-13 | KALLAK | 4G_FD900_KALLAK | 4G_FD2100_KALLAK | 4G_TD_KALLAK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527683 | 2021-09-22 | P/FVC/MDS/1062685/2021 | 2021-09-29 | ST202109526949 | 2021-09-21 | P/FVC/MDS/1062630/2021 | 2021-09-29 |  |  |  |  | ST202109527572 | 2021-09-22 | P/FBW/MDS/1062596/2021 | 2021-09-29
722 | KALADE | KALADE | Salem | Vellore |  | ROTN | Summit | I-TN-EDPD-ENB-9029 | SR-TN000469 |  | On Air | 2021-10-13 | KALADE | 4G_FD900_KALADE | 4G_FD2100_KALADE | 4G_TD_KALADE | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533432 | 2021-09-25 | P/FVC/MDS/1062974/2021 | 2021-10-01 | ST202109532053 | 2021-09-24 | P/FVC/MDS/1062913/2021 | 2021-10-01 | ST202109530314 | 2021-09-24 | P/FVC/MDS/1063074/2021 | 2021-10-01 | ST202109533094 | 2021-09-25 | P/FVC/MDS/1062850/2021 | 2021-10-01
723 | PONPAT | PONPAT | Viluppuram | Trichy |  | ROTN | Summit | I-TN-GNGE-ENB-9066 | SR-TN000479 |  | On Air | 2021-10-13 | PONPAT | 4G_FD900_PONPAT | 4G_FD2100_PONPAT | 4G_TD_PONPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533271 | 2021-09-25 | P/FVC/MDS/1062993/2021 | 2021-10-01 | ST202109531898 | 2021-09-24 | P/FVC/MDS/1062936/2021 | 2021-10-01 |  |  |  |  | ST202109528903 | 2021-09-23 | P/FBW/MDS/1062900/2021 | 2021-10-01
724 | REDPAL | REDPAL | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-CGLP-ENB-9075 | SR-TN000455 |  | On Air | 2021-10-13 | REDPAL | 4G_FD900_REDPAL | 4G_FD2100_REDPAL | 4G_TD_REDPAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533272 | 2021-09-25 | P/FVC/MDS/1062994/2021 | 2021-10-01 | ST202109531899 | 2021-09-24 | P/FVC/MDS/1062938/2021 | 2021-10-01 |  |  |  |  | ST202109528904 | 2021-09-23 | P/FBW/MDS/1062901/2021 | 2021-10-01
725 | KUNDAR | KUNDAR | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-KGRI-ENB-9101 | SR-TN000474 |  | On Air | 2021-10-13 | KUNDAR | 4G_FD900_KUNDAR | 4G_FD2100_KUNDAR | 4G_TD_KUNDAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527743 | 2021-09-22 | P/FVC/MDS/1062690/2021 | 2021-09-29 | ST202109526956 | 2021-09-21 | P/FVC/MDS/1062636/2021 | 2021-09-29 |  |  |  |  | ST202109528878 | 2021-09-23 | P/FBW/MDS/1062875/2021 | 2021-10-01
726 | SIPYUR | SIPYUR | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-KGRI-ENB-9117 | SR-TN000471 |  | On Air | 2021-10-13 | SIPYUR | 4G_FD900_SIPYUR | 4G_FD2100_SIPYUR | 4G_TD_SIPYUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527747 | 2021-09-22 | P/FVC/MDS/1062694/2021 | 2021-09-29 | ST202109526960 | 2021-09-21 | P/FVC/MDS/1062640/2021 | 2021-09-29 |  |  |  |  | ST202109528882 | 2021-09-23 | P/FBW/MDS/1062879/2021 | 2021-10-01
727 | PDY315 | PDY315 |  |  |  | ROTN | ATC | IN-1383193 | R/NN-420631 |  |  | 2021-10-04 | PDY315 | 4G_FD900_PDY315 | 4G_FD2100_PDY315 | 4G_TD_PDY315 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110550036 | 2021-10-05 | P/FVC/MDS/1063549/2021 | 2021-10-20 | ST202110554023 | 2021-10-08 | P/FVC/MDS/1063574/2021 | 2021-10-20 | ST202110573970 | 2021-10-28 | P/FVC/MDS/1065786/2021 | 2021-11-16 | ST202110554214 | 2021-10-08 | P/FBW/MDS/1063658/2021 | 2021-10-22
728 | CBE888 | CBE888 |  |  |  | ROTN | Indus | IN-3030889 | R/NN-628166 |  |  | 2021-10-19 | CBE888 | 4G_FD900_CBE888 | 4G_FD2100_CBE888 | 4G_TD_CBE888 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110567681 | 2021-10-22 | P/FVC/MDS/1066522/2021 | 2021-11-19 | ST202110568129 | 2021-10-22 | P/FVC/MDS/1065680/2021 | 2021-11-16 | ST202204111899 | 2022-04-20 | P/FVC/MDS/1079017/2022 | 2022-05-03 | ST202110568174 | 2021-10-22 | P/FBW/MDS/1066528/2021 | 2021-11-19
729 | SEMBI4 | SEMBI4 |  |  |  | ROTN | Indus | IN-3042532 | R/NN-629739 |  |  | 2021-10-14 | SEMBI4 | 4G_FD900_SEMBI4 | 4G_FD2100_SEMBI4 | 4G_TD_SEMBI4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110553085 | 2021-10-07 | P/FVC/MDS/1063652/2021 | 2021-10-22 | ST202110568084 | 2021-10-22 | P/FVC/MDS/1065671/2021 | 2021-11-16 | ST202110563968 | 2021-10-19 | P/FVC/MDS/1065442/2021 | 2021-10-28 | ST202110563775 | 2021-10-19 | P/FVC/MDS/1065426/2021 | 2021-10-28
730 | KIRU07 | KIRU07 |  |  |  | ROTN | Indus | IN-3044126 | R/NN-630199 |  |  | 2021-10-14 | KIRU07 | 4G_FD900_KIRU07 | 4G_FD2100_KIRU07 | 4G_TD_KIRU07 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110553083 | 2021-10-07 | P/FVC/MDS/1063650/2021 | 2021-10-22 | ST202110568082 | 2021-10-22 | P/FVC/MDS/1065669/2021 | 2021-11-16 | ST202110563938 | 2021-10-19 | P/FVC/MDS/1065440/2021 | 2021-10-28 | ST202110563773 | 2021-10-19 | P/FVC/MDS/1065424/2021 | 2021-10-28
731 | ELVP04 | ELVP04 |  |  |  | ROTN | Indus | IN-3042778 | R/NN-629847 |  |  | 2021-10-13 | ELVP04 | 4G_FD900_ELVP04 | 4G_FD2100_ELVP04 | 4G_TD_ELVP04 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110559326 | 2021-10-14 | P/FVC/MDS/1063726/2021 | 2021-10-22 | ST202110560201 | 2021-10-14 | P/FVC/MDS/1063706/2021 | 2021-10-22 | ST202110575068 | 2021-10-28 | P/FVC/MDS/1065810/2021 | 2021-11-16 | ST202110555482 | 2021-10-09 | P/FBW/MDS/1063526/2021 | 2021-10-18
732 | MGRN10 | MGRN10 |  |  |  | CHN | Indus | IN-3012839 | R/NN-626700 |  |  | 2021-10-13 | MGRN10 | 4G_FD900_MGRN10 | 4G_FD2100_MGRN10 | 4G_TD_MGRN10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110553077 | 2021-10-07 | P/FVC/MDS/1063644/2021 | 2021-10-22 | ST202110568064 | 2021-10-22 | P/FVC/MDS/1065663/2021 | 2021-11-16 | ST202110563926 | 2021-10-19 | P/FVC/MDS/1065434/2021 | 2021-10-28 | ST202110563767 | 2021-10-19 | P/FVC/MDS/1065418/2021 | 2021-10-28
733 | MDTI21 | MDTI21 | Nagapattinam | Trichy |  | ROTN | Ascend | - | - |  | SO | 2021-10-30 | MDTI21 | 4G_FD900_MDTI21 | 4G_FD2100_MDTI21 | 4G_TD_MDTI21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577529 | 2021-10-30 | P/FVC/MDS/1065913/2021 | 2021-11-16 | ST202111585299 | 2021-11-09 | P/FVC/MDS/1068105/2021 | 2021-12-08 |  |  |  |  | ST202110577791 | 2021-10-30 | P/FBW/MDS/1067964/2021 | 2021-12-08
734 | KVPT37 | KVPT37 | Thoothukkudi | Madurai |  | ROTN | TVI | - | - |  | On Air | 2021-10-28 | KVPT37 | 4G_FD900_KVPT37 | 4G_FD2100_KVPT37 | 4G_TD_KVPT37 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573641 | 2021-10-27 | P/FVC/MDS/1065761/2021 | 2021-11-16 | ST202110577699 | 2021-10-30 | P/FVC/MDS/1065916/2021 | 2021-11-16 |  |  |  |  | ST202110577781 | 2021-10-30 | P/FBW/MDS/1067955/2021 | 2021-12-08
735 | PTAMD1 | PTAMD1 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/22617 | TN/TR/AT/22617 |  | On Air | 2021-10-30 | PTAMD1 | 4G_FD900_PTAMD1 | 4G_FD2100_PTAMD1 | 4G_TD_PTAMD1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577528 | 2021-10-30 | P/FVC/MDS/1065912/2021 | 2021-11-16 | ST202110577707 | 2021-10-30 | P/FVC/MDS/1065924/2021 | 2021-11-16 | ST202210548547 | 2022-10-11 | P/FVC/MDS/1113926/2022 | 2022-10-21 | ST202110577790 | 2021-10-30 | P/FBW/MDS/1067963/2021 | 2021-12-08
736 | VEEPAN | VEEPAN | Madurai | Madurai |  | ROTN | Indus | IN-3057065 | R/NN-633233 |  | On Air | 2021-10-23 | VEEPAN | 4G_FD900_VEEPAN | 4G_FD2100_VEEPAN | 4G_TD_VEEPAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572381 | 2021-10-27 | P/FVC/MDS/1065709/2021 | 2021-11-16 | ST202110574285 | 2021-10-28 | P/FVC/MDS/1065842/2021 | 2021-11-16 |  |  |  |  | ST202110572932 | 2021-10-27 | P/FBW/MDS/1066553/2021 | 2021-11-19
737 | NAMBU4 | NAMBU4 | Erode | Coimbatore |  | ROTN | Indus | IN-3043441 | R/NN-630001 |  | On Air | 2021-10-23 | NAMBU4 | 4G_FD900_NAMBU4 | 4G_FD2100_NAMBU4 | 4G_TD_NAMBU4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572332 | 2021-10-27 | P/FVC/MDS/1065705/2021 | 2021-11-16 | ST202110574233 | 2021-10-28 | P/FVC/MDS/1065838/2021 | 2021-11-16 |  |  |  |  | ST202110572832 | 2021-10-27 | P/FBW/MDS/1066550/2021 | 2021-11-19
738 | VAIGA1 | VAIGA1 | Karur | Coimbatore |  | ROTN | Indus | IN-3059819 | IN-3059819 |  | On Air | 2021-10-28 | VAIGA1 | 4G_FD900_VAIGA1 | 4G_FD2100_VAIGA1 | 4G_TD_VAIGA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577523 | 2021-10-30 | P/FVC/MDS/1065907/2021 | 2021-11-16 | ST202110577703 | 2021-10-30 | P/FVC/MDS/1065920/2021 | 2021-11-16 |  |  |  |  | ST202110577785 | 2021-10-30 | P/FBW/MDS/1067959/2021 | 2021-12-08
739 | VELAN1 | VELAN1 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3027807 | R/NN-628039 |  | On Air | 2021-10-23 | VELAN1 | 4G_FD900_VELAN1 | 4G_FD2100_VELAN1 | 4G_TD_VELAN1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572136 | 2021-10-27 | P/FVC/MDS/1065686/2021 | 2021-11-16 | ST202110574137 | 2021-10-28 | P/FVC/MDS/1065821/2021 | 2021-11-16 |  |  |  |  | ST202110572530 | 2021-10-27 | P/FBW/MDS/1066533/2021 | 2021-11-19
740 | KASIAM | KASIAM | Erode | Coimbatore |  | ROTN | Indus | IN-3047744 | R/NN-632183 |  | On Air | 2021-10-23 | KASIAM | 4G_FD900_KASIAM | 4G_FD2100_KASIAM | 4G_TD_KASIAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572146 | 2021-10-27 | P/FVC/MDS/1065689/2021 | 2021-11-16 | ST202110574153 | 2021-10-28 | P/FVC/MDS/1065824/2021 | 2021-11-16 |  |  |  |  | ST202110572537 | 2021-10-27 | P/FBW/MDS/1066536/2021 | 2021-11-19
741 | NADPAT | NADPAT | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-NMKK-ENB-9074 | I-TN-NMKK-ENB-9074 |  | On Air | 2021-10-26 | NADPAT | 4G_FD900_NADPAT | 4G_FD2100_NADPAT | 4G_TD_NADPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550221 | 2021-10-05 | P/FVC/MDS/1063564/2021 | 2021-10-20 | ST202110554037 | 2021-10-08 | P/FVC/MDS/1063588/2021 | 2021-10-20 |  |  |  |  | ST202110554904 | 2021-10-08 | P/FBW/MDS/1063672/2021 | 2021-10-22
742 | CHENAI | CHENAI | Erode | Coimbatore |  | ROTN | Summit | I-TN-PNDI-ENB-9071 | I-TN-PNDI-ENB-9071 |  | On Air | 2021-10-26 | CHENAI | 4G_FD900_CHENAI | 4G_FD2100_CHENAI | 4G_TD_CHENAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527748 | 2021-09-22 | P/FVC/MDS/1062695/2021 | 2021-09-29 | ST202109526961 | 2021-09-21 | P/FVC/MDS/1062641/2021 | 2021-09-29 |  |  |  |  | ST202110563779 | 2021-10-19 | P/FVC/MDS/1065430/2021 | 2021-10-28
743 | THENAD | THENAD | Karur | Coimbatore |  | ROTN | Indus | IN-3046626 | IN-3046626 |  | On Air | 2021-10-28 | THENAD | 4G_FD900_THENAD | 4G_FD2100_THENAD | 4G_TD_THENAD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577522 | 2021-10-30 | P/FVC/MDS/1065906/2021 | 2021-11-16 | ST202110577702 | 2021-10-30 | P/FVC/MDS/1065919/2021 | 2021-11-16 |  |  |  |  | ST202110577784 | 2021-10-30 | P/FBW/MDS/1067958/2021 | 2021-12-08
744 | SEMDAP | SEMDAP | Karur | Coimbatore |  | ROTN | Summit | I-TN-KRUR-ENB-9051 | I-TN-KRUR-ENB-9051 |  | On Air | 2021-10-26 | SEMDAP | 4G_FD900_SEMDAP | 4G_FD2100_SEMDAP | 4G_TD_SEMDAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527755 | 2021-09-22 | P/FVC/MDS/1062702/2021 | 2021-09-29 | ST202109526968 | 2021-09-21 | P/FVC/MDS/1062648/2021 | 2021-09-29 |  |  |  |  | ST202109528890 | 2021-09-23 | P/FBW/MDS/1062887/2021 | 2021-10-01
745 | THICHE | THICHE | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-KDVS-ENB-9015 | SR-TN000482 |  | On Air | 2021-10-23 | THICHE | 4G_FD900_THICHE | 4G_FD2100_THICHE | 4G_TD_THICHE | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110567680 | 2021-10-22 | P/FVC/MDS/1066521/2021 | 2021-11-19 | ST202110574127 | 2021-10-28 | P/FVC/MDS/1065818/2021 | 2021-11-16 |  |  |  |  | ST202110568167 | 2021-10-22 | P/FBW/MDS/1066527/2021 | 2021-11-19
746 | MALAMI | MALAMI | Sivaganga | Madurai |  | ROTN | Summit | I-TN-SVGG-ENB-9085 | I-TN-SVGG-ENB-9085 |  | On Air | 2021-10-26 | MALAMI | 4G_FD900_MALAMI | 4G_FD2100_MALAMI | 4G_TD_MALAMI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550218 | 2021-10-05 | P/FVC/MDS/1063560/2021 | 2021-10-20 | ST202110554034 | 2021-10-08 | P/FVC/MDS/1063585/2021 | 2021-10-20 |  |  |  |  | ST202110554228 | 2021-10-08 | P/FBW/MDS/1063669/2021 | 2021-10-22
747 | SENBAG | SENBAG | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-VDRY-ENB-9052 | I-TN-VDRY-ENB-9052 |  | On Air | 2021-10-26 | SENBAG | 4G_FD900_SENBAG | 4G_FD2100_SENBAG | 4G_TD_SENBAG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522057 | 2021-09-16 | P/FVC/MDS/1062395/2021 | 2021-09-23 | ST202109522187 | 2021-09-16 | P/FVC/MDS/1062445/2021 | 2021-09-23 |  |  |  |  | ST202109522242 | 2021-09-16 | P/FBW/MDS/1062493/2021 | 2021-09-23
748 | ALAKAM | ALAKAM | Thiruvallur | Chennai |  | ROTN | Indus | IN-3046660 | R/NN-632058 |  |  | 2021-10-23 | ALAKAM | 4G_FD900_ALAKAM | 4G_FD2100_ALAKAM | 4G_TD_ALAKAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572250 | 2021-10-27 | P/FVC/MDS/1065695/2021 | 2021-11-16 | ST202110574172 | 2021-10-28 | P/FVC/MDS/1065829/2021 | 2021-11-16 | ST202110573984 | 2021-10-28 | P/FVC/MDS/1065795/2021 | 2021-11-16 | ST202110572621 | 2021-10-27 | P/FBW/MDS/1066541/2021 | 2021-11-19
749 | KETHAN | KETHAN | Vellore | Vellore |  | ROTN | Summit | I-TN-TRPR-ENB-9060 | I-TN-TRPR-ENB-9060 |  | On Air | 2021-10-26 | KETHAN | 4G_FD900_KETHAN | 4G_FD2100_KETHAN | 4G_TD_KETHAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522061 | 2021-09-16 | P/FVC/MDS/1062399/2021 | 2021-09-23 | ST202109522191 | 2021-09-16 | P/FVC/MDS/1062449/2021 | 2021-09-23 |  |  |  |  | ST202109522246 | 2021-09-16 | P/FBW/MDS/1062497/2021 | 2021-09-23
750 | VELGUD | VELGUD | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TVUR-ENB-0027 | I-TN-TVUR-ENB-0027 |  | On Air | 2021-10-26 | VELGUD | 4G_FD900_VELGUD | 4G_FD2100_VELGUD | 4G_TD_VELGUD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522064 | 2021-09-16 | P/FVC/MDS/1062402/2021 | 2021-09-23 | ST202109522194 | 2021-09-16 | P/FVC/MDS/1062452/2021 | 2021-09-23 |  |  |  |  | ST202109522249 | 2021-09-16 | P/FBW/MDS/1062500/2021 | 2021-09-23
751 | KONDAG | KONDAG | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-DMPI-ENB-9040 | I-TN-DMPI-ENB-9040 |  | On Air | 2021-10-26 | KONDAG | 4G_FD900_KONDAG | 4G_FD2100_KONDAG | 4G_TD_KONDAG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522065 | 2021-09-16 | P/FVC/MDS/1062403/2021 | 2021-09-23 | ST202109522195 | 2021-09-16 | P/FVC/MDS/1062453/2021 | 2021-09-23 |  |  |  |  | ST202109522250 | 2021-09-16 | P/FBW/MDS/1062501/2021 | 2021-09-23
752 | SOMLAM | SOMLAM | Sivaganga | Madurai |  | ROTN | ATC | TN/MU/AT/22851 | TN/MU/AT/22851 |  | On Air | 2021-10-26 | SOMLAM | 4G_FD900_SOMLAM | 4G_FD2100_SOMLAM | 4G_TD_SOMLAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574112 | 2021-10-28 | P/FVC/MDS/1065851/2021 | 2021-11-16 | ST202110573023 | 2021-10-27 | P/FVC/MDS/1065724/2021 | 2021-11-16 |  |  |  |  | ST202110572493 | 2021-10-27 | P/FBW/MDS/1067904/2021 | 2021-12-08
753 | PAVAOR | PAVAOR | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22854 | - |  | On Air | 2021-10-23 | PAVAOR | 4G_FD900_PAVAOR | 4G_FD2100_PAVAOR | 4G_TD_PAVAOR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572382 | 2021-10-27 | P/FVC/MDS/1065710/2021 | 2021-11-16 | ST202110574286 | 2021-10-28 | P/FVC/MDS/1065843/2021 | 2021-11-16 |  |  |  |  | ST202110572960 | 2021-10-27 | P/FBW/MDS/1066555/2021 | 2021-11-19
754 | PVKKM4 | PVKKM4 | Thiruvallur | Chennai |  | ROTN | ATC | TN/TU/AT/22855 | TN/TU/AT/22855 |  | On Air | 2021-10-26 | PVKKM4 | 4G_FD900_PVKKM4 | 4G_FD2100_PVKKM4 | 4G_TD_PVKKM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574111 | 2021-10-28 | P/FVC/MDS/1065850/2021 | 2021-11-16 | ST202110573022 | 2021-10-27 | P/FVC/MDS/1065723/2021 | 2021-11-16 |  |  |  |  | ST202110572492 | 2021-10-27 | P/FBW/MDS/1067903/2021 | 2021-12-08
755 | BATLAH | BATLAH | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-HRUR-ENB-9062 | I-TN-HRUR-ENB-9062 |  | On Air | 2021-10-26 | BATLAH | 4G_FD900_BATLAH | 4G_FD2100_BATLAH | 4G_TD_BATLAH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533316 | 2021-09-25 | P/FVC/MDS/1062990/2021 | 2021-10-01 | ST202109531914 | 2021-09-24 | P/FVC/MDS/1062953/2021 | 2021-10-01 |  |  |  |  | ST202109533053 | 2021-09-25 | P/FVC/MDS/1062868/2021 | 2021-10-01
756 | RAMART | RAMART | Salem | Vellore |  | ROTN | Summit | I-TN-OMLR-ENB-9083 | I-TN-OMLR-ENB-9083 |  | On Air | 2021-10-26 | RAMART | 4G_FD900_RAMART | 4G_FD2100_RAMART | 4G_TD_RAMART | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533318 | 2021-09-25 | P/FVC/MDS/1062992/2021 | 2021-10-01 | ST202109531916 | 2021-09-24 | P/FVC/MDS/1062955/2021 | 2021-10-01 |  |  |  |  | ST202109533055 | 2021-09-25 | P/FVC/MDS/1062870/2021 | 2021-10-01
757 | PERKOV | PERKOV | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-PRPT-ENB-9039 | I-TN-PRPT-ENB-9039 |  | On Air | 2021-10-26 | PERKOV | 4G_FD900_PERKOV | 4G_FD2100_PERKOV | 4G_TD_PERKOV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533311 | 2021-09-25 | P/FVC/MDS/1062985/2021 | 2021-10-01 | ST202109531908 | 2021-09-24 | P/FVC/MDS/1062947/2021 | 2021-10-01 |  |  |  |  | ST202109533047 | 2021-09-25 | P/FVC/MDS/1062862/2021 | 2021-10-01
758 | GURPAR | GURPAR | Ariyalur | Trichy |  | ROTN | Summit | I-TN-UAHR-ENB-9001 | I-TN-UAHR-ENB-9001 |  | On Air | 2021-10-26 | GURPAR | 4G_FD900_GURPAR | 4G_FD2100_GURPAR | 4G_TD_GURPAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533315 | 2021-09-25 | P/FVC/MDS/1062989/2021 | 2021-10-01 | ST202109531912 | 2021-09-24 | P/FVC/MDS/1062951/2021 | 2021-10-01 |  |  |  |  | ST202109533051 | 2021-09-25 | P/FVC/MDS/1062866/2021 | 2021-10-01
759 | ALAGAM | ALAGAM | Sivaganga | Madurai |  | ROTN | ATC | TN/SI/AT/22856 | TN/SI/AT/22856 |  | On Air | 2021-10-26 | ALAGAM | 4G_FD900_ALAGAM | 4G_FD2100_ALAGAM | 4G_TD_ALAGAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574110 | 2021-10-28 | P/FVC/MDS/1065849/2021 | 2021-11-16 | ST202110573021 | 2021-10-27 | P/FVC/MDS/1065720/2021 | 2021-11-16 |  |  |  |  | ST202110572491 | 2021-10-27 | P/FBW/MDS/1067902/2021 | 2021-12-08
760 | NEIKAR | NEIKAR | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/22857 | TN/DI/AT/22857 |  | On Air | 2021-10-26 | NEIKAR | 4G_FD900_NEIKAR | 4G_FD2100_NEIKAR | 4G_TD_NEIKAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574109 | 2021-10-28 | P/FVC/MDS/1065848/2021 | 2021-11-16 | ST202110573020 | 2021-10-27 | P/FVC/MDS/1065719/2021 | 2021-11-16 |  |  |  |  | ST202110572490 | 2021-10-27 | P/FBW/MDS/1067901/2021 | 2021-12-08
761 | TPAVAZ | TPAVAZ | Cuddalore | Trichy |  | ROTN | Summit | I-TN-VDCM-ENB-9068 | I-TN-VDCM-ENB-9068 |  | On Air | 2021-10-26 | TPAVAZ | 4G_FD900_TPAVAZ | 4G_FD2100_TPAVAZ | 4G_TD_TPAVAZ | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537828 | 2021-09-29 | P/FVC/MDS/1063294/2021 | 2021-10-11 | ST202109531917 | 2021-09-24 | P/FVC/MDS/1062956/2021 | 2021-10-01 |  |  |  |  | ST202109533056 | 2021-09-25 | P/FVC/MDS/1062871/2021 | 2021-10-01
762 | THLUKK | THLUKK | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-STTU-ENB-9045 | I-TN-STTU-ENB-9045 |  | On Air | 2021-10-26 | THLUKK | 4G_FD900_THLUKK | 4G_FD2100_THLUKK | 4G_TD_THLUKK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533426 | 2021-09-25 | P/FVC/MDS/1062798/2021 | 2021-10-01 | ST202109532047 | 2021-09-24 | P/FVC/MDS/1062907/2021 | 2021-10-01 | ST202109530308 | 2021-09-24 | P/FVC/MDS/1063068/2021 | 2021-10-01 | ST202109533088 | 2021-09-25 | P/FVC/MDS/1062844/2021 | 2021-10-01
763 | KEEKAR | KEEKAR | Thoothukkudi | Madurai |  | ROTN | Summit | I-TN-RDHP-ENB-9056 | I-TN-RDHP-ENB-9056 |  | On Air | 2021-10-26 | KEEKAR | 4G_FD900_KEEKAR | 4G_FD2100_KEEKAR | 4G_TD_KEEKAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550223 | 2021-10-05 | P/FVC/MDS/1063566/2021 | 2021-10-20 | ST202110554039 | 2021-10-08 | P/FVC/MDS/1063590/2021 | 2021-10-20 |  |  |  |  | ST202110554906 | 2021-10-08 | P/FBW/MDS/1063674/2021 | 2021-10-22
764 | MUKKUL | MUKKUL | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-PLCD-ENB-9053 | I-TN-PLCD-ENB-9053 |  | On Air | 2021-10-26 | MUKKUL | 4G_FD900_MUKKUL | 4G_FD2100_MUKKUL | 4G_TD_MUKKUL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109537893 | 2021-09-29 | P/FVC/MDS/1063334/2021 | 2021-10-11 | ST202109538158 | 2021-09-29 | P/FVC/MDS/1063356/2021 | 2021-10-11 | ST202109530298 | 2021-09-24 | P/FVC/MDS/1063058/2021 | 2021-10-01 | ST202109538570 | 2021-09-29 | P/FBW/MDS/1063321/2021 | 2021-10-11
765 | THUMBV | THUMBV | Karur | Coimbatore |  | ROTN | Summit | I-TN-ARHI-ENB-9044 | I-TN-ARHI-ENB-9044 |  | On Air | 2021-10-26 | THUMBV | 4G_FD900_THUMBV | 4G_FD2100_THUMBV | 4G_TD_THUMBV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550219 | 2021-10-05 | P/FVC/MDS/1063561/2021 | 2021-10-20 | ST202110554035 | 2021-10-08 | P/FVC/MDS/1063586/2021 | 2021-10-20 |  |  |  |  | ST202110554229 | 2021-10-08 | P/FBW/MDS/1063670/2021 | 2021-10-22
766 | BGLUR6 | BGLUR6 | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-HSUR-ENB-9078 | I-TN-HSUR-ENB-9078 |  | On Air | 2021-10-26 | BGLUR6 | 4G_FD900_BGLUR6 | 4G_FD2100_BGLUR6 | 4G_TD_BGLUR6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527764 | 2021-09-22 | P/FVC/MDS/1062711/2021 | 2021-09-29 | ST202109526977 | 2021-09-21 | P/FVC/MDS/1062658/2021 | 2021-09-29 |  |  |  |  | ST202109528896 | 2021-09-23 | P/FBW/MDS/1062893/2021 | 2021-10-01
767 | PEDDAT | PEDDAT | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-KGRI-ENB-9118 | I-TN-KGRI-ENB-9118 |  | On Air | 2021-10-26 | PEDDAT | 4G_FD900_PEDDAT | 4G_FD2100_PEDDAT | 4G_TD_PEDDAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527741 | 2021-09-22 | P/FVC/MDS/1062687/2021 | 2021-09-29 | ST202109526954 | 2021-09-21 | P/FVC/MDS/1062634/2021 | 2021-09-29 |  |  |  |  | ST202109527576 | 2021-09-22 | P/FBW/MDS/1062600/2021 | 2021-09-29
768 | PANPUL | PANPUL | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-RJPM-ENB-9027 | I-TN-RJPM-ENB-9027 |  | On Air | 2021-10-26 | PANPUL | 4G_FD900_PANPUL | 4G_FD2100_PANPUL | 4G_TD_PANPUL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533309 | 2021-09-25 | P/FVC/MDS/1062808/2021 | 2021-10-01 | ST202109531904 | 2021-09-24 | P/FVC/MDS/1062943/2021 | 2021-10-01 |  |  |  |  | ST202109533043 | 2021-09-25 | P/FVC/MDS/1062858/2021 | 2021-10-01
769 | NAGAMA | NAGAMA | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-KNGY-ENB-9054 | I-TN-KNGY-ENB-9054 |  | On Air | 2021-10-26 | NAGAMA | 4G_FD900_NAGAMA | 4G_FD2100_NAGAMA | 4G_TD_NAGAMA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533314 | 2021-09-25 | P/FVC/MDS/1062988/2021 | 2021-10-01 | ST202109531911 | 2021-09-24 | P/FVC/MDS/1062950/2021 | 2021-10-01 |  |  |  |  | ST202109533050 | 2021-09-25 | P/FVC/MDS/1062865/2021 | 2021-10-01
770 | PUNGAN | PUNGAN | Nagapattinam | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2021-10-28 | PUNGAN | 4G_FD900_PUNGAN | 4G_FD2100_PUNGAN | 4G_TD_PUNGAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577525 | 2021-10-30 | P/FVC/MDS/1065909/2021 | 2021-11-16 | ST202110577705 | 2021-10-30 | P/FVC/MDS/1065922/2021 | 2021-11-16 |  |  |  |  | ST202110577788 | 2021-10-30 | P/FBW/MDS/1067961/2021 | 2021-12-08
771 | NALLAM | NALLAM | Salem | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2021-10-28 | NALLAM | 4G_FD900_NALLAM | 4G_FD2100_NALLAM | 4G_TD_NALLAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577521 | 2021-10-30 | P/FVC/MDS/1065905/2021 | 2021-11-16 | ST202110577701 | 2021-10-30 | P/FVC/MDS/1065918/2021 | 2021-11-16 |  |  |  |  | ST202110577783 | 2021-10-30 | P/FBW/MDS/1067957/2021 | 2021-12-08
772 | AHMAUR | AHMAUR | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2021-10-28 | AHMAUR | 4G_FD900_AHMAUR | 4G_FD2100_AHMAUR | 4G_TD_AHMAUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110576270 | 2021-10-29 | P/FVC/MDS/1065778/2021 | 2021-11-16 | ST202110577700 | 2021-10-30 | P/FVC/MDS/1065917/2021 | 2021-11-16 |  |  |  |  | ST202110577782 | 2021-10-30 | P/FBW/MDS/1067956/2021 | 2021-12-08
773 | THILAM | THILAM | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2021-10-30 | THILAM | 4G_FD900_THILAM | 4G_FD2100_THILAM | 4G_TD_THILAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585131 | 2021-11-09 | P/FVC/MDS/1068104/2021 | 2021-12-08 | ST202111585309 | 2021-11-09 | P/FVC/MDS/1068111/2021 | 2021-12-08 |  |  |  |  | ST202111581315 | 2021-11-03 | P/FBW/MDS/1067997/2021 | 2021-12-08
774 | KEEMAT | KEEMAT | Krishnagiri | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2021-10-30 | KEEMAT | 4G_FD900_KEEMAT | 4G_FD2100_KEEMAT | 4G_TD_KEEMAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577530 | 2021-10-30 | P/FVC/MDS/1065914/2021 | 2021-11-16 | ST202111585303 | 2021-11-09 | P/FVC/MDS/1068107/2021 | 2021-12-08 |  |  |  |  | ST202111581313 | 2021-11-03 | P/FBW/MDS/1067995/2021 | 2021-12-08
775 | TNJ360 | TNJ360 |  |  |  | ROTN | Indus | IN-3047056 | R/NN-629792 |  |  | 2021-10-23 | TNJ360 | 4G_FD900_TNJ360 | 4G_FD2100_TNJ360 | 4G_TD_TNJ360 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110572303 | 2021-10-27 | P/FVC/MDS/1065703/2021 | 2021-11-16 | ST202110574223 | 2021-10-28 | P/FVC/MDS/1065836/2021 | 2021-11-16 | ST202110574007 | 2021-10-28 | P/FVC/MDS/1065802/2021 | 2021-11-16 | ST202110572783 | 2021-10-27 | P/FBW/MDS/1066548/2021 | 2021-11-19
776 | VENCD5 | VENCD5 |  |  |  | ROTN | Indus | IN-3060594 | R/NN-633454 |  |  | 2021-10-28 | VENCD5 | 4G_FD900_VENCD5 | 4G_FD2100_VENCD5 | 4G_TD_VENCD5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110577524 | 2021-10-30 | P/FVC/MDS/1065908/2021 | 2021-11-16 | ST202110577704 | 2021-10-30 | P/FVC/MDS/1065921/2021 | 2021-11-16 | ST202111585557 | 2021-11-09 | P/FVC/MDS/1068147/2021 | 2021-12-08 | ST202110577786 | 2021-10-30 | P/FBW/MDS/1067960/2021 | 2021-12-08
777 | TVTRM3 | TVTRM3 |  |  |  | ROTN | Ascend | - | - |  |  | 2021-10-26 | TVTRM3 | 4G_FD900_TVTRM3 | 4G_FD2100_TVTRM3 | 4G_TD_TVTRM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110574108 | 2021-10-28 | P/FVC/MDS/1065847/2021 | 2021-11-16 | ST202110573019 | 2021-10-27 | P/FVC/MDS/1065718/2021 | 2021-11-16 | ST202110575070 | 2021-10-28 | P/FVC/MDS/1065812/2021 | 2021-11-16 | ST202110572488 | 2021-10-27 | P/FBW/MDS/1067899/2021 | 2021-12-08
778 | KATT16 | KATT16 |  |  |  | CHN | Indus | IN-3042093 | R/NN-629697 |  |  | 2021-10-23 | KATT16 | 4G_FD900_KATT16 | 4G_FD2100_KATT16 | 4G_TD_KATT16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110572282 | 2021-10-27 | P/FVC/MDS/1065700/2021 | 2021-11-16 | ST202110574218 | 2021-10-28 | P/FVC/MDS/1065833/2021 | 2021-11-16 | ST202110573999 | 2021-10-28 | P/FVC/MDS/1065799/2021 | 2021-11-16 | ST202110572654 | 2021-10-27 | P/FBW/MDS/1066545/2021 | 2021-11-19
779 | TKSI18 | TKSI18 |  |  |  | ROTN | Indus | IN-3058602 | R/NN-633229 |  | On Air | 2021-11-03 | TKSI18 | 4G_FD900_TKSI18 | 4G_FD2100_TKSI18 | 4G_TD_TKSI18 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111586164 | 2021-11-10 | P/FVC/MDS/1068155/2021 | 2021-12-08 | ST202111585310 | 2021-11-09 | P/FVC/MDS/1068112/2021 | 2021-12-08 |  |  |  |  | ST202111584777 | 2021-11-09 | P/FBW/MDS/1068068/2021 | 2021-12-08
780 | ZAMIKK | ZAMIKK |  |  |  | ROTN | BSNL | 2892 | - |  | On Air | 2021-11-02 | ZAMIKK | 4G_FD900_ZAMIKK | 4G_FD2100_ZAMIKK | 4G_TD_ZAMIKK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527754 | 2021-09-22 | P/FVC/MDS/1062701/2021 | 2021-09-29 | ST202109526967 | 2021-09-21 | P/FVC/MDS/1062647/2021 | 2021-09-29 |  |  |  |  | ST202109528889 | 2021-09-23 | P/FBW/MDS/1062886/2021 | 2021-10-01
781 | HOLLY1 | HOLLY1 |  |  |  | ROTN | Summit | I-TN-VVCD-ENB-9050 | SR-TN000495 |  | On Air | 2021-11-03 | HOLLY1 | 4G_FD900_HOLLY1 | 4G_FD2100_HOLLY1 | 4G_TD_HOLLY1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110567677 | 2021-10-22 | P/FVC/MDS/1066518/2021 | 2021-11-19 | ST202110568108 | 2021-10-22 | P/FVC/MDS/1065675/2021 | 2021-11-16 |  |  |  |  | ST202110568155 | 2021-10-22 | P/FBW/MDS/1066524/2021 | 2021-11-19
782 | KOVLUR | KOVLUR |  |  |  | ROTN | Summit | I-TN-PLCD-ENB-9051 | SR-TN000501 |  | On Air | 2021-11-03 | KOVLUR | 4G_FD900_KOVLUR | 4G_FD2100_KOVLUR | 4G_TD_KOVLUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559422 | 2021-10-14 | P/FVC/MDS/1063744/2021 | 2021-10-22 | ST202110560215 | 2021-10-14 | P/FVC/MDS/1063720/2021 | 2021-10-22 |  |  |  |  | ST202110560334 | 2021-10-14 | P/FVC/MDS/1063695/2021 | 2021-10-22
783 | SRIREN | SRIREN |  |  |  | ROTN | ATC | TN/TR/SH/15376 | - |  | On Air | 2021-11-02 | SRIREN | 4G_FD900_SRIREN | 4G_FD2100_SRIREN | 4G_TD_SRIREN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585039 | 2021-11-09 | P/FVC/MDS/1068092/2021 | 2021-12-08 | ST202111585348 | 2021-11-09 | P/FVC/MDS/1068129/2021 | 2021-12-08 |  |  |  |  | ST202111584762 | 2021-11-09 | P/FBW/MDS/1068065/2021 | 2021-12-08
784 | PERIYA | PERIYA |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-0294 | SR-TN000496 |  | On Air | 2021-11-03 | PERIYA | 4G_FD900_PERIYA | 4G_FD2100_PERIYA | 4G_TD_PERIYA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559427 | 2021-10-14 | P/FVC/MDS/1063749/2021 | 2021-10-22 | ST202110554921 | 2021-10-08 | P/FVC/MDS/1063769/2021 | 2021-10-22 |  |  |  |  | ST202110560352 | 2021-10-14 | P/FVC/MDS/1063700/2021 | 2021-10-22
785 | SOOLAI | SOOLAI |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-9008 | SR-TN000500 |  | On Air | 2021-11-03 | SOOLAI | 4G_FD900_SOOLAI | 4G_FD2100_SOOLAI | 4G_TD_SOOLAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559429 | 2021-10-14 | P/FVC/MDS/1063750/2021 | 2021-10-22 | ST202110554922 | 2021-10-08 | P/FVC/MDS/1063770/2021 | 2021-10-22 |  |  |  |  | ST202110560353 | 2021-10-14 | P/FVC/MDS/1063701/2021 | 2021-10-22
786 | AGRAHA | AGRAHA |  |  |  | ROTN | Indus | IN-1364630 | R/RES-506977 |  | On Air | 2021-11-02 | AGRAHA | 4G_FD900_AGRAHA | 4G_FD2100_AGRAHA | 4G_TD_AGRAHA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110567679 | 2021-10-22 | P/FVC/MDS/1066520/2021 | 2021-11-19 | ST202110568121 | 2021-10-22 | P/FVC/MDS/1065678/2021 | 2021-11-16 |  |  |  |  | ST202110568166 | 2021-10-22 | P/FBW/MDS/1066526/2021 | 2021-11-19
787 | RAMAMI | RAMAMI |  |  |  | ROTN | Summit | I-TN-KCUH-ENB-9001 | SR-TN000497 |  | On Air | 2021-11-03 | RAMAMI | 4G_FD900_RAMAMI | 4G_FD2100_RAMAMI | 4G_TD_RAMAMI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577526 | 2021-10-30 | P/FVC/MDS/1065910/2021 | 2021-11-16 | ST202110554924 | 2021-10-08 | P/FVC/MDS/1063772/2021 | 2021-10-22 |  |  |  |  | ST202110560354 | 2021-10-14 | P/FVC/MDS/1063702/2021 | 2021-10-22
788 | SRIPUT | SRIPUT |  |  |  | ROTN | Indus | IN-1130103 | R/RES-507137 |  | On Air | 2021-11-02 | SRIPUT | 4G_FD900_SRIPUT | 4G_FD2100_SRIPUT | 4G_TD_SRIPUT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574163 | 2021-10-28 | P/FVC/MDS/1065861/2021 | 2021-11-16 | ST202110573045 | 2021-10-27 | P/FVC/MDS/1065734/2021 | 2021-11-16 |  |  |  |  | ST202110572526 | 2021-10-27 | P/FBW/MDS/1067913/2021 | 2021-12-08
789 | ANAPAL | ANAPAL |  |  |  | ROTN | ATC | TN/NM/AI/10769 | - |  | On Air | 2021-11-02 | ANAPAL | 4G_FD900_ANAPAL | 4G_FD2100_ANAPAL | 4G_TD_ANAPAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574113 | 2021-10-28 | P/FVC/MDS/1065852/2021 | 2021-11-16 | ST202110573024 | 2021-10-27 | P/FVC/MDS/1065725/2021 | 2021-11-16 |  |  |  |  | ST202110572518 | 2021-10-27 | P/FBW/MDS/1067905/2021 | 2021-12-08
790 | NAIOOR | NAIOOR |  |  |  | ROTN | TVI | ACTNKGR0148 | - |  | On Air | 2021-11-03 | NAIOOR | 4G_FD900_NAIOOR | 4G_FD2100_NAIOOR | 4G_TD_NAIOOR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585114 | 2021-11-09 | P/FVC/MDS/1068099/2021 | 2021-12-08 | ST202111585316 | 2021-11-09 | P/FVC/MDS/1068116/2021 | 2021-12-08 |  |  |  |  | ST202111584790 | 2021-11-09 | P/FBW/MDS/1068072/2021 | 2021-12-08
791 | MDKLR3 | MDKLR3 |  |  |  | ROTN | Indus | IN-1243551 | R/RL-4800612 |  |  |  | MDKLR3 | 4G_FD900_MDKLR3 | 4G_FD2100_MDKLR3 | 4G_TD_MDKLR3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110574302 | 2021-10-28 | P/FVC/MDS/1065865/2021 | 2021-11-16 | ST202110573049 | 2021-10-27 | P/FVC/MDS/1065739/2021 | 2021-11-16 | ST202112616162 | 2021-12-14 | P/FVC/MDS/1069544/2021 | 2021-12-20 | ST202110572578 | 2021-10-27 | P/FBW/MDS/1067918/2021 | 2021-12-08
792 | JNAGM2 | JNAGM2 |  |  |  | ROTN | Summit | I-TN-KGRI-ENB-9114 | SR-TN000330 |  | On Air | 2021-11-03 | JNAGM2 | 4G_FD900_JNAGM2 | 4G_FD2100_JNAGM2 | 4G_TD_JNAGM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109515585 | 2021-09-09 | P/FVC/MDS/1060957/2021 | 2021-09-14 | ST202109511458 | 2021-09-07 | P/FVC/MDS/1061813/2021 | 2021-09-16 | ST202109515210 | 2021-09-09 | P/FVC/MDS/1062235/2021 | 2021-09-20 | ST202109513262 | 2021-09-08 | P/FBW/MDS/1061688/2021 | 2021-09-16
793 | NGL088 | NGL088 |  |  |  | ROTN | Indus | IN-3042701 | R/NN-629806 |  |  | 2021-11-02 | NGL088 | 4G_FD900_NGL088 | 4G_FD2100_NGL088 | 4G_TD_NGL088 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202111585101 | 2021-11-09 | P/FVC/MDS/1068097/2021 | 2021-12-08 | ST202111585300 | 2021-11-09 | P/FVC/MDS/1068106/2021 | 2021-12-08 | ST202111585551 | 2021-11-09 | P/FVC/MDS/1068146/2021 | 2021-12-08 | ST202111584789 | 2021-11-09 | P/FBW/MDS/1068071/2021 | 2021-12-08
794 | MADH28 | MADH28 |  |  |  | ROTN | Indus | IN-3064085 | R/NN-634106 |  |  | 2021-11-02 | MADH28 | 4G_FD900_MADH28 | 4G_FD2100_MADH28 | 4G_TD_MADH28 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202111585113 | 2021-11-09 | P/FVC/MDS/1068098/2021 | 2021-12-08 | ST202111585304 | 2021-11-09 | P/FVC/MDS/1068108/2021 | 2021-12-08 | ST202111585558 | 2021-11-09 | P/FVC/MDS/1068148/2021 | 2021-12-08 | ST202111584791 | 2021-11-09 | P/FBW/MDS/1068073/2021 | 2021-12-08
795 | MYLA18 | MYLA18 |  |  |  | ROTN | Indus | IN-3042121 | R/NN-629703 |  |  | 2021-11-03 | MYLA18 | 4G_FD900_MYLA18 | 4G_FD2100_MYLA18 | 4G_TD_MYLA18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202111585120 | 2021-11-09 | P/FVC/MDS/1068101/2021 | 2021-12-08 | ST202111585318 | 2021-11-09 | P/FVC/MDS/1068118/2021 | 2021-12-08 | ST202111585560 | 2021-11-09 | P/FVC/MDS/1068150/2021 | 2021-12-08 | ST202111584792 | 2021-11-09 | P/FBW/MDS/1068074/2021 | 2021-12-08
796 | MLGRM2 | MLGRM2 |  |  |  | ROTN | ATC | TN/TR/AT/22672 | - |  | On Air | 2021-11-11 | MLGRM2 | 4G_FD900_MLGRM2 | 4G_FD2100_MLGRM2 | 4G_TD_MLGRM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625647 | 2021-12-23 | P/FVC/MDS/1070389/2022 | 2022-01-03 | ST202112626467 | 2021-12-24 | P/FVC/MDS/1070232/2021 | 2021-12-30 | ST202109530336 | 2021-09-24 | P/FVC/MDS/1063096/2021 | 2021-10-01 | ST202112616598 | 2021-12-15 | P/FBW/MDS/1069567/2021 | 2021-12-22
797 | THVNK1 | THVNK1 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2021-11-11 | THVNK1 | 4G_FD900_THVNK1 | 4G_FD2100_THVNK1 | 4G_TD_THVNK1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587755 | 2021-11-12 | P/FVC/MDS/1068163/2021 | 2021-12-08 | ST202111588039 | 2021-11-12 | P/FVC/MDS/1068180/2021 | 2021-12-08 |  |  |  |  | ST202111588153 | 2021-11-12 | P/FBW/MDS/1068198/2021 | 2021-12-08
798 | KALYAR | KALYAR |  |  |  | ROTN | Indus | IN-3021183 | R/NN-627498 |  | On Air | 2021-11-11 | KALYAR | 4G_FD900_KALYAR | 4G_FD2100_KALYAR | 4G_TD_KALYAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587756 | 2021-11-12 | P/FVC/MDS/1068164/2021 | 2021-12-08 | ST202111588040 | 2021-11-12 | P/FVC/MDS/1068181/2021 | 2021-12-08 |  |  |  |  | ST202111588154 | 2021-11-12 | P/FBW/MDS/1068199/2021 | 2021-12-08
799 | PARPAT | PARPAT |  |  |  | ROTN | Indus | in-1110149 | R/RES-393452 |  | On Air | 2021-11-11 | PARPAT | 4G_FD900_PARPAT | 4G_FD2100_PARPAT | 4G_TD_PARPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527751 | 2021-09-22 | P/FVC/MDS/1062698/2021 | 2021-09-29 | ST202109526964 | 2021-09-21 | P/FVC/MDS/1062644/2021 | 2021-09-29 |  |  |  |  | ST202109528886 | 2021-09-23 | P/FBW/MDS/1062883/2021 | 2021-10-01
800 | MATKUL | MATKUL |  |  |  | ROTN | Indus | in-1123980 | R/RES-393459 |  | Dropped | 2021-11-11 | MATKUL | 4G_FD900_MATKUL | 4G_FD2100_MATKUL | 4G_TD_MATKUL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522042 | 2021-09-16 | P/FVC/MDS/1062379/2021 | 2021-09-23 | ST202109522167 | 2021-09-16 | P/FVC/MDS/1062430/2021 | 2021-09-23 |  |  |  |  | ST202109522226 | 2021-09-16 | P/FBW/MDS/1062477/2021 | 2021-09-23
801 | PARKAN | PARKAN |  |  |  | ROTN | Indus | IN-1139255 | R/RES-395383 |  | On Air | 2021-11-11 | PARKAN | 4G_FD900_PARKAN | 4G_FD2100_PARKAN | 4G_TD_PARKAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527681 | 2021-09-22 | P/FVC/MDS/1062683/2021 | 2021-09-29 | ST202109526947 | 2021-09-21 | P/FVC/MDS/1062548/2021 | 2021-09-27 |  |  |  |  | ST202109527570 | 2021-09-22 | P/FBW/MDS/1062594/2021 | 2021-09-29
802 | KOTMAD | KOTMAD |  |  |  | ROTN | ATC | TN/SA/AT/22853 | - |  | On Air | 2021-11-11 | KOTMAD | 4G_FD900_KOTMAD | 4G_FD2100_KOTMAD | 4G_TD_KOTMAD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587753 | 2021-11-12 | P/FVC/MDS/1068161/2021 | 2021-12-08 | ST202111588037 | 2021-11-12 | P/FVC/MDS/1068178/2021 | 2021-12-08 |  |  |  |  | ST202111588151 | 2021-11-12 | P/FBW/MDS/1068196/2021 | 2021-12-08
803 | THALAI | THALAI |  |  |  | ROTN | Ascend | - | - |  | SO | 2021-11-11 | THALAI | 4G_FD900_THALAI | 4G_FD2100_THALAI | 4G_TD_THALAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587754 | 2021-11-12 | P/FVC/MDS/1068162/2021 | 2021-12-08 | ST202111588038 | 2021-11-12 | P/FVC/MDS/1068179/2021 | 2021-12-08 |  |  |  |  | ST202111588152 | 2021-11-12 | P/FBW/MDS/1068197/2021 | 2021-12-08
804 | KULLAM | KULLAM |  |  |  | ROTN | ATC | TN/SA/TT/14004 | - |  | On Air | 2021-11-13 | KULLAM | 4G_FD900_KULLAM | 4G_FD2100_KULLAM | 4G_TD_KULLAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585518 | 2021-11-09 | P/FVC/MDS/1068141/2021 | 2021-12-08 | ST202111585347 | 2021-11-09 | P/FVC/MDS/1068128/2021 | 2021-12-08 |  |  |  |  | ST202111584857 | 2021-11-09 | P/FBW/MDS/1068083/2021 | 2021-12-08
805 | MAHAJA | MAHAJA |  |  |  | ROTN | Indus | IN-1107066 | R/RES-507311 |  | On Air | 2021-11-13 | MAHAJA | 4G_FD900_MAHAJA | 4G_FD2100_MAHAJA | 4G_TD_MAHAJA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585528 | 2021-11-09 | P/FVC/MDS/1068143/2021 | 2021-12-08 | ST202111585349 | 2021-11-09 | P/FVC/MDS/1068130/2021 | 2021-12-08 |  |  |  |  | ST202111584800 | 2021-11-09 | P/FBW/MDS/1068076/2021 | 2021-12-08
806 | KODMOT | KODMOT |  |  |  | ROTN | ATC | TN/VE/AI/18685 | - |  | On Air | 2021-11-13 | KODMOT | 4G_FD900_KODMOT | 4G_FD2100_KODMOT | 4G_TD_KODMOT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585122 | 2021-11-09 | P/FVC/MDS/1068103/2021 | 2021-12-08 | ST202111585324 | 2021-11-09 | P/FVC/MDS/1068122/2021 | 2021-12-08 | ST202111587636 | 2021-11-12 | P/FVC/MDS/1068154/2021 | 2021-12-08 | ST202111584806 | 2021-11-09 | P/FBW/MDS/1068077/2021 | 2021-12-08
807 | VALIPA | VALIPA |  |  |  | ROTN | CNIL | TAM/GBT/K/08653 | - |  | On Air | 2021-11-11 | VALIPA | 4G_FD900_VALIPA | 4G_FD2100_VALIPA | 4G_TD_VALIPA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585038 | 2021-11-09 | P/FVC/MDS/1068091/2021 | 2021-12-08 | ST202111585311 | 2021-11-09 | P/FVC/MDS/1068113/2021 | 2021-12-08 |  |  |  |  | ST202111581318 | 2021-11-03 | P/FBW/MDS/1068000/2021 | 2021-12-08
808 | KALARA | KALARA |  |  |  | ROTN | Indus | IN-1116940 | R/RES-507310 |  | On Air | 2021-11-13 | KALARA | 4G_FD900_KALARA | 4G_FD2100_KALARA | 4G_TD_KALARA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592501 | 2021-11-17 | P/FVC/MDS/1066606/2021 | 2021-11-26 | ST202111592672 | 2021-11-17 | P/FVC/MDS/1066561/2021 | 2021-11-24 |  |  |  |  | ST202111592274 | 2021-11-16 | P/FBW/MDS/1066569/2021 | 2021-11-25
809 | SRYP05 | SRYP05 |  |  |  | ROTN | CNIL | TAM/GBT/K/28930 | - |  |  | 2021-11-11 | SRYP05 | 4G_FD900_SRYP05 | 4G_FD2100_SRYP05 | 4G_TD_SRYP05 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585509 | 2021-11-09 | P/FVC/MDS/1068136/2021 | 2021-12-08 | ST202111585351 | 2021-11-09 | P/FVC/MDS/1068132/2021 | 2021-12-08 | ST202112615788 | 2021-12-14 | P/FVC/MDS/1069532/2021 | 2021-12-20 | ST202111584807 | 2021-11-09 | P/FBW/MDS/1068078/2021 | 2021-12-08
810 | AIQUA1 | AIQUA1 |  |  |  | CHN | Indus | IN-3052077 | R/NN-632735 |  | On air | 2021-11-13 | AIQUA1 | 4G_FD900_AIQUA1 | 4G_FD2100_AIQUA1 | 4G_TD_AIQUA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592498 | 2021-11-17 | P/FVC/MDS/1066603/2021 | 2021-11-26 | ST202111592669 | 2021-11-17 | P/FVC/MDS/1066558/2021 | 2021-11-24 | ST202204095113 | 2022-04-08 | P/FVC/MDS/1078404/2022 | 2022-04-21 | ST202111588433 | 2021-11-12 | P/FBW/MDS/1068208/2021 | 2021-12-08
811 | TAJHO2 | TAJHO2 |  |  |  | CHN | Srigom |  |  |  | On air | 2021-11-12 | TAJHO2 | 4G_FD900_TAJHO2 | 4G_FD2100_TAJHO2 | 4G_TD_TAJHO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592499 | 2021-11-17 | P/FVC/MDS/1066604/2021 | 2021-11-26 | ST202111592670 | 2021-11-17 | P/FVC/MDS/1066559/2021 | 2021-11-24 | ST202210538366 | 2022-10-08 | P/FVC/MDS/1113887/2022 | 2022-10-21 | ST202111588434 | 2021-11-12 | P/FBW/MDS/1068209/2021 | 2021-12-08
812 | MPPNP | MPPNP |  |  |  | ROTN | ATC | TN/TA/AT/22442 | T21TN01779 |  |  | 2021-11-17 | MPPNP | 4G_FD900_MPPNP | 4G_FD2100_MPPNP | 4G_TD_MPPNP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109504568 | 2021-09-02 | P/FVC/MDS/1060786/2021 | 2021-09-13 | ST202109501781 | 2021-09-02 | P/FVC/MDS/1060727/2021 | 2021-09-13 |  |  |  |  | ST202109513238 | 2021-09-08 | P/FBW/MDS/1061664/2021 | 2021-09-16
813 | USSOOR | USSOOR |  |  |  | ROTN | ATC | TN/VE/AT/22880 |  |  | On Air | 2021-11-17 | USSOOR | 4G_FD900_USSOOR | 4G_FD2100_USSOOR | 4G_TD_USSOOR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111595154 | 2021-11-19 | P/FVC/MDS/1067074/2021 | 2021-12-01 | ST202111595248 | 2021-11-19 | P/FVC/MDS/1067061/2021 | 2021-12-01 |  |  |  |  | ST202111595313 | 2021-11-19 | P/FBW/MDS/1067050/2021 | 2021-12-01
814 | KATT11 | KATT11 |  |  |  | ROTN | ATC | TN/VE/AT/22887 |  |  | On Air | 2021-11-17 | KATT11 | 4G_FD900_KATT11 | 4G_FD2100_KATT11 | 4G_TD_KATT11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111595155 | 2021-11-19 | P/FVC/MDS/1067075/2021 | 2021-12-01 | ST202111595249 | 2021-11-19 | P/FVC/MDS/1067062/2021 | 2021-12-01 |  |  |  |  | ST202111595314 | 2021-11-19 | P/FBW/MDS/1067051/2021 | 2021-12-01
815 | NSNP16 | NSNP16 |  |  |  | ROTN | Airtel | - |  |  |  | 2021-11-20 | NSNP16 | 4G_FD900_NSNP16 | 4G_FD2100_NSNP16 | 4G_TD_NSNP16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202112610509 | 2021-12-10 | P/FVC/MDS/1069104/2021 | 2021-12-17 | ST202112604633 | 2021-12-07 | P/FVC/MDS/1068756/2021 | 2021-12-15 | ST202112615790 | 2021-12-14 | P/FVC/MDS/1069534/2021 | 2021-12-20 | ST202112608830 | 2021-12-09 | P/FBW/MDS/1068859/2021 | 2021-12-15
816 | TECGE2 | TECGE2 |  |  |  | ROTN | Ascend | - |  |  |  | 2021-11-20 | TECGE2 | 4G_FD900_TECGE2 | 4G_FD2100_TECGE2 | 4G_TD_TECGE2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202112610524 | 2021-12-10 | P/FVC/MDS/1069107/2021 | 2021-12-17 | ST202112604645 | 2021-12-07 | P/FVC/MDS/1068759/2021 | 2021-12-15 | ST202112615795 | 2021-12-14 | P/FVC/MDS/1069537/2021 | 2021-12-20 | ST202112608836 | 2021-12-09 | P/FBW/MDS/1068862/2021 | 2021-12-15
817 | TCGD76 | TCGD76 |  |  |  | ROTN | Airtel | - |  |  |  | 2021-11-20 | TCGD76 | 4G_FD900_TCGD76 | 4G_FD2100_TCGD76 | 4G_TD_TCGD76 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202112610510 | 2021-12-10 | P/FVC/MDS/1069105/2021 | 2021-12-17 | ST202112604638 | 2021-12-07 | P/FVC/MDS/1068757/2021 | 2021-12-15 | ST202112615793 | 2021-12-14 | P/FVC/MDS/1069535/2021 | 2021-12-20 | ST202112608831 | 2021-12-09 | P/FBW/MDS/1068860/2021 | 2021-12-15
818 | SMNLR4 | SMNLR4 |  |  |  | ROTN | BSNL | 1406 |  |  |  | 2021-11-20 | SMNLR4 | 4G_FD900_SMNLR4 | 4G_FD2100_SMNLR4 | 4G_TD_SMNLR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202112610508 | 2021-12-10 | P/FVC/MDS/1069103/2021 | 2021-12-17 | ST202112604628 | 2021-12-07 | P/FVC/MDS/1068755/2021 | 2021-12-15 | ST202112615789 | 2021-12-14 | P/FVC/MDS/1069533/2021 | 2021-12-20 | ST202112608821 | 2021-12-09 | P/FBW/MDS/1068858/2021 | 2021-12-15
819 | RAJAK7 | RAJAK7 |  |  |  | CHN | Airtel |  |  |  |  | 2021-11-20 | RAJAK7 | 4G_FD900_RAJAK7 | 4G_FD2100_RAJAK7 | 4G_TD_RAJAK7 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202112610532 | 2021-12-10 | P/FVC/MDS/1069108/2021 | 2021-12-17 | ST202112604652 | 2021-12-07 | P/FVC/MDS/1068760/2021 | 2021-12-15 | ST202112615796 | 2021-12-14 | P/FVC/MDS/1069538/2021 | 2021-12-20 | ST202112608842 | 2021-12-09 | P/FBW/MDS/1068863/2021 | 2021-12-15
820 | KUTH3 | KUTH03 |  |  |  | ROTN | Ascend | - |  |  | On Air | 2021-11-25 | KUTH03 | 4G_FD900_KUTH03 | 4G_FD2100_KUTH03 | 4G_TD_KUTH03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610810 | 2021-12-10 | P/FVC/MDS/1069069/2021 | 2021-12-17 | ST202112604851 | 2021-12-07 | P/FVC/MDS/1068816/2021 | 2021-12-15 |  |  |  |  | ST202112609173 | 2021-12-09 | P/FBW/MDS/1068780/2021 | 2021-12-15
821 | CHETTM | CHETTM |  |  |  | ROTN | TVI | - |  |  | On Air | 2021-11-24 | CHETTM | 4G_FD900_CHETTM | 4G_FD2100_CHETTM | 4G_TD_CHETTM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610623 | 2021-12-10 | P/FVC/MDS/1069120/2021 | 2021-12-17 | ST202112604730 | 2021-12-07 | P/FVC/MDS/1068772/2021 | 2021-12-15 |  |  |  |  | ST202112609094 | 2021-12-09 | P/FBW/MDS/1068876/2021 | 2021-12-15
822 | KASANG | KASANG |  |  |  | ROTN | Ascend | - |  |  | SR | 2021-11-25 | KASANG | 4G_FD900_KASANG | 4G_FD2100_KASANG | 4G_TD_KASANG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610678 | 2021-12-10 | P/FVC/MDS/1069128/2021 | 2021-12-17 | ST202112604847 | 2021-12-07 | P/FVC/MDS/1068815/2021 | 2021-12-15 |  |  |  |  | ST202112609172 | 2021-12-09 | P/FBW/MDS/1068779/2021 | 2021-12-15
823 | JAMVAN | JAMVAN |  |  |  | ROTN | ATC | TN/TI/AT/22889 |  |  | On Air | 2021-11-25 | JAMVAN | 4G_FD900_JAMVAN | 4G_FD2100_JAMVAN | 4G_TD_JAMVAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610816 | 2021-12-10 | P/FVC/MDS/1069072/2021 | 2021-12-17 | ST202112604864 | 2021-12-07 | P/FVC/MDS/1068819/2021 | 2021-12-15 |  |  |  |  | ST202112609183 | 2021-12-09 | P/FBW/MDS/1068783/2021 | 2021-12-15
824 | VEPPIL | VEPPIL |  |  |  | ROTN | Summit | I-TN-VLPD-ENB-9031 | SR-TN000505 |  | On Air | 2021-11-24 | VEPPIL | 4G_FD900_VEPPIL | 4G_FD2100_VEPPIL | 4G_TD_VEPPIL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559420 | 2021-10-14 | P/FVC/MDS/1063742/2021 | 2021-10-22 | ST202110560213 | 2021-10-14 | P/FVC/MDS/1063718/2021 | 2021-10-22 |  |  |  |  | ST202110560332 | 2021-10-14 | P/FVC/MDS/1063693/2021 | 2021-10-22
825 | MOKANR | MOKANR |  |  |  | ROTN | Ascend | - | - |  | On Air | 2021-11-24 | MOKANR | 4G_FD900_MOKANR | 4G_FD2100_MOKANR | 4G_TD_MOKANR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610572 | 2021-12-10 | P/FVC/MDS/1069113/2021 | 2021-12-17 | ST202112604675 | 2021-12-07 | P/FVC/MDS/1068765/2021 | 2021-12-15 |  |  |  |  | ST202112609073 | 2021-12-09 | P/FBW/MDS/1068869/2021 | 2021-12-15
826 | VENKA1 | VENKA1 |  |  |  | ROTN | Summit | I-TN-SVUR-ENB-0015 | SR-TN000548 |  | On Air | 2021-11-24 | VENKA1 | 4G_FD900_VENKA1 | 4G_FD2100_VENKA1 | 4G_TD_VENKA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572398 | 2021-10-27 | P/FVC/MDS/1065713/2021 | 2021-11-16 | ST202110574368 | 2021-10-28 | P/FVC/MDS/1065876/2021 | 2021-11-16 |  |  |  |  | ST202110573006 | 2021-10-27 | P/FBW/MDS/1066558/2021 | 2021-11-19
827 | PADVAI | PADVAI |  |  |  | ROTN | Summit | I-TN-SVUR-ENB-9039 | SR-TN000537 |  | On Air | 2021-11-24 | PADVAI | 4G_FD900_PADVAI | 4G_FD2100_PADVAI | 4G_TD_PADVAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573642 | 2021-10-27 | P/FVC/MDS/1065762/2021 | 2021-11-16 | ST202110574398 | 2021-10-28 | P/FVC/MDS/1065878/2021 | 2021-11-16 |  |  |  |  | ST202110573500 | 2021-10-27 | P/FBW/MDS/1067936/2021 | 2021-12-08
828 | UAGRAM | UAGRAM |  |  |  | ROTN | Summit | I-TN-VDCM-ENB-9073 | SR-TN000536 |  | On Air | 2021-11-25 | UAGRAM | 4G_FD900_UAGRAM | 4G_FD2100_UAGRAM | 4G_TD_UAGRAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573661 | 2021-10-27 | P/FVC/MDS/1065764/2021 | 2021-11-16 | ST202110574406 | 2021-10-28 | P/FVC/MDS/1065880/2021 | 2021-11-16 |  |  |  |  | ST202110573506 | 2021-10-27 | P/FBW/MDS/1067938/2021 | 2021-12-08
829 | CHINAK | CHINAK |  |  |  | ROTN | Ascend | - | - |  | On Air | 2021-11-25 | CHINAK | 4G_FD900_CHINAK | 4G_FD2100_CHINAK | 4G_TD_CHINAK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610639 | 2021-12-10 | P/FVC/MDS/1069123/2021 | 2021-12-17 | ST202112604821 | 2021-12-07 | P/FVC/MDS/1068810/2021 | 2021-12-15 |  |  |  |  | ST202112609147 | 2021-12-09 | P/FBW/MDS/1068774/2021 | 2021-12-15
830 | ADBASH | ADBASH |  |  |  | ROTN | Summit | I-TN-PNRT-ENB-9035 | SR-TN000547 |  | On Air | 2021-11-25 | ADBASH | 4G_FD900_ADBASH | 4G_FD2100_ADBASH | 4G_TD_ADBASH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573673 | 2021-10-27 | P/FVC/MDS/1065765/2021 | 2021-11-16 | ST202110574407 | 2021-10-28 | P/FVC/MDS/1065881/2021 | 2021-11-16 |  |  |  |  | ST202110573510 | 2021-10-27 | P/FBW/MDS/1067939/2021 | 2021-12-08
831 | MANPAM | MANPAM |  |  |  | ROTN | Summit | I-TN-PNRT-ENB-9061 | SR-TN000539 |  | On Air | 2021-11-25 | MANPAM | 4G_FD900_MANPAM | 4G_FD2100_MANPAM | 4G_TD_MANPAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573674 | 2021-10-27 | P/FVC/MDS/1065766/2021 | 2021-11-16 | ST202110574416 | 2021-10-28 | P/FVC/MDS/1065882/2021 | 2021-11-16 |  |  |  |  | ST202110573511 | 2021-10-27 | P/FBW/MDS/1067940/2021 | 2021-12-08
832 | NALPAL | NALPAL |  |  |  | ROTN | Ascend | - | - |  | On Air | 2021-11-24 | NALPAL | 4G_FD900_NALPAL | 4G_FD2100_NALPAL | 4G_TD_NALPAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610545 | 2021-12-10 | P/FVC/MDS/1069112/2021 | 2021-12-17 | ST202112604669 | 2021-12-07 | P/FVC/MDS/1068764/2021 | 2021-12-15 |  |  |  |  | ST202112609062 | 2021-12-09 | P/FBW/MDS/1068868/2021 | 2021-12-15
833 | NATHAM | NATHAM |  |  |  | ROTN | Summit | I-TN-PRPT-ENB-9054 | SR-TN000535 |  | On Air | 2021-11-24 | NATHAM | 4G_FD900_NATHAM | 4G_FD2100_NATHAM | 4G_TD_NATHAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573701 | 2021-10-27 | P/FVC/MDS/1065768/2021 | 2021-11-16 | ST202110574429 | 2021-10-28 | P/FVC/MDS/1065884/2021 | 2021-11-16 |  |  |  |  | ST202110573514 | 2021-10-27 | P/FBW/MDS/1067942/2021 | 2021-12-08
834 | NALHAL | NALHAL |  |  |  | ROTN | Summit | I-TN-PRPT-ENB-9056 | SR-TN000542 |  | On Air | 2021-11-24 | NALHAL | 4G_FD900_NALHAL | 4G_FD2100_NALHAL | 4G_TD_NALHAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573779 | 2021-10-27 | P/FVC/MDS/1065777/2021 | 2021-11-16 | ST202110574430 | 2021-10-28 | P/FVC/MDS/1065885/2021 | 2021-11-16 |  |  |  |  | ST202110573520 | 2021-10-27 | P/FBW/MDS/1067943/2021 | 2021-12-08
835 | MALPA1 | MALPA1 |  |  |  | ROTN | Summit | I-TN-UTHN-ENB-9057 | SR-TN000568 |  | On Air | 2021-11-24 | MALPA1 | 4G_FD900_MALPA1 | 4G_FD2100_MALPA1 | 4G_TD_MALPA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574161 | 2021-10-28 | P/FVC/MDS/1065859/2021 | 2021-11-16 | ST202110573043 | 2021-10-27 | P/FVC/MDS/1065732/2021 | 2021-11-16 |  |  |  |  | ST202111592282 | 2021-11-16 | P/FBW/MDS/1066577/2021 | 2021-11-25
836 | KOMPAT | KOMPAT |  |  |  | ROTN | Summit | I-TN-UTHN-ENB-9056 | SR-TN000540 |  | On Air | 2021-11-24 | KOMPAT | 4G_FD900_KOMPAT | 4G_FD2100_KOMPAT | 4G_TD_KOMPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573735 | 2021-10-27 | P/FVC/MDS/1065770/2021 | 2021-11-16 | ST202110574432 | 2021-10-28 | P/FVC/MDS/1065887/2021 | 2021-11-16 |  |  |  |  | ST202110573524 | 2021-10-27 | P/FBW/MDS/1067945/2021 | 2021-12-08
837 | POOSA1 | POOSA1 |  |  |  | ROTN | Summit | I-TN-AVNS-ENB-9109 | SR-TN000534 |  | On Air | 2021-11-24 | POOSA1 | 4G_FD900_POOSA1 | 4G_FD2100_POOSA1 | 4G_TD_POOSA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573775 | 2021-10-27 | P/FVC/MDS/1065773/2021 | 2021-11-16 | ST202110574435 | 2021-10-28 | P/FVC/MDS/1065890/2021 | 2021-11-16 |  |  |  |  | ST202110573529 | 2021-10-27 | P/FBW/MDS/1067948/2021 | 2021-12-08
838 | NAZATH | NAZATH |  |  |  | ROTN | Summit | I-TN-NZRT-ENB-9004 | SR-TN000530 |  | On Air | 2021-11-24 | NAZATH | 4G_FD900_NAZATH | 4G_FD2100_NAZATH | 4G_TD_NAZATH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573776 | 2021-10-27 | P/FVC/MDS/1065774/2021 | 2021-11-16 | ST202110574436 | 2021-10-28 | P/FVC/MDS/1065891/2021 | 2021-11-16 |  |  |  |  | ST202110573532 | 2021-10-27 | P/FBW/MDS/1067949/2021 | 2021-12-08
839 | KADENI | KADENI |  |  |  | ROTN | Summit | I-TN-NMKK-ENB-9109 | SR-TN000538 |  | On Air | 2021-11-24 | KADENI | 4G_FD900_KADENI | 4G_FD2100_KADENI | 4G_TD_KADENI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573777 | 2021-10-27 | P/FVC/MDS/1065775/2021 | 2021-11-16 | ST202110574437 | 2021-10-28 | P/FVC/MDS/1065893/2021 | 2021-11-16 |  |  |  |  | ST202110573533 | 2021-10-27 | P/FBW/MDS/1067950/2021 | 2021-12-08
840 | MUKPER | MUKPER |  |  |  | ROTN | Summit | I-TN-NZRT-ENB-0001 | SR-TN000544 |  | On Air | 2021-11-24 | MUKPER | 4G_FD900_MUKPER | 4G_FD2100_MUKPER | 4G_TD_MUKPER | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574158 | 2021-10-28 | P/FVC/MDS/1065856/2021 | 2021-11-16 | ST202110573040 | 2021-10-27 | P/FVC/MDS/1065729/2021 | 2021-11-16 |  |  |  |  | ST202110572522 | 2021-10-27 | P/FBW/MDS/1067909/2021 | 2021-12-08
841 | ERVADI | ERVADI |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-9029 | SR-TN000623 |  | On Air | 2021-11-24 | ERVADI | 4G_FD900_ERVADI | 4G_FD2100_ERVADI | 4G_TD_ERVADI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574304 | 2021-10-28 | P/FVC/MDS/1065867/2021 | 2021-11-16 | ST202110573051 | 2021-10-27 | P/FVC/MDS/1065742/2021 | 2021-11-16 |  |  |  |  | ST202110572580 | 2021-10-27 | P/FBW/MDS/1067920/2021 | 2021-12-08
842 | ELLIMA | ELLIMA |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-9071 | SR-TN000600 |  | On Air | 2021-11-24 | ELLIMA | 4G_FD900_ELLIMA | 4G_FD2100_ELLIMA | 4G_TD_ELLIMA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574305 | 2021-10-28 | P/FVC/MDS/1065868/2021 | 2021-11-16 | ST202110573052 | 2021-10-27 | P/FVC/MDS/1065743/2021 | 2021-11-16 |  |  |  |  | ST202110572581 | 2021-10-27 | P/FBW/MDS/1067921/2021 | 2021-12-08
843 | ERUMAI | ERUMAI |  |  |  | ROTN | Summit | I-TN-EDPD-ENB-9031 | SR-TN000602 |  | On Air | 2021-11-24 | ERUMAI | 4G_FD900_ERUMAI | 4G_FD2100_ERUMAI | 4G_TD_ERUMAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574308 | 2021-10-28 | P/FVC/MDS/1065871/2021 | 2021-11-16 | ST202110573055 | 2021-10-27 | P/FVC/MDS/1065746/2021 | 2021-11-16 |  |  |  |  | ST202110572584 | 2021-10-27 | P/FBW/MDS/1067924/2021 | 2021-12-08
844 | PARBAT | PARBAT |  |  |  | ROTN | Summit | I-TN-SKGR-ENB-9061 | SR-TN000603 |  | On Air | 2021-11-24 | PARBAT | 4G_FD900_PARBAT | 4G_FD2100_PARBAT | 4G_TD_PARBAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574309 | 2021-10-28 | P/FVC/MDS/1065872/2021 | 2021-11-16 | ST202110573056 | 2021-10-27 | P/FVC/MDS/1065747/2021 | 2021-11-16 |  |  |  |  | ST202110572585 | 2021-10-27 | P/FBW/MDS/1067925/2021 | 2021-12-08
845 | KEERIP | KEERIP |  |  |  | ROTN | ATC | TN/SA/AT/22865 |  |  | On Air | 2021-11-24 | KEERIP | 4G_FD900_KEERIP | 4G_FD2100_KEERIP | 4G_TD_KEERIP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610543 | 2021-12-10 | P/FVC/MDS/1069110/2021 | 2021-12-17 | ST202112604664 | 2021-12-07 | P/FVC/MDS/1068762/2021 | 2021-12-15 |  |  |  |  | ST202112608852 | 2021-12-09 | P/FBW/MDS/1068865/2021 | 2021-12-15
846 | VAZHAP | VAZHAP |  |  |  | ROTN | Summit | I-TN-VLPD-ENB-9036 | SR-TN000599 |  | On Air | 2021-11-24 | VAZHAP | 4G_FD900_VAZHAP | 4G_FD2100_VAZHAP | 4G_TD_VAZHAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574373 | 2021-10-28 | P/FVC/MDS/1065895/2021 | 2021-11-16 | ST202110573145 | 2021-10-27 | P/FVC/MDS/1065749/2021 | 2021-11-16 |  |  |  |  | ST202110572587 | 2021-10-27 | P/FBW/MDS/1067927/2021 | 2021-12-08
847 | TAILAN | TAILAN |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-9058 | SR-TN000613 |  | On Air | 2021-11-24 | TAILAN | 4G_FD900_TAILAN | 4G_FD2100_TAILAN | 4G_TD_TAILAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574374 | 2021-10-28 | P/FVC/MDS/1065896/2021 | 2021-11-16 | ST202110573146 | 2021-10-27 | P/FVC/MDS/1065750/2021 | 2021-11-16 |  |  |  |  | ST202110572588 | 2021-10-27 | P/FBW/MDS/1067928/2021 | 2021-12-08
848 | KANNAN | KANNAN |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-0179 | SR-TN000605 |  | On Air | 2021-11-24 | KANNAN | 4G_FD900_KANNAN | 4G_FD2100_KANNAN | 4G_TD_KANNAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574375 | 2021-10-28 | P/FVC/MDS/1065897/2021 | 2021-11-16 | ST202110573147 | 2021-10-27 | P/FVC/MDS/1065751/2021 | 2021-11-16 |  |  |  |  | ST202110572589 | 2021-10-27 | P/FBW/MDS/1067929/2021 | 2021-12-08
849 | CHETTI | CHETTI |  |  |  | ROTN | Summit | I-TN-YRCD-ENB-9019 | SR-TN000608 |  | On Air | 2021-11-24 | CHETTI | 4G_FD900_CHETTI | 4G_FD2100_CHETTI | 4G_TD_CHETTI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574376 | 2021-10-28 | P/FVC/MDS/1065898/2021 | 2021-11-16 | ST202110573148 | 2021-10-27 | P/FVC/MDS/1065752/2021 | 2021-11-16 |  |  |  |  | ST202110572590 | 2021-10-27 | P/FBW/MDS/1067930/2021 | 2021-12-08
850 | MPALAT | MPALAT |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-0374 | SR-TN000601 |  | On Air | 2021-11-24 | MPALAT | 4G_FD900_MPALAT | 4G_FD2100_MPALAT | 4G_TD_MPALAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574377 | 2021-10-28 | P/FVC/MDS/1065899/2021 | 2021-11-16 | ST202110573149 | 2021-10-27 | P/FVC/MDS/1065753/2021 | 2021-11-16 |  |  |  |  | ST202110572591 | 2021-10-27 | P/FBW/MDS/1067931/2021 | 2021-12-08
851 | MITTAP | MITTAP |  |  |  | ROTN | ATC | TN/SA/AT/22867 |  |  | On Air | 2021-11-24 | MITTAP | 4G_FD900_MITTAP | 4G_FD2100_MITTAP | 4G_TD_MITTAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610604 | 2021-12-10 | P/FVC/MDS/1069117/2021 | 2021-12-17 | ST202112604719 | 2021-12-07 | P/FVC/MDS/1068769/2021 | 2021-12-15 |  |  |  |  | ST202112609082 | 2021-12-09 | P/FBW/MDS/1068873/2021 | 2021-12-15
852 | PULYAM | PULYAM |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-9064 | SR-TN000616 |  | On Air | 2021-11-24 | PULYAM | 4G_FD900_PULYAM | 4G_FD2100_PULYAM | 4G_TD_PULYAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574378 | 2021-10-28 | P/FVC/MDS/1065900/2021 | 2021-11-16 | ST202110573150 | 2021-10-27 | P/FVC/MDS/1065754/2021 | 2021-11-16 |  |  |  |  | ST202110572592 | 2021-10-27 | P/FBW/MDS/1067932/2021 | 2021-12-08
853 | MANKAR | MANKAR |  |  |  | ROTN | Summit | I-TN-SLEM-ENB-9073 | SR-TN000624 |  | On Air | 2021-11-24 | MANKAR | 4G_FD900_MANKAR | 4G_FD2100_MANKAR | 4G_TD_MANKAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574380 | 2021-10-28 | P/FVC/MDS/1065902/2021 | 2021-11-16 | ST202110573152 | 2021-10-27 | P/FVC/MDS/1065757/2021 | 2021-11-16 |  |  |  |  | ST202110572594 | 2021-10-27 | P/FBW/MDS/1067934/2021 | 2021-12-08
854 | SANTAN | SANTAN |  |  |  | ROTN | ATC | TN/SA/AT/22869 |  |  | On Air | 2021-11-24 | SANTAN | 4G_FD900_SANTAN | 4G_FD2100_SANTAN | 4G_TD_SANTAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610592 | 2021-12-10 | P/FVC/MDS/1069116/2021 | 2021-12-17 | ST202112604715 | 2021-12-07 | P/FVC/MDS/1068768/2021 | 2021-12-15 |  |  |  |  | ST202112609081 | 2021-12-09 | P/FBW/MDS/1068872/2021 | 2021-12-15
855 | GONURF | GONURF |  |  |  | ROTN | ATC | TN/SA/AT/22870 |  |  | On Air | 2021-11-24 | GONURF | 4G_FD900_GONURF | 4G_FD2100_GONURF | 4G_TD_GONURF | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610590 | 2021-12-10 | P/FVC/MDS/1069115/2021 | 2021-12-17 | ST202112604714 | 2021-12-07 | P/FVC/MDS/1068767/2021 | 2021-12-15 |  |  |  |  | ST202112609080 | 2021-12-09 | P/FBW/MDS/1068871/2021 | 2021-12-15
856 | KALINI | KALINI |  |  |  | ROTN | Indus | IN-1245265 | R/RES-507309 |  | On Air | 2021-11-24 | KALINI | 4G_FD900_KALINI | 4G_FD2100_KALINI | 4G_TD_KALINI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592512 | 2021-11-17 | P/FVC/MDS/1066617/2021 | 2021-11-26 | ST202111592944 | 2021-11-17 | P/FVC/MDS/1066594/2021 | 2021-11-26 |  |  |  |  | ST202111595303 | 2021-11-19 | P/FBW/MDS/1067040/2021 | 2021-12-01
857 | ATHRAM | ATHRAM |  |  |  | ROTN | ATC | TN/SA/AT/22871 |  |  | On Air | 2021-11-25 | ATHRAM | 4G_FD900_ATHRAM | 4G_FD2100_ATHRAM | 4G_TD_ATHRAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610638 | 2021-12-10 | P/FVC/MDS/1069122/2021 | 2021-12-17 | ST202112604816 | 2021-12-07 | P/FVC/MDS/1068809/2021 | 2021-12-15 |  |  |  |  | ST202112609146 | 2021-12-09 | P/FBW/MDS/1068773/2021 | 2021-12-15
858 | PARAKA | PARAKA |  |  |  | ROTN | ATC | TN/SA/AT/22873 |  |  | On Air | 2021-11-25 | PARAKA | 4G_FD900_PARAKA | 4G_FD2100_PARAKA | 4G_TD_PARAKA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610812 | 2021-12-10 | P/FVC/MDS/1069071/2021 | 2021-12-17 | ST202112604861 | 2021-12-07 | P/FVC/MDS/1068818/2021 | 2021-12-15 |  |  |  |  | ST202112609182 | 2021-12-09 | P/FBW/MDS/1068782/2021 | 2021-12-15
859 | REDPAT | REDPAT |  |  |  | ROTN | Summit | I-TN-MTTR-ENB-9080 | SR-TN000611 |  | On Air | 2021-11-24 | REDPAT | 4G_FD900_REDPAT | 4G_FD2100_REDPAT | 4G_TD_REDPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574381 | 2021-10-28 | P/FVC/MDS/1065903/2021 | 2021-11-16 | ST202110573153 | 2021-10-27 | P/FVC/MDS/1065758/2021 | 2021-11-16 |  |  |  |  | ST202110576206 | 2021-10-29 | P/FBW/MDS/1067954/2021 | 2021-12-08
860 | ALAGUS | ALAGUS |  |  |  | ROTN | Summit | I-TN-OMLR-ENB-9008 | SR-TN000606 |  | On Air | 2021-11-24 | ALAGUS | 4G_FD900_ALAGUS | 4G_FD2100_ALAGUS | 4G_TD_ALAGUS | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579637 | 2021-11-01 | P/FVC/MDS/1065935/2021 | 2021-11-16 | ST202110578527 | 2021-10-31 | P/FVC/MDS/1065925/2021 | 2021-11-16 |  |  |  |  | ST202110578496 | 2021-10-30 | P/FBW/MDS/1067965/2021 | 2021-12-08
861 | THANIP | THANIP |  |  |  | ROTN | Summit | I-TN-TAUH-ENB-9002 | SR-TN000617 |  | On Air | 2021-11-24 | THANIP | 4G_FD900_THANIP | 4G_FD2100_THANIP | 4G_TD_THANIP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579638 | 2021-11-01 | P/FVC/MDS/1065936/2021 | 2021-11-16 | ST202110578528 | 2021-10-31 | P/FVC/MDS/1065926/2021 | 2021-11-16 |  |  |  |  | ST202110578497 | 2021-10-30 | P/FBW/MDS/1067966/2021 | 2021-12-08
862 | AMMAPA | AMMAPA |  |  |  | ROTN | Summit | I-TN-ARNI-ENB-9044 | SR-TN000625 |  | On Air | 2021-11-24 | AMMAPA | 4G_FD900_AMMAPA | 4G_FD2100_AMMAPA | 4G_TD_AMMAPA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579639 | 2021-11-01 | P/FVC/MDS/1065937/2021 | 2021-11-16 | ST202110578529 | 2021-10-31 | P/FVC/MDS/1065927/2021 | 2021-11-16 |  |  |  |  | ST202110578498 | 2021-10-30 | P/FBW/MDS/1067967/2021 | 2021-12-08
863 | VELPAD | VELPAD |  |  |  | ROTN | ATC | TN/TV/AT/22876 |  |  | On Air | 2021-11-24 | VELPAD | 4G_FD900_VELPAD | 4G_FD2100_VELPAD | 4G_TD_VELPAD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592513 | 2021-11-17 | P/FVC/MDS/1066618/2021 | 2021-11-26 | ST202111592945 | 2021-11-17 | P/FVC/MDS/1066595/2021 | 2021-11-26 |  |  |  |  | ST202111595304 | 2021-11-19 | P/FBW/MDS/1067041/2021 | 2021-12-01
864 | MUNUGA | MUNUGA |  |  |  | ROTN | Summit | I-TN-TRVT-ENB-9057 | SR-TN000604 |  | On Air | 2021-11-24 | MUNUGA | 4G_FD900_MUNUGA | 4G_FD2100_MUNUGA | 4G_TD_MUNUGA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579640 | 2021-11-01 | P/FVC/MDS/1065938/2021 | 2021-11-16 | ST202110578530 | 2021-10-31 | P/FVC/MDS/1065928/2021 | 2021-11-16 |  |  |  |  | ST202110578499 | 2021-10-30 | P/FBW/MDS/1067968/2021 | 2021-12-08
865 | VADLUP | VADLUP |  |  |  | ROTN | Summit | I-TN-TRVT-ENB-9080 | SR-TN000626 |  | On Air | 2021-11-24 | VADLUP | 4G_FD900_VADLUP | 4G_FD2100_VADLUP | 4G_TD_VADLUP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579642 | 2021-11-01 | P/FVC/MDS/1065940/2021 | 2021-11-16 | ST202110578532 | 2021-10-31 | P/FVC/MDS/1065930/2021 | 2021-11-16 |  |  |  |  | ST202110578501 | 2021-10-30 | P/FBW/MDS/1067970/2021 | 2021-12-08
866 | NOCHCH | NOCHCH |  |  |  | ROTN | Summit | I-TN-TVML-ENB-9103 | SR-TN000609 |  | On Air | 2021-11-24 | NOCHCH | 4G_FD900_NOCHCH | 4G_FD2100_NOCHCH | 4G_TD_NOCHCH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579644 | 2021-11-01 | P/FVC/MDS/1065942/2021 | 2021-11-16 | ST202110578534 | 2021-10-31 | P/FVC/MDS/1065932/2021 | 2021-11-16 |  |  |  |  | ST202110578503 | 2021-10-30 | P/FBW/MDS/1067972/2021 | 2021-12-08
867 | KARGIR | KARGIR |  |  |  | ROTN | Summit | I-TN-VLLR-ENB-9052 | SR-TN000618 |  | On Air | 2021-11-25 | KARGIR | 4G_FD900_KARGIR | 4G_FD2100_KARGIR | 4G_TD_KARGIR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579645 | 2021-11-01 | P/FVC/MDS/1065943/2021 | 2021-11-16 | ST202110578535 | 2021-10-31 | P/FVC/MDS/1065933/2021 | 2021-11-16 |  |  |  |  | ST202110578504 | 2021-10-30 | P/FBW/MDS/1067973/2021 | 2021-12-08
868 | MUDIAM | MUDIAM |  |  |  | ROTN | ATC | TN/VE/AT/22878 |  |  | On Air | 2021-11-25 | MUDIAM | 4G_FD900_MUDIAM | 4G_FD2100_MUDIAM | 4G_TD_MUDIAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610624 | 2021-12-10 | P/FVC/MDS/1069121/2021 | 2021-12-17 | ST202112604813 | 2021-12-07 | P/FVC/MDS/1068808/2021 | 2021-12-15 |  |  |  |  | ST202112609101 | 2021-12-09 | P/FBW/MDS/1068877/2021 | 2021-12-15
869 | KATTUP | KATTUP |  |  |  | ROTN | Summit | I-TN-VLLR-ENB-9066 | SR-TN000619 |  | On Air | 2021-11-25 | KATTUP | 4G_FD900_KATTUP | 4G_FD2100_KATTUP | 4G_TD_KATTUP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579646 | 2021-11-01 | P/FVC/MDS/1065944/2021 | 2021-11-16 | ST202110578536 | 2021-10-31 | P/FVC/MDS/1065934/2021 | 2021-11-16 |  |  |  |  | ST202110578505 | 2021-10-30 | P/FBW/MDS/1067974/2021 | 2021-12-08
870 | VADACH | VADACH |  |  |  | ROTN | ATC | TN/VE/AT/22881 |  |  | On Air | 2021-11-25 | VADACH | 4G_FD900_VADACH | 4G_FD2100_VADACH | 4G_TD_VADACH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610659 | 2021-12-10 | P/FVC/MDS/1069125/2021 | 2021-12-17 | ST202112604835 | 2021-12-07 | P/FVC/MDS/1068812/2021 | 2021-12-15 |  |  |  |  | ST202112609162 | 2021-12-09 | P/FBW/MDS/1068776/2021 | 2021-12-15
871 | KANAVA | KANAVA |  |  |  | ROTN | Summit | I-TN-VMBD-ENB-9047 | SR-TN000621 |  | On Air | 2021-11-25 | KANAVA | 4G_FD900_KANAVA | 4G_FD2100_KANAVA | 4G_TD_KANAVA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579664 | 2021-11-01 | P/FVC/MDS/1065945/2021 | 2021-11-16 | ST202110578537 | 2021-10-31 | P/FVC/MDS/1067980/2021 | 2021-12-08 |  |  |  |  | ST202110578516 | 2021-10-30 | P/FBW/MDS/1067975/2021 | 2021-12-08
872 | THANDA | THANDA |  |  |  | ROTN | ATC | TN/VE/AT/22883 |  |  | On Air | 2021-11-25 | THANDA | 4G_FD900_THANDA | 4G_FD2100_THANDA | 4G_TD_THANDA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610651 | 2021-12-10 | P/FVC/MDS/1069124/2021 | 2021-12-17 | ST202112604828 | 2021-12-07 | P/FVC/MDS/1068811/2021 | 2021-12-15 |  |  |  |  | ST202112609148 | 2021-12-09 | P/FBW/MDS/1068775/2021 | 2021-12-15
873 | VAZHA1 | VAZHA1 |  |  |  | ROTN | ATC | TN/SA/AT/22884 |  |  | On Air | 2021-11-24 | VAZHA1 | 4G_FD900_VAZHA1 | 4G_FD2100_VAZHA1 | 4G_TD_VAZHA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610544 | 2021-12-10 | P/FVC/MDS/1069111/2021 | 2021-12-17 | ST202112604666 | 2021-12-07 | P/FVC/MDS/1068763/2021 | 2021-12-15 |  |  |  |  | ST202112608853 | 2021-12-09 | P/FBW/MDS/1068866/2021 | 2021-12-15
874 | KUTHAN | KUTHAN |  |  |  | ROTN | Summit | I-TN-TRVT-ENB-9096 | SR-TN000622 |  | On Air | 2021-11-24 | KUTHAN | 4G_FD900_KUTHAN | 4G_FD2100_KUTHAN | 4G_TD_KUTHAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111579667 | 2021-11-01 | P/FVC/MDS/1065948/2021 | 2021-11-16 | ST202110578540 | 2021-10-31 | P/FVC/MDS/1067983/2021 | 2021-12-08 |  |  |  |  | ST202110578519 | 2021-10-30 | P/FBW/MDS/1067978/2021 | 2021-12-08
875 | CHINAV | CHINAV |  |  |  | ROTN | ATC | TN/VE/AT/22888 |  |  | On Air | 2021-11-25 | CHINAV | 4G_FD900_CHINAV | 4G_FD2100_CHINAV | 4G_TD_CHINAV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610811 | 2021-12-10 | P/FVC/MDS/1069070/2021 | 2021-12-17 | ST202112604853 | 2021-12-07 | P/FVC/MDS/1068817/2021 | 2021-12-15 |  |  |  |  | ST202112609174 | 2021-12-09 | P/FBW/MDS/1068781/2021 | 2021-12-15
876 | KURUTI | KURUTI |  |  |  | ROTN | Summit | I-TN-TRPR-ENB-9093 | SR-TN000633 |  | On Air | 2021-11-24 | KURUTI | 4G_FD900_KURUTI | 4G_FD2100_KURUTI | 4G_TD_KURUTI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585516 | 2021-11-09 | P/FVC/MDS/1068140/2021 | 2021-12-08 | ST202111588029 | 2021-11-12 | P/FVC/MDS/1068170/2021 | 2021-12-08 |  |  |  |  | ST202111584849 | 2021-11-09 | P/FBW/MDS/1068082/2021 | 2021-12-08
877 | KANNAL | KANNAL |  |  |  | ROTN | Summit | I-TN-TRPR-ENB-9067 | SR-TN000650 |  | On Air | 2021-11-24 | KANNAL | 4G_FD900_KANNAL | 4G_FD2100_KANNAL | 4G_TD_KANNAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585519 | 2021-11-09 | P/FVC/MDS/1068142/2021 | 2021-12-08 | ST202111588030 | 2021-11-12 | P/FVC/MDS/1068171/2021 | 2021-12-08 |  |  |  |  | ST202111584858 | 2021-11-09 | P/FBW/MDS/1068084/2021 | 2021-12-08
878 | KALAR1 | KALAR1 |  |  |  | ROTN | Indus | IN-3071644 | R/NN-629699 |  | On Air | 2021-11-25 | KALAR1 | 4G_FD900_KALAR1 | 4G_FD2100_KALAR1 | 4G_TD_KALAR1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610660 | 2021-12-10 | P/FVC/MDS/1069126/2021 | 2021-12-17 | ST202112604840 | 2021-12-07 | P/FVC/MDS/1068813/2021 | 2021-12-15 |  |  |  |  | ST202112609163 | 2021-12-09 | P/FBW/MDS/1068777/2021 | 2021-12-15
879 | CHITHA | CHITHA |  |  |  | ROTN | Summit | I-TN-WLLJ-ENB-9069 | SR-TN000632 |  | On Air | 2021-11-25 | CHITHA | 4G_FD900_CHITHA | 4G_FD2100_CHITHA | 4G_TD_CHITHA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610677 | 2021-12-10 | P/FVC/MDS/1069127/2021 | 2021-12-17 | ST202112604843 | 2021-12-07 | P/FVC/MDS/1068814/2021 | 2021-12-15 |  |  |  |  | ST202112609164 | 2021-12-09 | P/FBW/MDS/1068778/2021 | 2021-12-15
880 | KADRAP | KADRAP |  |  |  | ROTN | Summit | I-TN-HSUR-ENB-9072 | SR-TN000655 |  | On Air | 2021-11-24 | KADRAP | 4G_FD900_KADRAP | 4G_FD2100_KADRAP | 4G_TD_KADRAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610605 | 2021-12-10 | P/FVC/MDS/1069118/2021 | 2021-12-17 | ST202112604720 | 2021-12-07 | P/FVC/MDS/1068770/2021 | 2021-12-15 |  |  |  |  | ST202112609092 | 2021-12-09 | P/FBW/MDS/1068874/2021 | 2021-12-15
881 | NAGOND | NAGOND |  |  |  | ROTN | Summit | I-TN-MGRI-ENB-9003 | SR-TN000636 |  | On Air | 2021-11-24 | NAGOND | 4G_FD900_NAGOND | 4G_FD2100_NAGOND | 4G_TD_NAGOND | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610606 | 2021-12-10 | P/FVC/MDS/1069119/2021 | 2021-12-17 | ST202112604727 | 2021-12-07 | P/FVC/MDS/1068771/2021 | 2021-12-15 |  |  |  |  | ST202112609093 | 2021-12-09 | P/FBW/MDS/1068875/2021 | 2021-12-15
882 | MARTHA | MARTHA |  |  |  | ROTN | Summit | I-TN-HSUR-ENB-9092 | SR-TN000644 |  | On Air | 2021-11-24 | MARTHA | 4G_FD900_MARTHA | 4G_FD2100_MARTHA | 4G_TD_MARTHA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592503 | 2021-11-17 | P/FVC/MDS/1066608/2021 | 2021-11-26 | ST202111592674 | 2021-11-17 | P/FVC/MDS/1066563/2021 | 2021-11-24 |  |  |  |  | ST202111592276 | 2021-11-16 | P/FBW/MDS/1066571/2021 | 2021-11-25
883 | NALLAR | NALLAR |  |  |  | ROTN | Summit | I-TN-HSUR-ENB-9114 | SR-TN000648 |  | On Air | 2021-11-24 | NALLAR | 4G_FD900_NALLAR | 4G_FD2100_NALLAR | 4G_TD_NALLAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592504 | 2021-11-17 | P/FVC/MDS/1066609/2021 | 2021-11-26 | ST202111592675 | 2021-11-17 | P/FVC/MDS/1066564/2021 | 2021-11-24 |  |  |  |  | ST202111592277 | 2021-11-16 | P/FBW/MDS/1066572/2021 | 2021-11-25
884 | CHAPAD | CHAPAD |  |  |  | ROTN | Indus | IN-1113033 | R/RES-507382 |  | On Air | 2021-11-24 | CHAPAD | 4G_FD900_CHAPAD | 4G_FD2100_CHAPAD | 4G_TD_CHAPAD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592511 | 2021-11-17 | P/FVC/MDS/1066616/2021 | 2021-11-26 | ST202111592946 | 2021-11-17 | P/FVC/MDS/1066596/2021 | 2021-11-26 |  |  |  |  | ST202111595302 | 2021-11-19 | P/FBW/MDS/1067039/2021 | 2021-12-01
885 | KOPPAG | KOPPAG |  |  |  | ROTN | Summit | I-TN-DNKT-ENB-9095 | SR-TN000641 |  | On Air | 2021-11-24 | KOPPAG | 4G_FD900_KOPPAG | 4G_FD2100_KOPPAG | 4G_TD_KOPPAG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592505 | 2021-11-17 | P/FVC/MDS/1066610/2021 | 2021-11-26 | ST202111592676 | 2021-11-17 | P/FVC/MDS/1066565/2021 | 2021-11-24 |  |  |  |  | ST202111592278 | 2021-11-16 | P/FBW/MDS/1066573/2021 | 2021-11-25
886 | SUNDEK | SUNDEK |  |  |  | ROTN | Summit | I-TN-PBNJ-ENB-9004 | SR-TN000634 |  | On Air | 2021-11-24 | SUNDEK | 4G_FD900_SUNDEK | 4G_FD2100_SUNDEK | 4G_TD_SUNDEK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111586175 | 2021-11-10 | P/FVC/MDS/1068156/2021 | 2021-12-08 | ST202111588032 | 2021-11-12 | P/FVC/MDS/1068173/2021 | 2021-12-08 |  |  |  |  | ST202111588146 | 2021-11-12 | P/FBW/MDS/1068191/2021 | 2021-12-08
887 | AVATHA | AVATHA |  |  |  | ROTN | Summit | I-TN-PBNJ-ENB-9005 | SR-TN000631 |  | On Air | 2021-11-24 | AVATHA | 4G_FD900_AVATHA | 4G_FD2100_AVATHA | 4G_TD_AVATHA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111586176 | 2021-11-10 | P/FVC/MDS/1068157/2021 | 2021-12-08 | ST202111588033 | 2021-11-12 | P/FVC/MDS/1068174/2021 | 2021-12-08 |  |  |  |  | ST202111588147 | 2021-11-12 | P/FBW/MDS/1068192/2021 | 2021-12-08
888 | GOLLAP | GOLLAP |  |  |  | ROTN | Summit | I-TN-KGRI-ENB-9071 | SR-TN000653 |  | On Air | 2021-11-24 | GOLLAP | 4G_FD900_GOLLAP | 4G_FD2100_GOLLAP | 4G_TD_GOLLAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587757 | 2021-11-12 | P/FVC/MDS/1068165/2021 | 2021-12-08 | ST202111588041 | 2021-11-12 | P/FVC/MDS/1068182/2021 | 2021-12-08 |  |  |  |  | ST202111588425 | 2021-11-12 | P/FBW/MDS/1068200/2021 | 2021-12-08
889 | ILLUPP | ILLUPP |  |  |  | ROTN | Summit | I-TN-UTHN-ENB-9041 | SR-TN000651 |  | On Air | 2021-11-24 | ILLUPP | 4G_FD900_ILLUPP | 4G_FD2100_ILLUPP | 4G_TD_ILLUPP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587759 | 2021-11-12 | P/FVC/MDS/1068167/2021 | 2021-12-08 | ST202111588043 | 2021-11-12 | P/FVC/MDS/1068184/2021 | 2021-12-08 |  |  |  |  | ST202111588427 | 2021-11-12 | P/FBW/MDS/1068202/2021 | 2021-12-08
890 | TORNAM | TORNAM |  |  |  | ROTN | Summit | I-TN-UTHN-ENB-9066 | SR-TN000638 |  | On Air | 2021-11-24 | TORNAM | 4G_FD900_TORNAM | 4G_FD2100_TORNAM | 4G_TD_TORNAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587766 | 2021-11-12 | P/FVC/MDS/1068168/2021 | 2021-12-08 | ST202111588044 | 2021-11-12 | P/FVC/MDS/1068185/2021 | 2021-12-08 |  |  |  |  | ST202111588428 | 2021-11-12 | P/FBW/MDS/1068203/2021 | 2021-12-08
891 | GENDIG | GENDIG |  |  |  | ROTN | Summit | I-TN-PCMP-ENB-9036 | SR-TN000640 |  | On Air | 2021-11-24 | GENDIG | 4G_FD900_GENDIG | 4G_FD2100_GENDIG | 4G_TD_GENDIG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111586237 | 2021-11-10 | P/FVC/MDS/1068159/2021 | 2021-12-08 | ST202111588035 | 2021-11-12 | P/FVC/MDS/1068176/2021 | 2021-12-08 |  |  |  |  | ST202111588149 | 2021-11-12 | P/FBW/MDS/1068194/2021 | 2021-12-08
892 | VADAGA | VADAGA |  |  |  | ROTN | Summit | I-TN-PCMP-ENB-9038 | SR-TN000654 |  | On Air | 2021-11-24 | VADAGA | 4G_FD900_VADAGA | 4G_FD2100_VADAGA | 4G_TD_VADAGA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592507 | 2021-11-17 | P/FVC/MDS/1066612/2021 | 2021-11-26 | ST202111592678 | 2021-11-17 | P/FVC/MDS/1066567/2021 | 2021-11-24 |  |  |  |  | ST202111592280 | 2021-11-16 | P/FBW/MDS/1066575/2021 | 2021-11-25
893 | PCHPL7 | PCHPL7 |  |  |  | ROTN | Summit | I-TN-PCMP-ENB-9035 | SR-TN000649 |  | On Air | 2021-11-24 | PCHPL7 | 4G_FD900_PCHPL7 | 4G_FD2100_PCHPL7 | 4G_TD_PCHPL7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592508 | 2021-11-17 | P/FVC/MDS/1066613/2021 | 2021-11-26 | ST202111592941 | 2021-11-17 | P/FVC/MDS/1066591/2021 | 2021-11-26 |  |  |  |  | ST202111592281 | 2021-11-16 | P/FBW/MDS/1066576/2021 | 2021-11-25
894 | KATHIN | KATHIN |  |  |  | ROTN | Summit | I-TN-KGRI-ENB-9105 | SR-TN000645 |  | On Air | 2021-11-24 | KATHIN | 4G_FD900_KATHIN | 4G_FD2100_KATHIN | 4G_TD_KATHIN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111587758 | 2021-11-12 | P/FVC/MDS/1068166/2021 | 2021-12-08 | ST202111588042 | 2021-11-12 | P/FVC/MDS/1068183/2021 | 2021-12-08 |  |  |  |  | ST202111588426 | 2021-11-12 | P/FBW/MDS/1068201/2021 | 2021-12-08
895 | NANJAN | NANJAN |  |  |  | ROTN | Summit | I-TN-HSUR-ENB-9093 | SR-TN000646 |  | On Air | 2021-11-24 | NANJAN | 4G_FD900_NANJAN | 4G_FD2100_NANJAN | 4G_TD_NANJAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610573 | 2021-12-10 | P/FVC/MDS/1069114/2021 | 2021-12-17 | ST202112604676 | 2021-12-07 | P/FVC/MDS/1068766/2021 | 2021-12-15 |  |  |  |  | ST202112609074 | 2021-12-09 | P/FBW/MDS/1068870/2021 | 2021-12-15
896 | MDPM19 | MDPM19 |  |  |  | ROTN | Indus | IN-3058603 | R/NN-633231 |  |  | 2021-10-26 | MDPM19 | 4G_FD900_MDPM19 | 4G_FD2100_MDPM19 | 4G_TD_MDPM19 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202110574105 | 2021-10-28 | P/FVC/MDS/1065844/2021 | 2021-11-16 | ST202110573015 | 2021-10-27 | P/FVC/MDS/1065714/2021 | 2021-11-16 | ST202110574056 | 2021-10-28 | P/FVC/MDS/1065809/2021 | 2021-11-16 | ST202110572484 | 2021-10-27 | P/FBW/MDS/1067895/2021 | 2021-12-08
897 | PMKD26 | PMKD26 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2021-11-27 | PMKD26 | 4G_FD900_PMKD26 | 4G_FD2100_PMKD26 | 4G_TD_PMKD26 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610895 | 2021-12-10 | P/FVC/MDS/1069086/2021 | 2021-12-17 | ST202112604921 | 2021-12-07 | P/FVC/MDS/1068832/2021 | 2021-12-15 |  |  |  |  | ST202112609419 | 2021-12-10 | P/FBW/MDS/1068796/2021 | 2021-12-15
898 | VESTAS | VESTAS |  |  |  | ROTN | Airtel | - | - |  | On Air | 2021-12-02 | VESTAS | 4G_FD900_VESTAS | 4G_FD2100_VESTAS | 4G_TD_VESTAS | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610924 | 2021-12-10 | P/FVC/MDS/1069094/2021 | 2021-12-17 | ST202112604964 | 2021-12-07 | P/FVC/MDS/1068839/2021 | 2021-12-15 | ST202210548783 | 2022-10-11 | P/FVC/MDS/1113943/2022 | 2022-10-21 | ST202112609895 | 2021-12-10 | P/FBW/MDS/1069060/2021 | 2021-12-17
899 | KAMMAM | KAMMAM |  |  |  | ROTN | Indus | IN-3071717 | R/NN-632702 |  | On Air | 2021-11-27 | KAMMAM | 4G_FD900_KAMMAM | 4G_FD2100_KAMMAM | 4G_TD_KAMMAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610894 | 2021-12-10 | P/FVC/MDS/1069085/2021 | 2021-12-17 | ST202112604913 | 2021-12-07 | P/FVC/MDS/1068831/2021 | 2021-12-15 |  |  |  |  | ST202112609418 | 2021-12-10 | P/FBW/MDS/1068795/2021 | 2021-12-15
900 | PRMHR3 | PRMHR3 |  |  |  | CHN | Airtel |  | R/NN-478793 |  |  | 2021-11-29 | PRMHR3 | 4G_FD900_PRMHR3 | 4G_FD2100_PRMHR3 | 4G_TD_PRMHR3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201014661 | 2022-01-20 | P/FVC/MDS/1072380/2022 | 2022-01-31 | ST202201014727 | 2022-01-20 | P/FVC/MDS/1072350/2022 | 2022-01-31 | ST202201014830 | 2022-01-20 | P/FVC/MDS/1072402/2022 | 2022-01-31 | ST202201014786 | 2022-01-20 | P/FBW/MDS/1072321/2022 | 2022-01-31
901 | KKD41 | KKD041 |  |  |  | ROTN | ATC | TN/SI/AT/22602 | T21TN05666 |  | SR |  | KKD041 | 4G_FD900_KKD041 | 4G_FD2100_KKD041 | 4G_TD_KKD041 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109533378 | 2021-09-25 | P/FVC/MDS/1062802/2021 | 2021-10-01 | ST202109531920 | 2021-09-24 | P/FVC/MDS/1062959/2021 | 2021-10-01 |  |  |  |  | ST202109533059 | 2021-09-25 | P/FVC/MDS/1062874/2021 | 2021-10-01
902 | KKD35 | KKD035 |  |  |  | ROTN | Indus | IN-1367062 | R/NN-352874 |  | SO | 2019-08-01 | KKD035 | 4G_FD900_KKD035 | 4G_FD2100_KKD035 | 4G_TD_KKD035 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362307 | 2021-06-25 | P/FVC/MDS/1049959/2021 | 2021-08-09 | 2020361063 | 2020-02-10 | P/FVC/MDS/6050807/2020 | 2020-05-19 |  |  |  |  | 2020361348 | 2020-02-10 | P/FBW/MDS/6051035/2020 | 2020-05-19
903 | ARAMPK | ARAMPK |  |  |  | ROTN | Airtel | - | T21TN08800 |  | SO | 2021-12-10 | ARAMPK | 4G_FD900_ARAMPK | 4G_FD2100_ARAMPK | 4G_TD_ARAMPK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610938 | 2021-12-10 | P/FVC/MDS/1069098/2021 | 2021-12-17 | ST202112627253 | 2021-12-24 | P/FVC/MDS/1070554/2022 | 2022-01-03 |  |  |  |  | ST202112609922 | 2021-12-10 | P/FBW/MDS/1069064/2021 | 2021-12-17
904 | MURAIY | MURAIY |  |  |  | ROTN | BSNL | 6725 | - |  | On Air | 2021-12-15 | MURAIY | 4G_FD900_MURAIY | 4G_FD2100_MURAIY | 4G_TD_MURAIY | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109527753 | 2021-09-22 | P/FVC/MDS/1062700/2021 | 2021-09-29 | ST202109526966 | 2021-09-21 | P/FVC/MDS/1062646/2021 | 2021-09-29 |  |  |  |  | ST202109528888 | 2021-09-23 | P/FBW/MDS/1062885/2021 | 2021-10-01
905 | THATAP | THATAP |  |  |  | ROTN | BSNL | 3167 |  |  | On Air | 2021-12-04 | THATAP | 4G_FD900_THATAP | 4G_FD2100_THATAP | 4G_TD_THATAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110572110 | 2021-10-27 | P/FVC/MDS/1065681/2021 | 2021-11-16 | ST202110568120 | 2021-10-22 | P/FVC/MDS/1065677/2021 | 2021-11-16 |  |  |  |  | ST202110576193 | 2021-10-29 | P/FBW/MDS/1067952/2021 | 2021-12-08
906 | CHIKAV | CHIKAV |  |  |  | ROTN | ATC | TN/SA/AT/22866 |  |  | On Air | 2021-12-10 | CHIKAV | 4G_FD900_CHIKAV | 4G_FD2100_CHIKAV | 4G_TD_CHIKAV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610901 | 2021-12-10 | P/FVC/MDS/1069087/2021 | 2021-12-17 | ST202112627252 | 2021-12-24 | P/FVC/MDS/1070553/2022 | 2022-01-03 |  |  |  |  | ST202112609933 | 2021-12-10 | P/FBW/MDS/1069068/2021 | 2021-12-17
907 | THUKAN | THUKAN |  |  |  | ROTN | ATC | TN/SA/AT/22874 |  |  | On Air | 2021-12-08 | THUKAN | 4G_FD900_THUKAN | 4G_FD2100_THUKAN | 4G_TD_THUKAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623316 | 2021-12-21 | P/FVC/MDS/1070044/2021 | 2021-12-29 | ST202112625886 | 2021-12-23 | P/FVC/MDS/1069718/2021 | 2021-12-28 |  |  |  |  | ST202112616589 | 2021-12-15 | P/FBW/MDS/1069563/2021 | 2021-12-22
908 | ROYAND | ROYAND |  |  |  | ROTN | Indus | IN-1076782 | R/RES-507783 |  | On Air | 2021-12-04 | ROYAND | 4G_FD900_ROYAND | 4G_FD2100_ROYAND | 4G_TD_ROYAND | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610871 | 2021-12-10 | P/FVC/MDS/1069077/2021 | 2021-12-17 | ST202112604884 | 2021-12-07 | P/FVC/MDS/1068823/2021 | 2021-12-15 |  |  |  |  | ST202112609190 | 2021-12-09 | P/FBW/MDS/1068787/2021 | 2021-12-15
909 | THARVA | THARVA |  |  |  | ROTN | ATC | TN/VE/AT/22879 |  |  | On Air | 2021-12-10 | THARVA | 4G_FD900_THARVA | 4G_FD2100_THARVA | 4G_TD_THARVA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610932 | 2021-12-10 | P/FVC/MDS/1069096/2021 | 2021-12-17 | ST202201003459 | 2022-01-06 | P/FVC/MDS/1071099/2022 | 2022-01-10 | ST202201003474 | 2022-01-06 | P/FVC/MDS/1071119/2022 | 2022-01-10 | ST202112609913 | 2021-12-10 | P/FBW/MDS/1069063/2021 | 2021-12-17
910 | SEVUR2 | SEVUR2 |  |  |  | ROTN | CNIL | TAM/GBT/K/29099 | - |  |  | 2021-12-08 | SEVUR2 | 4G_FD900_SEVUR2 | 4G_FD2100_SEVUR2 | 4G_TD_SEVUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202112623418 | 2021-12-21 | P/FVC/MDS/1070049/2021 | 2021-12-29 | ST202112625900 | 2021-12-23 | P/FVC/MDS/1069723/2021 | 2021-12-28 | ST202201003484 | 2022-01-06 | P/FVC/MDS/1071124/2022 | 2022-01-10 | ST202112626677 | 2021-12-24 | P/FBW/MDS/1070157/2021 | 2021-12-29
911 | CUCOF2 | CUCOF2 |  |  |  | ROTN | TVI | - |  |  | On Air | 2021-12-22 | CUCOF2 | 4G_FD900_CUCOF2 | 4G_FD2100_CUCOF2 | 4G_TD_CUCOF2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112627230 | 2021-12-24 | P/FVC/MDS/1070565/2022 | 2022-01-03 | ST202112627244 | 2021-12-24 | P/FVC/MDS/1070545/2022 | 2022-01-03 |  |  |  |  | ST202112627254 | 2021-12-24 | P/FBW/MDS/1070555/2022 | 2022-01-03
912 | CHPT55 | CHPT55 |  |  |  | ROTN | Indus | IN-3074713 | R/NN-635431 |  | On Air | 2021-12-27 | CHPT55 | 4G_FD900_CHPT55 | 4G_FD2100_CHPT55 | 4G_TD_CHPT55 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631634 | 2021-12-30 | P/FVC/MDS/1070598/2022 | 2022-01-05 | ST202112631984 | 2021-12-30 | P/FVC/MDS/1070608/2022 | 2022-01-05 |  |  |  |  | ST202112632001 | 2021-12-30 | P/FBW/MDS/1070618/2022 | 2022-01-05
913 | CBE889 | CBE889 |  |  |  | ROTN | TVI | DATNCBE0326 |  |  | On Air | 2021-12-27 | CBE889 | 4G_FD900_CBE889 | 4G_FD2100_CBE889 | 4G_TD_CBE889 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610874 | 2021-12-10 | P/FVC/MDS/1069079/2021 | 2021-12-17 | ST202112604889 | 2021-12-07 | P/FVC/MDS/1068825/2021 | 2021-12-15 | ST202202054763 | 2022-02-25 | P/FVC/MDS/1075694/2022 | 2022-03-10 | ST202112609408 | 2021-12-10 | P/FBW/MDS/1068789/2021 | 2021-12-15
914 | MANDO3 | MANDO3 |  |  |  | ROTN | TVI | - | - |  | On Air | 2021-12-27 | MANDO3 | 4G_FD900_MANDO3 | 4G_FD2100_MANDO3 | 4G_TD_MANDO3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631633 | 2021-12-30 | P/FVC/MDS/1070597/2022 | 2022-01-05 | ST202112631983 | 2021-12-30 | P/FVC/MDS/1070607/2022 | 2022-01-05 | ST202210548134 | 2022-10-11 | P/FVC/MDS/1113910/2022 | 2022-10-21 | ST202112632000 | 2021-12-30 | P/FBW/MDS/1070617/2022 | 2022-01-05
915 | PUDUAM | PUDUAM |  |  |  | ROTN | Ascend | - | - |  | On Air | 2021-12-27 | PUDUAM | 4G_FD900_PUDUAM | 4G_FD2100_PUDUAM | 4G_TD_PUDUAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631637 | 2021-12-30 | P/FVC/MDS/1070599/2022 | 2022-01-05 | ST202112631988 | 2021-12-30 | P/FVC/MDS/1070609/2022 | 2022-01-05 | ST202210548549 | 2022-10-11 | P/FVC/MDS/1113928/2022 | 2022-10-21 | ST202112632004 | 2021-12-30 | P/FBW/MDS/1070619/2022 | 2022-01-05
916 | MUTHAK | MUTHAK |  |  |  | ROTN | Indus | IN-1126799 | R/RES-508398 |  | On Air | 2021-12-27 | MUTHAK | 4G_FD900_MUTHAK | 4G_FD2100_MUTHAK | 4G_TD_MUTHAK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631638 | 2021-12-30 | P/FVC/MDS/1070600/2022 | 2022-01-05 | ST202112631989 | 2021-12-30 | P/FVC/MDS/1070610/2022 | 2022-01-05 |  |  |  |  | ST202112632006 | 2021-12-30 | P/FBW/MDS/1070620/2022 | 2022-01-05
917 | KRISH1 | KRISH1 |  |  |  | ROTN | ATC | TN/SA/AT/22885 |  |  | On Air | 2021-12-22 | KRISH1 | 4G_FD900_KRISH1 | 4G_FD2100_KRISH1 | 4G_TD_KRISH1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112627232 | 2021-12-24 | P/FVC/MDS/1070567/2022 | 2022-01-03 | ST202112627246 | 2021-12-24 | P/FVC/MDS/1070547/2022 | 2022-01-03 |  |  |  |  | ST202112627256 | 2021-12-24 | P/FBW/MDS/1070557/2022 | 2022-01-03
918 | SEVANA | SEVANA |  |  |  | ROTN | ATC | TN/PU/AT/22893 |  |  | On Air | 2021-12-22 | SEVANA | 4G_FD900_SEVANA | 4G_FD2100_SEVANA | 4G_TD_SEVANA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623426 | 2021-12-21 | P/FVC/MDS/1070052/2021 | 2021-12-29 | ST202201003460 | 2022-01-06 | P/FVC/MDS/1071100/2022 | 2022-01-10 | ST202201003573 | 2022-01-06 | P/FVC/MDS/1071403/2022 | 2022-01-11 | ST202201003467 | 2022-01-06 | P/FBW/MDS/1071107/2022 | 2022-01-10
919 | KARAMB | KARAMB |  |  |  | ROTN | ATC | TN/TA/AT/22895 |  |  | On Air | 2021-12-22 | KARAMB | 4G_FD900_KARAMB | 4G_FD2100_KARAMB | 4G_TD_KARAMB | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112627237 | 2021-12-24 | P/FVC/MDS/1070571/2022 | 2022-01-03 | ST202112627250 | 2021-12-24 | P/FVC/MDS/1070551/2022 | 2022-01-03 |  |  |  |  | ST202112627260 | 2021-12-24 | P/FBW/MDS/1070561/2022 | 2022-01-03
920 | PARAVA | PARAVA |  |  |  | ROTN | ATC | TN/PU/AT/22896 |  |  | On Air | 2021-12-22 | PARAVA | 4G_FD900_PARAVA | 4G_FD2100_PARAVA | 4G_TD_PARAVA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056716 | 2022-02-27 | P/FVC/MDS/1076459/2022 | 2022-03-13 | ST202202055884 | 2022-02-26 | P/FVC/MDS/1075675/2022 | 2022-03-10 |  |  |  |  | ST202202056468 | 2022-02-26 | P/FBW/MDS/1075578/2022 | 2022-03-10
921 | NADUPA | NADUPA |  |  |  | ROTN | ATC | TN/PU/AT/22898 |  |  | On Air | 2021-12-22 | NADUPA | 4G_FD900_NADUPA | 4G_FD2100_NADUPA | 4G_TD_NADUPA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112627235 | 2021-12-24 | P/FVC/MDS/1070570/2022 | 2022-01-03 | ST202112627249 | 2021-12-24 | P/FVC/MDS/1070550/2022 | 2022-01-03 |  |  |  |  | ST202112627259 | 2021-12-24 | P/FBW/MDS/1070560/2022 | 2022-01-03
922 | VADAKA | VADAKA |  |  |  | ROTN | ATC | TN/PU/AT/22899 |  |  | On Air | 2021-12-22 | VADAKA | 4G_FD900_VADAKA | 4G_FD2100_VADAKA | 4G_TD_VADAKA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112627239 | 2021-12-24 | P/FVC/MDS/1070573/2022 | 2022-01-03 | ST202201003458 | 2022-01-06 | P/FVC/MDS/1071098/2022 | 2022-01-10 | ST202201003572 | 2022-01-06 | P/FVC/MDS/1071402/2022 | 2022-01-11 | ST202112627262 | 2021-12-24 | P/FBW/MDS/1070563/2022 | 2022-01-03
923 | ADANI1 | ADANI1 |  |  |  | CHN | Airtel |  |  |  | On air | 2021-12-28 | ADANI1 | 4G_FD900_ADANI1 | 4G_FD2100_ADANI1 | 4G_TD_ADANI1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202026308 | 2022-02-01 | P/FVC/MDS/1074466/2022 | 2022-02-22 | ST202202026310 | 2022-02-01 | P/FVC/MDS/1074411/2022 | 2022-02-22 |  |  |  |  | ST202202026315 | 2022-02-01 | P/FBW/MDS/1074351/2022 | 2022-02-22
924 | TRY360 | TRY360 | Tiruchirappalli |  |  | ROTN | TVI | - | - |  | SRB(Surrender) | 2021-12-29 | TRY360 | 4G_FD900_TRY360 | 4G_FD2100_TRY360 | 4G_TD_TRY360 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110567672 | 2021-10-22 | P/FVC/MDS/1066514/2021 | 2021-11-19 | ST202110568086 | 2021-10-22 | P/FVC/MDS/1065673/2021 | 2021-11-16 | ST202110573926 | 2021-10-28 | P/FVC/MDS/1065780/2021 | 2021-11-16 | ST202110563777 | 2021-10-19 | P/FVC/MDS/1065428/2021 | 2021-10-28
925 | AMARAV | AMARAV | Tiruppur |  |  | ROTN | Indus | IN-3020059 | R/NN-627443 |  | SR | 2021-12-29 | AMARAV | 4G_FD900_AMARAV | 4G_FD2100_AMARAV | 4G_TD_AMARAV | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000157 | 2022-01-02 | P/FVC/MDS/1070760/2022 | 2022-01-06 | ST202201000167 | 2022-01-02 | P/FVC/MDS/1070770/2022 | 2022-01-06 |  |  |  |  | ST202201000182 | 2022-01-02 | P/FBW/MDS/1070780/2022 | 2022-01-06
926 | THIRP1 | THIRP1 | Tiruvannamalai |  |  | ROTN | Indus | IN-1113709 | R/RES-508487 |  | On Air | 2021-12-29 | THIRP1 | 4G_FD900_THIRP1 | 4G_FD2100_THIRP1 | 4G_TD_THIRP1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497342 | 2021-08-30 | P/FVC/MDS/1060325/2021 | 2021-09-13 | ST202108494318 | 2021-08-27 | P/FVC/MDS/1060278/2021 | 2021-09-13 | ST202108493764 | 2021-08-27 | P/FVC/MDS/1060231/2021 | 2021-09-13 | ST202108493603 | 2021-08-27 | P/FBW/MDS/1060184/2021 | 2021-09-13
927 | OLAPAD | OLAPAD | Perambalur |  |  | ROTN | Indus | IN-3101473 | R/NN-638007 |  | On Air | 2021-12-29 | OLAPAD | 4G_FD900_OLAPAD | 4G_FD2100_OLAPAD | 4G_TD_OLAPAD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631646 | 2021-12-30 | P/FVC/MDS/1070604/2022 | 2022-01-05 | ST202112631995 | 2021-12-30 | P/FVC/MDS/1070614/2022 | 2022-01-05 |  |  |  |  | ST202112632011 | 2021-12-30 | P/FBW/MDS/1070624/2022 | 2022-01-05
928 | RENDAI | RENDAI | Vellore |  |  | ROTN | CNIL | TAM/GBT/1/35182 | - |  | SO | 2021-12-15 | RENDAI | 4G_FD900_RENDAI | 4G_FD2100_RENDAI | 4G_TD_RENDAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000149 | 2022-01-02 | P/FVC/MDS/1070752/2022 | 2022-01-06 | ST202201000164 | 2022-01-02 | P/FVC/MDS/1070767/2022 | 2022-01-06 |  |  |  |  | ST202201000179 | 2022-01-02 | P/FBW/MDS/1070777/2022 | 2022-01-06
929 | THIMA1 | THIMA1 | Vellore |  |  | ROTN | BSNL | 4622 | - |  | On Air | 2021-12-29 | THIMA1 | 4G_FD900_THIMA1 | 4G_FD2100_THIMA1 | 4G_TD_THIMA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592496 | 2021-11-17 | P/FVC/MDS/1066601/2021 | 2021-11-26 | ST202111588047 | 2021-11-12 | P/FVC/MDS/1068188/2021 | 2021-12-08 |  |  |  |  | ST202111588431 | 2021-11-12 | P/FBW/MDS/1068206/2021 | 2021-12-08
930 | BOMMIK | BOMMIK | Vellore |  |  | ROTN | ATC | TN/VE/AT/22892 | - |  | On Air | 2021-12-29 | BOMMIK | 4G_FD900_BOMMIK | 4G_FD2100_BOMMIK | 4G_TD_BOMMIK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631649 | 2021-12-30 | P/FVC/MDS/1070605/2022 | 2022-01-05 | ST202112631998 | 2021-12-30 | P/FVC/MDS/1070615/2022 | 2022-01-05 |  |  |  |  | ST202112632012 | 2021-12-30 | P/FBW/MDS/1070625/2022 | 2022-01-05
931 | PEDHAN | PEDHAN | Krishnagiri |  |  | ROTN | Indus | IN-3098454 | R/NN-637984 |  | On Air | 2021-12-29 | PEDHAN | 4G_FD900_PEDHAN | 4G_FD2100_PEDHAN | 4G_TD_PEDHAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631642 | 2021-12-30 | P/FVC/MDS/1070602/2022 | 2022-01-05 | ST202112631993 | 2021-12-30 | P/FVC/MDS/1070612/2022 | 2022-01-05 |  |  |  |  | ST202112632009 | 2021-12-30 | P/FBW/MDS/1070622/2022 | 2022-01-05
932 | TAILIH | TAILIH | Krishnagiri |  |  | ROTN | Indus | IN-3098466 | R/NN-637996 |  | On Air | 2021-12-29 | TAILIH | 4G_FD900_TAILIH | 4G_FD2100_TAILIH | 4G_TD_TAILIH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631645 | 2021-12-30 | P/FVC/MDS/1070603/2022 | 2022-01-05 | ST202112631994 | 2021-12-30 | P/FVC/MDS/1070613/2022 | 2022-01-05 |  |  |  |  | ST202112632010 | 2021-12-30 | P/FBW/MDS/1070623/2022 | 2022-01-05
933 | PADIYA | PADIYA | Tiruvannamalai |  |  | ROTN | Indus | IN-3101511 | R/NN-637979 |  | On Air | 2021-12-29 | PADIYA | 4G_FD900_PADIYA | 4G_FD2100_PADIYA | 4G_TD_PADIYA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112631641 | 2021-12-30 | P/FVC/MDS/1070601/2022 | 2022-01-05 | ST202112631990 | 2021-12-30 | P/FVC/MDS/1070611/2022 | 2022-01-05 |  |  |  |  | ST202112632007 | 2021-12-30 | P/FBW/MDS/1070621/2022 | 2022-01-05
934 | PALLAT | PALLAT | Pudukkottai |  |  | ROTN | ATC | TN/PU/AT/22894 | - |  | On Air | 2021-12-29 | PALLAT | 4G_FD900_PALLAT | 4G_FD2100_PALLAT | 4G_TD_PALLAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000156 | 2022-01-02 | P/FVC/MDS/1070759/2022 | 2022-01-06 | ST202201000171 | 2022-01-02 | P/FVC/MDS/1070774/2022 | 2022-01-06 |  |  |  |  | ST202201000186 | 2022-01-02 | P/FBW/MDS/1070784/2022 | 2022-01-06
935 | NSNP17 | NSNP17 |  |  |  | ROTN | Indus | IN-3096531 | R/RES-508702 |  |  | 2021-12-29 | NSNP17 | 4G_FD900_NSNP17 | 4G_FD2100_NSNP17 | 4G_TD_NSNP17 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201003442 | 2022-01-05 | P/FVC/MDS/1071087/2022 | 2022-01-10 | ST202201003456 | 2022-01-06 | P/FVC/MDS/1071096/2022 | 2022-01-10 | ST202201014843 | 2022-01-20 | P/FVC/MDS/1072411/2022 | 2022-01-31 | ST202201003465 | 2022-01-06 | P/FBW/MDS/1071105/2022 | 2022-01-10
936 | NANJAP | NANJAP |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-05 | NANJAP | 4G_FD900_NANJAP | 4G_FD2100_NANJAP | 4G_TD_NANJAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000147 | 2022-01-02 | P/FVC/MDS/1070750/2022 | 2022-01-06 | ST202201000162 | 2022-01-02 | P/FVC/MDS/1070765/2022 | 2022-01-06 |  |  |  |  | ST202201000177 | 2022-01-02 | P/FBW/MDS/1070775/2022 | 2022-01-06
937 | SENNIA | SENNIA |  |  |  | ROTN | ATC | TN/TA/AT/22900 | - |  | SO(Rural Hold) | 2022-01-05 | SENNIA | 4G_FD900_SENNIA | 4G_FD2100_SENNIA | 4G_TD_SENNIA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008787 | 2022-01-12 | P/FVC/MDS/1071723/2022 | 2022-01-20 | ST202201008643 | 2022-01-12 | P/FVC/MDS/1071623/2022 | 2022-01-20 |  |  |  |  | ST202201008803 | 2022-01-12 | P/FBW/MDS/1071538/2022 | 2022-01-20
938 | PMKD28 | PMKD28 |  |  |  | ROTN | Ascend | - | - |  | SR | 2022-01-08 | PMKD28 | 4G_FD900_PMKD28 | 4G_FD2100_PMKD28 | 4G_TD_PMKD28 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008750 | 2022-01-12 | P/FVC/MDS/1071701/2022 | 2022-01-20 | ST202201008647 | 2022-01-12 | P/FVC/MDS/1071626/2022 | 2022-01-20 |  |  |  |  | ST202201008807 | 2022-01-12 | P/FBW/MDS/1071541/2022 | 2022-01-20
939 | ARASA2 | ARASA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | ARASA2 | 4G_FD900_ARASA2 | 4G_FD2100_ARASA2 | 4G_TD_ARASA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008751 | 2022-01-12 | P/FVC/MDS/1071702/2022 | 2022-01-20 | ST202201008653 | 2022-01-12 | P/FVC/MDS/1071627/2022 | 2022-01-20 |  |  |  |  | ST202201008808 | 2022-01-12 | P/FBW/MDS/1071542/2022 | 2022-01-20
940 | KILKR2 | KILKR2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | KILKR2 | 4G_FD900_KILKR2 | 4G_FD2100_KILKR2 | 4G_TD_KILKR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008753 | 2022-01-12 | P/FVC/MDS/1071704/2022 | 2022-01-20 | ST202201008655 | 2022-01-12 | P/FVC/MDS/1071629/2022 | 2022-01-20 |  |  |  |  | ST202201008810 | 2022-01-12 | P/FBW/MDS/1071544/2022 | 2022-01-20
941 | GEMMA2 | GEMMA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | GEMMA2 | 4G_FD900_GEMMA2 | 4G_FD2100_GEMMA2 | 4G_TD_GEMMA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008757 | 2022-01-12 | P/FVC/MDS/1071705/2022 | 2022-01-20 | ST202201008659 | 2022-01-12 | P/FVC/MDS/1071630/2022 | 2022-01-20 |  |  |  |  | ST202201008933 | 2022-01-13 | P/FBW/MDS/1071545/2022 | 2022-01-20
942 | KUNIC2 | KUNIC2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | KUNIC2 | 4G_FD900_KUNIC2 | 4G_FD2100_KUNIC2 | 4G_TD_KUNIC2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008768 | 2022-01-12 | P/FVC/MDS/1071713/2022 | 2022-01-20 | ST202201008678 | 2022-01-12 | P/FVC/MDS/1071638/2022 | 2022-01-20 |  |  |  |  | ST202201008946 | 2022-01-13 | P/FBW/MDS/1071553/2022 | 2022-01-20
943 | GENAO2 | GENAO2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | GENAO2 | 4G_FD900_GENAO2 | 4G_FD2100_GENAO2 | 4G_TD_GENAO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008760 | 2022-01-12 | P/FVC/MDS/1071708/2022 | 2022-01-20 | ST202201008667 | 2022-01-12 | P/FVC/MDS/1071633/2022 | 2022-01-20 |  |  |  |  | ST202201008937 | 2022-01-13 | P/FBW/MDS/1071548/2022 | 2022-01-20
944 | AGAVA2 | AGAVA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | AGAVA2 | 4G_FD900_AGAVA2 | 4G_FD2100_AGAVA2 | 4G_TD_AGAVA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008764 | 2022-01-12 | P/FVC/MDS/1071711/2022 | 2022-01-20 | ST202201008674 | 2022-01-12 | P/FVC/MDS/1071636/2022 | 2022-01-20 |  |  |  |  | ST202201008943 | 2022-01-13 | P/FBW/MDS/1071551/2022 | 2022-01-20
945 | MAHEN2 | MAHEN2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | MAHEN2 | 4G_FD900_MAHEN2 | 4G_FD2100_MAHEN2 | 4G_TD_MAHEN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008758 | 2022-01-12 | P/FVC/MDS/1071706/2022 | 2022-01-20 | ST202201008660 | 2022-01-12 | P/FVC/MDS/1071631/2022 | 2022-01-20 |  |  |  |  | ST202201008934 | 2022-01-13 | P/FBW/MDS/1071546/2022 | 2022-01-20
946 | NATRA2 | NATRA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | NATRA2 | 4G_FD900_NATRA2 | 4G_FD2100_NATRA2 | 4G_TD_NATRA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008761 | 2022-01-12 | P/FVC/MDS/1071709/2022 | 2022-01-20 | ST202201008668 | 2022-01-12 | P/FVC/MDS/1071634/2022 | 2022-01-20 |  |  |  |  | ST202201008940 | 2022-01-13 | P/FBW/MDS/1071549/2022 | 2022-01-20
947 | GURUV2 | GURUV2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-01-08 | GURUV2 | 4G_FD900_GURUV2 | 4G_FD2100_GURUV2 | 4G_TD_GURUV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008759 | 2022-01-12 | P/FVC/MDS/1071707/2022 | 2022-01-20 | ST202201008661 | 2022-01-12 | P/FVC/MDS/1071632/2022 | 2022-01-20 |  |  |  |  | ST202201008936 | 2022-01-13 | P/FBW/MDS/1071547/2022 | 2022-01-20
948 | NAYAN2 | NAYAN2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-08 | NAYAN2 | 4G_FD900_NAYAN2 | 4G_FD2100_NAYAN2 | 4G_TD_NAYAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008763 | 2022-01-12 | P/FVC/MDS/1071710/2022 | 2022-01-20 | ST202201008669 | 2022-01-12 | P/FVC/MDS/1071635/2022 | 2022-01-20 |  |  |  |  | ST202201008941 | 2022-01-13 | P/FBW/MDS/1071550/2022 | 2022-01-20
949 | KRKL27 | KRKL27 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-01-05 | KRKL27 | 4G_FD900_KRKL27 | 4G_FD2100_KRKL27 | 4G_TD_KRKL27 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202052222 | 2022-02-22 | P/FVC/MDS/1076297/2022 | 2022-03-13 | ST202201008588 | 2022-01-12 | P/FVC/MDS/1071605/2022 | 2022-01-20 | ST202201008981 | 2022-01-13 | P/FVC/MDS/1071726/2022 | 2022-01-20 | ST202201025378 | 2022-01-31 | P/FBW/MDS/1074332/2022 | 2022-02-22
950 | KRNGL4 | KRNGL4 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-01-17 | KRNGL4 | 4G_FD900_KRNGL4 | 4G_FD2100_KRNGL4 | 4G_TD_KRNGL4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123458 | 2022-04-30 | P/FVC/MDS/1079433/2022 | 2022-05-16 | ST202204119674 | 2022-04-26 | P/FVC/MDS/1079348/2022 | 2022-05-13 |  |  |  |  | ST202204119426 | 2022-04-26 | P/FBW/MDS/1079255/2022 | 2022-05-13
951 | MLMDU3 | MLMDU3 | Viluppuram | Trichy |  | ROTN | Indus | IN-3005020 | R/NN-625901 |  | SO | 2022-01-20 | MLMDU3 | 4G_FD900_MLMDU3 | 4G_FD2100_MLMDU3 | 4G_TD_MLMDU3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 | 18,sacfa | ST202202052223 | 2022-02-22 | P/FVC/MDS/1076298/2022 | 2022-03-13 | ST202206165111 | 2022-06-07 | P/FVC/MDS/1082400/2022 | 2022-06-14 |  |  |  |  | ST202207247179 | 2022-07-12 | P/FBW/MDS/1088582/2022 | 2022-07-25
952 | SOMAN3 | SOMAN3 | Viluppuram | Trichy |  | ROTN | Indus | IN-3025335 | R/NN-619368 |  | On Air | 2022-01-20 | SOMAN3 | 4G_FD900_SOMAN3 | 4G_FD2100_SOMAN3 | 4G_TD_SOMAN3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022538 | 2022-01-28 | P/FVC/MDS/1072929/2022 | 2022-02-04 | ST202201022643 | 2022-01-28 | P/FVC/MDS/1072962/2022 | 2022-02-04 | ST202210548586 | 2022-10-11 | P/FVC/MDS/1113930/2022 | 2022-10-21 | ST202201022820 | 2022-01-28 | P/FBW/MDS/1072989/2022 | 2022-02-04
953 | TPERIY | TPERIY | Vellore | Vellore |  | ROTN | Ascend |  |  |  | On Air | 2022-01-20 | TPERIY | 4G_FD900_TPERIY | 4G_FD2100_TPERIY | 4G_TD_TPERIY | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014672 | 2022-01-20 | P/FVC/MDS/1072385/2022 | 2022-01-31 | ST202201014742 | 2022-01-20 | P/FVC/MDS/1072356/2022 | 2022-01-31 |  |  |  |  | ST202201014793 | 2022-01-20 | P/FBW/MDS/1072327/2022 | 2022-01-31
954 | MARNAM | MARNAM | Tiruvannamalai | Vellore |  | ROTN | Ascend | - | - |  | SO | 2022-01-17 | MARNAM | 4G_FD900_MARNAM | 4G_FD2100_MARNAM | 4G_TD_MARNAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014652 | 2022-01-20 | P/FVC/MDS/1072374/2022 | 2022-01-31 | ST202201014717 | 2022-01-20 | P/FVC/MDS/1072344/2022 | 2022-01-31 |  |  |  |  | ST202201014779 | 2022-01-20 | P/FBW/MDS/1072314/2022 | 2022-01-31
955 | TIRU02 | TIRU02 | Tiruvannamalai | Vellore |  | ROTN | ATC | TN/TV/AT/22877 | - |  | On Air | 2022-01-08 | TIRU02 | 4G_FD900_TIRU02 | 4G_FD2100_TIRU02 | 4G_TD_TIRU02 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008747 | 2022-01-12 | P/FVC/MDS/1071700/2022 | 2022-01-20 | ST202201008646 | 2022-01-12 | P/FVC/MDS/1071625/2022 | 2022-01-20 |  |  |  |  | ST202201008806 | 2022-01-12 | P/FBW/MDS/1071540/2022 | 2022-01-20
956 | AVANAP | AVANAP | Krishnagiri | Vellore |  | ROTN | Ascend |  |  |  | On Air | 2022-01-20 | AVANAP | 4G_FD900_AVANAP | 4G_FD2100_AVANAP | 4G_TD_AVANAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014676 | 2022-01-20 | P/FVC/MDS/1072386/2022 | 2022-01-31 | ST202201014743 | 2022-01-20 | P/FVC/MDS/1072357/2022 | 2022-01-31 | ST202202049473 | 2022-02-19 | P/FVC/MDS/1074791/2022 | 2022-02-25 | ST202201014794 | 2022-01-20 | P/FBW/MDS/1072328/2022 | 2022-01-31
957 | SENGOD | SENGOD | Krishnagiri | Vellore |  | ROTN | Ascend |  |  |  | On Air | 2022-01-20 | SENGOD | 4G_FD900_SENGOD | 4G_FD2100_SENGOD | 4G_TD_SENGOD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014671 | 2022-01-20 | P/FVC/MDS/1072384/2022 | 2022-01-31 | ST202201014740 | 2022-01-20 | P/FVC/MDS/1072355/2022 | 2022-01-31 |  |  |  |  | ST202201014791 | 2022-01-20 | P/FBW/MDS/1072326/2022 | 2022-01-31
958 | VADMAL | VADMAL | Krishnagiri | Vellore |  | ROTN | Ascend |  |  |  | On Air | 2022-01-20 | VADMAL | 4G_FD900_VADMAL | 4G_FD2100_VADMAL | 4G_TD_VADMAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111585512 | 2021-11-09 | P/FVC/MDS/1068138/2021 | 2021-12-08 | ST202111585359 | 2021-11-09 | P/FVC/MDS/1068134/2021 | 2021-12-08 |  |  |  |  | ST202111584819 | 2021-11-09 | P/FBW/MDS/1068080/2021 | 2021-12-08
959 | METUP3 | METUP3 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3113438 | R/NN-639893 |  | On Air | 2022-01-11 | METUP3 | 4G_FD900_METUP3 | 4G_FD2100_METUP3 | 4G_TD_METUP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201008774 | 2022-01-12 | P/FVC/MDS/1071715/2022 | 2022-01-20 | ST202201008683 | 2022-01-12 | P/FVC/MDS/1071640/2022 | 2022-01-20 |  |  |  |  | ST202201008949 | 2022-01-13 | P/FBW/MDS/1071555/2022 | 2022-01-20
960 | KADAMB | KADAMB | Pudukkottai | Trichy |  | ROTN | Indus | IN-3080899 | R/NN-636191 |  | On Air | 2022-01-20 | KADAMB | 4G_FD900_KADAMB | 4G_FD2100_KADAMB | 4G_TD_KADAMB | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000154 | 2022-01-02 | P/FVC/MDS/1070757/2022 | 2022-01-06 | ST202201000169 | 2022-01-02 | P/FVC/MDS/1070772/2022 | 2022-01-06 |  |  |  |  | ST202201000184 | 2022-01-02 | P/FBW/MDS/1070782/2022 | 2022-01-06
961 | ARASAR | ARASAR | Pudukkottai | Trichy |  | ROTN | Indus | IN-3080959 | R/NN-636199 |  | SR | 2022-01-20 | ARASAR | 4G_FD900_ARASAR | 4G_FD2100_ARASAR | 4G_TD_ARASAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000155 | 2022-01-02 | P/FVC/MDS/1070758/2022 | 2022-01-06 | ST202201000170 | 2022-01-02 | P/FVC/MDS/1070773/2022 | 2022-01-06 |  |  |  |  | ST202201000185 | 2022-01-02 | P/FBW/MDS/1070783/2022 | 2022-01-06
962 | AYANGD | AYANGD | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3080970 | R/NN-636201 |  | On Air | 2022-01-20 | AYANGD | 4G_FD900_AYANGD | 4G_FD2100_AYANGD | 4G_TD_AYANGD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201000153 | 2022-01-02 | P/FVC/MDS/1070756/2022 | 2022-01-06 | ST202201000168 | 2022-01-02 | P/FVC/MDS/1070771/2022 | 2022-01-06 |  |  |  |  | ST202201000183 | 2022-01-02 | P/FBW/MDS/1070781/2022 | 2022-01-06
963 | AUNR07 | AUNR07 | Tiruppur | Coimbatore |  | ROTN | Ascend | - |  |  | On Air | 2022-01-20 | AUNR07 | 4G_FD900_AUNR07 | 4G_FD2100_AUNR07 | 4G_TD_AUNR07 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014677 | 2022-01-20 | P/FVC/MDS/1072387/2022 | 2022-01-31 | ST202201014744 | 2022-01-20 | P/FVC/MDS/1072358/2022 | 2022-01-31 |  |  |  |  | ST202201014796 | 2022-01-20 | P/FBW/MDS/1072329/2022 | 2022-01-31
964 | PALDA2 | PALDA2 | Thoothukkudi | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-01-20 | PALDA2 | 4G_FD900_PALDA2 | 4G_FD2100_PALDA2 | 4G_TD_PALDA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014679 | 2022-01-20 | P/FVC/MDS/1072388/2022 | 2022-01-31 | ST202201014748 | 2022-01-20 | P/FVC/MDS/1072359/2022 | 2022-01-31 | ST202212811928 | 2022-12-14 | P/FVC/MDS/1119362/2022 | 2022-12-20 | ST202201014797 | 2022-01-20 | P/FBW/MDS/1072330/2022 | 2022-01-31
965 | SEMKU2 | SEMKU2 | Karur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-01-17 | SEMKU2 | 4G_FD900_SEMKU2 | 4G_FD2100_SEMKU2 | 4G_TD_SEMKU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014653 | 2022-01-20 | P/FVC/MDS/1072375/2022 | 2022-01-31 | ST202201014718 | 2022-01-20 | P/FVC/MDS/1072345/2022 | 2022-01-31 |  |  |  |  | ST202201014780 | 2022-01-20 | P/FBW/MDS/1072315/2022 | 2022-01-31
966 | KRISH2 | KRISH2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3114566 | R/NN-640101 |  | On Air | 2022-01-20 | KRISH2 | 4G_FD900_KRISH2 | 4G_FD2100_KRISH2 | 4G_TD_KRISH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014685 | 2022-01-20 | P/FVC/MDS/1072393/2022 | 2022-01-31 | ST202201014760 | 2022-01-20 | P/FVC/MDS/1072364/2022 | 2022-01-31 |  |  |  |  | ST202201014807 | 2022-01-20 | P/FBW/MDS/1072335/2022 | 2022-01-31
967 | AYILP2 | AYILP2 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-3114594 | R/NN-640113 |  | On Air | 2022-01-20 | AYILP2 | 4G_FD900_AYILP2 | 4G_FD2100_AYILP2 | 4G_TD_AYILP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014686 | 2022-01-20 | P/FVC/MDS/1072394/2022 | 2022-01-31 | ST202201014762 | 2022-01-20 | P/FVC/MDS/1072365/2022 | 2022-01-31 |  |  |  |  | ST202201014809 | 2022-01-20 | P/FBW/MDS/1072336/2022 | 2022-01-31
968 | SEKAM2 | SEKAM2 | Virudhunagar | Madurai |  | ROTN | ATC | - |  |  | On Air | 2022-01-17 | SEKAM2 | 4G_FD900_SEKAM2 | 4G_FD2100_SEKAM2 | 4G_TD_SEKAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014654 | 2022-01-20 | P/FVC/MDS/1072376/2022 | 2022-01-31 | ST202201014719 | 2022-01-20 | P/FVC/MDS/1072346/2022 | 2022-01-31 |  |  |  |  | ST202201014781 | 2022-01-20 | P/FBW/MDS/1072316/2022 | 2022-01-31
969 | TLKPI2 | TLKPI2 | Vellore | Vellore |  | ROTN | ATC | - |  |  | On Air | 2022-01-17 | TLKPI2 | 4G_FD900_TLKPI2 | 4G_FD2100_TLKPI2 | 4G_TD_TLKPI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014650 | 2022-01-20 | P/FVC/MDS/1072372/2022 | 2022-01-31 | ST202201014711 | 2022-01-20 | P/FVC/MDS/1072342/2022 | 2022-01-31 |  |  |  |  | ST202201014777 | 2022-01-20 | P/FBW/MDS/1072312/2022 | 2022-01-31
970 | NILVO2 | NILVO2 | Vellore | Vellore |  | ROTN | Ascend | - |  |  | On Air | 2022-01-20 | NILVO2 | 4G_FD900_NILVO2 | 4G_FD2100_NILVO2 | 4G_TD_NILVO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014682 | 2022-01-20 | P/FVC/MDS/1072391/2022 | 2022-01-31 | ST202201014754 | 2022-01-20 | P/FVC/MDS/1072362/2022 | 2022-01-31 | ST202202049474 | 2022-02-19 | P/FVC/MDS/1074792/2022 | 2022-02-25 | ST202201014802 | 2022-01-20 | P/FBW/MDS/1072333/2022 | 2022-01-31
971 | VEPPA2 | VEPPA2 | Virudhunagar | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-01-20 | VEPPA2 | 4G_FD900_VEPPA2 | 4G_FD2100_VEPPA2 | 4G_TD_VEPPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014683 | 2022-01-20 | P/FVC/MDS/1072392/2022 | 2022-01-31 | ST202201014759 | 2022-01-20 | P/FVC/MDS/1072363/2022 | 2022-01-31 |  |  |  |  | ST202201014806 | 2022-01-20 | P/FBW/MDS/1072334/2022 | 2022-01-31
972 | MARNR2 | MARNR2 | Virudhunagar | Madurai |  | ROTN | ATC | - |  |  | On Air | 2022-01-17 | MARNR2 | 4G_FD900_MARNR2 | 4G_FD2100_MARNR2 | 4G_TD_MARNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014648 | 2022-01-20 | P/FVC/MDS/1072371/2022 | 2022-01-31 | ST202201014710 | 2022-01-20 | P/FVC/MDS/1072341/2022 | 2022-01-31 | ST202201014851 | 2022-01-20 | P/FVC/MDS/1072418/2022 | 2022-01-31 | ST202201014776 | 2022-01-20 | P/FBW/MDS/1072311/2022 | 2022-01-31
973 | AMYPM2 | AMYPM2 | Tiruppur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-01-17 | AMYPM2 | 4G_FD900_AMYPM2 | 4G_FD2100_AMYPM2 | 4G_TD_AMYPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014655 | 2022-01-20 | P/FVC/MDS/1072377/2022 | 2022-01-31 | ST202201014721 | 2022-01-20 | P/FVC/MDS/1072347/2022 | 2022-01-31 |  |  |  |  | ST202201014782 | 2022-01-20 | P/FBW/MDS/1072317/2022 | 2022-01-31
974 | KADAT3 | KADAT3 | Coimbatore | Coimbatore |  | ROTN | Ascend | - |  |  | On Air | 2022-01-20 | KADAT3 | 4G_FD900_KADAT3 | 4G_FD2100_KADAT3 | 4G_TD_KADAT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085841 | 2022-03-30 | P/FVC/MDS/1078164/2022 | 2022-04-15 | ST202203084633 | 2022-03-29 | P/FVC/MDS/1077952/2022 | 2022-04-14 |  |  |  |  | ST202203082548 | 2022-03-26 | P/FBW/MDS/1077778/2022 | 2022-04-14
975 | SULR20 | SULR20 |  |  |  | ROTN | ATC | TN/CO/TT/13972 |  |  | On Air | 2022-01-21 | SULR20 | 4G_FD900_SULR20 | 4G_FD2100_SULR20 | 4G_TD_SULR20 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201014641 | 2022-01-20 | P/FVC/MDS/1072369/2022 | 2022-01-31 | ST202201014708 | 2022-01-20 | P/FVC/MDS/1072339/2022 | 2022-01-31 | ST202201014838 | 2022-01-20 | P/FVC/MDS/1072407/2022 | 2022-01-31 | ST202201014774 | 2022-01-20 | P/FBW/MDS/1072309/2022 | 2022-01-31
976 | CBE897 | CBE897 |  |  |  | ROTN | Indus | IN-3120561 | R/NN-641558 |  |  | 2022-01-18 | CBE897 | 4G_FD900_CBE897 | 4G_FD2100_CBE897 | 4G_TD_CBE897 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201007778 | 2022-01-11 | P/FVC/MDS/1071689/2022 | 2022-01-20 | ST202202029918 | 2022-02-04 | P/FVC/MDS/1074444/2022 | 2022-02-22 | ST202201008985 | 2022-01-13 | P/FVC/MDS/1071728/2022 | 2022-01-20 | ST202201008052 | 2022-01-12 | P/FBW/MDS/1071528/2022 | 2022-01-20
977 | TRY081 | TRY081 |  |  |  | ROTN | Indus | IN-3105720 | R/NN-639086 |  |  | 2022-01-11 | TRY081 | 4G_FD900_TRY081 | 4G_FD2100_TRY081 | 4G_TD_TRY081 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201008775 | 2022-01-12 | P/FVC/MDS/1071716/2022 | 2022-01-20 | ST202201022637 | 2022-01-28 | P/FVC/MDS/1072959/2022 | 2022-02-04 | ST202201008994 | 2022-01-13 | P/FVC/MDS/1071734/2022 | 2022-01-20 | ST202201008950 | 2022-01-13 | P/FBW/MDS/1071556/2022 | 2022-01-20
978 | CDBM64 | CDBM64 |  |  |  | ROTN | Indus | IN-3103005 | R/NN-638761 |  |  | 2022-01-17 | CDBM64 | 4G_FD900_CDBM64 | 4G_FD2100_CDBM64 | 4G_TD_CDBM64 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201014647 | 2022-01-20 | P/FVC/MDS/1072370/2022 | 2022-01-31 | ST202201014709 | 2022-01-20 | P/FVC/MDS/1072340/2022 | 2022-01-31 | ST202201014827 | 2022-01-20 | P/FVC/MDS/1072399/2022 | 2022-01-31 | ST202201014775 | 2022-01-20 | P/FBW/MDS/1072310/2022 | 2022-01-31
979 | TRY386 | TRY386 |  |  |  | ROTN | Indus | IN-3120303 | R/NN-640580 |  |  | 2022-01-18 | TRY386 | 4G_FD900_TRY386 | 4G_FD2100_TRY386 | 4G_TD_TRY386 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201014668 | 2022-01-20 | P/FVC/MDS/1072382/2022 | 2022-01-31 | ST202201014733 | 2022-01-20 | P/FVC/MDS/1072352/2022 | 2022-01-31 | ST202201014834 | 2022-01-20 | P/FVC/MDS/1072404/2022 | 2022-01-31 | ST202201014788 | 2022-01-20 | P/FBW/MDS/1072323/2022 | 2022-01-31
980 | OOTY43 | OOTY43 |  |  |  | ROTN | Indus | IN-3119826 | R/NN-640915 |  |  | 2022-01-18 | OOTY43 | 4G_FD900_OOTY43 | 4G_FD2100_OOTY43 | 4G_TD_OOTY43 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201014659 | 2022-01-20 | P/FVC/MDS/1072379/2022 | 2022-01-31 | ST202201014726 | 2022-01-20 | P/FVC/MDS/1072349/2022 | 2022-01-31 | ST202201014829 | 2022-01-20 | P/FVC/MDS/1072401/2022 | 2022-01-31 | ST202201014785 | 2022-01-20 | P/FBW/MDS/1072320/2022 | 2022-01-31
981 | DGL64 | DGL064 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-30 | DGL064 | 4G_FD900_DGL064 | 4G_FD2100_DGL064 | 4G_TD_DGL064 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108497375 | 2021-08-30 | P/FVC/MDS/1060348/2021 | 2021-09-13 | ST202108494550 | 2021-08-27 | P/FVC/MDS/1060301/2021 | 2021-09-13 | ST202108493803 | 2021-08-27 | P/FVC/MDS/1060254/2021 | 2021-09-13 | ST202108493628 | 2021-08-27 | P/FBW/MDS/1060207/2021 | 2021-09-13
982 | KDBKM2 | KDBKM2 |  |  |  | ROTN | ATC | TN/TU/AT/22891 | - |  |  | 2022-01-31 | KDBKM2 | 4G_FD900_KDBKM2 | 4G_FD2100_KDBKM2 | 4G_TD_KDBKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027962 | 2022-02-02 | P/FVC/MDS/1074469/2022 | 2022-02-22 | ST202202026311 | 2022-02-01 | P/FVC/MDS/1074412/2022 | 2022-02-22 |  |  |  |  | ST202202026316 | 2022-02-01 | P/FBW/MDS/1074352/2022 | 2022-02-22
983 | THRVY3 | THRVY3 |  |  |  | ROTN | Airtel | - | - |  | SO | 2022-01-31 | THRVY3 | 4G_FD900_THRVY3 | 4G_FD2100_THRVY3 | 4G_TD_THRVY3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027996 | 2022-02-02 | P/FVC/MDS/1074480/2022 | 2022-02-22 | ST202202029880 | 2022-02-04 | P/FVC/MDS/1074423/2022 | 2022-02-22 | ST202105294912 | 2021-05-25 | P/FVC/MDS/1036486/2021 | 2021-06-23 | ST202202039047 | 2022-02-08 | P/FBW/MDS/1074363/2022 | 2022-02-22
984 | MONKPT | MONKPT |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-30 | MONKPT | 4G_FD900_MONKPT | 4G_FD2100_MONKPT | 4G_TD_MONKPT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106363650 | 2021-06-28 | P/FVC/MDS/1050225/2021 | 2021-08-09 | ST202104126221 | 2021-04-06 | P/FVC/MDS/1017824/2021 | 2021-05-15 |  |  |  |  | ST202104119673 | 2021-04-03 | P/FBW/MDS/1020266/2021 | 2021-05-23
985 | CEATLD | CEATLD |  |  |  | ROTN | Airtel | - | - |  | On Air | 2022-01-30 | CEATLD | 4G_FD900_CEATLD | 4G_FD2100_CEATLD | 4G_TD_CEATLD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027961 | 2022-02-02 | P/FVC/MDS/1074468/2022 | 2022-02-22 | ST202201025358 | 2022-01-31 | P/FVC/MDS/1074409/2022 | 2022-02-22 |  |  |  |  | ST202201025412 | 2022-01-31 | P/FBW/MDS/1074349/2022 | 2022-02-22
986 | KOOTHA | KOOTHA |  |  |  | ROTN | Indus | IN-3080906 | R/NN-636192 |  | RFAI | 2022-01-22 | KOOTHA | 4G_FD900_KOOTHA | 4G_FD2100_KOOTHA | 4G_TD_KOOTHA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022588 | 2022-01-28 | P/FVC/MDS/1072947/2022 | 2022-02-04 | ST202201022762 | 2022-01-28 | P/FVC/MDS/1072980/2022 | 2022-02-04 |  |  |  |  | ST202201022869 | 2022-01-28 | P/FBW/MDS/1073007/2022 | 2022-02-04
987 | KARAM1 | KARAM1 |  |  |  | ROTN | Indus | IN-3080926 | R/NN-636196 |  |  | 2022-01-20 | KARAM1 | 4G_FD900_KARAM1 | 4G_FD2100_KARAM1 | 4G_TD_KARAM1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022550 | 2022-01-28 | P/FVC/MDS/1072932/2022 | 2022-02-04 | ST202201022647 | 2022-01-28 | P/FVC/MDS/1072965/2022 | 2022-02-04 |  |  |  |  | ST202201022833 | 2022-01-28 | P/FBW/MDS/1072992/2022 | 2022-02-04
988 | KOTHA3 | KOTHA3 |  |  |  | ROTN | Indus | IN-3080933 | R/NN-636197 |  | On Air | 2022-01-20 | KOTHA3 | 4G_FD900_KOTHA3 | 4G_FD2100_KOTHA3 | 4G_TD_KOTHA3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022539 | 2022-01-28 | P/FVC/MDS/1072930/2022 | 2022-02-04 | ST202201022645 | 2022-01-28 | P/FVC/MDS/1072963/2022 | 2022-02-04 |  |  |  |  | ST202201022829 | 2022-01-28 | P/FBW/MDS/1072990/2022 | 2022-02-04
989 | KURUNT | KURUNT |  |  |  | ROTN | Indus | IN-3080949 | R/NN-636198 |  | SO | 2022-01-20 | KURUNT | 4G_FD900_KURUNT | 4G_FD2100_KURUNT | 4G_TD_KURUNT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022540 | 2022-01-28 | P/FVC/MDS/1072931/2022 | 2022-02-04 | ST202201022646 | 2022-01-28 | P/FVC/MDS/1072964/2022 | 2022-02-04 |  |  |  |  | ST202201022830 | 2022-01-28 | P/FBW/MDS/1072991/2022 | 2022-02-04
990 | PREMIE | PREMIE |  |  |  | ROTN | Airtel | - | - |  | On Air | 2022-01-30 | PREMIE | 4G_FD900_PREMIE | 4G_FD2100_PREMIE | 4G_TD_PREMIE | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201007787 | 2022-01-11 | P/FVC/MDS/1071694/2022 | 2022-01-20 | ST202201008630 | 2022-01-12 | P/FVC/MDS/1071617/2022 | 2022-01-20 |  |  |  |  | ST202201008057 | 2022-01-12 | P/FBW/MDS/1071533/2022 | 2022-01-20
991 | KUNNA2 | KUNNA2 |  |  |  | ROTN | Indus | IN-3114431 | R/NN-640060 |  |  | 2022-02-04 | KUNNA2 | 4G_FD900_KUNNA2 | 4G_FD2100_KUNNA2 | 4G_TD_KUNNA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029940 | 2022-02-04 | P/FVC/MDS/1074501/2022 | 2022-02-22 | ST202202029920 | 2022-02-04 | P/FVC/MDS/1074446/2022 | 2022-02-22 |  |  |  |  | ST202202039078 | 2022-02-08 | P/FBW/MDS/1074384/2022 | 2022-02-22
992 | VADUP2 | VADUP2 |  |  |  | ROTN | Indus | IN-3114555 | R/NN-640095 |  | On Air | 2022-01-22 | VADUP2 | 4G_FD900_VADUP2 | 4G_FD2100_VADUP2 | 4G_TD_VADUP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022558 | 2022-01-28 | P/FVC/MDS/1072935/2022 | 2022-02-04 | ST202201022659 | 2022-01-28 | P/FVC/MDS/1072968/2022 | 2022-02-04 |  |  |  |  | ST202201022843 | 2022-01-28 | P/FBW/MDS/1072995/2022 | 2022-02-04
993 | THRTL2 | THRTL2 |  |  |  | ROTN | ATC | TN/VI/AT/22907 | - |  | On Air | 2022-01-30 | THRTL2 | 4G_FD900_THRTL2 | 4G_FD2100_THRTL2 | 4G_TD_THRTL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025230 | 2022-01-31 | P/FVC/MDS/1074458/2022 | 2022-02-22 | ST202201025334 | 2022-01-31 | P/FVC/MDS/1074401/2022 | 2022-02-22 |  |  |  |  | ST202201025399 | 2022-01-31 | P/FBW/MDS/1074341/2022 | 2022-02-22
994 | PALPA2 | PALPA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-30 | PALPA2 | 4G_FD900_PALPA2 | 4G_FD2100_PALPA2 | 4G_TD_PALPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025231 | 2022-01-31 | P/FVC/MDS/1074459/2022 | 2022-02-22 | ST202201025335 | 2022-01-31 | P/FVC/MDS/1074402/2022 | 2022-02-22 |  |  |  |  | ST202201025401 | 2022-01-31 | P/FBW/MDS/1074342/2022 | 2022-02-22
995 | MELNE2 | MELNE2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | MELNE2 | 4G_FD900_MELNE2 | 4G_FD2100_MELNE2 | 4G_TD_MELNE2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028036 | 2022-02-02 | P/FVC/MDS/1074494/2022 | 2022-02-22 | ST202202029902 | 2022-02-04 | P/FVC/MDS/1074437/2022 | 2022-02-22 |  |  |  |  | ST202202039071 | 2022-02-08 | P/FBW/MDS/1074377/2022 | 2022-02-22
996 | MUPAT2 | MUPAT2 |  |  |  | ROTN | Indus | IN-3114583 | R/NN-640107 |  |  | 2022-01-22 | MUPAT2 | 4G_FD900_MUPAT2 | 4G_FD2100_MUPAT2 | 4G_TD_MUPAT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022560 | 2022-01-28 | P/FVC/MDS/1072937/2022 | 2022-02-04 | ST202201022715 | 2022-01-28 | P/FVC/MDS/1072970/2022 | 2022-02-04 |  |  |  |  | ST202201022850 | 2022-01-28 | P/FBW/MDS/1072997/2022 | 2022-02-04
997 | RAJAA5 | RAJAA5 |  |  |  | ROTN | Indus | IN-3114590 | R/NN-640112 |  | On Air | 2022-01-22 | RAJAA5 | 4G_FD900_RAJAA5 | 4G_FD2100_RAJAA5 | 4G_TD_RAJAA5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022567 | 2022-01-28 | P/FVC/MDS/1072938/2022 | 2022-02-04 | ST202201022716 | 2022-01-28 | P/FVC/MDS/1072971/2022 | 2022-02-04 |  |  |  |  | ST202201022851 | 2022-01-28 | P/FBW/MDS/1072998/2022 | 2022-02-04
998 | MANDU2 | MANDU2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-01-30 | MANDU2 | 4G_FD900_MANDU2 | 4G_FD2100_MANDU2 | 4G_TD_MANDU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025233 | 2022-01-31 | P/FVC/MDS/1074460/2022 | 2022-02-22 | ST202201025341 | 2022-01-31 | P/FVC/MDS/1074403/2022 | 2022-02-22 |  |  |  |  | ST202201025402 | 2022-01-31 | P/FBW/MDS/1074343/2022 | 2022-02-22
999 | KULAI5 | KULAI5 |  |  |  | ROTN | Indus | IN-3114642 | R/NN-640168 |  |  | 2022-01-22 | KULAI5 | 4G_FD900_KULAI5 | 4G_FD2100_KULAI5 | 4G_TD_KULAI5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022552 | 2022-01-28 | P/FVC/MDS/1072934/2022 | 2022-02-04 | ST202201022654 | 2022-01-28 | P/FVC/MDS/1072967/2022 | 2022-02-04 |  |  |  |  | ST202201022842 | 2022-01-28 | P/FBW/MDS/1072994/2022 | 2022-02-04
1000 | CHERK2 | CHERK2 |  |  |  | ROTN | Indus | IN-3114652 | R/NN-640173 |  | On Air | 2022-01-22 | CHERK2 | 4G_FD900_CHERK2 | 4G_FD2100_CHERK2 | 4G_TD_CHERK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022559 | 2022-01-28 | P/FVC/MDS/1072936/2022 | 2022-02-04 | ST202201022660 | 2022-01-28 | P/FVC/MDS/1072969/2022 | 2022-02-04 |  |  |  |  | ST202201022844 | 2022-01-28 | P/FBW/MDS/1072996/2022 | 2022-02-04
1001 | RUPAN2 | RUPAN2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | RUPAN2 | 4G_FD900_RUPAN2 | 4G_FD2100_RUPAN2 | 4G_TD_RUPAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028006 | 2022-02-02 | P/FVC/MDS/1074484/2022 | 2022-02-22 | ST202202029888 | 2022-02-04 | P/FVC/MDS/1074427/2022 | 2022-02-22 |  |  |  |  | ST202202039052 | 2022-02-08 | P/FBW/MDS/1074367/2022 | 2022-02-22
1002 | MADHN2 | MADHN2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | MADHN2 | 4G_FD900_MADHN2 | 4G_FD2100_MADHN2 | 4G_TD_MADHN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027971 | 2022-02-02 | P/FVC/MDS/1074471/2022 | 2022-02-22 | ST202202029854 | 2022-02-04 | P/FVC/MDS/1074414/2022 | 2022-02-22 |  |  |  |  | ST202202039032 | 2022-02-08 | P/FBW/MDS/1074354/2022 | 2022-02-22
1003 | DUPLEX | DUPLEX |  |  |  | ROTN | Airtel | - | - |  | SO | 2022-01-30 | DUPLEX | 4G_FD900_DUPLEX | 4G_FD2100_DUPLEX | 4G_TD_DUPLEX | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025243 | 2022-01-31 | P/FVC/MDS/1074465/2022 | 2022-02-22 | ST202201025351 | 2022-01-31 | P/FVC/MDS/1074408/2022 | 2022-02-22 |  |  |  |  | ST202201025411 | 2022-01-31 | P/FBW/MDS/1074348/2022 | 2022-02-22
1004 | SUNDFT | SUNDFT |  |  |  | ROTN | Airtel | - | - |  | SO | 2022-02-04 | SUNDFT | 4G_FD900_SUNDFT | 4G_FD2100_SUNDFT | 4G_TD_SUNDFT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048023 | 2022-02-18 | P/FVC/MDS/1074962/2022 | 2022-02-28 | ST202202049392 | 2022-02-19 | P/FVC/MDS/1074907/2022 | 2022-02-28 |  |  |  |  | ST202202048583 | 2022-02-18 | P/FBW/MDS/1074845/2022 | 2022-02-28
1005 | KUNDAM | KUNDAM |  |  |  | ROTN | Indus | IN-3120346 | R/NN-641505 |  | On Air | 2022-02-04 | KUNDAM | 4G_FD900_KUNDAM | 4G_FD2100_KUNDAM | 4G_TD_KUNDAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029943 | 2022-02-04 | P/FVC/MDS/1074502/2022 | 2022-02-22 | ST202202029925 | 2022-02-04 | P/FVC/MDS/1074447/2022 | 2022-02-22 |  |  |  |  | ST202202039079 | 2022-02-08 | P/FBW/MDS/1074385/2022 | 2022-02-22
1006 | SNDMP2 | SNDMP2 |  |  |  | ROTN | ATC | TN/PU/AT/22922 | - |  | On Air | 2022-02-04 | SNDMP2 | 4G_FD900_SNDMP2 | 4G_FD2100_SNDMP2 | 4G_TD_SNDMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029948 | 2022-02-04 | P/FVC/MDS/1074507/2022 | 2022-02-22 | ST202202049386 | 2022-02-19 | P/FVC/MDS/1074903/2022 | 2022-02-28 |  |  |  |  | ST202202048577 | 2022-02-18 | P/FBW/MDS/1074841/2022 | 2022-02-28
1007 | NATHK2 | NATHK2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | NATHK2 | 4G_FD900_NATHK2 | 4G_FD2100_NATHK2 | 4G_TD_NATHK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028052 | 2022-02-02 | P/FVC/MDS/1074497/2022 | 2022-02-22 | ST202202029905 | 2022-02-04 | P/FVC/MDS/1074440/2022 | 2022-02-22 |  |  |  |  | ST202202039074 | 2022-02-08 | P/FBW/MDS/1074380/2022 | 2022-02-22
1008 | SALAV2 | SALAV2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | SALAV2 | 4G_FD900_SALAV2 | 4G_FD2100_SALAV2 | 4G_TD_SALAV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028035 | 2022-02-02 | P/FVC/MDS/1074493/2022 | 2022-02-22 | ST202202029901 | 2022-02-04 | P/FVC/MDS/1074436/2022 | 2022-02-22 |  |  |  |  | ST202202039070 | 2022-02-08 | P/FBW/MDS/1074376/2022 | 2022-02-22
1009 | THAGR2 | THAGR2 |  |  |  | ROTN | Indus | IN-3121030 | R/NN-642248 |  | On Air | 2022-02-04 | THAGR2 | 4G_FD900_THAGR2 | 4G_FD2100_THAGR2 | 4G_TD_THAGR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029944 | 2022-02-04 | P/FVC/MDS/1074503/2022 | 2022-02-22 | ST202202029926 | 2022-02-04 | P/FVC/MDS/1074448/2022 | 2022-02-22 |  |  |  |  | ST202202039080 | 2022-02-08 | P/FBW/MDS/1074386/2022 | 2022-02-22
1010 | OVALU2 | OVALU2 |  |  |  | ROTN | ATC | TN/MU/AT/22928 | - |  | On Air | 2022-02-04 | OVALU2 | 4G_FD900_OVALU2 | 4G_FD2100_OVALU2 | 4G_TD_OVALU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029946 | 2022-02-04 | P/FVC/MDS/1074505/2022 | 2022-02-22 | ST202202049383 | 2022-02-19 | P/FVC/MDS/1074901/2022 | 2022-02-28 |  |  |  |  | ST202202039098 | 2022-02-08 | P/FBW/MDS/1074388/2022 | 2022-02-22
1011 | KALAI2 | KALAI2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | KALAI2 | 4G_FD900_KALAI2 | 4G_FD2100_KALAI2 | 4G_TD_KALAI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027977 | 2022-02-02 | P/FVC/MDS/1074473/2022 | 2022-02-22 | ST202202029863 | 2022-02-04 | P/FVC/MDS/1074416/2022 | 2022-02-22 |  |  |  |  | ST202202039037 | 2022-02-08 | P/FBW/MDS/1074356/2022 | 2022-02-22
1012 | SOLAS3 | SOLAS3 |  |  |  | ROTN | ATC | TN/TR/AT/22940 | - |  | On Air | 2022-02-04 | SOLAS3 | 4G_FD900_SOLAS3 | 4G_FD2100_SOLAS3 | 4G_TD_SOLAS3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029947 | 2022-02-04 | P/FVC/MDS/1074506/2022 | 2022-02-22 | ST202202049384 | 2022-02-19 | P/FVC/MDS/1074902/2022 | 2022-02-28 |  |  |  |  | ST202202039099 | 2022-02-08 | P/FBW/MDS/1074389/2022 | 2022-02-22
1013 | ADAGA2 | ADAGA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | ADAGA2 | 4G_FD900_ADAGA2 | 4G_FD2100_ADAGA2 | 4G_TD_ADAGA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028011 | 2022-02-02 | P/FVC/MDS/1074486/2022 | 2022-02-22 | ST202202029890 | 2022-02-04 | P/FVC/MDS/1074429/2022 | 2022-02-22 |  |  |  |  | ST202202039055 | 2022-02-08 | P/FBW/MDS/1074369/2022 | 2022-02-22
1014 | PLKO11 | PLKO11 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | PLKO11 | 4G_FD900_PLKO11 | 4G_FD2100_PLKO11 | 4G_TD_PLKO11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027989 | 2022-02-02 | P/FVC/MDS/1074478/2022 | 2022-02-22 | ST202202029878 | 2022-02-04 | P/FVC/MDS/1074421/2022 | 2022-02-22 |  |  |  |  | ST202202039045 | 2022-02-08 | P/FBW/MDS/1074361/2022 | 2022-02-22
1015 | PLKO12 | PLKO12 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | PLKO12 | 4G_FD900_PLKO12 | 4G_FD2100_PLKO12 | 4G_TD_PLKO12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028007 | 2022-02-02 | P/FVC/MDS/1074485/2022 | 2022-02-22 | ST202202029889 | 2022-02-04 | P/FVC/MDS/1074428/2022 | 2022-02-22 |  |  |  |  | ST202202039054 | 2022-02-08 | P/FBW/MDS/1074368/2022 | 2022-02-22
1016 | SETIK2 | SETIK2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | SETIK2 | 4G_FD900_SETIK2 | 4G_FD2100_SETIK2 | 4G_TD_SETIK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028012 | 2022-02-02 | P/FVC/MDS/1074487/2022 | 2022-02-22 | ST202202029895 | 2022-02-04 | P/FVC/MDS/1074430/2022 | 2022-02-22 |  |  |  |  | ST202202039060 | 2022-02-08 | P/FBW/MDS/1074370/2022 | 2022-02-22
1017 | PNGRM8 | PNGRM8 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | PNGRM8 | 4G_FD900_PNGRM8 | 4G_FD2100_PNGRM8 | 4G_TD_PNGRM8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028043 | 2022-02-02 | P/FVC/MDS/1074495/2022 | 2022-02-22 | ST202202029903 | 2022-02-04 | P/FVC/MDS/1074438/2022 | 2022-02-22 |  |  |  |  | ST202202039072 | 2022-02-08 | P/FBW/MDS/1074378/2022 | 2022-02-22
1018 | PNGRM7 | PNGRM7 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | PNGRM7 | 4G_FD900_PNGRM7 | 4G_FD2100_PNGRM7 | 4G_TD_PNGRM7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028013 | 2022-02-02 | P/FVC/MDS/1074488/2022 | 2022-02-22 | ST202202029896 | 2022-02-04 | P/FVC/MDS/1074431/2022 | 2022-02-22 |  |  |  |  | ST202202039061 | 2022-02-08 | P/FBW/MDS/1074371/2022 | 2022-02-22
1019 | KARIA2 | KARIA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | KARIA2 | 4G_FD900_KARIA2 | 4G_FD2100_KARIA2 | 4G_TD_KARIA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027988 | 2022-02-02 | P/FVC/MDS/1074477/2022 | 2022-02-22 | ST202202029869 | 2022-02-04 | P/FVC/MDS/1074420/2022 | 2022-02-22 |  |  |  |  | ST202202039044 | 2022-02-08 | P/FBW/MDS/1074360/2022 | 2022-02-22
1020 | JAKKA2 | JAKKA2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | JAKKA2 | 4G_FD900_JAKKA2 | 4G_FD2100_JAKKA2 | 4G_TD_JAKKA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027978 | 2022-02-02 | P/FVC/MDS/1074474/2022 | 2022-02-22 | ST202202029864 | 2022-02-04 | P/FVC/MDS/1074417/2022 | 2022-02-22 |  |  |  |  | ST202202039040 | 2022-02-08 | P/FBW/MDS/1074357/2022 | 2022-02-22
1021 | NADOO2 | NADOO2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | NADOO2 | 4G_FD900_NADOO2 | 4G_FD2100_NADOO2 | 4G_TD_NADOO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028016 | 2022-02-02 | P/FVC/MDS/1074489/2022 | 2022-02-22 | ST202202029897 | 2022-02-04 | P/FVC/MDS/1074432/2022 | 2022-02-22 |  |  |  |  | ST202202039062 | 2022-02-08 | P/FBW/MDS/1074372/2022 | 2022-02-22
1022 | ANJHL3 | ANJHL3 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | ANJHL3 | 4G_FD900_ANJHL3 | 4G_FD2100_ANJHL3 | 4G_TD_ANJHL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027979 | 2022-02-02 | P/FVC/MDS/1074475/2022 | 2022-02-22 | ST202202029867 | 2022-02-04 | P/FVC/MDS/1074418/2022 | 2022-02-22 |  |  |  |  | ST202202039041 | 2022-02-08 | P/FBW/MDS/1074358/2022 | 2022-02-22
1023 | UNGAR2 | UNGAR2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | UNGAR2 | 4G_FD900_UNGAR2 | 4G_FD2100_UNGAR2 | 4G_TD_UNGAR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028017 | 2022-02-02 | P/FVC/MDS/1074490/2022 | 2022-02-22 | ST202210614703 | 2022-10-21 | P/FVC/MDS/1114226/2022 | 2022-11-03 |  |  |  |  | ST202202039066 | 2022-02-08 | P/FBW/MDS/1074373/2022 | 2022-02-22
1024 | MARGL2 | MARGL2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | MARGL2 | 4G_FD900_MARGL2 | 4G_FD2100_MARGL2 | 4G_TD_MARGL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027972 | 2022-02-02 | P/FVC/MDS/1074472/2022 | 2022-02-22 | ST202202029855 | 2022-02-04 | P/FVC/MDS/1074415/2022 | 2022-02-22 |  |  |  |  | ST202202039036 | 2022-02-08 | P/FBW/MDS/1074355/2022 | 2022-02-22
1025 | SETKR2 | SETKR2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | SETKR2 | 4G_FD900_SETKR2 | 4G_FD2100_SETKR2 | 4G_TD_SETKR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028025 | 2022-02-02 | P/FVC/MDS/1074491/2022 | 2022-02-22 | ST202202029899 | 2022-02-04 | P/FVC/MDS/1074434/2022 | 2022-02-22 |  |  |  |  | ST202202039067 | 2022-02-08 | P/FBW/MDS/1074374/2022 | 2022-02-22
1026 | JERTL2 | JERTL2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | JERTL2 | 4G_FD900_JERTL2 | 4G_FD2100_JERTL2 | 4G_TD_JERTL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027987 | 2022-02-02 | P/FVC/MDS/1074476/2022 | 2022-02-22 | ST202202029868 | 2022-02-04 | P/FVC/MDS/1074419/2022 | 2022-02-22 |  |  |  |  | ST202202039042 | 2022-02-08 | P/FBW/MDS/1074359/2022 | 2022-02-22
1027 | PLKO14 | PLKO14 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-30 | PLKO14 | 4G_FD900_PLKO14 | 4G_FD2100_PLKO14 | 4G_TD_PLKO14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025234 | 2022-01-31 | P/FVC/MDS/1074461/2022 | 2022-02-22 | ST202201025342 | 2022-01-31 | P/FVC/MDS/1074404/2022 | 2022-02-22 |  |  |  |  | ST202201025403 | 2022-01-31 | P/FBW/MDS/1074344/2022 | 2022-02-22
1028 | ADIUR2 | ADIUR2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-02-04 | ADIUR2 | 4G_FD900_ADIUR2 | 4G_FD2100_ADIUR2 | 4G_TD_ADIUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048022 | 2022-02-18 | P/FVC/MDS/1074961/2022 | 2022-02-28 | ST202202049391 | 2022-02-19 | P/FVC/MDS/1074906/2022 | 2022-02-28 |  |  |  |  | ST202202048582 | 2022-02-18 | P/FBW/MDS/1074844/2022 | 2022-02-28
1029 | IKANE2 | IKANE2 |  |  |  | ROTN | ATC | TN/ER/AT/22945 | - |  | On Air | 2022-02-04 | IKANE2 | 4G_FD900_IKANE2 | 4G_FD2100_IKANE2 | 4G_TD_IKANE2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029945 | 2022-02-04 | P/FVC/MDS/1074504/2022 | 2022-02-22 | ST202202029927 | 2022-02-04 | P/FVC/MDS/1074449/2022 | 2022-02-22 |  |  |  |  | ST202202039097 | 2022-02-08 | P/FBW/MDS/1074387/2022 | 2022-02-22
1030 | SELPM2 | SELPM2 |  |  |  | ROTN | ATC | TN/ER/AT/22946 | - |  | On Air | 2022-02-04 | SELPM2 | 4G_FD900_SELPM2 | 4G_FD2100_SELPM2 | 4G_TD_SELPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202029965 | 2022-02-04 | P/FVC/MDS/1074508/2022 | 2022-02-22 | ST202202049387 | 2022-02-19 | P/FVC/MDS/1074904/2022 | 2022-02-28 |  |  |  |  | ST202202048578 | 2022-02-18 | P/FBW/MDS/1074842/2022 | 2022-02-28
1031 | ARNI36 | ARNI36 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-01-31 | ARNI36 | 4G_FD900_ARNI36 | 4G_FD2100_ARNI36 | 4G_TD_ARNI36 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028026 | 2022-02-02 | P/FVC/MDS/1074492/2022 | 2022-02-22 | ST202202029900 | 2022-02-04 | P/FVC/MDS/1074435/2022 | 2022-02-22 |  |  |  |  | ST202202039068 | 2022-02-08 | P/FBW/MDS/1074375/2022 | 2022-02-22
1032 | EKBRN2 | EKBRN2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-01-31 | EKBRN2 | 4G_FD900_EKBRN2 | 4G_FD2100_EKBRN2 | 4G_TD_EKBRN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028044 | 2022-02-02 | P/FVC/MDS/1074496/2022 | 2022-02-22 | ST202202029904 | 2022-02-04 | P/FVC/MDS/1074439/2022 | 2022-02-22 |  |  |  |  | ST202202039073 | 2022-02-08 | P/FBW/MDS/1074379/2022 | 2022-02-22
1033 | KDVSL3 | KDVSL3 |  |  |  | ROTN | Airtel | - | - |  | On Air | 2022-01-31 | KDVSL3 | 4G_FD900_KDVSL3 | 4G_FD2100_KDVSL3 | 4G_TD_KDVSL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202027995 | 2022-02-02 | P/FVC/MDS/1074479/2022 | 2022-02-22 | ST202202029879 | 2022-02-04 | P/FVC/MDS/1074422/2022 | 2022-02-22 |  |  |  |  | ST202202039046 | 2022-02-08 | P/FBW/MDS/1074362/2022 | 2022-02-22
1034 | KGRI43 | KGRI43 |  |  |  | ROTN | Indus | IN-3042566 | R/RES-508910 |  |  | 2022-01-31 | KGRI43 | 4G_FD900_KGRI43 | 4G_FD2100_KGRI43 | 4G_TD_KGRI43 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201007784 | 2022-01-11 | P/FVC/MDS/1071692/2022 | 2022-01-20 | ST202201008604 | 2022-01-12 | P/FVC/MDS/1071614/2022 | 2022-01-20 | ST202201008988 | 2022-01-13 | P/FVC/MDS/1071730/2022 | 2022-01-20 | ST202201008055 | 2022-01-12 | P/FBW/MDS/1071531/2022 | 2022-01-20
1035 | TOPU11 | TOPU11 |  |  |  | ROTN | Airtel | - | - |  |  | 2022-01-29 | TOPU11 | 4G_FD900_TOPU11 | 4G_FD2100_TOPU11 | 4G_TD_TOPU11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201025235 | 2022-01-31 | P/FVC/MDS/1074462/2022 | 2022-02-22 | ST202201025343 | 2022-01-31 | P/FVC/MDS/1074405/2022 | 2022-02-22 | ST202201025478 | 2022-01-31 | P/FVC/MDS/1074513/2022 | 2022-02-22 | ST202201025406 | 2022-01-31 | P/FBW/MDS/1074345/2022 | 2022-02-22
1036 | CBE882 | CBE882 |  |  |  | ROTN | Indus | IN-3120405 | R/NN-641474 |  |  | 2022-01-22 | CBE882 | 4G_FD900_CBE882 | 4G_FD2100_CBE882 | 4G_TD_CBE882 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201022573 | 2022-01-28 | P/FVC/MDS/1072941/2022 | 2022-02-04 | ST202201022727 | 2022-01-28 | P/FVC/MDS/1072974/2022 | 2022-02-04 | ST202201022907 | 2022-01-28 | P/FVC/MDS/1073023/2022 | 2022-02-04 | ST202201022858 | 2022-01-28 | P/FBW/MDS/1073001/2022 | 2022-02-04
1037 | THNKR5 | THNKR5 |  |  |  | ROTN | Airtel | - | - |  |  | 2022-01-29 | THNKR5 | 4G_FD900_THNKR5 | 4G_FD2100_THNKR5 | 4G_TD_THNKR5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201025238 | 2022-01-31 | P/FVC/MDS/1074463/2022 | 2022-02-22 | ST202201025349 | 2022-01-31 | P/FVC/MDS/1074406/2022 | 2022-02-22 | ST202201025479 | 2022-01-31 | P/FVC/MDS/1074514/2022 | 2022-02-22 | ST202201025407 | 2022-01-31 | P/FBW/MDS/1074346/2022 | 2022-02-22
1038 | CBE894 | CBE894 |  |  |  | ROTN | Indus | IN-3107649 | R/NN-639586 |  |  | 2022-01-31 | CBE894 | 4G_FD900_CBE894 | 4G_FD2100_CBE894 | 4G_TD_CBE894 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202028003 | 2022-02-02 | P/FVC/MDS/1074483/2022 | 2022-02-22 | ST202202029884 | 2022-02-04 | P/FVC/MDS/1074426/2022 | 2022-02-22 | ST202202040233 | 2022-02-09 | P/FVC/MDS/1074519/2022 | 2022-02-22 | ST202202039051 | 2022-02-08 | P/FBW/MDS/1074366/2022 | 2022-02-22
1039 | DPI056 | DPI056 |  |  |  | ROTN | Indus | IN-3120307 | R/NN-641140 |  |  | 2022-01-22 | DPI056 | 4G_FD900_DPI056 | 4G_FD2100_DPI056 | 4G_TD_DPI056 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201022574 | 2022-01-28 | P/FVC/MDS/1072942/2022 | 2022-02-04 | ST202201022735 | 2022-01-28 | P/FVC/MDS/1072975/2022 | 2022-02-04 | ST202210625971 | 2022-10-24 | P/FVC/MDS/1114197/2022 | 2022-11-03 | ST202201022859 | 2022-01-28 | P/FBW/MDS/1073002/2022 | 2022-02-04
1040 | KNYUR2 | KNYUR2 |  |  |  | ROTN | Indus | IN-3120301 | R/NN-640382 |  |  | 2022-01-22 | KNYUR2 | 4G_FD900_KNYUR2 | 4G_FD2100_KNYUR2 | 4G_TD_KNYUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201022584 | 2022-01-28 | P/FVC/MDS/1072945/2022 | 2022-02-04 | ST202201022747 | 2022-01-28 | P/FVC/MDS/1072978/2022 | 2022-02-04 | ST202201022912 | 2022-01-28 | P/FVC/MDS/1073027/2022 | 2022-02-04 | ST202201022867 | 2022-01-28 | P/FBW/MDS/1073005/2022 | 2022-02-04
1041 | MATTU2 | MATTU2 |  |  |  | ROTN | Indus | IN-3120554 | R/NN-641573 |  |  | 2022-01-22 | MATTU2 | 4G_FD900_MATTU2 | 4G_FD2100_MATTU2 | 4G_TD_MATTU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201022583 | 2022-01-28 | P/FVC/MDS/1072944/2022 | 2022-02-04 | ST202201022746 | 2022-01-28 | P/FVC/MDS/1072977/2022 | 2022-02-04 | ST202201022911 | 2022-01-28 | P/FVC/MDS/1073026/2022 | 2022-02-04 | ST202201022865 | 2022-01-28 | P/FBW/MDS/1073004/2022 | 2022-02-04
1042 | NAND12 | NAND12 |  |  |  | CHN | Indus | IN-3114540 | R/NN-640093 |  |  | 2022-01-22 | NAND12 | 4G_FD900_NAND12 | 4G_FD2100_NAND12 | 4G_TD_NAND12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022587 | 2022-01-28 | P/FVC/MDS/1072946/2022 | 2022-02-04 | ST202201022748 | 2022-01-28 | P/FVC/MDS/1072979/2022 | 2022-02-04 |  |  |  |  | ST202201022868 | 2022-01-28 | P/FBW/MDS/1073006/2022 | 2022-02-04
1043 | MUDI30 | MUDI30 |  |  |  | CHN | Indus | IN-3120553 | R/NN-641557 |  |  | 2022-01-18 | MUDI30 | 4G_FD900_MUDI30 | 4G_FD2100_MUDI30 | 4G_TD_MUDI30 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201013802 | 2022-01-19 | P/FVC/MDS/1071783/2022 | 2022-01-21 | ST202201014739 | 2022-01-20 | P/FVC/MDS/1072354/2022 | 2022-01-31 | ST202201014837 | 2022-01-20 | P/FVC/MDS/1072406/2022 | 2022-01-31 | ST202201014790 | 2022-01-20 | P/FBW/MDS/1072325/2022 | 2022-01-31
1044 | TNJ85 | TNJ085 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-02-11 | TNJ085 | 4G_FD900_TNJ085 | 4G_FD2100_TNJ085 | 4G_TD_TNJ085 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048185 | 2022-02-18 | P/FVC/MDS/1074999/2022 | 2022-02-28 | ST202202049429 | 2022-02-19 | P/FVC/MDS/1074944/2022 | 2022-02-28 | ST202110560496 | 2021-10-14 | P/FVC/MDS/1063758/2021 | 2021-10-22 | ST202202048678 | 2022-02-18 | P/FBW/MDS/1074886/2022 | 2022-02-28
1045 | KKD61 | KKD061 | Sivaganga | Madurai |  | ROTN | TVI |  |  |  | On Air |  | KKD061 | 4G_FD900_KKD061 | 4G_FD2100_KKD061 | 4G_TD_KKD061 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048162 | 2022-02-18 | P/FVC/MDS/1074983/2022 | 2022-02-28 | ST202202049413 | 2022-02-19 | P/FVC/MDS/1074928/2022 | 2022-02-28 |  |  |  |  | ST202202048636 | 2022-02-18 | P/FBW/MDS/1074869/2022 | 2022-02-28
1046 | KOOTHR | KOOTHR | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-KLVR-ENB-9023 | SR-TN000565 |  | On Air | 2022-02-10 | KOOTHR | 4G_FD900_KOOTHR | 4G_FD2100_KOOTHR | 4G_TD_KOOTHR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048184 | 2022-02-18 | P/FVC/MDS/1074998/2022 | 2022-02-28 | ST202202049428 | 2022-02-19 | P/FVC/MDS/1074943/2022 | 2022-02-28 |  |  |  |  | ST202202048676 | 2022-02-18 | P/FBW/MDS/1074884/2022 | 2022-02-28
1047 | MUDLPL | MUDLPL | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-TPPR-ENB-9086 | SR-TN000562 |  | On Air | 2022-02-07 | MUDLPL | 4G_FD900_MUDLPL | 4G_FD2100_MUDLPL | 4G_TD_MUDLPL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108498633 | 2021-08-31 | P/FVC/MDS/1060425/2021 | 2021-09-13 | ST202108498279 | 2021-08-31 | P/FVC/MDS/1060493/2021 | 2021-09-13 | ST202109499782 | 2021-09-01 | P/FVC/MDS/1060701/2021 | 2021-09-13 | ST202109499911 | 2021-09-01 | P/FBW/MDS/1060659/2021 | 2021-09-13
1048 | VDLR23 | VDLR23 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | VDLR23 | 4G_FD900_VDLR23 | 4G_FD2100_VDLR23 | 4G_TD_VDLR23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048186 | 2022-02-18 | P/FVC/MDS/1075000/2022 | 2022-02-28 | ST202202049430 | 2022-02-19 | P/FVC/MDS/1074945/2022 | 2022-02-28 |  |  |  |  | ST202202048679 | 2022-02-18 | P/FBW/MDS/1074887/2022 | 2022-02-28
1049 | SANMAR | SANMAR | Puducherry | Trichy |  | ROTN | Airtel | - | - |  | On Air | 2022-02-07 | SANMAR | 4G_FD900_SANMAR | 4G_FD2100_SANMAR | 4G_TD_SANMAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048042 | 2022-02-18 | P/FVC/MDS/1074967/2022 | 2022-02-28 | ST202202049397 | 2022-02-19 | P/FVC/MDS/1074912/2022 | 2022-02-28 |  |  |  |  | ST202202048594 | 2022-02-18 | P/FBW/MDS/1074853/2022 | 2022-02-28
1050 | KALYUR | KALYUR | Tiruvannamalai | Vellore |  | ROTN | Summit | I-TN-TRVT-ENB-9068 | SR-TN000504 |  | On Air | 2022-02-11 | KALYUR | 4G_FD900_KALYUR | 4G_FD2100_KALYUR | 4G_TD_KALYUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559424 | 2021-10-14 | P/FVC/MDS/1063746/2021 | 2021-10-22 | ST202110560218 | 2021-10-14 | P/FVC/MDS/1063722/2021 | 2021-10-22 |  |  |  |  | ST202110560336 | 2021-10-14 | P/FVC/MDS/1063697/2021 | 2021-10-22
1051 | KALEND | KALEND | Vellore | Vellore |  | ROTN | Summit | I-TN-VMBD-ENB-9046 | SR-TN000637 |  | On Air | 2022-02-11 | KALEND | 4G_FD900_KALEND | 4G_FD2100_KALEND | 4G_TD_KALEND | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111592497 | 2021-11-17 | P/FVC/MDS/1066602/2021 | 2021-11-26 | ST202111588048 | 2021-11-12 | P/FVC/MDS/1068189/2021 | 2021-12-08 |  |  |  |  | ST202111588432 | 2021-11-12 | P/FBW/MDS/1068207/2021 | 2021-12-08
1052 | BENGUR | BENGUR | Krishnagiri | Vellore |  | ROTN | Indus | IN-3120222 | R/NN-641276 |  | On Air | 2022-02-11 | BENGUR | 4G_FD900_BENGUR | 4G_FD2100_BENGUR | 4G_TD_BENGUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048063 | 2022-02-18 | P/FVC/MDS/1074970/2022 | 2022-02-28 | ST202202049400 | 2022-02-19 | P/FVC/MDS/1074915/2022 | 2022-02-28 |  |  |  |  | ST202202048599 | 2022-02-18 | P/FBW/MDS/1074856/2022 | 2022-02-28
1053 | ETTIPA | ETTIPA | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-UTHN-ENB-9061 | SR-TN000643 |  | On Air | 2022-02-11 | ETTIPA | 4G_FD900_ETTIPA | 4G_FD2100_ETTIPA | 4G_TD_ETTIPA | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202111587767 | 2021-11-12 | P/FVC/MDS/1068169/2021 | 2021-12-08 | ST202111588045 | 2021-11-12 | P/FVC/MDS/1068186/2021 | 2021-12-08 |  |  |  |  | ST202111588429 | 2021-11-12 | P/FBW/MDS/1068204/2021 | 2021-12-08
1054 | PANNAN | PANNAN | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-ANGD-ENB-9028 | SR-TN000662 |  | On Air | 2022-02-10 | PANNAN | 4G_FD900_PANNAN | 4G_FD2100_PANNAN | 4G_TD_PANNAN | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202111595148 | 2021-11-19 | P/FVC/MDS/1067068/2021 | 2021-12-01 | ST202111592949 | 2021-11-17 | P/FVC/MDS/1066599/2021 | 2021-11-26 |  |  |  |  | ST202111595307 | 2021-11-19 | P/FBW/MDS/1067044/2021 | 2021-12-01
1055 | ARANA2 | ARANA2 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-TRMY-ENB-9046 | SR-TN000674 |  | On Air | 2022-02-10 | ARANA2 | 4G_FD900_ARANA2 | 4G_FD2100_ARANA2 | 4G_TD_ARANA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623542 | 2021-12-21 | P/FVC/MDS/1070058/2021 | 2021-12-29 | ST202112625931 | 2021-12-23 | P/FVC/MDS/1069732/2021 | 2021-12-28 |  |  |  |  | ST202112626690 | 2021-12-24 | P/FBW/MDS/1070165/2021 | 2021-12-29
1056 | MUGAP2 | MUGAP2 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-TRMY-ENB-9034 | SR-TN000675 |  | On Air | 2022-02-10 | MUGAP2 | 4G_FD900_MUGAP2 | 4G_FD2100_MUGAP2 | 4G_TD_MUGAP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623543 | 2021-12-21 | P/FVC/MDS/1070059/2021 | 2021-12-29 | ST202112625932 | 2021-12-23 | P/FVC/MDS/1069733/2021 | 2021-12-28 |  |  |  |  | ST202112626691 | 2021-12-24 | P/FBW/MDS/1070166/2021 | 2021-12-29
1057 | TIRYM3 | TIRYM3 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-TRMY-ENB-9035 | SR-TN000676 |  | On Air | 2022-02-07 | TIRYM3 | 4G_FD900_TIRYM3 | 4G_FD2100_TIRYM3 | 4G_TD_TIRYM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202028076 | 2022-02-02 | P/FVC/MDS/1074499/2022 | 2022-02-22 | ST202112625908 | 2021-12-23 | P/FVC/MDS/1069726/2021 | 2021-12-28 |  |  |  |  | ST202112626685 | 2021-12-24 | P/FBW/MDS/1070160/2021 | 2021-12-29
1058 | KOONA2 | KOONA2 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-KCYG-ENB-9001 | SR-TN000686 |  | On Air | 2022-02-07 | KOONA2 | 4G_FD900_KOONA2 | 4G_FD2100_KOONA2 | 4G_TD_KOONA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623610 | 2021-12-21 | P/FVC/MDS/1070068/2021 | 2021-12-29 | ST202112626110 | 2021-12-23 | P/FVC/MDS/1069742/2021 | 2021-12-28 |  |  |  |  | ST202112626714 | 2021-12-24 | P/FBW/MDS/1070175/2021 | 2021-12-29
1059 | ETTIV2 | ETTIV2 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-AVNS-ENB-9096 | SR-TN000692 |  | On Air | 2022-02-07 | ETTIV2 | 4G_FD900_ETTIV2 | 4G_FD2100_ETTIV2 | 4G_TD_ETTIV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623619 | 2021-12-21 | P/FVC/MDS/1070069/2021 | 2021-12-29 | ST202112626154 | 2021-12-23 | P/FVC/MDS/1069743/2021 | 2021-12-28 | ST202210538390 | 2022-10-08 | P/FVC/MDS/1113899/2022 | 2022-10-21 | ST202112626774 | 2021-12-24 | P/FBW/MDS/1070449/2022 | 2022-01-03
1060 | PNGYM2 | PNGYM2 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-PBYL-ENB-9001 | SR-TN000688 |  | On Air | 2022-02-07 | PNGYM2 | 4G_FD900_PNGYM2 | 4G_FD2100_PNGYM2 | 4G_TD_PNGYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112624416 | 2021-12-22 | P/FVC/MDS/1070359/2022 | 2022-01-03 | ST202112626167 | 2021-12-23 | P/FVC/MDS/1070419/2022 | 2022-01-03 |  |  |  |  | ST202112626775 | 2021-12-24 | P/FBW/MDS/1070450/2022 | 2022-01-03
1061 | MALUM1 | MALUM1 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-OTKM-ENB-9007 | SR-TN000693 |  | On Air | 2022-02-07 | MALUM1 | 4G_FD900_MALUM1 | 4G_FD2100_MALUM1 | 4G_TD_MALUM1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112624417 | 2021-12-22 | P/FVC/MDS/1070360/2022 | 2022-01-03 | ST202112626171 | 2021-12-23 | P/FVC/MDS/1070420/2022 | 2022-01-03 |  |  |  |  | ST202112626801 | 2021-12-24 | P/FBW/MDS/1070451/2022 | 2022-01-03
1062 | KUZHI2 | KUZHI2 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22903 | - |  | On Air | 2022-02-11 | KUZHI2 | 4G_FD900_KUZHI2 | 4G_FD2100_KUZHI2 | 4G_TD_KUZHI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073871 | 2022-03-16 | P/FVC/MDS/1077142/2022 | 2022-03-30 | ST202203073310 | 2022-03-15 | P/FVC/MDS/1077093/2022 | 2022-03-30 |  |  |  |  | ST202203072822 | 2022-03-15 | P/FBW/MDS/1077043/2022 | 2022-03-30
1063 | AVANI2 | AVANI2 | Sivaganga | Madurai |  | ROTN | Summit | I-TN-MDUR-ENB-9052 | SR-TN000684 |  | On Air | 2022-02-07 | AVANI2 | 4G_FD900_AVANI2 | 4G_FD2100_AVANI2 | 4G_TD_AVANI2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112624419 | 2021-12-22 | P/FVC/MDS/1070361/2022 | 2022-01-03 | ST202112626172 | 2021-12-23 | P/FVC/MDS/1070421/2022 | 2022-01-03 |  |  |  |  | ST202112626802 | 2021-12-24 | P/FBW/MDS/1070452/2022 | 2022-01-03
1064 | POOND8 | POOND8 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-PNRT-ENB-9029 | SR-TN000691 |  | On Air | 2022-02-07 | POOND8 | 4G_FD900_POOND8 | 4G_FD2100_POOND8 | 4G_TD_POOND8 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112624420 | 2021-12-22 | P/FVC/MDS/1070362/2022 | 2022-01-03 | ST202112626177 | 2021-12-23 | P/FVC/MDS/1070422/2022 | 2022-01-03 | ST202210548517 | 2022-10-11 | P/FVC/MDS/1113924/2022 | 2022-10-21 | ST202112626813 | 2021-12-24 | P/FBW/MDS/1070453/2022 | 2022-01-03
1065 | SEMMR2 | SEMMR2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-ULND-ENB-9077 | SR-TN000689 |  | On Air | 2022-02-10 | SEMMR2 | 4G_FD900_SEMMR2 | 4G_FD2100_SEMMR2 | 4G_TD_SEMMR2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112624425 | 2021-12-22 | P/FVC/MDS/1070364/2022 | 2022-01-03 | ST202112626183 | 2021-12-23 | P/FVC/MDS/1070424/2022 | 2022-01-03 |  |  |  |  | ST202112626833 | 2021-12-24 | P/FBW/MDS/1070455/2022 | 2022-01-03
1066 | VADIV2 | VADIV2 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBS-ENB-9037 | SR-TN000698 |  | On Air | 2022-02-07 | VADIV2 | 4G_FD900_VADIV2 | 4G_FD2100_VADIV2 | 4G_TD_VADIV2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625275 | 2021-12-22 | P/FVC/MDS/1070329/2022 | 2022-01-03 | ST202112626307 | 2021-12-24 | P/FVC/MDS/1070202/2021 | 2021-12-30 |  |  |  |  | ST202112627114 | 2021-12-24 | P/FBW/MDS/1070500/2022 | 2022-01-03
1067 | ILAVA2 | ILAVA2 | Thoothukkudi | Madurai |  | ROTN | Summit | I-TN-ETYP-ENB-9018 | SR-TN000699 |  | On Air | 2022-02-07 | ILAVA2 | 4G_FD900_ILAVA2 | 4G_FD2100_ILAVA2 | 4G_TD_ILAVA2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112623510 | 2021-12-21 | P/FVC/MDS/1070054/2021 | 2021-12-29 | ST202112625912 | 2021-12-23 | P/FVC/MDS/1069728/2021 | 2021-12-28 |  |  |  |  | ST202112626686 | 2021-12-24 | P/FBW/MDS/1070161/2021 | 2021-12-29
1068 | NEERV2 | NEERV2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-KCPM-ENB-9048 | SR-TN000696 |  | On Air | 2022-02-07 | NEERV2 | 4G_FD900_NEERV2 | 4G_FD2100_NEERV2 | 4G_TD_NEERV2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625288 | 2021-12-22 | P/FVC/MDS/1070331/2022 | 2022-01-03 | ST202112626309 | 2021-12-24 | P/FVC/MDS/1070204/2021 | 2021-12-30 |  |  |  |  | ST202112627118 | 2021-12-24 | P/FBW/MDS/1070502/2022 | 2022-01-03
1069 | SMPLM3 | SMPLM3 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-PLDM-ENB-9089 | SR-TN000694 |  | On Air | 2022-02-07 | SMPLM3 | 4G_FD900_SMPLM3 | 4G_FD2100_SMPLM3 | 4G_TD_SMPLM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625478 | 2021-12-23 | P/FVC/MDS/1070333/2022 | 2022-01-03 | ST202112626318 | 2021-12-24 | P/FVC/MDS/1070206/2021 | 2021-12-30 |  |  |  |  | ST202112627131 | 2021-12-24 | P/FBW/MDS/1070504/2022 | 2022-01-03
1070 | IRGKI2 | IRGKI2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-SPRM-ENB-0045 | SR-TN000704 |  | On Air | 2022-02-07 | IRGKI2 | 4G_FD900_IRGKI2 | 4G_FD2100_IRGKI2 | 4G_TD_IRGKI2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625479 | 2021-12-23 | P/FVC/MDS/1070334/2022 | 2022-01-03 | ST202112626319 | 2021-12-24 | P/FVC/MDS/1070207/2021 | 2021-12-30 |  |  |  |  | ST202112627132 | 2021-12-24 | P/FBW/MDS/1070505/2022 | 2022-01-03
1071 | PERML2 | PERML2 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9077 | SR-TN000700 |  | On Air | 2022-02-07 | PERML2 | 4G_FD900_PERML2 | 4G_FD2100_PERML2 | 4G_TD_PERML2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112624426 | 2021-12-22 | P/FVC/MDS/1070365/2022 | 2022-01-03 | ST202112626184 | 2021-12-23 | P/FVC/MDS/1070425/2022 | 2022-01-03 |  |  |  |  | ST202112626834 | 2021-12-24 | P/FBW/MDS/1070456/2022 | 2022-01-03
1072 | ATHIA2 | ATHIA2 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9090 | SR-TN000701 |  | On Air | 2022-02-07 | ATHIA2 | 4G_FD900_ATHIA2 | 4G_FD2100_ATHIA2 | 4G_TD_ATHIA2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112624427 | 2021-12-22 | P/FVC/MDS/1070366/2022 | 2022-01-03 | ST202112626187 | 2021-12-23 | P/FVC/MDS/1070426/2022 | 2022-01-03 |  |  |  |  | ST202112626852 | 2021-12-24 | P/FBW/MDS/1070457/2022 | 2022-01-03
1073 | PUDU08 | PUDU08 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBS-ENB-9042 | SR-TN000717 |  | On Air | 2022-02-07 | PUDU08 | 4G_FD900_PUDU08 | 4G_FD2100_PUDU08 | 4G_TD_PUDU08 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625483 | 2021-12-23 | P/FVC/MDS/1070337/2022 | 2022-01-03 | ST202112626326 | 2021-12-24 | P/FVC/MDS/1070210/2021 | 2021-12-30 |  |  |  |  | ST202112627139 | 2021-12-24 | P/FBW/MDS/1070508/2022 | 2022-01-03
1074 | AYPLM2 | AYPLM2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-SMNG-ENB-9068 | SR-TN000711 |  | On Air | 2022-02-07 | AYPLM2 | 4G_FD900_AYPLM2 | 4G_FD2100_AYPLM2 | 4G_TD_AYPLM2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625485 | 2021-12-23 | P/FVC/MDS/1070339/2022 | 2022-01-03 | ST202112626334 | 2021-12-24 | P/FVC/MDS/1070212/2021 | 2021-12-30 |  |  |  |  | ST202112627151 | 2021-12-24 | P/FBW/MDS/1070471/2022 | 2022-01-03
1075 | KILIY2 | KILIY2 | Tiruchirappalli | Trichy |  | ROTN | Summit | I-TN-THYR-ENB-9051 | SR-TN000724 |  | On Air | 2022-02-10 | KILIY2 | 4G_FD900_KILIY2 | 4G_FD2100_KILIY2 | 4G_TD_KILIY2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625087 | 2021-12-22 | P/FVC/MDS/1070373/2022 | 2022-01-03 | ST202112626204 | 2021-12-23 | P/FVC/MDS/1070433/2022 | 2022-01-03 |  |  |  |  | ST202112626927 | 2021-12-24 | P/FBW/MDS/1070464/2022 | 2022-01-03
1076 | MAMBA2 | MAMBA2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-TRKD-ENB-9048 | SR-TN000715 |  | On Air | 2022-02-07 | MAMBA2 | 4G_FD900_MAMBA2 | 4G_FD2100_MAMBA2 | 4G_TD_MAMBA2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625088 | 2021-12-22 | P/FVC/MDS/1070374/2022 | 2022-01-03 | ST202112626205 | 2021-12-23 | P/FVC/MDS/1070434/2022 | 2022-01-03 |  |  |  |  | ST202112626942 | 2021-12-24 | P/FBW/MDS/1070465/2022 | 2022-01-03
1077 | PALVA2 | PALVA2 | Tiruvannamalai | Vellore |  | ROTN | Summit | I-TN-TRVT-ENB-9099 | SR-TN000713 |  | On Air | 2022-02-07 | PALVA2 | 4G_FD900_PALVA2 | 4G_FD2100_PALVA2 | 4G_TD_PALVA2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625100 | 2021-12-22 | P/FVC/MDS/1070376/2022 | 2022-01-03 | ST202112626207 | 2021-12-23 | P/FVC/MDS/1070436/2022 | 2022-01-03 |  |  |  |  | ST202112626955 | 2021-12-24 | P/FBW/MDS/1070468/2022 | 2022-01-03
1078 | IRUND2 | IRUND2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-ULND-ENB-9078 | SR-TN000728 |  | On Air | 2022-02-07 | IRUND2 | 4G_FD900_IRUND2 | 4G_FD2100_IRUND2 | 4G_TD_IRUND2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625113 | 2021-12-22 | P/FVC/MDS/1070380/2022 | 2022-01-03 | ST202112626212 | 2021-12-23 | P/FVC/MDS/1070440/2022 | 2022-01-03 |  |  |  |  | ST202112627149 | 2021-12-24 | P/FBW/MDS/1070469/2022 | 2022-01-03
1079 | THAGA2 | THAGA2 | Nagapattinam | Trichy |  | ROTN | Ascend | 004500 | - |  | On Air | 2022-02-11 | THAGA2 | 4G_FD900_THAGA2 | 4G_FD2100_THAGA2 | 4G_TD_THAGA2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202201007764 | 2022-01-11 | P/FVC/MDS/1071679/2022 | 2022-01-20 | ST202201008574 | 2022-01-12 | P/FVC/MDS/1071601/2022 | 2022-01-20 |  |  |  |  | ST202201008044 | 2022-01-12 | P/FBW/MDS/1071520/2022 | 2022-01-20
1080 | GOVIN2 | GOVIN2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-WLJB-ENB-9002 | SR-TN000744 |  | On Air | 2022-02-07 | GOVIN2 | 4G_FD900_GOVIN2 | 4G_FD2100_GOVIN2 | 4G_TD_GOVIN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625632 | 2021-12-23 | P/FVC/MDS/1070355/2022 | 2022-01-03 | ST202112626444 | 2021-12-24 | P/FVC/MDS/1070228/2021 | 2021-12-30 |  |  |  |  | ST202112627177 | 2021-12-24 | P/FBW/MDS/1070487/2022 | 2022-01-03
1081 | KATHP2 | KATHP2 | Vellore | Vellore |  | ROTN | Summit | I-TN-WLLJ-ENB-9062 | SR-TN000741 |  | On Air | 2022-02-07 | KATHP2 | 4G_FD900_KATHP2 | 4G_FD2100_KATHP2 | 4G_TD_KATHP2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625124 | 2021-12-22 | P/FVC/MDS/1070382/2022 | 2022-01-03 | ST202112626216 | 2021-12-23 | P/FVC/MDS/1070442/2022 | 2022-01-03 | ST202201022900 | 2022-01-28 | P/FVC/MDS/1073016/2022 | 2022-02-04 | ST202112627103 | 2021-12-24 | P/FBW/MDS/1070493/2022 | 2022-01-03
1082 | SPD114 | SPD114 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-SPRM-ENB-9022 | SR-TN000739 |  | On Air | 2022-02-07 | SPD114 | 4G_FD900_SPD114 | 4G_FD2100_SPD114 | 4G_TD_SPD114 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625634 | 2021-12-23 | P/FVC/MDS/1070357/2022 | 2022-01-03 | ST202112626446 | 2021-12-24 | P/FVC/MDS/1070230/2021 | 2021-12-30 |  |  |  |  | ST202112627178 | 2021-12-24 | P/FBW/MDS/1070488/2022 | 2022-01-03
1083 | ALANU3 | ALANU3 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TTPN-ENB-9028 | SR-TN000746 |  | On Air | 2022-02-10 | ALANU3 | 4G_FD900_ALANU3 | 4G_FD2100_ALANU3 | 4G_TD_ALANU3 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625126 | 2021-12-22 | P/FVC/MDS/1070384/2022 | 2022-01-03 | ST202112626222 | 2021-12-23 | P/FVC/MDS/1070444/2022 | 2022-01-03 |  |  |  |  | ST202112627106 | 2021-12-24 | P/FBW/MDS/1070495/2022 | 2022-01-03
1084 | KAGRK2 | KAGRK2 | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-STTU-ENB-9050 | SR-TN000768 |  | On Air | 2022-02-10 | KAGRK2 | 4G_FD900_KAGRK2 | 4G_FD2100_KAGRK2 | 4G_TD_KAGRK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022520 | 2022-01-28 | P/FVC/MDS/1072927/2022 | 2022-02-04 | ST202112626485 | 2021-12-24 | P/FVC/MDS/1070243/2021 | 2021-12-30 |  |  |  |  | ST202112627199 | 2021-12-24 | P/FVC/MDS/1070537/2022 | 2022-01-03
1085 | TRVNL3 | TRVNL3 | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-RJPM-ENB-0047 | SR-TN000764 |  | On Air | 2022-02-07 | TRVNL3 | 4G_FD900_TRVNL3 | 4G_FD2100_TRVNL3 | 4G_TD_TRVNL3 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625680 | 2021-12-23 | P/FVC/MDS/1070401/2022 | 2022-01-03 | ST202112626487 | 2021-12-24 | P/FVC/MDS/1070245/2021 | 2021-12-30 |  |  |  |  | ST202112627201 | 2021-12-24 | P/FVC/MDS/1070539/2022 | 2022-01-03
1086 | AVATAX | AVATAX | Coimbatore | Coimbatore |  | ROTN | Airtel | - | - |  | On Air | 2022-02-07 | AVATAX | 4G_FD900_AVATAX | 4G_FD2100_AVATAX | 4G_TD_AVATAX | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048041 | 2022-02-18 | P/FVC/MDS/1074966/2022 | 2022-02-28 | ST202202049396 | 2022-02-19 | P/FVC/MDS/1074911/2022 | 2022-02-28 | ST202210538371 | 2022-10-08 | P/FVC/MDS/1113889/2022 | 2022-10-21 | ST202202048593 | 2022-02-18 | P/FBW/MDS/1074852/2022 | 2022-02-28
1087 | CHGKI2 | CHGKI2 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/22923 | - |  | On Air | 2022-02-07 | CHGKI2 | 4G_FD900_CHGKI2 | 4G_FD2100_CHGKI2 | 4G_TD_CHGKI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048032 | 2022-02-18 | P/FVC/MDS/1074963/2022 | 2022-02-28 | ST202202049393 | 2022-02-19 | P/FVC/MDS/1074908/2022 | 2022-02-28 |  |  |  |  | ST202202048589 | 2022-02-18 | P/FBW/MDS/1074849/2022 | 2022-02-28
1088 | MEIVA2 | MEIVA2 | Pudukkottai | Trichy |  | ROTN | ATC | TN/PU/AT/22924 | - |  | On Air | 2022-02-07 | MEIVA2 | 4G_FD900_MEIVA2 | 4G_FD2100_MEIVA2 | 4G_TD_MEIVA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048034 | 2022-02-18 | P/FVC/MDS/1074965/2022 | 2022-02-28 | ST202202049395 | 2022-02-19 | P/FVC/MDS/1074910/2022 | 2022-02-28 |  |  |  |  | ST202202048592 | 2022-02-18 | P/FBW/MDS/1074851/2022 | 2022-02-28
1089 | NERKM2 | NERKM2 | Viluppuram | Trichy |  | ROTN | ATC | TN/VLP/AT/22925 | - |  | On Air | 2022-02-07 | NERKM2 | 4G_FD900_NERKM2 | 4G_FD2100_NERKM2 | 4G_TD_NERKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048183 | 2022-02-18 | P/FVC/MDS/1074997/2022 | 2022-02-28 | ST202202049427 | 2022-02-19 | P/FVC/MDS/1074942/2022 | 2022-02-28 |  |  |  |  | ST202202048675 | 2022-02-18 | P/FBW/MDS/1074883/2022 | 2022-02-28
1090 | KANRT2 | KANRT2 | Ariyalur | Trichy |  | ROTN | Summit | I-TN-ARYL-ENB-9070 | SR-TN000703 |  | On Air | 2022-02-10 | KANRT2 | 4G_FD900_KANRT2 | 4G_FD2100_KANRT2 | 4G_TD_KANRT2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625481 | 2021-12-23 | P/FVC/MDS/1070335/2022 | 2022-01-03 | ST202112626320 | 2021-12-24 | P/FVC/MDS/1070208/2021 | 2021-12-30 |  |  |  |  | ST202112627137 | 2021-12-24 | P/FBW/MDS/1070506/2022 | 2022-01-03
1091 | RASTA2 | RASTA2 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-TLVL-ENB-9025 | SR-TN000720 |  | On Air | 2022-02-10 | RASTA2 | 4G_FD900_RASTA2 | 4G_FD2100_RASTA2 | 4G_TD_RASTA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625486 | 2021-12-23 | P/FVC/MDS/1070340/2022 | 2022-01-03 | ST202112626335 | 2021-12-24 | P/FVC/MDS/1070213/2021 | 2021-12-30 |  |  |  |  | ST202112627152 | 2021-12-24 | P/FBW/MDS/1070472/2022 | 2022-01-03
1092 | PIYAK2 | PIYAK2 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/22933 | - |  | On Air | 2022-02-11 | PIYAK2 | 4G_FD900_PIYAK2 | 4G_FD2100_PIYAK2 | 4G_TD_PIYAK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048066 | 2022-02-18 | P/FVC/MDS/1074971/2022 | 2022-02-28 | ST202202049401 | 2022-02-19 | P/FVC/MDS/1074916/2022 | 2022-02-28 |  |  |  |  | ST202202048607 | 2022-02-18 | P/FBW/MDS/1074857/2022 | 2022-02-28
1093 | NAVAL2 | NAVAL2 | Tiruvannamalai | Vellore |  | ROTN | Summit | I-TN-TRVT-ENB-9092 | SR-TN000722 |  | On Air | 2022-02-11 | NAVAL2 | 4G_FD900_NAVAL2 | 4G_FD2100_NAVAL2 | 4G_TD_NAVAL2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625494 | 2021-12-23 | P/FVC/MDS/1070343/2022 | 2022-01-03 | ST202201022633 | 2022-01-28 | P/FVC/MDS/1072957/2022 | 2022-02-04 |  |  |  |  | ST202112627155 | 2021-12-24 | P/FBW/MDS/1070475/2022 | 2022-01-03
1094 | VISHN2 | VISHN2 | Thanjavur | Trichy |  | ROTN | Summit | I-TN-TRVY-ENB-9020 | SR-TN000731 |  | On Air | 2022-02-10 | VISHN2 | 4G_FD900_VISHN2 | 4G_FD2100_VISHN2 | 4G_TD_VISHN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625495 | 2021-12-23 | P/FVC/MDS/1070344/2022 | 2022-01-03 | ST202112626359 | 2021-12-24 | P/FVC/MDS/1070217/2021 | 2021-12-30 |  |  |  |  | ST202112627156 | 2021-12-24 | P/FBW/MDS/1070476/2022 | 2022-01-03
1095 | TIVR38 | TIVR38 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TTPN-ENB-9033 | SR-TN000726 |  | On Air | 2022-02-10 | TIVR38 | 4G_FD900_TIVR38 | 4G_FD2100_TIVR38 | 4G_TD_TIVR38 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625496 | 2021-12-23 | P/FVC/MDS/1070345/2022 | 2022-01-03 | ST202112626360 | 2021-12-24 | P/FVC/MDS/1070218/2021 | 2021-12-30 |  |  |  |  | ST202112627157 | 2021-12-24 | P/FBW/MDS/1070477/2022 | 2022-01-03
1096 | POTHA2 | POTHA2 | Madurai | Madurai |  | ROTN | Summit | I-TN-USMP-ENB-9047 | SR-TN000734 |  | On Air | 2022-02-10 | POTHA2 | 4G_FD900_POTHA2 | 4G_FD2100_POTHA2 | 4G_TD_POTHA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625505 | 2021-12-23 | P/FVC/MDS/1070348/2022 | 2022-01-03 | ST202112626365 | 2021-12-24 | P/FVC/MDS/1070221/2021 | 2021-12-30 |  |  |  |  | ST202112627161 | 2021-12-24 | P/FBW/MDS/1070480/2022 | 2022-01-03
1097 | VIRU03 | VIRU03 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-VDCM-ENB-9058 | SR-TN000732 |  | On Air | 2022-02-10 | VIRU03 | 4G_FD900_VIRU03 | 4G_FD2100_VIRU03 | 4G_TD_VIRU03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625512 | 2021-12-23 | P/FVC/MDS/1070349/2022 | 2022-01-03 | ST202112626372 | 2021-12-24 | P/FVC/MDS/1070222/2021 | 2021-12-30 |  |  |  |  | ST202112627162 | 2021-12-24 | P/FBW/MDS/1070481/2022 | 2022-01-03
1098 | VIRU04 | VIRU04 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-VDCM-ENB-9069 | SR-TN000730 |  | On Air | 2022-02-10 | VIRU04 | 4G_FD900_VIRU04 | 4G_FD2100_VIRU04 | 4G_TD_VIRU04 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625523 | 2021-12-23 | P/FVC/MDS/1070350/2022 | 2022-01-03 | ST202112626373 | 2021-12-24 | P/FVC/MDS/1070223/2021 | 2021-12-30 |  |  |  |  | ST202112627163 | 2021-12-24 | P/FBW/MDS/1070482/2022 | 2022-01-03
1099 | MAHAP2 | MAHAP2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-VPPM-ENB-9083 | SR-TN000737 |  | On Air | 2022-02-10 | MAHAP2 | 4G_FD900_MAHAP2 | 4G_FD2100_MAHAP2 | 4G_TD_MAHAP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625526 | 2021-12-23 | P/FVC/MDS/1070353/2022 | 2022-01-03 | ST202112626439 | 2021-12-24 | P/FVC/MDS/1070226/2021 | 2021-12-30 |  |  |  |  | ST202112627169 | 2021-12-24 | P/FBW/MDS/1070485/2022 | 2022-01-03
1100 | SOLAS2 | SOLAS2 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-VKMP-ENB-9024 | SR-TN000740 |  | On Air | 2022-02-10 | SOLAS2 | 4G_FD900_SOLAS2 | 4G_FD2100_SOLAS2 | 4G_TD_SOLAS2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625633 | 2021-12-23 | P/FVC/MDS/1070356/2022 | 2022-01-03 | ST202112626445 | 2021-12-24 | P/FVC/MDS/1070229/2021 | 2021-12-30 |  |  |  |  | ST202112627181 | 2021-12-24 | P/FVC/MDS/1070525/2022 | 2022-01-03
1101 | PITVI2 | PITVI2 | Thoothukkudi | Madurai |  | ROTN | ATC | TN/TH/AT/22936 | - |  | On Air | 2022-02-11 | PITVI2 | 4G_FD900_PITVI2 | 4G_FD2100_PITVI2 | 4G_TD_PITVI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093163 | 2022-04-07 | P/FVC/MDS/1078388/2022 | 2022-04-21 | ST202204093150 | 2022-04-07 | P/FVC/MDS/1078347/2022 | 2022-04-21 | ST202209444080 | 2022-09-19 | P/FVC/MDS/1098035/2022 | 2022-09-27 | ST202204093050 | 2022-04-06 | P/FBW/MDS/1078290/2022 | 2022-04-21
1102 | MDU529 | MDU529 | Madurai | Madurai |  | ROTN | Summit | I-TN-TRMG-ENB-9050 | SR-TN000748 |  | On Air | 2022-02-10 | MDU529 | 4G_FD900_MDU529 | 4G_FD2100_MDU529 | 4G_TD_MDU529 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110550222 | 2021-10-05 | P/FVC/MDS/1063565/2021 | 2021-10-20 | ST202110554038 | 2021-10-08 | P/FVC/MDS/1063589/2021 | 2021-10-20 |  |  |  |  | ST202110554905 | 2021-10-08 | P/FBW/MDS/1063673/2021 | 2021-10-22
1103 | PKPUR2 | PKPUR2 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | PKPUR2 | 4G_FD900_PKPUR2 | 4G_FD2100_PKPUR2 | 4G_TD_PKPUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111682 | 2022-04-20 | P/FVC/MDS/1078934/2022 | 2022-05-02 | ST202204110010 | 2022-04-19 | P/FVC/MDS/1078996/2022 | 2022-05-03 |  |  |  |  | ST202204109562 | 2022-04-19 | P/FVC/MDS/1078892/2022 | 2022-05-02
1104 | VANJU2 | VANJU2 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | VANJU2 | 4G_FD900_VANJU2 | 4G_FD2100_VANJU2 | 4G_TD_VANJU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048062 | 2022-02-18 | P/FVC/MDS/1074969/2022 | 2022-02-28 | ST202202049399 | 2022-02-19 | P/FVC/MDS/1074914/2022 | 2022-02-28 |  |  |  |  | ST202202048598 | 2022-02-18 | P/FBW/MDS/1074855/2022 | 2022-02-28
1105 | VALAT2 | VALAT2 | Vellore | Vellore |  | ROTN | Summit | I-TN-GDTM-ENB-9063 | SR-TN000749 |  | On Air | 2022-02-11 | VALAT2 | 4G_FD900_VALAT2 | 4G_FD2100_VALAT2 | 4G_TD_VALAT2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625664 | 2021-12-23 | P/FVC/MDS/1070396/2022 | 2022-01-03 | ST202112626482 | 2021-12-24 | P/FVC/MDS/1070240/2021 | 2021-12-30 |  |  |  |  | ST202112627193 | 2021-12-24 | P/FVC/MDS/1070534/2022 | 2022-01-03
1106 | ALKLM3 | ALKLM3 | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-SVKS-ENB-9032 | SR-TN000754 |  | On Air | 2022-02-10 | ALKLM3 | 4G_FD900_ALKLM3 | 4G_FD2100_ALKLM3 | 4G_TD_ALKLM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625672 | 2021-12-23 | P/FVC/MDS/1070398/2022 | 2022-01-03 | ST202112626484 | 2021-12-24 | P/FVC/MDS/1070242/2021 | 2021-12-30 |  |  |  |  | ST202112627195 | 2021-12-24 | P/FVC/MDS/1070536/2022 | 2022-01-03
1107 | PNGRM9 | PNGRM9 | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-DMPI-ENB-9046 | SR-TN000759 |  | On Air | 2022-02-11 | PNGRM9 | 4G_FD900_PNGRM9 | 4G_FD2100_PNGRM9 | 4G_TD_PNGRM9 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202112625687 | 2021-12-23 | P/FVC/MDS/1070405/2022 | 2022-01-03 | ST202112626491 | 2021-12-24 | P/FVC/MDS/1070249/2021 | 2021-12-30 |  |  |  |  | ST202112627213 | 2021-12-24 | P/FVC/MDS/1070544/2022 | 2022-01-03
1108 | IRUUR2 | IRUUR2 | Perambalur | Trichy |  | ROTN | Indus | IN-3121100 | R/NN-642367 |  | On Air | 2022-02-11 | IRUUR2 | 4G_FD900_IRUUR2 | 4G_FD2100_IRUUR2 | 4G_TD_IRUUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048073 | 2022-02-18 | P/FVC/MDS/1074976/2022 | 2022-02-28 | ST202202049406 | 2022-02-19 | P/FVC/MDS/1074921/2022 | 2022-02-28 |  |  |  |  | ST202202048621 | 2022-02-18 | P/FBW/MDS/1074862/2022 | 2022-02-28
1109 | KOTAB2 | KOTAB2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-MAPE-ENB-9001 | SR-TN000777 |  | On Air | 2022-02-10 | KOTAB2 | 4G_FD900_KOTAB2 | 4G_FD2100_KOTAB2 | 4G_TD_KOTAB2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625715 | 2021-12-23 | P/FVC/MDS/1070417/2022 | 2022-01-03 | ST202112626507 | 2021-12-24 | P/FVC/MDS/1070261/2021 | 2021-12-30 |  |  |  |  | ST202112627223 | 2021-12-24 | P/FBW/MDS/1070524/2022 | 2022-01-03
1110 | BAGLR2 | BAGLR2 | Krishnagiri | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | BAGLR2 | 4G_FD900_BAGLR2 | 4G_FD2100_BAGLR2 | 4G_TD_BAGLR2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202201022602 | 2022-01-28 | P/FVC/MDS/1072954/2022 | 2022-02-04 | ST202201025274 | 2022-01-31 | P/FVC/MDS/1074394/2022 | 2022-02-22 |  |  |  |  | ST202201025385 | 2022-01-31 | P/FBW/MDS/1074334/2022 | 2022-02-22
1111 | SOSMR2 | SOSMR2 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | SOSMR2 | 4G_FD900_SOSMR2 | 4G_FD2100_SOSMR2 | 4G_TD_SOSMR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025208 | 2022-01-31 | P/FVC/MDS/1074452/2022 | 2022-02-22 | ST202201025314 | 2022-01-31 | P/FVC/MDS/1074395/2022 | 2022-02-22 |  |  |  |  | ST202201025386 | 2022-01-31 | P/FBW/MDS/1074335/2022 | 2022-02-22
1112 | PALPM2 | PALPM2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22949 | - |  | On Air | 2022-02-07 | PALPM2 | 4G_FD900_PALPM2 | 4G_FD2100_PALPM2 | 4G_TD_PALPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048033 | 2022-02-18 | P/FVC/MDS/1074964/2022 | 2022-02-28 | ST202202049394 | 2022-02-19 | P/FVC/MDS/1074909/2022 | 2022-02-28 |  |  |  |  | ST202202048590 | 2022-02-18 | P/FBW/MDS/1074850/2022 | 2022-02-28
1113 | KONDM2 | KONDM2 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/22950 | - |  | On Air | 2022-02-11 | KONDM2 | 4G_FD900_KONDM2 | 4G_FD2100_KONDM2 | 4G_TD_KONDM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048068 | 2022-02-18 | P/FVC/MDS/1074973/2022 | 2022-02-28 | ST202202049403 | 2022-02-19 | P/FVC/MDS/1074918/2022 | 2022-02-28 |  |  |  |  | ST202202048611 | 2022-02-18 | P/FBW/MDS/1074859/2022 | 2022-02-28
1114 | VLTPU2 | VLTPU2 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/22951 | - |  | On Air | 2022-02-11 | VLTPU2 | 4G_FD900_VLTPU2 | 4G_FD2100_VLTPU2 | 4G_TD_VLTPU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048071 | 2022-02-18 | P/FVC/MDS/1074974/2022 | 2022-02-28 | ST202202049404 | 2022-02-19 | P/FVC/MDS/1074919/2022 | 2022-02-28 |  |  |  |  | ST202202048612 | 2022-02-18 | P/FBW/MDS/1074860/2022 | 2022-02-28
1115 | THAKU3 | THAKU3 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22952 | - |  | On Air | 2022-02-07 | THAKU3 | 4G_FD900_THAKU3 | 4G_FD2100_THAKU3 | 4G_TD_THAKU3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025216 | 2022-01-31 | P/FVC/MDS/1074455/2022 | 2022-02-22 | ST202201025326 | 2022-01-31 | P/FVC/MDS/1074398/2022 | 2022-02-22 |  |  |  |  | ST202201025394 | 2022-01-31 | P/FBW/MDS/1074338/2022 | 2022-02-22
1116 | THAKU4 | THAKU4 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22953 | - |  | On Air | 2022-02-07 | THAKU4 | 4G_FD900_THAKU4 | 4G_FD2100_THAKU4 | 4G_TD_THAKU4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025217 | 2022-01-31 | P/FVC/MDS/1074456/2022 | 2022-02-22 | ST202201025327 | 2022-01-31 | P/FVC/MDS/1074399/2022 | 2022-02-22 |  |  |  |  | ST202201025395 | 2022-01-31 | P/FBW/MDS/1074339/2022 | 2022-02-22
1117 | VLRM75 | VLRM75 | Viluppuram | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | VLRM75 | 4G_FD900_VLRM75 | 4G_FD2100_VLRM75 | 4G_TD_VLRM75 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048136 | 2022-02-18 | P/FVC/MDS/1074979/2022 | 2022-02-28 | ST202202049409 | 2022-02-19 | P/FVC/MDS/1074924/2022 | 2022-02-28 |  |  |  |  | ST202202048629 | 2022-02-18 | P/FBW/MDS/1074865/2022 | 2022-02-28
1118 | THIVM2 | THIVM2 | Viluppuram | Trichy |  | ROTN | Ascend | - | - |  | SR | 2022-02-11 | THIVM2 | 4G_FD900_THIVM2 | 4G_FD2100_THIVM2 | 4G_TD_THIVM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048134 | 2022-02-18 | P/FVC/MDS/1074977/2022 | 2022-02-28 | ST202202049407 | 2022-02-19 | P/FVC/MDS/1074922/2022 | 2022-02-28 |  |  |  |  | ST202202048622 | 2022-02-18 | P/FBW/MDS/1074863/2022 | 2022-02-28
1119 | TIVR45 | TIVR45 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | TIVR45 | 4G_FD900_TIVR45 | 4G_FD2100_TIVR45 | 4G_TD_TIVR45 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048150 | 2022-02-18 | P/FVC/MDS/1074980/2022 | 2022-02-28 | ST202202049410 | 2022-02-19 | P/FVC/MDS/1074925/2022 | 2022-02-28 |  |  |  |  | ST202202048630 | 2022-02-18 | P/FBW/MDS/1074866/2022 | 2022-02-28
1120 | TIVR49 | TIVR49 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-11 | TIVR49 | 4G_FD900_TIVR49 | 4G_FD2100_TIVR49 | 4G_TD_TIVR49 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048135 | 2022-02-18 | P/FVC/MDS/1074978/2022 | 2022-02-28 | ST202202049408 | 2022-02-19 | P/FVC/MDS/1074923/2022 | 2022-02-28 |  |  |  |  | ST202202048623 | 2022-02-18 | P/FBW/MDS/1074864/2022 | 2022-02-28
1121 | ARAK44 | ARAK44 |  |  |  | ROTN | Indus | IN-3103028 | R/NN-638783 |  |  | 2022-02-10 | ARAK44 | 4G_FD900_ARAK44 | 4G_FD2100_ARAK44 | 4G_TD_ARAK44 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202048072 | 2022-02-18 | P/FVC/MDS/1074975/2022 | 2022-02-28 | ST202202049405 | 2022-02-19 | P/FVC/MDS/1074920/2022 | 2022-02-28 | ST202202049475 | 2022-02-19 | P/FVC/MDS/1074793/2022 | 2022-02-25 | ST202202048613 | 2022-02-18 | P/FBW/MDS/1074861/2022 | 2022-02-28
1122 | NERK19 | NERK19 |  |  |  | CHN |  |  |  |  | Drop(HPSC) |  | NERK19 | 4G_FD900_NERK19 | 4G_FD2100_NERK19 | 4G_TD_NERK19 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048152 | 2022-02-18 | P/FVC/MDS/1074982/2022 | 2022-02-28 | ST202202049412 | 2022-02-19 | P/FVC/MDS/1074927/2022 | 2022-02-28 | ST202106358265 | 2021-06-23 | P/FVC/MDS/1055862/2021 | 2021-09-04 | ST202202048635 | 2022-02-18 | P/FBW/MDS/1074868/2022 | 2022-02-28
1123 | ATHAN2 | ATHAN2 |  |  |  | CHN | Summit | I-TN-CHNN-ENB-2861 | SR-TN000685 |  | On air | 2022-02-19 | ATHAN2 | 4G_FD900_ATHAN2 | 4G_FD2100_ATHAN2 | 4G_TD_ATHAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623608 | 2021-12-21 | P/FVC/MDS/1070066/2021 | 2021-12-29 | ST202112626102 | 2021-12-23 | P/FVC/MDS/1069740/2021 | 2021-12-28 | ST202204095114 | 2022-04-08 | P/FVC/MDS/1078405/2022 | 2022-04-21 | ST202112626712 | 2021-12-24 | P/FBW/MDS/1070173/2021 | 2021-12-29
1124 | ALAGA2 | ALAGA2 | Tiruchirappalli | Trichy |  | ROTN | Summit | I-TN-SRGM-ENB-9039 | SR-TN000560 |  | On Air | 2022-02-15 | ALAGA2 | 4G_FD900_ALAGA2 | 4G_FD2100_ALAGA2 | 4G_TD_ALAGA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610887 | 2021-12-10 | P/FVC/MDS/1069083/2021 | 2021-12-17 | ST202112604904 | 2021-12-07 | P/FVC/MDS/1068829/2021 | 2021-12-15 |  |  |  |  | ST202112609416 | 2021-12-10 | P/FBW/MDS/1068793/2021 | 2021-12-15
1125 | APTN14 | APTN14 | Thanjavur | Trichy |  | ROTN | INDUS | IN-1662683 | R/NN-563444 |  | On Air | 2021-02-15 | APTN14 | 4G_FD900_APTN14 | 4G_FD2100_APTN14 | 4G_TD_APTN14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106363267 | 2021-06-26 | P/FVC/MDS/1050127/2021 | 2021-08-09 | ST202103073688 | 2021-03-01 | P/FVC/MDS/1012462/2021 | 2021-03-13 |  |  |  |  | ST202102071583 | 2021-02-27 | P/FBW/MDS/1012242/2021 | 2021-03-13
1126 | PDY330 | PDY330 | Puducherry | Trichy |  | ROTN | Indus | IN-3122679 | R/NN-644186 |  | SR | 2022-02-15 | PDY330 | 4G_FD900_PDY330 | 4G_FD2100_PDY330 | 4G_TD_PDY330 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048179 | 2022-02-18 | P/FVC/MDS/1074993/2022 | 2022-02-28 | ST202202049423 | 2022-02-19 | P/FVC/MDS/1074938/2022 | 2022-02-28 | ST202107388503 | 2021-07-19 | P/FVC/MDS/1056687/2021 | 2021-09-08 | ST202202048667 | 2022-02-18 | P/FBW/MDS/1074879/2022 | 2022-02-28
1127 | NAGALT | NAGALT | Dindigul | Coimbatore |  | ROTN | Airtel | - | - |  | On Air | 2022-02-19 | NAGALT | 4G_FD900_NAGALT | 4G_FD2100_NAGALT | 4G_TD_NAGALT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048181 | 2022-02-18 | P/FVC/MDS/1074995/2022 | 2022-02-28 | ST202202049425 | 2022-02-19 | P/FVC/MDS/1074940/2022 | 2022-02-28 |  |  |  |  | ST202202048671 | 2022-02-18 | P/FBW/MDS/1074881/2022 | 2022-02-28
1128 | KALGAM | KALGAM | Thanjavur | Trichy |  | ROTN | Summit | I-TN-PRVR-ENB-9022 | SR-TN000658 |  | On Air | 2022-02-19 | KALGAM | 4G_FD900_KALGAM | 4G_FD2100_KALGAM | 4G_TD_KALGAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052218 | 2022-02-22 | P/FVC/MDS/1076295/2022 | 2022-03-13 | ST202202054445 | 2022-02-24 | P/FVC/MDS/1076190/2022 | 2022-03-13 | ST202202049497 | 2022-02-19 | P/FVC/MDS/1074810/2022 | 2022-02-25 | ST202202053472 | 2022-02-23 | P/FBW/MDS/1076091/2022 | 2022-03-13
1129 | HRUR10 | HRUR10 | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-HRUR-ENB-9042 | SR-TN000494 |  | On Air | 2022-02-15 | HRUR10 | 4G_FD900_HRUR10 | 4G_FD2100_HRUR10 | 4G_TD_HRUR10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559419 | 2021-10-14 | P/FVC/MDS/1063741/2021 | 2021-10-22 | ST202110560212 | 2021-10-14 | P/FVC/MDS/1063717/2021 | 2021-10-22 |  |  |  |  | ST202110560331 | 2021-10-14 | P/FVC/MDS/1063692/2021 | 2021-10-22
1130 | SIVRAM | SIVRAM | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-PDKK-ENB-9010 | SR-TN000543 |  | On Air | 2022-02-15 | SIVRAM | 4G_FD900_SIVRAM | 4G_FD2100_SIVRAM | 4G_TD_SIVRAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574156 | 2021-10-28 | P/FVC/MDS/1065854/2021 | 2021-11-16 | ST202110573026 | 2021-10-27 | P/FVC/MDS/1065727/2021 | 2021-11-16 |  |  |  |  | ST202110572520 | 2021-10-27 | P/FBW/MDS/1067907/2021 | 2021-12-08
1131 | KANAPA | KANAPA | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-UTHN-ENB-9049 | SR-TN000546 |  | On Air | 2022-02-15 | KANAPA | 4G_FD900_KANAPA | 4G_FD2100_KANAPA | 4G_TD_KANAPA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574157 | 2021-10-28 | P/FVC/MDS/1065855/2021 | 2021-11-16 | ST202110573027 | 2021-10-27 | P/FVC/MDS/1065728/2021 | 2021-11-16 |  |  |  |  | ST202110572521 | 2021-10-27 | P/FBW/MDS/1067908/2021 | 2021-12-08
1132 | POYYAM | POYYAM | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-IPPR-ENB-9041 | SR-TN000663 |  | On Air | 2022-02-15 | POYYAM | 4G_FD900_POYYAM | 4G_FD2100_POYYAM | 4G_TD_POYYAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111595149 | 2021-11-19 | P/FVC/MDS/1067069/2021 | 2021-12-01 | ST202111585326 | 2021-11-09 | P/FVC/MDS/1068124/2021 | 2021-12-08 |  |  |  |  | ST202111595308 | 2021-11-19 | P/FBW/MDS/1067045/2021 | 2021-12-01
1133 | KOTHA2 | KOTHA2 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-ARTG-ENB-9031 | SR-TN000659 |  | On Air | 2022-02-15 | KOTHA2 | 4G_FD900_KOTHA2 | 4G_FD2100_KOTHA2 | 4G_TD_KOTHA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111595152 | 2021-11-19 | P/FVC/MDS/1067072/2021 | 2021-12-01 | ST202111595246 | 2021-11-19 | P/FVC/MDS/1067059/2021 | 2021-12-01 |  |  |  |  | ST202111595311 | 2021-11-19 | P/FBW/MDS/1067048/2021 | 2021-12-01
1134 | VELAL2 | VELAL2 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-GDRV-ENB-9022 | SR-TN000681 |  | On Air | 2022-02-19 | VELAL2 | 4G_FD900_VELAL2 | 4G_FD2100_VELAL2 | 4G_TD_VELAL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623553 | 2021-12-21 | P/FVC/MDS/1070061/2021 | 2021-12-29 | ST202112625942 | 2021-12-23 | P/FVC/MDS/1069735/2021 | 2021-12-28 |  |  |  |  | ST202112626694 | 2021-12-24 | P/FBW/MDS/1070168/2021 | 2021-12-29
1135 | VAIDY2 | VAIDY2 | Thanjavur | Trichy |  | ROTN | Indus | IN-1258123 | R/RES-508890 |  | On Air | 2022-02-15 | VAIDY2 | 4G_FD900_VAIDY2 | 4G_FD2100_VAIDY2 | 4G_TD_VAIDY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201007706 | 2022-01-11 | P/FVC/MDS/1071647/2022 | 2022-01-20 | ST202201008512 | 2022-01-12 | P/FVC/MDS/1071567/2022 | 2022-01-20 |  |  |  |  | ST202201007919 | 2022-01-11 | P/FBW/MDS/1071486/2022 | 2022-01-20
1136 | KAGIT2 | KAGIT2 | Karur | Coimbatore |  | ROTN | Indus | IN-3114422 | R/NN-640057 |  |  | 2022-02-15 | KAGIT2 | 4G_FD900_KAGIT2 | 4G_FD2100_KAGIT2 | 4G_TD_KAGIT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048163 | 2022-02-18 | P/FVC/MDS/1074984/2022 | 2022-02-28 | ST202202049414 | 2022-02-19 | P/FVC/MDS/1074929/2022 | 2022-02-28 |  |  |  |  | ST202202048644 | 2022-02-18 | P/FBW/MDS/1074870/2022 | 2022-02-28
1137 | NEIVI2 | NEIVI2 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1258128 | R/RES-508892 |  | On Air | 2022-02-15 | NEIVI2 | 4G_FD900_NEIVI2 | 4G_FD2100_NEIVI2 | 4G_TD_NEIVI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201007713 | 2022-01-11 | P/FVC/MDS/1071650/2022 | 2022-01-20 | ST202201008519 | 2022-01-12 | P/FVC/MDS/1071570/2022 | 2022-01-20 |  |  |  |  | ST202201007925 | 2022-01-11 | P/FBW/MDS/1071489/2022 | 2022-01-20
1138 | ARUNG2 | ARUNG2 | Viluppuram | Trichy |  | ROTN | Indus | IN-1074924 | R/RES-508893 |  | On Air | 2022-02-15 | ARUNG2 | 4G_FD900_ARUNG2 | 4G_FD2100_ARUNG2 | 4G_TD_ARUNG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112623511 | 2021-12-21 | P/FVC/MDS/1070055/2021 | 2021-12-29 | ST202112625913 | 2021-12-23 | P/FVC/MDS/1069729/2021 | 2021-12-28 |  |  |  |  | ST202112626687 | 2021-12-24 | P/FBW/MDS/1070162/2021 | 2021-12-29
1139 | MAMPT2 | MAMPT2 | Sivaganga | Madurai |  | ROTN | ATC | TN/SI/AT/22931 | - |  | On Air | 2022-02-15 | MAMPT2 | 4G_FD900_MAMPT2 | 4G_FD2100_MAMPT2 | 4G_TD_MAMPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048170 | 2022-02-18 | P/FVC/MDS/1074988/2022 | 2022-02-28 | ST202202049418 | 2022-02-19 | P/FVC/MDS/1074933/2022 | 2022-02-28 |  |  |  |  | ST202202048653 | 2022-02-18 | P/FBW/MDS/1074874/2022 | 2022-02-28
1140 | KAHIY2 | KAHIY2 | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-TRGB-ENB-9036 | SR-TN000712 |  | On Air | 2022-02-19 | KAHIY2 | 4G_FD900_KAHIY2 | 4G_FD2100_KAHIY2 | 4G_TD_KAHIY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625488 | 2021-12-23 | P/FVC/MDS/1070342/2022 | 2022-01-03 | ST202112626340 | 2021-12-24 | P/FVC/MDS/1070215/2021 | 2021-12-30 |  |  |  |  | ST202112627154 | 2021-12-24 | P/FBW/MDS/1070474/2022 | 2022-01-03
1141 | TIRNP2 | TIRNP2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-VPPM-ENB-9089 | SR-TN000735 |  | On Air | 2022-02-15 | TIRNP2 | 4G_FD900_TIRNP2 | 4G_FD2100_TIRNP2 | 4G_TD_TIRNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625631 | 2021-12-23 | P/FVC/MDS/1070354/2022 | 2022-01-03 | ST202112626440 | 2021-12-24 | P/FVC/MDS/1070227/2021 | 2021-12-30 |  |  |  |  | ST202112627176 | 2021-12-24 | P/FBW/MDS/1070486/2022 | 2022-01-03
1142 | SIRUV2 | SIRUV2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-KLKC-ENB-9068 | SR-TN000751 |  | On Air | 2022-02-15 | SIRUV2 | 4G_FD900_SIRUV2 | 4G_FD2100_SIRUV2 | 4G_TD_SIRUV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625636 | 2021-12-23 | P/FVC/MDS/1070358/2022 | 2022-01-03 | ST202112626447 | 2021-12-24 | P/FVC/MDS/1070231/2021 | 2021-12-30 |  |  |  |  | ST202112627182 | 2021-12-24 | P/FVC/MDS/1070526/2022 | 2022-01-03
1143 | NAGAK2 | NAGAK2 | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-VDRY-ENB-9033 | SR-TN000766 |  | On Air | 2022-02-15 | NAGAK2 | 4G_FD900_NAGAK2 | 4G_FD2100_NAGAK2 | 4G_TD_NAGAK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052197 | 2022-02-22 | P/FVC/MDS/1076287/2022 | 2022-03-13 | ST202202054419 | 2022-02-24 | P/FVC/MDS/1076182/2022 | 2022-03-13 |  |  |  |  | ST202202053464 | 2022-02-23 | P/FBW/MDS/1076083/2022 | 2022-03-13
1144 | TIRYM2 | TIRYM2 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-TRMY-ENB-9042 | SR-TN000747 |  | On Air | 2022-02-15 | TIRYM2 | 4G_FD900_TIRYM2 | 4G_FD2100_TIRYM2 | 4G_TD_TIRYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625648 | 2021-12-23 | P/FVC/MDS/1070390/2022 | 2022-01-03 | ST202112626469 | 2021-12-24 | P/FVC/MDS/1070234/2021 | 2021-12-30 |  |  |  |  | ST202112627185 | 2021-12-24 | P/FVC/MDS/1070528/2022 | 2022-01-03
1145 | KANKA2 | KANKA2 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-ARTG-ENB-9014 | SR-TN000745 |  | On Air | 2022-02-15 | KANKA2 | 4G_FD900_KANKA2 | 4G_FD2100_KANKA2 | 4G_TD_KANKA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625655 | 2021-12-23 | P/FVC/MDS/1070393/2022 | 2022-01-03 | ST202112626476 | 2021-12-24 | P/FVC/MDS/1070237/2021 | 2021-12-30 |  |  |  |  | ST202112627188 | 2021-12-24 | P/FVC/MDS/1070531/2022 | 2022-01-03
1146 | MUTDA2 | MUTDA2 | Pudukkottai | Trichy |  | ROTN | Summit | I-TN-KLTR-ENB-9049 | SR-TN000750 |  | On Air | 2022-02-15 | MUTDA2 | 4G_FD900_MUTDA2 | 4G_FD2100_MUTDA2 | 4G_TD_MUTDA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625660 | 2021-12-23 | P/FVC/MDS/1070394/2022 | 2022-01-03 | ST202112626479 | 2021-12-24 | P/FVC/MDS/1070238/2021 | 2021-12-30 |  |  |  |  | ST202112627189 | 2021-12-24 | P/FVC/MDS/1070532/2022 | 2022-01-03
1147 | MOOKK2 | MOOKK2 | Dharmapuri | Vellore |  | ROTN | Summit | I-TN-DMPI-ENB-9049 | SR-TN000767 |  | On Air | 2022-02-15 | MOOKK2 | 4G_FD900_MOOKK2 | 4G_FD2100_MOOKK2 | 4G_TD_MOOKK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625684 | 2021-12-23 | P/FVC/MDS/1070402/2022 | 2022-01-03 | ST202112626488 | 2021-12-24 | P/FVC/MDS/1070246/2021 | 2021-12-30 |  |  |  |  | ST202112627205 | 2021-12-24 | P/FVC/MDS/1070540/2022 | 2022-01-03
1148 | KAPPA2 | KAPPA2 | The Nilgiris | Coimbatore |  | ROTN | Summit | I-TN-OTCM-ENB-0046 | SR-TN000779 |  | On Air | 2022-02-15 | KAPPA2 | 4G_FD900_KAPPA2 | 4G_FD2100_KAPPA2 | 4G_TD_KAPPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112625709 | 2021-12-23 | P/FVC/MDS/1070416/2022 | 2022-01-03 | ST202112626506 | 2021-12-24 | P/FVC/MDS/1070260/2021 | 2021-12-30 |  |  |  |  | ST202112627222 | 2021-12-24 | P/FBW/MDS/1070523/2022 | 2022-01-03
1149 | THAKU2 | THAKU2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22944 | - |  | On Air | 2022-02-15 | THAKU2 | 4G_FD900_THAKU2 | 4G_FD2100_THAKU2 | 4G_TD_THAKU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085638 | 2022-03-29 | P/FVC/MDS/1078072/2022 | 2022-04-14 | ST202203084677 | 2022-03-29 | P/FVC/MDS/1077973/2022 | 2022-04-14 |  |  |  |  | ST202203082657 | 2022-03-26 | P/FBW/MDS/1077811/2022 | 2022-04-14
1150 | TNJ177 | TNJ177 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-15 | TNJ177 | 4G_FD900_TNJ177 | 4G_FD2100_TNJ177 | 4G_TD_TNJ177 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048177 | 2022-02-18 | P/FVC/MDS/1074991/2022 | 2022-02-28 | ST202202049421 | 2022-02-19 | P/FVC/MDS/1074936/2022 | 2022-02-28 |  |  |  |  | ST202202048660 | 2022-02-18 | P/FBW/MDS/1074877/2022 | 2022-02-28
1151 | ORIKI2 | ORIKI2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | On Air | 2022-02-15 | ORIKI2 | 4G_FD900_ORIKI2 | 4G_FD2100_ORIKI2 | 4G_TD_ORIKI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048216 | 2022-02-18 | P/FVC/MDS/1075010/2022 | 2022-02-28 | ST202202049441 | 2022-02-19 | P/FVC/MDS/1074956/2022 | 2022-02-28 |  |  |  |  | ST202202048697 | 2022-02-18 | P/FBW/MDS/1074898/2022 | 2022-02-28
1152 | NLPYM2 | NLPYM2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22977 | - |  | On Air | 2022-02-15 | NLPYM2 | 4G_FD900_NLPYM2 | 4G_FD2100_NLPYM2 | 4G_TD_NLPYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048168 | 2022-02-18 | P/FVC/MDS/1074986/2022 | 2022-02-28 | ST202202049416 | 2022-02-19 | P/FVC/MDS/1074931/2022 | 2022-02-28 |  |  |  |  | ST202202048646 | 2022-02-18 | P/FBW/MDS/1074872/2022 | 2022-02-28
1153 | KUMB89 | KUMB89 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-15 | KUMB89 | 4G_FD900_KUMB89 | 4G_FD2100_KUMB89 | 4G_TD_KUMB89 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048178 | 2022-02-18 | P/FVC/MDS/1074992/2022 | 2022-02-28 | ST202202049422 | 2022-02-19 | P/FVC/MDS/1074937/2022 | 2022-02-28 |  |  |  |  | ST202202048661 | 2022-02-18 | P/FBW/MDS/1074878/2022 | 2022-02-28
1154 | KRIPT6 | KRIPT6 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/22966 | - |  | On Air | 2022-02-15 | KRIPT6 | 4G_FD900_KRIPT6 | 4G_FD2100_KRIPT6 | 4G_TD_KRIPT6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052188 | 2022-02-22 | P/FVC/MDS/1076285/2022 | 2022-03-13 | ST202202049446 | 2022-02-19 | P/FVC/MDS/1074960/2022 | 2022-02-28 |  |  |  |  | ST202202053463 | 2022-02-23 | P/FBW/MDS/1076082/2022 | 2022-03-13
1155 | PKLM14 | PKLM14 | Theni | Madurai |  | ROTN | ATC | TN/TH/AT/22967 | - |  | On Air | 2022-02-15 | PKLM14 | 4G_FD900_PKLM14 | 4G_FD2100_PKLM14 | 4G_TD_PKLM14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048180 | 2022-02-18 | P/FVC/MDS/1074994/2022 | 2022-02-28 | ST202202049424 | 2022-02-19 | P/FVC/MDS/1074939/2022 | 2022-02-28 |  |  |  |  | ST202202048670 | 2022-02-18 | P/FBW/MDS/1074880/2022 | 2022-02-28
1156 | TAPKD2 | TAPKD2 | Theni | Madurai |  | ROTN | ATC | TN/TH/AT/22968 | - |  | On Air | 2022-02-15 | TAPKD2 | 4G_FD900_TAPKD2 | 4G_FD2100_TAPKD2 | 4G_TD_TAPKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056715 | 2022-02-27 | P/FVC/MDS/1076458/2022 | 2022-03-13 | ST202202055882 | 2022-02-26 | P/FVC/MDS/1075674/2022 | 2022-03-10 |  |  |  |  | ST202202056467 | 2022-02-26 | P/FBW/MDS/1075577/2022 | 2022-03-10
1157 | PGLPT2 | PGLPT2 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22970 | - |  | On Air | 2022-02-15 | PGLPT2 | 4G_FD900_PGLPT2 | 4G_FD2100_PGLPT2 | 4G_TD_PGLPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048169 | 2022-02-18 | P/FVC/MDS/1074987/2022 | 2022-02-28 | ST202202049417 | 2022-02-19 | P/FVC/MDS/1074932/2022 | 2022-02-28 |  |  |  |  | ST202202048652 | 2022-02-18 | P/FBW/MDS/1074873/2022 | 2022-02-28
1158 | SLM409 | SLM409 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22972 | - |  | On Air | 2022-02-15 | SLM409 | 4G_FD900_SLM409 | 4G_FD2100_SLM409 | 4G_TD_SLM409 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052183 | 2022-02-22 | P/FVC/MDS/1076282/2022 | 2022-03-13 | ST202202049442 | 2022-02-19 | P/FVC/MDS/1074957/2022 | 2022-02-28 |  |  |  |  | ST202202048699 | 2022-02-18 | P/FBW/MDS/1074899/2022 | 2022-02-28
1159 | SLM410 | SLM410 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22973 | - |  | On Air | 2022-02-15 | SLM410 | 4G_FD900_SLM410 | 4G_FD2100_SLM410 | 4G_TD_SLM410 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052187 | 2022-02-22 | P/FVC/MDS/1076284/2022 | 2022-03-13 | ST202202049444 | 2022-02-19 | P/FVC/MDS/1074959/2022 | 2022-02-28 |  |  |  |  | ST202202048677 | 2022-02-18 | P/FBW/MDS/1074885/2022 | 2022-02-28
1160 | PAMAI2 | PAMAI2 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-15 | PAMAI2 | 4G_FD900_PAMAI2 | 4G_FD2100_PAMAI2 | 4G_TD_PAMAI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048215 | 2022-02-18 | P/FVC/MDS/1075009/2022 | 2022-02-28 | ST202202049440 | 2022-02-19 | P/FVC/MDS/1074955/2022 | 2022-02-28 |  |  |  |  | ST202202048694 | 2022-02-18 | P/FBW/MDS/1074897/2022 | 2022-02-28
1161 | MGDI30 | MGDI30 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-02-15 | MGDI30 | 4G_FD900_MGDI30 | 4G_FD2100_MGDI30 | 4G_TD_MGDI30 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048175 | 2022-02-18 | P/FVC/MDS/1074990/2022 | 2022-02-28 | ST202202049420 | 2022-02-19 | P/FVC/MDS/1074935/2022 | 2022-02-28 |  |  |  |  | ST202202048659 | 2022-02-18 | P/FBW/MDS/1074876/2022 | 2022-02-28
1162 | MATUR7 | MATUR7 |  |  |  | ROTN | Indus | IN-3108990 | R/NN-639018 |  |  | 2022-02-19 | MATUR7 | 4G_FD900_MATUR7 | 4G_FD2100_MATUR7 | 4G_TD_MATUR7 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202052204 | 2022-02-22 | P/FVC/MDS/1076292/2022 | 2022-03-13 | ST202202054441 | 2022-02-24 | P/FVC/MDS/1076187/2022 | 2022-03-13 | ST202202049490 | 2022-02-19 | P/FVC/MDS/1074806/2022 | 2022-02-25 | ST202202053469 | 2022-02-23 | P/FBW/MDS/1076088/2022 | 2022-03-13
1163 | TLNYR2 | TLNYR2 |  |  |  | ROTN | Indus | IN-3056484 | R/RES-508926 |  |  | 2022-02-15 | TLNYR2 | 4G_FD900_TLNYR2 | 4G_FD2100_TLNYR2 | 4G_TD_TLNYR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202048213 | 2022-02-18 | P/FVC/MDS/1075008/2022 | 2022-02-28 | ST202202049439 | 2022-02-19 | P/FVC/MDS/1074954/2022 | 2022-02-28 | ST202202049484 | 2022-02-19 | P/FVC/MDS/1074801/2022 | 2022-02-25 | ST202202048693 | 2022-02-18 | P/FBW/MDS/1074896/2022 | 2022-02-28
1164 | ELPM04 | ELPM04 |  |  |  | ROTN | Indus | IN-3061295 | R/RES-508750 |  |  | 2022-02-15 | ELPM04 | 4G_FD900_ELPM04 | 4G_FD2100_ELPM04 | 4G_TD_ELPM04 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202048190 | 2022-02-18 | P/FVC/MDS/1075004/2022 | 2022-02-28 | ST202202049434 | 2022-02-19 | P/FVC/MDS/1074949/2022 | 2022-02-28 | ST202202049478 | 2022-02-19 | P/FVC/MDS/1074796/2022 | 2022-02-25 | ST202202048686 | 2022-02-18 | P/FBW/MDS/1074891/2022 | 2022-02-28
1165 | PRNDU1 | PRNDU1 | Erode | Coimbatore |  | ROTN | Airtel | - | - |  | On Air | 2022-02-23 | PRNDU1 | 4G_FD900_PRNDU1 | 4G_FD2100_PRNDU1 | 4G_TD_PRNDU1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056710 | 2022-02-27 | P/FVC/MDS/1076453/2022 | 2022-03-13 | ST202202055876 | 2022-02-26 | P/FVC/MDS/1075669/2022 | 2022-03-10 |  |  |  |  | ST202202056462 | 2022-02-26 | P/FBW/MDS/1075572/2022 | 2022-03-10
1166 | KGRI41 | KGRI41 | Krishnagiri | Vellore |  | ROTN | TVI | - | - |  | On Air | 2022-02-23 | KGRI41 | 4G_FD900_KGRI41 | 4G_FD2100_KGRI41 | 4G_TD_KGRI41 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056692 | 2022-02-27 | P/FVC/MDS/1076435/2022 | 2022-03-13 | ST202202055641 | 2022-02-26 | P/FVC/MDS/1075649/2022 | 2022-03-10 |  |  |  |  | ST202202055971 | 2022-02-26 | P/FBW/MDS/1075553/2022 | 2022-03-10
1167 | PULIRR | PULIRR | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3074792 | R/NN-635448 |  | SO | 2022-02-23 | PULIRR | 4G_FD900_PULIRR | 4G_FD2100_PULIRR | 4G_TD_PULIRR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402527 | 2022-09-08 | P/FVC/MDS/1096535/2022 | 2022-09-16 | ST202209402627 | 2022-09-08 | P/FVC/MDS/1096444/2022 | 2022-09-16 |  |  |  |  | ST202209398935 | 2022-09-07 | P/FVC/MDS/1096350/2022 | 2022-09-16
1168 | GMPD28 | GMPD28 | Thiruvallur | Chennai |  | ROTN | TVI | - | - |  | On Air | 2022-02-23 | GMPD28 | 4G_FD900_GMPD28 | 4G_FD2100_GMPD28 | 4G_TD_GMPD28 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056707 | 2022-02-27 | P/FVC/MDS/1076450/2022 | 2022-03-13 | ST202202055870 | 2022-02-26 | P/FVC/MDS/1075666/2022 | 2022-03-10 | ST202210538391 | 2022-10-08 | P/FVC/MDS/1113900/2022 | 2022-10-21 | ST202202055987 | 2022-02-26 | P/FBW/MDS/1075568/2022 | 2022-03-10
1169 | PALDU2 | PALDU2 | Viluppuram | Trichy |  | ROTN | Indus | IN-3122498 | R/NN-643820 |  | On Air | 2022-02-23 | PALDU2 | 4G_FD900_PALDU2 | 4G_FD2100_PALDU2 | 4G_TD_PALDU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056691 | 2022-02-27 | P/FVC/MDS/1076434/2022 | 2022-03-13 | ST202202055640 | 2022-02-26 | P/FVC/MDS/1075648/2022 | 2022-03-10 |  |  |  |  | ST202202055970 | 2022-02-26 | P/FBW/MDS/1075552/2022 | 2022-03-10
1170 | THIMAN | THIMAN | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-23 | THIMAN | 4G_FD900_THIMAN | 4G_FD2100_THIMAN | 4G_TD_THIMAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056703 | 2022-02-27 | P/FVC/MDS/1076446/2022 | 2022-03-13 | ST202202055861 | 2022-02-26 | P/FVC/MDS/1075662/2022 | 2022-03-10 |  |  |  |  | ST202202055982 | 2022-02-26 | P/FBW/MDS/1075564/2022 | 2022-03-10
1171 | AVADAI | AVADAI | Pudukkottai | Trichy |  | ROTN | Indus | IN-3080889 | R/NN-636189 |  | On Air | 2022-02-23 | AVADAI | 4G_FD900_AVADAI | 4G_FD2100_AVADAI | 4G_TD_AVADAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056517 | 2022-02-26 | P/FVC/MDS/1076410/2022 | 2022-03-13 | ST202202055616 | 2022-02-26 | P/FVC/MDS/1075624/2022 | 2022-03-10 |  |  |  |  | ST202202055943 | 2022-02-26 | P/FBW/MDS/1075528/2022 | 2022-03-10
1172 | SIKKAP | SIKKAP | Pudukkottai | Trichy |  | ROTN | Indus | IN-3120120 | R/NN-641179 |  | On Air | 2022-02-23 | SIKKAP | 4G_FD900_SIKKAP | 4G_FD2100_SIKKAP | 4G_TD_SIKKAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056597 | 2022-02-26 | P/FVC/MDS/1076430/2022 | 2022-03-13 | ST202202055636 | 2022-02-26 | P/FVC/MDS/1075644/2022 | 2022-03-10 |  |  |  |  | ST202202055965 | 2022-02-26 | P/FBW/MDS/1075548/2022 | 2022-03-10
1173 | ETTIYA | ETTIYA | Pudukkottai | Trichy |  | ROTN | Indus | IN-3080919 | R/NN-636194 |  | On Air | 2022-02-23 | ETTIYA | 4G_FD900_ETTIYA | 4G_FD2100_ETTIYA | 4G_TD_ETTIYA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056518 | 2022-02-26 | P/FVC/MDS/1076411/2022 | 2022-03-13 | ST202202055617 | 2022-02-26 | P/FVC/MDS/1075625/2022 | 2022-03-10 |  |  |  |  | ST202202055944 | 2022-02-26 | P/FBW/MDS/1075529/2022 | 2022-03-10
1174 | AYYAM2 | AYYAM2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3114414 | R/NN-640055 |  | On Air | 2022-02-23 | AYYAM2 | 4G_FD900_AYYAM2 | 4G_FD2100_AYYAM2 | 4G_TD_AYYAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056576 | 2022-02-26 | P/FVC/MDS/1076424/2022 | 2022-03-13 | ST202202055630 | 2022-02-26 | P/FVC/MDS/1075638/2022 | 2022-03-10 |  |  |  |  | ST202202055958 | 2022-02-26 | P/FBW/MDS/1075542/2022 | 2022-03-10
1175 | THENP2 | THENP2 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-02-23 | THENP2 | 4G_FD900_THENP2 | 4G_FD2100_THENP2 | 4G_TD_THENP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056711 | 2022-02-27 | P/FVC/MDS/1076454/2022 | 2022-03-13 | ST202202055877 | 2022-02-26 | P/FVC/MDS/1075670/2022 | 2022-03-10 |  |  |  |  | ST202202056463 | 2022-02-26 | P/FBW/MDS/1075573/2022 | 2022-03-10
1176 | VELLA2 | VELLA2 | Cuddalore | Trichy |  | ROTN | Indus | IN-3114559 | R/NN-640099 |  | On Air | 2022-02-23 | VELLA2 | 4G_FD900_VELLA2 | 4G_FD2100_VELLA2 | 4G_TD_VELLA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056538 | 2022-02-26 | P/FVC/MDS/1076415/2022 | 2022-03-13 | ST202202055621 | 2022-02-26 | P/FVC/MDS/1075629/2022 | 2022-03-10 |  |  |  |  | ST202202055948 | 2022-02-26 | P/FBW/MDS/1075533/2022 | 2022-03-10
1177 | MANPE2 | MANPE2 | Puducherry | Trichy |  | ROTN | Indus | IN-3120129 | R/NN-641187 |  | On Air | 2022-02-23 | MANPE2 | 4G_FD900_MANPE2 | 4G_FD2100_MANPE2 | 4G_TD_MANPE2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056588 | 2022-02-26 | P/FVC/MDS/1076426/2022 | 2022-03-13 | ST202202055632 | 2022-02-26 | P/FVC/MDS/1075640/2022 | 2022-03-10 |  |  |  |  | ST202202055961 | 2022-02-26 | P/FBW/MDS/1075544/2022 | 2022-03-10
1178 | PURIS2 | PURIS2 | Kancheepuram | Chennai |  | ROTN | Indus | IN-3120130 | R/NN-641190 |  | On Air | 2022-02-23 | PURIS2 | 4G_FD900_PURIS2 | 4G_FD2100_PURIS2 | 4G_TD_PURIS2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056697 | 2022-02-27 | P/FVC/MDS/1076440/2022 | 2022-03-13 | ST202202055852 | 2022-02-26 | P/FVC/MDS/1075656/2022 | 2022-03-10 |  |  |  |  | ST202202055976 | 2022-02-26 | P/FBW/MDS/1075558/2022 | 2022-03-10
1179 | THARA2 | THARA2 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3114570 | R/NN-640103 |  | SO(Rural Hold) | 2022-02-23 | THARA2 | 4G_FD900_THARA2 | 4G_FD2100_THARA2 | 4G_TD_THARA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056601 | 2022-02-26 | P/FVC/MDS/1076431/2022 | 2022-03-13 | ST202202055637 | 2022-02-26 | P/FVC/MDS/1075645/2022 | 2022-03-10 |  |  |  |  | ST202202055967 | 2022-02-26 | P/FBW/MDS/1075549/2022 | 2022-03-10
1180 | VERGP2 | VERGP2 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3114598 | R/NN-640114 |  | On Air | 2022-02-23 | VERGP2 | 4G_FD900_VERGP2 | 4G_FD2100_VERGP2 | 4G_TD_VERGP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056549 | 2022-02-26 | P/FVC/MDS/1076418/2022 | 2022-03-13 | ST202202055624 | 2022-02-26 | P/FVC/MDS/1075632/2022 | 2022-03-10 |  |  |  |  | ST202202055952 | 2022-02-26 | P/FBW/MDS/1075536/2022 | 2022-03-10
1181 | KELAN7 | KELAN7 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3114622 | R/NN-640159 |  | On Air | 2022-02-23 | KELAN7 | 4G_FD900_KELAN7 | 4G_FD2100_KELAN7 | 4G_TD_KELAN7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056522 | 2022-02-26 | P/FVC/MDS/1076412/2022 | 2022-03-13 | ST202202055618 | 2022-02-26 | P/FVC/MDS/1075626/2022 | 2022-03-10 |  |  |  |  | ST202202055945 | 2022-02-26 | P/FBW/MDS/1075530/2022 | 2022-03-10
1182 | TENDA2 | TENDA2 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3114627 | R/NN-640162 |  | On Air | 2022-02-23 | TENDA2 | 4G_FD900_TENDA2 | 4G_FD2100_TENDA2 | 4G_TD_TENDA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056523 | 2022-02-26 | P/FVC/MDS/1076413/2022 | 2022-03-13 | ST202202055619 | 2022-02-26 | P/FVC/MDS/1075627/2022 | 2022-03-10 |  |  |  |  | ST202202055946 | 2022-02-26 | P/FBW/MDS/1075531/2022 | 2022-03-10
1183 | KALME2 | KALME2 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3114635 | R/NN-640165 |  | SO(Rural Hold) | 2022-02-23 | KALME2 | 4G_FD900_KALME2 | 4G_FD2100_KALME2 | 4G_TD_KALME2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056577 | 2022-02-26 | P/FVC/MDS/1076425/2022 | 2022-03-13 | ST202202055631 | 2022-02-26 | P/FVC/MDS/1075639/2022 | 2022-03-10 |  |  |  |  | ST202202055959 | 2022-02-26 | P/FBW/MDS/1075543/2022 | 2022-03-10
1184 | POMBU2 | POMBU2 | Viluppuram | Trichy |  | ROTN | Indus | IN-3120132 | R/NN-641192 |  | On Air | 2022-02-23 | POMBU2 | 4G_FD900_POMBU2 | 4G_FD2100_POMBU2 | 4G_TD_POMBU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056540 | 2022-02-26 | P/FVC/MDS/1076417/2022 | 2022-03-13 | ST202202055623 | 2022-02-26 | P/FVC/MDS/1075631/2022 | 2022-03-10 |  |  |  |  | ST202202055950 | 2022-02-26 | P/FBW/MDS/1075535/2022 | 2022-03-10
1185 | TELI02 | TELI02 | Viluppuram | Trichy |  | ROTN | Indus | IN-3120143 | R/NN-641199 |  | SO(Rural Hold) | 2022-02-23 | TELI02 | 4G_FD900_TELI02 | 4G_FD2100_TELI02 | 4G_TD_TELI02 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056539 | 2022-02-26 | P/FVC/MDS/1076416/2022 | 2022-03-13 | ST202202055622 | 2022-02-26 | P/FVC/MDS/1075630/2022 | 2022-03-10 |  |  |  |  | ST202202055949 | 2022-02-26 | P/FBW/MDS/1075534/2022 | 2022-03-10
1186 | EKANA2 | EKANA2 | Kancheepuram | Chennai |  | ROTN | Indus | IN-3114648 | R/NN-640172 |  | On Air | 2022-02-23 | EKANA2 | 4G_FD900_EKANA2 | 4G_FD2100_EKANA2 | 4G_TD_EKANA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056524 | 2022-02-26 | P/FVC/MDS/1076414/2022 | 2022-03-13 | ST202202055620 | 2022-02-26 | P/FVC/MDS/1075628/2022 | 2022-03-10 |  |  |  |  | ST202202055947 | 2022-02-26 | P/FBW/MDS/1075532/2022 | 2022-03-10
1187 | RJPM48 | RJPM48 | Virudhunagar | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-02-23 | RJPM48 | 4G_FD900_RJPM48 | 4G_FD2100_RJPM48 | 4G_TD_RJPM48 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056705 | 2022-02-27 | P/FVC/MDS/1076448/2022 | 2022-03-13 | ST202202055866 | 2022-02-26 | P/FVC/MDS/1075664/2022 | 2022-03-10 |  |  |  |  | ST202202055984 | 2022-02-26 | P/FBW/MDS/1075566/2022 | 2022-03-10
1188 | THIMA2 | THIMA2 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-23 | THIMA2 | 4G_FD900_THIMA2 | 4G_FD2100_THIMA2 | 4G_TD_THIMA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056704 | 2022-02-27 | P/FVC/MDS/1076447/2022 | 2022-03-13 | ST202202055865 | 2022-02-26 | P/FVC/MDS/1075663/2022 | 2022-03-10 |  |  |  |  | ST202202055983 | 2022-02-26 | P/FBW/MDS/1075565/2022 | 2022-03-10
1189 | NADUV3 | NADUV3 | Cuddalore | Trichy |  | ROTN | Indus | IN-3121026 | R/NN-642246 |  |  | 2022-02-23 | NADUV3 | 4G_FD900_NADUV3 | 4G_FD2100_NADUV3 | 4G_TD_NADUV3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056550 | 2022-02-26 | P/FVC/MDS/1076419/2022 | 2022-03-13 | ST202202055625 | 2022-02-26 | P/FVC/MDS/1075633/2022 | 2022-03-10 |  |  |  |  | ST202202055953 | 2022-02-26 | P/FBW/MDS/1075537/2022 | 2022-03-10
1190 | KUDUM1 | KUDUM1 | Cuddalore | Trichy |  | ROTN | Indus | IN-3123929 | R/NN-645743 |  | SO(Rural Hold) | 2022-02-24 | KUDUM1 | 4G_FD900_KUDUM1 | 4G_FD2100_KUDUM1 | 4G_TD_KUDUM1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056717 | 2022-02-27 | P/FVC/MDS/1076460/2022 | 2022-03-13 | ST202202055885 | 2022-02-26 | P/FVC/MDS/1075676/2022 | 2022-03-10 |  |  |  |  | ST202202056469 | 2022-02-26 | P/FBW/MDS/1075579/2022 | 2022-03-10
1191 | DAMAR2 | DAMAR2 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-23 | DAMAR2 | 4G_FD900_DAMAR2 | 4G_FD2100_DAMAR2 | 4G_TD_DAMAR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056708 | 2022-02-27 | P/FVC/MDS/1076451/2022 | 2022-03-13 | ST202202055873 | 2022-02-26 | P/FVC/MDS/1075667/2022 | 2022-03-10 |  |  |  |  | ST202202055988 | 2022-02-26 | P/FBW/MDS/1075569/2022 | 2022-03-10
1192 | THRTL3 | THRTL3 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/22937 | - |  | On Air | 2022-02-23 | THRTL3 | 4G_FD900_THRTL3 | 4G_FD2100_THRTL3 | 4G_TD_THRTL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056696 | 2022-02-27 | P/FVC/MDS/1076439/2022 | 2022-03-13 | ST202202055851 | 2022-02-26 | P/FVC/MDS/1075655/2022 | 2022-03-10 |  |  |  |  | ST202202055975 | 2022-02-26 | P/FBW/MDS/1075557/2022 | 2022-03-10
1193 | PANCH2 | PANCH2 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3121082 | R/NN-642344 |  | On Air | 2022-02-23 | PANCH2 | 4G_FD900_PANCH2 | 4G_FD2100_PANCH2 | 4G_TD_PANCH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056698 | 2022-02-27 | P/FVC/MDS/1076441/2022 | 2022-03-13 | ST202202055854 | 2022-02-26 | P/FVC/MDS/1075657/2022 | 2022-03-10 |  |  |  |  | ST202202055977 | 2022-02-26 | P/FBW/MDS/1075559/2022 | 2022-03-10
1194 | NAMBA2 | NAMBA2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121084 | R/NN-642348 |  | On Air | 2022-02-23 | NAMBA2 | 4G_FD900_NAMBA2 | 4G_FD2100_NAMBA2 | 4G_TD_NAMBA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056589 | 2022-02-26 | P/FVC/MDS/1076427/2022 | 2022-03-13 | ST202202055633 | 2022-02-26 | P/FVC/MDS/1075641/2022 | 2022-03-10 |  |  |  |  | ST202202055962 | 2022-02-26 | P/FBW/MDS/1075545/2022 | 2022-03-10
1195 | VELAL3 | VELAL3 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121087 | R/NN-642349 |  | On Air | 2022-02-23 | VELAL3 | 4G_FD900_VELAL3 | 4G_FD2100_VELAL3 | 4G_TD_VELAL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056694 | 2022-02-27 | P/FVC/MDS/1076437/2022 | 2022-03-13 | ST202202055643 | 2022-02-26 | P/FVC/MDS/1075651/2022 | 2022-03-10 |  |  |  |  | ST202202055973 | 2022-02-26 | P/FBW/MDS/1075555/2022 | 2022-03-10
1196 | KALKO2 | KALKO2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121091 | R/NN-642352 |  | On Air | 2022-02-23 | KALKO2 | 4G_FD900_KALKO2 | 4G_FD2100_KALKO2 | 4G_TD_KALKO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056590 | 2022-02-26 | P/FVC/MDS/1076428/2022 | 2022-03-13 | ST202202055634 | 2022-02-26 | P/FVC/MDS/1075642/2022 | 2022-03-10 |  |  |  |  | ST202202055963 | 2022-02-26 | P/FBW/MDS/1075546/2022 | 2022-03-10
1197 | KILAN2 | KILAN2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121051 | R/NN-642290 |  | On Air | 2022-02-23 | KILAN2 | 4G_FD900_KILAN2 | 4G_FD2100_KILAN2 | 4G_TD_KILAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056551 | 2022-02-26 | P/FVC/MDS/1076420/2022 | 2022-03-13 | ST202202055626 | 2022-02-26 | P/FVC/MDS/1075634/2022 | 2022-03-10 |  |  |  |  | ST202202055954 | 2022-02-26 | P/FBW/MDS/1075538/2022 | 2022-03-10
1198 | MARAD2 | MARAD2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121095 | R/NN-642360 |  | On Air | 2022-02-23 | MARAD2 | 4G_FD900_MARAD2 | 4G_FD2100_MARAD2 | 4G_TD_MARAD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056562 | 2022-02-26 | P/FVC/MDS/1076421/2022 | 2022-03-13 | ST202202055627 | 2022-02-26 | P/FVC/MDS/1075635/2022 | 2022-03-10 |  |  |  |  | ST202202055955 | 2022-02-26 | P/FBW/MDS/1075539/2022 | 2022-03-10
1199 | MERKA2 | MERKA2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121097 | R/NN-642362 |  | On Air | 2022-02-23 | MERKA2 | 4G_FD900_MERKA2 | 4G_FD2100_MERKA2 | 4G_TD_MERKA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056596 | 2022-02-26 | P/FVC/MDS/1076429/2022 | 2022-03-13 | ST202202055635 | 2022-02-26 | P/FVC/MDS/1075643/2022 | 2022-03-10 |  |  |  |  | ST202202055964 | 2022-02-26 | P/FBW/MDS/1075547/2022 | 2022-03-10
1200 | SEMMA2 | SEMMA2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121280 | R/NN-642363 |  | On Air | 2022-02-23 | SEMMA2 | 4G_FD900_SEMMA2 | 4G_FD2100_SEMMA2 | 4G_TD_SEMMA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056563 | 2022-02-26 | P/FVC/MDS/1076422/2022 | 2022-03-13 | ST202202055628 | 2022-02-26 | P/FVC/MDS/1075636/2022 | 2022-03-10 |  |  |  |  | ST202202055956 | 2022-02-26 | P/FBW/MDS/1075540/2022 | 2022-03-10
1201 | MULLA2 | MULLA2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121098 | R/NN-642365 |  | On Air | 2022-02-23 | MULLA2 | 4G_FD900_MULLA2 | 4G_FD2100_MULLA2 | 4G_TD_MULLA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056602 | 2022-02-26 | P/FVC/MDS/1076432/2022 | 2022-03-13 | ST202202055638 | 2022-02-26 | P/FVC/MDS/1075646/2022 | 2022-03-10 |  |  |  |  | ST202202055968 | 2022-02-26 | P/FBW/MDS/1075550/2022 | 2022-03-10
1202 | KURUM2 | KURUM2 | Perambalur | Trichy |  | ROTN | Indus | IN-3123937 | R/NN-645752 |  | On Air | 2022-02-24 | KURUM2 | 4G_FD900_KURUM2 | 4G_FD2100_KURUM2 | 4G_TD_KURUM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056718 | 2022-02-27 | P/FVC/MDS/1076461/2022 | 2022-03-13 | ST202210614702 | 2022-10-21 | P/FVC/MDS/1114225/2022 | 2022-11-03 |  |  |  |  | ST202202056470 | 2022-02-26 | P/FBW/MDS/1075580/2022 | 2022-03-10
1203 | THUMN2 | THUMN2 | The Nilgiris | Coimbatore |  | ROTN | ATC | TN/NI/AT/22941 | - |  | On Air | 2022-02-24 | THUMN2 | 4G_FD900_THUMN2 | 4G_FD2100_THUMN2 | 4G_TD_THUMN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056713 | 2022-02-27 | P/FVC/MDS/1076456/2022 | 2022-03-13 | ST202202055880 | 2022-02-26 | P/FVC/MDS/1075672/2022 | 2022-03-10 |  |  |  |  | ST202202056465 | 2022-02-26 | P/FBW/MDS/1075575/2022 | 2022-03-10
1204 | THALA2 | THALA2 | Puducherry | Trichy |  | ROTN | Indus | IN-3121107 | R/NN-642368 |  | SR | 2022-02-23 | THALA2 | 4G_FD900_THALA2 | 4G_FD2100_THALA2 | 4G_TD_THALA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056699 | 2022-02-27 | P/FVC/MDS/1076442/2022 | 2022-03-13 | ST202202055855 | 2022-02-26 | P/FVC/MDS/1075658/2022 | 2022-03-10 |  |  |  |  | ST202202055978 | 2022-02-26 | P/FBW/MDS/1075560/2022 | 2022-03-10
1205 | MADPA2 | MADPA2 | Viluppuram | Trichy |  | ROTN | Indus | IN-3121127 | R/NN-642370 |  | On Air | 2022-02-23 | MADPA2 | 4G_FD900_MADPA2 | 4G_FD2100_MADPA2 | 4G_TD_MADPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056575 | 2022-02-26 | P/FVC/MDS/1076423/2022 | 2022-03-13 | ST202202055629 | 2022-02-26 | P/FVC/MDS/1075637/2022 | 2022-03-10 |  |  |  |  | ST202202055957 | 2022-02-26 | P/FBW/MDS/1075541/2022 | 2022-03-10
1206 | KOLPU2 | KOLPU2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-KLPU-ENB-9003 | SR-TN000790 |  | On Air | 2022-02-24 | KOLPU2 | 4G_FD900_KOLPU2 | 4G_FD2100_KOLPU2 | 4G_TD_KOLPU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025210 | 2022-01-31 | P/FVC/MDS/1074453/2022 | 2022-02-22 | ST202201025315 | 2022-01-31 | P/FVC/MDS/1074396/2022 | 2022-02-22 |  |  |  |  | ST202201025390 | 2022-01-31 | P/FBW/MDS/1074336/2022 | 2022-02-22
1207 | KURCI2 | KURCI2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-BHVN-ENB-9052 | SR-TN000792 |  | On Air | 2022-02-24 | KURCI2 | 4G_FD900_KURCI2 | 4G_FD2100_KURCI2 | 4G_TD_KURCI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201025211 | 2022-01-31 | P/FVC/MDS/1074454/2022 | 2022-02-22 | ST202201025316 | 2022-01-31 | P/FVC/MDS/1074397/2022 | 2022-02-22 |  |  |  |  | ST202201025391 | 2022-01-31 | P/FBW/MDS/1074337/2022 | 2022-02-22
1208 | IYAIY2 | IYAIY2 | Viluppuram | Trichy |  | ROTN | Indus | IN-3121128 | R/NN-642371 |  | On Air | 2022-02-23 | IYAIY2 | 4G_FD900_IYAIY2 | 4G_FD2100_IYAIY2 | 4G_TD_IYAIY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056603 | 2022-02-26 | P/FVC/MDS/1076433/2022 | 2022-03-13 | ST202202055639 | 2022-02-26 | P/FVC/MDS/1075647/2022 | 2022-03-10 |  |  |  |  | ST202202055969 | 2022-02-26 | P/FBW/MDS/1075551/2022 | 2022-03-10
1209 | PUNPT2 | PUNPT2 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/22974 | - |  | On Air | 2022-02-23 | PUNPT2 | 4G_FD900_PUNPT2 | 4G_FD2100_PUNPT2 | 4G_TD_PUNPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056701 | 2022-02-27 | P/FVC/MDS/1076444/2022 | 2022-03-13 | ST202202055859 | 2022-02-26 | P/FVC/MDS/1075660/2022 | 2022-03-10 |  |  |  |  | ST202202055980 | 2022-02-26 | P/FBW/MDS/1075562/2022 | 2022-03-10
1210 | MANGL2 | MANGL2 | Tiruvannamalai | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-02-23 | MANGL2 | 4G_FD900_MANGL2 | 4G_FD2100_MANGL2 | 4G_TD_MANGL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056709 | 2022-02-27 | P/FVC/MDS/1076452/2022 | 2022-03-13 | ST202202055874 | 2022-02-26 | P/FVC/MDS/1075668/2022 | 2022-03-10 | ST202210548135 | 2022-10-11 | P/FVC/MDS/1113911/2022 | 2022-10-21 | ST202202056461 | 2022-02-26 | P/FBW/MDS/1075571/2022 | 2022-03-10
1211 | NERUR2 | NERUR2 | Karur | Coimbatore |  | ROTN | ATC | TN/KU/AT/22975 | - |  | On Air | 2022-02-23 | NERUR2 | 4G_FD900_NERUR2 | 4G_FD2100_NERUR2 | 4G_TD_NERUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056702 | 2022-02-27 | P/FVC/MDS/1076445/2022 | 2022-03-13 | ST202202055860 | 2022-02-26 | P/FVC/MDS/1075661/2022 | 2022-03-10 |  |  |  |  | ST202202055981 | 2022-02-26 | P/FBW/MDS/1075563/2022 | 2022-03-10
1212 | ATHUK2 | ATHUK2 | Karur | Coimbatore |  | ROTN | ATC | TN/KU/AT/22976 | - |  | On Air | 2022-02-23 | ATHUK2 | 4G_FD900_ATHUK2 | 4G_FD2100_ATHUK2 | 4G_TD_ATHUK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056700 | 2022-02-27 | P/FVC/MDS/1076443/2022 | 2022-03-13 | ST202202055856 | 2022-02-26 | P/FVC/MDS/1075659/2022 | 2022-03-10 |  |  |  |  | ST202202055979 | 2022-02-26 | P/FBW/MDS/1075561/2022 | 2022-03-10
1213 | AGPLI2 | AGPLI2 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/22964 | - |  | On Air | 2022-02-24 | AGPLI2 | 4G_FD900_AGPLI2 | 4G_FD2100_AGPLI2 | 4G_TD_AGPLI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056714 | 2022-02-27 | P/FVC/MDS/1076457/2022 | 2022-03-13 | ST202202055881 | 2022-02-26 | P/FVC/MDS/1075673/2022 | 2022-03-10 |  |  |  |  | ST202202056466 | 2022-02-26 | P/FBW/MDS/1075576/2022 | 2022-03-10
1214 | DKRLM4 | DKRLM4 | Tirunelveli | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-02-23 | DKRLM4 | 4G_FD900_DKRLM4 | 4G_FD2100_DKRLM4 | 4G_TD_DKRLM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056706 | 2022-02-27 | P/FVC/MDS/1076449/2022 | 2022-03-13 | ST202202055869 | 2022-02-26 | P/FVC/MDS/1075665/2022 | 2022-03-10 |  |  |  |  | ST202202055986 | 2022-02-26 | P/FBW/MDS/1075567/2022 | 2022-03-10
1215 | NMKL69 | NMKL69 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-NMKK-ENB-0020 | SR-TN000797 |  | On Air | 2022-02-24 | NMKL69 | 4G_FD900_NMKL69 | 4G_FD2100_NMKL69 | 4G_TD_NMKL69 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056720 | 2022-02-27 | P/FVC/MDS/1076463/2022 | 2022-03-13 | ST202202055890 | 2022-02-26 | P/FVC/MDS/1075679/2022 | 2022-03-10 |  |  |  |  | ST202202056472 | 2022-02-26 | P/FBW/MDS/1075582/2022 | 2022-03-10
1216 | GNPYM2 | GNPYM2 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-PLDM-ENB-9082 | SR-TN000811 |  | On Air | 2022-02-24 | GNPYM2 | 4G_FD900_GNPYM2 | 4G_FD2100_GNPYM2 | 4G_TD_GNPYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052252 | 2022-02-22 | P/FVC/MDS/1076310/2022 | 2022-03-13 | ST202202054467 | 2022-02-24 | P/FVC/MDS/1076204/2022 | 2022-03-13 |  |  |  |  | ST202202054018 | 2022-02-24 | P/FBW/MDS/1076106/2022 | 2022-03-13
1217 | TIR491 | TIR491 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-PLDM-ENB-9086 | SR-TN000810 |  | On Air | 2022-02-24 | TIR491 | 4G_FD900_TIR491 | 4G_FD2100_TIR491 | 4G_TD_TIR491 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052254 | 2022-02-22 | P/FVC/MDS/1076312/2022 | 2022-03-13 | ST202202054470 | 2022-02-24 | P/FVC/MDS/1076206/2022 | 2022-03-13 |  |  |  |  | ST202202054020 | 2022-02-24 | P/FBW/MDS/1076108/2022 | 2022-03-13
1218 | TKLRR2 | TKLRR2 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-AVNS-ENB-9083 | SR-TN000824 |  | On Air | 2022-02-24 | TKLRR2 | 4G_FD900_TKLRR2 | 4G_FD2100_TKLRR2 | 4G_TD_TKLRR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052259 | 2022-02-22 | P/FVC/MDS/1076313/2022 | 2022-03-13 | ST202202054471 | 2022-02-24 | P/FVC/MDS/1076207/2022 | 2022-03-13 |  |  |  |  | ST202202054021 | 2022-02-24 | P/FBW/MDS/1076109/2022 | 2022-03-13
1219 | TKLRR3 | TKLRR3 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-TAVF-ENB-9003 | SR-TN000814 |  | On Air | 2022-02-24 | TKLRR3 | 4G_FD900_TKLRR3 | 4G_FD2100_TKLRR3 | 4G_TD_TKLRR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052260 | 2022-02-22 | P/FVC/MDS/1076314/2022 | 2022-03-13 | ST202202054472 | 2022-02-24 | P/FVC/MDS/1076208/2022 | 2022-03-13 |  |  |  |  | ST202202054023 | 2022-02-24 | P/FBW/MDS/1076110/2022 | 2022-03-13
1220 | CBE914 | CBE914 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBR-ENB-9119 | SR-TN000817 |  | On Air | 2022-02-24 | CBE914 | 4G_FD900_CBE914 | 4G_FD2100_CBE914 | 4G_TD_CBE914 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052263 | 2022-02-22 | P/FVC/MDS/1076316/2022 | 2022-03-13 | ST202202054474 | 2022-02-24 | P/FVC/MDS/1076210/2022 | 2022-03-13 |  |  |  |  | ST202202054025 | 2022-02-24 | P/FBW/MDS/1076112/2022 | 2022-03-13
1221 | ERD168 | ERD168 | Erode | Coimbatore |  | ROTN | Summit | I-TN-EROD-ENB-9072 | SR-TN000823 |  | On Air | 2022-02-24 | ERD168 | 4G_FD900_ERD168 | 4G_FD2100_ERD168 | 4G_TD_ERD168 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052268 | 2022-02-22 | P/FVC/MDS/1076318/2022 | 2022-03-13 | ST202202054933 | 2022-02-25 | P/FVC/MDS/1076212/2022 | 2022-03-13 |  |  |  |  | ST202202054034 | 2022-02-24 | P/FBW/MDS/1076114/2022 | 2022-03-13
1222 | TIVR41 | TIVR41 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TVUR-ENB-0037 | SR-TN000799 |  | On Air | 2022-02-24 | TIVR41 | 4G_FD900_TIVR41 | 4G_FD2100_TIVR41 | 4G_TD_TIVR41 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056719 | 2022-02-27 | P/FVC/MDS/1076462/2022 | 2022-03-13 | ST202202055889 | 2022-02-26 | P/FVC/MDS/1075678/2022 | 2022-03-10 |  |  |  |  | ST202202056471 | 2022-02-26 | P/FBW/MDS/1075581/2022 | 2022-03-10
1223 | TIVR42 | TIVR42 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TVUR-ENB-0035 | SR-TN000802 |  | On Air | 2022-02-24 | TIVR42 | 4G_FD900_TIVR42 | 4G_FD2100_TIVR42 | 4G_TD_TIVR42 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056722 | 2022-02-27 | P/FVC/MDS/1076465/2022 | 2022-03-13 | ST202202055893 | 2022-02-26 | P/FVC/MDS/1075681/2022 | 2022-03-10 |  |  |  |  | ST202202056477 | 2022-02-26 | P/FBW/MDS/1075584/2022 | 2022-03-10
1224 | TIVR44 | TIVR44 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TVUR-ENB-0019 | SR-TN000805 |  | On Air | 2022-02-24 | TIVR44 | 4G_FD900_TIVR44 | 4G_FD2100_TIVR44 | 4G_TD_TIVR44 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056721 | 2022-02-27 | P/FVC/MDS/1076464/2022 | 2022-03-13 | ST202202055891 | 2022-02-26 | P/FVC/MDS/1075680/2022 | 2022-03-10 |  |  |  |  | ST202202056475 | 2022-02-26 | P/FBW/MDS/1075583/2022 | 2022-03-10
1225 | PDY347 | PDY347 |  |  |  | ROTN | Airtel | - | - |  |  | 2022-02-15 | PDY347 | 4G_FD900_PDY347 | 4G_FD2100_PDY347 | 4G_TD_PDY347 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202048174 | 2022-02-18 | P/FVC/MDS/1074989/2022 | 2022-02-28 | ST202202049419 | 2022-02-19 | P/FVC/MDS/1074934/2022 | 2022-02-28 | ST202202049476 | 2022-02-19 | P/FVC/MDS/1074794/2022 | 2022-02-25 | ST202202048654 | 2022-02-18 | P/FBW/MDS/1074875/2022 | 2022-02-28
1226 | PDY364 | PDY364 |  |  |  | ROTN | Indus | IN-3061290 | R/RES-508703 |  |  | 2022-02-15 | PDY364 | 4G_FD900_PDY364 | 4G_FD2100_PDY364 | 4G_TD_PDY364 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202048191 | 2022-02-18 | P/FVC/MDS/1075005/2022 | 2022-02-28 | ST202202049435 | 2022-02-19 | P/FVC/MDS/1074950/2022 | 2022-02-28 | ST202202049479 | 2022-02-19 | P/FVC/MDS/1074797/2022 | 2022-02-25 | ST202202048687 | 2022-02-18 | P/FBW/MDS/1074892/2022 | 2022-02-28
1227 | MOGW22 | MOGW22 |  |  |  | CHN | ATC | TN/CH/AT/22731 | T21TN09756 |  | On air |  | MOGW22 | 4G_FD900_MOGW22 | 4G_FD2100_MOGW22 | 4G_TD_MOGW22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056695 | 2022-02-27 | P/FVC/MDS/1076438/2022 | 2022-03-13 | ST202202055644 | 2022-02-26 | P/FVC/MDS/1075652/2022 | 2022-03-10 | ST202204095116 | 2022-04-08 | P/FVC/MDS/1078407/2022 | 2022-04-21 | ST202202055974 | 2022-02-26 | P/FBW/MDS/1075556/2022 | 2022-03-10
1228 | MOGW23 | MOGW23 |  |  |  | CHN | Indus | IN-1284991 | R/RES-508894 |  | On air |  | MOGW23 | 4G_FD900_MOGW23 | 4G_FD2100_MOGW23 | 4G_TD_MOGW23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202102036616 | 2021-02-06 | P/FVC/MDS/1013098/2021 | 2021-03-16 | ST202102036295 | 2021-02-03 | P/FVC/MDS/1013038/2021 | 2021-03-16 |  |  |  |  | ST202102036501 | 2021-02-03 | P/FBW/MDS/1013069/2021 | 2021-03-16
1229 | CONR27 | CONR27 | The Nilgiris | Coimbatore |  | ROTN | Indus |  | R/NN-645870 |  |  | 2022-03-22 | CONR27 | 4G_FD900_CONR27 | 4G_FD2100_CONR27 | 4G_TD_CONR27 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085747 | 2022-03-29 | P/FVC/MDS/1078113/2022 | 2022-04-14 | ST202203084844 | 2022-03-29 | P/FVC/MDS/1078015/2022 | 2022-04-14 |  |  |  |  | ST202203082765 | 2022-03-26 | P/FBW/MDS/1077856/2022 | 2022-04-14
1230 | JOLR21 | JOLR21 | Vellore | Vellore |  | ROTN | Indus | IN-3124036 | R/NN-645839 |  | SRB(Surrender) | 2022-03-01 | JOLR21 | 4G_FD900_JOLR21 | 4G_FD2100_JOLR21 | 4G_TD_JOLR21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061491 | 2022-03-03 | P/FVC/MDS/1076629/2022 | 2022-03-13 | ST202203061587 | 2022-03-03 | P/FVC/MDS/1076581/2022 | 2022-03-13 |  |  |  |  | ST202203062351 | 2022-03-04 | P/FBW/MDS/1076525/2022 | 2022-03-13
1231 | MDKI14 | MDKI14 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-MKKR-ENB-0002 | SR-TN000888 |  | On Air | 2022-02-25 | MDKI14 | 4G_FD900_MDKI14 | 4G_FD2100_MDKI14 | 4G_TD_MDKI14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056724 | 2022-02-27 | P/FVC/MDS/1076467/2022 | 2022-03-13 | ST202202055895 | 2022-02-26 | P/FVC/MDS/1075683/2022 | 2022-03-10 |  |  |  |  | ST202202056485 | 2022-02-26 | P/FBW/MDS/1075586/2022 | 2022-03-10
1232 | APTNM8 | APTNM8 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-03-08 | APTNM8 | 4G_FD900_APTNM8 | 4G_FD2100_APTNM8 | 4G_TD_APTNM8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073973 | 2022-03-16 | P/FVC/MDS/1077162/2022 | 2022-03-30 | ST202203073581 | 2022-03-16 | P/FVC/MDS/1077114/2022 | 2022-03-30 |  |  |  |  | ST202203072928 | 2022-03-15 | P/FBW/MDS/1077066/2022 | 2022-03-30
1233 | ILKD5 | ILKD05 | Sivaganga | Madurai |  | ROTN | ATC | TN/SI/AT/22683 | - |  | On Air | 2022-03-08 | ILKD05 | 4G_FD900_ILKD05 | 4G_FD2100_ILKD05 | 4G_TD_ILKD05 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073960 | 2022-03-16 | P/FVC/MDS/1077154/2022 | 2022-03-30 | ST202203073559 | 2022-03-16 | P/FVC/MDS/1077106/2022 | 2022-03-30 |  |  |  |  | ST202203072903 | 2022-03-15 | P/FBW/MDS/1077058/2022 | 2022-03-30
1234 | KRMD12 | KRMD12 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22688 | - |  | SO - Sent for withdrawal | 2022-03-16 | KRMD12 | 4G_FD900_KRMD12 | 4G_FD2100_KRMD12 | 4G_TD_KRMD12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084552 | 2022-03-29 | P/FVC/MDS/1078033/2022 | 2022-04-14 | ST202203084455 | 2022-03-28 | P/FVC/MDS/1077934/2022 | 2022-04-14 |  |  |  |  | ST202203082564 | 2022-03-26 | P/FBW/MDS/1077780/2022 | 2022-04-14
1235 | GKNPTI | GKNPTI | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-03-16 | GKNPTI | 4G_FD900_GKNPTI | 4G_FD2100_GKNPTI | 4G_TD_GKNPTI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362274 | 2021-06-25 | P/FVC/MDS/1049945/2021 | 2021-08-09 | ST202012161509 | 2020-12-01 | P/FVC/MDS/1006969/2020 | 2020-12-06 | ST202012163590 | 2020-12-02 | P/FVC/MDS/1007135/2020 | 2020-12-11 | ST202203082576 | 2022-03-26 | P/FBW/MDS/1077784/2022 | 2022-04-14
1236 | KTYR3 | KTYR03 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | KTYR03 | 4G_FD900_KTYR03 | 4G_FD2100_KTYR03 | 4G_TD_KTYR03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073967 | 2022-03-16 | P/FVC/MDS/1077158/2022 | 2022-03-30 | ST202203073569 | 2022-03-16 | P/FVC/MDS/1077110/2022 | 2022-03-30 |  |  |  |  | ST202203072912 | 2022-03-15 | P/FBW/MDS/1077062/2022 | 2022-03-30
1237 | VALM9 | VALM09 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-03-08 | VALM09 | 4G_FD900_VALM09 | 4G_FD2100_VALM09 | 4G_TD_VALM09 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442786 | 2022-09-19 | P/FVC/MDS/1098122/2022 | 2022-09-27 | ST202209447435 | 2022-09-19 | P/FVC/MDS/1098209/2022 | 2022-09-27 |  |  |  |  | ST202209432403 | 2022-09-17 | P/FVC/MDS/1097986/2022 | 2022-09-27
1238 | KRPT4 | KRPT04 | Virudhunagar | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-16 | KRPT04 | 4G_FD900_KRPT04 | 4G_FD2100_KRPT04 | 4G_TD_KRPT04 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430678 | 2021-08-17 | P/FVC/MDS/1059633/2021 | 2021-09-12 | ST202108414421 | 2021-08-10 | P/FVC/MDS/1055942/2021 | 2021-09-05 |  |  |  |  | ST202108424120 | 2021-08-11 | P/FBW/MDS/1055964/2021 | 2021-09-05
1239 | STKLM3 | STKLM3 | Thoothukkudi | Madurai |  | ROTN | Indus |  | R/NN-645564 |  | On Air |  | STKLM3 | 4G_FD900_STKLM3 | 4G_FD2100_STKLM3 | 4G_TD_STKLM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362792 | 2021-06-26 | P/FVC/MDS/1050052/2021 | 2021-08-09 | ST202101005309 | 2021-01-08 | P/FVC/MDS/1009105/2021 | 2021-01-17 |  |  |  |  | ST202101005685 | 2021-01-08 | P/FBW/MDS/1009703/2021 | 2021-01-24
1240 | POTNR7 | POTNR7 | Namakkal | Coimbatore |  | ROTN | Ascend | - | - |  | SR | 2022-03-16 | POTNR7 | 4G_FD900_POTNR7 | 4G_FD2100_POTNR7 | 4G_TD_POTNR7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362756 | 2021-06-26 | P/FVC/MDS/1050028/2021 | 2021-08-09 | ST202103082640 | 2021-03-06 | P/FVC/MDS/1013439/2021 | 2021-03-17 |  |  |  |  | ST202103082315 | 2021-03-06 | P/FBW/MDS/1013407/2021 | 2021-03-17
1241 | SIGMP1 | SIGMP1 | Sivaganga | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-04 | SIGMP1 | 4G_FD900_SIGMP1 | 4G_FD2100_SIGMP1 | 4G_TD_SIGMP1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064644 | 2022-03-07 | P/FVC/MDS/1076942/2022 | 2022-03-23 | ST202203064598 | 2022-03-07 | P/FVC/MDS/1076915/2022 | 2022-03-23 |  |  |  |  | ST202203064533 | 2022-03-07 | P/FBW/MDS/1076884/2022 | 2022-03-23
1242 | ARGI22 | ARGI22 | Pudukkottai | Trichy |  | ROTN | ATC | TN/PU/AT/22618 | - |  | SO | 2022-03-16 | ARGI22 | 4G_FD900_ARGI22 | 4G_FD2100_ARGI22 | 4G_TD_ARGI22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108430680 | 2021-08-17 | P/FVC/MDS/1059635/2021 | 2021-09-12 | ST202108414423 | 2021-08-10 | P/FVC/MDS/1055944/2021 | 2021-09-05 | ST202211758049 | 2022-11-22 | P/FVC/MDS/1116770/2022 | 2022-11-29 | ST202108424122 | 2021-08-11 | P/FBW/MDS/1055966/2021 | 2021-09-05
1243 | MIMSL3 | MIMSL3 | Pudukkottai | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | MIMSL3 | 4G_FD900_MIMSL3 | 4G_FD2100_MIMSL3 | 4G_TD_MIMSL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073962 | 2022-03-16 | P/FVC/MDS/1077156/2022 | 2022-03-30 | ST202203073564 | 2022-03-16 | P/FVC/MDS/1077108/2022 | 2022-03-30 |  |  |  |  | ST202203072910 | 2022-03-15 | P/FBW/MDS/1077060/2022 | 2022-03-30
1244 | MDU482 | MDU482 | Madurai | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-03-16 | MDU482 | 4G_FD900_MDU482 | 4G_FD2100_MDU482 | 4G_TD_MDU482 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084515 | 2022-03-28 | P/FVC/MDS/1078024/2022 | 2022-04-14 | ST202203084446 | 2022-03-28 | P/FVC/MDS/1077925/2022 | 2022-04-14 |  |  |  |  | ST202203082506 | 2022-03-26 | P/FBW/MDS/1077769/2022 | 2022-04-14
1245 | MDBKM3 | MDBKM3 | Viluppuram | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | MDBKM3 | 4G_FD900_MDBKM3 | 4G_FD2100_MDBKM3 | 4G_TD_MDBKM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073957 | 2022-03-16 | P/FVC/MDS/1077152/2022 | 2022-03-30 | ST202203073557 | 2022-03-16 | P/FVC/MDS/1077104/2022 | 2022-03-30 |  |  |  |  | ST202203072894 | 2022-03-15 | P/FBW/MDS/1077056/2022 | 2022-03-30
1246 | PUNLV1 | PUNLV1 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | PUNLV1 | 4G_FD900_PUNLV1 | 4G_FD2100_PUNLV1 | 4G_TD_PUNLV1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073966 | 2022-03-16 | P/FVC/MDS/1077157/2022 | 2022-03-30 | ST202203073565 | 2022-03-16 | P/FVC/MDS/1077109/2022 | 2022-03-30 |  |  |  |  | ST202203072911 | 2022-03-15 | P/FBW/MDS/1077061/2022 | 2022-03-30
1247 | SLMAN6 | SLMAN6 | Madurai | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-16 | SLMAN6 | 4G_FD900_SLMAN6 | 4G_FD2100_SLMAN6 | 4G_TD_SLMAN6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084511 | 2022-03-28 | P/FVC/MDS/1078023/2022 | 2022-04-14 | ST202203084445 | 2022-03-28 | P/FVC/MDS/1077924/2022 | 2022-04-14 |  |  |  |  | ST202203082505 | 2022-03-26 | P/FBW/MDS/1077768/2022 | 2022-04-14
1248 | PDYM54 | PDYM54 | Cuddalore | Trichy |  | ROTN | ATC | TN/CU/AT/22748 | - |  | On Air | 2022-03-16 | PDYM54 | 4G_FD900_PDYM54 | 4G_FD2100_PDYM54 | 4G_TD_PDYM54 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085309 | 2022-03-29 | P/FVC/MDS/1078048/2022 | 2022-04-14 | ST202204093071 | 2022-04-06 | P/FVC/MDS/1078311/2022 | 2022-04-21 |  |  |  |  | ST202204092315 | 2022-04-06 | P/FBW/MDS/1078279/2022 | 2022-04-21
1249 | TIRUX4 | TIRUX4 | Viluppuram | Trichy |  | ROTN | Indus | IN-3059812 | IN-3059812 |  |  | 2021-10-30 | TIRUX4 | 4G_FD900_TIRUX4 | 4G_FD2100_TIRUX4 | 4G_TD_TIRUX4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110577527 | 2021-10-30 | P/FVC/MDS/1065911/2021 | 2021-11-16 | ST202110577706 | 2021-10-30 | P/FVC/MDS/1065923/2021 | 2021-11-16 |  |  |  |  | ST202110577789 | 2021-10-30 | P/FBW/MDS/1067962/2021 | 2021-12-08
1250 | VALVA4 | VALVA4 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3126183 | R/NN-648306 |  | SRB(Surrender) | 2022-03-17 | VALVA4 | 4G_FD900_VALVA4 | 4G_FD2100_VALVA4 | 4G_TD_VALVA4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084563 | 2022-03-29 | P/FVC/MDS/1078044/2022 | 2022-04-14 | ST202203084469 | 2022-03-28 | P/FVC/MDS/1077945/2022 | 2022-04-14 |  |  |  |  | ST202203082659 | 2022-03-26 | P/FBW/MDS/1077813/2022 | 2022-04-14
1251 | PNVA20 | PNVA20 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3124031 | R/NN-645864 |  | SO(Rural Hold) | 2022-03-10 | PNVA20 | 4G_FD900_PNVA20 | 4G_FD2100_PNVA20 | 4G_TD_PNVA20 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074028 | 2022-03-16 | P/FVC/MDS/1077183/2022 | 2022-03-30 | ST202203073648 | 2022-03-16 | P/FVC/MDS/1077135/2022 | 2022-03-30 |  |  |  |  | ST202203072948 | 2022-03-15 | P/FBW/MDS/1077072/2022 | 2022-03-30
1252 | PDY365 | PDY365 | Puducherry | Trichy |  | ROTN | INDUS | IN-3073558 | R/RES-509635 |  | On Air | 2022-03-04 | PDY365 | 4G_FD900_PDY365 | 4G_FD2100_PDY365 | 4G_TD_PDY365 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064649 | 2022-03-07 | P/FVC/MDS/1076947/2022 | 2022-03-23 | ST202202056432 | 2022-02-26 | P/FVC/MDS/1075693/2022 | 2022-03-10 |  |  |  |  | ST202202056460 | 2022-02-26 | P/FBW/MDS/1075570/2022 | 2022-03-10
1253 | VANKAD | VANKAD | Pudukkottai | Trichy |  | ROTN | Indus | IN-1129840 | R/RES-509688 |  | On Air | 2022-03-11 | VANKAD | 4G_FD900_VANKAD | 4G_FD2100_VANKAD | 4G_TD_VANKAD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522044 | 2021-09-16 | P/FVC/MDS/1062381/2021 | 2021-09-23 | ST202109522169 | 2021-09-16 | P/FVC/MDS/1062432/2021 | 2021-09-23 |  |  |  |  | ST202109522229 | 2021-09-16 | P/FBW/MDS/1062480/2021 | 2021-09-23
1254 | ALAKA1 | ALAKA1 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3124987 | R/NN-646636 |  | SP | 2022-03-08 | ALAKA1 | 4G_FD900_ALAKA1 | 4G_FD2100_ALAKA1 | 4G_TD_ALAKA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092701 | 2022-04-06 | P/FVC/MDS/1078375/2022 | 2022-04-21 | ST202204093138 | 2022-04-07 | P/FVC/MDS/1078335/2022 | 2022-04-21 |  |  |  |  | ST202204092283 | 2022-04-06 | P/FBW/MDS/1078272/2022 | 2022-04-21
1255 | OKAKUD | OKAKUD | Thanjavur | Trichy |  | ROTN | Indus | IN-3123942 | R/NN-645763 |  | On Air | 2022-03-08 | OKAKUD | 4G_FD900_OKAKUD | 4G_FD2100_OKAKUD | 4G_TD_OKAKUD | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522062 | 2021-09-16 | P/FVC/MDS/1062400/2021 | 2021-09-23 | ST202109522192 | 2021-09-16 | P/FVC/MDS/1062450/2021 | 2021-09-23 |  |  |  |  | ST202109522247 | 2021-09-16 | P/FBW/MDS/1062498/2021 | 2021-09-23
1256 | VIRIAN | VIRIAN | Thanjavur | Trichy |  | ROTN | Indus | IN-3123946 | R/NN-645770 |  | On Air | 2022-03-08 | VIRIAN | 4G_FD900_VIRIAN | 4G_FD2100_VIRIAN | 4G_TD_VIRIAN | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073995 | 2022-03-16 | P/FVC/MDS/1077171/2022 | 2022-03-30 | ST202203073624 | 2022-03-16 | P/FVC/MDS/1077123/2022 | 2022-03-30 |  |  |  |  | ST202203072953 | 2022-03-15 | P/FBW/MDS/1077076/2022 | 2022-03-30
1257 | CHANUR | CHANUR | Salem | Vellore |  | ROTN | Indus | IN-3124076 | R/NN-645573 |  | On Air | 2022-03-08 | CHANUR | 4G_FD900_CHANUR | 4G_FD2100_CHANUR | 4G_TD_CHANUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073980 | 2022-03-16 | P/FVC/MDS/1077164/2022 | 2022-03-30 | ST202203073583 | 2022-03-16 | P/FVC/MDS/1077116/2022 | 2022-03-30 |  |  |  |  | ST202203072937 | 2022-03-15 | P/FBW/MDS/1077068/2022 | 2022-03-30
1258 | NORACH | NORACH | Salem | Vellore |  | ROTN | Indus | IN-3123811 | R/NN-645575 |  |  | 2022-03-16 | NORACH | 4G_FD900_NORACH | 4G_FD2100_NORACH | 4G_TD_NORACH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110559423 | 2021-10-14 | P/FVC/MDS/1063745/2021 | 2021-10-22 | ST202110560217 | 2021-10-14 | P/FVC/MDS/1063721/2021 | 2021-10-22 |  |  |  |  | ST202110560335 | 2021-10-14 | P/FVC/MDS/1063696/2021 | 2021-10-22
1259 | MITTAH | MITTAH | Krishnagiri | Vellore |  | ROTN | Indus | IN-3123950 | R/NN-645771 |  | On Air | 2022-03-04 | MITTAH | 4G_FD900_MITTAH | 4G_FD2100_MITTAH | 4G_TD_MITTAH | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064648 | 2022-03-07 | P/FVC/MDS/1076946/2022 | 2022-03-23 | ST202203064606 | 2022-03-07 | P/FVC/MDS/1076920/2022 | 2022-03-23 |  |  |  |  | ST202203064539 | 2022-03-07 | P/FBW/MDS/1076889/2022 | 2022-03-23
1260 | KOTGAM | KOTGAM | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2021-12-29 | KOTGAM | 4G_FD900_KOTGAM | 4G_FD2100_KOTGAM | 4G_TD_KOTGAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201003438 | 2022-01-05 | P/FVC/MDS/1071083/2022 | 2022-01-10 | ST202201003452 | 2022-01-06 | P/FVC/MDS/1071092/2022 | 2022-01-10 |  |  |  |  | ST202201003462 | 2022-01-06 | P/FBW/MDS/1071102/2022 | 2022-01-10
1261 | CHARAM | CHARAM | Cuddalore | Trichy |  | ROTN | Indus | IN-3123836 | R/NN-645598 |  | On Air | 2022-03-16 | CHARAM | 4G_FD900_CHARAM | 4G_FD2100_CHARAM | 4G_TD_CHARAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574160 | 2021-10-28 | P/FVC/MDS/1065858/2021 | 2021-11-16 | ST202110573042 | 2021-10-27 | P/FVC/MDS/1065731/2021 | 2021-11-16 |  |  |  |  | ST202110572524 | 2021-10-27 | P/FBW/MDS/1067911/2021 | 2021-12-08
1262 | DEVAUR | DEVAUR | Salem | Vellore |  | ROTN | Indus | IN-3123840 | R/NN-645603 |  | On Air | 2022-03-08 | DEVAUR | 4G_FD900_DEVAUR | 4G_FD2100_DEVAUR | 4G_TD_DEVAUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073982 | 2022-03-16 | P/FVC/MDS/1077165/2022 | 2022-03-30 | ST202203073587 | 2022-03-16 | P/FVC/MDS/1077117/2022 | 2022-03-30 |  |  |  |  | ST202203072938 | 2022-03-15 | P/FBW/MDS/1077069/2022 | 2022-03-30
1263 | OTTPAT | OTTPAT | Salem | Vellore |  | ROTN | Indus | IN-3123841 | R/NN-645609 |  | On Air | 2022-03-08 | OTTPAT | 4G_FD900_OTTPAT | 4G_FD2100_OTTPAT | 4G_TD_OTTPAT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073983 | 2022-03-16 | P/FVC/MDS/1077166/2022 | 2022-03-30 | ST202203073588 | 2022-03-16 | P/FVC/MDS/1077118/2022 | 2022-03-30 |  |  |  |  | ST202203072939 | 2022-03-15 | P/FBW/MDS/1077070/2022 | 2022-03-30
1264 | NARNAM | NARNAM | Salem | Vellore |  | ROTN | Indus | IN-3123845 | R/NN-645613 |  | On Air | 2022-03-08 | NARNAM | 4G_FD900_NARNAM | 4G_FD2100_NARNAM | 4G_TD_NARNAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073984 | 2022-03-16 | P/FVC/MDS/1077167/2022 | 2022-03-30 | ST202203073589 | 2022-03-16 | P/FVC/MDS/1077119/2022 | 2022-03-30 |  |  |  |  | ST202203072947 | 2022-03-15 | P/FBW/MDS/1077071/2022 | 2022-03-30
1265 | KARKAL | KARKAL | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22955 | - |  | On Air | 2022-03-16 | KARKAL | 4G_FD900_KARKAL | 4G_FD2100_KARKAL | 4G_TD_KARKAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084554 | 2022-03-29 | P/FVC/MDS/1078035/2022 | 2022-04-14 | ST202203084457 | 2022-03-28 | P/FVC/MDS/1077936/2022 | 2022-04-14 |  |  |  |  | ST202203082577 | 2022-03-26 | P/FBW/MDS/1077785/2022 | 2022-04-14
1266 | THALIK | THALIK | Krishnagiri | Vellore |  | ROTN | Indus | IN-3123847 | R/NN-645617 |  | SO(Rural Hold) | 2022-03-10 | THALIK | 4G_FD900_THALIK | 4G_FD2100_THALIK | 4G_TD_THALIK | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074004 | 2022-03-16 | P/FVC/MDS/1077176/2022 | 2022-03-30 | ST202203073634 | 2022-03-16 | P/FVC/MDS/1077128/2022 | 2022-03-30 |  |  |  |  | ST202203072973 | 2022-03-15 | P/FBW/MDS/1077081/2022 | 2022-03-30
1267 | MARIGA | MARIGA | Krishnagiri | Vellore |  | ROTN | Indus | IN-3123849 | R/NN-645627 |  | On Air | 2022-03-04 | MARIGA | 4G_FD900_MARIGA | 4G_FD2100_MARIGA | 4G_TD_MARIGA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203065072 | 2022-03-08 | P/FVC/MDS/1076964/2022 | 2022-03-23 | ST202203064603 | 2022-03-07 | P/FVC/MDS/1076919/2022 | 2022-03-23 |  |  |  |  | ST202203064538 | 2022-03-07 | P/FBW/MDS/1076888/2022 | 2022-03-23
1268 | THANAM | THANAM | Krishnagiri | Vellore |  | ROTN | Indus | IN-3123916 | R/NN-645708 |  | On Air | 2022-03-16 | THANAM | 4G_FD900_THANAM | 4G_FD2100_THANAM | 4G_TD_THANAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111586236 | 2021-11-10 | P/FVC/MDS/1068158/2021 | 2021-12-08 | ST202111588034 | 2021-11-12 | P/FVC/MDS/1068175/2021 | 2021-12-08 |  |  |  |  | ST202111588148 | 2021-11-12 | P/FBW/MDS/1068193/2021 | 2021-12-08
1269 | KOTHAP | KOTHAP | Krishnagiri | Vellore |  | ROTN | Indus | IN-3123918 | R/NN-645713 |  | On Air | 2022-03-10 | KOTHAP | 4G_FD900_KOTHAP | 4G_FD2100_KOTHAP | 4G_TD_KOTHAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074001 | 2022-03-16 | P/FVC/MDS/1077174/2022 | 2022-03-30 | ST202203073632 | 2022-03-16 | P/FVC/MDS/1077126/2022 | 2022-03-30 |  |  |  |  | ST202203072971 | 2022-03-15 | P/FBW/MDS/1077079/2022 | 2022-03-30
1270 | KASIMP | KASIMP | Pudukkottai | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-03-25 | KASIMP | 4G_FD900_KASIMP | 4G_FD2100_KASIMP | 4G_TD_KASIMP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111595150 | 2021-11-19 | P/FVC/MDS/1067070/2021 | 2021-12-01 | ST202110578541 | 2021-10-31 | P/FVC/MDS/1067984/2021 | 2021-12-08 |  |  |  |  | ST202111595309 | 2021-11-19 | P/FBW/MDS/1067046/2021 | 2021-12-01
1271 | KODUMB | KODUMB | Pudukkottai | Trichy |  | ROTN | Indus | IN-3123925 | R/NN-645738 |  | On Air | 2022-03-16 | KODUMB | 4G_FD900_KODUMB | 4G_FD2100_KODUMB | 4G_TD_KODUMB | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202111595151 | 2021-11-19 | P/FVC/MDS/1067071/2021 | 2021-12-01 | ST202111595245 | 2021-11-19 | P/FVC/MDS/1067058/2021 | 2021-12-01 |  |  |  |  | ST202111595310 | 2021-11-19 | P/FBW/MDS/1067047/2021 | 2021-12-01
1272 | KARAM2 | KARAM2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3124074 | R/NN-645867 |  | SO | 2022-03-08 | KARAM2 | 4G_FD900_KARAM2 | 4G_FD2100_KARAM2 | 4G_TD_KARAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073988 | 2022-03-16 | P/FVC/MDS/1077170/2022 | 2022-03-30 | ST202203073620 | 2022-03-16 | P/FVC/MDS/1077122/2022 | 2022-03-30 |  |  |  |  | ST202203072952 | 2022-03-15 | P/FBW/MDS/1077075/2022 | 2022-03-30
1273 | ULAPA2 | ULAPA2 | Sivaganga | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-16 | ULAPA2 | 4G_FD900_ULAPA2 | 4G_FD2100_ULAPA2 | 4G_TD_ULAPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084550 | 2022-03-29 | P/FVC/MDS/1078031/2022 | 2022-04-14 | ST202203084453 | 2022-03-28 | P/FVC/MDS/1077932/2022 | 2022-04-14 |  |  |  |  | ST202203082531 | 2022-03-26 | P/FBW/MDS/1077776/2022 | 2022-04-14
1274 | PADAI2 | PADAI2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3123926 | R/NN-645740 |  | On Air | 2022-03-08 | PADAI2 | 4G_FD900_PADAI2 | 4G_FD2100_PADAI2 | 4G_TD_PADAI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073986 | 2022-03-16 | P/FVC/MDS/1077168/2022 | 2022-03-30 | ST202203073618 | 2022-03-16 | P/FVC/MDS/1077120/2022 | 2022-03-30 |  |  |  |  | ST202203072949 | 2022-03-15 | P/FBW/MDS/1077073/2022 | 2022-03-30
1275 | KULAI6 | KULAI6 | Dindigul | Coimbatore |  | ROTN | Indus | IN-3124073 | R/NN-645868 |  | On Air | 2022-03-01 | KULAI6 | 4G_FD900_KULAI6 | 4G_FD2100_KULAI6 | 4G_TD_KULAI6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061492 | 2022-03-03 | P/FVC/MDS/1076630/2022 | 2022-03-13 | ST202203064587 | 2022-03-07 | P/FVC/MDS/1076909/2022 | 2022-03-23 |  |  |  |  | ST202203062356 | 2022-03-04 | P/FBW/MDS/1076526/2022 | 2022-03-13
1276 | COLAP3 | COLAP3 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/22929 | - |  | On Air | 2022-03-16 | COLAP3 | 4G_FD900_COLAP3 | 4G_FD2100_COLAP3 | 4G_TD_COLAP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084562 | 2022-03-29 | P/FVC/MDS/1078043/2022 | 2022-04-14 | ST202203084468 | 2022-03-28 | P/FVC/MDS/1077944/2022 | 2022-04-14 |  |  |  |  | ST202203082636 | 2022-03-26 | P/FBW/MDS/1077802/2022 | 2022-04-14
1277 | KAKPA2 | KAKPA2 | Thanjavur | Trichy |  | ROTN | Summit | I-TN-TVDD-ENB-9033 | SR-TN000900 |  | On Air | 2022-02-28 | KAKPA2 | 4G_FD900_KAKPA2 | 4G_FD2100_KAKPA2 | 4G_TD_KAKPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061354 | 2022-03-03 | P/FVC/MDS/1076603/2022 | 2022-03-13 | ST202203059678 | 2022-03-02 | P/FVC/MDS/1076556/2022 | 2022-03-13 |  |  |  |  | ST202203062626 | 2022-03-04 | P/FBW/MDS/1076530/2022 | 2022-03-13
1278 | KELMI3 | KELMI3 | Thiruvarur | Trichy |  | ROTN | Indus | IN-3121047 | R/NN-642283 |  | SO | 2022-03-08 | KELMI3 | 4G_FD900_KELMI3 | 4G_FD2100_KELMI3 | 4G_TD_KELMI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209404978 | 2022-09-09 | P/FVC/MDS/1096565/2022 | 2022-09-16 | ST202209404060 | 2022-09-08 | P/FVC/MDS/1096474/2022 | 2022-09-16 |  |  |  |  | ST202209399067 | 2022-09-07 | P/FVC/MDS/1096380/2022 | 2022-09-16
1279 | KATHA2 | KATHA2 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3123933 | R/NN-645748 |  | On Air | 2022-03-01 | KATHA2 | 4G_FD900_KATHA2 | 4G_FD2100_KATHA2 | 4G_TD_KATHA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061486 | 2022-03-03 | P/FVC/MDS/1076628/2022 | 2022-03-13 | ST202203061586 | 2022-03-03 | P/FVC/MDS/1076580/2022 | 2022-03-13 |  |  |  |  | ST202203062350 | 2022-03-04 | P/FBW/MDS/1076524/2022 | 2022-03-13
1280 | MALAI2 | MALAI2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121083 | R/NN-642347 |  | On Air | 2022-03-16 | MALAI2 | 4G_FD900_MALAI2 | 4G_FD2100_MALAI2 | 4G_TD_MALAI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084556 | 2022-03-29 | P/FVC/MDS/1078037/2022 | 2022-04-14 | ST202203084459 | 2022-03-28 | P/FVC/MDS/1077938/2022 | 2022-04-14 |  |  |  |  | ST202203082588 | 2022-03-26 | P/FBW/MDS/1077789/2022 | 2022-04-14
1281 | ELANJ2 | ELANJ2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3123936 | R/NN-645751 |  | On Air | 2022-03-01 | ELANJ2 | 4G_FD900_ELANJ2 | 4G_FD2100_ELANJ2 | 4G_TD_ELANJ2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061485 | 2022-03-03 | P/FVC/MDS/1076627/2022 | 2022-03-13 | ST202203061581 | 2022-03-03 | P/FVC/MDS/1076579/2022 | 2022-03-13 |  |  |  |  | ST202203062299 | 2022-03-04 | P/FBW/MDS/1076523/2022 | 2022-03-13
1282 | MARAY2 | MARAY2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121279 | R/NN-642359 |  | On Air | 2022-03-16 | MARAY2 | 4G_FD900_MARAY2 | 4G_FD2100_MARAY2 | 4G_TD_MARAY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084558 | 2022-03-29 | P/FVC/MDS/1078039/2022 | 2022-04-14 | ST202203084461 | 2022-03-28 | P/FVC/MDS/1077940/2022 | 2022-04-14 |  |  |  |  | ST202203082608 | 2022-03-26 | P/FBW/MDS/1077797/2022 | 2022-04-14
1283 | PAKAM2 | PAKAM2 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-03-16 | PAKAM2 | 4G_FD900_PAKAM2 | 4G_FD2100_PAKAM2 | 4G_TD_PAKAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084510 | 2022-03-28 | P/FVC/MDS/1078022/2022 | 2022-04-14 | ST202203084444 | 2022-03-28 | P/FVC/MDS/1077923/2022 | 2022-04-14 |  |  |  |  | ST202203082504 | 2022-03-26 | P/FBW/MDS/1077767/2022 | 2022-04-14
1284 | TIRMY2 | TIRMY2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3121129 | R/NN-642372 |  | On Air | 2022-03-08 | TIRMY2 | 4G_FD900_TIRMY2 | 4G_FD2100_TIRMY2 | 4G_TD_TIRMY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073891 | 2022-03-16 | P/FVC/MDS/1077148/2022 | 2022-03-30 | ST202203073546 | 2022-03-16 | P/FVC/MDS/1077100/2022 | 2022-03-30 |  |  |  |  | ST202203072883 | 2022-03-15 | P/FBW/MDS/1077052/2022 | 2022-03-30
1285 | KGRI46 | KGRI46 | Krishnagiri | Vellore |  | ROTN | Ascend |  |  |  | On Air | 2022-03-25 | KGRI46 | 4G_FD900_KGRI46 | 4G_FD2100_KGRI46 | 4G_TD_KGRI46 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085712 | 2022-03-29 | P/FVC/MDS/1078098/2022 | 2022-04-14 | ST202203084803 | 2022-03-29 | P/FVC/MDS/1078000/2022 | 2022-04-14 |  |  |  |  | ST202203082702 | 2022-03-26 | P/FBW/MDS/1077841/2022 | 2022-04-14
1286 | TCGD51 | TCGD51 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22993 | - |  | On Air | 2022-03-16 | TCGD51 | 4G_FD900_TCGD51 | 4G_FD2100_TCGD51 | 4G_TD_TCGD51 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084502 | 2022-03-28 | P/FVC/MDS/1078017/2022 | 2022-04-14 | ST202203084088 | 2022-03-28 | P/FVC/MDS/1077918/2022 | 2022-04-14 |  |  |  |  | ST202203082314 | 2022-03-26 | P/FBW/MDS/1077761/2022 | 2022-04-14
1287 | PLNGM3 | PLNGM3 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-04 | PLNGM3 | 4G_FD900_PLNGM3 | 4G_FD2100_PLNGM3 | 4G_TD_PLNGM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064646 | 2022-03-07 | P/FVC/MDS/1076944/2022 | 2022-03-23 | ST202203064600 | 2022-03-07 | P/FVC/MDS/1076917/2022 | 2022-03-23 |  |  |  |  | ST202203064535 | 2022-03-07 | P/FBW/MDS/1076886/2022 | 2022-03-23
1288 | ASARP3 | ASARP3 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-04 | ASARP3 | 4G_FD900_ASARP3 | 4G_FD2100_ASARP3 | 4G_TD_ASARP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064647 | 2022-03-07 | P/FVC/MDS/1076945/2022 | 2022-03-23 | ST202203064602 | 2022-03-07 | P/FVC/MDS/1076918/2022 | 2022-03-23 |  |  |  |  | ST202203064536 | 2022-03-07 | P/FBW/MDS/1076887/2022 | 2022-03-23
1289 | ASARP4 | ASARP4 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-03-08 | ASARP4 | 4G_FD900_ASARP4 | 4G_FD2100_ASARP4 | 4G_TD_ASARP4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073901 | 2022-03-16 | P/FVC/MDS/1077150/2022 | 2022-03-30 | ST202203073552 | 2022-03-16 | P/FVC/MDS/1077102/2022 | 2022-03-30 |  |  |  |  | ST202203072885 | 2022-03-15 | P/FBW/MDS/1077054/2022 | 2022-03-30
1290 | ASARP5 | ASARP5 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | ASARP5 | 4G_FD900_ASARP5 | 4G_FD2100_ASARP5 | 4G_TD_ASARP5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073968 | 2022-03-16 | P/FVC/MDS/1077159/2022 | 2022-03-30 | ST202203073570 | 2022-03-16 | P/FVC/MDS/1077111/2022 | 2022-03-30 |  |  |  |  | ST202203072917 | 2022-03-15 | P/FBW/MDS/1077063/2022 | 2022-03-30
1291 | KUDIK2 | KUDIK2 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | KUDIK2 | 4G_FD900_KUDIK2 | 4G_FD2100_KUDIK2 | 4G_TD_KUDIK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073900 | 2022-03-16 | P/FVC/MDS/1077149/2022 | 2022-03-30 | ST202203073551 | 2022-03-16 | P/FVC/MDS/1077101/2022 | 2022-03-30 |  |  |  |  | ST202203072884 | 2022-03-15 | P/FBW/MDS/1077053/2022 | 2022-03-30
1292 | THOZR2 | THOZR2 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-03-04 | THOZR2 | 4G_FD900_THOZR2 | 4G_FD2100_THOZR2 | 4G_TD_THOZR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064636 | 2022-03-07 | P/FVC/MDS/1076937/2022 | 2022-03-23 | ST202203064588 | 2022-03-07 | P/FVC/MDS/1076910/2022 | 2022-03-23 |  |  |  |  | ST202203062617 | 2022-03-04 | P/FBW/MDS/1076528/2022 | 2022-03-13
1293 | NMKL68 | NMKL68 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22978 | - |  | On Air | 2022-03-16 | NMKL68 | 4G_FD900_NMKL68 | 4G_FD2100_NMKL68 | 4G_TD_NMKL68 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084548 | 2022-03-29 | P/FVC/MDS/1078029/2022 | 2022-04-14 | ST202203084451 | 2022-03-28 | P/FVC/MDS/1077930/2022 | 2022-04-14 |  |  |  |  | ST202203082528 | 2022-03-26 | P/FBW/MDS/1077774/2022 | 2022-04-14
1294 | RMPM50 | RMPM50 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-16 | RMPM50 | 4G_FD900_RMPM50 | 4G_FD2100_RMPM50 | 4G_TD_RMPM50 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084549 | 2022-03-29 | P/FVC/MDS/1078030/2022 | 2022-04-14 | ST202203084452 | 2022-03-28 | P/FVC/MDS/1077931/2022 | 2022-04-14 |  |  |  |  | ST202203082529 | 2022-03-26 | P/FBW/MDS/1077775/2022 | 2022-04-14
1295 | KVPT51 | KVPT51 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-03-08 | KVPT51 | 4G_FD900_KVPT51 | 4G_FD2100_KVPT51 | 4G_TD_KVPT51 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360980 | 2022-08-28 | P/FVC/MDS/1094652/2022 | 2022-09-07 | ST202208364553 | 2022-08-29 | P/FVC/MDS/1094717/2022 | 2022-09-07 |  |  |  |  | ST202208355404 | 2022-08-26 | P/FBW/MDS/1094589/2022 | 2022-09-07
1296 | NALPU2 | NALPU2 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | NALPU2 | 4G_FD900_NALPU2 | 4G_FD2100_NALPU2 | 4G_TD_NALPU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073956 | 2022-03-16 | P/FVC/MDS/1077151/2022 | 2022-03-30 | ST202203073553 | 2022-03-16 | P/FVC/MDS/1077103/2022 | 2022-03-30 |  |  |  |  | ST202203072893 | 2022-03-15 | P/FBW/MDS/1077055/2022 | 2022-03-30
1297 | KKDI72 | KKDI72 | Sivaganga | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | KKDI72 | 4G_FD900_KKDI72 | 4G_FD2100_KKDI72 | 4G_TD_KKDI72 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073979 | 2022-03-16 | P/FVC/MDS/1077163/2022 | 2022-03-30 | ST202203073582 | 2022-03-16 | P/FVC/MDS/1077115/2022 | 2022-03-30 |  |  |  |  | ST202203072929 | 2022-03-15 | P/FBW/MDS/1077067/2022 | 2022-03-30
1298 | CBE907 | CBE907 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22981 | - |  | On Air | 2022-03-16 | CBE907 | 4G_FD900_CBE907 | 4G_FD2100_CBE907 | 4G_TD_CBE907 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084506 | 2022-03-28 | P/FVC/MDS/1078020/2022 | 2022-04-14 | ST202203084442 | 2022-03-28 | P/FVC/MDS/1077921/2022 | 2022-04-14 |  |  |  |  | ST202203082318 | 2022-03-26 | P/FBW/MDS/1077764/2022 | 2022-04-14
1299 | PDMPL3 | PDMPL3 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22982 | - |  | On Air | 2022-03-16 | PDMPL3 | 4G_FD900_PDMPL3 | 4G_FD2100_PDMPL3 | 4G_TD_PDMPL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084505 | 2022-03-28 | P/FVC/MDS/1078019/2022 | 2022-04-14 | ST202203084441 | 2022-03-28 | P/FVC/MDS/1077920/2022 | 2022-04-14 |  |  |  |  | ST202203082317 | 2022-03-26 | P/FBW/MDS/1077763/2022 | 2022-04-14
1300 | CBE908 | CBE908 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22983 | - |  | On Air | 2022-03-16 | CBE908 | 4G_FD900_CBE908 | 4G_FD2100_CBE908 | 4G_TD_CBE908 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123453 | 2022-04-30 | P/FVC/MDS/1079430/2022 | 2022-05-16 | ST202204119661 | 2022-04-26 | P/FVC/MDS/1079345/2022 | 2022-05-13 | ST202209444099 | 2022-09-19 | P/FVC/MDS/1098037/2022 | 2022-09-27 | ST202204119418 | 2022-04-26 | P/FBW/MDS/1079253/2022 | 2022-05-13
1301 | CBE911 | CBE911 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22986 | - |  | On Air | 2022-03-16 | CBE911 | 4G_FD900_CBE911 | 4G_FD2100_CBE911 | 4G_TD_CBE911 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084516 | 2022-03-28 | P/FVC/MDS/1078025/2022 | 2022-04-14 | ST202203084447 | 2022-03-28 | P/FVC/MDS/1077926/2022 | 2022-04-14 |  |  |  |  | ST202203082515 | 2022-03-26 | P/FBW/MDS/1077770/2022 | 2022-04-14
1302 | CBE912 | CBE912 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22987 | - |  | On Air | 2022-03-16 | CBE912 | 4G_FD900_CBE912 | 4G_FD2100_CBE912 | 4G_TD_CBE912 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084507 | 2022-03-28 | P/FVC/MDS/1078021/2022 | 2022-04-14 | ST202203084443 | 2022-03-28 | P/FVC/MDS/1077922/2022 | 2022-04-14 |  |  |  |  | ST202203082319 | 2022-03-26 | P/FBW/MDS/1077765/2022 | 2022-04-14
1303 | MDU530 | MDU530 | Madurai | Madurai |  | ROTN | ATC |  |  |  | SR | 2022-03-22 | MDU530 | 4G_FD900_MDU530 | 4G_FD2100_MDU530 | 4G_TD_MDU530 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085665 | 2022-03-29 | P/FVC/MDS/1078084/2022 | 2022-04-14 | ST202203084703 | 2022-03-29 | P/FVC/MDS/1077985/2022 | 2022-04-14 |  |  |  |  | ST202203082673 | 2022-03-26 | P/FBW/MDS/1077826/2022 | 2022-04-14
1304 | PDY366 | PDY366 | Puducherry | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-03-25 | PDY366 | 4G_FD900_PDY366 | 4G_FD2100_PDY366 | 4G_TD_PDY366 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085729 | 2022-03-29 | P/FVC/MDS/1078106/2022 | 2022-04-14 | ST202203084830 | 2022-03-29 | P/FVC/MDS/1078008/2022 | 2022-04-14 |  |  |  |  | ST202203082757 | 2022-03-26 | P/FBW/MDS/1077849/2022 | 2022-04-14
1305 | KUMB86 | KUMB86 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | SR | 2022-03-08 | KUMB86 | 4G_FD900_KUMB86 | 4G_FD2100_KUMB86 | 4G_TD_KUMB86 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073972 | 2022-03-16 | P/FVC/MDS/1077161/2022 | 2022-03-30 | ST202203073577 | 2022-03-16 | P/FVC/MDS/1077113/2022 | 2022-03-30 |  |  |  |  | ST202203072927 | 2022-03-15 | P/FBW/MDS/1077065/2022 | 2022-03-30
1306 | TRY392 | TRY392 | Tiruchirappalli | Trichy |  | ROTN | ATC |  |  |  | On Air | 2022-03-22 | TRY392 | 4G_FD900_TRY392 | 4G_FD2100_TRY392 | 4G_TD_TRY392 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085844 | 2022-03-30 | P/FVC/MDS/1078167/2022 | 2022-04-15 | ST202203084938 | 2022-03-29 | P/FVC/MDS/1078122/2022 | 2022-04-15 |  |  |  |  | ST202203083974 | 2022-03-28 | P/FBW/MDS/1077880/2022 | 2022-04-14
1307 | TRY393 | TRY393 | Tiruchirappalli | Trichy |  | ROTN | ATC |  |  |  | SO | 2022-03-22 | TRY393 | 4G_FD900_TRY393 | 4G_FD2100_TRY393 | 4G_TD_TRY393 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361043 | 2022-08-28 | P/FVC/MDS/1094678/2022 | 2022-09-07 | ST202208364615 | 2022-08-29 | P/FVC/MDS/1094743/2022 | 2022-09-07 |  |  |  |  | ST202208355521 | 2022-08-26 | P/FBW/MDS/1094613/2022 | 2022-09-07
1308 | KATGP2 | KATGP2 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/22965 | - |  | On Air | 2022-03-16 | KATGP2 | 4G_FD900_KATGP2 | 4G_FD2100_KATGP2 | 4G_TD_KATGP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084546 | 2022-03-29 | P/FVC/MDS/1078027/2022 | 2022-04-14 | ST202203084449 | 2022-03-28 | P/FVC/MDS/1077928/2022 | 2022-04-14 |  |  |  |  | ST202203082523 | 2022-03-26 | P/FBW/MDS/1077772/2022 | 2022-04-14
1309 | VAGRP2 | VAGRP2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22988 | - |  | On Air | 2022-03-01 | VAGRP2 | 4G_FD900_VAGRP2 | 4G_FD2100_VAGRP2 | 4G_TD_VAGRP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061479 | 2022-03-03 | P/FVC/MDS/1076625/2022 | 2022-03-13 | ST202203061574 | 2022-03-03 | P/FVC/MDS/1076577/2022 | 2022-03-13 |  |  |  |  | ST202203062297 | 2022-03-04 | P/FBW/MDS/1076521/2022 | 2022-03-13
1310 | NMKL70 | NMKL70 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22989 | - |  | On Air | 2022-03-16 | NMKL70 | 4G_FD900_NMKL70 | 4G_FD2100_NMKL70 | 4G_TD_NMKL70 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074150 | 2022-03-16 | P/FVC/MDS/1077191/2022 | 2022-03-30 | ST202203084566 | 2022-03-29 | P/FVC/MDS/1077949/2022 | 2022-04-14 | ST202204095038 | 2022-04-08 | P/FVC/MDS/1078398/2022 | 2022-04-21 | ST202203082313 | 2022-03-26 | P/FBW/MDS/1077760/2022 | 2022-04-14
1311 | KULPI2 | KULPI2 | Virudhunagar | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-04 | KULPI2 | 4G_FD900_KULPI2 | 4G_FD2100_KULPI2 | 4G_TD_KULPI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064637 | 2022-03-07 | P/FVC/MDS/1076938/2022 | 2022-03-23 | ST202203064589 | 2022-03-07 | P/FVC/MDS/1076911/2022 | 2022-03-23 |  |  |  |  | ST202203062618 | 2022-03-04 | P/FBW/MDS/1076529/2022 | 2022-03-13
1312 | SLM405 | SLM405 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22969 | - |  | On Air | 2022-03-16 | SLM405 | 4G_FD900_SLM405 | 4G_FD2100_SLM405 | 4G_TD_SLM405 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084553 | 2022-03-29 | P/FVC/MDS/1078034/2022 | 2022-04-14 | ST202203084456 | 2022-03-28 | P/FVC/MDS/1077935/2022 | 2022-04-14 |  |  |  |  | ST202203082567 | 2022-03-26 | P/FBW/MDS/1077781/2022 | 2022-04-14
1313 | PGLPT3 | PGLPT3 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22971 | - |  | On Air | 2022-03-16 | PGLPT3 | 4G_FD900_PGLPT3 | 4G_FD2100_PGLPT3 | 4G_TD_PGLPT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084547 | 2022-03-29 | P/FVC/MDS/1078028/2022 | 2022-04-14 | ST202203084450 | 2022-03-28 | P/FVC/MDS/1077929/2022 | 2022-04-14 |  |  |  |  | ST202203082524 | 2022-03-26 | P/FBW/MDS/1077773/2022 | 2022-04-14
1314 | KTTYR9 | KTTYR9 | Sivaganga | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-03-08 | KTTYR9 | 4G_FD900_KTTYR9 | 4G_FD2100_KTTYR9 | 4G_TD_KTTYR9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111686 | 2022-04-20 | P/FVC/MDS/1078935/2022 | 2022-05-02 | ST202204110011 | 2022-04-19 | P/FVC/MDS/1078997/2022 | 2022-05-03 |  |  |  |  | ST202204109563 | 2022-04-19 | P/FVC/MDS/1078893/2022 | 2022-05-02
1315 | KVPT52 | KVPT52 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-03-04 | KVPT52 | 4G_FD900_KVPT52 | 4G_FD2100_KVPT52 | 4G_TD_KVPT52 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064638 | 2022-03-07 | P/FVC/MDS/1076939/2022 | 2022-03-23 | ST202203064592 | 2022-03-07 | P/FVC/MDS/1076912/2022 | 2022-03-23 |  |  |  |  | ST202203059258 | 2022-03-01 | P/FBW/MDS/1076511/2022 | 2022-03-13
1316 | PANYP2 | PANYP2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/22991 | - |  | On Air | 2022-03-16 | PANYP2 | 4G_FD900_PANYP2 | 4G_FD2100_PANYP2 | 4G_TD_PANYP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084545 | 2022-03-29 | P/FVC/MDS/1078026/2022 | 2022-04-14 | ST202203084448 | 2022-03-28 | P/FVC/MDS/1077927/2022 | 2022-04-14 |  |  |  |  | ST202203082516 | 2022-03-26 | P/FBW/MDS/1077771/2022 | 2022-04-14
1317 | TIVR39 | TIVR39 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-03-04 | TIVR39 | 4G_FD900_TIVR39 | 4G_FD2100_TIVR39 | 4G_TD_TIVR39 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403784 | 2022-09-08 | P/FVC/MDS/1096554/2022 | 2022-09-16 | ST202209403983 | 2022-09-08 | P/FVC/MDS/1096463/2022 | 2022-09-16 |  |  |  |  | ST202209399011 | 2022-09-07 | P/FVC/MDS/1096369/2022 | 2022-09-16
1318 | TIVR43 | TIVR43 | Thiruvarur | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-03-25 | TIVR43 | 4G_FD900_TIVR43 | 4G_FD2100_TIVR43 | 4G_TD_TIVR43 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085713 | 2022-03-29 | P/FVC/MDS/1078099/2022 | 2022-04-14 | ST202203084805 | 2022-03-29 | P/FVC/MDS/1078001/2022 | 2022-04-14 |  |  |  |  | ST202203082737 | 2022-03-26 | P/FBW/MDS/1077842/2022 | 2022-04-14
1319 | TIVR46 | TIVR46 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | SR | 2022-03-04 | TIVR46 | 4G_FD900_TIVR46 | 4G_FD2100_TIVR46 | 4G_TD_TIVR46 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110354 | 2022-04-19 | P/FVC/MDS/1078932/2022 | 2022-05-02 | ST202204109994 | 2022-04-19 | P/FVC/MDS/1078994/2022 | 2022-05-03 |  |  |  |  | ST202204109551 | 2022-04-19 | P/FVC/MDS/1078890/2022 | 2022-05-02
1320 | PAPAM3 | PAPAM3 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22992 | - |  | On Air | 2022-03-16 | PAPAM3 | 4G_FD900_PAPAM3 | 4G_FD2100_PAPAM3 | 4G_TD_PAPAM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084503 | 2022-03-28 | P/FVC/MDS/1078018/2022 | 2022-04-14 | ST202203084440 | 2022-03-28 | P/FVC/MDS/1077919/2022 | 2022-04-14 |  |  |  |  | ST202203082316 | 2022-03-26 | P/FBW/MDS/1077762/2022 | 2022-04-14
1321 | SHBIMX | SHBIMX | Karur | Coimbatore |  | ROTN | Ascend | - | - |  | On Air | 2022-03-08 | SHBIMX | 4G_FD900_SHBIMX | 4G_FD2100_SHBIMX | 4G_TD_SHBIMX | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203073996 | 2022-03-16 | P/FVC/MDS/1077172/2022 | 2022-03-30 | ST202203073625 | 2022-03-16 | P/FVC/MDS/1077124/2022 | 2022-03-30 |  |  |  |  | ST202203072963 | 2022-03-15 | P/FBW/MDS/1077077/2022 | 2022-03-30
1322 | LNIMCG | LNIMCG | Puducherry | Trichy |  | ROTN | Summit | I-TN-VLNR-ENB-0002 | SR-TN000902 |  | On Air | 2022-02-25 | LNIMCG | 4G_FD900_LNIMCG | 4G_FD2100_LNIMCG | 4G_TD_LNIMCG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056725 | 2022-02-27 | P/FVC/MDS/1076468/2022 | 2022-03-13 | ST202202055645 | 2022-02-26 | P/FVC/MDS/1075653/2022 | 2022-03-10 |  |  |  |  | ST202202056486 | 2022-02-26 | P/FBW/MDS/1075587/2022 | 2022-03-10
1323 | ARYPT2 | ARYPT2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-1106768 | R/RES-509469 |  | On Air | 2022-02-25 | ARYPT2 | 4G_FD900_ARYPT2 | 4G_FD2100_ARYPT2 | 4G_TD_ARYPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201007711 | 2022-01-11 | P/FVC/MDS/1071649/2022 | 2022-01-20 | ST202201008514 | 2022-01-12 | P/FVC/MDS/1071569/2022 | 2022-01-20 |  |  |  |  | ST202201007924 | 2022-01-11 | P/FBW/MDS/1071488/2022 | 2022-01-20
1324 | KAMAT2 | KAMAT2 | Theni | Madurai |  | ROTN | Indus | IN-1134865 | R/RES-509470 |  | On Air | 2022-02-25 | KAMAT2 | 4G_FD900_KAMAT2 | 4G_FD2100_KAMAT2 | 4G_TD_KAMAT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201022595 | 2022-01-28 | P/FVC/MDS/1072951/2022 | 2022-02-04 | ST202201022773 | 2022-01-28 | P/FVC/MDS/1072984/2022 | 2022-02-04 |  |  |  |  | ST202201022876 | 2022-01-28 | P/FBW/MDS/1073011/2022 | 2022-02-04
1325 | PUSVM3 | PUSVM3 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1258127 | R/RES-509471 |  | On Air | 2022-02-25 | PUSVM3 | 4G_FD900_PUSVM3 | 4G_FD2100_PUSVM3 | 4G_TD_PUSVM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201007708 | 2022-01-11 | P/FVC/MDS/1071648/2022 | 2022-01-20 | ST202201008513 | 2022-01-12 | P/FVC/MDS/1071568/2022 | 2022-01-20 |  |  |  |  | ST202201007920 | 2022-01-11 | P/FBW/MDS/1071487/2022 | 2022-01-20
1326 | NOCHY2 | NOCHY2 | Perambalur | Trichy |  | ROTN | Indus | IN-1335881 | R/RES-509475 |  | On Air | 2022-02-25 | NOCHY2 | 4G_FD900_NOCHY2 | 4G_FD2100_NOCHY2 | 4G_TD_NOCHY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201007717 | 2022-01-11 | P/FVC/MDS/1071653/2022 | 2022-01-20 | ST202201008525 | 2022-01-12 | P/FVC/MDS/1071573/2022 | 2022-01-20 |  |  |  |  | ST202201007930 | 2022-01-11 | P/FBW/MDS/1071492/2022 | 2022-01-20
1327 | NALLA3 | NALLA3 | Dharmapuri | Vellore |  | ROTN | ATC | TN/SA/PR/11113 | - |  | On Air | 2022-03-10 | NALLA3 | 4G_FD900_NALLA3 | 4G_FD2100_NALLA3 | 4G_TD_NALLA3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202201007719 | 2022-01-11 | P/FVC/MDS/1071655/2022 | 2022-01-20 | ST202201008528 | 2022-01-12 | P/FVC/MDS/1071575/2022 | 2022-01-20 | ST202210548425 | 2022-10-11 | P/FVC/MDS/1113918/2022 | 2022-10-21 | ST202201007935 | 2022-01-11 | P/FBW/MDS/1071494/2022 | 2022-01-20
1328 | THOND2 | THOND2 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/23027 | - |  | On Air | 2022-03-17 | THOND2 | 4G_FD900_THOND2 | 4G_FD2100_THOND2 | 4G_TD_THOND2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085639 | 2022-03-29 | P/FVC/MDS/1078073/2022 | 2022-04-14 | ST202203084679 | 2022-03-29 | P/FVC/MDS/1077974/2022 | 2022-04-14 |  |  |  |  | ST202203082658 | 2022-03-26 | P/FBW/MDS/1077812/2022 | 2022-04-14
1329 | NANJU5 | NANJU5 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3124087 | R/NN-645923 |  | On Air | 2022-03-10 | NANJU5 | 4G_FD900_NANJU5 | 4G_FD2100_NANJU5 | 4G_TD_NANJU5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092707 | 2022-04-06 | P/FVC/MDS/1078376/2022 | 2022-04-21 | ST202204093139 | 2022-04-07 | P/FVC/MDS/1078336/2022 | 2022-04-21 |  |  |  |  | ST202204092293 | 2022-04-06 | P/FBW/MDS/1078273/2022 | 2022-04-21
1330 | MDKI21 | MDKI21 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/23028 | - |  | On Air | 2022-03-16 | MDKI21 | 4G_FD900_MDKI21 | 4G_FD2100_MDKI21 | 4G_TD_MDKI21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085395 | 2022-03-29 | P/FVC/MDS/1078054/2022 | 2022-04-14 | ST202203084641 | 2022-03-29 | P/FVC/MDS/1077956/2022 | 2022-04-14 |  |  |  |  | ST202203082578 | 2022-03-26 | P/FBW/MDS/1077786/2022 | 2022-04-14
1331 | TEKPT2 | TEKPT2 | Coimbatore | Coimbatore |  | ROTN | ATC |  |  |  | On Air | 2022-03-22 | TEKPT2 | 4G_FD900_TEKPT2 | 4G_FD2100_TEKPT2 | 4G_TD_TEKPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085847 | 2022-03-30 | P/FVC/MDS/1078170/2022 | 2022-04-15 | ST202203084954 | 2022-03-29 | P/FVC/MDS/1078125/2022 | 2022-04-15 |  |  |  |  | ST202203083984 | 2022-03-28 | P/FBW/MDS/1077883/2022 | 2022-04-14
1332 | CETPL2 | CETPL2 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBR-ENB-0644 | SR-TN000825 |  | On Air | 2022-02-25 | CETPL2 | 4G_FD900_CETPL2 | 4G_FD2100_CETPL2 | 4G_TD_CETPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061344 | 2022-03-03 | P/FVC/MDS/1076600/2022 | 2022-03-13 | ST202203059658 | 2022-03-02 | P/FVC/MDS/1076553/2022 | 2022-03-13 |  |  |  |  | ST202203059229 | 2022-03-01 | P/FBW/MDS/1076496/2022 | 2022-03-13
1333 | KALPA2 | KALPA2 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-SLUR-ENB-9057 | SR-TN000807 |  | On Air | 2022-02-25 | KALPA2 | 4G_FD900_KALPA2 | 4G_FD2100_KALPA2 | 4G_TD_KALPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052245 | 2022-02-22 | P/FVC/MDS/1076309/2022 | 2022-03-13 | ST202202054466 | 2022-02-24 | P/FVC/MDS/1076203/2022 | 2022-03-13 |  |  |  |  | ST202202054017 | 2022-02-24 | P/FBW/MDS/1076105/2022 | 2022-03-13
1334 | LKSMP2 | LKSMP2 | Coimbatore | Coimbatore |  | ROTN | Indus | - | R/NN-645925 |  | On Air | 2022-03-25 | LKSMP2 | 4G_FD900_LKSMP2 | 4G_FD2100_LKSMP2 | 4G_TD_LKSMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085685 | 2022-03-29 | P/FVC/MDS/1078088/2022 | 2022-04-14 | ST202203084709 | 2022-03-29 | P/FVC/MDS/1077990/2022 | 2022-04-14 |  |  |  |  | ST202203082685 | 2022-03-26 | P/FBW/MDS/1077831/2022 | 2022-04-14
1335 | UGYNR2 | UGYNR2 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3124089 | R/NN-645926 |  | On Air | 2022-03-10 | UGYNR2 | 4G_FD900_UGYNR2 | 4G_FD2100_UGYNR2 | 4G_TD_UGYNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074011 | 2022-03-16 | P/FVC/MDS/1077178/2022 | 2022-03-30 | ST202203073637 | 2022-03-16 | P/FVC/MDS/1077130/2022 | 2022-03-30 |  |  |  |  | ST202203072981 | 2022-03-15 | P/FBW/MDS/1077083/2022 | 2022-03-30
1336 | GNPYM3 | GNPYM3 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-PLDM-ENB-9083 | SR-TN000821 |  | On Air | 2022-02-25 | GNPYM3 | 4G_FD900_GNPYM3 | 4G_FD2100_GNPYM3 | 4G_TD_GNPYM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052253 | 2022-02-22 | P/FVC/MDS/1076311/2022 | 2022-03-13 | ST202202054469 | 2022-02-24 | P/FVC/MDS/1076205/2022 | 2022-03-13 | ST202210538394 | 2022-10-08 | P/FVC/MDS/1113901/2022 | 2022-10-21 | ST202202054019 | 2022-02-24 | P/FBW/MDS/1076107/2022 | 2022-03-13
1337 | TIR492 | TIR492 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-TPPR-ENB-9077 | SR-TN000815 |  | On Air | 2022-02-25 | TIR492 | 4G_FD900_TIR492 | 4G_FD2100_TIR492 | 4G_TD_TIR492 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061343 | 2022-03-03 | P/FVC/MDS/1076599/2022 | 2022-03-13 | ST202203059650 | 2022-03-02 | P/FVC/MDS/1076552/2022 | 2022-03-13 |  |  |  |  | ST202203059228 | 2022-03-01 | P/FBW/MDS/1076495/2022 | 2022-03-13
1338 | SNPNT2 | SNPNT2 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-UDMP-ENB-9046 | SR-TN000822 |  | On Air | 2022-02-25 | SNPNT2 | 4G_FD900_SNPNT2 | 4G_FD2100_SNPNT2 | 4G_TD_SNPNT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052262 | 2022-02-22 | P/FVC/MDS/1076315/2022 | 2022-03-13 | ST202202054473 | 2022-02-24 | P/FVC/MDS/1076209/2022 | 2022-03-13 |  |  |  |  | ST202202054024 | 2022-02-24 | P/FBW/MDS/1076111/2022 | 2022-03-13
1339 | ANUUR3 | ANUUR3 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBR-ENB-9097 | SR-TN000813 |  | On Air | 2022-02-24 | ANUUR3 | 4G_FD900_ANUUR3 | 4G_FD2100_ANUUR3 | 4G_TD_ANUUR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052264 | 2022-02-22 | P/FVC/MDS/1076317/2022 | 2022-03-13 | ST202202054475 | 2022-02-24 | P/FVC/MDS/1076211/2022 | 2022-03-13 |  |  |  |  | ST202202054033 | 2022-02-24 | P/FBW/MDS/1076113/2022 | 2022-03-13
1340 | TPLYM2 | TPLYM2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-PNDI-ENB-9083 | SR-TN000820 |  | On Air | 2022-02-25 | TPLYM2 | 4G_FD900_TPLYM2 | 4G_FD2100_TPLYM2 | 4G_TD_TPLYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052269 | 2022-02-22 | P/FVC/MDS/1076319/2022 | 2022-03-13 | ST202202054934 | 2022-02-25 | P/FVC/MDS/1076213/2022 | 2022-03-13 |  |  |  |  | ST202202054038 | 2022-02-24 | P/FBW/MDS/1076115/2022 | 2022-03-13
1341 | SINGN2 | SINGN2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-PNDI-ENB-9115 | SR-TN000836 |  | On Air | 2022-02-25 | SINGN2 | 4G_FD900_SINGN2 | 4G_FD2100_SINGN2 | 4G_TD_SINGN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052271 | 2022-02-22 | P/FVC/MDS/1076320/2022 | 2022-03-13 | ST202202054943 | 2022-02-25 | P/FVC/MDS/1076214/2022 | 2022-03-13 |  |  |  |  | ST202202054039 | 2022-02-24 | P/FBW/MDS/1076116/2022 | 2022-03-13
1342 | ERD241 | ERD241 | Erode | Coimbatore |  | ROTN | Summit | I-TN-CTHD-ENB-9003 | SR-TN000846 |  | On Air | 2022-02-25 | ERD241 | 4G_FD900_ERD241 | 4G_FD2100_ERD241 | 4G_TD_ERD241 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052274 | 2022-02-22 | P/FVC/MDS/1076322/2022 | 2022-03-13 | ST202202054945 | 2022-02-25 | P/FVC/MDS/1076216/2022 | 2022-03-13 |  |  |  |  | ST202202054043 | 2022-02-24 | P/FBW/MDS/1076118/2022 | 2022-03-13
1343 | ERD242 | ERD242 | Erode | Coimbatore |  | ROTN | Summit | I-TN-EROD-ENB-9091 | SR-TN000829 |  | On Air | 2022-02-25 | ERD242 | 4G_FD900_ERD242 | 4G_FD2100_ERD242 | 4G_TD_ERD242 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052275 | 2022-02-22 | P/FVC/MDS/1076323/2022 | 2022-03-13 | ST202202054946 | 2022-02-25 | P/FVC/MDS/1076217/2022 | 2022-03-13 |  |  |  |  | ST202202054045 | 2022-02-24 | P/FBW/MDS/1076119/2022 | 2022-03-13
1344 | ERD243 | ERD243 | Erode | Coimbatore |  | ROTN | Summit | I-TN-MODR-ENB-9002 | SR-TN000833 |  | On Air | 2022-02-25 | ERD243 | 4G_FD900_ERD243 | 4G_FD2100_ERD243 | 4G_TD_ERD243 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061345 | 2022-03-03 | P/FVC/MDS/1076601/2022 | 2022-03-13 | ST202203059660 | 2022-03-02 | P/FVC/MDS/1076554/2022 | 2022-03-13 |  |  |  |  | ST202203059231 | 2022-03-01 | P/FBW/MDS/1076497/2022 | 2022-03-13
1345 | TCGD54 | TCGD54 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9106 | SR-TN000838 |  | On Air | 2022-02-25 | TCGD54 | 4G_FD900_TCGD54 | 4G_FD2100_TCGD54 | 4G_TD_TCGD54 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052276 | 2022-02-22 | P/FVC/MDS/1076324/2022 | 2022-03-13 | ST202202054951 | 2022-02-25 | P/FVC/MDS/1076218/2022 | 2022-03-13 |  |  |  |  | ST202202054046 | 2022-02-24 | P/FBW/MDS/1076120/2022 | 2022-03-13
1346 | TCGD56 | TCGD56 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9089 | SR-TN000835 |  | On Air | 2022-02-25 | TCGD56 | 4G_FD900_TCGD56 | 4G_FD2100_TCGD56 | 4G_TD_TCGD56 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052279 | 2022-02-22 | P/FVC/MDS/1076326/2022 | 2022-03-13 | ST202202055075 | 2022-02-25 | P/FVC/MDS/1076220/2022 | 2022-03-13 |  |  |  |  | ST202202054051 | 2022-02-24 | P/FBW/MDS/1076122/2022 | 2022-03-13
1347 | TCGD57 | TCGD57 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9092 | SR-TN000844 |  | On Air | 2022-02-25 | TCGD57 | 4G_FD900_TCGD57 | 4G_FD2100_TCGD57 | 4G_TD_TCGD57 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052283 | 2022-02-22 | P/FVC/MDS/1076327/2022 | 2022-03-13 | ST202202055076 | 2022-02-25 | P/FVC/MDS/1076221/2022 | 2022-03-13 |  |  |  |  | ST202202054053 | 2022-02-24 | P/FBW/MDS/1076123/2022 | 2022-03-13
1348 | PALPM3 | PALPM3 | Erode | Coimbatore |  | ROTN | Summit | I-TN-KRPY-ENB-9002 | SR-TN000827 |  | On Air | 2022-02-25 | PALPM3 | 4G_FD900_PALPM3 | 4G_FD2100_PALPM3 | 4G_TD_PALPM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052284 | 2022-02-22 | P/FVC/MDS/1076328/2022 | 2022-03-13 | ST202202055077 | 2022-02-25 | P/FVC/MDS/1076222/2022 | 2022-03-13 |  |  |  |  | ST202202054054 | 2022-02-24 | P/FBW/MDS/1076124/2022 | 2022-03-13
1349 | KMPM30 | KMPM30 | Erode | Coimbatore |  | ROTN | Summit | I-TN-SKGR-ENB-9058 | SR-TN000839 |  | On Air | 2022-02-25 | KMPM30 | 4G_FD900_KMPM30 | 4G_FD2100_KMPM30 | 4G_TD_KMPM30 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052290 | 2022-02-22 | P/FVC/MDS/1076330/2022 | 2022-03-13 | ST202202055080 | 2022-02-25 | P/FVC/MDS/1076224/2022 | 2022-03-13 |  |  |  |  | ST202202054058 | 2022-02-24 | P/FBW/MDS/1076126/2022 | 2022-03-13
1350 | TCGD58 | TCGD58 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9074 | SR-TN000840 |  | On Air | 2022-02-25 | TCGD58 | 4G_FD900_TCGD58 | 4G_FD2100_TCGD58 | 4G_TD_TCGD58 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052292 | 2022-02-22 | P/FVC/MDS/1076331/2022 | 2022-03-13 | ST202202055083 | 2022-02-25 | P/FVC/MDS/1076225/2022 | 2022-03-13 |  |  |  |  | ST202202054062 | 2022-02-24 | P/FBW/MDS/1076127/2022 | 2022-03-13
1351 | OYKSV2 | OYKSV2 | Sivaganga | Madurai |  | ROTN | Indus | IN-3124090 | R/NN-645927 |  | On Air | 2022-03-10 | OYKSV2 | 4G_FD900_OYKSV2 | 4G_FD2100_OYKSV2 | 4G_TD_OYKSV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074012 | 2022-03-16 | P/FVC/MDS/1077179/2022 | 2022-03-30 | ST202203073638 | 2022-03-16 | P/FVC/MDS/1077131/2022 | 2022-03-30 |  |  |  |  | ST202203072982 | 2022-03-15 | P/FBW/MDS/1077084/2022 | 2022-03-30
1352 | TIVR48 | TIVR48 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-TVUR-ENB-9009 | SR-TN000887 |  | On Air | 2022-02-25 | TIVR48 | 4G_FD900_TIVR48 | 4G_FD2100_TIVR48 | 4G_TD_TIVR48 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056723 | 2022-02-27 | P/FVC/MDS/1076466/2022 | 2022-03-13 | ST202202055894 | 2022-02-26 | P/FVC/MDS/1075682/2022 | 2022-03-10 |  |  |  |  | ST202202056484 | 2022-02-26 | P/FBW/MDS/1075585/2022 | 2022-03-10
1353 | PEROD2 | PEROD2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-CTHD-ENB-0006 | SR-TN000857 |  | On Air | 2022-02-25 | PEROD2 | 4G_FD900_PEROD2 | 4G_FD2100_PEROD2 | 4G_TD_PEROD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052336 | 2022-02-22 | P/FVC/MDS/1076364/2022 | 2022-03-13 | ST202202055445 | 2022-02-25 | P/FVC/MDS/1076258/2022 | 2022-03-13 |  |  |  |  | ST202202054115 | 2022-02-24 | P/FBW/MDS/1076160/2022 | 2022-03-13
1354 | KNDMP2 | KNDMP2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-PNDI-ENB-9085 | SR-TN000868 |  | On Air | 2022-02-25 | KNDMP2 | 4G_FD900_KNDMP2 | 4G_FD2100_KNDMP2 | 4G_TD_KNDMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052337 | 2022-02-22 | P/FVC/MDS/1076365/2022 | 2022-03-13 | ST202202055448 | 2022-02-25 | P/FVC/MDS/1076259/2022 | 2022-03-13 |  |  |  |  | ST202202054116 | 2022-02-24 | P/FBW/MDS/1076161/2022 | 2022-03-13
1355 | TLYMP2 | TLYMP2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-PNDI-ENB-9107 | SR-TN000880 |  | On Air | 2022-02-25 | TLYMP2 | 4G_FD900_TLYMP2 | 4G_FD2100_TLYMP2 | 4G_TD_TLYMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052339 | 2022-02-22 | P/FVC/MDS/1076367/2022 | 2022-03-13 | ST202202055450 | 2022-02-25 | P/FVC/MDS/1076261/2022 | 2022-03-13 |  |  |  |  | ST202202054250 | 2022-02-24 | P/FBW/MDS/1076163/2022 | 2022-03-13
1356 | TCGD60 | TCGD60 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-TCGD-ENB-9081 | SR-TN000874 |  | On Air | 2022-02-25 | TCGD60 | 4G_FD900_TCGD60 | 4G_FD2100_TCGD60 | 4G_TD_TCGD60 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052342 | 2022-02-22 | P/FVC/MDS/1076370/2022 | 2022-03-13 | ST202202055458 | 2022-02-25 | P/FVC/MDS/1076264/2022 | 2022-03-13 |  |  |  |  | ST202202054260 | 2022-02-24 | P/FBW/MDS/1076166/2022 | 2022-03-13
1357 | KMPLM2 | KMPLM2 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-MPLM-ENB-9045 | SR-TN000864 |  | On Air | 2022-02-28 | KMPLM2 | 4G_FD900_KMPLM2 | 4G_FD2100_KMPLM2 | 4G_TD_KMPLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053340 | 2022-02-23 | P/FVC/MDS/1076378/2022 | 2022-03-13 | ST202202055487 | 2022-02-25 | P/FVC/MDS/1076272/2022 | 2022-03-13 |  |  |  |  | ST202202054281 | 2022-02-24 | P/FBW/MDS/1076174/2022 | 2022-03-13
1358 | GGPRM3 | GGPRM3 | Erode | Coimbatore |  | ROTN | Summit | I-TN-EROD-ENB-9118 | SR-TN000882 |  | On Air | 2022-02-25 | GGPRM3 | 4G_FD900_GGPRM3 | 4G_FD2100_GGPRM3 | 4G_TD_GGPRM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053341 | 2022-02-23 | P/FVC/MDS/1076379/2022 | 2022-03-13 | ST202202055488 | 2022-02-25 | P/FVC/MDS/1076273/2022 | 2022-03-13 |  |  |  |  | ST202202054282 | 2022-02-24 | P/FBW/MDS/1076175/2022 | 2022-03-13
1359 | KPNYP2 | KPNYP2 | Theni | Madurai |  | ROTN | Summit | I-TN-TGMM-ENB-9018 | SR-TN000842 |  | On Air | 2022-02-25 | KPNYP2 | 4G_FD900_KPNYP2 | 4G_FD2100_KPNYP2 | 4G_TD_KPNYP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052294 | 2022-02-22 | P/FVC/MDS/1076333/2022 | 2022-03-13 | ST202202055084 | 2022-02-25 | P/FVC/MDS/1076226/2022 | 2022-03-13 |  |  |  |  | ST202202054063 | 2022-02-24 | P/FBW/MDS/1076128/2022 | 2022-03-13
1360 | PRPTI3 | PRPTI3 | Dharmapuri | Vellore |  | ROTN | Indus |  | R/NN-646680 |  | On Air | 2022-03-22 | PRPTI3 | 4G_FD900_PRPTI3 | 4G_FD2100_PRPTI3 | 4G_TD_PRPTI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085650 | 2022-03-29 | P/FVC/MDS/1078077/2022 | 2022-04-14 | ST202203084688 | 2022-03-29 | P/FVC/MDS/1077978/2022 | 2022-04-14 |  |  |  |  | ST202203082665 | 2022-03-26 | P/FBW/MDS/1077819/2022 | 2022-04-14
1361 | BLANM2 | BLANM2 | Dharmapuri | Vellore |  | ROTN | Indus | IN-3124705 | R/NN-646693 |  | On Air | 2022-03-10 | BLANM2 | 4G_FD900_BLANM2 | 4G_FD2100_BLANM2 | 4G_TD_BLANM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092700 | 2022-04-06 | P/FVC/MDS/1078374/2022 | 2022-04-21 | ST202204093137 | 2022-04-07 | P/FVC/MDS/1078334/2022 | 2022-04-21 |  |  |  |  | ST202204092282 | 2022-04-06 | P/FBW/MDS/1078271/2022 | 2022-04-21
1362 | AMBAK2 | AMBAK2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-CGLP-ENB-0061 | SR-TN000855 |  | On Air | 2022-02-25 | AMBAK2 | 4G_FD900_AMBAK2 | 4G_FD2100_AMBAK2 | 4G_TD_AMBAK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052305 | 2022-02-22 | P/FVC/MDS/1076336/2022 | 2022-03-13 | ST202202055088 | 2022-02-25 | P/FVC/MDS/1076229/2022 | 2022-03-13 |  |  |  |  | ST202202054067 | 2022-02-24 | P/FBW/MDS/1076131/2022 | 2022-03-13
1363 | CDBM58 | CDBM58 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-CMBM-ENB-0034 | SR-TN000853 |  | On Air | 2022-02-25 | CDBM58 | 4G_FD900_CDBM58 | 4G_FD2100_CDBM58 | 4G_TD_CDBM58 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052308 | 2022-02-22 | P/FVC/MDS/1076337/2022 | 2022-03-13 | ST202202055091 | 2022-02-25 | P/FVC/MDS/1076230/2022 | 2022-03-13 |  |  |  |  | ST202202054068 | 2022-02-24 | P/FBW/MDS/1076132/2022 | 2022-03-13
1364 | MKMGM2 | MKMGM2 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-PNRT-ENB-9055 | SR-TN000845 |  | On Air | 2022-02-25 | MKMGM2 | 4G_FD900_MKMGM2 | 4G_FD2100_MKMGM2 | 4G_TD_MKMGM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052313 | 2022-02-22 | P/FVC/MDS/1076341/2022 | 2022-03-13 | ST202202055106 | 2022-02-25 | P/FVC/MDS/1076234/2022 | 2022-03-13 |  |  |  |  | ST202202054074 | 2022-02-24 | P/FBW/MDS/1076136/2022 | 2022-03-13
1365 | GRAMA2 | GRAMA2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-ULND-ENB-9066 | SR-TN000854 |  | On Air | 2022-02-25 | GRAMA2 | 4G_FD900_GRAMA2 | 4G_FD2100_GRAMA2 | 4G_TD_GRAMA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052314 | 2022-02-22 | P/FVC/MDS/1076342/2022 | 2022-03-13 | ST202202055107 | 2022-02-25 | P/FVC/MDS/1076235/2022 | 2022-03-13 |  |  |  |  | ST202202054076 | 2022-02-24 | P/FBW/MDS/1076137/2022 | 2022-03-13
1366 | PRUR07 | PRUR07 | Tiruchirappalli | Trichy |  | ROTN | Indus |  | R/NN-646698 |  | On Air | 2022-03-22 | PRUR07 | 4G_FD900_PRUR07 | 4G_FD2100_PRUR07 | 4G_TD_PRUR07 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085743 | 2022-03-29 | P/FVC/MDS/1078111/2022 | 2022-04-14 | ST202203084842 | 2022-03-29 | P/FVC/MDS/1078013/2022 | 2022-04-14 |  |  |  |  | ST202203082763 | 2022-03-26 | P/FBW/MDS/1077854/2022 | 2022-04-14
1367 | MDTI48 | MDTI48 | Thanjavur | Trichy |  | ROTN | Summit | I-TN-TVDD-ENB-9031 | SR-TN000851 |  | On Air | 2022-02-25 | MDTI48 | 4G_FD900_MDTI48 | 4G_FD2100_MDTI48 | 4G_TD_MDTI48 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052316 | 2022-02-22 | P/FVC/MDS/1076344/2022 | 2022-03-13 | ST202202055132 | 2022-02-25 | P/FVC/MDS/1076238/2022 | 2022-03-13 |  |  |  |  | ST202202054082 | 2022-02-24 | P/FBW/MDS/1076140/2022 | 2022-03-13
1368 | MUSI16 | MUSI16 | Vellore | Vellore |  | ROTN | Summit | I-TN-WLLJ-ENB-9068 | SR-TN000830 |  | On Air | 2022-02-25 | MUSI16 | 4G_FD900_MUSI16 | 4G_FD2100_MUSI16 | 4G_TD_MUSI16 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052319 | 2022-02-22 | P/FVC/MDS/1076347/2022 | 2022-03-13 | ST202202055388 | 2022-02-25 | P/FVC/MDS/1076241/2022 | 2022-03-13 |  |  |  |  | ST202202054088 | 2022-02-24 | P/FBW/MDS/1076143/2022 | 2022-03-13
1369 | VACHP2 | VACHP2 | Virudhunagar | Madurai |  | ROTN | Summit | I-TN-VDGR-ENB-9029 | SR-TN000834 |  | On Air | 2022-02-25 | VACHP2 | 4G_FD900_VACHP2 | 4G_FD2100_VACHP2 | 4G_TD_VACHP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052320 | 2022-02-22 | P/FVC/MDS/1076348/2022 | 2022-03-13 | ST202202055395 | 2022-02-25 | P/FVC/MDS/1076242/2022 | 2022-03-13 |  |  |  |  | ST202202054089 | 2022-02-24 | P/FBW/MDS/1076144/2022 | 2022-03-13
1370 | MDVLM2 | MDVLM2 | Vellore | Vellore |  | ROTN | Indus | IN-3124713 | R/NN-646710 |  | On Air | 2022-03-17 | MDVLM2 | 4G_FD900_MDVLM2 | 4G_FD2100_MDVLM2 | 4G_TD_MDVLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085648 | 2022-03-29 | P/FVC/MDS/1078075/2022 | 2022-04-14 | ST202203084682 | 2022-03-29 | P/FVC/MDS/1077976/2022 | 2022-04-14 |  |  |  |  | ST202203082662 | 2022-03-26 | P/FBW/MDS/1077816/2022 | 2022-04-14
1371 | AVDYP2 | AVDYP2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-VPPM-ENB-9097 | SR-TN000873 |  | On Air | 2022-02-25 | AVDYP2 | 4G_FD900_AVDYP2 | 4G_FD2100_AVDYP2 | 4G_TD_AVDYP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052330 | 2022-02-22 | P/FVC/MDS/1076358/2022 | 2022-03-13 | ST202202055430 | 2022-02-25 | P/FVC/MDS/1076252/2022 | 2022-03-13 |  |  |  |  | ST202202054106 | 2022-02-24 | P/FBW/MDS/1076154/2022 | 2022-03-13
1372 | CNBMD2 | CNBMD2 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-PDCY-ENB-0172 | SR-TN000863 |  | On Air | 2022-02-25 | CNBMD2 | 4G_FD900_CNBMD2 | 4G_FD2100_CNBMD2 | 4G_TD_CNBMD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052331 | 2022-02-22 | P/FVC/MDS/1076359/2022 | 2022-03-13 | ST202202055437 | 2022-02-25 | P/FVC/MDS/1076253/2022 | 2022-03-13 |  |  |  |  | ST202202054107 | 2022-02-24 | P/FBW/MDS/1076155/2022 | 2022-03-13
1373 | TDVMK3 | TDVMK3 | Viluppuram | Trichy |  | ROTN | Summit | I-TN-CARH-ENB-9001 | SR-TN000861 |  | On Air | 2022-02-25 | TDVMK3 | 4G_FD900_TDVMK3 | 4G_FD2100_TDVMK3 | 4G_TD_TDVMK3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052332 | 2022-02-22 | P/FVC/MDS/1076360/2022 | 2022-03-13 | ST202202055438 | 2022-02-25 | P/FVC/MDS/1076254/2022 | 2022-03-13 |  |  |  |  | ST202202054110 | 2022-02-24 | P/FBW/MDS/1076156/2022 | 2022-03-13
1374 | KUNNV2 | KUNNV2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-CGLP-ENB-0050 | SR-TN000862 |  | On Air | 2022-02-25 | KUNNV2 | 4G_FD900_KUNNV2 | 4G_FD2100_KUNNV2 | 4G_TD_KUNNV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052333 | 2022-02-22 | P/FVC/MDS/1076361/2022 | 2022-03-13 | ST202202055440 | 2022-02-25 | P/FVC/MDS/1076255/2022 | 2022-03-13 |  |  |  |  | ST202202054111 | 2022-02-24 | P/FBW/MDS/1076157/2022 | 2022-03-13
1375 | SKGI23 | SKGI23 | Salem | Vellore |  | ROTN | Summit | I-TN-TCGD-ENB-9085 | SR-TN000877 |  | On Air | 2022-02-25 | SKGI23 | 4G_FD900_SKGI23 | 4G_FD2100_SKGI23 | 4G_TD_SKGI23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052343 | 2022-02-22 | P/FVC/MDS/1076371/2022 | 2022-03-13 | ST202202055462 | 2022-02-25 | P/FVC/MDS/1076265/2022 | 2022-03-13 |  |  |  |  | ST202202054262 | 2022-02-24 | P/FBW/MDS/1076167/2022 | 2022-03-13
1376 | SKGI24 | SKGI24 | Salem | Vellore |  | ROTN | Summit | I-TN-SKGR-ENB-9050 | SR-TN000866 |  | On Air | 2022-02-25 | SKGI24 | 4G_FD900_SKGI24 | 4G_FD2100_SKGI24 | 4G_TD_SKGI24 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052344 | 2022-02-22 | P/FVC/MDS/1076372/2022 | 2022-03-13 | ST202202055463 | 2022-02-25 | P/FVC/MDS/1076266/2022 | 2022-03-13 |  |  |  |  | ST202202054263 | 2022-02-24 | P/FBW/MDS/1076168/2022 | 2022-03-13
1377 | SKGI25 | SKGI25 | Salem | Vellore |  | ROTN | Summit | I-TN-SKGR-ENB-9044 | SR-TN000878 |  | On Air | 2022-02-25 | SKGI25 | 4G_FD900_SKGI25 | 4G_FD2100_SKGI25 | 4G_TD_SKGI25 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052345 | 2022-02-22 | P/FVC/MDS/1076373/2022 | 2022-03-13 | ST202202055464 | 2022-02-25 | P/FVC/MDS/1076267/2022 | 2022-03-13 |  |  |  |  | ST202202054274 | 2022-02-24 | P/FBW/MDS/1076169/2022 | 2022-03-13
1378 | SKGI26 | SKGI26 | Salem | Vellore |  | ROTN | Summit | I-TN-SKGR-ENB-9006 | SR-TN000879 |  | On Air | 2022-02-25 | SKGI26 | 4G_FD900_SKGI26 | 4G_FD2100_SKGI26 | 4G_TD_SKGI26 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053331 | 2022-02-23 | P/FVC/MDS/1076374/2022 | 2022-03-13 | ST202202055469 | 2022-02-25 | P/FVC/MDS/1076268/2022 | 2022-03-13 |  |  |  |  | ST202202054275 | 2022-02-24 | P/FBW/MDS/1076170/2022 | 2022-03-13
1379 | VMBTI3 | VMBTI3 | Erode | Coimbatore |  | ROTN | Summit | I-TN-ANYR-ENB-9014 | SR-TN000871 |  | On Air | 2022-02-25 | VMBTI3 | 4G_FD900_VMBTI3 | 4G_FD2100_VMBTI3 | 4G_TD_VMBTI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061353 | 2022-03-03 | P/FVC/MDS/1076602/2022 | 2022-03-13 | ST202203059677 | 2022-03-02 | P/FVC/MDS/1076555/2022 | 2022-03-13 |  |  |  |  | ST202203059232 | 2022-03-01 | P/FBW/MDS/1076498/2022 | 2022-03-13
1380 | PSVPL2 | PSVPL2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-SMNG-ENB-9065 | SR-TN000881 |  | On Air | 2022-02-28 | PSVPL2 | 4G_FD900_PSVPL2 | 4G_FD2100_PSVPL2 | 4G_TD_PSVPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053334 | 2022-02-23 | P/FVC/MDS/1076376/2022 | 2022-03-13 | ST202202055480 | 2022-02-25 | P/FVC/MDS/1076270/2022 | 2022-03-13 |  |  |  |  | ST202202054278 | 2022-02-24 | P/FBW/MDS/1076172/2022 | 2022-03-13
1381 | KORPY2 | KORPY2 | Erode | Coimbatore |  | ROTN | Indus | IN-3124716 | R/NN-646716 |  | On Air | 2022-03-16 | KORPY2 | 4G_FD900_KORPY2 | 4G_FD2100_KORPY2 | 4G_TD_KORPY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085454 | 2022-03-29 | P/FVC/MDS/1078061/2022 | 2022-04-14 | ST202203084655 | 2022-03-29 | P/FVC/MDS/1077962/2022 | 2022-04-14 |  |  |  |  | ST202203082600 | 2022-03-26 | P/FBW/MDS/1077795/2022 | 2022-04-14
1382 | NELMK2 | NELMK2 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23037 | - |  | On Air | 2022-03-10 | NELMK2 | 4G_FD900_NELMK2 | 4G_FD2100_NELMK2 | 4G_TD_NELMK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053385 | 2022-02-23 | P/FVC/MDS/1076384/2022 | 2022-03-13 | ST202202055496 | 2022-02-25 | P/FVC/MDS/1076277/2022 | 2022-03-13 |  |  |  |  | ST202202054287 | 2022-02-24 | P/FBW/MDS/1076179/2022 | 2022-03-13
1383 | KNCPT2 | KNCPT2 | Dindigul | Coimbatore |  | ROTN | Summit | I-TN-ATUA-ENB-9017 | SR-TN000886 |  | On Air | 2022-02-25 | KNCPT2 | 4G_FD900_KNCPT2 | 4G_FD2100_KNCPT2 | 4G_TD_KNCPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053402 | 2022-02-23 | P/FVC/MDS/1076385/2022 | 2022-03-13 | ST202202055497 | 2022-02-25 | P/FVC/MDS/1076278/2022 | 2022-03-13 |  |  |  |  | ST202202054288 | 2022-02-24 | P/FBW/MDS/1076180/2022 | 2022-03-13
1384 | CNPT13 | CNPT13 | Dindigul | Coimbatore |  | ROTN | Summit | I-TN-DDGL-ENB-9019 | SR-TN000889 |  | On Air | 2022-02-25 | CNPT13 | 4G_FD900_CNPT13 | 4G_FD2100_CNPT13 | 4G_TD_CNPT13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053403 | 2022-02-23 | P/FVC/MDS/1076386/2022 | 2022-03-13 | ST202202055498 | 2022-02-25 | P/FVC/MDS/1076279/2022 | 2022-03-13 |  |  |  |  | ST202202054289 | 2022-02-24 | P/FBW/MDS/1076181/2022 | 2022-03-13
1385 | SLPDI5 | SLPDI5 | Dindigul | Coimbatore |  | ROTN | Summit | I-TN-DDGL-ENB-9016 | SR-TN000885 |  | On Air | 2022-02-28 | SLPDI5 | 4G_FD900_SLPDI5 | 4G_FD2100_SLPDI5 | 4G_TD_SLPDI5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053407 | 2022-02-23 | P/FVC/MDS/1076388/2022 | 2022-03-13 | ST202202055504 | 2022-02-25 | P/FVC/MDS/1076281/2022 | 2022-03-13 |  |  |  |  | ST202202054297 | 2022-02-24 | P/FBW/MDS/1075504/2022 | 2022-03-10
1386 | VDSNR7 | VDSNR7 | Dindigul | Coimbatore |  | ROTN | Summit | I-TN-VDSD-ENB-9072 | SR-TN000905 |  | On Air | 2022-02-28 | VDSNR7 | 4G_FD900_VDSNR7 | 4G_FD2100_VDSNR7 | 4G_TD_VDSNR7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053416 | 2022-02-23 | P/FVC/MDS/1076391/2022 | 2022-03-13 | ST202202055598 | 2022-02-26 | P/FVC/MDS/1075606/2022 | 2022-03-10 |  |  |  |  | ST202202054300 | 2022-02-24 | P/FBW/MDS/1075507/2022 | 2022-03-10
1387 | MNMGL2 | MNMGL2 | Karur | Coimbatore |  | ROTN | Summit | I-TN-MBPY-ENB-9002 | SR-TN000895 |  | On Air | 2022-03-02 | MNMGL2 | 4G_FD900_MNMGL2 | 4G_FD2100_MNMGL2 | 4G_TD_MNMGL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053418 | 2022-02-23 | P/FVC/MDS/1076392/2022 | 2022-03-13 | ST202202055599 | 2022-02-26 | P/FVC/MDS/1075607/2022 | 2022-03-10 | ST202210548423 | 2022-10-11 | P/FVC/MDS/1113916/2022 | 2022-10-21 | ST202202054301 | 2022-02-24 | P/FBW/MDS/1075508/2022 | 2022-03-10
1388 | VLNAI2 | VLNAI2 | Karur | Coimbatore |  | ROTN | Indus | IN-3124718 | R/NN-646720 |  | On Air | 2022-03-16 | VLNAI2 | 4G_FD900_VLNAI2 | 4G_FD2100_VLNAI2 | 4G_TD_VLNAI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085456 | 2022-03-29 | P/FVC/MDS/1078062/2022 | 2022-04-14 | ST202203084659 | 2022-03-29 | P/FVC/MDS/1077963/2022 | 2022-04-14 |  |  |  |  | ST202203082601 | 2022-03-26 | P/FBW/MDS/1077796/2022 | 2022-04-14
1389 | MNTPM2 | MNTPM2 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-KNGY-ENB-9056 | SR-TN000892 |  | On Air | 2022-02-28 | MNTPM2 | 4G_FD900_MNTPM2 | 4G_FD2100_MNTPM2 | 4G_TD_MNTPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053421 | 2022-02-23 | P/FVC/MDS/1076395/2022 | 2022-03-13 | ST202202055602 | 2022-02-26 | P/FVC/MDS/1075610/2022 | 2022-03-10 |  |  |  |  | ST202202054305 | 2022-02-24 | P/FBW/MDS/1075511/2022 | 2022-03-10
1390 | VDVNP2 | VDVNP2 | Theni | Madurai |  | ROTN | Summit | I-TN-BDKK-ENB-9014 | SR-TN000890 |  | On Air | 2022-02-28 | VDVNP2 | 4G_FD900_VDVNP2 | 4G_FD2100_VDVNP2 | 4G_TD_VDVNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061360 | 2022-03-03 | P/FVC/MDS/1076606/2022 | 2022-03-13 | ST202203064584 | 2022-03-07 | P/FVC/MDS/1076908/2022 | 2022-03-23 |  |  |  |  | ST202203059239 | 2022-03-01 | P/FBW/MDS/1076501/2022 | 2022-03-13
1391 | UMPT50 | UMPT50 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-UDMP-ENB-9052 | SR-TN000891 |  | On Air | 2022-02-28 | UMPT50 | 4G_FD900_UMPT50 | 4G_FD2100_UMPT50 | 4G_TD_UMPT50 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061355 | 2022-03-03 | P/FVC/MDS/1076604/2022 | 2022-03-13 | ST202203059813 | 2022-03-02 | P/FVC/MDS/1076557/2022 | 2022-03-13 |  |  |  |  | ST202203059233 | 2022-03-01 | P/FBW/MDS/1076499/2022 | 2022-03-13
1392 | UMPT51 | UMPT51 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-UDMP-ENB-9050 | SR-TN000903 |  | On Air | 2022-02-28 | UMPT51 | 4G_FD900_UMPT51 | 4G_FD2100_UMPT51 | 4G_TD_UMPT51 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203061359 | 2022-03-03 | P/FVC/MDS/1076605/2022 | 2022-03-13 | ST202203059814 | 2022-03-02 | P/FVC/MDS/1076558/2022 | 2022-03-13 |  |  |  |  | ST202203059238 | 2022-03-01 | P/FBW/MDS/1076500/2022 | 2022-03-13
1393 | KATUP2 | KATUP2 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3125336 | R/NN-647357 |  |  | 2022-03-16 | KATUP2 | 4G_FD900_KATUP2 | 4G_FD2100_KATUP2 | 4G_TD_KATUP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084557 | 2022-03-29 | P/FVC/MDS/1078038/2022 | 2022-04-14 | ST202203084460 | 2022-03-28 | P/FVC/MDS/1077939/2022 | 2022-04-14 |  |  |  |  | ST202203082599 | 2022-03-26 | P/FBW/MDS/1077794/2022 | 2022-04-14
1394 | KALVS2 | KALVS2 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/23044 | - |  | On Air | 2022-03-16 | KALVS2 | 4G_FD900_KALVS2 | 4G_FD2100_KALVS2 | 4G_TD_KALVS2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084561 | 2022-03-29 | P/FVC/MDS/1078042/2022 | 2022-04-14 | ST202203084465 | 2022-03-28 | P/FVC/MDS/1077943/2022 | 2022-04-14 |  |  |  |  | ST202203082632 | 2022-03-26 | P/FBW/MDS/1077801/2022 | 2022-04-14
1395 | CBE915 | CBE915 | Coimbatore | Coimbatore |  | ROTN | Indus |  | R/NN-647365 |  | On Air | 2022-03-25 | CBE915 | 4G_FD900_CBE915 | 4G_FD2100_CBE915 | 4G_TD_CBE915 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085308 | 2022-03-29 | P/FVC/MDS/1078047/2022 | 2022-04-14 | ST202203084708 | 2022-03-29 | P/FVC/MDS/1077989/2022 | 2022-04-14 | ST202210538382 | 2022-10-08 | P/FVC/MDS/1113895/2022 | 2022-10-21 | ST202203082683 | 2022-03-26 | P/FBW/MDS/1077830/2022 | 2022-04-14
1396 | CNTLV2 | CNTLV2 | Karur | Coimbatore |  | ROTN | Indus | IN-3125346 | R/NN-647366 |  | On Air | 2022-03-17 | CNTLV2 | 4G_FD900_CNTLV2 | 4G_FD2100_CNTLV2 | 4G_TD_CNTLV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084565 | 2022-03-29 | P/FVC/MDS/1078046/2022 | 2022-04-14 | ST202203084474 | 2022-03-28 | P/FVC/MDS/1077947/2022 | 2022-04-14 |  |  |  |  | ST202203082663 | 2022-03-26 | P/FBW/MDS/1077817/2022 | 2022-04-14
1397 | KITPM2 | KITPM2 | Coimbatore | Coimbatore |  | ROTN | Indus |  | R/NN-647367 |  | On Air | 2022-03-25 | KITPM2 | 4G_FD900_KITPM2 | 4G_FD2100_KITPM2 | 4G_TD_KITPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085686 | 2022-03-29 | P/FVC/MDS/1078089/2022 | 2022-04-14 | ST202203084714 | 2022-03-29 | P/FVC/MDS/1077991/2022 | 2022-04-14 |  |  |  |  | ST202203082686 | 2022-03-26 | P/FBW/MDS/1077832/2022 | 2022-04-14
1398 | THAIL2 | THAIL2 | Virudhunagar | Madurai |  | ROTN | Indus | IN-1113526 | R/RES-509472 |  | On Air | 2022-03-04 | THAIL2 | 4G_FD900_THAIL2 | 4G_FD2100_THAIL2 | 4G_TD_THAIL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052322 | 2022-02-22 | P/FVC/MDS/1076350/2022 | 2022-03-13 | ST202202055407 | 2022-02-25 | P/FVC/MDS/1076244/2022 | 2022-03-13 |  |  |  |  | ST202202054093 | 2022-02-24 | P/FBW/MDS/1076146/2022 | 2022-03-13
1399 | VELNP2 | VELNP2 | Coimbatore | Coimbatore |  | ROTN | Indus |  | R/NN-647370 |  | SO | 2022-03-22 | VELNP2 | 4G_FD900_VELNP2 | 4G_FD2100_VELNP2 | 4G_TD_VELNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085658 | 2022-03-29 | P/FVC/MDS/1078082/2022 | 2022-04-14 | ST202203084699 | 2022-03-29 | P/FVC/MDS/1077983/2022 | 2022-04-14 |  |  |  |  | ST202203082671 | 2022-03-26 | P/FBW/MDS/1077824/2022 | 2022-04-14
1400 | TVKND5 | TVKND5 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/PR/11159 | - |  | On Air | 2022-03-10 | TVKND5 | 4G_FD900_TVKND5 | 4G_FD2100_TVKND5 | 4G_TD_TVKND5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052326 | 2022-02-22 | P/FVC/MDS/1076354/2022 | 2022-03-13 | ST202210614704 | 2022-10-21 | P/FVC/MDS/1114227/2022 | 2022-11-03 |  |  |  |  | ST202202054098 | 2022-02-24 | P/FBW/MDS/1076150/2022 | 2022-03-13
1401 | PLKUD2 | PLKUD2 | Karur | Coimbatore |  | ROTN | Summit | I-TN-KAVR-ENB-9020 | SR-TN000907 |  | On Air | 2022-03-08 | PLKUD2 | 4G_FD900_PLKUD2 | 4G_FD2100_PLKUD2 | 4G_TD_PLKUD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052334 | 2022-02-22 | P/FVC/MDS/1076362/2022 | 2022-03-13 | ST202202055441 | 2022-02-25 | P/FVC/MDS/1076256/2022 | 2022-03-13 |  |  |  |  | ST202202054112 | 2022-02-24 | P/FBW/MDS/1076158/2022 | 2022-03-13
1402 | MYLPT2 | MYLPT2 | Karur | Coimbatore |  | ROTN | Indus |  | R/NN-647382 |  | SO | 2022-03-25 | MYLPT2 | 4G_FD900_MYLPT2 | 4G_FD2100_MYLPT2 | 4G_TD_MYLPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085690 | 2022-03-29 | P/FVC/MDS/1078090/2022 | 2022-04-14 | ST202203084715 | 2022-03-29 | P/FVC/MDS/1077992/2022 | 2022-04-14 |  |  |  |  | ST202203082687 | 2022-03-26 | P/FBW/MDS/1077833/2022 | 2022-04-14
1403 | KTALI8 | KTALI8 | Karur | Coimbatore |  | ROTN | Indus |  | R/NN-647407 |  | On Air | 2022-03-22 | KTALI8 | 4G_FD900_KTALI8 | 4G_FD2100_KTALI8 | 4G_TD_KTALI8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085749 | 2022-03-29 | P/FVC/MDS/1078115/2022 | 2022-04-14 | ST202203084920 | 2022-03-29 | P/FVC/MDS/1078117/2022 | 2022-04-15 |  |  |  |  | ST202203083960 | 2022-03-28 | P/FBW/MDS/1077875/2022 | 2022-04-14
1404 | SATMG2 | SATMG2 | Karur | Coimbatore |  | ROTN | Indus |  | R/NN-647408 |  | SO(Rural Hold) | 2022-03-22 | SATMG2 | 4G_FD900_SATMG2 | 4G_FD2100_SATMG2 | 4G_TD_SATMG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085755 | 2022-03-29 | P/FVC/MDS/1078116/2022 | 2022-04-14 | ST202203084921 | 2022-03-29 | P/FVC/MDS/1078118/2022 | 2022-04-15 |  |  |  |  | ST202203083965 | 2022-03-28 | P/FBW/MDS/1077876/2022 | 2022-04-14
1405 | IRMBT2 | IRMBT2 | Karur | Coimbatore |  | ROTN | Indus |  | R/NN-647486 |  | On Air | 2022-03-22 | IRMBT2 | 4G_FD900_IRMBT2 | 4G_FD2100_IRMBT2 | 4G_TD_IRMBT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204094900 | 2022-04-08 | P/FVC/MDS/1078395/2022 | 2022-04-21 | ST202203084929 | 2022-03-29 | P/FVC/MDS/1078119/2022 | 2022-04-15 |  |  |  |  | ST202203083966 | 2022-03-28 | P/FBW/MDS/1077877/2022 | 2022-04-14
1406 | TOTCH2 | TOTCH2 | Karur | Coimbatore |  | ROTN | Indus | IN-3125451 | R/NN-647645 |  | On Air | 2022-03-17 | TOTCH2 | 4G_FD900_TOTCH2 | 4G_FD2100_TOTCH2 | 4G_TD_TOTCH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084564 | 2022-03-29 | P/FVC/MDS/1078045/2022 | 2022-04-14 | ST202203084470 | 2022-03-28 | P/FVC/MDS/1077946/2022 | 2022-04-14 |  |  |  |  | ST202203082661 | 2022-03-26 | P/FBW/MDS/1077815/2022 | 2022-04-14
1407 | OLPLY2 | OLPLY2 | Erode | Coimbatore |  | ROTN | ATC | TN/SA/PR/11119 | - |  | On Air | 2022-03-10 | OLPLY2 | 4G_FD900_OLPLY2 | 4G_FD2100_OLPLY2 | 4G_TD_OLPLY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202052338 | 2022-02-22 | P/FVC/MDS/1076366/2022 | 2022-03-13 | ST202202055449 | 2022-02-25 | P/FVC/MDS/1076260/2022 | 2022-03-13 |  |  |  |  | ST202202054249 | 2022-02-24 | P/FBW/MDS/1076162/2022 | 2022-03-13
1408 | TRMPM2 | TRMPM2 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/PR/11123 | - |  | On Air | 2022-03-10 | TRMPM2 | 4G_FD900_TRMPM2 | 4G_FD2100_TRMPM2 | 4G_TD_TRMPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053335 | 2022-02-23 | P/FVC/MDS/1076377/2022 | 2022-03-13 | ST202202055481 | 2022-02-25 | P/FVC/MDS/1076271/2022 | 2022-03-13 |  |  |  |  | ST202202054279 | 2022-02-24 | P/FBW/MDS/1076173/2022 | 2022-03-13
1409 | ULMPT2 | ULMPT2 | Dindigul | Coimbatore |  | ROTN | ATC | TN/MU/TT/15392 | - |  | On Air | 2022-03-10 | ULMPT2 | 4G_FD900_ULMPT2 | 4G_FD2100_ULMPT2 | 4G_TD_ULMPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053408 | 2022-02-23 | P/FVC/MDS/1076389/2022 | 2022-03-13 | ST202202055596 | 2022-02-26 | P/FVC/MDS/1075604/2022 | 2022-03-10 |  |  |  |  | ST202202054298 | 2022-02-24 | P/FBW/MDS/1075505/2022 | 2022-03-10
1410 | GRNLR7 | GRNLR7 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/23045 | - |  | On Air | 2022-03-16 | GRNLR7 | 4G_FD900_GRNLR7 | 4G_FD2100_GRNLR7 | 4G_TD_GRNLR7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084555 | 2022-03-29 | P/FVC/MDS/1078036/2022 | 2022-04-14 | ST202203084458 | 2022-03-28 | P/FVC/MDS/1077937/2022 | 2022-04-14 |  |  |  |  | ST202203082586 | 2022-03-26 | P/FBW/MDS/1077787/2022 | 2022-04-14
1411 | KZAPR2 | KZAPR2 | Tirunelveli | Madurai |  | ROTN | ATC |  |  |  | On Air | 2022-03-22 | KZAPR2 | 4G_FD900_KZAPR2 | 4G_FD2100_KZAPR2 | 4G_TD_KZAPR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085655 | 2022-03-29 | P/FVC/MDS/1078080/2022 | 2022-04-14 | ST202203084692 | 2022-03-29 | P/FVC/MDS/1077981/2022 | 2022-04-14 |  |  |  |  | ST202203082669 | 2022-03-26 | P/FBW/MDS/1077822/2022 | 2022-04-14
1412 | PVCRM4 | PVCRM4 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-ANGM-ENB-9046 | SR-TN000911 |  | On Air | 2022-03-08 | PVCRM4 | 4G_FD900_PVCRM4 | 4G_FD2100_PVCRM4 | 4G_TD_PVCRM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053427 | 2022-02-23 | P/FVC/MDS/1076396/2022 | 2022-03-13 | ST202202055603 | 2022-02-26 | P/FVC/MDS/1075611/2022 | 2022-03-10 |  |  |  |  | ST202202054306 | 2022-02-24 | P/FBW/MDS/1075512/2022 | 2022-03-10
1413 | SUTMP2 | SUTMP2 | Tirunelveli | Madurai |  | ROTN | Ascend |  |  |  | On Air | 2022-03-25 | SUTMP2 | 4G_FD900_SUTMP2 | 4G_FD2100_SUTMP2 | 4G_TD_SUTMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085691 | 2022-03-29 | P/FVC/MDS/1078091/2022 | 2022-04-14 | ST202203084716 | 2022-03-29 | P/FVC/MDS/1077993/2022 | 2022-04-14 |  |  |  |  | ST202203082691 | 2022-03-26 | P/FBW/MDS/1077834/2022 | 2022-04-14
1414 | TKSI26 | TKSI26 | Tirunelveli | Madurai |  | ROTN | ATC |  |  |  | On Air | 2022-03-22 | TKSI26 | 4G_FD900_TKSI26 | 4G_FD2100_TKSI26 | 4G_TD_TKSI26 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085666 | 2022-03-29 | P/FVC/MDS/1078085/2022 | 2022-04-14 | ST202203084704 | 2022-03-29 | P/FVC/MDS/1077986/2022 | 2022-04-14 |  |  |  |  | ST202203082676 | 2022-03-26 | P/FBW/MDS/1077827/2022 | 2022-04-14
1415 | ANDPT2 | ANDPT2 | Theni | Madurai |  | ROTN | Summit | I-TN-ADPJ-ENB-9042 |  |  | On Air | 2022-03-22 | ANDPT2 | 4G_FD900_ANDPT2 | 4G_FD2100_ANDPT2 | 4G_TD_ANDPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085851 | 2022-03-30 | P/FVC/MDS/1078174/2022 | 2022-04-15 | ST202203084965 | 2022-03-29 | P/FVC/MDS/1078129/2022 | 2022-04-15 |  |  |  |  | ST202203083989 | 2022-03-28 | P/FBW/MDS/1077886/2022 | 2022-04-14
1416 | CDBM65 | CDBM65 | Cuddalore | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-03-25 | CDBM65 | 4G_FD900_CDBM65 | 4G_FD2100_CDBM65 | 4G_TD_CDBM65 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085700 | 2022-03-29 | P/FVC/MDS/1078095/2022 | 2022-04-14 | ST202203084750 | 2022-03-29 | P/FVC/MDS/1077997/2022 | 2022-04-14 |  |  |  |  | ST202203082697 | 2022-03-26 | P/FBW/MDS/1077838/2022 | 2022-04-14
1417 | MDTI49 | MDTI49 | Thanjavur | Trichy |  | ROTN | Summit | I-TN-KUTM-ENB-9015 |  |  | On Air | 2022-03-22 | MDTI49 | 4G_FD900_MDTI49 | 4G_FD2100_MDTI49 | 4G_TD_MDTI49 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085848 | 2022-03-30 | P/FVC/MDS/1078171/2022 | 2022-04-15 | ST202203084955 | 2022-03-29 | P/FVC/MDS/1078126/2022 | 2022-04-15 |  |  |  |  | ST202203083986 | 2022-03-28 | P/FBW/MDS/1077884/2022 | 2022-04-14
1418 | TRY396 | TRY396 | Tiruchirappalli | Trichy |  | ROTN | ATC |  |  |  | On Air | 2022-03-22 | TRY396 | 4G_FD900_TRY396 | 4G_FD2100_TRY396 | 4G_TD_TRY396 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085667 | 2022-03-29 | P/FVC/MDS/1078086/2022 | 2022-04-14 | ST202203084705 | 2022-03-29 | P/FVC/MDS/1077987/2022 | 2022-04-14 |  |  |  |  | ST202203082677 | 2022-03-26 | P/FBW/MDS/1077828/2022 | 2022-04-14
1419 | MARAD3 | MARAD3 | Thanjavur | Trichy |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | MARAD3 | 4G_FD900_MARAD3 | 4G_FD2100_MARAD3 | 4G_TD_MARAD3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085708 | 2022-03-29 | P/FVC/MDS/1078097/2022 | 2022-04-14 | ST202203084802 | 2022-03-29 | P/FVC/MDS/1077999/2022 | 2022-04-14 |  |  |  |  | ST202203082701 | 2022-03-26 | P/FBW/MDS/1077840/2022 | 2022-04-14
1420 | NRAYR2 | NRAYR2 | Viluppuram | Trichy |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | NRAYR2 | 4G_FD900_NRAYR2 | 4G_FD2100_NRAYR2 | 4G_TD_NRAYR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085720 | 2022-03-29 | P/FVC/MDS/1078102/2022 | 2022-04-14 | ST202203084817 | 2022-03-29 | P/FVC/MDS/1078004/2022 | 2022-04-14 |  |  |  |  | ST202203082746 | 2022-03-26 | P/FBW/MDS/1077845/2022 | 2022-04-14
1421 | KALUR3 | KALUR3 | Vellore | Vellore |  | ROTN | Indus | - | R/NN-647713 |  | On Air | 2022-03-25 | KALUR3 | 4G_FD900_KALUR3 | 4G_FD2100_KALUR3 | 4G_TD_KALUR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085684 | 2022-03-29 | P/FVC/MDS/1078087/2022 | 2022-04-14 | ST202203084707 | 2022-03-29 | P/FVC/MDS/1077988/2022 | 2022-04-14 |  |  |  |  | ST202203082678 | 2022-03-26 | P/FBW/MDS/1077829/2022 | 2022-04-14
1422 | ADILA2 | ADILA2 | Dharmapuri | Vellore |  | ROTN | Indus | - | R/NN-647714 |  |  | 2022-03-22 | ADILA2 | 4G_FD900_ADILA2 | 4G_FD2100_ADILA2 | 4G_TD_ADILA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085744 | 2022-03-29 | P/FVC/MDS/1078112/2022 | 2022-04-14 | ST202203084843 | 2022-03-29 | P/FVC/MDS/1078014/2022 | 2022-04-14 |  |  |  |  | ST202203082764 | 2022-03-26 | P/FBW/MDS/1077855/2022 | 2022-04-14
1423 | NATAN2 | NATAN2 | Pudukkottai | Trichy |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | NATAN2 | 4G_FD900_NATAN2 | 4G_FD2100_NATAN2 | 4G_TD_NATAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110353 | 2022-04-19 | P/FVC/MDS/1078931/2022 | 2022-05-02 | ST202204109993 | 2022-04-19 | P/FVC/MDS/1078993/2022 | 2022-05-03 |  |  |  |  | ST202204109550 | 2022-04-19 | P/FVC/MDS/1078889/2022 | 2022-05-02
1424 | VNRKT2 | VNRKT2 | Vellore | Vellore |  | ROTN | Indus | IN-3125576 | R/NN-647716 |  | On Air | 2022-03-17 | VNRKT2 | 4G_FD900_VNRKT2 | 4G_FD2100_VNRKT2 | 4G_TD_VNRKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085640 | 2022-03-29 | P/FVC/MDS/1078074/2022 | 2022-04-14 | ST202203084680 | 2022-03-29 | P/FVC/MDS/1077975/2022 | 2022-04-14 |  |  |  |  | ST202203082660 | 2022-03-26 | P/FBW/MDS/1077814/2022 | 2022-04-14
1425 | ALAGU2 | ALAGU2 | Kancheepuram | Chennai |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | ALAGU2 | 4G_FD900_ALAGU2 | 4G_FD2100_ALAGU2 | 4G_TD_ALAGU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085722 | 2022-03-29 | P/FVC/MDS/1078104/2022 | 2022-04-14 | ST202203084826 | 2022-03-29 | P/FVC/MDS/1078006/2022 | 2022-04-14 |  |  |  |  | ST202203082748 | 2022-03-26 | P/FBW/MDS/1077847/2022 | 2022-04-14
1426 | DPI058 | DPI058 | Dharmapuri | Vellore |  | ROTN | Indus | - | R/NN-647718 |  | SO | 2022-03-22 | DPI058 | 4G_FD900_DPI058 | 4G_FD2100_DPI058 | 4G_TD_DPI058 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085657 | 2022-03-29 | P/FVC/MDS/1078081/2022 | 2022-04-14 | ST202203084693 | 2022-03-29 | P/FVC/MDS/1077982/2022 | 2022-04-14 |  |  |  |  | ST202203082670 | 2022-03-26 | P/FBW/MDS/1077823/2022 | 2022-04-14
1427 | KADGT2 | KADGT2 | Dharmapuri | Vellore |  | ROTN | Indus | - | R/NN-647761 |  | On Air | 2022-03-22 | KADGT2 | 4G_FD900_KADGT2 | 4G_FD2100_KADGT2 | 4G_TD_KADGT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085748 | 2022-03-29 | P/FVC/MDS/1078114/2022 | 2022-04-14 | ST202203084849 | 2022-03-29 | P/FVC/MDS/1078016/2022 | 2022-04-14 |  |  |  |  | ST202203083959 | 2022-03-28 | P/FBW/MDS/1077874/2022 | 2022-04-14
1428 | DEVAU2 | DEVAU2 | Salem | Vellore |  | ROTN | Indus | - | R/NN-647767 |  | On Air | 2022-03-22 | DEVAU2 | 4G_FD900_DEVAU2 | 4G_FD2100_DEVAU2 | 4G_TD_DEVAU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085664 | 2022-03-29 | P/FVC/MDS/1078083/2022 | 2022-04-14 | ST202203084700 | 2022-03-29 | P/FVC/MDS/1077984/2022 | 2022-04-14 |  |  |  |  | ST202203082672 | 2022-03-26 | P/FBW/MDS/1077825/2022 | 2022-04-14
1429 | PVLKT2 | PVLKT2 | Tirunelveli | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | PVLKT2 | 4G_FD900_PVLKT2 | 4G_FD2100_PVLKT2 | 4G_TD_PVLKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148306 | 2022-05-28 | P/FVC/MDS/1081257/2022 | 2022-06-03 | ST202205147196 | 2022-05-27 | P/FVC/MDS/1081104/2022 | 2022-06-03 |  |  |  |  | ST202205147765 | 2022-05-27 | P/FBW/MDS/1081178/2022 | 2022-06-03
1430 | PKT216 | PKT216 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-PYMK-ENB-0040 | SR-TN000909 |  | On Air | 2022-03-08 | PKT216 | 4G_FD900_PKT216 | 4G_FD2100_PKT216 | 4G_TD_PKT216 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053428 | 2022-02-23 | P/FVC/MDS/1076397/2022 | 2022-03-13 | ST202202055604 | 2022-02-26 | P/FVC/MDS/1075612/2022 | 2022-03-10 |  |  |  |  | ST202202054307 | 2022-02-24 | P/FBW/MDS/1075513/2022 | 2022-03-10
1431 | PKT217 | PKT217 | Tirunelveli | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | PKT217 | 4G_FD900_PKT217 | 4G_FD2100_PKT217 | 4G_TD_PKT217 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085699 | 2022-03-29 | P/FVC/MDS/1078094/2022 | 2022-04-14 | ST202203084749 | 2022-03-29 | P/FVC/MDS/1077996/2022 | 2022-04-14 | ST202212811930 | 2022-12-14 | P/FVC/MDS/1119363/2022 | 2022-12-20 | ST202203082696 | 2022-03-26 | P/FBW/MDS/1077837/2022 | 2022-04-14
1432 | PKT218 | PKT218 | Tirunelveli | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | PKT218 | 4G_FD900_PKT218 | 4G_FD2100_PKT218 | 4G_TD_PKT218 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085738 | 2022-03-29 | P/FVC/MDS/1078110/2022 | 2022-04-14 | ST202203084839 | 2022-03-29 | P/FVC/MDS/1078012/2022 | 2022-04-14 |  |  |  |  | ST202203082762 | 2022-03-26 | P/FBW/MDS/1077853/2022 | 2022-04-14
1433 | PKT220 | PKT220 | Tirunelveli | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | PKT220 | 4G_FD900_PKT220 | 4G_FD2100_PKT220 | 4G_TD_PKT220 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085698 | 2022-03-29 | P/FVC/MDS/1078093/2022 | 2022-04-14 | ST202203084724 | 2022-03-29 | P/FVC/MDS/1077995/2022 | 2022-04-14 |  |  |  |  | ST202203082693 | 2022-03-26 | P/FBW/MDS/1077836/2022 | 2022-04-14
1434 | PKT222 | PKT222 | Tirunelveli | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | PKT222 | 4G_FD900_PKT222 | 4G_FD2100_PKT222 | 4G_TD_PKT222 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085692 | 2022-03-29 | P/FVC/MDS/1078092/2022 | 2022-04-14 | ST202203084723 | 2022-03-29 | P/FVC/MDS/1077994/2022 | 2022-04-14 |  |  |  |  | ST202203082692 | 2022-03-26 | P/FBW/MDS/1077835/2022 | 2022-04-14
1435 | PKT224 | PKT224 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-KBYG-ENB-9001 | SR-TN000910 |  | On Air | 2022-03-08 | PKT224 | 4G_FD900_PKT224 | 4G_FD2100_PKT224 | 4G_TD_PKT224 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053429 | 2022-02-23 | P/FVC/MDS/1076398/2022 | 2022-03-13 | ST202202055605 | 2022-02-26 | P/FVC/MDS/1075613/2022 | 2022-03-10 |  |  |  |  | ST202202054309 | 2022-02-24 | P/FBW/MDS/1075514/2022 | 2022-03-10
1436 | PKT225 | PKT225 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/TT/13840 | - |  | On Air | 2022-03-08 | PKT225 | 4G_FD900_PKT225 | 4G_FD2100_PKT225 | 4G_TD_PKT225 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053434 | 2022-02-23 | P/FVC/MDS/1076399/2022 | 2022-03-13 | ST202202055606 | 2022-02-26 | P/FVC/MDS/1075614/2022 | 2022-03-10 |  |  |  |  | ST202202054310 | 2022-02-24 | P/FBW/MDS/1075515/2022 | 2022-03-10
1437 | TATNP2 | TATNP2 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-ABAM-ENB-9054 | SR-TN000908 |  | On Air | 2022-03-08 | TATNP2 | 4G_FD900_TATNP2 | 4G_FD2100_TATNP2 | 4G_TD_TATNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053441 | 2022-02-23 | P/FVC/MDS/1076404/2022 | 2022-03-13 | ST202202055611 | 2022-02-26 | P/FVC/MDS/1075619/2022 | 2022-03-10 |  |  |  |  | ST202202054324 | 2022-02-24 | P/FBW/MDS/1075520/2022 | 2022-03-10
1438 | ARGI25 | ARGI25 | Pudukkottai | Trichy |  | ROTN | Ascend | - |  |  | SO | 2022-03-25 | ARGI25 | 4G_FD900_ARGI25 | 4G_FD2100_ARGI25 | 4G_TD_ARGI25 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085736 | 2022-03-29 | P/FVC/MDS/1078108/2022 | 2022-04-14 | ST202203084832 | 2022-03-29 | P/FVC/MDS/1078010/2022 | 2022-04-14 |  |  |  |  | ST202203082760 | 2022-03-26 | P/FBW/MDS/1077851/2022 | 2022-04-14
1439 | TIRPD2 | TIRPD2 | Viluppuram | Trichy |  | ROTN | Ascend | TNBS0006 | - |  | On Air | 2022-03-08 | TIRPD2 | 4G_FD900_TIRPD2 | 4G_FD2100_TIRPD2 | 4G_TD_TIRPD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060507 | 2022-03-02 | P/FVC/MDS/1076586/2022 | 2022-03-13 | ST202203059469 | 2022-03-02 | P/FVC/MDS/1076539/2022 | 2022-03-13 |  |  |  |  | ST202203059196 | 2022-03-01 | P/FBW/MDS/1076482/2022 | 2022-03-13
1440 | TKERN2 | TKERN2 | Viluppuram | Trichy |  | ROTN | Ascend | TNBS0024 | - |  | On Air | 2022-03-08 | TKERN2 | 4G_FD900_TKERN2 | 4G_FD2100_TKERN2 | 4G_TD_TKERN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060508 | 2022-03-02 | P/FVC/MDS/1076587/2022 | 2022-03-13 | ST202203059470 | 2022-03-02 | P/FVC/MDS/1076540/2022 | 2022-03-13 |  |  |  |  | ST202203059197 | 2022-03-01 | P/FBW/MDS/1076483/2022 | 2022-03-13
1441 | KRIUR6 | KRIUR6 | Cuddalore | Trichy |  | ROTN | Ascend | TNBS0041 | - |  | On Air | 2022-03-08 | KRIUR6 | 4G_FD900_KRIUR6 | 4G_FD2100_KRIUR6 | 4G_TD_KRIUR6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060511 | 2022-03-02 | P/FVC/MDS/1076588/2022 | 2022-03-13 | ST202203059471 | 2022-03-02 | P/FVC/MDS/1076541/2022 | 2022-03-13 |  |  |  |  | ST202203059201 | 2022-03-01 | P/FBW/MDS/1076484/2022 | 2022-03-13
1442 | SDVDM2 | SDVDM2 | Sivaganga | Madurai |  | ROTN | Ascend | 1322 | - |  | On Air | 2022-03-08 | SDVDM2 | 4G_FD900_SDVDM2 | 4G_FD2100_SDVDM2 | 4G_TD_SDVDM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060512 | 2022-03-02 | P/FVC/MDS/1076589/2022 | 2022-03-13 | ST202203059475 | 2022-03-02 | P/FVC/MDS/1076542/2022 | 2022-03-13 |  |  |  |  | ST202203059202 | 2022-03-01 | P/FBW/MDS/1076485/2022 | 2022-03-13
1443 | ADNKT3 | ADNKT3 | Thanjavur | Trichy |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | ADNKT3 | 4G_FD900_ADNKT3 | 4G_FD2100_ADNKT3 | 4G_TD_ADNKT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085715 | 2022-03-29 | P/FVC/MDS/1078101/2022 | 2022-04-14 | ST202203084807 | 2022-03-29 | P/FVC/MDS/1078003/2022 | 2022-04-14 |  |  |  |  | ST202203082739 | 2022-03-26 | P/FBW/MDS/1077844/2022 | 2022-04-14
1444 | VALAD2 | VALAD2 | Tiruchirappalli | Trichy |  | ROTN | Ascend | 2510 | - |  | On Air | 2022-03-08 | VALAD2 | 4G_FD900_VALAD2 | 4G_FD2100_VALAD2 | 4G_TD_VALAD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060516 | 2022-03-02 | P/FVC/MDS/1076591/2022 | 2022-03-13 | ST202203059480 | 2022-03-02 | P/FVC/MDS/1076544/2022 | 2022-03-13 |  |  |  |  | ST202203059213 | 2022-03-01 | P/FBW/MDS/1076487/2022 | 2022-03-13
1445 | PNCMP2 | PNCMP2 | Karur | Coimbatore |  | ROTN | Ascend | 4473 | - |  | On Air | 2022-03-08 | PNCMP2 | 4G_FD900_PNCMP2 | 4G_FD2100_PNCMP2 | 4G_TD_PNCMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060519 | 2022-03-02 | P/FVC/MDS/1076594/2022 | 2022-03-13 | ST202203059490 | 2022-03-02 | P/FVC/MDS/1076547/2022 | 2022-03-13 |  |  |  |  | ST202203059219 | 2022-03-01 | P/FBW/MDS/1076490/2022 | 2022-03-13
1446 | VIGDM2 | VIGDM2 | Theni | Madurai |  | ROTN | ATC | - |  |  | On Air | 2022-03-22 | VIGDM2 | 4G_FD900_VIGDM2 | 4G_FD2100_VIGDM2 | 4G_TD_VIGDM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085845 | 2022-03-30 | P/FVC/MDS/1078168/2022 | 2022-04-15 | ST202203084945 | 2022-03-29 | P/FVC/MDS/1078123/2022 | 2022-04-15 |  |  |  |  | ST202203083977 | 2022-03-28 | P/FBW/MDS/1077881/2022 | 2022-04-14
1447 | TENI38 | TENI38 | Theni | Madurai |  | ROTN | Summit | I-TN-TGMM-ENB-9012 |  |  | On Air | 2022-03-22 | TENI38 | 4G_FD900_TENI38 | 4G_FD2100_TENI38 | 4G_TD_TENI38 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085849 | 2022-03-30 | P/FVC/MDS/1078172/2022 | 2022-04-15 | ST202203084959 | 2022-03-29 | P/FVC/MDS/1078127/2022 | 2022-04-15 |  |  |  |  | ST202203083988 | 2022-03-28 | P/FBW/MDS/1077885/2022 | 2022-04-14
1448 | PLMPM4 | PLMPM4 | Karur | Coimbatore |  | ROTN | ATC | ATC/TA/BS/00006 | - |  | On Air | 2022-03-08 | PLMPM4 | 4G_FD900_PLMPM4 | 4G_FD2100_PLMPM4 | 4G_TD_PLMPM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056736 | 2022-02-27 | P/FVC/MDS/1076479/2022 | 2022-03-13 | ST202203059456 | 2022-03-02 | P/FVC/MDS/1076532/2022 | 2022-03-13 |  |  |  |  | ST202202056499 | 2022-02-26 | P/FBW/MDS/1075598/2022 | 2022-03-10
1449 | UTKDU3 | UTKDU3 | Kancheepuram | Chennai |  | ROTN | ATC | ATC/TA/BS/00009 | - |  | On Air | 2022-03-08 | UTKDU3 | 4G_FD900_UTKDU3 | 4G_FD2100_UTKDU3 | 4G_TD_UTKDU3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203062676 | 2022-03-04 | P/FVC/MDS/1076631/2022 | 2022-03-13 | ST202203064583 | 2022-03-07 | P/FVC/MDS/1076907/2022 | 2022-03-23 |  |  |  |  | ST202203062627 | 2022-03-04 | P/FBW/MDS/1076531/2022 | 2022-03-13
1450 | PULVK2 | PULVK2 | Thiruvarur | Trichy |  | ROTN | ATC | TN/TA/PR/11163 | - |  | On Air | 2022-03-08 | PULVK2 | 4G_FD900_PULVK2 | 4G_FD2100_PULVK2 | 4G_TD_PULVK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056738 | 2022-02-27 | P/FVC/MDS/1076481/2022 | 2022-03-13 | ST202203059460 | 2022-03-02 | P/FVC/MDS/1076534/2022 | 2022-03-13 |  |  |  |  | ST202202056739 | 2022-02-27 | P/FBW/MDS/1075600/2022 | 2022-03-10
1451 | SOGND2 | SOGND2 | Kancheepuram | Chennai |  | ROTN | ATC | TN/VE/TT/14253 | - |  | On Air | 2022-03-08 | SOGND2 | 4G_FD900_SOGND2 | 4G_FD2100_SOGND2 | 4G_TD_SOGND2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060498 | 2022-03-02 | P/FVC/MDS/1076582/2022 | 2022-03-13 | ST202203059461 | 2022-03-02 | P/FVC/MDS/1076535/2022 | 2022-03-13 |  |  |  |  | ST202202056740 | 2022-02-27 | P/FBW/MDS/1075601/2022 | 2022-03-10
1452 | ARULB2 | ARULB2 | Viluppuram | Trichy |  | ROTN | ATC | TN/VLP/TT/18015 | - |  | On Air | 2022-03-08 | ARULB2 | 4G_FD900_ARULB2 | 4G_FD2100_ARULB2 | 4G_TD_ARULB2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203060499 | 2022-03-02 | P/FVC/MDS/1076583/2022 | 2022-03-13 | ST202203059465 | 2022-03-02 | P/FVC/MDS/1076536/2022 | 2022-03-13 |  |  |  |  | ST202202056741 | 2022-02-27 | P/FBW/MDS/1075602/2022 | 2022-03-10
1453 | PAPPN3 | PAPPN3 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-ABAM-ENB-9032 |  |  | On Air | 2022-03-22 | PAPPN3 | 4G_FD900_PAPPN3 | 4G_FD2100_PAPPN3 | 4G_TD_PAPPN3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085852 | 2022-03-30 | P/FVC/MDS/1078175/2022 | 2022-04-15 | ST202203059497 | 2022-03-02 | P/FVC/MDS/1076550/2022 | 2022-03-13 |  |  |  |  | ST202203059224 | 2022-03-01 | P/FBW/MDS/1076493/2022 | 2022-03-13
1454 | THRKT2 | THRKT2 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-CMBM-ENB-9068 |  |  | On Air | 2022-03-22 | THRKT2 | 4G_FD900_THRKT2 | 4G_FD2100_THRKT2 | 4G_TD_THRKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085850 | 2022-03-30 | P/FVC/MDS/1078173/2022 | 2022-04-15 | ST202203084960 | 2022-03-29 | P/FVC/MDS/1078128/2022 | 2022-04-15 |  |  |  |  | ST202203059225 | 2022-03-01 | P/FBW/MDS/1076494/2022 | 2022-03-13
1455 | ALKLI2 | ALKLI2 | Erode | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-03-22 | ALKLI2 | 4G_FD900_ALKLI2 | 4G_FD2100_ALKLI2 | 4G_TD_ALKLI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085842 | 2022-03-30 | P/FVC/MDS/1078165/2022 | 2022-04-15 | ST202203084930 | 2022-03-29 | P/FVC/MDS/1078120/2022 | 2022-04-15 |  |  |  |  | ST202203083967 | 2022-03-28 | P/FBW/MDS/1077878/2022 | 2022-04-14
1456 | GPLSM2 | GPLSM2 | Tirunelveli | Madurai |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | GPLSM2 | 4G_FD900_GPLSM2 | 4G_FD2100_GPLSM2 | 4G_TD_GPLSM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085737 | 2022-03-29 | P/FVC/MDS/1078109/2022 | 2022-04-14 | ST202203084838 | 2022-03-29 | P/FVC/MDS/1078011/2022 | 2022-04-14 |  |  |  |  | ST202203082761 | 2022-03-26 | P/FBW/MDS/1077852/2022 | 2022-04-14
1457 | SRYMD3 | SRYMD3 | Viluppuram | Trichy |  | ROTN | Ascend | - |  |  | On Air | 2022-03-25 | SRYMD3 | 4G_FD900_SRYMD3 | 4G_FD2100_SRYMD3 | 4G_TD_SRYMD3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085728 | 2022-03-29 | P/FVC/MDS/1078105/2022 | 2022-04-14 | ST202203084827 | 2022-03-29 | P/FVC/MDS/1078007/2022 | 2022-04-14 |  |  |  |  | ST202203082756 | 2022-03-26 | P/FBW/MDS/1077848/2022 | 2022-04-14
1458 | COLKO3 | COLKO3 | Namakkal | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-03-22 | COLKO3 | 4G_FD900_COLKO3 | 4G_FD2100_COLKO3 | 4G_TD_COLKO3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085843 | 2022-03-30 | P/FVC/MDS/1078166/2022 | 2022-04-15 | ST202203084937 | 2022-03-29 | P/FVC/MDS/1078121/2022 | 2022-04-15 |  |  |  |  | ST202203083973 | 2022-03-28 | P/FBW/MDS/1077879/2022 | 2022-04-14
1459 | TIR480 | TIR480 |  |  |  | ROTN | Indus | IN-3108981 | R/NN-638312 |  |  | 2022-03-17 | TIR480 | 4G_FD900_TIR480 | 4G_FD2100_TIR480 | 4G_TD_TIR480 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085502 | 2022-03-29 | P/FVC/MDS/1078065/2022 | 2022-04-14 | ST202203084664 | 2022-03-29 | P/FVC/MDS/1077966/2022 | 2022-04-14 | ST202204111901 | 2022-04-20 | P/FVC/MDS/1079019/2022 | 2022-05-03 | ST202203082638 | 2022-03-26 | P/FBW/MDS/1077804/2022 | 2022-04-14
1460 | VALLR3 | VALLR3 |  |  |  | ROTN | Summit | I-TN-CMBM-ENB-9043 | SR-TN000670 |  |  | 2022-02-19 | VALLR3 | 4G_FD900_VALLR3 | 4G_FD2100_VALLR3 | 4G_TD_VALLR3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202202052202 | 2022-02-22 | P/FVC/MDS/1076290/2022 | 2022-03-13 | ST202202054437 | 2022-02-24 | P/FVC/MDS/1076185/2022 | 2022-03-13 | ST202202049487 | 2022-02-19 | P/FVC/MDS/1074804/2022 | 2022-02-25 | ST202202053467 | 2022-02-23 | P/FBW/MDS/1076086/2022 | 2022-03-13
1461 | COWP93 | COWP93 |  |  |  | ROTN | Indus | IN-3123956 | R/NN-645590 |  |  | 2022-03-02 | COWP93 | 4G_FD900_COWP93 | 4G_FD2100_COWP93 | 4G_TD_COWP93 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202203061484 | 2022-03-03 | P/FVC/MDS/1076626/2022 | 2022-03-13 | ST202203061580 | 2022-03-03 | P/FVC/MDS/1076578/2022 | 2022-03-13 | ST202203062907 | 2022-03-04 | P/FVC/MDS/1076639/2022 | 2022-03-13 | ST202203062298 | 2022-03-04 | P/FBW/MDS/1076522/2022 | 2022-03-13
1462 | MGRN12 | MGRN12 |  |  |  | CHN | Indus | IN-3124077 | R/NN-645869 |  | On air | 2022-03-10 | MGRN12 | 4G_FD900_MGRN12 | 4G_FD2100_MGRN12 | 4G_TD_MGRN12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074010 | 2022-03-16 | P/FVC/MDS/1077177/2022 | 2022-03-30 | ST202203073636 | 2022-03-16 | P/FVC/MDS/1077129/2022 | 2022-03-30 |  |  |  |  | ST202203072980 | 2022-03-15 | P/FBW/MDS/1077082/2022 | 2022-03-30
1463 | PRNG32 | PRNG32 |  |  |  | CHN | TVI | - | - |  | On air | 2022-03-16 | PRNG32 | 4G_FD900_PRNG32 | 4G_FD2100_PRNG32 | 4G_TD_PRNG32 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203084560 | 2022-03-29 | P/FVC/MDS/1078041/2022 | 2022-04-14 | ST202203084464 | 2022-03-28 | P/FVC/MDS/1077942/2022 | 2022-04-14 | ST202204095123 | 2022-04-08 | P/FVC/MDS/1078413/2022 | 2022-04-21 | ST202203082610 | 2022-03-26 | P/FBW/MDS/1077799/2022 | 2022-04-14
1464 | POTHR2 | POTHR2 |  |  |  | CHN | Indus | IN-1284991 | R/RES-508894 |  | On air | 2022-02-24 | POTHR2 | 4G_FD900_POTHR2 | 4G_FD2100_POTHR2 | 4G_TD_POTHR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202056712 | 2022-02-27 | P/FVC/MDS/1076455/2022 | 2022-03-13 | ST202202055878 | 2022-02-26 | P/FVC/MDS/1075671/2022 | 2022-03-10 | ST202204095117 | 2022-04-08 | P/FVC/MDS/1078408/2022 | 2022-04-21 | ST202202056464 | 2022-02-26 | P/FBW/MDS/1075574/2022 | 2022-03-10
1465 | PUZH18 | PUZH18 |  |  |  | CHN | Ascend |  |  |  | SO | 2022-03-25 | PUZH18 | 4G_FD900_PUZH18 | 4G_FD2100_PUZH18 | 4G_TD_PUZH18 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203085714 | 2022-03-29 | P/FVC/MDS/1078100/2022 | 2022-04-14 | ST202203084806 | 2022-03-29 | P/FVC/MDS/1078002/2022 | 2022-04-14 | ST202204095124 | 2022-04-08 | P/FVC/MDS/1078414/2022 | 2022-04-21 | ST202203082738 | 2022-03-26 | P/FBW/MDS/1077843/2022 | 2022-04-14
1466 | EDACH3 | EDACH3 |  |  |  | CHN | Airtel | - | - |  | On air | 2022-03-16 | EDACH3 | 4G_FD900_EDACH3 | 4G_FD2100_EDACH3 | 4G_TD_EDACH3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093165 | 2022-04-07 | P/FVC/MDS/1078390/2022 | 2022-04-21 | ST202204093152 | 2022-04-07 | P/FVC/MDS/1078349/2022 | 2022-04-21 | ST202204095122 | 2022-04-08 | P/FVC/MDS/1078412/2022 | 2022-04-21 | ST202204093058 | 2022-04-06 | P/FBW/MDS/1078292/2022 | 2022-04-21
1467 | POTRH2 | POTRH2 |  |  |  | CHN | Airtel | - | - |  | On air | 2022-03-10 | POTRH2 | 4G_FD900_POTRH2 | 4G_FD2100_POTRH2 | 4G_TD_POTRH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074023 | 2022-03-16 | P/FVC/MDS/1077181/2022 | 2022-03-30 | ST202203073643 | 2022-03-16 | P/FVC/MDS/1077133/2022 | 2022-03-30 | ST202204095118 | 2022-04-08 | P/FVC/MDS/1078409/2022 | 2022-04-21 | ST202203072995 | 2022-03-15 | P/FBW/MDS/1077086/2022 | 2022-03-30
1468 | EDPLY2 | EDPLY2 |  |  |  | CHN | Airtel | - | - |  | On air | 2022-03-10 | EDPLY2 | 4G_FD900_EDPLY2 | 4G_FD2100_EDPLY2 | 4G_TD_EDPLY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203074024 | 2022-03-16 | P/FVC/MDS/1077182/2022 | 2022-03-30 | ST202203084087 | 2022-03-28 | P/FVC/MDS/1077917/2022 | 2022-04-14 | ST202204095120 | 2022-04-08 | P/FVC/MDS/1078411/2022 | 2022-04-21 | ST202203082310 | 2022-03-26 | P/FBW/MDS/1077757/2022 | 2022-04-14
1469 | VADAB3 | VADAB3 |  |  |  | CHN | Airtel | - | - |  | On air | 2022-03-10 | VADAB3 | 4G_FD900_VADAB3 | 4G_FD2100_VADAB3 | 4G_TD_VADAB3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148749 | 2022-05-28 | P/FVC/MDS/1081316/2022 | 2022-06-03 | ST202205147397 | 2022-05-27 | P/FVC/MDS/1081163/2022 | 2022-06-03 | ST202204095119 | 2022-04-08 | P/FVC/MDS/1078410/2022 | 2022-04-21 | ST202205148149 | 2022-05-28 | P/FBW/MDS/1081237/2022 | 2022-06-03
1470 | MAND21 | MAND21 |  |  |  | CHN | Indus | IN-3123752 | R/NN-644873 |  |  | 2022-03-17 | MAND21 | 4G_FD900_MAND21 | 4G_FD2100_MAND21 | 4G_TD_MAND21 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202203085626 | 2022-03-29 | P/FVC/MDS/1078071/2022 | 2022-04-14 | ST202203084676 | 2022-03-29 | P/FVC/MDS/1077972/2022 | 2022-04-14 | ST202203086227 | 2022-03-30 | P/FVC/MDS/1078216/2022 | 2022-04-15 | ST202203082656 | 2022-03-26 | P/FBW/MDS/1077810/2022 | 2022-04-14
1471 | GNGE7 | GNGE07 |  |  |  | ROTN | Indus | IN-3120127 | R/NN-641185 |  | On Air | 2022-03-25 | GNGE07 | 4G_FD900_GNGE07 | 4G_FD2100_GNGE07 | 4G_TD_GNGE07 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092549 | 2022-04-06 | P/FVC/MDS/1078359/2022 | 2022-04-21 | ST202204093121 | 2022-04-07 | P/FVC/MDS/1078318/2022 | 2022-04-21 |  |  |  |  | ST202204092253 | 2022-04-06 | P/FBW/MDS/1078255/2022 | 2022-04-21
1472 | APTNM9 | APTNM9 |  |  |  | ROTN | Indus | IN-3123717 | R/NN-645486 |  | SR | 2022-03-25 | APTNM9 | 4G_FD900_APTNM9 | 4G_FD2100_APTNM9 | 4G_TD_APTNM9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092546 | 2022-04-06 | P/FVC/MDS/1078358/2022 | 2022-04-21 | ST202204093120 | 2022-04-07 | P/FVC/MDS/1078317/2022 | 2022-04-21 |  |  |  |  | ST202204092252 | 2022-04-06 | P/FBW/MDS/1078254/2022 | 2022-04-21
1473 | CBE916 | CBE916 |  |  |  | ROTN | Indus | IN-3123533 | R/NN-644776 |  |  | 2022-03-25 | CBE916 | 4G_FD900_CBE916 | 4G_FD2100_CBE916 | 4G_TD_CBE916 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092551 | 2022-04-06 | P/FVC/MDS/1078361/2022 | 2022-04-21 | ST202204093123 | 2022-04-07 | P/FVC/MDS/1078320/2022 | 2022-04-21 |  |  |  |  | ST202204092256 | 2022-04-06 | P/FBW/MDS/1078257/2022 | 2022-04-21
1474 | TENKR4 | TENKR4 |  |  |  | ROTN | ATC |  |  |  | SO | 2022-04-06 | TENKR4 | 4G_FD900_TENKR4 | 4G_FD2100_TENKR4 | 4G_TD_TENKR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403828 | 2022-09-08 | P/FVC/MDS/1096561/2022 | 2022-09-16 | ST202209404036 | 2022-09-08 | P/FVC/MDS/1096470/2022 | 2022-09-16 |  |  |  |  | ST202209399056 | 2022-09-07 | P/FVC/MDS/1096376/2022 | 2022-09-16
1475 | PKNPT2 | PKNPT2 |  |  |  | ROTN | ATC | - | - |  | On Air | 2022-04-06 | PKNPT2 | 4G_FD900_PKNPT2 | 4G_FD2100_PKNPT2 | 4G_TD_PKNPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093161 | 2022-04-07 | P/FVC/MDS/1078386/2022 | 2022-04-21 | ST202204093148 | 2022-04-07 | P/FVC/MDS/1078345/2022 | 2022-04-21 |  |  |  |  | ST202204093043 | 2022-04-06 | P/FBW/MDS/1078288/2022 | 2022-04-21
1476 | SPD108 | SPD108 |  |  |  | ROTN | ATC | TN/CH/AT/22716 | - |  | On Air | 2022-03-25 | SPD108 | 4G_FD900_SPD108 | 4G_FD2100_SPD108 | 4G_TD_SPD108 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092542 | 2022-04-06 | P/FVC/MDS/1078356/2022 | 2022-04-21 | ST202204093118 | 2022-04-07 | P/FVC/MDS/1078315/2022 | 2022-04-21 |  |  |  |  | ST202204094800 | 2022-04-08 | P/FBW/MDS/1078300/2022 | 2022-04-21
1477 | PULLV2 | PULLV2 |  |  |  | ROTN | Indus | IN-3126632 | R/NN-648800 |  | On Air | 2022-03-30 | PULLV2 | 4G_FD900_PULLV2 | 4G_FD2100_PULLV2 | 4G_TD_PULLV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092680 | 2022-04-06 | P/FVC/MDS/1078368/2022 | 2022-04-21 | ST202204093131 | 2022-04-07 | P/FVC/MDS/1078328/2022 | 2022-04-21 |  |  |  |  | ST202204092271 | 2022-04-06 | P/FBW/MDS/1078265/2022 | 2022-04-21
1478 | GUNDU3 | GUNDU3 |  |  |  | ROTN | Indus | - | R/NN-640104 |  | On Air | 2022-04-06 | GUNDU3 | 4G_FD900_GUNDU3 | 4G_FD2100_GUNDU3 | 4G_TD_GUNDU3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093155 | 2022-04-07 | P/FVC/MDS/1078380/2022 | 2022-04-21 | ST202204093142 | 2022-04-07 | P/FVC/MDS/1078339/2022 | 2022-04-21 |  |  |  |  | ST202204093031 | 2022-04-06 | P/FBW/MDS/1078282/2022 | 2022-04-21
1479 | KMPM27 | KMPM27 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-13 | KMPM27 | 4G_FD900_KMPM27 | 4G_FD2100_KMPM27 | 4G_TD_KMPM27 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111717 | 2022-04-20 | P/FVC/MDS/1078948/2022 | 2022-05-02 | ST202204110104 | 2022-04-19 | P/FVC/MDS/1079010/2022 | 2022-05-03 |  |  |  |  | ST202204109687 | 2022-04-19 | P/FVC/MDS/1078906/2022 | 2022-05-02
1480 | KITSP2 | KITSP2 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-06 | KITSP2 | 4G_FD900_KITSP2 | 4G_FD2100_KITSP2 | 4G_TD_KITSP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093154 | 2022-04-07 | P/FVC/MDS/1078379/2022 | 2022-04-21 | ST202204093141 | 2022-04-07 | P/FVC/MDS/1078338/2022 | 2022-04-21 |  |  |  |  | ST202204093030 | 2022-04-06 | P/FBW/MDS/1078281/2022 | 2022-04-21
1481 | VALYK2 | VALYK2 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-06 | VALYK2 | 4G_FD900_VALYK2 | 4G_FD2100_VALYK2 | 4G_TD_VALYK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203064668 | 2022-03-07 | P/FVC/MDS/1076961/2022 | 2022-03-23 | ST202203064985 | 2022-03-08 | P/FVC/MDS/1076936/2022 | 2022-03-23 |  |  |  |  | ST202203064954 | 2022-03-08 | P/FBW/MDS/1076906/2022 | 2022-03-23
1482 | DENPL2 | DENPL2 |  |  |  | ROTN | ATC | TN/CO/AT/23031 | - |  | SR | 2022-03-30 | DENPL2 | 4G_FD900_DENPL2 | 4G_FD2100_DENPL2 | 4G_TD_DENPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110265 | 2022-04-19 | P/FVC/MDS/1078918/2022 | 2022-05-02 | ST202204093128 | 2022-04-07 | P/FVC/MDS/1078325/2022 | 2022-04-21 |  |  |  |  | ST202204092263 | 2022-04-06 | P/FBW/MDS/1078262/2022 | 2022-04-21
1483 | SUNPL2 | SUNPL2 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-06 | SUNPL2 | 4G_FD900_SUNPL2 | 4G_FD2100_SUNPL2 | 4G_TD_SUNPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093153 | 2022-04-07 | P/FVC/MDS/1078378/2022 | 2022-04-21 | ST202204093140 | 2022-04-07 | P/FVC/MDS/1078337/2022 | 2022-04-21 |  |  |  |  | ST202204092316 | 2022-04-06 | P/FBW/MDS/1078280/2022 | 2022-04-21
1484 | ETMDI8 | ETMDI8 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-13 | ETMDI8 | 4G_FD900_ETMDI8 | 4G_FD2100_ETMDI8 | 4G_TD_ETMDI8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111702 | 2022-04-20 | P/FVC/MDS/1078942/2022 | 2022-05-02 | ST202204110057 | 2022-04-19 | P/FVC/MDS/1079004/2022 | 2022-05-03 | ST202212780791 | 2022-12-02 | P/AFC/MDS/1118363/2022 | 2022-12-13 | ST202204109634 | 2022-04-19 | P/FVC/MDS/1078900/2022 | 2022-05-02
1485 | KNDPL2 | KNDPL2 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-13 | KNDPL2 | 4G_FD900_KNDPL2 | 4G_FD2100_KNDPL2 | 4G_TD_KNDPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111729 | 2022-04-20 | P/FVC/MDS/1078951/2022 | 2022-05-02 | ST202204110128 | 2022-04-19 | P/FVC/MDS/1079013/2022 | 2022-05-03 |  |  |  |  | ST202204109706 | 2022-04-19 | P/FVC/MDS/1078909/2022 | 2022-05-02
1486 | KUPMT2 | KUPMT2 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-06 | KUPMT2 | 4G_FD900_KUPMT2 | 4G_FD2100_KUPMT2 | 4G_TD_KUPMT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093158 | 2022-04-07 | P/FVC/MDS/1078383/2022 | 2022-04-21 | ST202204093145 | 2022-04-07 | P/FVC/MDS/1078342/2022 | 2022-04-21 |  |  |  |  | ST202204093036 | 2022-04-06 | P/FBW/MDS/1078285/2022 | 2022-04-21
1487 | VELYP2 | VELYP2 |  |  |  | ROTN | Indus |  | R/NN-650565 |  | On Air | 2022-04-13 | VELYP2 | 4G_FD900_VELYP2 | 4G_FD2100_VELYP2 | 4G_TD_VELYP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111711 | 2022-04-20 | P/FVC/MDS/1078946/2022 | 2022-05-02 | ST202204110073 | 2022-04-19 | P/FVC/MDS/1079008/2022 | 2022-05-03 | ST202210548754 | 2022-10-11 | P/FVC/MDS/1113942/2022 | 2022-10-21 | ST202204109659 | 2022-04-19 | P/FVC/MDS/1078904/2022 | 2022-05-02
1488 | DVNPU2 | DVNPU2 |  |  |  | ROTN | Indus | IN-3127759 | R/NN-650521 |  | On Air | 2022-03-30 | DVNPU2 | 4G_FD900_DVNPU2 | 4G_FD2100_DVNPU2 | 4G_TD_DVNPU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092690 | 2022-04-06 | P/FVC/MDS/1078372/2022 | 2022-04-21 | ST202204093135 | 2022-04-07 | P/FVC/MDS/1078332/2022 | 2022-04-21 |  |  |  |  | ST202204092278 | 2022-04-06 | P/FBW/MDS/1078269/2022 | 2022-04-21
1489 | VLIPY2 | VLIPY2 |  |  |  | ROTN | Indus | IN-3127761 | R/NN-650522 |  | On Air | 2022-03-30 | VLIPY2 | 4G_FD900_VLIPY2 | 4G_FD2100_VLIPY2 | 4G_TD_VLIPY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092691 | 2022-04-06 | P/FVC/MDS/1078373/2022 | 2022-04-21 | ST202204093136 | 2022-04-07 | P/FVC/MDS/1078333/2022 | 2022-04-21 |  |  |  |  | ST202204092281 | 2022-04-06 | P/FBW/MDS/1078270/2022 | 2022-04-21
1490 | VRLPT2 | VRLPT2 |  |  |  | ROTN | Indus |  | R/NN-647363 |  | On Air | 2022-04-06 | VRLPT2 | 4G_FD900_VRLPT2 | 4G_FD2100_VRLPT2 | 4G_TD_VRLPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093156 | 2022-04-07 | P/FVC/MDS/1078381/2022 | 2022-04-21 | ST202204093143 | 2022-04-07 | P/FVC/MDS/1078340/2022 | 2022-04-21 |  |  |  |  | ST202204093034 | 2022-04-06 | P/FBW/MDS/1078283/2022 | 2022-04-21
1491 | VDIYM2 | VDIYM2 |  |  |  | ROTN | Indus |  | R/NN-647405 |  |  | 2022-04-06 | VDIYM2 | 4G_FD900_VDIYM2 | 4G_FD2100_VDIYM2 | 4G_TD_VDIYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093157 | 2022-04-07 | P/FVC/MDS/1078382/2022 | 2022-04-21 | ST202204093144 | 2022-04-07 | P/FVC/MDS/1078341/2022 | 2022-04-21 |  |  |  |  | ST202204093035 | 2022-04-06 | P/FBW/MDS/1078284/2022 | 2022-04-21
1492 | TRY395 | TRY395 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-13 | TRY395 | 4G_FD900_TRY395 | 4G_FD2100_TRY395 | 4G_TD_TRY395 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111704 | 2022-04-20 | P/FVC/MDS/1078943/2022 | 2022-05-02 | ST202204110058 | 2022-04-19 | P/FVC/MDS/1079005/2022 | 2022-05-03 |  |  |  |  | ST202204109635 | 2022-04-19 | P/FVC/MDS/1078901/2022 | 2022-05-02
1493 | PKT227 | PKT227 |  |  |  | ROTN | ATC | TN/TR/AI/18763 | - |  | On Air | 2022-03-30 | PKT227 | 4G_FD900_PKT227 | 4G_FD2100_PKT227 | 4G_TD_PKT227 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092682 | 2022-04-06 | P/FVC/MDS/1078370/2022 | 2022-04-21 | ST202204093133 | 2022-04-07 | P/FVC/MDS/1078330/2022 | 2022-04-21 |  |  |  |  | ST202204092273 | 2022-04-06 | P/FBW/MDS/1078267/2022 | 2022-04-21
1494 | THATM2 | THATM2 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-04-06 | THATM2 | 4G_FD900_THATM2 | 4G_FD2100_THATM2 | 4G_TD_THATM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093160 | 2022-04-07 | P/FVC/MDS/1078385/2022 | 2022-04-21 | ST202204093147 | 2022-04-07 | P/FVC/MDS/1078344/2022 | 2022-04-21 |  |  |  |  | ST202204093042 | 2022-04-06 | P/FBW/MDS/1078287/2022 | 2022-04-21
1495 | ADILA5 | ADILA5 |  |  |  | ROTN | Indus | - | R/NN-651670 |  | On Air | 2022-04-13 | ADILA5 | 4G_FD900_ADILA5 | 4G_FD2100_ADILA5 | 4G_TD_ADILA5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111716 | 2022-04-20 | P/FVC/MDS/1078947/2022 | 2022-05-02 | ST202204110103 | 2022-04-19 | P/FVC/MDS/1079009/2022 | 2022-05-03 |  |  |  |  | ST202204109686 | 2022-04-19 | P/FVC/MDS/1078905/2022 | 2022-05-02
1496 | TIR493 | TIR493 |  |  |  | ROTN | Indus | IN-3125577 | R/NN-647717 |  | On Air | 2022-03-30 | TIR493 | 4G_FD900_TIR493 | 4G_FD2100_TIR493 | 4G_TD_TIR493 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092681 | 2022-04-06 | P/FVC/MDS/1078369/2022 | 2022-04-21 | ST202204093132 | 2022-04-07 | P/FVC/MDS/1078329/2022 | 2022-04-21 |  |  |  |  | ST202204092272 | 2022-04-06 | P/FBW/MDS/1078266/2022 | 2022-04-21
1497 | VDPYM2 | VDPYM2 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-04-13 | VDPYM2 | 4G_FD900_VDPYM2 | 4G_FD2100_VDPYM2 | 4G_TD_VDPYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111723 | 2022-04-20 | P/FVC/MDS/1078950/2022 | 2022-05-02 | ST202204110127 | 2022-04-19 | P/FVC/MDS/1079012/2022 | 2022-05-03 |  |  |  |  | ST202204109705 | 2022-04-19 | P/FVC/MDS/1078908/2022 | 2022-05-02
1498 | KPRSAL | KPRSAL |  |  |  | ROTN | Airtel |  |  |  | On Air | 2022-04-06 | KPRSAL | 4G_FD900_KPRSAL | 4G_FD2100_KPRSAL | 4G_TD_KPRSAL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204093164 | 2022-04-07 | P/FVC/MDS/1078389/2022 | 2022-04-21 | ST202204093151 | 2022-04-07 | P/FVC/MDS/1078348/2022 | 2022-04-21 | ST202209444081 | 2022-09-19 | P/FVC/MDS/1098036/2022 | 2022-09-27 | ST202204093051 | 2022-04-06 | P/FBW/MDS/1078291/2022 | 2022-04-21
1499 | NAVIST | NAVIST |  |  |  | CHN | TVI | - | - |  | On Air | 2022-03-25 | NAVIST | 4G_FD900_NAVIST | 4G_FD2100_NAVIST | 4G_TD_NAVIST | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092552 | 2022-04-06 | P/FVC/MDS/1078362/2022 | 2022-04-21 | ST202204093124 | 2022-04-07 | P/FVC/MDS/1078321/2022 | 2022-04-21 |  |  |  |  | ST202204092257 | 2022-04-06 | P/FBW/MDS/1078258/2022 | 2022-04-21
1500 | REDH44 | REDH44 |  |  |  | CHN | Indus | IN-3125637 | R/NN-647799 |  | On air | 2022-03-26 | REDH44 | 4G_FD900_REDH44 | 4G_FD2100_REDH44 | 4G_TD_REDH44 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092554 | 2022-04-06 | P/FVC/MDS/1078363/2022 | 2022-04-21 | ST202204093125 | 2022-04-07 | P/FVC/MDS/1078322/2022 | 2022-04-21 |  |  |  |  | ST202204092259 | 2022-04-06 | P/FBW/MDS/1078259/2022 | 2022-04-21
1501 | ORAKD2 | ORAKD2 |  |  |  | CHN | Indus | IN-3125615 | R/NN-647773 |  | On Air | 2022-03-25 | ORAKD2 | 4G_FD900_ORAKD2 | 4G_FD2100_ORAKD2 | 4G_TD_ORAKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204092555 | 2022-04-06 | P/FVC/MDS/1078364/2022 | 2022-04-21 | ST202204093126 | 2022-04-07 | P/FVC/MDS/1078323/2022 | 2022-04-21 |  |  |  |  | ST202204092260 | 2022-04-06 | P/FBW/MDS/1078260/2022 | 2022-04-21
1502 | CBE658 | CBE658 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-27 | CBE658 | 4G_FD900_CBE658 | 4G_FD2100_CBE658 | 4G_TD_CBE658 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | 2018665240 | 2018-09-14 | P/FBW/MDS/5143584/2018 | 2018-10-01 | 2018415616 | 2018-10-09 | P/FBW/MDS/5226977/2018 | 2018-11-28 | 2018671313 | 2018-09-18 | P/FBW/MDS/5150720/2018 | 2018-10-05 | 2018669909 | 2018-09-17 | P/FVC/MDS/5161661/2018 | 2018-10-17
1503 | TTPTU7 | TTPTU7 |  |  |  | ROTN | Indus |  | R/NN-657256 |  | On Air | 2022-05-05 | TTPTU7 | 4G_FD900_TTPTU7 | 4G_FD2100_TTPTU7 | 4G_TD_TTPTU7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138463 | 2022-05-16 | P/FVC/MDS/1081030/2022 | 2022-05-25 | ST202205139080 | 2022-05-17 | P/FVC/MDS/1080968/2022 | 2022-05-25 |  |  |  |  | ST202205138089 | 2022-05-16 | P/FBW/MDS/1080879/2022 | 2022-05-25
1504 | UMPT25 | UMPT25 |  |  |  | ROTN | Indus | - | R/NN-649035 |  | SO | 2022-05-19 | UMPT25 | 4G_FD900_UMPT25 | 4G_FD2100_UMPT25 | 4G_TD_UMPT25 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148670 | 2022-05-28 | P/FVC/MDS/1081305/2022 | 2022-06-03 | ST202205147379 | 2022-05-27 | P/FVC/MDS/1081152/2022 | 2022-06-03 |  |  |  |  | ST202205147832 | 2022-05-27 | P/FBW/MDS/1081226/2022 | 2022-06-03
1505 | IDPD14 | IDPD14 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-05 | IDPD14 | 4G_FD900_IDPD14 | 4G_FD2100_IDPD14 | 4G_TD_IDPD14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210570535 | 2022-10-14 | P/FVC/MDS/1113237/2022 | 2022-10-20 | ST202210574033 | 2022-10-14 | P/FVC/MDS/1113305/2022 | 2022-10-20 |  |  |  |  | ST202210559751 | 2022-10-12 | P/FBW/MDS/1114042/2022 | 2022-10-30
1506 | KVPT36 | KVPT36 |  |  |  | ROTN | Summit | I-TN-KVLP-ENB-0032 | SR-TN000919 |  | On Air | 2022-05-09 | KVPT36 | 4G_FD900_KVPT36 | 4G_FD2100_KVPT36 | 4G_TD_KVPT36 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202109522074 | 2021-09-16 | P/FVC/MDS/1062412/2021 | 2021-09-23 | ST202109522202 | 2021-09-16 | P/FVC/MDS/1062460/2021 | 2021-09-23 | ST202109530291 | 2021-09-24 | P/FVC/MDS/1063051/2021 | 2021-10-01 | ST202109522257 | 2021-09-16 | P/FBW/MDS/1062508/2021 | 2021-09-23
1507 | DGL85 | DGL085 |  |  |  | ROTN | Indus | IN-3126737 | R/NN-649037 |  | On Air | 2022-05-05 | DGL085 | 4G_FD900_DGL085 | 4G_FD2100_DGL085 | 4G_TD_DGL085 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138442 | 2022-05-16 | P/FVC/MDS/1081014/2022 | 2022-05-25 | ST202205139016 | 2022-05-17 | P/FVC/MDS/1080952/2022 | 2022-05-25 |  |  |  |  | ST202205136591 | 2022-05-14 | P/FBW/MDS/1080863/2022 | 2022-05-25
1508 | PATU42 | PATU42 |  |  |  | ROTN | Ascend | TN/TA/AT/22687 | T21TN08790 |  | On Air | 2022-05-02 | PATU42 | 4G_FD900_PATU42 | 4G_FD2100_PATU42 | 4G_TD_PATU42 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124895 | 2022-05-02 | P/FVC/MDS/1079482/2022 | 2022-05-16 | ST202205124828 | 2022-05-02 | P/FVC/MDS/1079403/2022 | 2022-05-13 |  |  |  |  | ST202205124767 | 2022-05-02 | P/FBW/MDS/1079320/2022 | 2022-05-13
1509 | NANGAM | NANGAM |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-04-27 | NANGAM | 4G_FD900_NANGAM | 4G_FD2100_NANGAM | 4G_TD_NANGAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123696 | 2022-04-30 | P/FVC/MDS/1079472/2022 | 2022-05-16 | ST202205124574 | 2022-05-02 | P/FVC/MDS/1079393/2022 | 2022-05-13 |  |  |  |  | ST202204124002 | 2022-04-30 | P/FBW/MDS/1079309/2022 | 2022-05-13
1510 | TIR432 | TIR432 |  |  |  | ROTN | Indus |  | R/NN-657746 |  | On Air | 2022-05-17 | TIR432 | 4G_FD900_TIR432 | 4G_FD2100_TIR432 | 4G_TD_TIR432 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206210274 | 2022-06-30 | P/FVC/MDS/1087989/2022 | 2022-07-18 | ST202207225039 | 2022-07-06 | P/FVC/MDS/1087943/2022 | 2022-07-18 | ST202207228631 | 2022-07-07 | P/FVC/MDS/1087978/2022 | 2022-07-18 | ST202207224151 | 2022-07-06 | P/FBW/MDS/1087864/2022 | 2022-07-18
1511 | VILLK2 | VILLK2 |  |  |  | ROTN | Indus | IN-3126154 | R/NN-648268 |  | SO | 2022-04-28 | VILLK2 | 4G_FD900_VILLK2 | 4G_FD2100_VILLK2 | 4G_TD_VILLK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123583 | 2022-04-30 | P/FVC/MDS/1079457/2022 | 2022-05-16 | ST202205124542 | 2022-05-02 | P/FVC/MDS/1079378/2022 | 2022-05-13 |  |  |  |  | ST202204123966 | 2022-04-30 | P/FBW/MDS/1079294/2022 | 2022-05-13
1512 | MTPM28 | MTPM28 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-09 | MTPM28 | 4G_FD900_MTPM28 | 4G_FD2100_MTPM28 | 4G_TD_MTPM28 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138419 | 2022-05-16 | P/FVC/MDS/1080999/2022 | 2022-05-25 | ST202205138970 | 2022-05-17 | P/FVC/MDS/1080937/2022 | 2022-05-25 |  |  |  |  | ST202205136577 | 2022-05-14 | P/FBW/MDS/1080849/2022 | 2022-05-25
1513 | RNPT32 | RNPT32 |  |  |  | ROTN | Summit | I-TN-WLLJ-ENB-0022 | SR-TN000925 |  | On Air | 2022-04-29 | RNPT32 | 4G_FD900_RNPT32 | 4G_FD2100_RNPT32 | 4G_TD_RNPT32 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123512 | 2022-04-30 | P/FVC/MDS/1079447/2022 | 2022-05-16 | ST202205124513 | 2022-05-02 | P/FVC/MDS/1079368/2022 | 2022-05-13 |  |  |  |  | ST202204123861 | 2022-04-30 | P/FBW/MDS/1079284/2022 | 2022-05-13
1514 | RSMGM5 | RSMGM5 |  |  |  | ROTN | Indus | IN-3012385 | R/NN-626673 |  | On Air | 2022-04-28 | RSMGM5 | 4G_FD900_RSMGM5 | 4G_FD2100_RSMGM5 | 4G_TD_RSMGM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123564 | 2022-04-30 | P/FVC/MDS/1079455/2022 | 2022-05-16 | ST202205124540 | 2022-05-02 | P/FVC/MDS/1079376/2022 | 2022-05-13 |  |  |  |  | ST202204123891 | 2022-04-30 | P/FBW/MDS/1079292/2022 | 2022-05-13
1515 | VLKL13 | VLKL13 |  |  |  | ROTN | Indus |  | R/NN-657749 |  | On Air | 2022-05-17 | VLKL13 | 4G_FD900_VLKL13 | 4G_FD2100_VLKL13 | 4G_TD_VLKL13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148633 | 2022-05-28 | P/FVC/MDS/1081298/2022 | 2022-06-03 | ST202205147366 | 2022-05-27 | P/FVC/MDS/1081145/2022 | 2022-06-03 |  |  |  |  | ST202205147823 | 2022-05-27 | P/FBW/MDS/1081219/2022 | 2022-06-03
1516 | KUZH5 | KUZH05 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-04-27 | KUZH05 | 4G_FD900_KUZH05 | 4G_FD2100_KUZH05 | 4G_TD_KUZH05 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297660 | 2022-07-29 | P/FVC/MDS/1093401/2022 | 2022-08-09 | ST202207298935 | 2022-07-29 | P/FVC/MDS/1093312/2022 | 2022-08-09 |  |  |  |  | ST202207295368 | 2022-07-28 | P/FBW/MDS/1093195/2022 | 2022-08-09
1517 | TVKND4 | TVKND4 |  |  |  | ROTN | Indus | IN-3126156 | R/NN-648305 |  | On Air | 2022-04-28 | TVKND4 | 4G_FD900_TVKND4 | 4G_FD2100_TVKND4 | 4G_TD_TVKND4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123584 | 2022-04-30 | P/FVC/MDS/1079458/2022 | 2022-05-16 | ST202205124543 | 2022-05-02 | P/FVC/MDS/1079379/2022 | 2022-05-13 |  |  |  |  | ST202204123967 | 2022-04-30 | P/FBW/MDS/1079295/2022 | 2022-05-13
1518 | KCP133 | KCP133 |  |  |  | ROTN | Indus | IN-3127032 | R/NN-649426 |  | On Air | 2022-04-28 | KCP133 | 4G_FD900_KCP133 | 4G_FD2100_KCP133 | 4G_TD_KCP133 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123595 | 2022-04-30 | P/FVC/MDS/1079459/2022 | 2022-05-16 | ST202205124544 | 2022-05-02 | P/FVC/MDS/1079380/2022 | 2022-05-13 |  |  |  |  | ST202204123968 | 2022-04-30 | P/FBW/MDS/1079296/2022 | 2022-05-13
1519 | OOTY42 | OOTY42 |  |  |  | ROTN | Summit | I-TN-OTCM-ENB-0038 | SR-TN000917 |  | On Air | 2022-05-02 | OOTY42 | 4G_FD900_OOTY42 | 4G_FD2100_OOTY42 | 4G_TD_OOTY42 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124896 | 2022-05-02 | P/FVC/MDS/1079483/2022 | 2022-05-16 | ST202205124834 | 2022-05-02 | P/FVC/MDS/1079404/2022 | 2022-05-13 |  |  |  |  | ST202205124769 | 2022-05-02 | P/FBW/MDS/1079321/2022 | 2022-05-13
1520 | HICROP | HICROP |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-27 | HICROP | 4G_FD900_HICROP | 4G_FD2100_HICROP | 4G_TD_HICROP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123618 | 2022-04-30 | P/FVC/MDS/1079463/2022 | 2022-05-16 | ST202205124553 | 2022-05-02 | P/FVC/MDS/1079384/2022 | 2022-05-13 |  |  |  |  | ST202204123977 | 2022-04-30 | P/FBW/MDS/1079300/2022 | 2022-05-13
1521 | SOMAN2 | SOMAN2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-27 | SOMAN2 | 4G_FD900_SOMAN2 | 4G_FD2100_SOMAN2 | 4G_TD_SOMAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206156659 | 2022-06-02 | P/FVC/MDS/1082445/2022 | 2022-06-14 | ST202206156571 | 2022-06-02 | P/FVC/MDS/1082395/2022 | 2022-06-14 |  |  |  |  | ST202206156131 | 2022-06-02 | P/FBW/MDS/1082341/2022 | 2022-06-14
1522 | PNVAI8 | PNVAI8 |  |  |  | ROTN | Indus | - | R/NN-627497 |  | On Air | 2022-05-19 | PNVAI8 | 4G_FD900_PNVAI8 | 4G_FD2100_PNVAI8 | 4G_TD_PNVAI8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148649 | 2022-05-28 | P/FVC/MDS/1081302/2022 | 2022-06-03 | ST202205147375 | 2022-05-27 | P/FVC/MDS/1081149/2022 | 2022-06-03 |  |  |  |  | ST202205147827 | 2022-05-27 | P/FBW/MDS/1081223/2022 | 2022-06-03
1523 | NORAC1 | NORAC1 |  |  |  | ROTN | Indus |  | R/NN-656813 |  | On Air | 2022-05-19 | NORAC1 | 4G_FD900_NORAC1 | 4G_FD2100_NORAC1 | 4G_TD_NORAC1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148684 | 2022-05-28 | P/FVC/MDS/1081309/2022 | 2022-06-03 | ST202205147385 | 2022-05-27 | P/FVC/MDS/1081156/2022 | 2022-06-03 |  |  |  |  | ST202205147837 | 2022-05-27 | P/FBW/MDS/1081230/2022 | 2022-06-03
1524 | MARUDR | MARUDR |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-18 | MARUDR | 4G_FD900_MARUDR | 4G_FD2100_MARUDR | 4G_TD_MARUDR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110352 | 2022-04-19 | P/FVC/MDS/1078930/2022 | 2022-05-02 | ST202204109976 | 2022-04-19 | P/FVC/MDS/1078992/2022 | 2022-05-03 |  |  |  |  | ST202204109532 | 2022-04-19 | P/FVC/MDS/1078888/2022 | 2022-05-02
1525 | PERKAP | PERKAP |  |  |  | ROTN | Summit | I-TN-VDCM-ENB-9066 | SR-TN000922 |  | On Air | 2022-05-02 | PERKAP | 4G_FD900_PERKAP | 4G_FD2100_PERKAP | 4G_TD_PERKAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110573660 | 2021-10-27 | P/FVC/MDS/1065763/2021 | 2021-11-16 | ST202110574399 | 2021-10-28 | P/FVC/MDS/1065879/2021 | 2021-11-16 |  |  |  |  | ST202110573505 | 2021-10-27 | P/FBW/MDS/1067937/2021 | 2021-12-08
1526 | AUTHAI | AUTHAI |  |  |  | ROTN | Ascend | - | - |  | SR | 2022-04-18 | AUTHAI | 4G_FD900_AUTHAI | 4G_FD2100_AUTHAI | 4G_TD_AUTHAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110324 | 2022-04-19 | P/FVC/MDS/1078924/2022 | 2022-05-02 | ST202204119694 | 2022-04-26 | P/FVC/MDS/1079357/2022 | 2022-05-13 |  |  |  |  | ST202204109069 | 2022-04-19 | P/FVC/MDS/1078882/2022 | 2022-05-02
1527 | PAAVAI | PAAVAI |  |  |  | ROTN | Summit | I-TN-PNRT-ENB-9048 | SR-TN000923 |  | On Air | 2022-05-02 | PAAVAI | 4G_FD900_PAAVAI | 4G_FD2100_PAAVAI | 4G_TD_PAAVAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110574114 | 2021-10-28 | P/FVC/MDS/1065853/2021 | 2021-11-16 | ST202110573025 | 2021-10-27 | P/FVC/MDS/1065726/2021 | 2021-11-16 |  |  |  |  | ST202110572519 | 2021-10-27 | P/FBW/MDS/1067906/2021 | 2021-12-08
1528 | BOMMA2 | BOMMA2 |  |  |  | ROTN | Summit | I-TN-TCGD-ENB-9108 | SR-TN000932 |  | On Air | 2022-04-29 | BOMMA2 | 4G_FD900_BOMMA2 | 4G_FD2100_BOMMA2 | 4G_TD_BOMMA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123534 | 2022-04-30 | P/FVC/MDS/1079451/2022 | 2022-05-16 | ST202205124528 | 2022-05-02 | P/FVC/MDS/1079372/2022 | 2022-05-13 |  |  |  |  | ST202204123879 | 2022-04-30 | P/FBW/MDS/1079288/2022 | 2022-05-13
1529 | MUPAT3 | MUPAT3 |  |  |  | ROTN | Indus | IN-3124079 | R/NN-645865 |  |  | 2022-04-22 | MUPAT3 | 4G_FD900_MUPAT3 | 4G_FD2100_MUPAT3 | 4G_TD_MUPAT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123463 | 2022-04-30 | P/FVC/MDS/1079434/2022 | 2022-05-16 | ST202204119675 | 2022-04-26 | P/FVC/MDS/1079349/2022 | 2022-05-13 |  |  |  |  | ST202204119427 | 2022-04-26 | P/FBW/MDS/1079256/2022 | 2022-05-13
1530 | RANDH2 | RANDH2 |  |  |  | ROTN | Ascend | - | - |  | SO(Rural Hold) | 2022-04-27 | RANDH2 | 4G_FD900_RANDH2 | 4G_FD2100_RANDH2 | 4G_TD_RANDH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123675 | 2022-04-30 | P/FVC/MDS/1079471/2022 | 2022-05-16 | ST202205124568 | 2022-05-02 | P/FVC/MDS/1079392/2022 | 2022-05-13 |  |  |  |  | ST202204123996 | 2022-04-30 | P/FBW/MDS/1079308/2022 | 2022-05-13
1531 | DELTA1 | DELTA1 |  |  |  | ROTN | Airtel | - | - |  | On Air | 2022-05-27 | DELTA1 | 4G_FD900_DELTA1 | 4G_FD2100_DELTA1 | 4G_TD_DELTA1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487208 | 2022-09-27 | P/FVC/MDS/1101548/2022 | 2022-10-10 | ST202209497182 | 2022-09-29 | P/FVC/MDS/1101505/2022 | 2022-10-10 | ST202209487715 | 2022-09-28 | P/FVC/MDS/1101349/2022 | 2022-10-10 | ST202209489369 | 2022-09-28 | P/FBW/MDS/1101081/2022 | 2022-10-10
1532 | THNJM2 | THNJM2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-18 | THNJM2 | 4G_FD900_THNJM2 | 4G_FD2100_THNJM2 | 4G_TD_THNJM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110326 | 2022-04-19 | P/FVC/MDS/1078926/2022 | 2022-05-02 | ST202204109890 | 2022-04-19 | P/FVC/MDS/1078988/2022 | 2022-05-03 |  |  |  |  | ST202204109466 | 2022-04-19 | P/FVC/MDS/1078884/2022 | 2022-05-02
1533 | MAGLM2 | MAGLM2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-17 | MAGLM2 | 4G_FD900_MAGLM2 | 4G_FD2100_MAGLM2 | 4G_TD_MAGLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148331 | 2022-05-28 | P/FVC/MDS/1081266/2022 | 2022-06-03 | ST202205147235 | 2022-05-27 | P/FVC/MDS/1081113/2022 | 2022-06-03 |  |  |  |  | ST202205147775 | 2022-05-27 | P/FBW/MDS/1081187/2022 | 2022-06-03
1534 | TRY390 | TRY390 |  |  |  | ROTN | ATC |  |  |  | On Air | 2022-05-19 | TRY390 | 4G_FD900_TRY390 | 4G_FD2100_TRY390 | 4G_TD_TRY390 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202202053448 | 2022-02-23 | P/FVC/MDS/1076408/2022 | 2022-03-13 | ST202202055613 | 2022-02-26 | P/FVC/MDS/1075621/2022 | 2022-03-10 | ST202202056743 | 2022-02-27 | P/FVC/MDS/1075696/2022 | 2022-03-10 | ST202203064542 | 2022-03-07 | P/FBW/MDS/1076890/2022 | 2022-03-23
1535 | CIRMD2 | CIRMD2 |  |  |  | ROTN | Ascend | - | - |  | SO(Rural Hold) | 2022-04-18 | CIRMD2 | 4G_FD900_CIRMD2 | 4G_FD2100_CIRMD2 | 4G_TD_CIRMD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110325 | 2022-04-19 | P/FVC/MDS/1078925/2022 | 2022-05-02 | ST202204109889 | 2022-04-19 | P/FVC/MDS/1078987/2022 | 2022-05-03 |  |  |  |  | ST202204109465 | 2022-04-19 | P/FVC/MDS/1078883/2022 | 2022-05-02
1536 | TIVR40 | TIVR40 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-27 | TIVR40 | 4G_FD900_TIVR40 | 4G_FD2100_TIVR40 | 4G_TD_TIVR40 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206156642 | 2022-06-02 | P/FVC/MDS/1082438/2022 | 2022-06-14 | ST202206156440 | 2022-06-02 | P/FVC/MDS/1082388/2022 | 2022-06-14 |  |  |  |  | ST202206156098 | 2022-06-02 | P/FBW/MDS/1082334/2022 | 2022-06-14
1537 | PRICER | PRICER |  |  |  | ROTN | Airtel | - | - |  | Dropped | 2022-04-25 | PRICER | 4G_FD900_PRICER | 4G_FD2100_PRICER | 4G_TD_PRICER | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123425 | 2022-04-30 | P/FVC/MDS/1079421/2022 | 2022-05-16 | ST202204119650 | 2022-04-26 | P/FVC/MDS/1079336/2022 | 2022-05-13 |  |  |  |  | ST202204119400 | 2022-04-26 | P/FBW/MDS/1079244/2022 | 2022-05-13
1538 | RSMGM3 | RSMGM3 |  |  |  | ROTN | ATC | TN/RA/AT/23025 | T22TN01348 |  | On Air | 2022-04-22 | RSMGM3 | 4G_FD900_RSMGM3 | 4G_FD2100_RSMGM3 | 4G_TD_RSMGM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123446 | 2022-04-30 | P/FVC/MDS/1079428/2022 | 2022-05-16 | ST202204119659 | 2022-04-26 | P/FVC/MDS/1079343/2022 | 2022-05-13 |  |  |  |  | ST202204119412 | 2022-04-26 | P/FBW/MDS/1079251/2022 | 2022-05-13
1539 | VLR244 | VLR244 |  |  |  | ROTN | ATC | TN/VE/AT/23030 | T22TN00838 |  | On Air | 2022-04-22 | VLR244 | 4G_FD900_VLR244 | 4G_FD2100_VLR244 | 4G_TD_VLR244 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123438 | 2022-04-30 | P/FVC/MDS/1079425/2022 | 2022-05-16 | ST202204119655 | 2022-04-26 | P/FVC/MDS/1079340/2022 | 2022-05-13 |  |  |  |  | ST202204119407 | 2022-04-26 | P/FBW/MDS/1079248/2022 | 2022-05-13
1540 | TEKPT3 | TEKPT3 |  |  |  | ROTN | ATC | TN/CO/AT/23035 | T22TN00843 |  | SO | 2022-04-22 | TEKPT3 | 4G_FD900_TEKPT3 | 4G_FD2100_TEKPT3 | 4G_TD_TEKPT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123452 | 2022-04-30 | P/FVC/MDS/1079429/2022 | 2022-05-16 | ST202204119660 | 2022-04-26 | P/FVC/MDS/1079344/2022 | 2022-05-13 |  |  |  |  | ST202204119417 | 2022-04-26 | P/FBW/MDS/1079252/2022 | 2022-05-13
1541 | KEZHP4 | KEZHP4 |  |  |  | ROTN | Summit | I-TN-WLLJ-ENB-9064 | SR-TN000841 |  | On Air | 2022-04-22 | KEZHP4 | 4G_FD900_KEZHP4 | 4G_FD2100_KEZHP4 | 4G_TD_KEZHP4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123473 | 2022-04-30 | P/FVC/MDS/1079438/2022 | 2022-05-16 | ST202204119685 | 2022-04-26 | P/FVC/MDS/1079353/2022 | 2022-05-13 |  |  |  |  | ST202204119438 | 2022-04-26 | P/FBW/MDS/1079260/2022 | 2022-05-13
1542 | IRREN3 | IRREN3 |  |  |  | ROTN | ATC | TN/DI/AT/23038 | T22TN01008 |  | On Air | 2022-04-22 | IRREN3 | 4G_FD900_IRREN3 | 4G_FD2100_IRREN3 | 4G_TD_IRREN3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123444 | 2022-04-30 | P/FVC/MDS/1079426/2022 | 2022-05-16 | ST202204119657 | 2022-04-26 | P/FVC/MDS/1079341/2022 | 2022-05-13 |  |  |  |  | ST202204119410 | 2022-04-26 | P/FBW/MDS/1079249/2022 | 2022-05-13
1543 | NRNPM3 | NRNPM3 |  |  |  | ROTN | Indus | IN-3130617 | R/NN-654021 |  | On Air | 2022-04-22 | NRNPM3 | 4G_FD900_NRNPM3 | 4G_FD2100_NRNPM3 | 4G_TD_NRNPM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123472 | 2022-04-30 | P/FVC/MDS/1079437/2022 | 2022-05-16 | ST202204119684 | 2022-04-26 | P/FVC/MDS/1079352/2022 | 2022-05-13 |  |  |  |  | ST202204119437 | 2022-04-26 | P/FBW/MDS/1079259/2022 | 2022-05-13
1544 | PUDPM2 | PUDPM2 |  |  |  | ROTN | Indus |  | R/NN-657742 |  | On Air | 2022-05-17 | PUDPM2 | 4G_FD900_PUDPM2 | 4G_FD2100_PUDPM2 | 4G_TD_PUDPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148625 | 2022-05-28 | P/FVC/MDS/1081296/2022 | 2022-06-03 | ST202205147362 | 2022-05-27 | P/FVC/MDS/1081143/2022 | 2022-06-03 | ST202210548548 | 2022-10-11 | P/FVC/MDS/1113927/2022 | 2022-10-21 | ST202205147821 | 2022-05-27 | P/FBW/MDS/1081217/2022 | 2022-06-03
1545 | KATUP3 | KATUP3 |  |  |  | ROTN | Indus | IN-3130612 | R/NN-654018 |  | On Air | 2022-04-22 | KATUP3 | 4G_FD900_KATUP3 | 4G_FD2100_KATUP3 | 4G_TD_KATUP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123465 | 2022-04-30 | P/FVC/MDS/1079436/2022 | 2022-05-16 | ST202204119683 | 2022-04-26 | P/FVC/MDS/1079351/2022 | 2022-05-13 |  |  |  |  | ST202204119436 | 2022-04-26 | P/FBW/MDS/1079258/2022 | 2022-05-13
1546 | CBE913 | CBE913 |  |  |  | ROTN | Indus | IN-3125339 | R/NN-647360 |  | SO | 2022-04-28 | CBE913 | 4G_FD900_CBE913 | 4G_FD2100_CBE913 | 4G_TD_CBE913 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123596 | 2022-04-30 | P/FVC/MDS/1079460/2022 | 2022-05-16 | ST202205124546 | 2022-05-02 | P/FVC/MDS/1079381/2022 | 2022-05-13 |  |  |  |  | ST202204123969 | 2022-04-30 | P/FBW/MDS/1079297/2022 | 2022-05-13
1547 | PZAVI2 | PZAVI2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-27 | PZAVI2 | 4G_FD900_PZAVI2 | 4G_FD2100_PZAVI2 | 4G_TD_PZAVI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123673 | 2022-04-30 | P/FVC/MDS/1079469/2022 | 2022-05-16 | ST202205124566 | 2022-05-02 | P/FVC/MDS/1079390/2022 | 2022-05-13 |  |  |  |  | ST202204123994 | 2022-04-30 | P/FBW/MDS/1079306/2022 | 2022-05-13
1548 | KNKPL2 | KNKPL2 |  |  |  | ROTN | Indus | IN-3125405 | R/NN-647484 |  | SO(Rural Hold) | 2022-04-27 | KNKPL2 | 4G_FD900_KNKPL2 | 4G_FD2100_KNKPL2 | 4G_TD_KNKPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123722 | 2022-04-30 | P/FVC/MDS/1079478/2022 | 2022-05-16 | ST202205124589 | 2022-05-02 | P/FVC/MDS/1079399/2022 | 2022-05-13 |  |  |  |  | ST202204124018 | 2022-04-30 | P/FBW/MDS/1079315/2022 | 2022-05-13
1549 | KTALI9 | KTALI9 |  |  |  | ROTN | Indus |  | R/NN-647646 |  | On Air | 2022-05-19 | KTALI9 | 4G_FD900_KTALI9 | 4G_FD2100_KTALI9 | 4G_TD_KTALI9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148650 | 2022-05-28 | P/FVC/MDS/1081303/2022 | 2022-06-03 | ST202205147376 | 2022-05-27 | P/FVC/MDS/1081150/2022 | 2022-06-03 |  |  |  |  | ST202205147828 | 2022-05-27 | P/FBW/MDS/1081224/2022 | 2022-06-03
1550 | MTUPT2 | MTUPT2 |  |  |  | ROTN | Indus | IN-3125459 | R/NN-647647 |  |  | 2022-04-22 | MTUPT2 | 4G_FD900_MTUPT2 | 4G_FD2100_MTUPT2 | 4G_TD_MTUPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123464 | 2022-04-30 | P/FVC/MDS/1079435/2022 | 2022-05-16 | ST202204119676 | 2022-04-26 | P/FVC/MDS/1079350/2022 | 2022-05-13 |  |  |  |  | ST202204119428 | 2022-04-26 | P/FBW/MDS/1079257/2022 | 2022-05-13
1551 | KDAKM9 | KDAKM9 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-27 | KDAKM9 | 4G_FD900_KDAKM9 | 4G_FD2100_KDAKM9 | 4G_TD_KDAKM9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123619 | 2022-04-30 | P/FVC/MDS/1079464/2022 | 2022-05-16 | ST202205124554 | 2022-05-02 | P/FVC/MDS/1079385/2022 | 2022-05-13 |  |  |  |  | ST202204123978 | 2022-04-30 | P/FBW/MDS/1079301/2022 | 2022-05-13
1552 | CDLR97 | CDLR97 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-04-29 | CDLR97 | 4G_FD900_CDLR97 | 4G_FD2100_CDLR97 | 4G_TD_CDLR97 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123500 | 2022-04-30 | P/FVC/MDS/1079445/2022 | 2022-05-16 | ST202205124511 | 2022-05-02 | P/FVC/MDS/1079366/2022 | 2022-05-13 |  |  |  |  | ST202204123859 | 2022-04-30 | P/FBW/MDS/1079282/2022 | 2022-05-13
1553 | VADAG2 | VADAG2 |  |  |  | ROTN | Ascend | - |  |  | SO | 2022-05-10 | VADAG2 | 4G_FD900_VADAG2 | 4G_FD2100_VADAG2 | 4G_TD_VADAG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138398 | 2022-05-16 | P/FVC/MDS/1080987/2022 | 2022-05-25 | ST202205138933 | 2022-05-17 | P/FVC/MDS/1080925/2022 | 2022-05-25 |  |  |  |  | ST202205136564 | 2022-05-14 | P/FBW/MDS/1080837/2022 | 2022-05-25
1554 | MMBTU2 | MMBTU2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-04-18 | MMBTU2 | 4G_FD900_MMBTU2 | 4G_FD2100_MMBTU2 | 4G_TD_MMBTU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110340 | 2022-04-19 | P/FVC/MDS/1078928/2022 | 2022-05-02 | ST202204109973 | 2022-04-19 | P/FVC/MDS/1078990/2022 | 2022-05-03 |  |  |  |  | ST202204109504 | 2022-04-19 | P/FVC/MDS/1078886/2022 | 2022-05-02
1555 | TRMIK2 | TRMIK2 |  |  |  | ROTN | Ascend | - | - |  | SO(Rural Hold) | 2022-04-18 | TRMIK2 | 4G_FD900_TRMIK2 | 4G_FD2100_TRMIK2 | 4G_TD_TRMIK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110312 | 2022-04-19 | P/FVC/MDS/1078922/2022 | 2022-05-02 | ST202204109870 | 2022-04-19 | P/FVC/MDS/1078984/2022 | 2022-05-03 |  |  |  |  | ST202204119453 | 2022-04-26 | P/FBW/MDS/1079265/2022 | 2022-05-13
1556 | TLYTH2 | TLYTH2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-18 | TLYTH2 | 4G_FD900_TLYTH2 | 4G_FD2100_TLYTH2 | 4G_TD_TLYTH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110341 | 2022-04-19 | P/FVC/MDS/1078929/2022 | 2022-05-02 | ST202204109975 | 2022-04-19 | P/FVC/MDS/1078991/2022 | 2022-05-03 |  |  |  |  | ST202204109531 | 2022-04-19 | P/FVC/MDS/1078887/2022 | 2022-05-02
1557 | PAPPN2 | PAPPN2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-04-18 | PAPPN2 | 4G_FD900_PAPPN2 | 4G_FD2100_PAPPN2 | 4G_TD_PAPPN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110339 | 2022-04-19 | P/FVC/MDS/1078927/2022 | 2022-05-02 | ST202204109891 | 2022-04-19 | P/FVC/MDS/1078989/2022 | 2022-05-03 |  |  |  |  | ST202204109502 | 2022-04-19 | P/FVC/MDS/1078885/2022 | 2022-05-02
1558 | DGL117 | DGL117 |  |  |  | ROTN | ATC | TN/DI/AT/23056 | T22TN00892 |  | On Air | 2022-04-22 | DGL117 | 4G_FD900_DGL117 | 4G_FD2100_DGL117 | 4G_TD_DGL117 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123445 | 2022-04-30 | P/FVC/MDS/1079427/2022 | 2022-05-16 | ST202204119658 | 2022-04-26 | P/FVC/MDS/1079342/2022 | 2022-05-13 |  |  |  |  | ST202204119411 | 2022-04-26 | P/FBW/MDS/1079250/2022 | 2022-05-13
1559 | PILIP3 | PILIP3 |  |  |  | ROTN | Indus | IN-3125616 | R/NN-647774 |  | On Air | 2022-04-28 | PILIP3 | 4G_FD900_PILIP3 | 4G_FD2100_PILIP3 | 4G_TD_PILIP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123597 | 2022-04-30 | P/FVC/MDS/1079461/2022 | 2022-05-16 | ST202205124547 | 2022-05-02 | P/FVC/MDS/1079382/2022 | 2022-05-13 |  |  |  |  | ST202204123970 | 2022-04-30 | P/FBW/MDS/1079298/2022 | 2022-05-13
1560 | NGL112 | NGL112 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-02 | NGL112 | 4G_FD900_NGL112 | 4G_FD2100_NGL112 | 4G_TD_NGL112 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124888 | 2022-05-02 | P/FVC/MDS/1079480/2022 | 2022-05-16 | ST202205124826 | 2022-05-02 | P/FVC/MDS/1079401/2022 | 2022-05-13 |  |  |  |  | ST202205124762 | 2022-05-02 | P/FBW/MDS/1079318/2022 | 2022-05-13
1561 | GNPPL1 | GNPPL1 |  |  |  | ROTN | Indus | - | R/NN-649031 |  | On Air | 2022-04-13 | GNPPL1 | 4G_FD900_GNPPL1 | 4G_FD2100_GNPPL1 | 4G_TD_GNPPL1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111722 | 2022-04-20 | P/FVC/MDS/1078949/2022 | 2022-05-02 | ST202204110105 | 2022-04-19 | P/FVC/MDS/1079011/2022 | 2022-05-03 |  |  |  |  | ST202204109704 | 2022-04-19 | P/FVC/MDS/1078907/2022 | 2022-05-02
1562 | PJPT09 | PJPT09 |  |  |  | ROTN | Indus | - | R/NN-649034 |  | On Air | 2022-04-13 | PJPT09 | 4G_FD900_PJPT09 | 4G_FD2100_PJPT09 | 4G_TD_PJPT09 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204111710 | 2022-04-20 | P/FVC/MDS/1078945/2022 | 2022-05-02 | ST202204110072 | 2022-04-19 | P/FVC/MDS/1079007/2022 | 2022-05-03 |  |  |  |  | ST202204109658 | 2022-04-19 | P/FVC/MDS/1078903/2022 | 2022-05-02
1563 | RMTCN1 | RMTCN1 |  |  |  | ROTN | Indus | IN-3127035 | R/NN-649434 |  | On Air | 2022-04-18 | RMTCN1 | 4G_FD900_RMTCN1 | 4G_FD2100_RMTCN1 | 4G_TD_RMTCN1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110311 | 2022-04-19 | P/FVC/MDS/1078921/2022 | 2022-05-02 | ST202204109855 | 2022-04-19 | P/FVC/MDS/1078983/2022 | 2022-05-03 |  |  |  |  | ST202204119448 | 2022-04-26 | P/FBW/MDS/1079264/2022 | 2022-05-13
1564 | SENGPR | SENGPR |  |  |  | ROTN | Summit | SR-TN000924 | SR-TN000924 |  | On Air | 2022-04-22 | SENGPR | 4G_FD900_SENGPR | 4G_FD2100_SENGPR | 4G_TD_SENGPR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123487 | 2022-04-30 | P/FVC/MDS/1079441/2022 | 2022-05-16 | ST202204119693 | 2022-04-26 | P/FVC/MDS/1079356/2022 | 2022-05-13 |  |  |  |  | ST202204119447 | 2022-04-26 | P/FBW/MDS/1079263/2022 | 2022-05-13
1565 | TATAEP | TATAEP |  |  |  | ROTN | Airtel | - | - |  | On Air | 2022-05-27 | TATAEP | 4G_FD900_TATAEP | 4G_FD2100_TATAEP | 4G_TD_TATAEP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206156638 | 2022-06-02 | P/FVC/MDS/1082436/2022 | 2022-06-14 | ST202206156431 | 2022-06-02 | P/FVC/MDS/1082386/2022 | 2022-06-14 |  |  |  |  | ST202206156096 | 2022-06-02 | P/FBW/MDS/1082332/2022 | 2022-06-14
1566 | VLR237 | VLR237 |  |  |  | ROTN | ATC | TN/VE/AT/23112 | T22TN01294 |  | On Air | 2022-05-17 | VLR237 | 4G_FD900_VLR237 | 4G_FD2100_VLR237 | 4G_TD_VLR237 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148383 | 2022-05-28 | P/FVC/MDS/1081280/2022 | 2022-06-03 | ST202205147333 | 2022-05-27 | P/FVC/MDS/1081127/2022 | 2022-06-03 |  |  |  |  | ST202205147799 | 2022-05-27 | P/FBW/MDS/1081201/2022 | 2022-06-03
1567 | VLR240 | VLR240 |  |  |  | ROTN | Indus | - | R/NN-653773 |  | On Air | 2022-05-05 | VLR240 | 4G_FD900_VLR240 | 4G_FD2100_VLR240 | 4G_TD_VLR240 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138448 | 2022-05-16 | P/FVC/MDS/1081019/2022 | 2022-05-25 | ST202205139037 | 2022-05-17 | P/FVC/MDS/1080957/2022 | 2022-05-25 |  |  |  |  | ST202205136596 | 2022-05-14 | P/FBW/MDS/1080868/2022 | 2022-05-25
1568 | VLR242 | VLR242 |  |  |  | ROTN | Indus | - | R/NN-653778 |  | SRB(Surrender) | 2022-05-19 | VLR242 | 4G_FD900_VLR242 | 4G_FD2100_VLR242 | 4G_TD_VLR242 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148669 | 2022-05-28 | P/FVC/MDS/1081304/2022 | 2022-06-03 | ST202205147378 | 2022-05-27 | P/FVC/MDS/1081151/2022 | 2022-06-03 |  |  |  |  | ST202205147831 | 2022-05-27 | P/FBW/MDS/1081225/2022 | 2022-06-03
1569 | PKGD18 | PKGD18 |  |  |  | ROTN | ATC | TN/TR/AT/23115 | T22TN01297 |  | On Air | 2022-05-17 | PKGD18 | 4G_FD900_PKGD18 | 4G_FD2100_PKGD18 | 4G_TD_PKGD18 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148607 | 2022-05-28 | P/FVC/MDS/1081294/2022 | 2022-06-03 | ST202205147356 | 2022-05-27 | P/FVC/MDS/1081141/2022 | 2022-06-03 |  |  |  |  | ST202205147819 | 2022-05-27 | P/FBW/MDS/1081215/2022 | 2022-06-03
1570 | AGST10 | AGST10 |  |  |  | ROTN | Summit | I-TN-NGCL-ENB-0012 | SR-TN000929 |  | On Air | 2022-05-02 | AGST10 | 4G_FD900_AGST10 | 4G_FD2100_AGST10 | 4G_TD_AGST10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124909 | 2022-05-02 | P/FVC/MDS/1079490/2022 | 2022-05-16 | ST202205124846 | 2022-05-02 | P/FVC/MDS/1079411/2022 | 2022-05-13 |  |  |  |  | ST202205124795 | 2022-05-02 | P/FBW/MDS/1079328/2022 | 2022-05-13
1571 | KRUMB2 | KRUMB2 |  |  |  | ROTN | Summit | I-TN-KZPV-ENB-9004 | SR-TN000930 |  | On Air | 2022-04-29 | KRUMB2 | 4G_FD900_KRUMB2 | 4G_FD2100_KRUMB2 | 4G_TD_KRUMB2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123514 | 2022-04-30 | P/FVC/MDS/1079448/2022 | 2022-05-16 | ST202205124518 | 2022-05-02 | P/FVC/MDS/1079369/2022 | 2022-05-13 |  |  |  |  | ST202204123870 | 2022-04-30 | P/FBW/MDS/1079285/2022 | 2022-05-13
1572 | CBE936 | CBE936 |  |  |  | ROTN | ATC | TN/CO/AT/23117 | T22TN01299 |  | On Air | 2022-05-05 | CBE936 | 4G_FD900_CBE936 | 4G_FD2100_CBE936 | 4G_TD_CBE936 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138464 | 2022-05-16 | P/FVC/MDS/1081031/2022 | 2022-05-25 | ST202205139081 | 2022-05-17 | P/FVC/MDS/1080969/2022 | 2022-05-25 |  |  |  |  | ST202205138090 | 2022-05-16 | P/FBW/MDS/1080880/2022 | 2022-05-25
1573 | PDTUP2 | PDTUP2 |  |  |  | ROTN | ATC | TN/TU/AT/23118 | T22TN01300 |  | On Air | 2022-05-09 | PDTUP2 | 4G_FD900_PDTUP2 | 4G_FD2100_PDTUP2 | 4G_TD_PDTUP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138423 | 2022-05-16 | P/FVC/MDS/1081003/2022 | 2022-05-25 | ST202205138983 | 2022-05-17 | P/FVC/MDS/1080941/2022 | 2022-05-25 |  |  |  |  | ST202205136580 | 2022-05-14 | P/FBW/MDS/1080852/2022 | 2022-05-25
1574 | KOMPT2 | KOMPT2 |  |  |  | ROTN | ATC | TN/VI/AT/23119 | T22TN01301 |  | On Air | 2022-04-22 | KOMPT2 | 4G_FD900_KOMPT2 | 4G_FD2100_KOMPT2 | 4G_TD_KOMPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123454 | 2022-04-30 | P/FVC/MDS/1079431/2022 | 2022-05-16 | ST202204119662 | 2022-04-26 | P/FVC/MDS/1079346/2022 | 2022-05-13 |  |  |  |  | ST202205130123 | 2022-05-07 | P/FBW/MDS/1079895/2022 | 2022-05-20
1575 | PKLM15 | PKLM15 |  |  |  | ROTN | ATC | TN/TH/AT/23120 | T22TN01302 |  | On Air | 2022-05-09 | PKLM15 | 4G_FD900_PKLM15 | 4G_FD2100_PKLM15 | 4G_TD_PKLM15 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138431 | 2022-05-16 | P/FVC/MDS/1081009/2022 | 2022-05-25 | ST202205139003 | 2022-05-17 | P/FVC/MDS/1080947/2022 | 2022-05-25 |  |  |  |  | ST202205136586 | 2022-05-14 | P/FBW/MDS/1080858/2022 | 2022-05-25
1576 | TIR501 | TIR501 |  |  |  | ROTN | Indus | - | R/NN-653791 |  | On Air | 2022-05-17 | TIR501 | 4G_FD900_TIR501 | 4G_FD2100_TIR501 | 4G_TD_TIR501 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148423 | 2022-05-28 | P/FVC/MDS/1081283/2022 | 2022-06-03 | ST202205147338 | 2022-05-27 | P/FVC/MDS/1081130/2022 | 2022-06-03 |  |  |  |  | ST202205147804 | 2022-05-27 | P/FBW/MDS/1081204/2022 | 2022-06-03
1577 | CNKLP2 | CNKLP2 |  |  |  | ROTN | ATC | TN/TI/AT/23121 | T22TN01303 |  | On Air | 2022-04-22 | CNKLP2 | 4G_FD900_CNKLP2 | 4G_FD2100_CNKLP2 | 4G_TD_CNKLP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123457 | 2022-04-30 | P/FVC/MDS/1079432/2022 | 2022-05-16 | ST202204119663 | 2022-04-26 | P/FVC/MDS/1079347/2022 | 2022-05-13 |  |  |  |  | ST202204119419 | 2022-04-26 | P/FBW/MDS/1079254/2022 | 2022-05-13
1578 | TIR502 | TIR502 |  |  |  | ROTN | Summit | I-TN-TPPR-ENB-9087 | SR-TN000931 |  | On Air | 2022-05-02 | TIR502 | 4G_FD900_TIR502 | 4G_FD2100_TIR502 | 4G_TD_TIR502 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124908 | 2022-05-02 | P/FVC/MDS/1079489/2022 | 2022-05-16 | ST202205124845 | 2022-05-02 | P/FVC/MDS/1079410/2022 | 2022-05-13 |  |  |  |  | ST202205124786 | 2022-05-02 | P/FBW/MDS/1079327/2022 | 2022-05-13
1579 | CBE933 | CBE933 |  |  |  | ROTN | Indus | - | R/NN-653832 |  | On Air | 2022-05-05 | CBE933 | 4G_FD900_CBE933 | 4G_FD2100_CBE933 | 4G_TD_CBE933 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138449 | 2022-05-16 | P/FVC/MDS/1081020/2022 | 2022-05-25 | ST202205139038 | 2022-05-17 | P/FVC/MDS/1080958/2022 | 2022-05-25 |  |  |  |  | ST202205136598 | 2022-05-14 | P/FBW/MDS/1080869/2022 | 2022-05-25
1580 | CBE934 | CBE934 |  |  |  | ROTN | ATC | TN/CO/AT/23125 | T22TN01307 |  | SO | 2022-04-29 | CBE934 | 4G_FD900_CBE934 | 4G_FD2100_CBE934 | 4G_TD_CBE934 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123546 | 2022-04-30 | P/FVC/MDS/1079453/2022 | 2022-05-16 | ST202205124535 | 2022-05-02 | P/FVC/MDS/1079374/2022 | 2022-05-13 |  |  |  |  | ST202204123889 | 2022-04-30 | P/FBW/MDS/1079290/2022 | 2022-05-13
1581 | SKMNG2 | SKMNG2 |  |  |  | ROTN | ATC | TN/MU/AT/23126 | T22TN01308 |  | SRB(Surrender) | 2022-05-09 | SKMNG2 | 4G_FD900_SKMNG2 | 4G_FD2100_SKMNG2 | 4G_TD_SKMNG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138420 | 2022-05-16 | P/FVC/MDS/1081000/2022 | 2022-05-25 | ST202205138971 | 2022-05-17 | P/FVC/MDS/1080938/2022 | 2022-05-25 |  |  |  |  | ST202205138173 | 2022-05-16 | P/FBW/MDS/1080903/2022 | 2022-05-25
1582 | KRSRI2 | KRSRI2 |  |  |  | ROTN | ATC | TN/MU/AT/23127 | T22TN01309 |  | On Air | 2022-05-09 | KRSRI2 | 4G_FD900_KRSRI2 | 4G_FD2100_KRSRI2 | 4G_TD_KRSRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138424 | 2022-05-16 | P/FVC/MDS/1081004/2022 | 2022-05-25 | ST202205138984 | 2022-05-17 | P/FVC/MDS/1080942/2022 | 2022-05-25 |  |  |  |  | ST202205136581 | 2022-05-14 | P/FBW/MDS/1080853/2022 | 2022-05-25
1583 | PLCH45 | PLCH45 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-05-10 | PLCH45 | 4G_FD900_PLCH45 | 4G_FD2100_PLCH45 | 4G_TD_PLCH45 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138362 | 2022-05-16 | P/FVC/MDS/1080974/2022 | 2022-05-25 | ST202205138627 | 2022-05-17 | P/FVC/MDS/1080911/2022 | 2022-05-25 |  |  |  |  | ST202205136548 | 2022-05-14 | P/FBW/MDS/1080824/2022 | 2022-05-25
1584 | MDU531 | MDU531 |  |  |  | ROTN | Indus | IN-3130542 | R/NN-654441 |  | On Air | 2022-05-27 | MDU531 | 4G_FD900_MDU531 | 4G_FD2100_MDU531 | 4G_TD_MDU531 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206156651 | 2022-06-02 | P/FVC/MDS/1082441/2022 | 2022-06-14 | ST202206156563 | 2022-06-02 | P/FVC/MDS/1082391/2022 | 2022-06-14 |  |  |  |  | ST202206156109 | 2022-06-02 | P/FBW/MDS/1082337/2022 | 2022-06-14
1585 | TIR495 | TIR495 |  |  |  | ROTN | ATC | TN/TI/AT/23137 | T22TN01389 |  | On Air | 2022-04-29 | TIR495 | 4G_FD900_TIR495 | 4G_FD2100_TIR495 | 4G_TD_TIR495 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123563 | 2022-04-30 | P/FVC/MDS/1079454/2022 | 2022-05-16 | ST202205124536 | 2022-05-02 | P/FVC/MDS/1079375/2022 | 2022-05-13 |  |  |  |  | ST202204123890 | 2022-04-30 | P/FBW/MDS/1079291/2022 | 2022-05-13
1586 | PLCH54 | PLCH54 |  |  |  | ROTN | ATC | TN/CO/AT/23138 | T22TN01390 |  | On Air | 2022-05-09 | PLCH54 | 4G_FD900_PLCH54 | 4G_FD2100_PLCH54 | 4G_TD_PLCH54 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138425 | 2022-05-16 | P/FVC/MDS/1081005/2022 | 2022-05-25 | ST202205138988 | 2022-05-17 | P/FVC/MDS/1080943/2022 | 2022-05-25 |  |  |  |  | ST202205136582 | 2022-05-14 | P/FBW/MDS/1080854/2022 | 2022-05-25
1587 | ERD244 | ERD244 |  |  |  | ROTN | ATC | TN/ER/AT/23139 | T22TN01391 |  | On Air | 2022-05-17 | ERD244 | 4G_FD900_ERD244 | 4G_FD2100_ERD244 | 4G_TD_ERD244 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148606 | 2022-05-28 | P/FVC/MDS/1081293/2022 | 2022-06-03 | ST202205147355 | 2022-05-27 | P/FVC/MDS/1081140/2022 | 2022-06-03 |  |  |  |  | ST202205147818 | 2022-05-27 | P/FBW/MDS/1081214/2022 | 2022-06-03
1588 | PLKRI2 | PLKRI2 |  |  |  | ROTN | Summit | SR-TN000876 | SR-TN000876 |  | On Air | 2022-04-22 | PLKRI2 | 4G_FD900_PLKRI2 | 4G_FD2100_PLKRI2 | 4G_TD_PLKRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123481 | 2022-04-30 | P/FVC/MDS/1079439/2022 | 2022-05-16 | ST202204119686 | 2022-04-26 | P/FVC/MDS/1079354/2022 | 2022-05-13 |  |  |  |  | ST202204119445 | 2022-04-26 | P/FBW/MDS/1079261/2022 | 2022-05-13
1589 | SINGD2 | SINGD2 |  |  |  | ROTN | ATC | TN/DI/AT/23142 | T22TN01394 |  | On Air | 2022-05-09 | SINGD2 | 4G_FD900_SINGD2 | 4G_FD2100_SINGD2 | 4G_TD_SINGD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138426 | 2022-05-16 | P/FVC/MDS/1081006/2022 | 2022-05-25 | ST202205138989 | 2022-05-17 | P/FVC/MDS/1080944/2022 | 2022-05-25 |  |  |  |  | ST202205136583 | 2022-05-14 | P/FBW/MDS/1080855/2022 | 2022-05-25
1590 | JVLSG2 | JVLSG2 |  |  |  | ROTN | ATC | TN/DI/AT/23143 | T22TN01395 |  | On Air | 2022-04-27 | JVLSG2 | 4G_FD900_JVLSG2 | 4G_FD2100_JVLSG2 | 4G_TD_JVLSG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123711 | 2022-04-30 | P/FVC/MDS/1079476/2022 | 2022-05-16 | ST202205124583 | 2022-05-02 | P/FVC/MDS/1079397/2022 | 2022-05-13 |  |  |  |  | ST202204124011 | 2022-04-30 | P/FBW/MDS/1079313/2022 | 2022-05-13
1591 | DGL118 | DGL118 |  |  |  | ROTN | ATC | TN/DI/AT/23144 | T22TN01396 |  | On Air | 2022-04-29 | DGL118 | 4G_FD900_DGL118 | 4G_FD2100_DGL118 | 4G_TD_DGL118 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123545 | 2022-04-30 | P/FVC/MDS/1079452/2022 | 2022-05-16 | ST202205124534 | 2022-05-02 | P/FVC/MDS/1079373/2022 | 2022-05-13 |  |  |  |  | ST202204123880 | 2022-04-30 | P/FBW/MDS/1079289/2022 | 2022-05-13
1592 | DGL120 | DGL120 |  |  |  | ROTN | ATC | TN/DI/AT/23146 | T22TN01398 |  | On Air | 2022-05-17 | DGL120 | 4G_FD900_DGL120 | 4G_FD2100_DGL120 | 4G_TD_DGL120 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148370 | 2022-05-28 | P/FVC/MDS/1081278/2022 | 2022-06-03 | ST202205147329 | 2022-05-27 | P/FVC/MDS/1081125/2022 | 2022-06-03 |  |  |  |  | ST202205147796 | 2022-05-27 | P/FBW/MDS/1081199/2022 | 2022-06-03
1593 | VDSNR9 | VDSNR9 |  |  |  | ROTN | ATC | TN/DI/AT/23147 | T22TN01399 |  | On Air | 2022-04-27 | VDSNR9 | 4G_FD900_VDSNR9 | 4G_FD2100_VDSNR9 | 4G_TD_VDSNR9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123698 | 2022-04-30 | P/FVC/MDS/1079474/2022 | 2022-05-16 | ST202205124576 | 2022-05-02 | P/FVC/MDS/1079395/2022 | 2022-05-13 |  |  |  |  | ST202204124004 | 2022-04-30 | P/FBW/MDS/1079311/2022 | 2022-05-13
1594 | PETPL2 | PETPL2 |  |  |  | ROTN | ATC | TN/NM/AT/23148 | T22TN01400 |  | On Air | 2022-04-27 | PETPL2 | 4G_FD900_PETPL2 | 4G_FD2100_PETPL2 | 4G_TD_PETPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123697 | 2022-04-30 | P/FVC/MDS/1079473/2022 | 2022-05-16 | ST202205124575 | 2022-05-02 | P/FVC/MDS/1079394/2022 | 2022-05-13 |  |  |  |  | ST202204124003 | 2022-04-30 | P/FBW/MDS/1079310/2022 | 2022-05-13
1595 | TRTMP2 | TRTMP2 |  |  |  | ROTN | ATC | TN/NM/AT/23149 | T22TN01401 |  | On Air | 2022-04-27 | TRTMP2 | 4G_FD900_TRTMP2 | 4G_FD2100_TRTMP2 | 4G_TD_TRTMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123710 | 2022-04-30 | P/FVC/MDS/1079475/2022 | 2022-05-16 | ST202205124582 | 2022-05-02 | P/FVC/MDS/1079396/2022 | 2022-05-13 |  |  |  |  | ST202204124010 | 2022-04-30 | P/FBW/MDS/1079312/2022 | 2022-05-13
1596 | NALIP2 | NALIP2 |  |  |  | ROTN | ATC | TN/NM/AT/23151 | T22TN01403 |  | SO(Rural Hold) | 2022-05-09 | NALIP2 | 4G_FD900_NALIP2 | 4G_FD2100_NALIP2 | 4G_TD_NALIP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138429 | 2022-05-16 | P/FVC/MDS/1081007/2022 | 2022-05-25 | ST202205138990 | 2022-05-17 | P/FVC/MDS/1080945/2022 | 2022-05-25 |  |  |  |  | ST202205136584 | 2022-05-14 | P/FBW/MDS/1080856/2022 | 2022-05-25
1597 | SIVGR2 | SIVGR2 |  |  |  | ROTN | ATC | TN/ER/AT/23152 | T22TN01404 |  | On Air | 2022-05-17 | SIVGR2 | 4G_FD900_SIVGR2 | 4G_FD2100_SIVGR2 | 4G_TD_SIVGR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148549 | 2022-05-28 | P/FVC/MDS/1081290/2022 | 2022-06-03 | ST202205147350 | 2022-05-27 | P/FVC/MDS/1081137/2022 | 2022-06-03 |  |  |  |  | ST202205147814 | 2022-05-27 | P/FBW/MDS/1081211/2022 | 2022-06-03
1598 | MYVAD2 | MYVAD2 |  |  |  | ROTN | ATC | TN/TI/AT/23153 | T22TN01405 |  | On Air | 2022-05-17 | MYVAD2 | 4G_FD900_MYVAD2 | 4G_FD2100_MYVAD2 | 4G_TD_MYVAD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148382 | 2022-05-28 | P/FVC/MDS/1081279/2022 | 2022-06-03 | ST202205147330 | 2022-05-27 | P/FVC/MDS/1081126/2022 | 2022-06-03 |  |  |  |  | ST202205147797 | 2022-05-27 | P/FBW/MDS/1081200/2022 | 2022-06-03
1599 | SVIPT1 | SVIPT1 |  |  |  | ROTN | Indus | - | R/NN-654833 |  | On Air | 2022-05-17 | SVIPT1 | 4G_FD900_SVIPT1 | 4G_FD2100_SVIPT1 | 4G_TD_SVIPT1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148466 | 2022-05-28 | P/FVC/MDS/1081287/2022 | 2022-06-03 | ST202205147346 | 2022-05-27 | P/FVC/MDS/1081134/2022 | 2022-06-03 |  |  |  |  | ST202205147809 | 2022-05-27 | P/FBW/MDS/1081208/2022 | 2022-06-03
1600 | SMPDU2 | SMPDU2 |  |  |  | ROTN | Indus | IN-1129797 | R/RES-510235 |  | On Air | 2022-04-22 | SMPDU2 | 4G_FD900_SMPDU2 | 4G_FD2100_SMPDU2 | 4G_TD_SMPDU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203086096 | 2022-03-30 | P/FVC/MDS/1078193/2022 | 2022-04-15 | ST202203085241 | 2022-03-29 | P/FVC/MDS/1078146/2022 | 2022-04-15 |  |  |  |  | ST202203085825 | 2022-03-30 | P/FBW/MDS/1077901/2022 | 2022-04-14
1601 | PLNKT2 | PLNKT2 |  |  |  | ROTN | TVI | BSTNTNL1207 | - |  | On Air | 2022-04-22 | PLNKT2 | 4G_FD900_PLNKT2 | 4G_FD2100_PLNKT2 | 4G_TD_PLNKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203086119 | 2022-03-30 | P/FVC/MDS/1078207/2022 | 2022-04-15 | ST202203085378 | 2022-03-29 | P/FVC/MDS/1078160/2022 | 2022-04-15 |  |  |  |  | ST202203085839 | 2022-03-30 | P/FBW/MDS/1077915/2022 | 2022-04-14
1602 | TNMPT2 | TNMPT2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-27 | TNMPT2 | 4G_FD900_TNMPT2 | 4G_FD2100_TNMPT2 | 4G_TD_TNMPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123674 | 2022-04-30 | P/FVC/MDS/1079470/2022 | 2022-05-16 | ST202205124567 | 2022-05-02 | P/FVC/MDS/1079391/2022 | 2022-05-13 |  |  |  |  | ST202204123995 | 2022-04-30 | P/FBW/MDS/1079307/2022 | 2022-05-13
1603 | NDIGL2 | NDIGL2 |  |  |  | ROTN | Indus | - | R/NN-654442 |  | On Air | 2022-05-05 | NDIGL2 | 4G_FD900_NDIGL2 | 4G_FD2100_NDIGL2 | 4G_TD_NDIGL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138450 | 2022-05-16 | P/FVC/MDS/1081021/2022 | 2022-05-25 | ST202205139039 | 2022-05-17 | P/FVC/MDS/1080959/2022 | 2022-05-25 |  |  |  |  | ST202205136599 | 2022-05-14 | P/FBW/MDS/1080870/2022 | 2022-05-25
1604 | KRR106 | KRR106 |  |  |  | ROTN | ATC | TN/KU/AT/23155 | T22TN01407 |  | On Air | 2022-05-09 | KRR106 | 4G_FD900_KRR106 | 4G_FD2100_KRR106 | 4G_TD_KRR106 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138435 | 2022-05-16 | P/FVC/MDS/1081011/2022 | 2022-05-25 | ST202205139009 | 2022-05-17 | P/FVC/MDS/1080949/2022 | 2022-05-25 |  |  |  |  | ST202205136588 | 2022-05-14 | P/FBW/MDS/1080860/2022 | 2022-05-25
1605 | VDIUR2 | VDIUR2 |  |  |  | ROTN | Indus | - | R/NN-654445 |  | On Air | 2022-05-05 | VDIUR2 | 4G_FD900_VDIUR2 | 4G_FD2100_VDIUR2 | 4G_TD_VDIUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138456 | 2022-05-16 | P/FVC/MDS/1081026/2022 | 2022-05-25 | ST202205139060 | 2022-05-17 | P/FVC/MDS/1080964/2022 | 2022-05-25 |  |  |  |  | ST202205138077 | 2022-05-16 | P/FBW/MDS/1080875/2022 | 2022-05-25
1606 | URPNR2 | URPNR2 |  |  |  | ROTN | Indus | - | R/NN-654449 |  | SO | 2022-05-19 | URPNR2 | 4G_FD900_URPNR2 | 4G_FD2100_URPNR2 | 4G_TD_URPNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148705 | 2022-05-28 | P/FVC/MDS/1081311/2022 | 2022-06-03 | ST202205147388 | 2022-05-27 | P/FVC/MDS/1081158/2022 | 2022-06-03 |  |  |  |  | ST202205147839 | 2022-05-27 | P/FBW/MDS/1081232/2022 | 2022-06-03
1607 | NRSIM2 | NRSIM2 |  |  |  | ROTN | Indus | - | R/NN-654453 |  |  | 2022-05-19 | NRSIM2 | 4G_FD900_NRSIM2 | 4G_FD2100_NRSIM2 | 4G_TD_NRSIM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148706 | 2022-05-28 | P/FVC/MDS/1081312/2022 | 2022-06-03 | ST202205147389 | 2022-05-27 | P/FVC/MDS/1081159/2022 | 2022-06-03 |  |  |  |  | ST202205148142 | 2022-05-28 | P/FBW/MDS/1081233/2022 | 2022-06-03
1608 | PRIUR2 | PRIUR2 |  |  |  | ROTN | Indus | - | R/NN-654454 |  | On Air | 2022-05-05 | PRIUR2 | 4G_FD900_PRIUR2 | 4G_FD2100_PRIUR2 | 4G_TD_PRIUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138452 | 2022-05-16 | P/FVC/MDS/1081022/2022 | 2022-05-25 | ST202205139046 | 2022-05-17 | P/FVC/MDS/1080960/2022 | 2022-05-25 |  |  |  |  | ST202205138043 | 2022-05-16 | P/FBW/MDS/1080871/2022 | 2022-05-25
1609 | KOTKD2 | KOTKD2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-05-02 | KOTKD2 | 4G_FD900_KOTKD2 | 4G_FD2100_KOTKD2 | 4G_TD_KOTKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124889 | 2022-05-02 | P/FVC/MDS/1079481/2022 | 2022-05-16 | ST202205124827 | 2022-05-02 | P/FVC/MDS/1079402/2022 | 2022-05-13 |  |  |  |  | ST202205124766 | 2022-05-02 | P/FBW/MDS/1079319/2022 | 2022-05-13
1610 | ILANJ2 | ILANJ2 |  |  |  | ROTN | Indus | - | R/NN-654455 |  | On Air | 2022-05-05 | ILANJ2 | 4G_FD900_ILANJ2 | 4G_FD2100_ILANJ2 | 4G_TD_ILANJ2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138459 | 2022-05-16 | P/FVC/MDS/1081027/2022 | 2022-05-25 | ST202205139074 | 2022-05-17 | P/FVC/MDS/1080965/2022 | 2022-05-25 |  |  |  |  | ST202205138082 | 2022-05-16 | P/FBW/MDS/1080876/2022 | 2022-05-25
1611 | ELTHR2 | ELTHR2 |  |  |  | ROTN | Indus | - | R/NN-654459 |  | On Air | 2022-05-05 | ELTHR2 | 4G_FD900_ELTHR2 | 4G_FD2100_ELTHR2 | 4G_TD_ELTHR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138460 | 2022-05-16 | P/FVC/MDS/1081028/2022 | 2022-05-25 | ST202205139075 | 2022-05-17 | P/FVC/MDS/1080966/2022 | 2022-05-25 |  |  |  |  | ST202205138083 | 2022-05-16 | P/FBW/MDS/1080877/2022 | 2022-05-25
1612 | KODKL2 | KODKL2 |  |  |  | ROTN | Summit | I-TN-MDUR-ENB-9038 | SR-TN000933 |  | On Air | 2022-05-02 | KODKL2 | 4G_FD900_KODKL2 | 4G_FD2100_KODKL2 | 4G_TD_KODKL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124901 | 2022-05-02 | P/FVC/MDS/1079485/2022 | 2022-05-16 | ST202205124836 | 2022-05-02 | P/FVC/MDS/1079406/2022 | 2022-05-13 |  |  |  |  | ST202205124777 | 2022-05-02 | P/FBW/MDS/1079323/2022 | 2022-05-13
1613 | MNDKL2 | MNDKL2 |  |  |  | ROTN | Summit | I-TN-MDUI-ENB-9028 | SR-TN000934 |  | On Air | 2022-05-02 | MNDKL2 | 4G_FD900_MNDKL2 | 4G_FD2100_MNDKL2 | 4G_TD_MNDKL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124900 | 2022-05-02 | P/FVC/MDS/1079484/2022 | 2022-05-16 | ST202205124835 | 2022-05-02 | P/FVC/MDS/1079405/2022 | 2022-05-13 |  |  |  |  | ST202205124776 | 2022-05-02 | P/FBW/MDS/1079322/2022 | 2022-05-13
1614 | MOLPT2 | MOLPT2 |  |  |  | ROTN | Summit | I-TN-VDGR-ENB-9027 | SR-TN000935 |  | On Air | 2022-05-02 | MOLPT2 | 4G_FD900_MOLPT2 | 4G_FD2100_MOLPT2 | 4G_TD_MOLPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124902 | 2022-05-02 | P/FVC/MDS/1079486/2022 | 2022-05-16 | ST202205124840 | 2022-05-02 | P/FVC/MDS/1079407/2022 | 2022-05-13 |  |  |  |  | ST202205124778 | 2022-05-02 | P/FBW/MDS/1079324/2022 | 2022-05-13
1615 | KODGP2 | KODGP2 |  |  |  | ROTN | Indus | - | R/NN-654462 |  | On Air | 2022-05-17 | KODGP2 | 4G_FD900_KODGP2 | 4G_FD2100_KODGP2 | 4G_TD_KODGP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148547 | 2022-05-28 | P/FVC/MDS/1081288/2022 | 2022-06-03 | ST202205147347 | 2022-05-27 | P/FVC/MDS/1081135/2022 | 2022-06-03 |  |  |  |  | ST202205147812 | 2022-05-27 | P/FBW/MDS/1081209/2022 | 2022-06-03
1616 | KRVIK2 | KRVIK2 |  |  |  | ROTN | Indus | - | R/NN-654476 |  | On Air | 2022-05-02 | KRVIK2 | 4G_FD900_KRVIK2 | 4G_FD2100_KRVIK2 | 4G_TD_KRVIK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124910 | 2022-05-02 | P/FVC/MDS/1079491/2022 | 2022-05-16 | ST202205124847 | 2022-05-02 | P/FVC/MDS/1079412/2022 | 2022-05-13 |  |  |  |  | ST202205124796 | 2022-05-02 | P/FBW/MDS/1079329/2022 | 2022-05-13
1617 | MLSND2 | MLSND2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-25 | MLSND2 | 4G_FD900_MLSND2 | 4G_FD2100_MLSND2 | 4G_TD_MLSND2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123426 | 2022-04-30 | P/FVC/MDS/1079422/2022 | 2022-05-16 | ST202204119651 | 2022-04-26 | P/FVC/MDS/1079337/2022 | 2022-05-13 |  |  |  |  | ST202204119401 | 2022-04-26 | P/FBW/MDS/1079245/2022 | 2022-05-13
1618 | MTHPL2 | MTHPL2 |  |  |  | ROTN | ATC | TN/CO/AT/23157 | T22TN01409 |  | On Air | 2022-05-17 | MTHPL2 | 4G_FD900_MTHPL2 | 4G_FD2100_MTHPL2 | 4G_TD_MTHPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148369 | 2022-05-28 | P/FVC/MDS/1081277/2022 | 2022-06-03 | ST202205147328 | 2022-05-27 | P/FVC/MDS/1081124/2022 | 2022-06-03 |  |  |  |  | ST202205147795 | 2022-05-27 | P/FBW/MDS/1081198/2022 | 2022-06-03
1619 | KARIA3 | KARIA3 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-04-29 | KARIA3 | 4G_FD900_KARIA3 | 4G_FD2100_KARIA3 | 4G_TD_KARIA3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123501 | 2022-04-30 | P/FVC/MDS/1079446/2022 | 2022-05-16 | ST202205124512 | 2022-05-02 | P/FVC/MDS/1079367/2022 | 2022-05-13 |  |  |  |  | ST202204123860 | 2022-04-30 | P/FBW/MDS/1079283/2022 | 2022-05-13
1620 | VETMP2 | VETMP2 |  |  |  | ROTN | ATC | TN/NM/AT/23158 | T22TN01410 |  | On Air | 2022-05-17 | VETMP2 | 4G_FD900_VETMP2 | 4G_FD2100_VETMP2 | 4G_TD_VETMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148561 | 2022-05-28 | P/FVC/MDS/1081292/2022 | 2022-06-03 | ST202205147354 | 2022-05-27 | P/FVC/MDS/1081139/2022 | 2022-06-03 |  |  |  |  | ST202205147816 | 2022-05-27 | P/FBW/MDS/1081213/2022 | 2022-06-03
1621 | ERD245 | ERD245 |  |  |  | ROTN | ATC | TN/ER/AT/23159 | T22TN01411 |  | On Air | 2022-05-19 | ERD245 | 4G_FD900_ERD245 | 4G_FD2100_ERD245 | 4G_TD_ERD245 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148760 | 2022-05-28 | P/FVC/MDS/1081318/2022 | 2022-06-03 | ST202205147399 | 2022-05-27 | P/FVC/MDS/1081165/2022 | 2022-06-03 |  |  |  |  | ST202205148153 | 2022-05-28 | P/FBW/MDS/1081239/2022 | 2022-06-03
1622 | KRR108 | KRR108 |  |  |  | ROTN | ATC | TN/KU/AT/23161 | T22TN01413 |  | On Air | 2022-05-09 | KRR108 | 4G_FD900_KRR108 | 4G_FD2100_KRR108 | 4G_TD_KRR108 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206165591 | 2022-06-07 | P/FVC/MDS/1082467/2022 | 2022-06-14 | ST202206165491 | 2022-06-07 | P/FVC/MDS/1082420/2022 | 2022-06-14 |  |  |  |  | ST202206165053 | 2022-06-07 | P/FBW/MDS/1082369/2022 | 2022-06-14
1623 | KOYMB2 | KOYMB2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-05-10 | KOYMB2 | 4G_FD900_KOYMB2 | 4G_FD2100_KOYMB2 | 4G_TD_KOYMB2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138397 | 2022-05-16 | P/FVC/MDS/1080986/2022 | 2022-05-25 | ST202205138708 | 2022-05-17 | P/FVC/MDS/1080923/2022 | 2022-05-25 |  |  |  |  | ST202205136563 | 2022-05-14 | P/FBW/MDS/1080836/2022 | 2022-05-25
1624 | MUSRV2 | MUSRV2 |  |  |  | ROTN | Indus | - | R/NN-654479 |  | On Air | 2022-05-17 | MUSRV2 | 4G_FD900_MUSRV2 | 4G_FD2100_MUSRV2 | 4G_TD_MUSRV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148548 | 2022-05-28 | P/FVC/MDS/1081289/2022 | 2022-06-03 | ST202205147349 | 2022-05-27 | P/FVC/MDS/1081136/2022 | 2022-06-03 |  |  |  |  | ST202205147813 | 2022-05-27 | P/FBW/MDS/1081210/2022 | 2022-06-03
1625 | PLNDR2 | PLNDR2 |  |  |  | ROTN | Ascend | - | - |  | Dropped | 2022-05-02 | PLNDR2 | 4G_FD900_PLNDR2 | 4G_FD2100_PLNDR2 | 4G_TD_PLNDR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124913 | 2022-05-02 | P/FVC/MDS/1079492/2022 | 2022-05-16 | ST202205124852 | 2022-05-02 | P/FVC/MDS/1079413/2022 | 2022-05-13 |  |  |  |  | ST202205124797 | 2022-05-02 | P/FBW/MDS/1079330/2022 | 2022-05-13
1626 | NTRKU2 | NTRKU2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-27 | NTRKU2 | 4G_FD900_NTRKU2 | 4G_FD2100_NTRKU2 | 4G_TD_NTRKU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123636 | 2022-04-30 | P/FVC/MDS/1079465/2022 | 2022-05-16 | ST202205124555 | 2022-05-02 | P/FVC/MDS/1079386/2022 | 2022-05-13 |  |  |  |  | ST202204123982 | 2022-04-30 | P/FBW/MDS/1079302/2022 | 2022-05-13
1627 | NOCHK2 | NOCHK2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-04-27 | NOCHK2 | 4G_FD900_NOCHK2 | 4G_FD2100_NOCHK2 | 4G_TD_NOCHK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123637 | 2022-04-30 | P/FVC/MDS/1079466/2022 | 2022-05-16 | ST202205124559 | 2022-05-02 | P/FVC/MDS/1079387/2022 | 2022-05-13 |  |  |  |  | ST202204123983 | 2022-04-30 | P/FBW/MDS/1079303/2022 | 2022-05-13
1628 | KLPNR2 | KLPNR2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-04-27 | KLPNR2 | 4G_FD900_KLPNR2 | 4G_FD2100_KLPNR2 | 4G_TD_KLPNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403761 | 2022-09-08 | P/FVC/MDS/1096552/2022 | 2022-09-16 | ST202209403965 | 2022-09-08 | P/FVC/MDS/1096461/2022 | 2022-09-16 |  |  |  |  | ST202209398999 | 2022-09-07 | P/FVC/MDS/1096367/2022 | 2022-09-16
1629 | TIR497 | TIR497 |  |  |  | ROTN | ATC | TN/TI/AT/23166 | T22TN01418 |  | On Air | 2022-05-09 | TIR497 | 4G_FD900_TIR497 | 4G_FD2100_TIR497 | 4G_TD_TIR497 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138430 | 2022-05-16 | P/FVC/MDS/1081008/2022 | 2022-05-25 | ST202205139002 | 2022-05-17 | P/FVC/MDS/1080946/2022 | 2022-05-25 |  |  |  |  | ST202205136585 | 2022-05-14 | P/FBW/MDS/1080857/2022 | 2022-05-25
1630 | KALIM2 | KALIM2 |  |  |  | ROTN | ATC | TN/TI/AT/23167 | T22TN01419 |  | On Air | 2022-05-05 | KALIM2 | 4G_FD900_KALIM2 | 4G_FD2100_KALIM2 | 4G_TD_KALIM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138466 | 2022-05-16 | P/FVC/MDS/1081032/2022 | 2022-05-25 | ST202205139082 | 2022-05-17 | P/FVC/MDS/1080970/2022 | 2022-05-25 |  |  |  |  | ST202205138095 | 2022-05-16 | P/FBW/MDS/1080881/2022 | 2022-05-25
1631 | KLCIP2 | KLCIP2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-05 | KLCIP2 | 4G_FD900_KLCIP2 | 4G_FD2100_KLCIP2 | 4G_TD_KLCIP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138455 | 2022-05-16 | P/FVC/MDS/1081025/2022 | 2022-05-25 | ST202205139059 | 2022-05-17 | P/FVC/MDS/1080963/2022 | 2022-05-25 |  |  |  |  | ST202205138076 | 2022-05-16 | P/FBW/MDS/1080874/2022 | 2022-05-25
1632 | MLTHK2 | MLTHK2 |  |  |  | ROTN | Summit | I-TN-TVML-ENB-9085 | SR-TN000937 |  | On Air | 2022-04-29 | MLTHK2 | 4G_FD900_MLTHK2 | 4G_FD2100_MLTHK2 | 4G_TD_MLTHK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203086116 | 2022-03-30 | P/FVC/MDS/1078206/2022 | 2022-04-15 | ST202203085364 | 2022-03-29 | P/FVC/MDS/1078159/2022 | 2022-04-15 |  |  |  |  | ST202203085838 | 2022-03-30 | P/FBW/MDS/1077914/2022 | 2022-04-14
1633 | KEENR2 | KEENR2 |  |  |  | ROTN | Summit | I-TN-RSPM-ENB-9055 | SR-TN000939 |  | On Air | 2022-05-09 | KEENR2 | 4G_FD900_KEENR2 | 4G_FD2100_KEENR2 | 4G_TD_KEENR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205130273 | 2022-05-07 | P/FVC/MDS/1080429/2022 | 2022-05-20 | ST202205130235 | 2022-05-07 | P/FVC/MDS/1080401/2022 | 2022-05-20 |  |  |  |  | ST202205130214 | 2022-05-07 | P/FBW/MDS/1079898/2022 | 2022-05-20
1634 | VLMPT2 | VLMPT2 |  |  |  | ROTN | Summit | I-TN-SVKS-ENB-9046 | SR-TN000938 |  | On Air | 2022-05-02 | VLMPT2 | 4G_FD900_VLMPT2 | 4G_FD2100_VLMPT2 | 4G_TD_VLMPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205124903 | 2022-05-02 | P/FVC/MDS/1079487/2022 | 2022-05-16 | ST202205124841 | 2022-05-02 | P/FVC/MDS/1079408/2022 | 2022-05-13 |  |  |  |  | ST202205124784 | 2022-05-02 | P/FBW/MDS/1079325/2022 | 2022-05-13
1635 | CBE918 | CBE918 |  |  |  | ROTN | ATC | TN/CO/TT/13440 | - |  | On Air | 2022-04-22 | CBE918 | 4G_FD900_CBE918 | 4G_FD2100_CBE918 | 4G_TD_CBE918 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204110279 | 2022-04-19 | P/FVC/MDS/1078920/2022 | 2022-05-02 | ST202204109854 | 2022-04-19 | P/FVC/MDS/1078982/2022 | 2022-05-03 | ST202204111898 | 2022-04-20 | P/FVC/MDS/1079016/2022 | 2022-05-03 | ST202204097829 | 2022-04-11 | P/FBW/MDS/1078304/2022 | 2022-04-21
1636 | ANKRI2 | ANKRI2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-19 | ANKRI2 | 4G_FD900_ANKRI2 | 4G_FD2100_ANKRI2 | 4G_TD_ANKRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148634 | 2022-05-28 | P/FVC/MDS/1081299/2022 | 2022-06-03 | ST202205147367 | 2022-05-27 | P/FVC/MDS/1081146/2022 | 2022-06-03 |  |  |  |  | ST202205147824 | 2022-05-27 | P/FBW/MDS/1081220/2022 | 2022-06-03
1637 | PRUMK2 | PRUMK2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-10 | PRUMK2 | 4G_FD900_PRUMK2 | 4G_FD2100_PRUMK2 | 4G_TD_PRUMK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138363 | 2022-05-16 | P/FVC/MDS/1080975/2022 | 2022-05-25 | ST202205138628 | 2022-05-17 | P/FVC/MDS/1080912/2022 | 2022-05-25 |  |  |  |  | ST202205136549 | 2022-05-14 | P/FBW/MDS/1080825/2022 | 2022-05-25
1638 | AYNVL2 | AYNVL2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-10 | AYNVL2 | 4G_FD900_AYNVL2 | 4G_FD2100_AYNVL2 | 4G_TD_AYNVL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138364 | 2022-05-16 | P/FVC/MDS/1080976/2022 | 2022-05-25 | ST202205138629 | 2022-05-17 | P/FVC/MDS/1080913/2022 | 2022-05-25 |  |  |  |  | ST202205136550 | 2022-05-14 | P/FBW/MDS/1080826/2022 | 2022-05-25
1639 | KURUV2 | KURUV2 |  |  |  | ROTN | Indus |  | R/NN-656895 |  | SO | 2022-05-19 | KURUV2 | 4G_FD900_KURUV2 | 4G_FD2100_KURUV2 | 4G_TD_KURUV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148718 | 2022-05-28 | P/FVC/MDS/1081313/2022 | 2022-06-03 | ST202205147394 | 2022-05-27 | P/FVC/MDS/1081160/2022 | 2022-06-03 |  |  |  |  | ST202205148143 | 2022-05-28 | P/FBW/MDS/1081234/2022 | 2022-06-03
1640 | AVRMP2 | AVRMP2 |  |  |  | ROTN | Indus |  | R/NN-656896 |  | On Air | 2022-05-19 | AVRMP2 | 4G_FD900_AVRMP2 | 4G_FD2100_AVRMP2 | 4G_TD_AVRMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148720 | 2022-05-28 | P/FVC/MDS/1081314/2022 | 2022-06-03 | ST202205147395 | 2022-05-27 | P/FVC/MDS/1081161/2022 | 2022-06-03 |  |  |  |  | ST202205148144 | 2022-05-28 | P/FBW/MDS/1081235/2022 | 2022-06-03
1641 | PRUMK3 | PRUMK3 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-19 | PRUMK3 | 4G_FD900_PRUMK3 | 4G_FD2100_PRUMK3 | 4G_TD_PRUMK3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148635 | 2022-05-28 | P/FVC/MDS/1081300/2022 | 2022-06-03 | ST202205147370 | 2022-05-27 | P/FVC/MDS/1081147/2022 | 2022-06-03 |  |  |  |  | ST202205147825 | 2022-05-27 | P/FBW/MDS/1081221/2022 | 2022-06-03
1642 | TNMBK2 | TNMBK2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-10 | TNMBK2 | 4G_FD900_TNMBK2 | 4G_FD2100_TNMBK2 | 4G_TD_TNMBK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138392 | 2022-05-16 | P/FVC/MDS/1080985/2022 | 2022-05-25 | ST202205138707 | 2022-05-17 | P/FVC/MDS/1080922/2022 | 2022-05-25 |  |  |  |  | ST202205136562 | 2022-05-14 | P/FBW/MDS/1080835/2022 | 2022-05-25
1643 | TLYMG2 | TLYMG2 |  |  |  | ROTN | Summit | I-TN-MRGD-ENB-9041 | SR-TN000943 |  | On Air | 2022-05-09 | TLYMG2 | 4G_FD900_TLYMG2 | 4G_FD2100_TLYMG2 | 4G_TD_TLYMG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127158 | 2022-05-04 | P/FVC/MDS/1080422/2022 | 2022-05-20 | ST202205126783 | 2022-05-04 | P/FVC/MDS/1080317/2022 | 2022-05-20 |  |  |  |  | ST202205126239 | 2022-05-03 | P/FBW/MDS/1079890/2022 | 2022-05-20
1644 | TIRMK2 | TIRMK2 |  |  |  | ROTN | Summit | I-TN-MRGD-ENB-9029 | SR-TN000944 |  | On Air | 2022-05-09 | TIRMK2 | 4G_FD900_TIRMK2 | 4G_FD2100_TIRMK2 | 4G_TD_TIRMK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126852 | 2022-05-04 | P/FVC/MDS/1080413/2022 | 2022-05-20 | ST202205126763 | 2022-05-04 | P/FVC/MDS/1080308/2022 | 2022-05-20 |  |  |  |  | ST202205126216 | 2022-05-03 | P/FBW/MDS/1079881/2022 | 2022-05-20
1645 | PRVKT2 | PRVKT2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-10 | PRVKT2 | 4G_FD900_PRVKT2 | 4G_FD2100_PRVKT2 | 4G_TD_PRVKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138383 | 2022-05-16 | P/FVC/MDS/1080982/2022 | 2022-05-25 | ST202205138704 | 2022-05-17 | P/FVC/MDS/1080919/2022 | 2022-05-25 |  |  |  |  | ST202205136556 | 2022-05-14 | P/FBW/MDS/1080832/2022 | 2022-05-25
1646 | KNDMG2 | KNDMG2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-10 | KNDMG2 | 4G_FD900_KNDMG2 | 4G_FD2100_KNDMG2 | 4G_TD_KNDMG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138382 | 2022-05-16 | P/FVC/MDS/1080981/2022 | 2022-05-25 | ST202205138701 | 2022-05-17 | P/FVC/MDS/1080918/2022 | 2022-05-25 |  |  |  |  | ST202205136555 | 2022-05-14 | P/FBW/MDS/1080831/2022 | 2022-05-25
1647 | VNKRM2 | VNKRM2 |  |  |  | ROTN | Summit | I-TN-KTNL-ENB-9011 | SR-TN000945 |  | On Air | 2022-05-09 | VNKRM2 | 4G_FD900_VNKRM2 | 4G_FD2100_VNKRM2 | 4G_TD_VNKRM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126845 | 2022-05-04 | P/FVC/MDS/1080411/2022 | 2022-05-20 | ST202205126752 | 2022-05-04 | P/FVC/MDS/1080306/2022 | 2022-05-20 |  |  |  |  | ST202205126211 | 2022-05-03 | P/FBW/MDS/1079879/2022 | 2022-05-20
1648 | VTYPM2 | VTYPM2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-10 | VTYPM2 | 4G_FD900_VTYPM2 | 4G_FD2100_VTYPM2 | 4G_TD_VTYPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138390 | 2022-05-16 | P/FVC/MDS/1080983/2022 | 2022-05-25 | ST202205138705 | 2022-05-17 | P/FVC/MDS/1080920/2022 | 2022-05-25 |  |  |  |  | ST202205136559 | 2022-05-14 | P/FBW/MDS/1080833/2022 | 2022-05-25
1649 | AYKDI2 | AYKDI2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-10 | AYKDI2 | 4G_FD900_AYKDI2 | 4G_FD2100_AYKDI2 | 4G_TD_AYKDI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138391 | 2022-05-16 | P/FVC/MDS/1080984/2022 | 2022-05-25 | ST202205138706 | 2022-05-17 | P/FVC/MDS/1080921/2022 | 2022-05-25 |  |  |  |  | ST202205136560 | 2022-05-14 | P/FBW/MDS/1080834/2022 | 2022-05-25
1650 | KPMNG2 | KPMNG2 |  |  |  | ROTN | Summit | I-TN-NNLM-ENB-9021 | SR-TN000948 |  | On Air | 2022-05-09 | KPMNG2 | 4G_FD900_KPMNG2 | 4G_FD2100_KPMNG2 | 4G_TD_KPMNG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127157 | 2022-05-04 | P/FVC/MDS/1080421/2022 | 2022-05-20 | ST202205126782 | 2022-05-04 | P/FVC/MDS/1080316/2022 | 2022-05-20 |  |  |  |  | ST202205126238 | 2022-05-03 | P/FBW/MDS/1079889/2022 | 2022-05-20
1651 | MTHUR2 | MTHUR2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-19 | MTHUR2 | 4G_FD900_MTHUR2 | 4G_FD2100_MTHUR2 | 4G_TD_MTHUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148648 | 2022-05-28 | P/FVC/MDS/1081301/2022 | 2022-06-03 | ST202205147371 | 2022-05-27 | P/FVC/MDS/1081148/2022 | 2022-06-03 |  |  |  |  | ST202205147826 | 2022-05-27 | P/FBW/MDS/1081222/2022 | 2022-06-03
1652 | VRCM37 | VRCM37 |  |  |  | ROTN | Indus | IN-3132379 | R/NN-656967 |  | On Air | 2022-05-21 | VRCM37 | 4G_FD900_VRCM37 | 4G_FD2100_VRCM37 | 4G_TD_VRCM37 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148782 | 2022-05-28 | P/FVC/MDS/1081324/2022 | 2022-06-03 | ST202205147405 | 2022-05-27 | P/FVC/MDS/1081171/2022 | 2022-06-03 |  |  |  |  | ST202205148171 | 2022-05-28 | P/FBW/MDS/1081245/2022 | 2022-06-03
1653 | STUKD2 | STUKD2 |  |  |  | ROTN | Summit | I-TN-VDCM-ENB-9049 | SR-TN000950 |  | On Air | 2022-05-09 | STUKD2 | 4G_FD900_STUKD2 | 4G_FD2100_STUKD2 | 4G_TD_STUKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127145 | 2022-05-04 | P/FVC/MDS/1080419/2022 | 2022-05-20 | ST202205126778 | 2022-05-04 | P/FVC/MDS/1080314/2022 | 2022-05-20 |  |  |  |  | ST202205126232 | 2022-05-03 | P/FBW/MDS/1079887/2022 | 2022-05-20
1654 | VRCM40 | VRCM40 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-27 | VRCM40 | 4G_FD900_VRCM40 | 4G_FD2100_VRCM40 | 4G_TD_VRCM40 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205151097 | 2022-05-16 | P/FVC/MDS/1081327/2022 | 2022-06-03 | ST202206156579 | 2022-06-02 | P/FVC/MDS/1082397/2022 | 2022-06-14 |  |  |  |  | ST202206156133 | 2022-06-02 | P/FBW/MDS/1082343/2022 | 2022-06-14
1655 | PRVLR2 | PRVLR2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-17 | PRVLR2 | 4G_FD900_PRVLR2 | 4G_FD2100_PRVLR2 | 4G_TD_PRVLR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148341 | 2022-05-28 | P/FVC/MDS/1081269/2022 | 2022-06-03 | ST202205147239 | 2022-05-27 | P/FVC/MDS/1081116/2022 | 2022-06-03 |  |  |  |  | ST202205147778 | 2022-05-27 | P/FBW/MDS/1081190/2022 | 2022-06-03
1656 | KMNGL2 | KMNGL2 |  |  |  | ROTN | Summit | I-TN-VDCM-ENB-9051 | SR-TN000951 |  | On Air | 2022-05-09 | KMNGL2 | 4G_FD900_KMNGL2 | 4G_FD2100_KMNGL2 | 4G_TD_KMNGL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127144 | 2022-05-04 | P/FVC/MDS/1080418/2022 | 2022-05-20 | ST202205126777 | 2022-05-04 | P/FVC/MDS/1080313/2022 | 2022-05-20 |  |  |  |  | ST202205126231 | 2022-05-03 | P/FBW/MDS/1079886/2022 | 2022-05-20
1657 | PLYPT2 | PLYPT2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-17 | PLYPT2 | 4G_FD900_PLYPT2 | 4G_FD2100_PLYPT2 | 4G_TD_PLYPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148333 | 2022-05-28 | P/FVC/MDS/1081267/2022 | 2022-06-03 | ST202205147236 | 2022-05-27 | P/FVC/MDS/1081114/2022 | 2022-06-03 |  |  |  |  | ST202205147776 | 2022-05-27 | P/FBW/MDS/1081188/2022 | 2022-06-03
1658 | KRINJ2 | KRINJ2 |  |  |  | ROTN | Indus |  | R/NN-656972 |  | On Air | 2022-05-17 | KRINJ2 | 4G_FD900_KRINJ2 | 4G_FD2100_KRINJ2 | 4G_TD_KRINJ2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148465 | 2022-05-28 | P/FVC/MDS/1081286/2022 | 2022-06-03 | ST202205147345 | 2022-05-27 | P/FVC/MDS/1081133/2022 | 2022-06-03 |  |  |  |  | ST202205147808 | 2022-05-27 | P/FBW/MDS/1081207/2022 | 2022-06-03
1659 | VIRUK2 | VIRUK2 |  |  |  | ROTN | Summit | I-TN-KURJ-ENB-9033 | SR-TN000952 |  | On Air | 2022-05-09 | VIRUK2 | 4G_FD900_VIRUK2 | 4G_FD2100_VIRUK2 | 4G_TD_VIRUK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126824 | 2022-05-04 | P/FVC/MDS/1080406/2022 | 2022-05-20 | ST202205126728 | 2022-05-04 | P/FVC/MDS/1080301/2022 | 2022-05-20 |  |  |  |  | ST202205126200 | 2022-05-03 | P/FBW/MDS/1079874/2022 | 2022-05-20
1660 | KNJMP2 | KNJMP2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-17 | KNJMP2 | 4G_FD900_KNJMP2 | 4G_FD2100_KNJMP2 | 4G_TD_KNJMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148368 | 2022-05-28 | P/FVC/MDS/1081276/2022 | 2022-06-03 | ST202205147323 | 2022-05-27 | P/FVC/MDS/1081123/2022 | 2022-06-03 |  |  |  |  | ST202205147788 | 2022-05-27 | P/FBW/MDS/1081197/2022 | 2022-06-03
1661 | PEDNK2 | PEDNK2 |  |  |  | ROTN | Summit | I-TN-KURJ-ENB-9032 | SR-TN000953 |  | On Air | 2022-05-09 | PEDNK2 | 4G_FD900_PEDNK2 | 4G_FD2100_PEDNK2 | 4G_TD_PEDNK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126823 | 2022-05-04 | P/FVC/MDS/1080405/2022 | 2022-05-20 | ST202205126727 | 2022-05-04 | P/FVC/MDS/1080300/2022 | 2022-05-20 |  |  |  |  | ST202205126172 | 2022-05-03 | P/FBW/MDS/1079873/2022 | 2022-05-20
1662 | ARNKM2 | ARNKM2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-17 | ARNKM2 | 4G_FD900_ARNKM2 | 4G_FD2100_ARNKM2 | 4G_TD_ARNKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148340 | 2022-05-28 | P/FVC/MDS/1081268/2022 | 2022-06-03 | ST202205147238 | 2022-05-27 | P/FVC/MDS/1081115/2022 | 2022-06-03 |  |  |  |  | ST202205147777 | 2022-05-27 | P/FBW/MDS/1081189/2022 | 2022-06-03
1663 | PNKKM2 | PNKKM2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | PNKKM2 | 4G_FD900_PNKKM2 | 4G_FD2100_PNKKM2 | 4G_TD_PNKKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403826 | 2022-09-08 | P/FVC/MDS/1096559/2022 | 2022-09-16 | ST202209404014 | 2022-09-08 | P/FVC/MDS/1096468/2022 | 2022-09-16 |  |  |  |  | ST202209399021 | 2022-09-07 | P/FVC/MDS/1096374/2022 | 2022-09-16
1664 | NLKP11 | NLKP11 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | NLKP11 | 4G_FD900_NLKP11 | 4G_FD2100_NLKP11 | 4G_TD_NLKP11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148348 | 2022-05-28 | P/FVC/MDS/1081271/2022 | 2022-06-03 | ST202205147242 | 2022-05-27 | P/FVC/MDS/1081118/2022 | 2022-06-03 |  |  |  |  | ST202205147780 | 2022-05-27 | P/FBW/MDS/1081192/2022 | 2022-06-03
1665 | MPRI25 | MPRI25 |  |  |  | ROTN | Indus | IN-3132383 | R/NN-656978 |  | On Air | 2022-05-21 | MPRI25 | 4G_FD900_MPRI25 | 4G_FD2100_MPRI25 | 4G_TD_MPRI25 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148783 | 2022-05-28 | P/FVC/MDS/1081325/2022 | 2022-06-03 | ST202206156182 | 2022-06-02 | P/FVC/MDS/1082375/2022 | 2022-06-14 |  |  |  |  | ST202205148179 | 2022-05-28 | P/FBW/MDS/1081246/2022 | 2022-06-03
1666 | MPRI26 | MPRI26 |  |  |  | ROTN | Indus | IN-3132389 | R/NN-656983 |  | On Air | 2022-05-21 | MPRI26 | 4G_FD900_MPRI26 | 4G_FD2100_MPRI26 | 4G_TD_MPRI26 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148784 | 2022-05-28 | P/FVC/MDS/1081326/2022 | 2022-06-03 | ST202206156183 | 2022-06-02 | P/FVC/MDS/1082376/2022 | 2022-06-14 |  |  |  |  | ST202205148180 | 2022-05-28 | P/FBW/MDS/1081247/2022 | 2022-06-03
1667 | VRLIM5 | VRLIM5 |  |  |  | ROTN | Summit | I-TN-VRMI-ENB-9003 | SR-TN000954 |  | On Air | 2022-05-09 | VRLIM5 | 4G_FD900_VRLIM5 | 4G_FD2100_VRLIM5 | 4G_TD_VRLIM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126846 | 2022-05-04 | P/FVC/MDS/1080412/2022 | 2022-05-20 | ST202205126762 | 2022-05-04 | P/FVC/MDS/1080307/2022 | 2022-05-20 |  |  |  |  | ST202205126215 | 2022-05-03 | P/FBW/MDS/1079880/2022 | 2022-05-20
1668 | ADMBI3 | ADMBI3 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-05 | ADMBI3 | 4G_FD900_ADMBI3 | 4G_FD2100_ADMBI3 | 4G_TD_ADMBI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138453 | 2022-05-16 | P/FVC/MDS/1081023/2022 | 2022-05-25 | ST202205139047 | 2022-05-17 | P/FVC/MDS/1080961/2022 | 2022-05-25 |  |  |  |  | ST202205138044 | 2022-05-16 | P/FBW/MDS/1080872/2022 | 2022-05-25
1669 | TIPIN2 | TIPIN2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | TIPIN2 | 4G_FD900_TIPIN2 | 4G_FD2100_TIPIN2 | 4G_TD_TIPIN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148313 | 2022-05-28 | P/FVC/MDS/1081259/2022 | 2022-06-03 | ST202205147198 | 2022-05-27 | P/FVC/MDS/1081106/2022 | 2022-06-03 |  |  |  |  | ST202205147767 | 2022-05-27 | P/FBW/MDS/1081180/2022 | 2022-06-03
1670 | SKNGD2 | SKNGD2 |  |  |  | ROTN | Summit | I-TN-CMBM-ENB-9063 | SR-TN000957 |  | On Air | 2022-05-09 | SKNGD2 | 4G_FD900_SKNGD2 | 4G_FD2100_SKNGD2 | 4G_TD_SKNGD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126840 | 2022-05-04 | P/FVC/MDS/1080409/2022 | 2022-05-20 | ST202205126737 | 2022-05-04 | P/FVC/MDS/1080304/2022 | 2022-05-20 |  |  |  |  | ST202205126209 | 2022-05-03 | P/FBW/MDS/1079877/2022 | 2022-05-20
1671 | PRNRP2 | PRNRP2 |  |  |  | ROTN | Summit | I-TN-CMBM-ENB-9051 | SR-TN000958 |  | On Air | 2022-05-09 | PRNRP2 | 4G_FD900_PRNRP2 | 4G_FD2100_PRNRP2 | 4G_TD_PRNRP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126837 | 2022-05-04 | P/FVC/MDS/1080408/2022 | 2022-05-20 | ST202205126736 | 2022-05-04 | P/FVC/MDS/1080303/2022 | 2022-05-20 |  |  |  |  | ST202205126202 | 2022-05-03 | P/FBW/MDS/1079876/2022 | 2022-05-20
1672 | VETAN2 | VETAN2 |  |  |  | ROTN | Summit | I-TN-SRKI-ENB-9050 | SR-TN000959 |  | On Air | 2022-05-09 | VETAN2 | 4G_FD900_VETAN2 | 4G_FD2100_VETAN2 | 4G_TD_VETAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127164 | 2022-05-04 | P/FVC/MDS/1080425/2022 | 2022-05-20 | ST202205126794 | 2022-05-04 | P/FVC/MDS/1080320/2022 | 2022-05-20 |  |  |  |  | ST202205126702 | 2022-05-04 | P/FBW/MDS/1079893/2022 | 2022-05-20
1673 | THIRL2 | THIRL2 |  |  |  | ROTN | Indus | IN-1082655 | R/RES-510452 |  | On Air | 2022-05-05 | THIRL2 | 4G_FD900_THIRL2 | 4G_FD2100_THIRL2 | 4G_TD_THIRL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127162 | 2022-05-04 | P/FVC/MDS/1080423/2022 | 2022-05-20 | ST202205126792 | 2022-05-04 | P/FVC/MDS/1080318/2022 | 2022-05-20 |  |  |  |  | ST202205126240 | 2022-05-03 | P/FBW/MDS/1079891/2022 | 2022-05-20
1674 | KTYMP2 | KTYMP2 |  |  |  | ROTN | Summit | I-TN-SRKI-ENB-9070 | SR-TN000960 |  | On Air | 2022-05-09 | KTYMP2 | 4G_FD900_KTYMP2 | 4G_FD2100_KTYMP2 | 4G_TD_KTYMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127166 | 2022-05-04 | P/FVC/MDS/1080426/2022 | 2022-05-20 | ST202205126804 | 2022-05-04 | P/FVC/MDS/1080321/2022 | 2022-05-20 |  |  |  |  | ST202205126703 | 2022-05-04 | P/FBW/MDS/1079894/2022 | 2022-05-20
1675 | PRPRM2 | PRPRM2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | PRPRM2 | 4G_FD900_PRPRM2 | 4G_FD2100_PRPRM2 | 4G_TD_PRPRM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148314 | 2022-05-28 | P/FVC/MDS/1081260/2022 | 2022-06-03 | ST202205147225 | 2022-05-27 | P/FVC/MDS/1081107/2022 | 2022-06-03 |  |  |  |  | ST202205147768 | 2022-05-27 | P/FBW/MDS/1081181/2022 | 2022-06-03
1676 | KRNGN2 | KRNGN2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | KRNGN2 | 4G_FD900_KRNGN2 | 4G_FD2100_KRNGN2 | 4G_TD_KRNGN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148315 | 2022-05-28 | P/FVC/MDS/1081261/2022 | 2022-06-03 | ST202205147226 | 2022-05-27 | P/FVC/MDS/1081108/2022 | 2022-06-03 |  |  |  |  | ST202205147769 | 2022-05-27 | P/FBW/MDS/1081182/2022 | 2022-06-03
1677 | PRNDB2 | PRNDB2 |  |  |  | ROTN | Indus | IN-1106568 | R/RES-510453 |  | On Air | 2022-05-09 | PRNDB2 | 4G_FD900_PRNDB2 | 4G_FD2100_PRNDB2 | 4G_TD_PRNDB2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205127163 | 2022-05-04 | P/FVC/MDS/1080424/2022 | 2022-05-20 | ST202205126793 | 2022-05-04 | P/FVC/MDS/1080319/2022 | 2022-05-20 |  |  |  |  | ST202205126701 | 2022-05-04 | P/FBW/MDS/1079892/2022 | 2022-05-20
1678 | TRMYP2 | TRMYP2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-17 | TRMYP2 | 4G_FD900_TRMYP2 | 4G_FD2100_TRMYP2 | 4G_TD_TRMYP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148358 | 2022-05-28 | P/FVC/MDS/1081274/2022 | 2022-06-03 | ST202205147321 | 2022-05-27 | P/FVC/MDS/1081121/2022 | 2022-06-03 |  |  |  |  | ST202205147786 | 2022-05-27 | P/FBW/MDS/1081195/2022 | 2022-06-03
1679 | TRMYP4 | TRMYP4 |  |  |  | ROTN | Summit | I-TN-KRKL-ENB-9026 | SR-TN000961 |  | On Air | 2022-05-09 | TRMYP4 | 4G_FD900_TRMYP4 | 4G_FD2100_TRMYP4 | 4G_TD_TRMYP4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126853 | 2022-05-04 | P/FVC/MDS/1080414/2022 | 2022-05-20 | ST202205126764 | 2022-05-04 | P/FVC/MDS/1080309/2022 | 2022-05-20 |  |  |  |  | ST202205126217 | 2022-05-03 | P/FBW/MDS/1079882/2022 | 2022-05-20
1680 | TNLR10 | TNLR10 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | TNLR10 | 4G_FD900_TNLR10 | 4G_FD2100_TNLR10 | 4G_TD_TNLR10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148321 | 2022-05-28 | P/FVC/MDS/1081262/2022 | 2022-06-03 | ST202205147227 | 2022-05-27 | P/FVC/MDS/1081109/2022 | 2022-06-03 |  |  |  |  | ST202205147771 | 2022-05-27 | P/FBW/MDS/1081183/2022 | 2022-06-03
1681 | POVAM2 | POVAM2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | POVAM2 | 4G_FD900_POVAM2 | 4G_FD2100_POVAM2 | 4G_TD_POVAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148322 | 2022-05-28 | P/FVC/MDS/1081263/2022 | 2022-06-03 | ST202205147230 | 2022-05-27 | P/FVC/MDS/1081110/2022 | 2022-06-03 |  |  |  |  | ST202205147772 | 2022-05-27 | P/FBW/MDS/1081184/2022 | 2022-06-03
1682 | NEDNG2 | NEDNG2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-17 | NEDNG2 | 4G_FD900_NEDNG2 | 4G_FD2100_NEDNG2 | 4G_TD_NEDNG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148349 | 2022-05-28 | P/FVC/MDS/1081272/2022 | 2022-06-03 | ST202205147243 | 2022-05-27 | P/FVC/MDS/1081119/2022 | 2022-06-03 |  |  |  |  | ST202205147781 | 2022-05-27 | P/FBW/MDS/1081193/2022 | 2022-06-03
1683 | EDTKD2 | EDTKD2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | EDTKD2 | 4G_FD900_EDTKD2 | 4G_FD2100_EDTKD2 | 4G_TD_EDTKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148323 | 2022-05-28 | P/FVC/MDS/1081264/2022 | 2022-06-03 | ST202205147231 | 2022-05-27 | P/FVC/MDS/1081111/2022 | 2022-06-03 |  |  |  |  | ST202205147773 | 2022-05-27 | P/FBW/MDS/1081185/2022 | 2022-06-03
1684 | TRKDU2 | TRKDU2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-17 | TRKDU2 | 4G_FD900_TRKDU2 | 4G_FD2100_TRKDU2 | 4G_TD_TRKDU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148357 | 2022-05-28 | P/FVC/MDS/1081273/2022 | 2022-06-03 | ST202205147244 | 2022-05-27 | P/FVC/MDS/1081120/2022 | 2022-06-03 |  |  |  |  | ST202205147782 | 2022-05-27 | P/FBW/MDS/1081194/2022 | 2022-06-03
1685 | KLMNR2 | KLMNR2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-17 | KLMNR2 | 4G_FD900_KLMNR2 | 4G_FD2100_KLMNR2 | 4G_TD_KLMNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148330 | 2022-05-28 | P/FVC/MDS/1081265/2022 | 2022-06-03 | ST202205147234 | 2022-05-27 | P/FVC/MDS/1081112/2022 | 2022-06-03 |  |  |  |  | ST202205147774 | 2022-05-27 | P/FBW/MDS/1081186/2022 | 2022-06-03
1686 | MANUR2 | MANUR2 |  |  |  | ROTN | Ascend |  |  |  | SO(Rural Hold) | 2022-05-10 | MANUR2 | 4G_FD900_MANUR2 | 4G_FD2100_MANUR2 | 4G_TD_MANUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138373 | 2022-05-16 | P/FVC/MDS/1080978/2022 | 2022-05-25 | ST202205138631 | 2022-05-17 | P/FVC/MDS/1080915/2022 | 2022-05-25 |  |  |  |  | ST202205136552 | 2022-05-14 | P/FBW/MDS/1080828/2022 | 2022-05-25
1687 | DEVNR2 | DEVNR2 |  |  |  | ROTN | Ascend | TNBS0017 |  |  | On Air | 2022-05-17 | DEVNR2 | 4G_FD900_DEVNR2 | 4G_FD2100_DEVNR2 | 4G_TD_DEVNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126854 | 2022-05-04 | P/FVC/MDS/1080415/2022 | 2022-05-20 | ST202205126771 | 2022-05-04 | P/FVC/MDS/1080310/2022 | 2022-05-20 |  |  |  |  | ST202205126222 | 2022-05-03 | P/FBW/MDS/1079883/2022 | 2022-05-20
1688 | TVLKP3 | TVLKP3 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-10 | TVLKP3 | 4G_FD900_TVLKP3 | 4G_FD2100_TVLKP3 | 4G_TD_TVLKP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138374 | 2022-05-16 | P/FVC/MDS/1080979/2022 | 2022-05-25 | ST202205138699 | 2022-05-17 | P/FVC/MDS/1080916/2022 | 2022-05-25 |  |  |  |  | ST202205136553 | 2022-05-14 | P/FBW/MDS/1080829/2022 | 2022-05-25
1689 | MNGKP2 | MNGKP2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-17 | MNGKP2 | 4G_FD900_MNGKP2 | 4G_FD2100_MNGKP2 | 4G_TD_MNGKP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148307 | 2022-05-28 | P/FVC/MDS/1081258/2022 | 2022-06-03 | ST202205147197 | 2022-05-27 | P/FVC/MDS/1081105/2022 | 2022-06-03 |  |  |  |  | ST202205147766 | 2022-05-27 | P/FBW/MDS/1081179/2022 | 2022-06-03
1690 | CDL100 | CDL100 |  |  |  | ROTN | Indus |  | R/NN-656854 |  | SO | 2022-05-17 | CDL100 | 4G_FD900_CDL100 | 4G_FD2100_CDL100 | 4G_TD_CDL100 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148424 | 2022-05-28 | P/FVC/MDS/1081284/2022 | 2022-06-03 | ST202205147339 | 2022-05-27 | P/FVC/MDS/1081131/2022 | 2022-06-03 |  |  |  |  | ST202205147805 | 2022-05-27 | P/FBW/MDS/1081205/2022 | 2022-06-03
1691 | MDLPT2 | MDLPT2 |  |  |  | ROTN | Ascend |  |  |  | SO | 2022-05-10 | MDLPT2 | 4G_FD900_MDLPT2 | 4G_FD2100_MDLPT2 | 4G_TD_MDLPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138372 | 2022-05-16 | P/FVC/MDS/1080977/2022 | 2022-05-25 | ST202205138630 | 2022-05-17 | P/FVC/MDS/1080914/2022 | 2022-05-25 |  |  |  |  | ST202205136551 | 2022-05-14 | P/FBW/MDS/1080827/2022 | 2022-05-25
1692 | PNCKM2 | PNCKM2 |  |  |  | ROTN | Indus | IN-1129751 | R/RES-510455 |  | On Air | 2022-05-17 | PNCKM2 | 4G_FD900_PNCKM2 | 4G_FD2100_PNCKM2 | 4G_TD_PNCKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205126822 | 2022-05-04 | P/FVC/MDS/1080404/2022 | 2022-05-20 | ST202205126726 | 2022-05-04 | P/FVC/MDS/1080299/2022 | 2022-05-20 |  |  |  |  | ST202205126171 | 2022-05-03 | P/FBW/MDS/1079872/2022 | 2022-05-20
1693 | GVDPM5 | GVDPM5 |  |  |  | ROTN | Indus |  | R/NN-656862 |  | On Air | 2022-05-19 | GVDPM5 | 4G_FD900_GVDPM5 | 4G_FD2100_GVDPM5 | 4G_TD_GVDPM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148704 | 2022-05-28 | P/FVC/MDS/1081310/2022 | 2022-06-03 | ST202205147387 | 2022-05-27 | P/FVC/MDS/1081157/2022 | 2022-06-03 |  |  |  |  | ST202205147838 | 2022-05-27 | P/FBW/MDS/1081231/2022 | 2022-06-03
1694 | TRKTI2 | TRKTI2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-10 | TRKTI2 | 4G_FD900_TRKTI2 | 4G_FD2100_TRKTI2 | 4G_TD_TRKTI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138399 | 2022-05-16 | P/FVC/MDS/1080988/2022 | 2022-05-25 | ST202205138934 | 2022-05-17 | P/FVC/MDS/1080926/2022 | 2022-05-25 |  |  |  |  | ST202205136565 | 2022-05-14 | P/FBW/MDS/1080838/2022 | 2022-05-25
1695 | PDKT61 | PDKT61 |  |  |  | ROTN | Indus | IN-3132280 | R/NN-656864 |  | On Air | 2022-05-21 | PDKT61 | 4G_FD900_PDKT61 | 4G_FD2100_PDKT61 | 4G_TD_PDKT61 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148770 | 2022-05-28 | P/FVC/MDS/1081322/2022 | 2022-06-03 | ST202205147403 | 2022-05-27 | P/FVC/MDS/1081169/2022 | 2022-06-03 |  |  |  |  | ST202205148160 | 2022-05-28 | P/FBW/MDS/1081243/2022 | 2022-06-03
1696 | TNJ181 | TNJ181 |  |  |  | ROTN | Indus |  | R/NN-656877 |  |  | 2022-05-17 | TNJ181 | 4G_FD900_TNJ181 | 4G_FD2100_TNJ181 | 4G_TD_TNJ181 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148464 | 2022-05-28 | P/FVC/MDS/1081285/2022 | 2022-06-03 | ST202205147340 | 2022-05-27 | P/FVC/MDS/1081132/2022 | 2022-06-03 |  |  |  |  | ST202205147807 | 2022-05-27 | P/FBW/MDS/1081206/2022 | 2022-06-03
1697 | CDBM69 | CDBM69 |  |  |  | ROTN | Indus |  | R/NN-656891 |  | SO | 2022-05-17 | CDBM69 | 4G_FD900_CDBM69 | 4G_FD2100_CDBM69 | 4G_TD_CDBM69 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148422 | 2022-05-28 | P/FVC/MDS/1081282/2022 | 2022-06-03 | ST202205147335 | 2022-05-27 | P/FVC/MDS/1081129/2022 | 2022-06-03 |  |  |  |  | ST202205147801 | 2022-05-27 | P/FBW/MDS/1081203/2022 | 2022-06-03
1698 | PRKLP2 | PRKLP2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-05-10 | PRKLP2 | 4G_FD900_PRKLP2 | 4G_FD2100_PRKLP2 | 4G_TD_PRKLP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138381 | 2022-05-16 | P/FVC/MDS/1080980/2022 | 2022-05-25 | ST202205138700 | 2022-05-17 | P/FVC/MDS/1080917/2022 | 2022-05-25 |  |  |  |  | ST202205136554 | 2022-05-14 | P/FBW/MDS/1080830/2022 | 2022-05-25
1699 | TRY399 | TRY399 |  |  |  | ROTN | Indus | IN-3132298 | R/NN-656892 |  | On Air | 2022-05-21 | TRY399 | 4G_FD900_TRY399 | 4G_FD2100_TRY399 | 4G_TD_TRY399 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148771 | 2022-05-28 | P/FVC/MDS/1081323/2022 | 2022-06-03 | ST202205147404 | 2022-05-27 | P/FVC/MDS/1081170/2022 | 2022-06-03 |  |  |  |  | ST202205148170 | 2022-05-28 | P/FBW/MDS/1081244/2022 | 2022-06-03
1700 | CDL104 | CDL104 |  |  |  | ROTN | Ascend | IN-3122365 | R/NN-643580 |  | On Air | 2022-05-17 | CDL104 | 4G_FD900_CDL104 | 4G_FD2100_CDL104 | 4G_TD_CDL104 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148359 | 2022-05-28 | P/FVC/MDS/1081275/2022 | 2022-06-03 | ST202205147322 | 2022-05-27 | P/FVC/MDS/1081122/2022 | 2022-06-03 |  |  |  |  | ST202205147787 | 2022-05-27 | P/FBW/MDS/1081196/2022 | 2022-06-03
1701 | BODI21 | BODI21 |  |  |  | ROTN | Indus | IN-1867364 | R/NN-569197 |  |  | 2022-05-10 | BODI21 | 4G_FD900_BODI21 | 4G_FD2100_BODI21 | 4G_TD_BODI21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138351 | 2022-05-16 | P/FVC/MDS/1080971/2022 | 2022-05-25 | ST202205138624 | 2022-05-17 | P/FVC/MDS/1080908/2022 | 2022-05-25 |  |  |  |  | ST202205136543 | 2022-05-14 | P/FBW/MDS/1080821/2022 | 2022-05-25
1702 | TVLR75/CWTVL2 | TVLR75 |  |  |  | ROTN | Indus | IN-3116345 | R/RES-509902 |  |  | 2021-04-15 | TVLR75 | 4G_FD900_TVLR75 | 4G_FD2100_TVLR75 | 4G_TD_TVLR75 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106329348 | 2021-06-07 | P/FVC/MDS/1036809/2021 | 2021-06-24 | ST202105296034 | 2021-05-25 | P/FVC/MDS/1045138/2021 | 2021-07-28 | ST202105295088 | 2021-05-25 | P/FVC/MDS/1036508/2021 | 2021-06-23 | ST202106326220 | 2021-06-06 | P/FVC/MDS/1036577/2021 | 2021-06-23
1703 | PATWM5 | PATWM5 |  |  |  | ROTN | Indus | IN-3126631 | R/NN-648565 |  |  | 2022-05-09 | PATWM5 | 4G_FD900_PATWM5 | 4G_FD2100_PATWM5 | 4G_TD_PATWM5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202205138410 | 2022-05-16 | P/FVC/MDS/1080992/2022 | 2022-05-25 | ST202205138944 | 2022-05-17 | P/FVC/MDS/1080930/2022 | 2022-05-25 | ST202205138185 | 2022-05-16 | P/FVC/MDS/1081042/2022 | 2022-05-25 | ST202205136569 | 2022-05-14 | P/FBW/MDS/1080842/2022 | 2022-05-25
1704 | PDY349 | PDY349 |  |  |  | ROTN | Indus | IN-3120404 | R/NN-641472 |  |  | - | PDY349 | 4G_FD900_PDY349 | 4G_FD2100_PDY349 | 4G_TD_PDY349 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202204111696 | 2022-04-20 | P/FVC/MDS/1078940/2022 | 2022-05-02 | ST202204110041 | 2022-04-19 | P/FVC/MDS/1079002/2022 | 2022-05-03 | ST202204111914 | 2022-04-20 | P/FVC/MDS/1079024/2022 | 2022-05-03 | ST202204109609 | 2022-04-19 | P/FVC/MDS/1078898/2022 | 2022-05-02
1705 | CBE906 | CBE906 |  |  |  | ROTN | Indus | - | - |  |  | 2022-05-09 | CBE906 | 4G_FD900_CBE906 | 4G_FD2100_CBE906 | 4G_TD_CBE906 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138403 | 2022-05-16 | P/FVC/MDS/1080990/2022 | 2022-05-25 | ST202205138942 | 2022-05-17 | P/FVC/MDS/1080928/2022 | 2022-05-25 |  |  |  |  | ST202205136567 | 2022-05-14 | P/FBW/MDS/1080840/2022 | 2022-05-25
1706 | PDY355 | PDY355 |  |  |  | ROTN | Airtel | I-TN-KRYP-ENB-9007 | SR-TN000485 |  |  |  | PDY355 | 4G_FD900_PDY355 | 4G_FD2100_PDY355 | 4G_TD_PDY355 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202205138443 | 2022-05-16 | P/FVC/MDS/1081015/2022 | 2022-05-25 | ST202205139018 | 2022-05-17 | P/FVC/MDS/1080954/2022 | 2022-05-25 | ST202205138336 | 2022-05-16 | P/FVC/MDS/1081050/2022 | 2022-05-25 | ST202205136592 | 2022-05-14 | P/FBW/MDS/1080864/2022 | 2022-05-25
1707 | SHANT5 | SHANT5 |  |  |  | ROTN | Airtel | IN-3122568 | R/RES-510828 |  |  | 2022-04-25 | SHANT5 | 4G_FD900_SHANT5 | 4G_FD2100_SHANT5 | 4G_TD_SHANT5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202204123424 | 2022-04-30 | P/FVC/MDS/1079420/2022 | 2022-05-16 | ST202204119643 | 2022-04-26 | P/FVC/MDS/1079335/2022 | 2022-05-13 | ST202205124686 | 2022-05-02 | P/FVC/MDS/1079509/2022 | 2022-05-16 | ST202204119394 | 2022-04-26 | P/FBW/MDS/1079243/2022 | 2022-05-13
1708 | MUSI18 | MUSI18 |  |  |  | ROTN | Indus | IN-3124988 | R/NN-646751 |  |  |  | MUSI18 | 4G_FD900_MUSI18 | 4G_FD2100_MUSI18 | 4G_TD_MUSI18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539016 | 2022-10-08 | P/FVC/MDS/1113982/2022 | 2022-10-21 | ST202210537814 | 2022-10-07 | P/FVC/MDS/1113797/2022 | 2022-10-21 | ST202210538263 | 2022-10-08 | P/FVC/MDS/1113858/2022 | 2022-10-21 | ST202210535008 | 2022-10-06 | P/FBW/MDS/1113715/2022 | 2022-10-21
1709 | CBE917 | CBE917 |  |  |  | ROTN | Indus | TN/TU/AT/23076 | T22TN01110 |  |  | 2022-05-17 | CBE917 | 4G_FD900_CBE917 | 4G_FD2100_CBE917 | 4G_TD_CBE917 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361124 | 2022-08-28 | P/FVC/MDS/1094706/2022 | 2022-09-07 | ST202208364727 | 2022-08-29 | P/FVC/MDS/1094771/2022 | 2022-09-07 | ST202208364773 | 2022-08-29 | P/FVC/MDS/1094795/2022 | 2022-09-07 | ST202208360954 | 2022-08-28 | P/FBW/MDS/1094641/2022 | 2022-09-07
1710 | SVPT33 | SVPT33 |  |  |  | ROTN | ATC | IN-3127687 | R/NN-649607 |  |  | 2022-05-09 | SVPT33 | 4G_FD900_SVPT33 | 4G_FD2100_SVPT33 | 4G_TD_SVPT33 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207296160 | 2022-07-28 | P/FVC/MDS/1093394/2022 | 2022-08-09 | ST202207298901 | 2022-07-29 | P/FVC/MDS/1093303/2022 | 2022-08-09 | ST202205138324 | 2022-05-16 | P/FVC/MDS/1081044/2022 | 2022-05-25 | ST202207295314 | 2022-07-28 | P/FBW/MDS/1093186/2022 | 2022-08-09
1711 | KLPRM2 | KLPRM2 |  |  |  | ROTN | Indus | IN-3130615 | R/NN-654029 |  |  | 2022-05-09 | KLPRM2 | 4G_FD900_KLPRM2 | 4G_FD2100_KLPRM2 | 4G_TD_KLPRM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202205138418 | 2022-05-16 | P/FVC/MDS/1080998/2022 | 2022-05-25 | ST202205138964 | 2022-05-17 | P/FVC/MDS/1080936/2022 | 2022-05-25 | ST202205138329 | 2022-05-16 | P/FVC/MDS/1081048/2022 | 2022-05-25 | ST202205136576 | 2022-05-14 | P/FBW/MDS/1080848/2022 | 2022-05-25
1712 | VRCM36 | VRCM36 |  |  |  | ROTN | Indus | IN-3131822 | R/NN-654259 |  |  | 2022-05-09 | VRCM36 | 4G_FD900_VRCM36 | 4G_FD2100_VRCM36 | 4G_TD_VRCM36 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202205138416 | 2022-05-16 | P/FVC/MDS/1080996/2022 | 2022-05-25 | ST202205138962 | 2022-05-17 | P/FVC/MDS/1080934/2022 | 2022-05-25 | ST202205138327 | 2022-05-16 | P/FVC/MDS/1081046/2022 | 2022-05-25 | ST202205136574 | 2022-05-14 | P/FBW/MDS/1080846/2022 | 2022-05-25
1713 | COWPNR | COWPNR |  |  |  | ROTN | Indus | TN/DH/VI/23169 | - |  |  |  | COWPNR | 4G_FD900_COWPNR | 4G_FD2100_COWPNR | 4G_TD_COWPNR | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202205138436 | 2022-05-16 | P/FVC/MDS/1081012/2022 | 2022-05-25 | ST202205139010 | 2022-05-17 | P/FVC/MDS/1080950/2022 | 2022-05-25 | ST202205138335 | 2022-05-16 | P/FVC/MDS/1081049/2022 | 2022-05-25 | ST202205136589 | 2022-05-14 | P/FBW/MDS/1080861/2022 | 2022-05-25
1714 | URAP23 | URAP23 |  |  |  | CHN | ATC | TN/CH/AT/23099 | T22TN01237 |  | On air | 2022-05-17 | URAP23 | 4G_FD900_URAP23 | 4G_FD2100_URAP23 | 4G_TD_URAP23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148608 | 2022-05-28 | P/FVC/MDS/1081295/2022 | 2022-06-03 | ST202205147361 | 2022-05-27 | P/FVC/MDS/1081142/2022 | 2022-06-03 |  |  |  |  | ST202205147820 | 2022-05-27 | P/FBW/MDS/1081216/2022 | 2022-06-03
1715 | KOLA50 | KOLA50 |  |  |  | CHN | ATC | TN/CH/AT/23101 | T22TN01239 |  | On air | 2022-05-09 | KOLA50 | 4G_FD900_KOLA50 | 4G_FD2100_KOLA50 | 4G_TD_KOLA50 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138421 | 2022-05-16 | P/FVC/MDS/1081001/2022 | 2022-05-25 | ST202205138972 | 2022-05-17 | P/FVC/MDS/1080939/2022 | 2022-05-25 |  |  |  |  | ST202205136578 | 2022-05-14 | P/FBW/MDS/1080850/2022 | 2022-05-25
1716 | PUZH15 | PUZH15 |  |  |  | CHN | ATC | TN/CH/AT/23102 | T22TN01240 |  | On air | 2022-05-19 | PUZH15 | 4G_FD900_PUZH15 | 4G_FD2100_PUZH15 | 4G_TD_PUZH15 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226816 | 2022-07-07 | P/FVC/MDS/1088037/2022 | 2022-07-18 | ST202207225020 | 2022-07-06 | P/FVC/MDS/1087929/2022 | 2022-07-18 |  |  |  |  | ST202207223995 | 2022-07-06 | P/FBW/MDS/1087845/2022 | 2022-07-18
1717 | NAND13 | NAND13 |  |  |  | CHN | Indus |  | R/NN-656815 |  | On air | 2022-05-05 | NAND13 | 4G_FD900_NAND13 | 4G_FD2100_NAND13 | 4G_TD_NAND13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205138461 | 2022-05-16 | P/FVC/MDS/1081029/2022 | 2022-05-25 | ST202205139079 | 2022-05-17 | P/FVC/MDS/1080967/2022 | 2022-05-25 | ST202210538364 | 2022-10-08 | P/FVC/MDS/1113885/2022 | 2022-10-21 | ST202205138084 | 2022-05-16 | P/FBW/MDS/1080878/2022 | 2022-05-25
1718 | REDH46 | REDH46 |  |  |  | CHN | Indus | IN-3125612 | R/NN-647770 |  | On air | 2022-05-19 | REDH46 | 4G_FD900_REDH46 | 4G_FD2100_REDH46 | 4G_TD_REDH46 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205148721 | 2022-05-28 | P/FVC/MDS/1081315/2022 | 2022-06-03 | ST202205147396 | 2022-05-27 | P/FVC/MDS/1081162/2022 | 2022-06-03 |  |  |  |  | ST202205148148 | 2022-05-28 | P/FBW/MDS/1081236/2022 | 2022-06-03
1719 | PERNG4 | PERNG4 |  |  |  | CHN | Indus | IN-3125613 | R/NN-647771 |  | On air | 2022-04-28 | PERNG4 | 4G_FD900_PERNG4 | 4G_FD2100_PERNG4 | 4G_TD_PERNG4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123617 | 2022-04-30 | P/FVC/MDS/1079462/2022 | 2022-05-16 | ST202205124548 | 2022-05-02 | P/FVC/MDS/1079383/2022 | 2022-05-13 |  |  |  |  | ST202204123976 | 2022-04-30 | P/FBW/MDS/1079299/2022 | 2022-05-13
1720 | PERNG5 | PERNG5 |  |  |  | CHN | Indus |  | R/NN-647772 |  | SO | 2022-04-29 | PERNG5 | 4G_FD900_PERNG5 | 4G_FD2100_PERNG5 | 4G_TD_PERNG5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123515 | 2022-04-30 | P/FVC/MDS/1079449/2022 | 2022-05-16 | ST202205124519 | 2022-05-02 | P/FVC/MDS/1079370/2022 | 2022-05-13 |  |  |  |  | ST202204123871 | 2022-04-30 | P/FBW/MDS/1079286/2022 | 2022-05-13
1721 | AVAD34 | AVAD34 |  |  |  | CHN | Ascend | - | - |  | SO | 2022-04-25 | AVAD34 | 4G_FD900_AVAD34 | 4G_FD2100_AVAD34 | 4G_TD_AVAD34 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202204123436 | 2022-04-30 | P/FVC/MDS/1079423/2022 | 2022-05-16 | ST202204119652 | 2022-04-26 | P/FVC/MDS/1079338/2022 | 2022-05-13 |  |  |  |  | ST202204119405 | 2022-04-26 | P/FBW/MDS/1079246/2022 | 2022-05-13
1722 | PTRA19 | PTRA19 |  |  |  | CHN | Indus | IN-3123969 | R/NN-644870 |  |  | 2022-05-21 | PTRA19 | 4G_FD900_PTRA19 | 4G_FD2100_PTRA19 | 4G_TD_PTRA19 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202205148762 | 2022-05-28 | P/FVC/MDS/1081320/2022 | 2022-06-03 | ST202205147401 | 2022-05-27 | P/FVC/MDS/1081167/2022 | 2022-06-03 | ST202205148282 | 2022-05-28 | P/FVC/MDS/1081252/2022 | 2022-06-03 | ST202205148158 | 2022-05-28 | P/FBW/MDS/1081241/2022 | 2022-06-03
1723 | VELBY9 | VELBY9 |  |  |  | CHN | INDUS | IN-3114361 | R/NN-639919 |  |  | 2022-05-09 | VELBY9 | 4G_FD900_VELBY9 | 4G_FD2100_VELBY9 | 4G_TD_VELBY9 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202205138415 | 2022-05-16 | P/FVC/MDS/1080995/2022 | 2022-05-25 | ST202205138954 | 2022-05-17 | P/FVC/MDS/1080933/2022 | 2022-05-25 | ST202205138325 | 2022-05-16 | P/FVC/MDS/1081045/2022 | 2022-05-25 | ST202205136573 | 2022-05-14 | P/FBW/MDS/1080845/2022 | 2022-05-25
1724 | KOTCR2 | KOTCR2 |  |  |  | ROTN | Indus | IN-3131449 | R/NN-660049 |  | On Air | 2022-06-04 | KOTCR2 | 4G_FD900_KOTCR2 | 4G_FD2100_KOTCR2 | 4G_TD_KOTCR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206165601 | 2022-06-07 | P/FVC/MDS/1082472/2022 | 2022-06-14 | ST202206165504 | 2022-06-07 | P/FVC/MDS/1082425/2022 | 2022-06-14 |  |  |  |  | ST202206165070 | 2022-06-07 | P/FBW/MDS/1082374/2022 | 2022-06-14
1725 | MGDI31 | MGDI31 |  |  |  | ROTN | Ascend | - |  |  | On Air | 2022-06-04 | MGDI31 | 4G_FD900_MGDI31 | 4G_FD2100_MGDI31 | 4G_TD_MGDI31 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206165599 | 2022-06-07 | P/FVC/MDS/1082471/2022 | 2022-06-14 | ST202206165503 | 2022-06-07 | P/FVC/MDS/1082424/2022 | 2022-06-14 |  |  |  |  | ST202206165069 | 2022-06-07 | P/FBW/MDS/1082373/2022 | 2022-06-14
1726 | VLR238 | VLR238 |  |  |  | ROTN | ATC | TN/VE/AT/23113 | T22TN01295 |  | On Air | 2022-06-06 | VLR238 | 4G_FD900_VLR238 | 4G_FD2100_VLR238 | 4G_TD_VLR238 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206178742 | 2022-06-14 | P/FVC/MDS/1085103/2022 | 2022-06-24 | ST202206178664 | 2022-06-14 | P/FVC/MDS/1085086/2022 | 2022-06-24 | ST202206179363 | 2022-06-14 | P/FVC/MDS/1085118/2022 | 2022-06-24 | ST202206178574 | 2022-06-14 | P/FBW/MDS/1085066/2022 | 2022-06-24
1727 | VLR243 | VLR243 |  |  |  | ROTN | ATC | TN/VE/AT/23114 | T22TN01296 |  | On Air | 2022-06-02 | VLR243 | 4G_FD900_VLR243 | 4G_FD2100_VLR243 | 4G_TD_VLR243 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205139103 | 2022-05-17 | P/FVC/MDS/1081038/2022 | 2022-05-25 | ST202205138709 | 2022-05-17 | P/FVC/MDS/1080924/2022 | 2022-05-25 |  |  |  |  | ST202205138096 | 2022-05-16 | P/FBW/MDS/1080882/2022 | 2022-05-25
1728 | KMBM18 | KMBM18 |  |  |  | ROTN | Indus | - | R/NN-653782 |  | SR | 2022-06-01 | KMBM18 | 4G_FD900_KMBM18 | 4G_FD2100_KMBM18 | 4G_TD_KMBM18 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206165559 | 2022-06-07 | P/FVC/MDS/1082463/2022 | 2022-06-14 | ST202206165468 | 2022-06-07 | P/FVC/MDS/1082415/2022 | 2022-06-14 |  |  |  |  | ST202206165027 | 2022-06-07 | P/FBW/MDS/1082364/2022 | 2022-06-14
1729 | CBE932 | CBE932 |  |  |  | ROTN | Indus | - | R/NN-653798 |  | On Air | 2022-06-01 | CBE932 | 4G_FD900_CBE932 | 4G_FD2100_CBE932 | 4G_TD_CBE932 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206165560 | 2022-06-07 | P/FVC/MDS/1082464/2022 | 2022-06-14 | ST202206165469 | 2022-06-07 | P/FVC/MDS/1082416/2022 | 2022-06-14 |  |  |  |  | ST202206165043 | 2022-06-07 | P/FBW/MDS/1082365/2022 | 2022-06-14
1730 | KRR110 | KRR110 |  |  |  | ROTN | ATC | TN/KU/AT/23163 | T22TN01415 |  | On Air | 2022-06-06 | KRR110 | 4G_FD900_KRR110 | 4G_FD2100_KRR110 | 4G_TD_KRR110 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206178803 | 2022-06-14 | P/FVC/MDS/1085104/2022 | 2022-06-24 | ST202206178665 | 2022-06-14 | P/FVC/MDS/1085087/2022 | 2022-06-24 | ST202206179371 | 2022-06-14 | P/FVC/MDS/1085119/2022 | 2022-06-24 | ST202206178591 | 2022-06-14 | P/FBW/MDS/1085067/2022 | 2022-06-24
1731 | PACHK2 | PACHK2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-06-04 | PACHK2 | 4G_FD900_PACHK2 | 4G_FD2100_PACHK2 | 4G_TD_PACHK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206165595 | 2022-06-07 | P/FVC/MDS/1082469/2022 | 2022-06-14 | ST202206165493 | 2022-06-07 | P/FVC/MDS/1082422/2022 | 2022-06-14 |  |  |  |  | ST202206165060 | 2022-06-07 | P/FBW/MDS/1082371/2022 | 2022-06-14
1732 | VENCD6 | VENCD6 |  |  |  | ROTN | Indus | IN-3134708 | R/NN-659649 |  |  | 2022-06-02 | VENCD6 | 4G_FD900_VENCD6 | 4G_FD2100_VENCD6 | 4G_TD_VENCD6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206165551 | 2022-06-07 | P/FVC/MDS/1082461/2022 | 2022-06-14 | ST202206165164 | 2022-06-07 | P/FVC/MDS/1082413/2022 | 2022-06-14 | ST202206165649 | 2022-06-07 | P/FVC/MDS/1082497/2022 | 2022-06-14 | ST202206164317 | 2022-06-07 | P/FBW/MDS/1082362/2022 | 2022-06-14
1733 | MDU522 | MDU522 |  |  |  | ROTN | Indus | IN-3134692 | R/NN-658997 |  |  | 2022-05-30 | MDU522 | 4G_FD900_MDU522 | 4G_FD2100_MDU522 | 4G_TD_MDU522 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206156609 | 2022-06-02 | P/FVC/MDS/1082430/2022 | 2022-06-14 | ST202206156418 | 2022-06-02 | P/FVC/MDS/1082380/2022 | 2022-06-14 | ST202206156709 | 2022-06-02 | P/FVC/MDS/1082476/2022 | 2022-06-14 | ST202206156077 | 2022-06-02 | P/FBW/MDS/1082326/2022 | 2022-06-14
1734 | KDCNL2 | KDCNL2 |  |  |  | ROTN | Indus | IN-3135226 | R/NN-660717 |  |  | 2022-06-06 | KDCNL2 | 4G_FD900_KDCNL2 | 4G_FD2100_KDCNL2 | 4G_TD_KDCNL2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206178727 | 2022-06-14 | P/FVC/MDS/1085100/2022 | 2022-06-24 | ST202206178640 | 2022-06-14 | P/FVC/MDS/1085083/2022 | 2022-06-24 | ST202206179351 | 2022-06-14 | P/FVC/MDS/1085115/2022 | 2022-06-24 | ST202206178561 | 2022-06-14 | P/FBW/MDS/1085063/2022 | 2022-06-24
1735 | TNYKR2 | TNYKR2 |  |  |  | ROTN | Indus | IN-3134451 | R/NN-659658 |  |  | 2022-05-30 | TNYKR2 | 4G_FD900_TNYKR2 | 4G_FD2100_TNYKR2 | 4G_TD_TNYKR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206156614 | 2022-06-02 | P/FVC/MDS/1082432/2022 | 2022-06-14 | ST202206156423 | 2022-06-02 | P/FVC/MDS/1082382/2022 | 2022-06-14 | ST202206156714 | 2022-06-02 | P/FVC/MDS/1082478/2022 | 2022-06-14 | ST202206156079 | 2022-06-02 | P/FBW/MDS/1082328/2022 | 2022-06-14
1736 | ACMGM5 | ACMGM5 |  |  |  | ROTN | Indus | IN-3133897 | R/NN-658921 |  |  | 2022-06-06 | ACMGM5 | 4G_FD900_ACMGM5 | 4G_FD2100_ACMGM5 | 4G_TD_ACMGM5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206178726 | 2022-06-14 | P/FVC/MDS/1085099/2022 | 2022-06-24 | ST202206178639 | 2022-06-14 | P/FVC/MDS/1085082/2022 | 2022-06-24 | ST202206179350 | 2022-06-14 | P/FVC/MDS/1085114/2022 | 2022-06-24 | ST202206178560 | 2022-06-14 | P/FBW/MDS/1085062/2022 | 2022-06-24
1737 | CBE956 | CBE956 |  |  |  | ROTN | Indus | IN-3127686 | R/NN-649557 |  |  | 2022-06-09 | CBE956 | 4G_FD900_CBE956 | 4G_FD2100_CBE956 | 4G_TD_CBE956 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206178710 | 2022-06-14 | P/FVC/MDS/1085096/2022 | 2022-06-24 | ST202206172973 | 2022-06-10 | P/FVC/MDS/1085079/2022 | 2022-06-24 | ST202206179342 | 2022-06-14 | P/FVC/MDS/1085111/2022 | 2022-06-24 | ST202206178199 | 2022-06-14 | P/FBW/MDS/1085059/2022 | 2022-06-24
1738 | TNJ363 | TNJ363 |  |  |  | ROTN | Indus | IN-3115214 | R/NN-640089 |  |  | 2022-05-30 | TNJ363 | 4G_FD900_TNJ363 | 4G_FD2100_TNJ363 | 4G_TD_TNJ363 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206156603 | 2022-06-02 | P/FVC/MDS/1082427/2022 | 2022-06-14 | ST202206156193 | 2022-06-02 | P/FVC/MDS/1082377/2022 | 2022-06-14 | ST202206156703 | 2022-06-02 | P/FVC/MDS/1082474/2022 | 2022-06-14 | ST202206156052 | 2022-06-02 | P/FBW/MDS/1082323/2022 | 2022-06-14
1739 | MULNR4 | MULNR4 |  |  |  | ROTN | Indus | IN-3127688 | R/NN-649615 |  |  | 2022-05-31 | MULNR4 | 4G_FD900_MULNR4 | 4G_FD2100_MULNR4 | 4G_TD_MULNR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206156608 | 2022-06-02 | P/FVC/MDS/1082429/2022 | 2022-06-14 | ST202206156195 | 2022-06-02 | P/FVC/MDS/1082379/2022 | 2022-06-14 | ST202206156704 | 2022-06-02 | P/FVC/MDS/1082475/2022 | 2022-06-14 | ST202206156064 | 2022-06-02 | P/FBW/MDS/1082325/2022 | 2022-06-14
1740 | PDY373 | PDY373 |  |  |  | ROTN | Indus | IN-3132107 | R/NN-656008 |  |  | 2022-06-02 | PDY373 | 4G_FD900_PDY373 | 4G_FD2100_PDY373 | 4G_TD_PDY373 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206165533 | 2022-06-07 | P/FVC/MDS/1082452/2022 | 2022-06-14 | ST202206165126 | 2022-06-07 | P/FVC/MDS/1082404/2022 | 2022-06-14 | ST202206165633 | 2022-06-07 | P/FVC/MDS/1082490/2022 | 2022-06-14 | ST202206164290 | 2022-06-07 | P/FBW/MDS/1082353/2022 | 2022-06-14
1741 | SITAR3 | SITAR3 |  |  |  | ROTN | Indus | IN-3132102 | R/NN-655940 |  |  | 2022-05-27 | SITAR3 | 4G_FD900_SITAR3 | 4G_FD2100_SITAR3 | 4G_TD_SITAR3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206156637 | 2022-06-02 | P/FVC/MDS/1082435/2022 | 2022-06-14 | ST202206156430 | 2022-06-02 | P/FVC/MDS/1082385/2022 | 2022-06-14 | ST202206156719 | 2022-06-02 | P/FVC/MDS/1082481/2022 | 2022-06-14 | ST202206156089 | 2022-06-02 | P/FBW/MDS/1082331/2022 | 2022-06-14
1742 | PDY375 | PDY375 |  |  |  | ROTN | Indus | IN-3132111 | R/NN-656175 |  |  | 2022-06-02 | PDY375 | 4G_FD900_PDY375 | 4G_FD2100_PDY375 | 4G_TD_PDY375 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206165525 | 2022-06-07 | P/FVC/MDS/1082451/2022 | 2022-06-14 | ST202206165125 | 2022-06-07 | P/FVC/MDS/1082403/2022 | 2022-06-14 | ST202206165627 | 2022-06-07 | P/FVC/MDS/1082489/2022 | 2022-06-14 | ST202206164284 | 2022-06-07 | P/FBW/MDS/1082352/2022 | 2022-06-14
1743 | PDY376 | PDY376 |  |  |  | ROTN | Indus | IN-3132110 | R/NN-656030 |  |  | 2022-05-23 | PDY376 | 4G_FD900_PDY376 | 4G_FD2100_PDY376 | 4G_TD_PDY376 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206156669 | 2022-06-02 | P/FVC/MDS/1082447/2022 | 2022-06-14 | ST202206156580 | 2022-06-02 | P/FVC/MDS/1082398/2022 | 2022-06-14 | ST202206156725 | 2022-06-02 | P/FVC/MDS/1082485/2022 | 2022-06-14 | ST202206156142 | 2022-06-02 | P/FBW/MDS/1082346/2022 | 2022-06-14
1744 | ODAPT2 | ODAPT2 |  |  |  | ROTN | TVI | ACTNDGL0015 | - |  |  | 2022-06-06 | ODAPT2 | 4G_FD900_ODAPT2 | 4G_FD2100_ODAPT2 | 4G_TD_ODAPT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206178740 | 2022-06-14 | P/FVC/MDS/1085101/2022 | 2022-06-24 | ST202206178641 | 2022-06-14 | P/FVC/MDS/1085084/2022 | 2022-06-24 | ST202206179361 | 2022-06-14 | P/FVC/MDS/1085116/2022 | 2022-06-24 | ST202206178572 | 2022-06-14 | P/FBW/MDS/1085064/2022 | 2022-06-24
1745 | PRODAP | PRODAP |  |  |  | CHN | Airtel |  |  |  | On air | 2021-11-25 | PRODAP | 4G_FD900_PRODAP | 4G_FD2100_PRODAP | 4G_TD_PRODAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202112610817 | 2021-12-10 | P/FVC/MDS/1069073/2021 | 2021-12-17 | ST202112604870 | 2021-12-07 | P/FVC/MDS/1068820/2021 | 2021-12-15 |  |  |  |  | ST202112609184 | 2021-12-09 | P/FBW/MDS/1068784/2021 | 2021-12-15
1746 | BHAR17 | BHAR17 |  |  |  | CHN | Indus | IN-3134676 | R/NN-659339 |  |  | 2022-05-27 | BHAR17 | 4G_FD900_BHAR17 | 4G_FD2100_BHAR17 | 4G_TD_BHAR17 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206156652 | 2022-06-02 | P/FVC/MDS/1082442/2022 | 2022-06-14 | ST202206156564 | 2022-06-02 | P/FVC/MDS/1082392/2022 | 2022-06-14 | ST202206156720 | 2022-06-02 | P/FVC/MDS/1082482/2022 | 2022-06-14 | ST202206156120 | 2022-06-02 | P/FBW/MDS/1082338/2022 | 2022-06-14
1747 | GSTR11 | GSTR11 |  |  |  | CHN | Indus | IN-1007100 | R/RES-510841 |  |  | 2022-06-02 | GSTR11 | 4G_FD900_GSTR11 | 4G_FD2100_GSTR11 | 4G_TD_GSTR11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206165552 | 2022-06-07 | P/FVC/MDS/1082462/2022 | 2022-06-14 | ST202206165165 | 2022-06-07 | P/FVC/MDS/1082414/2022 | 2022-06-14 | ST202206165653 | 2022-06-07 | P/FVC/MDS/1082498/2022 | 2022-06-14 | ST202206164318 | 2022-06-07 | P/FBW/MDS/1082363/2022 | 2022-06-14
1748 | KORU19 | KORU19 |  |  |  | CHN | Indus | IN-3116323 | R/NN-639915 |  |  | 2022-06-02 | KORU19 | 4G_FD900_KORU19 | 4G_FD2100_KORU19 | 4G_TD_KORU19 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206165524 | 2022-06-07 | P/FVC/MDS/1082450/2022 | 2022-06-14 | ST202206165113 | 2022-06-07 | P/FVC/MDS/1082402/2022 | 2022-06-14 | ST202206165626 | 2022-06-07 | P/FVC/MDS/1082488/2022 | 2022-06-14 | ST202206164283 | 2022-06-07 | P/FBW/MDS/1082351/2022 | 2022-06-14
1749 | TAMB20 | TAMB20 |  |  |  | CHN | Indus | IN-3123968 | R/NN-644874 |  |  | 2022-06-02 | TAMB20 | 4G_FD900_TAMB20 | 4G_FD2100_TAMB20 | 4G_TD_TAMB20 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206165523 | 2022-06-07 | P/FVC/MDS/1082449/2022 | 2022-06-14 | ST202206165112 | 2022-06-07 | P/FVC/MDS/1082401/2022 | 2022-06-14 | ST202206165625 | 2022-06-07 | P/FVC/MDS/1082487/2022 | 2022-06-14 | ST202206157373 | 2022-06-03 | P/FBW/MDS/1082350/2022 | 2022-06-14
1750 | CBSRP1 | CBSRP1 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | On Air | 2022-06-16 | CBSRP1 | 4G_FD900_CBSRP1 | 4G_FD2100_CBSRP1 | 4G_TD_CBSRP1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206197693 | 2022-06-24 | P/FVC/MDS/1085760/2022 | 2022-07-05 | ST202206196188 | 2022-06-23 | P/FVC/MDS/1085726/2022 | 2022-07-05 |  |  |  |  | ST202206196439 | 2022-06-23 | P/FBW/MDS/1085688/2022 | 2022-07-05
1751 | NGL093 | NGL93 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22739 | T21TN09764 |  |  | 2022-06-24 | NGL093 | 4G_FD900_NGL093 | 4G_FD2100_NGL093 | 4G_TD_NGL093 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226080 | 2022-07-07 | P/FVC/MDS/1088003/2022 | 2022-07-18 | ST202207224982 | 2022-07-06 | P/FVC/MDS/1087896/2022 | 2022-07-18 |  |  |  |  | ST202207222837 | 2022-07-06 | P/FBW/MDS/1087811/2022 | 2022-07-18
1752 | CHPT53 | CHPT53 | Kancheepuram | Chennai |  | ROTN | TVI | - | - |  | SRB(Surrender) | 2022-06-18 | CHPT53 | 4G_FD900_CHPT53 | 4G_FD2100_CHPT53 | 4G_TD_CHPT53 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206197992 | 2022-06-24 | P/FVC/MDS/1085771/2022 | 2022-07-05 | ST202206196252 | 2022-06-23 | P/FVC/MDS/1085737/2022 | 2022-07-05 |  |  |  |  | ST202206196523 | 2022-06-23 | P/FBW/MDS/1085699/2022 | 2022-07-05
1753 | GUDA03 | GUDA3 | Theni | Madurai |  | ROTN | Indus | IN-3126634 | R/NN-648640 |  |  | 2022-06-16 | GUDA03 | 4G_FD900_GUDA03 | 4G_FD2100_GUDA03 | 4G_TD_GUDA03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206197719 | 2022-06-24 | P/FVC/MDS/1085762/2022 | 2022-07-05 | ST202206196190 | 2022-06-23 | P/FVC/MDS/1085728/2022 | 2022-07-05 |  |  |  |  | ST202206196441 | 2022-06-23 | P/FBW/MDS/1085690/2022 | 2022-07-05
1754 | EZDSM7 | EZDSM7 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/23243 | T20TN06527 |  | SO | 2022-06-18 | EZDSM7 | 4G_FD900_EZDSM7 | 4G_FD2100_EZDSM7 | 4G_TD_EZDSM7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206198057 | 2022-06-24 | P/FVC/MDS/1085783/2022 | 2022-07-05 | ST202206196370 | 2022-06-23 | P/FVC/MDS/1085749/2022 | 2022-07-05 |  |  |  |  | ST202206196753 | 2022-06-23 | P/FBW/MDS/1085711/2022 | 2022-07-05
1755 | VILVNC | VILVNC | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22691 | T21TN08794 |  | SO | 2022-06-24 | VILVNC | 4G_FD900_VILVNC | 4G_FD2100_VILVNC | 4G_TD_VILVNC | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226052 | 2022-07-07 | P/FVC/MDS/1088000/2022 | 2022-07-18 | ST202207224977 | 2022-07-06 | P/FVC/MDS/1087893/2022 | 2022-07-18 |  |  |  |  | ST202207222821 | 2022-07-06 | P/FBW/MDS/1087808/2022 | 2022-07-18
1756 | VALLV1 | VALLV1 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3138410 | R/NN-667006 |  | SO | 2022-07-05 | VALLV1 | 4G_FD900_VALLV1 | 4G_FD2100_VALLV1 | 4G_TD_VALLV1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106363268 | 2021-06-26 | P/FVC/MDS/1050128/2021 | 2021-08-09 | ST202207265216 | 2022-07-18 | P/FVC/MDS/1088747/2022 | 2022-07-25 |  |  |  |  | ST202207247207 | 2022-07-12 | P/FBW/MDS/1088586/2022 | 2022-07-25
1757 | MELPL1 | MELPL1 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3138414 | R/NN-667010 |  |  | 2022-07-05 | MELPL1 | 4G_FD900_MELPL1 | 4G_FD2100_MELPL1 | 4G_TD_MELPL1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107371981 | 2021-07-03 | P/FVC/MDS/1051635/2021 | 2021-08-14 | ST202107393905 | 2021-07-23 | P/FVC/MDS/1055991/2021 | 2021-09-06 | ST202107378045 | 2021-07-08 | P/FVC/MDS/1056093/2021 | 2021-09-07 | ST202107380628 | 2021-07-10 | P/FBW/MDS/1057196/2021 | 2021-09-09
1758 | SIRUK3 | SIRUK3 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-SPRM-ENB-0051 | SR-TN000928 |  | On Air | 2022-06-28 | SIRUK3 | 4G_FD900_SIRUK3 | 4G_FD2100_SIRUK3 | 4G_TD_SIRUK3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202205130266 | 2022-05-07 | P/FVC/MDS/1080428/2022 | 2022-05-20 | ST202205130226 | 2022-05-07 | P/FVC/MDS/1080400/2022 | 2022-05-20 |  |  |  |  | ST202205130212 | 2022-05-07 | P/FBW/MDS/1079897/2022 | 2022-05-20
1759 | PKT228 | PKT228 | Tirunelveli | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-06-28 | PKT228 | 4G_FD900_PKT228 | 4G_FD2100_PKT228 | 4G_TD_PKT228 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210570560 | 2022-10-14 | P/FVC/MDS/1113239/2022 | 2022-10-20 | ST202210574048 | 2022-10-14 | P/FVC/MDS/1113307/2022 | 2022-10-20 |  |  |  |  | ST202210559754 | 2022-10-12 | P/FBW/MDS/1114044/2022 | 2022-10-30
1760 | PKT219 | PKT219 | Tirunelveli | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-06-13 | PKT219 | 4G_FD900_PKT219 | 4G_FD2100_PKT219 | 4G_TD_PKT219 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206179110 | 2022-06-14 | P/FVC/MDS/1085109/2022 | 2022-06-24 | ST202206178954 | 2022-06-14 | P/FVC/MDS/1085092/2022 | 2022-06-24 |  |  |  |  | ST202206179003 | 2022-06-14 | P/FBW/MDS/1085072/2022 | 2022-06-24
1761 | CBE921 | CBE921 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/23135 | T22TN01387 |  | On Air | 2022-06-18 | CBE921 | 4G_FD900_CBE921 | 4G_FD2100_CBE921 | 4G_TD_CBE921 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206198024 | 2022-06-24 | P/FVC/MDS/1085778/2022 | 2022-07-05 | ST202206196341 | 2022-06-23 | P/FVC/MDS/1085744/2022 | 2022-07-05 |  |  |  |  | ST202206196562 | 2022-06-23 | P/FBW/MDS/1085706/2022 | 2022-07-05
1762 | DGL119 | DGL119 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23145 | T22TN01397 |  | On Air | 2022-06-24 | DGL119 | 4G_FD900_DGL119 | 4G_FD2100_DGL119 | 4G_TD_DGL119 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226121 | 2022-07-07 | P/FVC/MDS/1088008/2022 | 2022-07-18 | ST202207224987 | 2022-07-06 | P/FVC/MDS/1087901/2022 | 2022-07-18 |  |  |  |  | ST202207223753 | 2022-07-06 | P/FBW/MDS/1087816/2022 | 2022-07-18
1763 | PKLM16 | PKLM16 | Theni | Madurai |  | ROTN | Indus | IN-3130650 | R/NN-654475 |  | On Air | 2022-06-28 | PKLM16 | 4G_FD900_PKLM16 | 4G_FD2100_PKLM16 | 4G_TD_PKLM16 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361078 | 2022-08-28 | P/FVC/MDS/1094685/2022 | 2022-09-07 | ST202208364633 | 2022-08-29 | P/FVC/MDS/1094750/2022 | 2022-09-07 |  |  |  |  | ST202208355560 | 2022-08-26 | P/FBW/MDS/1094620/2022 | 2022-09-07
1764 | ALIKP2 | ALIKP2 | Tiruppur | Coimbatore |  | ROTN | ATC | TN/TI/AT/23165 | T22TN01417 |  | On Air | 2022-06-18 | ALIKP2 | 4G_FD900_ALIKP2 | 4G_FD2100_ALIKP2 | 4G_TD_ALIKP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206198023 | 2022-06-24 | P/FVC/MDS/1085777/2022 | 2022-07-05 | ST202206196340 | 2022-06-23 | P/FVC/MDS/1085743/2022 | 2022-07-05 |  |  |  |  | ST202206196552 | 2022-06-23 | P/FBW/MDS/1085705/2022 | 2022-07-05
1765 | MACNR3 | MACNR3 | Tiruchirappalli | Trichy |  | ROTN | ATC | TN/TC/AT/23246 | - |  | On Air | 2022-07-05 | MACNR3 | 4G_FD900_MACNR3 | 4G_FD2100_MACNR3 | 4G_TD_MACNR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207251983 | 2022-07-13 | P/FVC/MDS/1088648/2022 | 2022-07-25 | ST202207254677 | 2022-07-14 | P/FVC/MDS/1088702/2022 | 2022-07-25 |  |  |  |  | ST202207247245 | 2022-07-12 | P/FBW/MDS/1088591/2022 | 2022-07-25
1766 | SVGI30 | SVGI30 | Sivaganga | Madurai |  | ROTN | Indus | IN-3137108 | R/NN-664999 |  | On Air | 2022-06-28 | SVGI30 | 4G_FD900_SVGI30 | 4G_FD2100_SVGI30 | 4G_TD_SVGI30 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207227204 | 2022-07-07 | P/FVC/MDS/1088044/2022 | 2022-07-18 | ST202207225030 | 2022-07-06 | P/FVC/MDS/1087937/2022 | 2022-07-18 |  |  |  |  | ST202207224060 | 2022-07-06 | P/FBW/MDS/1087853/2022 | 2022-07-18
1767 | PULGD2 | PULGD2 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/23229 | T22TN02941 |  | On Air | 2022-06-24 | PULGD2 | 4G_FD900_PULGD2 | 4G_FD2100_PULGD2 | 4G_TD_PULGD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226033 | 2022-07-07 | P/FVC/MDS/1087999/2022 | 2022-07-18 | ST202207224976 | 2022-07-06 | P/FVC/MDS/1087892/2022 | 2022-07-18 |  |  |  |  | ST202207222802 | 2022-07-06 | P/FBW/MDS/1087807/2022 | 2022-07-18
1768 | TENI39 | TENI39 | Theni | Madurai |  | ROTN | ATC | TN/TH/AT/23230 | T22TN02942 |  | On Air | 2022-06-24 | TENI39 | 4G_FD900_TENI39 | 4G_FD2100_TENI39 | 4G_TD_TENI39 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226099 | 2022-07-07 | P/FVC/MDS/1088007/2022 | 2022-07-18 | ST202207224986 | 2022-07-06 | P/FVC/MDS/1087900/2022 | 2022-07-18 |  |  |  |  | ST202207223752 | 2022-07-06 | P/FBW/MDS/1087815/2022 | 2022-07-18
1769 | PKLM17 | PKLM17 | Theni | Madurai |  | ROTN | ATC | TN/TH/AT/23231 | T22TN02943 |  | On Air | 2022-06-18 | PKLM17 | 4G_FD900_PKLM17 | 4G_FD2100_PKLM17 | 4G_TD_PKLM17 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206198025 | 2022-06-24 | P/FVC/MDS/1085779/2022 | 2022-07-05 | ST202206196354 | 2022-06-23 | P/FVC/MDS/1085745/2022 | 2022-07-05 |  |  |  |  | ST202206196563 | 2022-06-23 | P/FBW/MDS/1085707/2022 | 2022-07-05
1770 | SVKI79 | SVKI79 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/23233 | T22TN02945 |  | On Air | 2022-06-24 | SVKI79 | 4G_FD900_SVKI79 | 4G_FD2100_SVKI79 | 4G_TD_SVKI79 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226122 | 2022-07-07 | P/FVC/MDS/1088009/2022 | 2022-07-18 | ST202207224988 | 2022-07-06 | P/FVC/MDS/1087902/2022 | 2022-07-18 |  |  |  |  | ST202207223774 | 2022-07-06 | P/FBW/MDS/1087817/2022 | 2022-07-18
1771 | MDTI50 | MDTI50 |  |  |  | ROTN | Indus | IN-3123168 | R/RES-510831 |  |  | 2022-07-07 | MDTI50 | 4G_FD900_MDTI50 | 4G_FD2100_MDTI50 | 4G_TD_MDTI50 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252838 | 2022-07-13 | P/FVC/MDS/1088658/2022 | 2022-07-25 | ST202207254727 | 2022-07-14 | P/FVC/MDS/1088712/2022 | 2022-07-25 | ST202207254102 | 2022-07-13 | P/FVC/MDS/1088756/2022 | 2022-07-25 | ST202207247342 | 2022-07-12 | P/FBW/MDS/1088601/2022 | 2022-07-25
1772 | CBE881 | CBE881 |  |  |  | ROTN | Indus | IN-3115141 | R/RES-510842 |  |  | 2022-07-07 | CBE881 | 4G_FD900_CBE881 | 4G_FD2100_CBE881 | 4G_TD_CBE881 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252827 | 2022-07-13 | P/FVC/MDS/1088657/2022 | 2022-07-25 | ST202207254726 | 2022-07-14 | P/FVC/MDS/1088711/2022 | 2022-07-25 | ST202207254100 | 2022-07-13 | P/FVC/MDS/1088755/2022 | 2022-07-25 | ST202207247322 | 2022-07-12 | P/FBW/MDS/1088600/2022 | 2022-07-25
1773 | PLGA10 | PLGA10 |  |  |  | ROTN | Indus | IN-3133804 | R/NN-658791 |  |  | 2022-06-13 | PLGA10 | 4G_FD900_PLGA10 | 4G_FD2100_PLGA10 | 4G_TD_PLGA10 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206179097 | 2022-06-14 | P/FVC/MDS/1085107/2022 | 2022-06-24 | ST202206178939 | 2022-06-14 | P/FVC/MDS/1085090/2022 | 2022-06-24 | ST202206179373 | 2022-06-14 | P/FVC/MDS/1085121/2022 | 2022-06-24 | ST202206179001 | 2022-06-14 | P/FBW/MDS/1085070/2022 | 2022-06-24
1774 | SEMI11 | SEMI11 |  |  |  | ROTN | Indus | IN-3137928 | R/NN-666404 |  |  | 2022-06-24 | SEMI11 | 4G_FD900_SEMI11 | 4G_FD2100_SEMI11 | 4G_TD_SEMI11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226053 | 2022-07-07 | P/FVC/MDS/1088001/2022 | 2022-07-18 | ST202207224978 | 2022-07-06 | P/FVC/MDS/1087894/2022 | 2022-07-18 | ST202207228392 | 2022-07-07 | P/FVC/MDS/1087957/2022 | 2022-07-18 | ST202207222822 | 2022-07-06 | P/FBW/MDS/1087809/2022 | 2022-07-18
1775 | MDTI46 | MDTI46 |  |  |  | ROTN | Indus | IN-3133836 | R/NN-658827 |  |  | 2022-06-28 | MDTI46 | 4G_FD900_MDTI46 | 4G_FD2100_MDTI46 | 4G_TD_MDTI46 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226743 | 2022-07-07 | P/FVC/MDS/1088030/2022 | 2022-07-18 | ST202207225011 | 2022-07-06 | P/FVC/MDS/1087922/2022 | 2022-07-18 | ST202207228539 | 2022-07-07 | P/FVC/MDS/1087970/2022 | 2022-07-18 | ST202207223948 | 2022-07-06 | P/FBW/MDS/1087838/2022 | 2022-07-18
1776 | VDATL2 | VDATL2 |  |  |  | ROTN | Indus | IN-3133857 | R/NN-658862 |  |  | 2022-06-20 | VDATL2 | 4G_FD900_VDATL2 | 4G_FD2100_VDATL2 | 4G_TD_VDATL2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206198040 | 2022-06-24 | P/FVC/MDS/1085781/2022 | 2022-07-05 | ST202206196363 | 2022-06-23 | P/FVC/MDS/1085747/2022 | 2022-07-05 | ST202206200658 | 2022-06-25 | P/FVC/MDS/1086732/2022 | 2022-07-07 | ST202206196576 | 2022-06-23 | P/FBW/MDS/1085709/2022 | 2022-07-05
1777 | PRVSI2 | PRVSI2 |  |  |  | ROTN | Indus | IN-3134449 | R/NN-659657 |  |  | 2022-06-18 | PRVSI2 | 4G_FD900_PRVSI2 | 4G_FD2100_PRVSI2 | 4G_TD_PRVSI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206197790 | 2022-06-24 | P/FVC/MDS/1085769/2022 | 2022-07-05 | ST202206196242 | 2022-06-23 | P/FVC/MDS/1085735/2022 | 2022-07-05 | ST202206200644 | 2022-06-25 | P/FVC/MDS/1086726/2022 | 2022-07-07 | ST202206196508 | 2022-06-23 | P/FBW/MDS/1085697/2022 | 2022-07-05
1778 | SLM394 | SLM394 |  |  |  | ROTN | Indus | IN-3133899 | R/NN-658925 |  |  | 2022-07-07 | SLM394 | 4G_FD900_SLM394 | 4G_FD2100_SLM394 | 4G_TD_SLM394 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254008 | 2022-07-13 | P/FVC/MDS/1088672/2022 | 2022-07-25 | ST202207254863 | 2022-07-14 | P/FVC/MDS/1088727/2022 | 2022-07-25 | ST202207254116 | 2022-07-13 | P/FVC/MDS/1088770/2022 | 2022-07-25 | ST202207247966 | 2022-07-12 | P/FBW/MDS/1088615/2022 | 2022-07-25
1779 | MDU547 | MDU547 |  |  |  | ROTN | Indus | IN-3140688 | R/NN-669568 |  |  | 2022-07-07 | MDU547 | 4G_FD900_MDU547 | 4G_FD2100_MDU547 | 4G_TD_MDU547 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254023 | 2022-07-13 | P/FVC/MDS/1088677/2022 | 2022-07-25 | ST202207254949 | 2022-07-14 | P/FVC/MDS/1088733/2022 | 2022-07-25 | ST202207254122 | 2022-07-13 | P/FVC/MDS/1088776/2022 | 2022-07-25 | ST202207248025 | 2022-07-12 | P/FBW/MDS/1088621/2022 | 2022-07-25
1780 | VLRM63 | VLRM63 |  |  |  | ROTN | Indus | IN-3134690 | R/NN-658926 |  |  | 2022-06-28 | VLRM63 | 4G_FD900_VLRM63 | 4G_FD2100_VLRM63 | 4G_TD_VLRM63 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226760 | 2022-07-07 | P/FVC/MDS/1088031/2022 | 2022-07-18 | ST202207225012 | 2022-07-06 | P/FVC/MDS/1087923/2022 | 2022-07-18 | ST202207228549 | 2022-07-07 | P/FVC/MDS/1087971/2022 | 2022-07-18 | ST202207223949 | 2022-07-06 | P/FBW/MDS/1087839/2022 | 2022-07-18
1781 | KDKL46 | KDKL46 |  |  |  | ROTN | ATC | TN/DI/AT/23081 | - |  |  | 2022-06-28 | KDKL46 | 4G_FD900_KDKL46 | 4G_FD2100_KDKL46 | 4G_TD_KDKL46 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226188 | 2022-07-07 | P/FVC/MDS/1088015/2022 | 2022-07-18 | ST202207224994 | 2022-07-06 | P/FVC/MDS/1087907/2022 | 2022-07-18 |  |  |  |  | ST202207223836 | 2022-07-06 | P/FBW/MDS/1087823/2022 | 2022-07-18
1782 | KLKLU2 | KLKLU2 |  |  |  | ROTN | Indus | IN-3133834 | R/NN-658824 |  |  | 2022-06-28 | KLKLU2 | 4G_FD900_KLKLU2 | 4G_FD2100_KLKLU2 | 4G_TD_KLKLU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226345 | 2022-07-07 | P/FVC/MDS/1088019/2022 | 2022-07-18 | ST202207224998 | 2022-07-06 | P/FVC/MDS/1087911/2022 | 2022-07-18 | ST202212858247 | 2022-12-27 | 0 |  | ST202207223866 | 2022-07-06 | P/FBW/MDS/1087827/2022 | 2022-07-18
1783 | NGL140 | NGL140 |  |  |  | ROTN | Indus | IN-3133788 | R/NN-658790 |  |  | 2022-06-18 | NGL140 | 4G_FD900_NGL140 | 4G_FD2100_NGL140 | 4G_TD_NGL140 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206198011 | 2022-06-24 | P/FVC/MDS/1085774/2022 | 2022-07-05 | ST202206196265 | 2022-06-23 | P/FVC/MDS/1085740/2022 | 2022-07-05 | ST202206200650 | 2022-06-25 | P/FVC/MDS/1086729/2022 | 2022-07-07 | ST202206196535 | 2022-06-23 | P/FBW/MDS/1085702/2022 | 2022-07-05
1784 | PDY371 | PDY371 |  |  |  | ROTN | Indus | IN-3134691 | R/NN-658928 |  |  | 2022-06-28 | PDY371 | 4G_FD900_PDY371 | 4G_FD2100_PDY371 | 4G_TD_PDY371 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226762 | 2022-07-07 | P/FVC/MDS/1088032/2022 | 2022-07-18 | ST202207225013 | 2022-07-06 | P/FVC/MDS/1087924/2022 | 2022-07-18 | ST202207228581 | 2022-07-07 | P/FVC/MDS/1087972/2022 | 2022-07-18 | ST202207223968 | 2022-07-06 | P/FBW/MDS/1087840/2022 | 2022-07-18
1785 | RSPM15 | RSPM15 |  |  |  | ROTN | TVI | - | - |  |  | 2022-06-28 | RSPM15 | 4G_FD900_RSPM15 | 4G_FD2100_RSPM15 | 4G_TD_RSPM15 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226708 | 2022-07-07 | P/FVC/MDS/1088026/2022 | 2022-07-18 | ST202207225006 | 2022-07-06 | P/FVC/MDS/1087918/2022 | 2022-07-18 | ST202207228508 | 2022-07-07 | P/FVC/MDS/1087966/2022 | 2022-07-18 | ST202207223927 | 2022-07-06 | P/FBW/MDS/1087834/2022 | 2022-07-18
1786 | VNDNI3 | VNDNI3 |  |  |  | ROTN | Indus | IN-3133822 | R/NN-658809 |  |  | 2022-06-18 | VNDNI3 | 4G_FD900_VNDNI3 | 4G_FD2100_VNDNI3 | 4G_TD_VNDNI3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206197993 | 2022-06-24 | P/FVC/MDS/1085772/2022 | 2022-07-05 | ST202206196253 | 2022-06-23 | P/FVC/MDS/1085738/2022 | 2022-07-05 | ST202206200645 | 2022-06-25 | P/FVC/MDS/1086727/2022 | 2022-07-07 | ST202206196524 | 2022-06-23 | P/FBW/MDS/1085700/2022 | 2022-07-05
1787 | VYMDU2 | VYMDU2 |  |  |  | ROTN | Indus | IN-3133854 | R/NN-658858 |  |  | 2022-06-18 | VYMDU2 | 4G_FD900_VYMDU2 | 4G_FD2100_VYMDU2 | 4G_TD_VYMDU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206198012 | 2022-06-24 | P/FVC/MDS/1085775/2022 | 2022-07-05 | ST202206196266 | 2022-06-23 | P/FVC/MDS/1085741/2022 | 2022-07-05 | ST202206200651 | 2022-06-25 | P/FVC/MDS/1086730/2022 | 2022-07-07 | ST202206196536 | 2022-06-23 | P/FBW/MDS/1085703/2022 | 2022-07-05
1788 | MANVL2 | MANVL2 |  |  |  | ROTN | Indus | IN-3131828 | R/NN-656071 |  |  | 2022-06-16 | MANVL2 | 4G_FD900_MANVL2 | 4G_FD2100_MANVL2 | 4G_TD_MANVL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442790 | 2022-09-19 | P/FVC/MDS/1098125/2022 | 2022-09-27 | ST202209447441 | 2022-09-19 | P/FVC/MDS/1098212/2022 | 2022-09-27 | ST202209433030 | 2022-09-17 | P/FVC/MDS/1098034/2022 | 2022-09-27 | ST202209448063 | 2022-09-20 | P/FVC/MDS/1097997/2022 | 2022-09-27
1789 | TVML92 | TVML92 |  |  |  | ROTN | Indus | IN-3132128 | R/NN-656161 |  |  | 2022-06-24 | TVML92 | 4G_FD900_TVML92 | 4G_FD2100_TVML92 | 4G_TD_TVML92 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226003 | 2022-07-07 | P/FVC/MDS/1087996/2022 | 2022-07-18 | ST202207224766 | 2022-07-06 | P/FVC/MDS/1087889/2022 | 2022-07-18 | ST202207228363 | 2022-07-07 | P/FVC/MDS/1087955/2022 | 2022-07-18 | ST202207222791 | 2022-07-06 | P/FBW/MDS/1087804/2022 | 2022-07-18
1790 | RMPM51 | RMPM51 |  |  |  | ROTN | Indus | IN-3131824 | R/NN-655307 |  |  | 2022-06-24 | RMPM51 | 4G_FD900_RMPM51 | 4G_FD2100_RMPM51 | 4G_TD_RMPM51 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207225974 | 2022-07-07 | P/FVC/MDS/1087995/2022 | 2022-07-18 | ST202207224761 | 2022-07-06 | P/FVC/MDS/1087888/2022 | 2022-07-18 |  |  |  |  | ST202207222790 | 2022-07-06 | P/FBW/MDS/1087803/2022 | 2022-07-18
1791 | KTVRC2 | KTVRC2 |  |  |  | ROTN | Indus | IN-3136060 | R/NN-662544 |  |  | 2022-06-24 | KTVRC2 | 4G_FD900_KTVRC2 | 4G_FD2100_KTVRC2 | 4G_TD_KTVRC2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226005 | 2022-07-07 | P/FVC/MDS/1087997/2022 | 2022-07-18 | ST202207224778 | 2022-07-06 | P/FVC/MDS/1087890/2022 | 2022-07-18 | ST202207228391 | 2022-07-07 | P/FVC/MDS/1087956/2022 | 2022-07-18 | ST202207222800 | 2022-07-06 | P/FBW/MDS/1087805/2022 | 2022-07-18
1792 | PAKRI3 | PAKRI3 |  |  |  | ROTN | Indus | IN-3136131 | R/NN-662651 |  |  | 2022-07-07 | PAKRI3 | 4G_FD900_PAKRI3 | 4G_FD2100_PAKRI3 | 4G_TD_PAKRI3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207253991 | 2022-07-13 | P/FVC/MDS/1088665/2022 | 2022-07-25 | ST202207254799 | 2022-07-14 | P/FVC/MDS/1088719/2022 | 2022-07-25 | ST202207254108 | 2022-07-13 | P/FVC/MDS/1088762/2022 | 2022-07-25 | ST202207247400 | 2022-07-12 | P/FBW/MDS/1088608/2022 | 2022-07-25
1793 | PLGLM2 | PLGLM2 |  |  |  | ROTN | Indus | IN-3136086 | R/NN-662569 |  |  | 2022-06-28 | PLGLM2 | 4G_FD900_PLGLM2 | 4G_FD2100_PLGLM2 | 4G_TD_PLGLM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207227192 | 2022-07-07 | P/FVC/MDS/1088041/2022 | 2022-07-18 | ST202207225027 | 2022-07-06 | P/FVC/MDS/1087934/2022 | 2022-07-18 | ST202207228603 | 2022-07-07 | P/FVC/MDS/1087974/2022 | 2022-07-18 | ST202207224037 | 2022-07-06 | P/FBW/MDS/1087850/2022 | 2022-07-18
1794 | VGMBD3 | VGMBD3 |  |  |  | ROTN | Indus | IN-3136045 | R/NN-662512 |  |  | 2022-06-28 | VGMBD3 | 4G_FD900_VGMBD3 | 4G_FD2100_VGMBD3 | 4G_TD_VGMBD3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226830 | 2022-07-07 | P/FVC/MDS/1088040/2022 | 2022-07-18 | ST202207225026 | 2022-07-06 | P/FVC/MDS/1087933/2022 | 2022-07-18 |  |  |  |  | ST202207224021 | 2022-07-06 | P/FBW/MDS/1087849/2022 | 2022-07-18
1795 | CENYH2 | CENYH2 |  |  |  | ROTN | Indus | IN-3136150 | R/NN-662709 |  |  | 2022-06-28 | CENYH2 | 4G_FD900_CENYH2 | 4G_FD2100_CENYH2 | 4G_TD_CENYH2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207227193 | 2022-07-07 | P/FVC/MDS/1088042/2022 | 2022-07-18 | ST202207225028 | 2022-07-06 | P/FVC/MDS/1087935/2022 | 2022-07-18 | ST202207228604 | 2022-07-07 | P/FVC/MDS/1087975/2022 | 2022-07-18 | ST202207224038 | 2022-07-06 | P/FBW/MDS/1087851/2022 | 2022-07-18
1796 | RNPT44 | RNPT44 |  |  |  | ROTN | Indus | IN-3136152 | R/NN-662719 |  |  | 2022-07-07 | RNPT44 | 4G_FD900_RNPT44 | 4G_FD2100_RNPT44 | 4G_TD_RNPT44 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 1902-06-18 | ST202208327981 | 2022-08-11 | P/FVC/MDS/1093898/2022 | 2022-08-19 | ST202207254883 | 2022-07-14 | P/FVC/MDS/1088729/2022 | 2022-07-25 | ST202207254118 | 2022-07-13 | P/FVC/MDS/1088772/2022 | 2022-07-25 | ST202207247992 | 2022-07-12 | P/FBW/MDS/1088617/2022 | 2022-07-25
1797 | SRKDU7 | SRKDU7 |  |  |  | ROTN | Indus | IN-3135970 | R/NN-662431 |  |  | 2022-07-07 | SRKDU7 | 4G_FD900_SRKDU7 | 4G_FD2100_SRKDU7 | 4G_TD_SRKDU7 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207253997 | 2022-07-13 | P/FVC/MDS/1088667/2022 | 2022-07-25 | ST202207254813 | 2022-07-14 | P/FVC/MDS/1088721/2022 | 2022-07-25 | ST202207254110 | 2022-07-13 | P/FVC/MDS/1088764/2022 | 2022-07-25 | ST202207247869 | 2022-07-12 | P/FBW/MDS/1088610/2022 | 2022-07-25
1798 | SULGR6 | SULGR6 |  |  |  | ROTN | ATC | TN3048 | - |  |  | 2022-06-24 | SULGR6 | 4G_FD900_SULGR6 | 4G_FD2100_SULGR6 | 4G_TD_SULGR6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207225938 | 2022-07-07 | P/FVC/MDS/1087993/2022 | 2022-07-18 | ST202207224740 | 2022-07-06 | P/FVC/MDS/1087886/2022 | 2022-07-18 | ST202207228361 | 2022-07-07 | P/FVC/MDS/1087953/2022 | 2022-07-18 | ST202207218728 | 2022-07-05 | P/FBW/MDS/1087800/2022 | 2022-07-18
1799 | SARKR2 | SARKR2 |  |  |  | ROTN | Indus | IN-3138568 | R/NN-663151 |  |  | 2022-07-05 | SARKR2 | 4G_FD900_SARKR2 | 4G_FD2100_SARKR2 | 4G_TD_SARKR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252072 | 2022-07-13 | P/FVC/MDS/1088652/2022 | 2022-07-25 | ST202207254702 | 2022-07-14 | P/FVC/MDS/1088706/2022 | 2022-07-25 | ST202207254098 | 2022-07-13 | P/FVC/MDS/1088753/2022 | 2022-07-25 | ST202207247299 | 2022-07-12 | P/FBW/MDS/1088595/2022 | 2022-07-25
1800 | NGVRM2 | NGVRM2 |  |  |  | ROTN | Indus | IN-1070513 | R/RES-511176 |  |  | 2022-07-07 | NGVRM2 | 4G_FD900_NGVRM2 | 4G_FD2100_NGVRM2 | 4G_TD_NGVRM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252862 | 2022-07-13 | P/FVC/MDS/1088663/2022 | 2022-07-25 | ST202207254769 | 2022-07-14 | P/FVC/MDS/1088717/2022 | 2022-07-25 |  |  |  |  | ST202207247375 | 2022-07-12 | P/FBW/MDS/1088606/2022 | 2022-07-25
1801 | VLANR4 | VLANR4 |  |  |  | ROTN | Indus | IN-1030594 | R/RES-511183 |  |  | 2022-07-07 | VLANR4 | 4G_FD900_VLANR4 | 4G_FD2100_VLANR4 | 4G_TD_VLANR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252848 | 2022-07-13 | P/FVC/MDS/1088661/2022 | 2022-07-25 | ST202207254761 | 2022-07-14 | P/FVC/MDS/1088715/2022 | 2022-07-25 | ST202207254105 | 2022-07-13 | P/FVC/MDS/1088759/2022 | 2022-07-25 | ST202207247356 | 2022-07-12 | P/FBW/MDS/1088604/2022 | 2022-07-25
1802 | KGMRM3 | KGMRM3 |  |  |  | ROTN | Indus | IN-3138571 | R/NN-663177 |  |  | 2022-07-07 | KGMRM3 | 4G_FD900_KGMRM3 | 4G_FD2100_KGMRM3 | 4G_TD_KGMRM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207253998 | 2022-07-13 | P/FVC/MDS/1088668/2022 | 2022-07-25 | ST202207254814 | 2022-07-14 | P/FVC/MDS/1088722/2022 | 2022-07-25 | ST202207254111 | 2022-07-13 | P/FVC/MDS/1088765/2022 | 2022-07-25 | ST202207265021 | 2022-07-18 | P/FBW/MDS/1088634/2022 | 2022-07-25
1803 | PRVPM2 | PRVPM2 |  |  |  | ROTN | Indus | IN-3138582 | R/NN-663224 |  |  | 2022-07-07 | PRVPM2 | 4G_FD900_PRVPM2 | 4G_FD2100_PRVPM2 | 4G_TD_PRVPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254009 | 2022-07-13 | P/FVC/MDS/1088673/2022 | 2022-07-25 | ST202207254864 | 2022-07-14 | P/FVC/MDS/1088728/2022 | 2022-07-25 | ST202207254117 | 2022-07-13 | P/FVC/MDS/1088771/2022 | 2022-07-25 | ST202207247968 | 2022-07-12 | P/FBW/MDS/1088616/2022 | 2022-07-25
1804 | KAPPA3 | KAPPA3 |  |  |  | ROTN | Indus | IN-3136300 | R/NN-663226 |  |  | 2022-07-07 | KAPPA3 | 4G_FD900_KAPPA3 | 4G_FD2100_KAPPA3 | 4G_TD_KAPPA3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254003 | 2022-07-13 | P/FVC/MDS/1088670/2022 | 2022-07-25 | ST202207254831 | 2022-07-14 | P/FVC/MDS/1088724/2022 | 2022-07-25 | ST202207254113 | 2022-07-13 | P/FVC/MDS/1088767/2022 | 2022-07-25 | ST202207247921 | 2022-07-12 | P/FBW/MDS/1088612/2022 | 2022-07-25
1805 | MRVNR4 | MRVNR4 |  |  |  | ROTN | Indus | IN-1070512 | R/RES-511180 |  |  | 2022-07-07 | MRVNR4 | 4G_FD900_MRVNR4 | 4G_FD2100_MRVNR4 | 4G_TD_MRVNR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252859 | 2022-07-13 | P/FVC/MDS/1088662/2022 | 2022-07-25 | ST202207254762 | 2022-07-14 | P/FVC/MDS/1088716/2022 | 2022-07-25 | ST202207254106 | 2022-07-13 | P/FVC/MDS/1088760/2022 | 2022-07-25 | ST202207247374 | 2022-07-12 | P/FBW/MDS/1088605/2022 | 2022-07-25
1806 | PDLUR3 | PDLUR3 |  |  |  | ROTN | Indus | IN-1030502 | R/RES-511181 |  |  | 2022-07-07 | PDLUR3 | 4G_FD900_PDLUR3 | 4G_FD2100_PDLUR3 | 4G_TD_PDLUR3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252847 | 2022-07-13 | P/FVC/MDS/1088660/2022 | 2022-07-25 | ST202207254739 | 2022-07-14 | P/FVC/MDS/1088714/2022 | 2022-07-25 | ST202207254104 | 2022-07-13 | P/FVC/MDS/1088758/2022 | 2022-07-25 | ST202207247355 | 2022-07-12 | P/FBW/MDS/1088603/2022 | 2022-07-25
1807 | REDUR2 | REDUR2 |  |  |  | ROTN | Indus | IN-3138607 | R/NN-664147 |  |  | 2022-07-07 | REDUR2 | 4G_FD900_REDUR2 | 4G_FD2100_REDUR2 | 4G_TD_REDUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254002 | 2022-07-13 | P/FVC/MDS/1088669/2022 | 2022-07-25 | ST202207254830 | 2022-07-14 | P/FVC/MDS/1088723/2022 | 2022-07-25 | ST202207254112 | 2022-07-13 | P/FVC/MDS/1088766/2022 | 2022-07-25 | ST202207247870 | 2022-07-12 | P/FBW/MDS/1088611/2022 | 2022-07-25
1808 | EGMO16 | EGMO13 |  |  |  | CHN | ATC | TN/CH/TT/13100 | - |  |  | 2022-06-24 | EGMO16 | 4G_FD900_EGMO16 | 4G_FD2100_EGMO16 | 4G_TD_EGMO16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207225973 | 2022-07-07 | P/FVC/MDS/1087994/2022 | 2022-07-18 | ST202207224760 | 2022-07-06 | P/FVC/MDS/1087887/2022 | 2022-07-18 | ST202207228362 | 2022-07-07 | P/FVC/MDS/1087954/2022 | 2022-07-18 | ST202207222789 | 2022-07-06 | P/FBW/MDS/1087802/2022 | 2022-07-18
1809 | KATP25 | KATP25 |  |  |  | CHN | Indus | IN-3134680 | R/NN-659347 |  |  | 2022-07-05 | KATP25 | 4G_FD900_KATP25 | 4G_FD2100_KATP25 | 4G_TD_KATP25 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207233582 | 2022-07-08 | P/FVC/MDS/1088641/2022 | 2022-07-25 | ST202207254649 | 2022-07-14 | P/FVC/MDS/1088696/2022 | 2022-07-25 | ST202207254097 | 2022-07-13 | P/FVC/MDS/1088752/2022 | 2022-07-25 | ST202207247195 | 2022-07-12 | P/FBW/MDS/1088584/2022 | 2022-07-25
1810 | ANNA34 | ANNA34 |  |  |  | CHN | Indus | IN-3134201 | R/NN-659332 |  |  | 2022-07-07 | ANNA34 | 4G_FD900_ANNA34 | 4G_FD2100_ANNA34 | 4G_TD_ANNA34 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252839 | 2022-07-13 | P/FVC/MDS/1088659/2022 | 2022-07-25 | ST202207254738 | 2022-07-14 | P/FVC/MDS/1088713/2022 | 2022-07-25 | ST202207254103 | 2022-07-13 | P/FVC/MDS/1088757/2022 | 2022-07-25 | ST202207247343 | 2022-07-12 | P/FBW/MDS/1088602/2022 | 2022-07-25
1811 | MYLA20 | MYLA20 |  |  |  | CHN | Indus | IN-3134899 | R/NN-659385 |  |  | 2022-06-20 | MYLA20 | 4G_FD900_MYLA20 | 4G_FD2100_MYLA20 | 4G_TD_MYLA20 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202206198041 | 2022-06-24 | P/FVC/MDS/1085782/2022 | 2022-07-05 | ST202206196364 | 2022-06-23 | P/FVC/MDS/1085748/2022 | 2022-07-05 | ST202206200659 | 2022-06-25 | P/FVC/MDS/1086733/2022 | 2022-07-07 | ST202206196577 | 2022-06-23 | P/FBW/MDS/1085710/2022 | 2022-07-05
1812 | GOPAL6 | GOPAL6 |  |  |  | CHN | Indus | IN-3134637 | R/NN-659793 |  |  | 2022-06-28 | GOPAL6 | 4G_FD900_GOPAL6 | 4G_FD2100_GOPAL6 | 4G_TD_GOPAL6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207226347 | 2022-07-07 | P/FVC/MDS/1088020/2022 | 2022-07-18 | ST202207225000 | 2022-07-06 | P/FVC/MDS/1087912/2022 | 2022-07-18 | ST202207228430 | 2022-07-07 | P/FVC/MDS/1087961/2022 | 2022-07-18 | ST202207223881 | 2022-07-06 | P/FBW/MDS/1087828/2022 | 2022-07-18
1813 | KLPVR6 | KLPVR6 |  |  |  | ROTN | Indus | IN-3138433 | R/NN-667048 |  |  | 2022-07-07 | KLPVR6 | 4G_FD900_KLPVR6 | 4G_FD2100_KLPVR6 | 4G_TD_KLPVR6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254016 | 2022-07-13 | P/FVC/MDS/1088674/2022 | 2022-07-25 | ST202207254884 | 2022-07-14 | P/FVC/MDS/1088730/2022 | 2022-07-25 | ST202207254119 | 2022-07-13 | P/FVC/MDS/1088773/2022 | 2022-07-25 | ST202207247994 | 2022-07-12 | P/FBW/MDS/1088618/2022 | 2022-07-25
1814 | MNYPT2 | MNYPT2 |  |  |  | ROTN | Indus | IN-3138348 | R/NN-666930 |  |  | 2022-07-07 | MNYPT2 | 4G_FD900_MNYPT2 | 4G_FD2100_MNYPT2 | 4G_TD_MNYPT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254026 | 2022-07-13 | P/FVC/MDS/1088679/2022 | 2022-07-25 | ST202207254960 | 2022-07-14 | P/FVC/MDS/1088735/2022 | 2022-07-25 | ST202207254124 | 2022-07-13 | P/FVC/MDS/1088778/2022 | 2022-07-25 | ST202207248045 | 2022-07-12 | P/FBW/MDS/1088623/2022 | 2022-07-25
1815 | THIR15 | THIR15 |  |  |  | CHN | ATC | TN/CH/TT/13021 | - |  |  | 2022-07-07 | THIR15 | 4G_FD900_THIR15 | 4G_FD2100_THIR15 | 4G_TD_THIR15 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252863 | 2022-07-13 | P/FVC/MDS/1088664/2022 | 2022-07-25 | ST202207254770 | 2022-07-14 | P/FVC/MDS/1088718/2022 | 2022-07-25 | ST202207254107 | 2022-07-13 | P/FVC/MDS/1088761/2022 | 2022-07-25 | ST202207247399 | 2022-07-12 | P/FBW/MDS/1088607/2022 | 2022-07-25
1816 | TKPYM2 | TKPYM2 |  |  |  | ROTN | Indus | IN-3138581 | R/NN-667240 |  |  | 2022-07-07 | TKPYM2 | 4G_FD900_TKPYM2 | 4G_FD2100_TKPYM2 | 4G_TD_TKPYM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254017 | 2022-07-13 | P/FVC/MDS/1088675/2022 | 2022-07-25 | ST202207254937 | 2022-07-14 | P/FVC/MDS/1088731/2022 | 2022-07-25 | ST202207254120 | 2022-07-13 | P/FVC/MDS/1088774/2022 | 2022-07-25 | ST202207247995 | 2022-07-12 | P/FBW/MDS/1088619/2022 | 2022-07-25
1817 | PDY391 | PDY391 |  |  |  | ROTN | Indus | IN-3139956 | R/NN-667981 |  |  | 2022-07-07 | PDY391 | 4G_FD900_PDY391 | 4G_FD2100_PDY391 | 4G_TD_PDY391 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254004 | 2022-07-13 | P/FVC/MDS/1088671/2022 | 2022-07-25 | ST202207254846 | 2022-07-14 | P/FVC/MDS/1088726/2022 | 2022-07-25 | ST202207254115 | 2022-07-13 | P/FVC/MDS/1088769/2022 | 2022-07-25 | ST202207247935 | 2022-07-12 | P/FBW/MDS/1088614/2022 | 2022-07-25
1818 | VAND31 | VAND31 |  |  |  | CHN | Indus | IN-3138703 | R/NN-666793 |  |  | 2022-07-07 | VAND31 | 4G_FD900_VAND31 | 4G_FD2100_VAND31 | 4G_TD_VAND31 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207253992 | 2022-07-13 | P/FVC/MDS/1088666/2022 | 2022-07-25 | ST202207254800 | 2022-07-14 | P/FVC/MDS/1088720/2022 | 2022-07-25 | ST202207254109 | 2022-07-13 | P/FVC/MDS/1088763/2022 | 2022-07-25 | ST202207247867 | 2022-07-12 | P/FBW/MDS/1088609/2022 | 2022-07-25
1819 | KDMDI6 | KDMDI6 |  |  |  | ROTN | Indus | IN-3139183 | R/NN-666721 |  |  | 2022-06-28 | KDMDI6 | 4G_FD900_KDMDI6 | 4G_FD2100_KDMDI6 | 4G_TD_KDMDI6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207227205 | 2022-07-07 | P/FVC/MDS/1088045/2022 | 2022-07-18 | ST202207225032 | 2022-07-06 | P/FVC/MDS/1087938/2022 | 2022-07-18 | ST202207228605 | 2022-07-07 | P/FVC/MDS/1087976/2022 | 2022-07-18 | ST202207224061 | 2022-07-06 | P/FBW/MDS/1087854/2022 | 2022-07-18
1820 | DVMPT3 | DVMPT3 |  |  |  | ROTN | Indus | IN-3138624 | R/NN-666739 |  |  | 2022-06-28 | DVMPT3 | 4G_FD900_DVMPT3 | 4G_FD2100_DVMPT3 | 4G_TD_DVMPT3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207227206 | 2022-07-07 | P/FVC/MDS/1088046/2022 | 2022-07-18 | ST202207225033 | 2022-07-06 | P/FVC/MDS/1087939/2022 | 2022-07-18 | ST202207228630 | 2022-07-07 | P/FVC/MDS/1087977/2022 | 2022-07-18 | ST202207224062 | 2022-07-06 | P/FBW/MDS/1087855/2022 | 2022-07-18
1821 | PATT30 | PATT30 |  |  |  | CHN | Indus | IN-3138219 | R/NN-666653 |  |  | 2022-07-07 | PATT30 | 4G_FD900_PATT30 | 4G_FD2100_PATT30 | 4G_TD_PATT30 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 1902-06-18 | ST202208327992 | 2022-08-11 | P/FVC/MDS/1093899/2022 | 2022-08-19 | ST202207254845 | 2022-07-14 | P/FVC/MDS/1088725/2022 | 2022-07-25 | ST202207254114 | 2022-07-13 | P/FVC/MDS/1088768/2022 | 2022-07-25 | ST202207247922 | 2022-07-12 | P/FBW/MDS/1088613/2022 | 2022-07-25
1822 | SLM421 | SLM421 |  |  |  | ROTN | Indus | IN-3139957 | R/NN-667999 |  |  | 2022-07-05 | SLM421 | 4G_FD900_SLM421 | 4G_FD2100_SLM421 | 4G_TD_SLM421 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207252073 | 2022-07-13 | P/FVC/MDS/1088653/2022 | 2022-07-25 | ST202207254707 | 2022-07-14 | P/FVC/MDS/1088707/2022 | 2022-07-25 | ST202207254099 | 2022-07-13 | P/FVC/MDS/1088754/2022 | 2022-07-25 | ST202207247300 | 2022-07-12 | P/FBW/MDS/1088596/2022 | 2022-07-25
1823 | JAMU01 | JAMU01 |  |  |  | CHN | Indus | IN-3133270 | R/NN-658103 |  | On air | 2022-06-13 | JAMU01 | 4G_FD900_JAMU01 | 4G_FD2100_JAMU01 | 4G_TD_JAMU01 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206178806 | 2022-06-14 | P/FVC/MDS/1085106/2022 | 2022-06-24 | ST202206178938 | 2022-06-14 | P/FVC/MDS/1085089/2022 | 2022-06-24 |  |  |  |  | ST202206178593 | 2022-06-14 | P/FBW/MDS/1085069/2022 | 2022-06-24
1824 | REDH41 | REDH41 |  |  |  | CHN | Indus | IN-3133339 | R/NN-658217 |  |  | 2022-06-28 | REDH41 | 4G_FD900_REDH41 | 4G_FD2100_REDH41 | 4G_TD_REDH41 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226829 | 2022-07-07 | P/FVC/MDS/1088039/2022 | 2022-07-18 | ST202207225023 | 2022-07-06 | P/FVC/MDS/1087932/2022 | 2022-07-18 | ST202106358278 | 2021-06-23 | P/FVC/MDS/1055868/2021 | 2021-09-04 | ST202207224020 | 2022-07-06 | P/FBW/MDS/1087848/2022 | 2022-07-18
1825 | CHOR22 | CHOR22 |  |  |  | CHN | ATC | TN/CH/AT/23100 | - |  | On air | 2022-06-18 | CHOR22 | 4G_FD900_CHOR22 | 4G_FD2100_CHOR22 | 4G_TD_CHOR22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360968 | 2022-08-28 | P/FVC/MDS/1094644/2022 | 2022-09-07 | ST202208364531 | 2022-08-29 | P/FVC/MDS/1094709/2022 | 2022-09-07 |  |  |  |  | ST202208355358 | 2022-08-26 | P/FBW/MDS/1094581/2022 | 2022-09-07
1826 | AVAD33 | AVAD33 |  |  |  | CHN | Ascend | - | - |  | On air | 2022-06-28 | AVAD33 | 4G_FD900_AVAD33 | 4G_FD2100_AVAD33 | 4G_TD_AVAD33 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226763 | 2022-07-07 | P/FVC/MDS/1088033/2022 | 2022-07-18 | ST202207225015 | 2022-07-06 | P/FVC/MDS/1087925/2022 | 2022-07-18 |  |  |  |  | ST202207223969 | 2022-07-06 | P/FBW/MDS/1087841/2022 | 2022-07-18
1827 | GSTRD8 | GSTRD8 |  |  |  | CHN | ATC | TN/CH/AT/23225 | - |  | SRB(Surrender) | 2022-06-28 | GSTRD8 | 4G_FD900_GSTRD8 | 4G_FD2100_GSTRD8 | 4G_TD_GSTRD8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207228187 | 2022-07-07 | P/FVC/MDS/1088047/2022 | 2022-07-18 | ST202207225034 | 2022-07-06 | P/FVC/MDS/1087940/2022 | 2022-07-18 |  |  |  |  | ST202207224084 | 2022-07-06 | P/FBW/MDS/1087856/2022 | 2022-07-18
1828 | PALA12 | PALA12 |  |  |  | CHN | TVI | - | - |  | On air | 2022-07-05 | PALA12 | 4G_FD900_PALA12 | 4G_FD2100_PALA12 | 4G_TD_PALA12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252826 | 2022-07-13 | P/FVC/MDS/1088656/2022 | 2022-07-25 | ST202207254717 | 2022-07-14 | P/FVC/MDS/1088710/2022 | 2022-07-25 |  |  |  |  | ST202207247321 | 2022-07-12 | P/FBW/MDS/1088599/2022 | 2022-07-25
1829 | KUNR36 | KUNR36 |  |  |  | CHN | Indus | IN-3137082 | R/NN-664963 |  | On air | 2022-06-28 | KUNR36 | 4G_FD900_KUNR36 | 4G_FD2100_KUNR36 | 4G_TD_KUNR36 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207227194 | 2022-07-07 | P/FVC/MDS/1088043/2022 | 2022-07-18 | ST202207225029 | 2022-07-06 | P/FVC/MDS/1087936/2022 | 2022-07-18 |  |  |  |  | ST202207224039 | 2022-07-06 | P/FBW/MDS/1087852/2022 | 2022-07-18
1830 | KUNR38 | KUNR38 |  |  |  | CHN | Indus | IN-3137104 | R/NN-664992 |  | On air | 2022-06-16 | KUNR38 | 4G_FD900_KUNR38 | 4G_FD2100_KUNR38 | 4G_TD_KUNR38 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206197729 | 2022-06-24 | P/FVC/MDS/1085763/2022 | 2022-07-05 | ST202206196203 | 2022-06-23 | P/FVC/MDS/1085729/2022 | 2022-07-05 | ST202210538357 | 2022-10-08 | P/FVC/MDS/1113884/2022 | 2022-10-21 | ST202206196451 | 2022-06-23 | P/FBW/MDS/1085691/2022 | 2022-07-05
1831 | TIMZI2 | TIMZI2 |  |  |  | CHN | ATC | TN/CH/AT/23237 | T22TN02949 |  | On air | 2022-06-24 | TIMZI2 | 4G_FD900_TIMZI2 | 4G_FD2100_TIMZI2 | 4G_TD_TIMZI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226081 | 2022-07-07 | P/FVC/MDS/1088004/2022 | 2022-07-18 | ST202207224983 | 2022-07-06 | P/FVC/MDS/1087897/2022 | 2022-07-18 |  |  |  |  | ST202207222838 | 2022-07-06 | P/FBW/MDS/1087812/2022 | 2022-07-18
1832 | PRMLP3 | PRMLP3 |  |  |  | CHN | ATC | TN/CH/AT/23240 | - |  | On air | 2022-06-18 | PRMLP3 | 4G_FD900_PRMLP3 | 4G_FD2100_PRMLP3 | 4G_TD_PRMLP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206198013 | 2022-06-24 | P/FVC/MDS/1085776/2022 | 2022-07-05 | ST202206196267 | 2022-06-23 | P/FVC/MDS/1085742/2022 | 2022-07-05 |  |  |  |  | ST202206196551 | 2022-06-23 | P/FBW/MDS/1085704/2022 | 2022-07-05
1833 | TRNIL3 | TRNIL3 |  |  |  | CHN | ATC | TN/CH/AT/23242 | T22TN02954 |  | On air | 2022-06-24 | TRNIL3 | 4G_FD900_TRNIL3 | 4G_FD2100_TRNIL3 | 4G_TD_TRNIL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226032 | 2022-07-07 | P/FVC/MDS/1087998/2022 | 2022-07-18 | ST202207224779 | 2022-07-06 | P/FVC/MDS/1087891/2022 | 2022-07-18 |  |  |  |  | ST202207222801 | 2022-07-06 | P/FBW/MDS/1087806/2022 | 2022-07-18
1834 | NGL93 | NGL93 |  |  |  | ROTN | ATC | TN/KN/AT/22739 | T21TN09764 |  |  | 2022-06-24 | NGL093 | 4G_FD900_NGL093 | 4G_FD2100_NGL093 | 4G_TD_NGL093 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207226080 | 2022-07-07 | P/FVC/MDS/1088003/2022 | 2022-07-18 | ST202207224982 | 2022-07-06 | P/FVC/MDS/1087896/2022 | 2022-07-18 |  |  |  |  | ST202207222837 | 2022-07-06 | P/FBW/MDS/1087811/2022 | 2022-07-18
1835 | GUDA3 | GUDA3 |  |  |  | ROTN | Indus | IN-3126634 | R/NN-648640 |  |  | 2022-06-16 | GUDA03 | 4G_FD900_GUDA03 | 4G_FD2100_GUDA03 | 4G_TD_GUDA03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206197719 | 2022-06-24 | P/FVC/MDS/1085762/2022 | 2022-07-05 | ST202206196190 | 2022-06-23 | P/FVC/MDS/1085728/2022 | 2022-07-05 |  |  |  |  | ST202206196441 | 2022-06-23 | P/FBW/MDS/1085690/2022 | 2022-07-05
1836 | ILPUR3 | ILPUR3 |  |  |  | ROTN | ATC | TN/PU/AT/23215 | - |  | On Air | 2022-07-05 | ILPUR3 | 4G_FD900_ILPUR3 | 4G_FD2100_ILPUR3 | 4G_TD_ILPUR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207251967 | 2022-07-13 | P/FVC/MDS/1088647/2022 | 2022-07-25 | ST202207254676 | 2022-07-14 | P/FVC/MDS/1088701/2022 | 2022-07-25 |  |  |  |  | ST202207247244 | 2022-07-12 | P/FBW/MDS/1088590/2022 | 2022-07-25
1837 | COLAC2 | COLAC2 |  |  |  | ROTN | ATC | TN/KN/AT/22905 | T21TN11366 |  | On Air | 2022-07-05 | COLAC2 | 4G_FD900_COLAC2 | 4G_FD2100_COLAC2 | 4G_TD_COLAC2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207251985 | 2022-07-13 | P/FVC/MDS/1088649/2022 | 2022-07-25 | ST202207254685 | 2022-07-14 | P/FVC/MDS/1088703/2022 | 2022-07-25 |  |  |  |  | ST202207247281 | 2022-07-12 | P/FBW/MDS/1088592/2022 | 2022-07-25
1838 | VLR225 | VLR225 |  |  |  | ROTN | ATC | TN/VE/AT/22201 | T20TN07091 |  | SRB(Surrender) | 2022-07-07 | VLR225 | 4G_FD900_VLR225 | 4G_FD2100_VLR225 | 4G_TD_VLR225 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207254027 | 2022-07-13 | P/FVC/MDS/1088680/2022 | 2022-07-25 | ST202207254961 | 2022-07-14 | P/FVC/MDS/1088736/2022 | 2022-07-25 |  |  |  |  | ST202207248057 | 2022-07-12 | P/FBW/MDS/1088624/2022 | 2022-07-25
1839 | KTKIN2 | KTKIN2 |  |  |  | ROTN | Indus | IN-3130128 | R/NN-653784 |  | SRB(Surrender) | 2022-07-05 | KTKIN2 | 4G_FD900_KTKIN2 | 4G_FD2100_KTKIN2 | 4G_TD_KTKIN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252006 | 2022-07-13 | P/FVC/MDS/1088651/2022 | 2022-07-25 | ST202207254701 | 2022-07-14 | P/FVC/MDS/1088705/2022 | 2022-07-25 |  |  |  |  | ST202207247283 | 2022-07-12 | P/FBW/MDS/1088594/2022 | 2022-07-25
1840 | CDBM68 | CDBM68 |  |  |  | ROTN | Indus | IN-3132294 | R/NN-656882 |  | On Air | 2022-07-05 | CDBM68 | 4G_FD900_CDBM68 | 4G_FD2100_CDBM68 | 4G_TD_CDBM68 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252228 | 2022-07-13 | P/FVC/MDS/1088654/2022 | 2022-07-25 | ST202207254708 | 2022-07-14 | P/FVC/MDS/1088708/2022 | 2022-07-25 |  |  |  |  | ST202207247302 | 2022-07-12 | P/FBW/MDS/1088597/2022 | 2022-07-25
1841 | GOPURA | GOPURA |  |  |  | ROTN | ATC | TN/TA/AT/23220 | - |  | On Air | 2022-07-07 | GOPURA | 4G_FD900_GOPURA | 4G_FD2100_GOPURA | 4G_TD_GOPURA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207254031 | 2022-07-13 | P/FVC/MDS/1088681/2022 | 2022-07-25 | ST202207254976 | 2022-07-14 | P/FVC/MDS/1088737/2022 | 2022-07-25 |  |  |  |  | ST202207248058 | 2022-07-12 | P/FBW/MDS/1088625/2022 | 2022-07-25
1842 | KLKC55 | KLKC55 |  |  |  | ROTN | Indus | IN-3137106 | R/NN-664996 |  | On Air | 2022-07-05 | KLKC55 | 4G_FD900_KLKC55 | 4G_FD2100_KLKC55 | 4G_TD_KLKC55 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252229 | 2022-07-13 | P/FVC/MDS/1088655/2022 | 2022-07-25 | ST202207254716 | 2022-07-14 | P/FVC/MDS/1088709/2022 | 2022-07-25 |  |  |  |  | ST202207247319 | 2022-07-12 | P/FBW/MDS/1088598/2022 | 2022-07-25
1843 | PULGD3 | PULGD3 |  |  |  | ROTN | ATC | TN/TR/AT/23232 | - |  | On Air | 2022-07-05 | PULGD3 | 4G_FD900_PULGD3 | 4G_FD2100_PULGD3 | 4G_TD_PULGD3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207251966 | 2022-07-13 | P/FVC/MDS/1088646/2022 | 2022-07-25 | ST202207254665 | 2022-07-14 | P/FVC/MDS/1088700/2022 | 2022-07-25 |  |  |  |  | ST202207247222 | 2022-07-12 | P/FBW/MDS/1088589/2022 | 2022-07-25
1844 | KGRI50 | KGRI50 |  |  |  | ROTN | ATC | TN/DH/AT/23236 | - |  | On Air | 2022-07-05 | KGRI50 | 4G_FD900_KGRI50 | 4G_FD2100_KGRI50 | 4G_TD_KGRI50 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207251954 | 2022-07-13 | P/FVC/MDS/1088645/2022 | 2022-07-25 | ST202207254664 | 2022-07-14 | P/FVC/MDS/1088699/2022 | 2022-07-25 |  |  |  |  | ST202207247220 | 2022-07-12 | P/FBW/MDS/1088588/2022 | 2022-07-25
1845 | RNGPM2 | RNGPM2 |  |  |  | ROTN | Summit | I-TN-EROD-ENB-9101 | SR-TN000940 |  |  | 2022-07-12 | RNGPM2 | 4G_FD900_RNGPM2 | 4G_FD2100_RNGPM2 | 4G_TD_RNGPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254046 | 2022-07-13 | P/FVC/MDS/1088689/2022 | 2022-07-25 | ST202207255039 | 2022-07-14 | P/FVC/MDS/1088745/2022 | 2022-07-25 | ST202207254130 | 2022-07-13 | P/FVC/MDS/1088781/2022 | 2022-07-25 | ST202207248120 | 2022-07-12 | P/FBW/MDS/1088633/2022 | 2022-07-25
1846 | GVPTI4 | GVPTI4 |  |  |  | ROTN | Indus | IN-3132119 | R/NN-656108 |  |  | 2022-07-12 | GVPTI4 | 4G_FD900_GVPTI4 | 4G_FD2100_GVPTI4 | 4G_TD_GVPTI4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254041 | 2022-07-13 | P/FVC/MDS/1088687/2022 | 2022-07-25 | ST202207255022 | 2022-07-14 | P/FVC/MDS/1088743/2022 | 2022-07-25 | ST202207254125 | 2022-07-13 | P/FVC/MDS/1088779/2022 | 2022-07-25 | ST202207248118 | 2022-07-12 | P/FBW/MDS/1088631/2022 | 2022-07-25
1847 | EGMO13 | EGMO13 |  |  |  | CHN | ATC | TN/CH/TT/13100 | - |  |  | 2022-06-24 | EGMO16 | 4G_FD900_EGMO16 | 4G_FD2100_EGMO16 | 4G_TD_EGMO16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207225973 | 2022-07-07 | P/FVC/MDS/1087994/2022 | 2022-07-18 | ST202207224760 | 2022-07-06 | P/FVC/MDS/1087887/2022 | 2022-07-18 | ST202207228362 | 2022-07-07 | P/FVC/MDS/1087954/2022 | 2022-07-18 | ST202207222789 | 2022-07-06 | P/FBW/MDS/1087802/2022 | 2022-07-18
1848 | UMKDI7 | UMKDI7 |  |  |  | ROTN | INDUS | IN-1031245 | R/RES-511472 |  |  | 2022-07-12 | UMKDI7 | 4G_FD900_UMKDI7 | 4G_FD2100_UMKDI7 | 4G_TD_UMKDI7 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207254042 | 2022-07-13 | P/FVC/MDS/1088688/2022 | 2022-07-25 | ST202207255038 | 2022-07-14 | P/FVC/MDS/1088744/2022 | 2022-07-25 | ST202207254129 | 2022-07-13 | P/FVC/MDS/1088780/2022 | 2022-07-25 | ST202207248119 | 2022-07-12 | P/FBW/MDS/1088632/2022 | 2022-07-25
1849 | TUT101 | TUT101 |  |  |  | ROTN | ATC | - | - |  | SO | 2022-07-11 | TUT101 | 4G_FD900_TUT101 | 4G_FD2100_TUT101 | 4G_TD_TUT101 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106363086 | 2021-06-26 | P/FVC/MDS/1050092/2021 | 2021-08-09 | ST202104148072 | 2021-04-15 | P/FVC/MDS/1018020/2021 | 2021-05-15 | ST202212839566 | 2022-12-22 |  |  | ST202104148946 | 2021-04-15 | P/FBW/MDS/1018079/2021 | 2021-05-16
1850 | NGL144 | NGL144 |  |  |  | ROTN | Indus | IN-3140074 | R/NN-669014 |  | SO ( Withdrwan request sent to SCM ) | 2022-07-14 | NGL144 | 4G_FD900_NGL144 | 4G_FD2100_NGL144 | 4G_TD_NGL144 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296176 | 2022-07-28 | P/FVC/MDS/1093397/2022 | 2022-08-09 | ST202207298909 | 2022-07-29 | P/FVC/MDS/1093306/2022 | 2022-08-09 |  |  |  |  | ST202207295328 | 2022-07-28 | P/FBW/MDS/1093189/2022 | 2022-08-09
1851 | BODI18 | BODI18 |  |  |  | ROTN | Ascend | - | - |  | SR | 2022-07-16 | BODI18 | 4G_FD900_BODI18 | 4G_FD2100_BODI18 | 4G_TD_BODI18 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297688 | 2022-07-29 | P/FVC/MDS/1093406/2022 | 2022-08-09 | ST202207298954 | 2022-07-29 | P/FVC/MDS/1093318/2022 | 2022-08-09 |  |  |  |  | ST202207295402 | 2022-07-28 | P/FBW/MDS/1093201/2022 | 2022-08-09
1852 | TRY335 | TRY335 |  |  |  | ROTN | Ascend | TN/TR/AT/23066 | T22TN01100 |  | On Air | 2022-06-17 | TRY335 | 4G_FD900_TRY335 | 4G_FD2100_TRY335 | 4G_TD_TRY335 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298008 | 2022-07-29 | P/FVC/MDS/1093429/2022 | 2022-08-09 | ST202207299199 | 2022-07-29 | P/FVC/MDS/1093352/2022 | 2022-08-09 | ST202211757954 | 2022-11-22 | P/FVC/MDS/1116759/2022 | 2022-11-29 | ST202207295955 | 2022-07-28 | P/FBW/MDS/1093235/2022 | 2022-08-09
1853 | PDY289 | PDY289 |  |  |  | ROTN | Spacetele | STIPL-TN-381 | - |  | On Air | 2022-07-23 | PDY289 | 4G_FD900_PDY289 | 4G_FD2100_PDY289 | 4G_TD_PDY289 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296103 | 2022-07-28 | P/FVC/MDS/1093382/2022 | 2022-08-09 | ST202207298672 | 2022-07-29 | P/FVC/MDS/1093285/2022 | 2022-08-09 |  |  |  |  | ST202207295232 | 2022-07-28 | P/FBW/MDS/1093168/2022 | 2022-08-09
1854 | SVPT29 | SVPT29 |  |  |  | ROTN | ATC | TN/VI/AT/22045 | T20TN04054 |  | SRB(Surrender) | 2022-04-27 | SVPT29 | 4G_FD900_SVPT29 | 4G_FD2100_SVPT29 | 4G_TD_SVPT29 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313070 | 2022-08-05 | P/FVC/MDS/1093832/2022 | 2022-08-19 | ST202208320596 | 2022-08-09 | P/FVC/MDS/1093970/2022 | 2022-08-19 |  |  |  |  | ST202208306012 | 2022-08-02 | P/FBW/MDS/1093735/2022 | 2022-08-19
1855 | HSR181 | HSR181 |  |  |  | ROTN | Indus | IN-3131825 | R/NN-655337 |  | SO | 2022-07-18 | HSR181 | 4G_FD900_HSR181 | 4G_FD2100_HSR181 | 4G_TD_HSR181 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207274245 | 2022-07-20 | P/FVC/MDS/1093368/2022 | 2022-08-09 | ST202207274189 | 2022-07-20 | P/FVC/MDS/1093270/2022 | 2022-08-09 |  |  |  |  | ST202207293768 | 2022-07-28 | P/FBW/MDS/1093153/2022 | 2022-08-09
1856 | TIMMPM | TIMMPM |  |  |  | ROTN | ATC | TN/DH/AT/22096 | T20TN05732 |  | On Air | 2022-06-16 | TIMMPM | 4G_FD900_TIMMPM | 4G_FD2100_TIMMPM | 4G_TD_TIMMPM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298046 | 2022-07-29 | P/FVC/MDS/1093434/2022 | 2022-08-09 | ST202207299229 | 2022-07-29 | P/FVC/MDS/1093357/2022 | 2022-08-09 |  |  |  |  | ST202207295971 | 2022-07-28 | P/FBW/MDS/1093240/2022 | 2022-08-09
1857 | MDU456 | MDU456 |  |  |  | ROTN | ATC | TN/MU/AT/23199 | T22TN02161 |  | On Air | 2022-07-11 | MDU456 | 4G_FD900_MDU456 | 4G_FD2100_MDU456 | 4G_TD_MDU456 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298920 | 2022-07-29 | P/FVC/MDS/1093308/2022 | 2022-08-09 |  |  |  |  | ST202207295336 | 2022-07-28 | P/FBW/MDS/1093191/2022 | 2022-08-09
1858 | PDY395 | PDY395 |  |  |  | ROTN | Indus | IN-3142637 | R/NN-671996 |  |  | 2022-06-14 | PDY395 | 4G_FD900_PDY395 | 4G_FD2100_PDY395 | 4G_TD_PDY395 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297652 | 2022-07-29 | P/FVC/MDS/1093398/2022 | 2022-08-09 | ST202207298919 | 2022-07-29 | P/FVC/MDS/1093307/2022 | 2022-08-09 |  |  |  |  | ST202207295329 | 2022-07-28 | P/FBW/MDS/1093190/2022 | 2022-08-09
1859 | VELRAM | VELRAM |  |  |  | ROTN | ATC | TN/SA/AT/23217 | - |  | On Air | 2022-07-15 | VELRAM | 4G_FD900_VELRAM | 4G_FD2100_VELRAM | 4G_TD_VELRAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296102 | 2022-07-28 | P/FVC/MDS/1093381/2022 | 2022-08-09 | ST202207298660 | 2022-07-29 | P/FVC/MDS/1093283/2022 | 2022-08-09 |  |  |  |  | ST202207295210 | 2022-07-28 | P/FBW/MDS/1093166/2022 | 2022-08-09
1860 | KUNNA3 | KUNNA3 |  |  |  | ROTN | Indus | IN-3142909 | R/NN-671999 |  |  | 2022-07-25 | KUNNA3 | 4G_FD900_KUNNA3 | 4G_FD2100_KUNNA3 | 4G_TD_KUNNA3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297913 | 2022-07-29 | P/FVC/MDS/1093413/2022 | 2022-08-09 | ST202207300568 | 2022-07-30 | P/FVC/MDS/1093539/2022 | 2022-08-09 |  |  |  |  | ST202207295445 | 2022-07-28 | P/FBW/MDS/1093212/2022 | 2022-08-09
1861 | TIVR21 | TIVR21 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-07-07 | TIVR21 | 4G_FD900_TIVR21 | 4G_FD2100_TIVR21 | 4G_TD_TIVR21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362809 | 2021-06-26 | P/FVC/MDS/1050066/2021 | 2021-08-09 | ST202208320605 | 2022-08-09 | P/FVC/MDS/1093975/2022 | 2022-08-19 |  |  |  |  | ST202208306020 | 2022-08-02 | P/FBW/MDS/1093740/2022 | 2022-08-19
1862 | TNJ178 | TNJ178 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-07-07 | TNJ178 | 4G_FD900_TNJ178 | 4G_FD2100_TNJ178 | 4G_TD_TNJ178 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296136 | 2022-07-28 | P/FVC/MDS/1093388/2022 | 2022-08-09 | ST202207298736 | 2022-07-29 | P/FVC/MDS/1093292/2022 | 2022-08-09 |  |  |  |  | ST202207295261 | 2022-07-28 | P/FBW/MDS/1093175/2022 | 2022-08-09
1863 | VLRM77 | VLRM77 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-06-16 | VLRM77 | 4G_FD900_VLRM77 | 4G_FD2100_VLRM77 | 4G_TD_VLRM77 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296150 | 2022-07-28 | P/FVC/MDS/1093390/2022 | 2022-08-09 | ST202207298751 | 2022-07-29 | P/FVC/MDS/1093294/2022 | 2022-08-09 |  |  |  |  | ST202207295271 | 2022-07-28 | P/FBW/MDS/1093177/2022 | 2022-08-09
1864 | CBE909 | CBE909 |  |  |  | ROTN | ATC | TN/CO/AT/22984 | T22TN00464 |  | SO | 2022-07-13 | CBE909 | 4G_FD900_CBE909 | 4G_FD2100_CBE909 | 4G_TD_CBE909 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297653 | 2022-07-29 | P/FVC/MDS/1093399/2022 | 2022-08-09 | ST202207298928 | 2022-07-29 | P/FVC/MDS/1093309/2022 | 2022-08-09 | ST202211682876 | 2022-11-05 | P/FVC/MDS/1114586/2022 | 2022-11-15 | ST202207295337 | 2022-07-28 | P/FBW/MDS/1093192/2022 | 2022-08-09
1865 | KTTY10 | KTTY10 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-05-23 | KTTY10 | 4G_FD900_KTTY10 | 4G_FD2100_KTTY10 | 4G_TD_KTTY10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297674 | 2022-07-29 | P/FVC/MDS/1093403/2022 | 2022-08-09 | ST202207298945 | 2022-07-29 | P/FVC/MDS/1093314/2022 | 2022-08-09 |  |  |  |  | ST202207295377 | 2022-07-28 | P/FBW/MDS/1093197/2022 | 2022-08-09
1866 | VNBKM2 | VNBKM2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-07-22 | VNBKM2 | 4G_FD900_VNBKM2 | 4G_FD2100_VNBKM2 | 4G_TD_VNBKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296088 | 2022-07-28 | P/FVC/MDS/1093374/2022 | 2022-08-09 | ST202207298617 | 2022-07-29 | P/FVC/MDS/1093276/2022 | 2022-08-09 | ST202210548784 | 2022-10-11 | P/FVC/MDS/1113944/2022 | 2022-10-21 | ST202207293838 | 2022-07-28 | P/FBW/MDS/1093159/2022 | 2022-08-09
1867 | MTYPM7 | MTYPM7 |  |  |  | ROTN | ATC |  |  |  | SO | 2022-05-23 | MTYPM7 | 4G_FD900_MTYPM7 | 4G_FD2100_MTYPM7 | 4G_TD_MTYPM7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208308173 | 2022-08-03 | P/FVC/MDS/1093824/2022 | 2022-08-19 | ST202208319518 | 2022-08-09 | P/FVC/MDS/1093961/2022 | 2022-08-19 | ST202211758072 | 2022-11-22 | P/FVC/MDS/1116771/2022 | 2022-11-29 | ST202208306000 | 2022-08-02 | P/FBW/MDS/1093726/2022 | 2022-08-19
1868 | PTMVL2 | PTMVL2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-05-26 | PTMVL2 | 4G_FD900_PTMVL2 | 4G_FD2100_PTMVL2 | 4G_TD_PTMVL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296087 | 2022-07-28 | P/FVC/MDS/1093373/2022 | 2022-08-09 | ST202207298616 | 2022-07-29 | P/FVC/MDS/1093275/2022 | 2022-08-09 |  |  |  |  | ST202207293823 | 2022-07-28 | P/FBW/MDS/1093158/2022 | 2022-08-09
1869 | KUTH06 | KUTH06 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-05-20 | KUTH06 | 4G_FD900_KUTH06 | 4G_FD2100_KUTH06 | 4G_TD_KUTH06 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296092 | 2022-07-28 | P/FVC/MDS/1093377/2022 | 2022-08-09 | ST202207298639 | 2022-07-29 | P/FVC/MDS/1093279/2022 | 2022-08-09 |  |  |  |  | ST202207293846 | 2022-07-28 | P/FBW/MDS/1093162/2022 | 2022-08-09
1870 | PLYNT2 | PLYNT2 |  |  |  | ROTN | ATC | TN/DI/AT/23128 | T22TN01310 |  | On Air | 2022-05-23 | PLYNT2 | 4G_FD900_PLYNT2 | 4G_FD2100_PLYNT2 | 4G_TD_PLYNT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296080 | 2022-07-28 | P/FVC/MDS/1093370/2022 | 2022-08-09 | ST202207298590 | 2022-07-29 | P/FVC/MDS/1093272/2022 | 2022-08-09 |  |  |  |  | ST202207293791 | 2022-07-28 | P/FBW/MDS/1093155/2022 | 2022-08-09
1871 | PNTHI2 | PNTHI2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-05-24 | PNTHI2 | 4G_FD900_PNTHI2 | 4G_FD2100_PNTHI2 | 4G_TD_PNTHI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296082 | 2022-07-28 | P/FVC/MDS/1093372/2022 | 2022-08-09 | ST202207298603 | 2022-07-29 | P/FVC/MDS/1093274/2022 | 2022-08-09 |  |  |  |  | ST202207293822 | 2022-07-28 | P/FBW/MDS/1093157/2022 | 2022-08-09
1872 | KESVP2 | KESVP2 |  |  |  | ROTN | Indus | IN-3130578 | R/NN-654458 |  | On Air | 2022-07-11 | KESVP2 | 4G_FD900_KESVP2 | 4G_FD2100_KESVP2 | 4G_TD_KESVP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296091 | 2022-07-28 | P/FVC/MDS/1093376/2022 | 2022-08-09 | ST202207298624 | 2022-07-29 | P/FVC/MDS/1093278/2022 | 2022-08-09 |  |  |  |  | ST202207293845 | 2022-07-28 | P/FBW/MDS/1093161/2022 | 2022-08-09
1873 | AVYOR2 | AVYOR2 |  |  |  | ROTN | Indus | IN-3130591 | R/NN-654461 |  | On Air | 2022-07-14 | AVYOR2 | 4G_FD900_AVYOR2 | 4G_FD2100_AVYOR2 | 4G_TD_AVYOR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296175 | 2022-07-28 | P/FVC/MDS/1093396/2022 | 2022-08-09 | ST202207298908 | 2022-07-29 | P/FVC/MDS/1093305/2022 | 2022-08-09 |  |  |  |  | ST202207295325 | 2022-07-28 | P/FBW/MDS/1093188/2022 | 2022-08-09
1874 | WJPT24 | WJPT24 |  |  |  | ROTN | Ascend | - | - |  | SR | 2022-06-22 | WJPT24 | 4G_FD900_WJPT24 | 4G_FD2100_WJPT24 | 4G_TD_WJPT24 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297695 | 2022-07-29 | P/FVC/MDS/1093409/2022 | 2022-08-09 | ST202207298968 | 2022-07-29 | P/FVC/MDS/1093322/2022 | 2022-08-09 |  |  |  |  | ST202207295417 | 2022-07-28 | P/FBW/MDS/1093205/2022 | 2022-08-09
1875 | PLNDR3 | PLNDR3 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-07-25 | PLNDR3 | 4G_FD900_PLNDR3 | 4G_FD2100_PLNDR3 | 4G_TD_PLNDR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296109 | 2022-07-28 | P/FVC/MDS/1093384/2022 | 2022-08-09 | ST202207298699 | 2022-07-29 | P/FVC/MDS/1093287/2022 | 2022-08-09 |  |  |  |  | ST202207295243 | 2022-07-28 | P/FBW/MDS/1093170/2022 | 2022-08-09
1876 | PDY369 | PDY369 |  |  |  | ROTN | Ascend |  |  |  | SR | 2022-07-25 | PDY369 | 4G_FD900_PDY369 | 4G_FD2100_PDY369 | 4G_TD_PDY369 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313087 | 2022-08-05 | P/FVC/MDS/1093835/2022 | 2022-08-19 | ST202208320603 | 2022-08-09 | P/FVC/MDS/1093973/2022 | 2022-08-19 |  |  |  |  | ST202208306017 | 2022-08-02 | P/FBW/MDS/1093738/2022 | 2022-08-19
1877 | NLKP10 | NLKP10 |  |  |  | ROTN | Ascend |  |  |  | SR | 2022-05-16 | NLKP10 | 4G_FD900_NLKP10 | 4G_FD2100_NLKP10 | 4G_TD_NLKP10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313072 | 2022-08-05 | P/FVC/MDS/1093834/2022 | 2022-08-19 | ST202208320598 | 2022-08-09 | P/FVC/MDS/1093972/2022 | 2022-08-19 |  |  |  |  | ST202208306016 | 2022-08-02 | P/FBW/MDS/1093737/2022 | 2022-08-19
1878 | USLMP3 | USLMP3 |  |  |  | ROTN | Indus | IN-3132393 | R/NN-656988 |  | On Air | 2022-05-26 | USLMP3 | 4G_FD900_USLMP3 | 4G_FD2100_USLMP3 | 4G_TD_USLMP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296079 | 2022-07-28 | P/FVC/MDS/1093369/2022 | 2022-08-09 | ST202207298589 | 2022-07-29 | P/FVC/MDS/1093271/2022 | 2022-08-09 |  |  |  |  | ST202207293769 | 2022-07-28 | P/FBW/MDS/1093154/2022 | 2022-08-09
1879 | VRLIM6 | VRLIM6 |  |  |  | ROTN | Indus | IN-3132401 | R/NN-656989 |  | On Air | 2022-06-23 | VRLIM6 | 4G_FD900_VRLIM6 | 4G_FD2100_VRLIM6 | 4G_TD_VRLIM6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296094 | 2022-07-28 | P/FVC/MDS/1093378/2022 | 2022-08-09 | ST202207298640 | 2022-07-29 | P/FVC/MDS/1093280/2022 | 2022-08-09 |  |  |  |  | ST202207293850 | 2022-07-28 | P/FBW/MDS/1093163/2022 | 2022-08-09
1880 | BUTKD2 | BUTKD2 |  |  |  | ROTN | Summit | I-TN-IPPR-ENB-9048 | SR-TN000955 |  | On Air | 2022-07-13 | BUTKD2 | 4G_FD900_BUTKD2 | 4G_FD2100_BUTKD2 | 4G_TD_BUTKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296117 | 2022-07-28 | P/FVC/MDS/1093385/2022 | 2022-08-09 | ST202207298700 | 2022-07-29 | P/FVC/MDS/1093288/2022 | 2022-08-09 |  |  |  |  | ST202207295244 | 2022-07-28 | P/FBW/MDS/1093171/2022 | 2022-08-09
1881 | NGPM22 | NGPM22 |  |  |  | ROTN | Indus | IN-3132268 | R/NN-656848 |  | On Air | 2022-06-08 | NGPM22 | 4G_FD900_NGPM22 | 4G_FD2100_NGPM22 | 4G_TD_NGPM22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297679 | 2022-07-29 | P/FVC/MDS/1093404/2022 | 2022-08-09 | ST202207298949 | 2022-07-29 | P/FVC/MDS/1093315/2022 | 2022-08-09 |  |  |  |  | ST202207295378 | 2022-07-28 | P/FBW/MDS/1093198/2022 | 2022-08-09
1882 | KOTGM2 | KOTGM2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-06-22 | KOTGM2 | 4G_FD900_KOTGM2 | 4G_FD2100_KOTGM2 | 4G_TD_KOTGM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296096 | 2022-07-28 | P/FVC/MDS/1093380/2022 | 2022-08-09 | ST202207298659 | 2022-07-29 | P/FVC/MDS/1093282/2022 | 2022-08-09 |  |  |  |  | ST202207295209 | 2022-07-28 | P/FBW/MDS/1093165/2022 | 2022-08-09
1883 | KIZHA2 | KIZHA2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-05-23 | KIZHA2 | 4G_FD900_KIZHA2 | 4G_FD2100_KIZHA2 | 4G_TD_KIZHA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539059 | 2022-10-08 | P/FVC/MDS/1114008/2022 | 2022-10-21 | ST202210537859 | 2022-10-07 | P/FVC/MDS/1113822/2022 | 2022-10-21 |  |  |  |  | ST202210535567 | 2022-10-07 | P/FBW/MDS/1113741/2022 | 2022-10-21
1884 | TIRBV2 | TIRBV2 |  |  |  | ROTN | Ascend | - | - |  | SR | 2022-07-22 | TIRBV2 | 4G_FD900_TIRBV2 | 4G_FD2100_TIRBV2 | 4G_TD_TIRBV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296081 | 2022-07-28 | P/FVC/MDS/1093371/2022 | 2022-08-09 | ST202207298602 | 2022-07-29 | P/FVC/MDS/1093273/2022 | 2022-08-09 |  |  |  |  | ST202207293792 | 2022-07-28 | P/FBW/MDS/1093156/2022 | 2022-08-09
1885 | ARLR23 | ARLR23 |  |  |  | ROTN | Indus |  | R/NN-674250 |  | On Air | 2022-05-23 | ARLR23 | 4G_FD900_ARLR23 | 4G_FD2100_ARLR23 | 4G_TD_ARLR23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208308241 | 2022-08-03 | P/FVC/MDS/1093825/2022 | 2022-08-19 | ST202208319520 | 2022-08-09 | P/FVC/MDS/1093963/2022 | 2022-08-19 |  |  |  |  | ST202208306002 | 2022-08-02 | P/FBW/MDS/1093728/2022 | 2022-08-19
1886 | ALYKD3 | ALYKD3 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-07-14 | ALYKD3 | 4G_FD900_ALYKD3 | 4G_FD2100_ALYKD3 | 4G_TD_ALYKD3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296090 | 2022-07-28 | P/FVC/MDS/1093375/2022 | 2022-08-09 | ST202207298623 | 2022-07-29 | P/FVC/MDS/1093277/2022 | 2022-08-09 |  |  |  |  | ST202207293839 | 2022-07-28 | P/FBW/MDS/1093160/2022 | 2022-08-09
1887 | PDRIK2 | PDRIK2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-07-15 | PDRIK2 | 4G_FD900_PDRIK2 | 4G_FD2100_PDRIK2 | 4G_TD_PDRIK2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298953 | 2022-07-29 | P/FVC/MDS/1093317/2022 | 2022-08-09 |  |  |  |  | ST202207295393 | 2022-07-28 | P/FBW/MDS/1093200/2022 | 2022-08-09
1888 | THIRAI | THIRAI |  |  |  | ROTN | ATC | TN/PR/AT/23219 | - |  | On Air | 2022-07-07 | THIRAI | 4G_FD900_THIRAI | 4G_FD2100_THIRAI | 4G_TD_THIRAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297912 | 2022-07-29 | P/FVC/MDS/1093412/2022 | 2022-08-09 | ST202207299115 | 2022-07-29 | P/FVC/MDS/1093327/2022 | 2022-08-09 |  |  |  |  | ST202207295437 | 2022-07-28 | P/FBW/MDS/1093210/2022 | 2022-08-09
1889 | ANUPP2 | ANUPP2 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-06-25 | ANUPP2 | 4G_FD900_ANUPP2 | 4G_FD2100_ANUPP2 | 4G_TD_ANUPP2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298752 | 2022-07-29 | P/FVC/MDS/1093295/2022 | 2022-08-09 |  |  |  |  | ST202207295284 | 2022-07-28 | P/FBW/MDS/1093178/2022 | 2022-08-09
1890 | TRVYR7 | TRVYR7 |  |  |  | ROTN | ATC | TN/TA/AT/23222 | - |  | SO | 2022-07-15 | TRVYR7 | 4G_FD900_TRVYR7 | 4G_FD2100_TRVYR7 | 4G_TD_TRVYR7 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364116 | 2021-06-28 | P/FVC/MDS/1050142/2021 | 2021-08-09 | ST202207298704 | 2022-07-29 | P/FVC/MDS/1093289/2022 | 2022-08-09 |  |  |  |  | ST202207295252 | 2022-07-28 | P/FBW/MDS/1093172/2022 | 2022-08-09
1891 | THIRU2 | THIRU2 |  |  |  | ROTN | Indus |  | R/NN-664907 |  | On Air | 2022-07-06 | THIRU2 | 4G_FD900_THIRU2 | 4G_FD2100_THIRU2 | 4G_TD_THIRU2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299198 | 2022-07-29 | P/FVC/MDS/1093351/2022 | 2022-08-09 |  |  |  |  | ST202207295941 | 2022-07-28 | P/FBW/MDS/1093234/2022 | 2022-08-09
1892 | KDVIP2 | KDVIP2 |  |  |  | ROTN | Summit | I-TN-TGMM-ENB-9021 | SR-TN001019 |  | On Air | 2022-07-06 | KDVIP2 | 4G_FD900_KDVIP2 | 4G_FD2100_KDVIP2 | 4G_TD_KDVIP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296118 | 2022-07-28 | P/FVC/MDS/1093386/2022 | 2022-08-09 | ST202207298717 | 2022-07-29 | P/FVC/MDS/1093290/2022 | 2022-08-09 |  |  |  |  | ST202207295253 | 2022-07-28 | P/FBW/MDS/1093173/2022 | 2022-08-09
1893 | KMBM19 | KMBM19 |  |  |  | ROTN | Summit | I-TN-UTMP-ENB-9026 | SR-TN001020 |  | On Air | 2022-07-14 | KMBM19 | 4G_FD900_KMBM19 | 4G_FD2100_KMBM19 | 4G_TD_KMBM19 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296135 | 2022-07-28 | P/FVC/MDS/1093387/2022 | 2022-08-09 | ST202207298718 | 2022-07-29 | P/FVC/MDS/1093291/2022 | 2022-08-09 |  |  |  |  | ST202207295260 | 2022-07-28 | P/FBW/MDS/1093174/2022 | 2022-08-09
1894 | SVKI81 | SVKI81 |  |  |  | ROTN | ATC | TN/VI/AT/23234 | - |  | On Air | 2022-07-23 | SVKI81 | 4G_FD900_SVKI81 | 4G_FD2100_SVKI81 | 4G_TD_SVKI81 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298980 | 2022-07-29 | P/FVC/MDS/1093324/2022 | 2022-08-09 |  |  |  |  | ST202207295419 | 2022-07-28 | P/FBW/MDS/1093207/2022 | 2022-08-09
1895 | WJPT25 | WJPT25 |  |  |  | ROTN | ATC |  |  |  | SRB(Surrender) | 2022-07-20 | WJPT25 | 4G_FD900_WJPT25 | 4G_FD2100_WJPT25 | 4G_TD_WJPT25 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313054 | 2022-08-05 | P/FVC/MDS/1093831/2022 | 2022-08-19 | ST202208320591 | 2022-08-09 | P/FVC/MDS/1093969/2022 | 2022-08-19 |  |  |  |  | ST202208306011 | 2022-08-02 | P/FBW/MDS/1093734/2022 | 2022-08-19
1896 | THOND3 | THOND3 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-20 | THOND3 | 4G_FD900_THOND3 | 4G_FD2100_THOND3 | 4G_TD_THOND3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298086 | 2022-07-29 | P/FVC/MDS/1093439/2022 | 2022-08-09 | ST202207300350 | 2022-07-30 | P/FVC/MDS/1093362/2022 | 2022-08-09 |  |  |  |  | ST202207300790 | 2022-07-30 | P/FBW/MDS/1093561/2022 | 2022-08-09
1897 | AVNI34 | AVNI34 |  |  |  | ROTN | ATC | - |  |  | SO | 2022-07-18 | AVNI34 | 4G_FD900_AVNI34 | 4G_FD2100_AVNI34 | 4G_TD_AVNI34 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298071 | 2022-07-29 | P/FVC/MDS/1093435/2022 | 2022-08-09 | ST202207300334 | 2022-07-30 | P/FVC/MDS/1093358/2022 | 2022-08-09 |  |  |  |  | ST202207295979 | 2022-07-28 | P/FBW/MDS/1093241/2022 | 2022-08-09
1898 | TCGD78 | TCGD78 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-16 | TCGD78 | 4G_FD900_TCGD78 | 4G_FD2100_TCGD78 | 4G_TD_TCGD78 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298045 | 2022-07-29 | P/FVC/MDS/1093433/2022 | 2022-08-09 | ST202207299228 | 2022-07-29 | P/FVC/MDS/1093356/2022 | 2022-08-09 |  |  |  |  | ST202207295970 | 2022-07-28 | P/FBW/MDS/1093239/2022 | 2022-08-09
1899 | KRR104 | KRR104 |  |  |  | ROTN | Summit | I-TN-KRUR-ENB-0038 | SR-TN001025 |  | On Air | 2022-07-23 | KRR104 | 4G_FD900_KRR104 | 4G_FD2100_KRR104 | 4G_TD_KRR104 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297935 | 2022-07-29 | P/FVC/MDS/1093417/2022 | 2022-08-09 | ST202207299176 | 2022-07-29 | P/FVC/MDS/1093333/2022 | 2022-08-09 |  |  |  |  | ST202207295469 | 2022-07-28 | P/FBW/MDS/1093217/2022 | 2022-08-09
1900 | KRR105 | KRR105 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-13 | KRR105 | 4G_FD900_KRR105 | 4G_FD2100_KRR105 | 4G_TD_KRR105 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313052 | 2022-08-05 | P/FVC/MDS/1093829/2022 | 2022-08-19 | ST202208320589 | 2022-08-09 | P/FVC/MDS/1093967/2022 | 2022-08-19 |  |  |  |  | ST202208306007 | 2022-08-02 | P/FBW/MDS/1093732/2022 | 2022-08-19
1901 | PMKD33 | PMKD33 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-07-14 | PMKD33 | 4G_FD900_PMKD33 | 4G_FD2100_PMKD33 | 4G_TD_PMKD33 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297673 | 2022-07-29 | P/FVC/MDS/1093402/2022 | 2022-08-09 | ST202207298944 | 2022-07-29 | P/FVC/MDS/1093313/2022 | 2022-08-09 |  |  |  |  | ST202207295369 | 2022-07-28 | P/FBW/MDS/1093196/2022 | 2022-08-09
1902 | PMKD34 | PMKD34 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-07-14 | PMKD34 | 4G_FD900_PMKD34 | 4G_FD2100_PMKD34 | 4G_TD_PMKD34 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297694 | 2022-07-29 | P/FVC/MDS/1093408/2022 | 2022-08-09 | ST202207298967 | 2022-07-29 | P/FVC/MDS/1093321/2022 | 2022-08-09 |  |  |  |  | ST202207295411 | 2022-07-28 | P/FBW/MDS/1093204/2022 | 2022-08-09
1903 | AMNR08 | AMNR08 |  |  |  | ROTN | Ascend | - | - |  | On Air | 2022-07-14 | AMNR08 | 4G_FD900_AMNR08 | 4G_FD2100_AMNR08 | 4G_TD_AMNR08 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297689 | 2022-07-29 | P/FVC/MDS/1093407/2022 | 2022-08-09 | ST202207298959 | 2022-07-29 | P/FVC/MDS/1093320/2022 | 2022-08-09 |  |  |  |  | ST202207295410 | 2022-07-28 | P/FBW/MDS/1093203/2022 | 2022-08-09
1904 | KRR107 | KRR107 |  |  |  | ROTN | ATC | TN/KU/AT/23259 | - |  | On Air | 2022-07-20 | KRR107 | 4G_FD900_KRR107 | 4G_FD2100_KRR107 | 4G_TD_KRR107 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360967 | 2022-08-28 | P/FVC/MDS/1094643/2022 | 2022-09-07 | ST202208364530 | 2022-08-29 | P/FVC/MDS/1094708/2022 | 2022-09-07 |  |  |  |  | ST202208355357 | 2022-08-26 | P/FBW/MDS/1094580/2022 | 2022-09-07
1905 | TIR496 | TIR496 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-20 | TIR496 | 4G_FD900_TIR496 | 4G_FD2100_TIR496 | 4G_TD_TIR496 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298072 | 2022-07-29 | P/FVC/MDS/1093436/2022 | 2022-08-09 | ST202207300335 | 2022-07-30 | P/FVC/MDS/1093359/2022 | 2022-08-09 |  |  |  |  | ST202207295980 | 2022-07-28 | P/FBW/MDS/1093242/2022 | 2022-08-09
1906 | TIR498 | TIR498 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-16 | TIR498 | 4G_FD900_TIR498 | 4G_FD2100_TIR498 | 4G_TD_TIR498 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298085 | 2022-07-29 | P/FVC/MDS/1093438/2022 | 2022-08-09 | ST202207300341 | 2022-07-30 | P/FVC/MDS/1093361/2022 | 2022-08-09 |  |  |  |  | ST202207295994 | 2022-07-28 | P/FBW/MDS/1093244/2022 | 2022-08-09
1907 | JOLR22 | JOLR22 |  |  |  | ROTN | Summit | I-TN-TRPR-ENB-9096 | SR-TN001026 |  | On Air | 2022-07-16 | JOLR22 | 4G_FD900_JOLR22 | 4G_FD2100_JOLR22 | 4G_TD_JOLR22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297927 | 2022-07-29 | P/FVC/MDS/1093415/2022 | 2022-08-09 | ST202207299172 | 2022-07-29 | P/FVC/MDS/1093330/2022 | 2022-08-09 |  |  |  |  | ST202207295455 | 2022-07-28 | P/FBW/MDS/1093214/2022 | 2022-08-09
1908 | ARNI37 | ARNI37 |  |  |  | ROTN | Summit | I-TN-ARNI-ENB-0016 | SR-TN001027 |  | On Air | 2022-07-18 | ARNI37 | 4G_FD900_ARNI37 | 4G_FD2100_ARNI37 | 4G_TD_ARNI37 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297936 | 2022-07-29 | P/FVC/MDS/1093418/2022 | 2022-08-09 | ST202207299177 | 2022-07-29 | P/FVC/MDS/1093334/2022 | 2022-08-09 |  |  |  |  | ST202207295470 | 2022-07-28 | P/FBW/MDS/1093218/2022 | 2022-08-09
1909 | ATURE2 | ATURE2 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-18 | ATURE2 | 4G_FD900_ATURE2 | 4G_FD2100_ATURE2 | 4G_TD_ATURE2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298032 | 2022-07-29 | P/FVC/MDS/1093431/2022 | 2022-08-09 | ST202207299201 | 2022-07-29 | P/FVC/MDS/1093354/2022 | 2022-08-09 |  |  |  |  | ST202207295957 | 2022-07-28 | P/FBW/MDS/1093237/2022 | 2022-08-09
1910 | HSR188 | HSR188 |  |  |  | ROTN | ATC | TN/DH/AT/23268 | - |  | On Air | 2022-07-14 | HSR188 | 4G_FD900_HSR188 | 4G_FD2100_HSR188 | 4G_TD_HSR188 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299185 | 2022-07-29 | P/FVC/MDS/1093338/2022 | 2022-08-09 |  |  |  |  | ST202207295490 | 2022-07-28 | P/FBW/MDS/1093222/2022 | 2022-08-09
1911 | HSR192 | HSR192 |  |  |  | ROTN | ATC | TN/DH/AT/23250 | - |  | On Air | 2022-07-18 | HSR192 | 4G_FD900_HSR192 | 4G_FD2100_HSR192 | 4G_TD_HSR192 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298979 | 2022-07-29 | P/FVC/MDS/1093323/2022 | 2022-08-09 |  |  |  |  | ST202207295418 | 2022-07-28 | P/FBW/MDS/1093206/2022 | 2022-08-09
1912 | SLM422 | SLM422 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-20 | SLM422 | 4G_FD900_SLM422 | 4G_FD2100_SLM422 | 4G_TD_SLM422 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298033 | 2022-07-29 | P/FVC/MDS/1093432/2022 | 2022-08-09 | ST202207299202 | 2022-07-29 | P/FVC/MDS/1093355/2022 | 2022-08-09 |  |  |  |  | ST202207295969 | 2022-07-28 | P/FBW/MDS/1093238/2022 | 2022-08-09
1913 | SLM424 | SLM424 |  |  |  | ROTN | ATC | - |  |  | On Air | 2022-07-22 | SLM424 | 4G_FD900_SLM424 | 4G_FD2100_SLM424 | 4G_TD_SLM424 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298084 | 2022-07-29 | P/FVC/MDS/1093437/2022 | 2022-08-09 | ST202207300340 | 2022-07-30 | P/FVC/MDS/1093360/2022 | 2022-08-09 |  |  |  |  | ST202207295981 | 2022-07-28 | P/FBW/MDS/1093243/2022 | 2022-08-09
1914 | EDGSL5 | EDGSL5 |  |  |  | ROTN | ATC | - |  |  | SRB(Surrender) | 2022-07-14 | EDGSL5 | 4G_FD900_EDGSL5 | 4G_FD2100_EDGSL5 | 4G_TD_EDGSL5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208308172 | 2022-08-03 | P/FVC/MDS/1093823/2022 | 2022-08-19 | ST202208319515 | 2022-08-09 | P/FVC/MDS/1093960/2022 | 2022-08-19 |  |  |  |  | ST202208305999 | 2022-08-02 | P/FBW/MDS/1093725/2022 | 2022-08-19
1915 | BODI23 | BODI23 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-07-16 | BODI23 | 4G_FD900_BODI23 | 4G_FD2100_BODI23 | 4G_TD_BODI23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297680 | 2022-07-29 | P/FVC/MDS/1093405/2022 | 2022-08-09 | ST202207298950 | 2022-07-29 | P/FVC/MDS/1093316/2022 | 2022-08-09 |  |  |  |  | ST202207295392 | 2022-07-28 | P/FBW/MDS/1093199/2022 | 2022-08-09
1916 | KLPM04 | KLPM04 |  |  |  | ROTN | Summit | I-TN-SCRM-ENB-9003 | SR-TN001029 |  | On Air | 2022-07-14 | KLPM04 | 4G_FD900_KLPM04 | 4G_FD2100_KLPM04 | 4G_TD_KLPM04 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297928 | 2022-07-29 | P/FVC/MDS/1093416/2022 | 2022-08-09 | ST202207299175 | 2022-07-29 | P/FVC/MDS/1093332/2022 | 2022-08-09 |  |  |  |  | ST202207295458 | 2022-07-28 | P/FBW/MDS/1093216/2022 | 2022-08-09
1917 | TRY420 | TRY420 |  |  |  | ROTN | ATC | TN/TC/AT/23282 | - |  | SO | 2022-07-16 | TRY420 | 4G_FD900_TRY420 | 4G_FD2100_TRY420 | 4G_TD_TRY420 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297901 | 2022-07-29 | P/FVC/MDS/1093411/2022 | 2022-08-09 | ST202207299114 | 2022-07-29 | P/FVC/MDS/1093326/2022 | 2022-08-09 |  |  |  |  | ST202207295431 | 2022-07-28 | P/FBW/MDS/1093209/2022 | 2022-08-09
1918 | TPAT14 | TPAT14 |  |  |  | ROTN | Summit | I-TN-TPTI-ENB-9061 | SR-TN001030 |  | On Air | 2022-07-16 | TPAT14 | 4G_FD900_TPAT14 | 4G_FD2100_TPAT14 | 4G_TD_TPAT14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299173 | 2022-07-29 | P/FVC/MDS/1093331/2022 | 2022-08-09 |  |  |  |  | ST202207295457 | 2022-07-28 | P/FBW/MDS/1093215/2022 | 2022-08-09
1919 | KVLKR4 | KVLKR4 |  |  |  | ROTN | Summit | I-TN-RDHP-ENB-9058 | SR-TN001031 |  | On Air | 2022-07-14 | KVLKR4 | 4G_FD900_KVLKR4 | 4G_FD2100_KVLKR4 | 4G_TD_KVLKR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297920 | 2022-07-29 | P/FVC/MDS/1093414/2022 | 2022-08-09 | ST202207299122 | 2022-07-29 | P/FVC/MDS/1093329/2022 | 2022-08-09 |  |  |  |  | ST202207295446 | 2022-07-28 | P/FBW/MDS/1093213/2022 | 2022-08-09
1920 | SVTRM4 | SVTRM4 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-07-25 | SVTRM4 | 4G_FD900_SVTRM4 | 4G_FD2100_SVTRM4 | 4G_TD_SVTRM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298958 | 2022-07-29 | P/FVC/MDS/1093319/2022 | 2022-08-09 |  |  |  |  | ST202207295403 | 2022-07-28 | P/FBW/MDS/1093202/2022 | 2022-08-09
1921 | KNJIP2 | KNJIP2 |  |  |  | ROTN | Ascend |  |  |  | On Air | 2022-07-23 | KNJIP2 | 4G_FD900_KNJIP2 | 4G_FD2100_KNJIP2 | 4G_TD_KNJIP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313088 | 2022-08-05 | P/FVC/MDS/1093836/2022 | 2022-08-19 | ST202208320604 | 2022-08-09 | P/FVC/MDS/1093974/2022 | 2022-08-19 |  |  |  |  | ST202208306018 | 2022-08-02 | P/FBW/MDS/1093739/2022 | 2022-08-19
1922 | KNPYM4 | KNPYM4 |  |  |  | ROTN | ATC |  |  |  | SO | 2022-07-25 | KNPYM4 | 4G_FD900_KNPYM4 | 4G_FD2100_KNPYM4 | 4G_TD_KNPYM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313071 | 2022-08-05 | P/FVC/MDS/1093833/2022 | 2022-08-19 | ST202208320597 | 2022-08-09 | P/FVC/MDS/1093971/2022 | 2022-08-19 |  |  |  |  | ST202208306013 | 2022-08-02 | P/FBW/MDS/1093736/2022 | 2022-08-19
1923 | CHAPM2 | CHAPM2 |  |  |  | ROTN | Indus | - | R/RES-512198 |  | On Air | 2022-07-25 | CHAPM2 | 4G_FD900_CHAPM2 | 4G_FD2100_CHAPM2 | 4G_TD_CHAPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203086085 | 2022-03-30 | P/FVC/MDS/1078189/2022 | 2022-04-15 | ST202203084999 | 2022-03-29 | P/FVC/MDS/1078143/2022 | 2022-04-15 |  |  |  |  | ST202203085821 | 2022-03-30 | P/FBW/MDS/1077897/2022 | 2022-04-14
1924 | MDKUR7 | MDKUR7 |  |  |  | ROTN | Ascend |  |  |  | SO |  | MDKUR7 | 4G_FD900_MDKUR7 | 4G_FD2100_MDKUR7 | 4G_TD_MDKUR7 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202208320613 | 2022-08-09 | P/FVC/MDS/1093976/2022 | 2022-08-19 |  |  |  |  | ST202208306021 | 2022-08-02 | P/FBW/MDS/1093741/2022 | 2022-08-19
1925 | KELA22 | KELA22 |  |  |  | CHN | ATC | TN/CH/AT/22725 | T21TN09750 |  | On air | 2022-07-16 | KELA22 | 4G_FD900_KELA22 | 4G_FD2100_KELA22 | 4G_TD_KELA22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296174 | 2022-07-28 | P/FVC/MDS/1093395/2022 | 2022-08-09 | ST202207298902 | 2022-07-29 | P/FVC/MDS/1093304/2022 | 2022-08-09 |  |  |  |  | ST202207295324 | 2022-07-28 | P/FBW/MDS/1093187/2022 | 2022-08-09
1926 | CHRO23 | CHRO23 |  |  |  | CHN | Ascend | - | - |  | SR | 2022-07-20 | CHRO23 | 4G_FD900_CHRO23 | 4G_FD2100_CHRO23 | 4G_TD_CHRO23 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299184 | 2022-07-29 | P/FVC/MDS/1093337/2022 | 2022-08-09 |  |  |  |  | ST202207295479 | 2022-07-28 | P/FBW/MDS/1093221/2022 | 2022-08-09
1927 | AMBE22 | AMBE22 |  |  |  | CHN | Ascend | - | - |  | SO | 2022-07-20 | AMBE22 | 4G_FD900_AMBE22 | 4G_FD2100_AMBE22 | 4G_TD_AMBE22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297939 | 2022-07-29 | P/FVC/MDS/1093419/2022 | 2022-08-09 | ST202207299179 | 2022-07-29 | P/FVC/MDS/1093336/2022 | 2022-08-09 |  |  |  |  | ST202207295478 | 2022-07-28 | P/FBW/MDS/1093220/2022 | 2022-08-09
1928 | KADVR2 | KADVR2 |  |  |  | CHN | Ascend |  |  |  | On air | 2022-07-16 | KADVR2 | 4G_FD900_KADVR2 | 4G_FD2100_KADVR2 | 4G_TD_KADVR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296149 | 2022-07-28 | P/FVC/MDS/1093389/2022 | 2022-08-09 | ST202207298737 | 2022-07-29 | P/FVC/MDS/1093293/2022 | 2022-08-09 |  |  |  |  | ST202207295270 | 2022-07-28 | P/FBW/MDS/1093176/2022 | 2022-08-09
1929 | SPKL14 | SPKL14 |  |  |  | CHN | ATC | - |  |  | On air | 2022-07-20 | SPKL14 | 4G_FD900_SPKL14 | 4G_FD2100_SPKL14 | 4G_TD_SPKL14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298934 | 2022-07-29 | P/FVC/MDS/1093311/2022 | 2022-08-09 |  |  |  |  | ST202207295364 | 2022-07-28 | P/FBW/MDS/1093194/2022 | 2022-08-09
1930 | OTTIA2 | OTTIA2 |  |  |  | CHN | Summit | I-TN-CHNN-ENB-3020 | SR-TN001028 |  | On air | 2022-07-20 | OTTIA2 | 4G_FD900_OTTIA2 | 4G_FD2100_OTTIA2 | 4G_TD_OTTIA2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299178 | 2022-07-29 | P/FVC/MDS/1093335/2022 | 2022-08-09 |  |  |  |  | ST202207295471 | 2022-07-28 | P/FBW/MDS/1093219/2022 | 2022-08-09
1931 | ANOOR2 | ANOOR2 |  |  |  | CHN | Indus | IN-3142423 | R/NN-671773 |  | On air | 2022-07-29 | ANOOR2 | 4G_FD900_ANOOR2 | 4G_FD2100_ANOOR2 | 4G_TD_ANOOR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202208319519 | 2022-08-09 | P/FVC/MDS/1093962/2022 | 2022-08-19 |  |  |  |  | ST202208306001 | 2022-08-02 | P/FBW/MDS/1093727/2022 | 2022-08-19
1932 | KAND38 | KAND38 |  |  |  | CHN | Indus | - | R/NN-671757 |  |  | 2022-07-20 | KAND38 | 4G_FD900_KAND38 | 4G_FD2100_KAND38 | 4G_TD_KAND38 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299121 | 2022-07-29 | P/FVC/MDS/1093328/2022 | 2022-08-09 |  |  |  |  | ST202207295438 | 2022-07-28 | P/FBW/MDS/1093211/2022 | 2022-08-09
1933 | TUT150 | TUT150 |  |  |  | ROTN | Indus | IN-3137409 | R/NN-664471 |  |  | 2022-07-16 | TUT150 | 4G_FD900_TUT150 | 4G_FD2100_TUT150 | 4G_TD_TUT150 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208327997 | 2022-08-11 | P/FVC/MDS/1093900/2022 | 2022-08-19 | ST202207298757 | 2022-07-29 | P/FVC/MDS/1093297/2022 | 2022-08-09 | ST202207298189 | 2022-07-29 | P/FVC/MDS/1093250/2022 | 2022-08-09 | ST202207295292 | 2022-07-28 | P/FBW/MDS/1093180/2022 | 2022-08-09
1934 | MDU550 | MDU550 |  |  |  | ROTN | Indus | IN-3143719 | R/NN-673573 |  |  | 2022-07-26 | MDU550 | 4G_FD900_MDU550 | 4G_FD2100_MDU550 | 4G_TD_MDU550 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207298109 | 2022-07-29 | P/FVC/MDS/1093440/2022 | 2022-08-09 | ST202207299188 | 2022-07-29 | P/FVC/MDS/1093341/2022 | 2022-08-09 | ST202207298222 | 2022-07-29 | P/FVC/MDS/1093261/2022 | 2022-08-09 | ST202207300791 | 2022-07-30 | P/FBW/MDS/1093562/2022 | 2022-08-09
1935 | KALAL7 | KALAL7 |  |  |  | ROTN | Indus | IN-3134204 | R/NN-659346 |  |  | 2022-07-16 | KALAL7 | 4G_FD900_KALAL7 | 4G_FD2100_KALAL7 | 4G_TD_KALAL7 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207296158 | 2022-07-28 | P/FVC/MDS/1093392/2022 | 2022-08-09 | ST202207298798 | 2022-07-29 | P/FVC/MDS/1093299/2022 | 2022-08-09 | ST202207298195 | 2022-07-29 | P/FVC/MDS/1093252/2022 | 2022-08-09 | ST202207295301 | 2022-07-28 | P/FBW/MDS/1093182/2022 | 2022-08-09
1936 | TNJ365 | TNJ365 |  |  |  | ROTN | Indus | IN-3134909 | R/NN-659341 |  |  | 2022-07-16 | TNJ365 | 4G_FD900_TNJ365 | 4G_FD2100_TNJ365 | 4G_TD_TNJ365 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208327998 | 2022-08-11 | P/FVC/MDS/1093901/2022 | 2022-08-19 | ST202207298766 | 2022-07-29 | P/FVC/MDS/1093298/2022 | 2022-08-09 | ST202207298190 | 2022-07-29 | P/FVC/MDS/1093251/2022 | 2022-08-09 | ST202207295293 | 2022-07-28 | P/FBW/MDS/1093181/2022 | 2022-08-09
1937 | SLM392 | SLM392 |  |  |  | ROTN | Indus | IN-3133835 | R/NN-658822 |  |  | 2022-07-25 | SLM392 | 4G_FD900_SLM392 | 4G_FD2100_SLM392 | 4G_TD_SLM392 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202201007775 | 2022-01-11 | P/FVC/MDS/1071687/2022 | 2022-01-20 | ST202207299193 | 2022-07-29 | P/FVC/MDS/1093346/2022 | 2022-08-09 | ST202207298211 | 2022-07-29 | P/FVC/MDS/1093259/2022 | 2022-08-09 | ST202207295512 | 2022-07-28 | P/FBW/MDS/1093229/2022 | 2022-08-09
1938 | LALPT5 | LALPT5 |  |  |  | ROTN | Indus | IN-3142908 | R/NN-671953 |  |  | 2022-07-29 | LALPT5 | 4G_FD900_LALPT5 | 4G_FD2100_LALPT5 | 4G_TD_LALPT5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308157 | 2022-08-03 | P/FVC/MDS/1093821/2022 | 2022-08-19 | ST202208319509 | 2022-08-09 | P/FVC/MDS/1093957/2022 | 2022-08-19 | ST202208316945 | 2022-08-08 | P/FVC/MDS/1093915/2022 | 2022-08-19 | ST202208305993 | 2022-08-02 | P/FBW/MDS/1093722/2022 | 2022-08-19
1939 | ARAK58 | ARAK58 |  |  |  | ROTN | Indus | IN-3142907 | R/NN-671949 |  |  | 2022-07-29 | ARAK58 | 4G_FD900_ARAK58 | 4G_FD2100_ARAK58 | 4G_TD_ARAK58 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308156 | 2022-08-03 | P/FVC/MDS/1093820/2022 | 2022-08-19 | ST202208319508 | 2022-08-09 | P/FVC/MDS/1093956/2022 | 2022-08-19 | ST202208316944 | 2022-08-08 | P/FVC/MDS/1093914/2022 | 2022-08-19 | ST202208305985 | 2022-08-02 | P/FBW/MDS/1093721/2022 | 2022-08-19
1940 | PKT226 | PKT226 |  |  |  | ROTN | Indus | IN-1070741 | R/RES-511388 |  |  | 2022-07-16 | PKT226 | 4G_FD900_PKT226 | 4G_FD2100_PKT226 | 4G_TD_PKT226 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208328006 | 2022-08-11 | P/FVC/MDS/1093902/2022 | 2022-08-19 | ST202207298671 | 2022-07-29 | P/FVC/MDS/1093284/2022 | 2022-08-09 | ST202207298184 | 2022-07-29 | P/FVC/MDS/1093249/2022 | 2022-08-09 | ST202207295231 | 2022-07-28 | P/FBW/MDS/1093167/2022 | 2022-08-09
1941 | MDU532 | MDU532 |  |  |  | ROTN | Ascend | 6329 | - |  |  | 2022-07-16 | MDU532 | 4G_FD900_MDU532 | 4G_FD2100_MDU532 | 4G_TD_MDU532 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298799 | 2022-07-29 | P/FVC/MDS/1093300/2022 | 2022-08-09 |  |  |  |  | ST202207295302 | 2022-07-28 | P/FBW/MDS/1093183/2022 | 2022-08-09
1942 | AVOOR4 | AVOOR4 |  |  |  | ROTN | Indus | IN-3133824 | R/NN-658812 |  |  | 2022-07-25 | AVOOR4 | 4G_FD900_AVOOR4 | 4G_FD2100_AVOOR4 | 4G_TD_AVOOR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297993 | 2022-07-29 | P/FVC/MDS/1093428/2022 | 2022-08-09 | ST202207299197 | 2022-07-29 | P/FVC/MDS/1093350/2022 | 2022-08-09 |  |  |  |  | ST202207295940 | 2022-07-28 | P/FBW/MDS/1093233/2022 | 2022-08-09
1943 | TRY403 | TRY403 |  |  |  | ROTN | Indus | IN-3131827 | R/NN-655923 |  |  | 2022-07-16 | TRY403 | 4G_FD900_TRY403 | 4G_FD2100_TRY403 | 4G_TD_TRY403 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207296095 | 2022-07-28 | P/FVC/MDS/1093379/2022 | 2022-08-09 | ST202207298645 | 2022-07-29 | P/FVC/MDS/1093281/2022 | 2022-08-09 | ST202207298183 | 2022-07-29 | P/FVC/MDS/1093248/2022 | 2022-08-09 | ST202207295208 | 2022-07-28 | P/FBW/MDS/1093164/2022 | 2022-08-09
1944 | CHPRM2 | CHPRM2 |  |  |  | ROTN | Indus | IN-3144173 | R/NN-675623 |  |  | 2022-07-29 | CHPRM2 | 4G_FD900_CHPRM2 | 4G_FD2100_CHPRM2 | 4G_TD_CHPRM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308242 | 2022-08-03 | P/FVC/MDS/1093826/2022 | 2022-08-19 | ST202208319523 | 2022-08-09 | P/FVC/MDS/1093964/2022 | 2022-08-19 | ST202208316985 | 2022-08-08 | P/FVC/MDS/1093916/2022 | 2022-08-19 | ST202208306003 | 2022-08-02 | P/FBW/MDS/1093729/2022 | 2022-08-19
1945 | KIRUP8 | KIRUP8 |  |  |  | ROTN | Indus | IN-3134814 | R/NN-659697 |  |  | 2022-07-29 | KIRUP8 | 4G_FD900_KIRUP8 | 4G_FD2100_KIRUP8 | 4G_TD_KIRUP8 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308042 | 2022-08-03 | P/FVC/MDS/1093810/2022 | 2022-08-19 | ST202208318934 | 2022-08-09 | P/FVC/MDS/1093945/2022 | 2022-08-19 | ST202208316882 | 2022-08-08 | P/FVC/MDS/1093904/2022 | 2022-08-19 | ST202208305974 | 2022-08-02 | P/FBW/MDS/1093710/2022 | 2022-08-19
1946 | PNRI07 | PNRI07 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-07-29 | PNRI07 | 4G_FD900_PNRI07 | 4G_FD2100_PNRI07 | 4G_TD_PNRI07 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308064 | 2022-08-03 | P/FVC/MDS/1093817/2022 | 2022-08-19 | ST202208319004 | 2022-08-09 | P/FVC/MDS/1093953/2022 | 2022-08-19 | ST202208316924 | 2022-08-08 | P/FVC/MDS/1093911/2022 | 2022-08-19 | ST202208305982 | 2022-08-02 | P/FBW/MDS/1093718/2022 | 2022-08-19
1947 | SVLGD2 | SVLGD2 |  |  |  | ROTN | Indus | IN-3138561 | R/NN-662885 |  |  | 2022-07-16 | SVLGD2 | 4G_FD900_SVLGD2 | 4G_FD2100_SVLGD2 | 4G_TD_SVLGD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296151 | 2022-07-28 | P/FVC/MDS/1093391/2022 | 2022-08-09 | ST202207298756 | 2022-07-29 | P/FVC/MDS/1093296/2022 | 2022-08-09 |  |  |  |  | ST202207295285 | 2022-07-28 | P/FBW/MDS/1093179/2022 | 2022-08-09
1948 | VRCM41 | VRCM41 |  |  |  | ROTN | Summit | I-TN-VDCM-ENB-0007 | SR-TN001049 |  |  | 2022-07-29 | VRCM41 | 4G_FD900_VRCM41 | 4G_FD2100_VRCM41 | 4G_TD_VRCM41 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313095 | 2022-08-05 | P/FVC/MDS/1093838/2022 | 2022-08-19 | ST202208320614 | 2022-08-09 | P/FVC/MDS/1093977/2022 | 2022-08-19 | ST202208316987 | 2022-08-08 | P/FVC/MDS/1093917/2022 | 2022-08-19 | ST202208306022 | 2022-08-02 | P/FBW/MDS/1093742/2022 | 2022-08-19
1949 | NDKDI2 | NDKDI2 |  |  |  | ROTN | Summit | I-TN-NGPM-ENB-9025 | SR-TN001015 |  |  | 2022-07-29 | NDKDI2 | 4G_FD900_NDKDI2 | 4G_FD2100_NDKDI2 | 4G_TD_NDKDI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308053 | 2022-08-03 | P/FVC/MDS/1093815/2022 | 2022-08-19 | ST202208318989 | 2022-08-09 | P/FVC/MDS/1093950/2022 | 2022-08-19 | ST202208316898 | 2022-08-08 | P/FVC/MDS/1093908/2022 | 2022-08-19 | ST202208305979 | 2022-08-02 | P/FBW/MDS/1093715/2022 | 2022-08-19
1950 | VEDUR2 | VEDUR2 |  |  |  | ROTN | Ascend | TNBS0021 | - |  |  | 2022-07-25 | VEDUR2 | 4G_FD900_VEDUR2 | 4G_FD2100_VEDUR2 | 4G_TD_VEDUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207297961 | 2022-07-29 | P/FVC/MDS/1093424/2022 | 2022-08-09 | ST202207299191 | 2022-07-29 | P/FVC/MDS/1093344/2022 | 2022-08-09 | ST202207298209 | 2022-07-29 | P/FVC/MDS/1093257/2022 | 2022-08-09 | ST202207295506 | 2022-07-28 | P/FBW/MDS/1093227/2022 | 2022-08-09
1951 | TANK05 | TANK05 |  |  |  | ROTN | Indus | IN-3134673 | R/NN-659260 |  |  | 2022-07-29 | TANK05 | 4G_FD900_TANK05 | 4G_FD2100_TANK05 | 4G_TD_TANK05 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202109522073 | 2021-09-16 | P/FVC/MDS/1062411/2021 | 2021-09-23 | ST202109522201 | 2021-09-16 | P/FVC/MDS/1062459/2021 | 2021-09-23 | ST202109530290 | ST202109530290 | P/FVC/MDS/1063050/2021 | 2021-10-01 | ST202109522256 | 2021-09-16 | P/FBW/MDS/1062507/2021 | 2021-09-23
1952 | RAJAK8 | RAJAK8 |  |  |  | ROTN | Indus | IN-3134146 | R/NN-659275 |  |  | 2022-07-29 | RAJAK8 | 4G_FD900_RAJAK8 | 4G_FD2100_RAJAK8 | 4G_TD_RAJAK8 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308044 | 2022-08-03 | P/FVC/MDS/1093812/2022 | 2022-08-19 | ST202208318973 | 2022-08-09 | P/FVC/MDS/1093947/2022 | 2022-08-19 | ST202208316883 | 2022-08-08 | P/FVC/MDS/1093905/2022 | 2022-08-19 | ST202208305976 | 2022-08-02 | P/FBW/MDS/1093712/2022 | 2022-08-19
1953 | ANAK19 | ANAK19 |  |  |  | ROTN | Indus | IN-3002375 | R/RES-511389 |  |  | 2022-07-29 | ANAK19 | 4G_FD900_ANAK19 | 4G_FD2100_ANAK19 | 4G_TD_ANAK19 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442294 | 2022-09-18 | P/FVC/MDS/1098039/2022 | 2022-09-27 | ST202209445692 | 2022-09-19 | P/FVC/MDS/1098126/2022 | 2022-09-27 | ST202209432079 | 2022-09-17 | P/FVC/MDS/1097998/2022 | 2022-09-27 | ST202209431743 | 2022-09-17 | P/FVC/MDS/1097943/2022 | 2022-09-27
1954 | ANNA25 | ANNA25 |  |  |  | ROTN | ATC | TN/CH/TT/12610 | - |  |  | 2022-07-25 | ANNA25 | 4G_FD900_ANNA25 | 4G_FD2100_ANNA25 | 4G_TD_ANNA25 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207297949 | 2022-07-29 | P/FVC/MDS/1093422/2022 | 2022-08-09 | ST202207299189 | 2022-07-29 | P/FVC/MDS/1093342/2022 | 2022-08-09 | ST202207298202 | 2022-07-29 | P/FVC/MDS/1093255/2022 | 2022-08-09 | ST202207295499 | 2022-07-28 | P/FBW/MDS/1093225/2022 | 2022-08-09
1955 | TURNB4 | TURNB4 |  |  |  | ROTN | Indus | IN-3137410 | R/NN-664491 |  |  | 2022-07-29 | TURNB4 | 4G_FD900_TURNB4 | 4G_FD2100_TURNB4 | 4G_TD_TURNB4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210643008 | 2022-10-28 | P/FVC/MDS/1114501/2022 | 2022-11-06 | ST202210651716 | 2022-10-29 | P/FVC/MDS/1114549/2022 | 2022-11-06 | ST202210607871 | 2022-10-20 | P/FVC/MDS/1093906/2022 | 2022-08-19 | ST202210637038 | 2022-10-27 | P/FBW/MDS/1114442/2022 | 2022-11-06
1956 | MANI22 | MANI22 |  |  |  | ROTN | Indus | IN-3123549 | R/RES-510835 |  |  | 2022-07-29 | MANI22 | 4G_FD900_MANI22 | 4G_FD2100_MANI22 | 4G_TD_MANI22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208308043 | 2022-08-03 | P/FVC/MDS/1093811/2022 | 2022-08-19 | ST202208318935 | 2022-08-09 | P/FVC/MDS/1093946/2022 | 2022-08-19 | ST202212858136 | 2022-12-27 | 0 |  | ST202208305975 | 2022-08-02 | P/FBW/MDS/1093711/2022 | 2022-08-19
1957 | PONM10 | PONM10 |  |  |  | ROTN | Indus | IN-3136467 | R/NN-664408 |  |  | 2022-07-25 | PONM10 | 4G_FD900_PONM10 | 4G_FD2100_PONM10 | 4G_TD_PONM10 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207297960 | 2022-07-29 | P/FVC/MDS/1093423/2022 | 2022-08-09 | ST202207299190 | 2022-07-29 | P/FVC/MDS/1093343/2022 | 2022-08-09 | ST202207298203 | 2022-07-29 | P/FVC/MDS/1093256/2022 | 2022-08-09 | ST202207295505 | 2022-07-28 | P/FBW/MDS/1093226/2022 | 2022-08-09
1958 | SHOL52 | SHOL52 |  |  |  | ROTN | Indus | IN-3138528 | R/NN-667174 |  |  | 2022-07-29 | SHOL52 | 4G_FD900_SHOL52 | 4G_FD2100_SHOL52 | 4G_TD_SHOL52 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308065 | 2022-08-03 | P/FVC/MDS/1093818/2022 | 2022-08-19 | ST202208319005 | 2022-08-09 | P/FVC/MDS/1093954/2022 | 2022-08-19 | ST202208316925 | 2022-08-08 | P/FVC/MDS/1093912/2022 | 2022-08-19 | ST202208305983 | 2022-08-02 | P/FBW/MDS/1093719/2022 | 2022-08-19
1959 | NGPM24 | NGPM24 |  |  |  | ROTN | Indus | IN-3138662 | R/NN-666662 |  |  | 2022-07-25 | NGPM24 | 4G_FD900_NGPM24 | 4G_FD2100_NGPM24 | 4G_TD_NGPM24 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207297974 | 2022-07-29 | P/FVC/MDS/1093426/2022 | 2022-08-09 | ST202207299194 | 2022-07-29 | P/FVC/MDS/1093347/2022 | 2022-08-09 | ST202207298221 | 2022-07-29 | P/FVC/MDS/1093260/2022 | 2022-08-09 | ST202208314937 | 2022-08-07 | P/FBW/MDS/1093680/2022 | 2022-08-19
1960 | KUMB93 | KUMB93 |  |  |  | ROTN | Indus | IN-3138556 | R/NN-659640 |  |  | 2022-07-29 | KUMB93 | 4G_FD900_KUMB93 | 4G_FD2100_KUMB93 | 4G_TD_KUMB93 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208328007 | 2022-08-11 | P/FVC/MDS/1093903/2022 | 2022-08-19 | ST202208318990 | 2022-08-09 | P/FVC/MDS/1093951/2022 | 2022-08-19 | ST202208316917 | 2022-08-08 | P/FVC/MDS/1093909/2022 | 2022-08-19 | ST202208305980 | 2022-08-02 | P/FBW/MDS/1093716/2022 | 2022-08-19
1961 | MDU545 | MDU545 |  |  |  | ROTN | Indus | IN-3138666 | R/NN-666896 |  |  | 2022-07-18 | MDU545 | 4G_FD900_MDU545 | 4G_FD2100_MDU545 | 4G_TD_MDU545 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207297659 | 2022-07-29 | P/FVC/MDS/1093400/2022 | 2022-08-09 | ST202207298929 | 2022-07-29 | P/FVC/MDS/1093310/2022 | 2022-08-09 | ST202207298197 | 2022-07-29 | P/FVC/MDS/1093254/2022 | 2022-08-09 | ST202207295363 | 2022-07-28 | P/FBW/MDS/1093193/2022 | 2022-08-09
1962 | BESA12 | BESA12 |  |  |  | ROTN | TVI | BSTNCHN1884 | - |  |  | 2022-07-25 | BESA12 | 4G_FD900_BESA12 | 4G_FD2100_BESA12 | 4G_TD_BESA12 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207297973 | 2022-07-29 | P/FVC/MDS/1093425/2022 | 2022-08-09 | ST202207299192 | 2022-07-29 | P/FVC/MDS/1093345/2022 | 2022-08-09 | ST202207298210 | 2022-07-29 | P/FVC/MDS/1093258/2022 | 2022-08-09 | ST202207295507 | 2022-07-28 | P/FBW/MDS/1093228/2022 | 2022-08-09
1963 | RGNPM2 | RGNPM2 |  |  |  | ROTN | ATC | TN/TR/AT/23244 | - |  |  | 2022-07-29 | RGNPM2 | 4G_FD900_RGNPM2 | 4G_FD2100_RGNPM2 | 4G_TD_RGNPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208308063 | 2022-08-03 | P/FVC/MDS/1093816/2022 | 2022-08-19 | ST202208318991 | 2022-08-09 | P/FVC/MDS/1093952/2022 | 2022-08-19 | ST202208316918 | 2022-08-08 | P/FVC/MDS/1093910/2022 | 2022-08-19 | ST202208305981 | 2022-08-02 | P/FBW/MDS/1093717/2022 | 2022-08-19
1964 | AVAD36 | AVAD36 |  |  |  | ROTN | TVI | TATNCHN0367 | - |  |  | 2022-07-16 | AVAD36 | 4G_FD900_AVAD36 | 4G_FD2100_AVAD36 | 4G_TD_AVAD36 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207296159 | 2022-07-28 | P/FVC/MDS/1093393/2022 | 2022-08-09 | ST202207298811 | 2022-07-29 | P/FVC/MDS/1093301/2022 | 2022-08-09 | ST202207298196 | 2022-07-29 | P/FVC/MDS/1093253/2022 | 2022-08-09 | ST202207295303 | 2022-07-28 | P/FBW/MDS/1093184/2022 | 2022-08-09
1965 | PDY304 | PDY304 | Puducherry | Trichy |  | ROTN | Own |  |  |  | RFAI | 2022-08-02 | PDY304 | 4G_FD900_PDY304 | 4G_FD2100_PDY304 | 4G_TD_PDY304 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313271 | 2022-08-05 | P/FVC/MDS/1093868/2022 | 2022-08-19 | ST202208327119 | 2022-08-11 | P/FVC/MDS/1094016/2022 | 2022-08-19 |  |  |  |  | ST202208307097 | 2022-08-03 | P/FBW/MDS/1093780/2022 | 2022-08-19
1966 | TUT101 | TUT101 | Thoothukkudi | Madurai |  | ROTN | ATC | - | - |  | SO | 2022-07-29 | TUT101 | 4G_FD900_TUT101 | 4G_FD2100_TUT101 | 4G_TD_TUT101 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106363086 | 2021-06-26 | P/FVC/MDS/1050092/2021 | 2021-08-09 | ST202104148072 | 2021-04-15 | P/FVC/MDS/1018020/2021 | 2021-05-15 | ST202212839566 | 2022-12-22 |  |  | ST202104148946 | 2021-04-15 | P/FBW/MDS/1018079/2021 | 2021-05-16
1967 | KNKI07 | KNKI07 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3146644 | R/NN-677633 |  |  | 2022-08-18 | KNKI07 | 4G_FD900_KNKI07 | 4G_FD2100_KNKI07 | 4G_TD_KNKI07 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202110560523 | 2021-10-14 | P/FVC/MDS/1063751/2021 | 2021-10-22 | ST202110554916 | 2021-10-08 | P/FVC/MDS/1063764/2021 | 2021-10-22 | ST202110560498 | 2021-10-14 | P/FVC/MDS/1063760/2021 | 2021-10-22 | ST202110560355 | 2021-10-14 | P/FVC/MDS/1063703/2021 | 2021-10-22
1968 | MDTI22 | MDTI22 | Nagapattinam | Trichy |  | ROTN | ATC | TN/NA/AT/23383 | T22TN05280 |  | SRB(Surrender) | 2022-08-18 | MDTI22 | 4G_FD900_MDTI22 | 4G_FD2100_MDTI22 | 4G_TD_MDTI22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361054 | 2022-08-28 | P/FVC/MDS/1094682/2022 | 2022-09-07 | ST202208364623 | 2022-08-29 | P/FVC/MDS/1094747/2022 | 2022-09-07 |  |  |  |  | ST202208355544 | 2022-08-26 | P/FBW/MDS/1094617/2022 | 2022-09-07
1969 | NGL144 | NGL144 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3140074 | R/NN-669014 |  | SO ( Withdrwan request sent to SCM ) | 2022-07-16 | NGL144 | 4G_FD900_NGL144 | 4G_FD2100_NGL144 | 4G_TD_NGL144 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296176 | 2022-07-28 | P/FVC/MDS/1093397/2022 | 2022-08-09 | ST202207298909 | 2022-07-29 | P/FVC/MDS/1093306/2022 | 2022-08-09 |  |  |  |  | ST202207295328 | 2022-07-28 | P/FBW/MDS/1093189/2022 | 2022-08-09
1970 | VSPM09 | VSPM09 | Tirunelveli | Madurai |  | ROTN | Indus |  | R/NN-669054 |  | SRB(Surrender) | 2022-08-02 | VSPM09 | 4G_FD900_VSPM09 | 4G_FD2100_VSPM09 | 4G_TD_VSPM09 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313316 | 2022-08-05 | P/FVC/MDS/1093873/2022 | 2022-08-19 | ST202208327144 | 2022-08-11 | P/FVC/MDS/1094021/2022 | 2022-08-19 |  |  |  |  | ST202208307111 | 2022-08-03 | P/FBW/MDS/1093785/2022 | 2022-08-19
1971 | BODI18 | BODI18 | Theni | Madurai |  | ROTN | Ascend | - | - |  | SR | 2022-07-20 | BODI18 | 4G_FD900_BODI18 | 4G_FD2100_BODI18 | 4G_TD_BODI18 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297688 | 2022-07-29 | P/FVC/MDS/1093406/2022 | 2022-08-09 | ST202207298954 | 2022-07-29 | P/FVC/MDS/1093318/2022 | 2022-08-09 |  |  |  |  | ST202207295402 | 2022-07-28 | P/FBW/MDS/1093201/2022 | 2022-08-09
1972 | DGL126 | DGL126 | Dindigul | Coimbatore |  | ROTN | Indus | IN-3142893 | R/NN-666188 |  | SO | 2022-08-12 | DGL126 | 4G_FD900_DGL126 | 4G_FD2100_DGL126 | 4G_TD_DGL126 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334531 | 2022-08-15 | P/FVC/MDS/1094171/2022 | 2022-08-25 | ST202208340417 | 2022-08-18 | P/FVC/MDS/1094347/2022 | 2022-08-25 |  |  |  |  | ST202208331396 | 2022-08-13 | P/FBW/MDS/1094246/2022 | 2022-08-25
1973 | MGDI17 | MGDI17 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | SR | 2022-08-12 | MGDI17 | 4G_FD900_MGDI17 | 4G_FD2100_MGDI17 | 4G_TD_MGDI17 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202108404988 | 2021-08-02 | P/FVC/MDS/1052807/2021 | 2021-08-20 | ST202108407513 | 2021-08-03 | P/FVC/MDS/1056761/2021 | 2021-09-09 |  |  |  |  | ST202108407163 | 2021-08-03 | P/FBW/MDS/1052849/2021 | 2021-08-20
1974 | TRY335 | TRY335 | Tiruchirappalli | Trichy |  | ROTN | Ascend | TN/TR/AT/23066 | T22TN01100 |  | On Air | 2022-07-25 | TRY335 | 4G_FD900_TRY335 | 4G_FD2100_TRY335 | 4G_TD_TRY335 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298008 | 2022-07-29 | P/FVC/MDS/1093429/2022 | 2022-08-09 | ST202207299199 | 2022-07-29 | P/FVC/MDS/1093352/2022 | 2022-08-09 | ST202211757954 | 2022-11-22 | P/FVC/MDS/1116759/2022 | 2022-11-29 | ST202207295955 | 2022-07-28 | P/FBW/MDS/1093235/2022 | 2022-08-09
1975 | PDY400 | PDY400 | Puducherry | Trichy |  | ROTN | Indus | IN-3146906 | R/NN-677913 |  | SRB(Surrender) | 2022-08-12 | PDY400 | 4G_FD900_PDY400 | 4G_FD2100_PDY400 | 4G_TD_PDY400 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208334555 | 2022-08-15 | P/FVC/MDS/1094177/2022 | 2022-08-25 | ST202208340472 | 2022-08-18 | P/FVC/MDS/1094353/2022 | 2022-08-25 |  |  |  |  | ST202208331409 | 2022-08-13 | P/FBW/MDS/1094252/2022 | 2022-08-25
1976 | CBE812 | CBE812 | Coimbatore | Coimbatore |  | ROTN | Airtel | - | - |  | SO | 2022-08-24 | CBE812 | 4G_FD900_CBE812 | 4G_FD2100_CBE812 | 4G_TD_CBE812 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209402563 | 2022-09-08 | P/FVC/MDS/1096539/2022 | 2022-09-16 | ST202209403804 | 2022-09-08 | P/FVC/MDS/1096448/2022 | 2022-09-16 | ST202212839565 | 2022-12-22 |  |  | ST202209398948 | 2022-09-07 | P/FVC/MDS/1096354/2022 | 2022-09-16
1977 | SVPT29 | SVPT29 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/22045 | T20TN04054 |  | SRB(Surrender) | 2022-07-29 | SVPT29 | 4G_FD900_SVPT29 | 4G_FD2100_SVPT29 | 4G_TD_SVPT29 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313070 | 2022-08-05 | P/FVC/MDS/1093832/2022 | 2022-08-19 | ST202208320596 | 2022-08-09 | P/FVC/MDS/1093970/2022 | 2022-08-19 |  |  |  |  | ST202208306012 | 2022-08-02 | P/FBW/MDS/1093735/2022 | 2022-08-19
1978 | HSR181 | HSR181 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3131825 | R/NN-655337 |  | SO | 2022-07-16 | HSR181 | 4G_FD900_HSR181 | 4G_FD2100_HSR181 | 4G_TD_HSR181 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207274245 | 2022-07-20 | P/FVC/MDS/1093368/2022 | 2022-08-09 | ST202207274189 | 2022-07-20 | P/FVC/MDS/1093270/2022 | 2022-08-09 |  |  |  |  | ST202207293768 | 2022-07-28 | P/FBW/MDS/1093153/2022 | 2022-08-09
1979 | DRPM22 | DRPM22 | Tiruppur | Coimbatore |  | ROTN | Ascend | - | - |  | On Air | 2022-08-12 | DRPM22 | 4G_FD900_DRPM22 | 4G_FD2100_DRPM22 | 4G_TD_DRPM22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334923 | 2022-08-16 | P/FVC/MDS/1094181/2022 | 2022-08-25 | ST202208340518 | 2022-08-18 | P/FVC/MDS/1094357/2022 | 2022-08-25 |  |  |  |  | ST202208331414 | 2022-08-13 | P/FBW/MDS/1094256/2022 | 2022-08-25
1980 | GUDA03 | GUDA03 | Theni | Madurai |  | ROTN | Indus | IN-3126634 | R/NN-648640 |  | SRB(Surrender) | 2022-06-16 | GUDA03 | 4G_FD900_GUDA03 | 4G_FD2100_GUDA03 | 4G_TD_GUDA03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202206197719 | 2022-06-24 | P/FVC/MDS/1085762/2022 | 2022-07-05 | ST202206196190 | 2022-06-23 | P/FVC/MDS/1085728/2022 | 2022-07-05 |  |  |  |  | ST202206196441 | 2022-06-23 | P/FBW/MDS/1085690/2022 | 2022-07-05
1981 | MDU456 | MDU456 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/23199 | T22TN02161 |  | On Air | 2022-07-20 | MDU456 | 4G_FD900_MDU456 | 4G_FD2100_MDU456 | 4G_TD_MDU456 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298920 | 2022-07-29 | P/FVC/MDS/1093308/2022 | 2022-08-09 |  |  |  |  | ST202207295336 | 2022-07-28 | P/FBW/MDS/1093191/2022 | 2022-08-09
1982 | PKT196 | PKT196 | Tirunelveli | Madurai |  | ROTN | Indus |  | R/NN-675760 |  | On Air | 2022-08-02 | PKT196 | 4G_FD900_PKT196 | 4G_FD2100_PKT196 | 4G_TD_PKT196 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362734 | 2021-06-26 | P/FVC/MDS/1050020/2021 | 2021-08-09 | ST202208327177 | 2022-08-11 | P/FVC/MDS/1094026/2022 | 2022-08-19 |  |  |  |  | ST202208307146 | 2022-08-03 | P/FBW/MDS/1093789/2022 | 2022-08-19
1983 | KRKL31 | KRKL31 | Nagapattinam | Trichy |  | ROTN | Indus | IN-1303064 | R/RES-512423 |  | On Air | 2022-08-10 | KRKL31 | 4G_FD900_KRKL31 | 4G_FD2100_KRKL31 | 4G_TD_KRKL31 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331435 | 2022-08-13 | P/FVC/MDS/1094139/2022 | 2022-08-25 | ST202208339395 | 2022-08-18 | P/FVC/MDS/1094315/2022 | 2022-08-25 |  |  |  |  | ST202208331306 | 2022-08-13 | P/FBW/MDS/1094214/2022 | 2022-08-25
1984 | SMVRI3 | SMVRI3 | Tirunelveli | Madurai |  | ROTN | Indus |  | R/NN-677634 |  | SO | 2022-08-10 | SMVRI3 | 4G_FD900_SMVRI3 | 4G_FD2100_SMVRI3 | 4G_TD_SMVRI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362788 | 2021-06-26 | P/FVC/MDS/1050048/2021 | 2021-08-09 | ST202208339409 | 2022-08-18 | P/FVC/MDS/1094318/2022 | 2022-08-25 |  |  |  |  | ST202208331317 | 2022-08-13 | P/FBW/MDS/1094217/2022 | 2022-08-25
1985 | ILPUR3 | ILPUR3 | Pudukkottai | Trichy |  | ROTN | ATC | TN/PU/AT/23215 | - |  | On Air | 2022-07-05 | ILPUR3 | 4G_FD900_ILPUR3 | 4G_FD2100_ILPUR3 | 4G_TD_ILPUR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207251967 | 2022-07-13 | P/FVC/MDS/1088647/2022 | 2022-07-25 | ST202207254676 | 2022-07-14 | P/FVC/MDS/1088701/2022 | 2022-07-25 |  |  |  |  | ST202207247244 | 2022-07-12 | P/FBW/MDS/1088590/2022 | 2022-07-25
1986 | UDPLM3 | UDPLM3 | Ariyalur | Trichy |  | ROTN | Ascend |  |  |  | SO | 2022-08-10 | UDPLM3 | 4G_FD900_UDPLM3 | 4G_FD2100_UDPLM3 | 4G_TD_UDPLM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106366856 | 2021-06-30 | P/FVC/MDS/1050202/2021 | 2021-08-09 | ST202208339323 | 2022-08-18 | P/FVC/MDS/1094305/2022 | 2022-08-25 |  |  |  |  | ST202208331289 | 2022-08-13 | P/FBW/MDS/1094204/2022 | 2022-08-25
1987 | CBE962 | CBE962 | Coimbatore | Coimbatore |  | ROTN | Airtel | - | - |  | SO | 2022-08-24 | CBE962 | 4G_FD900_CBE962 | 4G_FD2100_CBE962 | 4G_TD_CBE962 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681027 | 2022-11-04 | P/FVC/MDS/1114803/2022 | 2022-11-22 | ST202211685840 | 2022-11-07 | P/FVC/MDS/1114645/2022 | 2022-11-15 | ST202212839570 | 22-12-2022 |  |  | ST202211685489 | 2022-11-07 | P/FBW/MDS/1114725/2022 | 2022-11-16
1988 | ACHRP1 | ACHRP1 | Kancheepuram | Chennai |  | ROTN | Ascend | IN-1532003 | R/NN-559563 |  | SO | 2022-08-02 | ACHRP1 | 4G_FD900_ACHRP1 | 4G_FD2100_ACHRP1 | 4G_TD_ACHRP1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106360479 | 2021-06-24 | P/FVC/MDS/1049890/2021 | 2021-08-09 | ST202208327103 | 2022-08-11 | P/FVC/MDS/1094014/2022 | 2022-08-19 |  |  |  |  | ST202208307085 | 2022-08-03 | P/FBW/MDS/1093778/2022 | 2022-08-19
1989 | KPMPT5 | KPMPT5 | Tiruchirappalli | Trichy |  | ROTN | Indus |  | R/NN-677917 |  | SRB(Surrender) | 2022-08-10 | KPMPT5 | 4G_FD900_KPMPT5 | 4G_FD2100_KPMPT5 | 4G_TD_KPMPT5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334384 | 2022-08-15 | P/FVC/MDS/1094158/2022 | 2022-08-25 | ST202208339885 | 2022-08-18 | P/FVC/MDS/1094334/2022 | 2022-08-25 |  |  |  |  | ST202208331361 | 2022-08-13 | P/FBW/MDS/1094233/2022 | 2022-08-25
1990 | KADATT | KADATT | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/23308 | T22TN04299 |  | SRB(Surrender) | 2022-08-24 | KADATT | 4G_FD900_KADATT | 4G_FD2100_KADATT | 4G_TD_KADATT | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202107371830 | 2021-07-03 | P/FVC/MDS/1051798/2021 | 2021-08-15 | ST202105293978 | 2021-05-25 | P/FVC/MDS/1036611/2021 | 2021-06-23 | ST202105294911 | 2021-05-25 | P/FVC/MDS/1036484/2021 | 2021-06-23 | ST202108430479 | 2021-08-17 | P/FBW/MDS/1056039/2021 | 2021-09-07
1991 | PDY401 | PDY401 | Puducherry | Trichy |  | ROTN | Indus |  | R/NN-677908 |  |  | 2022-08-10 | PDY401 | 4G_FD900_PDY401 | 4G_FD2100_PDY401 | 4G_TD_PDY401 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334374 | 2022-08-15 | P/FVC/MDS/1094156/2022 | 2022-08-25 | ST202208339629 | 2022-08-18 | P/FVC/MDS/1094332/2022 | 2022-08-25 |  |  |  |  | ST202208331352 | 2022-08-13 | P/FBW/MDS/1094231/2022 | 2022-08-25
1992 | SATYTS | SATYTS | Thoothukkudi | Madurai |  | ROTN | ATC | - | - |  | On Air | 2022-08-02 | SATYTS | 4G_FD900_SATYTS | 4G_FD2100_SATYTS | 4G_TD_SATYTS | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313748 | 2022-08-06 | P/FVC/MDS/1093893/2022 | 2022-08-19 | ST202208327770 | 2022-08-11 | P/FVC/MDS/1094049/2022 | 2022-08-19 |  |  |  |  | ST202208307581 | 2022-08-03 | P/FBW/MDS/1093808/2022 | 2022-08-19
1993 | SPD109 | SPD109 | Kancheepuram | Chennai |  | ROTN | Airtel | - | - |  | SO | 2022-08-18 | SPD109 | 4G_FD900_SPD109 | 4G_FD2100_SPD109 | 4G_TD_SPD109 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360979 | 2022-08-28 | P/FVC/MDS/1094651/2022 | 2022-09-07 | ST202208364548 | 2022-08-29 | P/FVC/MDS/1094716/2022 | 2022-09-07 |  |  |  |  | ST202208355394 | 2022-08-26 | P/FBW/MDS/1094588/2022 | 2022-09-07
1994 | PDY402 | PDY402 | Viluppuram | Trichy |  | ROTN | Indus | IN-3148120 | R/NN-680257 |  | SO | 2022-08-18 | PDY402 | 4G_FD900_PDY402 | 4G_FD2100_PDY402 | 4G_TD_PDY402 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360990 | 2022-08-28 | P/FVC/MDS/1094657/2022 | 2022-09-07 | ST202208364564 | 2022-08-29 | P/FVC/MDS/1094722/2022 | 2022-09-07 |  |  |  |  | ST202208355416 | 2022-08-26 | P/FBW/MDS/1094594/2022 | 2022-09-07
1995 | VADVEL | VADVEL | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-08-12 | VADVEL | 4G_FD900_VADVEL | 4G_FD2100_VADVEL | 4G_TD_VADVEL | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334393 | 2022-08-15 | P/FVC/MDS/1094160/2022 | 2022-08-25 | ST202208339887 | 2022-08-18 | P/FVC/MDS/1094336/2022 | 2022-08-25 |  |  |  |  | ST202208331366 | 2022-08-13 | P/FBW/MDS/1094235/2022 | 2022-08-25
1996 | VELRAM | VELRAM | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/23217 | - |  | On Air | 2022-07-16 | VELRAM | 4G_FD900_VELRAM | 4G_FD2100_VELRAM | 4G_TD_VELRAM | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296102 | 2022-07-28 | P/FVC/MDS/1093381/2022 | 2022-08-09 | ST202207298660 | 2022-07-29 | P/FVC/MDS/1093283/2022 | 2022-08-09 |  |  |  |  | ST202207295210 | 2022-07-28 | P/FBW/MDS/1093166/2022 | 2022-08-09
1997 | KUNNA3 | KUNNA3 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3142909 | R/NN-671999 |  |  | 2022-07-20 | KUNNA3 | 4G_FD900_KUNNA3 | 4G_FD2100_KUNNA3 | 4G_TD_KUNNA3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297913 | 2022-07-29 | P/FVC/MDS/1093413/2022 | 2022-08-09 | ST202207300568 | 2022-07-30 | P/FVC/MDS/1093539/2022 | 2022-08-09 |  |  |  |  | ST202207295445 | 2022-07-28 | P/FBW/MDS/1093212/2022 | 2022-08-09
1998 | COLAC2 | COLAC2 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/22905 | T21TN11366 |  | On Air | 2022-07-05 | COLAC2 | 4G_FD900_COLAC2 | 4G_FD2100_COLAC2 | 4G_TD_COLAC2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207251985 | 2022-07-13 | P/FVC/MDS/1088649/2022 | 2022-07-25 | ST202207254685 | 2022-07-14 | P/FVC/MDS/1088703/2022 | 2022-07-25 |  |  |  |  | ST202207247281 | 2022-07-12 | P/FBW/MDS/1088592/2022 | 2022-07-25
1999 | THPTI2 | THPTI2 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/23315 | T22TN04306 |  | On Air | 2022-08-12 | THPTI2 | 4G_FD900_THPTI2 | 4G_FD2100_THPTI2 | 4G_TD_THPTI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334530 | 2022-08-15 | P/FVC/MDS/1094170/2022 | 2022-08-25 | ST202208340345 | 2022-08-18 | P/FVC/MDS/1094346/2022 | 2022-08-25 |  |  |  |  | ST202208331392 | 2022-08-13 | P/FBW/MDS/1094245/2022 | 2022-08-25
2000 | NADUV4 | NADUV4 | Cuddalore | Trichy |  | ROTN | Indus | IN-3147247 | R/NN-678407 |  | SO | 2022-08-24 | NADUV4 | 4G_FD900_NADUV4 | 4G_FD2100_NADUV4 | 4G_TD_NADUV4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402551 | 2022-09-08 | P/FVC/MDS/1096538/2022 | 2022-09-16 | ST202209403803 | 2022-09-08 | P/FVC/MDS/1096447/2022 | 2022-09-16 |  |  |  |  | ST202209398945 | 2022-09-07 | P/FVC/MDS/1096353/2022 | 2022-09-16
2001 | TIVR21 | TIVR21 | Thiruvarur | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-07-29 | TIVR21 | 4G_FD900_TIVR21 | 4G_FD2100_TIVR21 | 4G_TD_TIVR21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202106362809 | 2021-06-26 | P/FVC/MDS/1050066/2021 | 2021-08-09 | ST202208320605 | 2022-08-09 | P/FVC/MDS/1093975/2022 | 2022-08-19 |  |  |  |  | ST202208306020 | 2022-08-02 | P/FBW/MDS/1093740/2022 | 2022-08-19
2002 | TNJ178 | TNJ178 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-07-16 | TNJ178 | 4G_FD900_TNJ178 | 4G_FD2100_TNJ178 | 4G_TD_TNJ178 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296136 | 2022-07-28 | P/FVC/MDS/1093388/2022 | 2022-08-09 | ST202207298736 | 2022-07-29 | P/FVC/MDS/1093292/2022 | 2022-08-09 |  |  |  |  | ST202207295261 | 2022-07-28 | P/FBW/MDS/1093175/2022 | 2022-08-09
2003 | VLRM77 | VLRM77 | Viluppuram | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-07-16 | VLRM77 | 4G_FD900_VLRM77 | 4G_FD2100_VLRM77 | 4G_TD_VLRM77 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296150 | 2022-07-28 | P/FVC/MDS/1093390/2022 | 2022-08-09 | ST202207298751 | 2022-07-29 | P/FVC/MDS/1093294/2022 | 2022-08-09 |  |  |  |  | ST202207295271 | 2022-07-28 | P/FBW/MDS/1093177/2022 | 2022-08-09
2004 | CBE909 | CBE909 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/22984 | T22TN00464 |  | SO | 2022-07-20 | CBE909 | 4G_FD900_CBE909 | 4G_FD2100_CBE909 | 4G_TD_CBE909 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297653 | 2022-07-29 | P/FVC/MDS/1093399/2022 | 2022-08-09 | ST202207298928 | 2022-07-29 | P/FVC/MDS/1093309/2022 | 2022-08-09 | ST202211682876 | 2022-11-05 | P/FVC/MDS/1114586/2022 | 2022-11-15 | ST202207295337 | 2022-07-28 | P/FBW/MDS/1093192/2022 | 2022-08-09
2005 | KUMB87 | KUMB87 | Thanjavur | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-08-10 | KUMB87 | 4G_FD900_KUMB87 | 4G_FD2100_KUMB87 | 4G_TD_KUMB87 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331385 | 2022-08-13 | P/FVC/MDS/1094131/2022 | 2022-08-25 | ST202208339326 | 2022-08-18 | P/FVC/MDS/1094307/2022 | 2022-08-25 |  |  |  |  | ST202208331293 | 2022-08-13 | P/FBW/MDS/1094206/2022 | 2022-08-25
2006 | TRY389 | TRY389 | Tiruchirappalli | Trichy |  | ROTN | TVI |  |  |  | SO | 2022-08-08 | TRY389 | 4G_FD900_TRY389 | 4G_FD2100_TRY389 | 4G_TD_TRY389 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334991 | 2022-08-16 | P/FVC/MDS/1094193/2022 | 2022-08-25 | ST202208340599 | 2022-08-18 | P/FVC/MDS/1094369/2022 | 2022-08-25 |  |  |  |  | ST202208331446 | 2022-08-13 | P/FBW/MDS/1094268/2022 | 2022-08-25
2007 | KLAKU4 | KLAKU4 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/23319 | T22TN04310 |  | On Air | 2022-08-24 | KLAKU4 | 4G_FD900_KLAKU4 | 4G_FD2100_KLAKU4 | 4G_TD_KLAKU4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402612 | 2022-09-08 | P/FVC/MDS/1096547/2022 | 2022-09-16 | ST202209403934 | 2022-09-08 | P/FVC/MDS/1096456/2022 | 2022-09-16 |  |  |  |  | ST202209398989 | 2022-09-07 | P/FVC/MDS/1096362/2022 | 2022-09-16
2008 | KLAKU5 | KLAKU5 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/23320 | T22TN04311 |  | On Air | 2022-08-24 | KLAKU5 | 4G_FD900_KLAKU5 | 4G_FD2100_KLAKU5 | 4G_TD_KLAKU5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402470 | 2022-09-08 | P/FVC/MDS/1096531/2022 | 2022-09-16 | ST202209402484 | 2022-09-08 | P/FVC/MDS/1096440/2022 | 2022-09-16 |  |  |  |  | ST202209398922 | 2022-09-07 | P/FVC/MDS/1096346/2022 | 2022-09-16
2009 | KTTY10 | KTTY10 | Sivaganga | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-07-20 | KTTY10 | 4G_FD900_KTTY10 | 4G_FD2100_KTTY10 | 4G_TD_KTTY10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297674 | 2022-07-29 | P/FVC/MDS/1093403/2022 | 2022-08-09 | ST202207298945 | 2022-07-29 | P/FVC/MDS/1093314/2022 | 2022-08-09 |  |  |  |  | ST202207295377 | 2022-07-28 | P/FBW/MDS/1093197/2022 | 2022-08-09
2010 | MGDI29 | MGDI29 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-08-12 | MGDI29 | 4G_FD900_MGDI29 | 4G_FD2100_MGDI29 | 4G_TD_MGDI29 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334941 | 2022-08-16 | P/FVC/MDS/1094184/2022 | 2022-08-25 | ST202208340535 | 2022-08-18 | P/FVC/MDS/1094360/2022 | 2022-08-25 |  |  |  |  | ST202208331426 | 2022-08-13 | P/FBW/MDS/1094259/2022 | 2022-08-25
2011 | VNBKM2 | VNBKM2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | On Air | 2022-07-16 | VNBKM2 | 4G_FD900_VNBKM2 | 4G_FD2100_VNBKM2 | 4G_TD_VNBKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296088 | 2022-07-28 | P/FVC/MDS/1093374/2022 | 2022-08-09 | ST202207298617 | 2022-07-29 | P/FVC/MDS/1093276/2022 | 2022-08-09 | ST202210548784 | 2022-10-11 | P/FVC/MDS/1113944/2022 | 2022-10-21 | ST202207293838 | 2022-07-28 | P/FBW/MDS/1093159/2022 | 2022-08-09
2012 | CBE803 | CBE803 | Coimbatore | Coimbatore |  | ROTN | TVI |  |  |  | On Air | 2022-08-08 | CBE803 | 4G_FD900_CBE803 | 4G_FD2100_CBE803 | 4G_TD_CBE803 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334992 | 2022-08-16 | P/FVC/MDS/1094194/2022 | 2022-08-25 | ST202208340600 | 2022-08-18 | P/FVC/MDS/1094370/2022 | 2022-08-25 |  |  |  |  | ST202208331452 | 2022-08-13 | P/FBW/MDS/1094269/2022 | 2022-08-25
2013 | MTYPM7 | MTYPM7 | Thoothukkudi | Madurai |  | ROTN | ATC |  |  |  | SO | 2022-07-29 | MTYPM7 | 4G_FD900_MTYPM7 | 4G_FD2100_MTYPM7 | 4G_TD_MTYPM7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208308173 | 2022-08-03 | P/FVC/MDS/1093824/2022 | 2022-08-19 | ST202208319518 | 2022-08-09 | P/FVC/MDS/1093961/2022 | 2022-08-19 | ST202211758072 | 2022-11-22 | P/FVC/MDS/1116771/2022 | 2022-11-29 | ST202208306000 | 2022-08-02 | P/FBW/MDS/1093726/2022 | 2022-08-19
2014 | PTMVL2 | PTMVL2 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-07-16 | PTMVL2 | 4G_FD900_PTMVL2 | 4G_FD2100_PTMVL2 | 4G_TD_PTMVL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296087 | 2022-07-28 | P/FVC/MDS/1093373/2022 | 2022-08-09 | ST202207298616 | 2022-07-29 | P/FVC/MDS/1093275/2022 | 2022-08-09 |  |  |  |  | ST202207293823 | 2022-07-28 | P/FBW/MDS/1093158/2022 | 2022-08-09
2015 | KRMDI2 | KRMDI2 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3125464 | R/NN-647650 |  | On Air | 2022-08-18 | KRMDI2 | 4G_FD900_KRMDI2 | 4G_FD2100_KRMDI2 | 4G_TD_KRMDI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360984 | 2022-08-28 | P/FVC/MDS/1094654/2022 | 2022-09-07 | ST202208364557 | 2022-08-29 | P/FVC/MDS/1094719/2022 | 2022-09-07 |  |  |  |  | ST202208355407 | 2022-08-26 | P/FBW/MDS/1094591/2022 | 2022-09-07
2016 | URUYR3 | URUYR3 | Puducherry | Trichy |  | ROTN | ATC | TN/PO/AT/23388 | T22TN05299 |  | SO | 2022-08-24 | URUYR3 | 4G_FD900_URUYR3 | 4G_FD2100_URUYR3 | 4G_TD_URUYR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402586 | 2022-09-08 | P/FVC/MDS/1096543/2022 | 2022-09-16 | ST202209403890 | 2022-09-08 | P/FVC/MDS/1096452/2022 | 2022-09-16 |  |  |  |  | ST202209398959 | 2022-09-07 | P/FVC/MDS/1096358/2022 | 2022-09-16
2017 | VGNI09 | VGNI09 | Nagapattinam | Trichy |  | ROTN | Ascend |  |  |  | SR | 2022-08-10 | VGNI09 | 4G_FD900_VGNI09 | 4G_FD2100_VGNI09 | 4G_TD_VGNI09 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331354 | 2022-08-13 | P/FVC/MDS/1094126/2022 | 2022-08-25 | ST202208339316 | 2022-08-18 | P/FVC/MDS/1094302/2022 | 2022-08-25 |  |  |  |  | ST202208331286 | 2022-08-13 | P/FBW/MDS/1094201/2022 | 2022-08-25
2018 | VLR225 | VLR225 | Vellore | Vellore |  | ROTN | ATC | TN/VE/AT/22201 | T20TN07091 |  | SRB(Surrender) | 2022-07-07 | VLR225 | 4G_FD900_VLR225 | 4G_FD2100_VLR225 | 4G_TD_VLR225 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202207254027 | 2022-07-13 | P/FVC/MDS/1088680/2022 | 2022-07-25 | ST202207254961 | 2022-07-14 | P/FVC/MDS/1088736/2022 | 2022-07-25 |  |  |  |  | ST202207248057 | 2022-07-12 | P/FBW/MDS/1088624/2022 | 2022-07-25
2019 | KUTH06 | KUTH06 | Nagapattinam | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-07-16 | KUTH06 | 4G_FD900_KUTH06 | 4G_FD2100_KUTH06 | 4G_TD_KUTH06 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296092 | 2022-07-28 | P/FVC/MDS/1093377/2022 | 2022-08-09 | ST202207298639 | 2022-07-29 | P/FVC/MDS/1093279/2022 | 2022-08-09 |  |  |  |  | ST202207293846 | 2022-07-28 | P/FBW/MDS/1093162/2022 | 2022-08-09
2020 | KTKIN2 | KTKIN2 | Madurai | Madurai |  | ROTN | Indus | IN-3130128 | R/NN-653784 |  | SRB(Surrender) | 2022-07-05 | KTKIN2 | 4G_FD900_KTKIN2 | 4G_FD2100_KTKIN2 | 4G_TD_KTKIN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252006 | 2022-07-13 | P/FVC/MDS/1088651/2022 | 2022-07-25 | ST202207254701 | 2022-07-14 | P/FVC/MDS/1088705/2022 | 2022-07-25 |  |  |  |  | ST202207247283 | 2022-07-12 | P/FBW/MDS/1088594/2022 | 2022-07-25
2021 | YPDPT2 | YPDPT2 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/23385 | T22TN05282 |  | SRB(Surrender) | 2022-08-18 | YPDPT2 | 4G_FD900_YPDPT2 | 4G_FD2100_YPDPT2 | 4G_TD_YPDPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361055 | 2022-08-28 | P/FVC/MDS/1094683/2022 | 2022-09-07 | ST202208364628 | 2022-08-29 | P/FVC/MDS/1094748/2022 | 2022-09-07 |  |  |  |  | ST202208355551 | 2022-08-26 | P/FBW/MDS/1094618/2022 | 2022-09-07
2022 | PLYNT2 | PLYNT2 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23128 | T22TN01310 |  | On Air | 2022-07-16 | PLYNT2 | 4G_FD900_PLYNT2 | 4G_FD2100_PLYNT2 | 4G_TD_PLYNT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296080 | 2022-07-28 | P/FVC/MDS/1093370/2022 | 2022-08-09 | ST202207298590 | 2022-07-29 | P/FVC/MDS/1093272/2022 | 2022-08-09 |  |  |  |  | ST202207293791 | 2022-07-28 | P/FBW/MDS/1093155/2022 | 2022-08-09
2023 | PNTHI2 | PNTHI2 | Dharmapuri | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-07-16 | PNTHI2 | 4G_FD900_PNTHI2 | 4G_FD2100_PNTHI2 | 4G_TD_PNTHI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296082 | 2022-07-28 | P/FVC/MDS/1093372/2022 | 2022-08-09 | ST202207298603 | 2022-07-29 | P/FVC/MDS/1093274/2022 | 2022-08-09 |  |  |  |  | ST202207293822 | 2022-07-28 | P/FBW/MDS/1093157/2022 | 2022-08-09
2024 | KESVP2 | KESVP2 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3130578 | R/NN-654458 |  | On Air | 2022-07-16 | KESVP2 | 4G_FD900_KESVP2 | 4G_FD2100_KESVP2 | 4G_TD_KESVP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296091 | 2022-07-28 | P/FVC/MDS/1093376/2022 | 2022-08-09 | ST202207298624 | 2022-07-29 | P/FVC/MDS/1093278/2022 | 2022-08-09 |  |  |  |  | ST202207293845 | 2022-07-28 | P/FBW/MDS/1093161/2022 | 2022-08-09
2025 | AVYOR2 | AVYOR2 | Virudhunagar | Madurai |  | ROTN | Indus | IN-3130591 | R/NN-654461 |  | On Air | 2022-07-16 | AVYOR2 | 4G_FD900_AVYOR2 | 4G_FD2100_AVYOR2 | 4G_TD_AVYOR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296175 | 2022-07-28 | P/FVC/MDS/1093396/2022 | 2022-08-09 | ST202207298908 | 2022-07-29 | P/FVC/MDS/1093305/2022 | 2022-08-09 |  |  |  |  | ST202207295325 | 2022-07-28 | P/FBW/MDS/1093188/2022 | 2022-08-09
2026 | WJPT24 | WJPT24 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | SR | 2022-07-20 | WJPT24 | 4G_FD900_WJPT24 | 4G_FD2100_WJPT24 | 4G_TD_WJPT24 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297695 | 2022-07-29 | P/FVC/MDS/1093409/2022 | 2022-08-09 | ST202207298968 | 2022-07-29 | P/FVC/MDS/1093322/2022 | 2022-08-09 |  |  |  |  | ST202207295417 | 2022-07-28 | P/FBW/MDS/1093205/2022 | 2022-08-09
2027 | PLNDR3 | PLNDR3 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-07-16 | PLNDR3 | 4G_FD900_PLNDR3 | 4G_FD2100_PLNDR3 | 4G_TD_PLNDR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296109 | 2022-07-28 | P/FVC/MDS/1093384/2022 | 2022-08-09 | ST202207298699 | 2022-07-29 | P/FVC/MDS/1093287/2022 | 2022-08-09 |  |  |  |  | ST202207295243 | 2022-07-28 | P/FBW/MDS/1093170/2022 | 2022-08-09
2028 | PDY292 | PDY292 | Puducherry | Trichy |  | ROTN | Ascend |  |  |  | Dropped | 2022-08-02 | PDY292 | 4G_FD900_PDY292 | 4G_FD2100_PDY292 | 4G_TD_PDY292 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313262 | 2022-08-05 | P/FVC/MDS/1093865/2022 | 2022-08-19 | ST202208327102 | 2022-08-11 | P/FVC/MDS/1094013/2022 | 2022-08-19 |  |  |  |  | ST202208307079 | 2022-08-03 | P/FBW/MDS/1093777/2022 | 2022-08-19
2029 | VDKTP2 | VDKTP2 | Pudukkottai | Trichy |  | ROTN | ATC | TN/PU/AT/23380 | T22TN05277 |  | On Air | 2022-08-18 | VDKTP2 | 4G_FD900_VDKTP2 | 4G_FD2100_VDKTP2 | 4G_TD_VDKTP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361095 | 2022-08-28 | P/FVC/MDS/1094691/2022 | 2022-09-07 | ST202208364696 | 2022-08-29 | P/FVC/MDS/1094756/2022 | 2022-09-07 |  |  |  |  | ST202208355584 | 2022-08-26 | P/FBW/MDS/1094626/2022 | 2022-09-07
2030 | TIVM32 | TIVM32 | Viluppuram | Trichy |  | ROTN | Ascend |  |  |  | SO | 2022-08-10 | TIVM32 | 4G_FD900_TIVM32 | 4G_FD2100_TIVM32 | 4G_TD_TIVM32 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331371 | 2022-08-13 | P/FVC/MDS/1094128/2022 | 2022-08-25 | ST202208339322 | 2022-08-18 | P/FVC/MDS/1094304/2022 | 2022-08-25 |  |  |  |  | ST202208331288 | 2022-08-13 | P/FBW/MDS/1094203/2022 | 2022-08-25
2031 | PDY369 | PDY369 | Puducherry | Trichy |  | ROTN | Ascend |  |  |  | SR | 2022-07-29 | PDY369 | 4G_FD900_PDY369 | 4G_FD2100_PDY369 | 4G_TD_PDY369 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313087 | 2022-08-05 | P/FVC/MDS/1093835/2022 | 2022-08-19 | ST202208320603 | 2022-08-09 | P/FVC/MDS/1093973/2022 | 2022-08-19 |  |  |  |  | ST202208306017 | 2022-08-02 | P/FBW/MDS/1093738/2022 | 2022-08-19
2032 | PONTM3 | PONTM3 | Thiruvarur | Trichy |  | ROTN | Ascend | - |  |  | On Air | 2022-08-10 | PONTM3 | 4G_FD900_PONTM3 | 4G_FD2100_PONTM3 | 4G_TD_PONTM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331384 | 2022-08-13 | P/FVC/MDS/1094130/2022 | 2022-08-25 | ST202208339325 | 2022-08-18 | P/FVC/MDS/1094306/2022 | 2022-08-25 |  |  |  |  | ST202208331292 | 2022-08-13 | P/FBW/MDS/1094205/2022 | 2022-08-25
2033 | VRCM38 | VRCM38 | Cuddalore | Trichy |  | ROTN | Indus | IN-3144323 | R/NN-675774 |  | On Air | 2022-08-18 | VRCM38 | 4G_FD900_VRCM38 | 4G_FD2100_VRCM38 | 4G_TD_VRCM38 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361034 | 2022-08-28 | P/FVC/MDS/1094675/2022 | 2022-09-07 | ST202208364606 | 2022-08-29 | P/FVC/MDS/1094740/2022 | 2022-09-07 |  |  |  |  | ST202208355503 | 2022-08-26 | P/FBW/MDS/1094610/2022 | 2022-09-07
2034 | NLKP10 | NLKP10 | Cuddalore | Trichy |  | ROTN | Ascend |  |  |  | SR | 2022-07-29 | NLKP10 | 4G_FD900_NLKP10 | 4G_FD2100_NLKP10 | 4G_TD_NLKP10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313072 | 2022-08-05 | P/FVC/MDS/1093834/2022 | 2022-08-19 | ST202208320598 | 2022-08-09 | P/FVC/MDS/1093972/2022 | 2022-08-19 |  |  |  |  | ST202208306016 | 2022-08-02 | P/FBW/MDS/1093737/2022 | 2022-08-19
2035 | USLMP3 | USLMP3 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3132393 | R/NN-656988 |  | On Air | 2022-07-16 | USLMP3 | 4G_FD900_USLMP3 | 4G_FD2100_USLMP3 | 4G_TD_USLMP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296079 | 2022-07-28 | P/FVC/MDS/1093369/2022 | 2022-08-09 | ST202207298589 | 2022-07-29 | P/FVC/MDS/1093271/2022 | 2022-08-09 |  |  |  |  | ST202207293769 | 2022-07-28 | P/FBW/MDS/1093154/2022 | 2022-08-09
2036 | VRLIM6 | VRLIM6 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3132401 | R/NN-656989 |  | On Air | 2022-07-16 | VRLIM6 | 4G_FD900_VRLIM6 | 4G_FD2100_VRLIM6 | 4G_TD_VRLIM6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296094 | 2022-07-28 | P/FVC/MDS/1093378/2022 | 2022-08-09 | ST202207298640 | 2022-07-29 | P/FVC/MDS/1093280/2022 | 2022-08-09 |  |  |  |  | ST202207293850 | 2022-07-28 | P/FBW/MDS/1093163/2022 | 2022-08-09
2037 | NGPM22 | NGPM22 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3132268 | R/NN-656848 |  | On Air | 2022-07-20 | NGPM22 | 4G_FD900_NGPM22 | 4G_FD2100_NGPM22 | 4G_TD_NGPM22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297679 | 2022-07-29 | P/FVC/MDS/1093404/2022 | 2022-08-09 | ST202207298949 | 2022-07-29 | P/FVC/MDS/1093315/2022 | 2022-08-09 |  |  |  |  | ST202207295378 | 2022-07-28 | P/FBW/MDS/1093198/2022 | 2022-08-09
2038 | KOTGM2 | KOTGM2 | Nagapattinam | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-07-16 | KOTGM2 | 4G_FD900_KOTGM2 | 4G_FD2100_KOTGM2 | 4G_TD_KOTGM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296096 | 2022-07-28 | P/FVC/MDS/1093380/2022 | 2022-08-09 | ST202207298659 | 2022-07-29 | P/FVC/MDS/1093282/2022 | 2022-08-09 |  |  |  |  | ST202207295209 | 2022-07-28 | P/FBW/MDS/1093165/2022 | 2022-08-09
2039 | KIZHA2 | KIZHA2 | Karaikal | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-07-16 | KIZHA2 | 4G_FD900_KIZHA2 | 4G_FD2100_KIZHA2 | 4G_TD_KIZHA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539059 | 2022-10-08 | P/FVC/MDS/1114008/2022 | 2022-10-21 | ST202210537859 | 2022-10-07 | P/FVC/MDS/1113822/2022 | 2022-10-21 |  |  |  |  | ST202210535567 | 2022-10-07 | P/FBW/MDS/1113741/2022 | 2022-10-21
2040 | TIRBV2 | TIRBV2 | Puducherry | Trichy |  | ROTN | Ascend | - | - |  | SR | 2022-07-16 | TIRBV2 | 4G_FD900_TIRBV2 | 4G_FD2100_TIRBV2 | 4G_TD_TIRBV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296081 | 2022-07-28 | P/FVC/MDS/1093371/2022 | 2022-08-09 | ST202207298602 | 2022-07-29 | P/FVC/MDS/1093273/2022 | 2022-08-09 |  |  |  |  | ST202207293792 | 2022-07-28 | P/FBW/MDS/1093156/2022 | 2022-08-09
2041 | SLIMD2 | SLIMD2 | Puducherry | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-08-10 | SLIMD2 | 4G_FD900_SLIMD2 | 4G_FD2100_SLIMD2 | 4G_TD_SLIMD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331395 | 2022-08-13 | P/FVC/MDS/1094133/2022 | 2022-08-25 | ST202208339331 | 2022-08-18 | P/FVC/MDS/1094309/2022 | 2022-08-25 |  |  |  |  | ST202208331299 | 2022-08-13 | P/FBW/MDS/1094208/2022 | 2022-08-25
2042 | ARLR23 | ARLR23 | Ariyalur | Trichy |  | ROTN | Indus |  | R/NN-674250 |  | On Air | 2022-07-29 | ARLR23 | 4G_FD900_ARLR23 | 4G_FD2100_ARLR23 | 4G_TD_ARLR23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208308241 | 2022-08-03 | P/FVC/MDS/1093825/2022 | 2022-08-19 | ST202208319520 | 2022-08-09 | P/FVC/MDS/1093963/2022 | 2022-08-19 |  |  |  |  | ST202208306002 | 2022-08-02 | P/FBW/MDS/1093728/2022 | 2022-08-19
2043 | ALYKD3 | ALYKD3 | Pudukkottai | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-07-16 | ALYKD3 | 4G_FD900_ALYKD3 | 4G_FD2100_ALYKD3 | 4G_TD_ALYKD3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207296090 | 2022-07-28 | P/FVC/MDS/1093375/2022 | 2022-08-09 | ST202207298623 | 2022-07-29 | P/FVC/MDS/1093277/2022 | 2022-08-09 |  |  |  |  | ST202207293839 | 2022-07-28 | P/FBW/MDS/1093160/2022 | 2022-08-09
2044 | CDBM68 | CDBM68 | Cuddalore | Trichy |  | ROTN | Indus | IN-3132294 | R/NN-656882 |  | On Air | 2022-07-05 | CDBM68 | 4G_FD900_CDBM68 | 4G_FD2100_CDBM68 | 4G_TD_CDBM68 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252228 | 2022-07-13 | P/FVC/MDS/1088654/2022 | 2022-07-25 | ST202207254708 | 2022-07-14 | P/FVC/MDS/1088708/2022 | 2022-07-25 |  |  |  |  | ST202207247302 | 2022-07-12 | P/FBW/MDS/1088597/2022 | 2022-07-25
2045 | PDRIK2 | PDRIK2 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-07-20 | PDRIK2 | 4G_FD900_PDRIK2 | 4G_FD2100_PDRIK2 | 4G_TD_PDRIK2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298953 | 2022-07-29 | P/FVC/MDS/1093317/2022 | 2022-08-09 |  |  |  |  | ST202207295393 | 2022-07-28 | P/FBW/MDS/1093200/2022 | 2022-08-09
2046 | THIRAI | THIRAI | Perambalur | Trichy |  | ROTN | ATC | TN/PR/AT/23219 | - |  | On Air | 2022-07-20 | THIRAI | 4G_FD900_THIRAI | 4G_FD2100_THIRAI | 4G_TD_THIRAI | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297912 | 2022-07-29 | P/FVC/MDS/1093412/2022 | 2022-08-09 | ST202207299115 | 2022-07-29 | P/FVC/MDS/1093327/2022 | 2022-08-09 |  |  |  |  | ST202207295437 | 2022-07-28 | P/FBW/MDS/1093210/2022 | 2022-08-09
2047 | GOPURA | GOPURA | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/23220 | - |  | On Air | 2022-07-07 | GOPURA | 4G_FD900_GOPURA | 4G_FD2100_GOPURA | 4G_TD_GOPURA | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202207254031 | 2022-07-13 | P/FVC/MDS/1088681/2022 | 2022-07-25 | ST202207254976 | 2022-07-14 | P/FVC/MDS/1088737/2022 | 2022-07-25 |  |  |  |  | ST202207248058 | 2022-07-12 | P/FBW/MDS/1088625/2022 | 2022-07-25
2048 | PENDM3 | PENDM3 | Cuddalore | Trichy |  | ROTN | Ascend |  |  |  | On Air | 2022-08-10 | PENDM3 | 4G_FD900_PENDM3 | 4G_FD2100_PENDM3 | 4G_TD_PENDM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208331394 | 2022-08-13 | P/FVC/MDS/1094132/2022 | 2022-08-25 | ST202208339330 | 2022-08-18 | P/FVC/MDS/1094308/2022 | 2022-08-25 |  |  |  |  | ST202208331294 | 2022-08-13 | P/FBW/MDS/1094207/2022 | 2022-08-25
2049 | TRVYR7 | TRVYR7 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/23222 | - |  | SO | 2022-07-16 | TRVYR7 | 4G_FD900_TRVYR7 | 4G_FD2100_TRVYR7 | 4G_TD_TRVYR7 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106364116 | 2021-06-28 | P/FVC/MDS/1050142/2021 | 2021-08-09 | ST202207298704 | 2022-07-29 | P/FVC/MDS/1093289/2022 | 2022-08-09 |  |  |  |  | ST202207295252 | 2022-07-28 | P/FBW/MDS/1093172/2022 | 2022-08-09
2050 | KLKC55 | KLKC55 | Viluppuram | Trichy |  | ROTN | Indus | IN-3137106 | R/NN-664996 |  | On Air | 2022-07-05 | KLKC55 | 4G_FD900_KLKC55 | 4G_FD2100_KLKC55 | 4G_TD_KLKC55 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207252229 | 2022-07-13 | P/FVC/MDS/1088655/2022 | 2022-07-25 | ST202207254716 | 2022-07-14 | P/FVC/MDS/1088709/2022 | 2022-07-25 |  |  |  |  | ST202207247319 | 2022-07-12 | P/FBW/MDS/1088598/2022 | 2022-07-25
2051 | SLM414 | SLM414 | Salem | Vellore |  | ROTN | Indus |  | R/NN-664905 |  | SO | 2022-08-10 | SLM414 | 4G_FD900_SLM414 | 4G_FD2100_SLM414 | 4G_TD_SLM414 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208331513 | 2022-08-13 | P/FVC/MDS/1094147/2022 | 2022-08-25 | ST202208339599 | 2022-08-18 | P/FVC/MDS/1094323/2022 | 2022-08-25 |  |  |  |  | ST202208331330 | 2022-08-13 | P/FBW/MDS/1094222/2022 | 2022-08-25
2052 | THIRU2 | THIRU2 | Madurai | Madurai |  | ROTN | Indus |  | R/NN-664907 |  | On Air | 2022-07-25 | THIRU2 | 4G_FD900_THIRU2 | 4G_FD2100_THIRU2 | 4G_TD_THIRU2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299198 | 2022-07-29 | P/FVC/MDS/1093351/2022 | 2022-08-09 |  |  |  |  | ST202207295941 | 2022-07-28 | P/FBW/MDS/1093234/2022 | 2022-08-09
2053 | MDU535 | MDU535 | Madurai | Madurai |  | ROTN | Indus | IN-3137077 | R/NN-664953 |  |  | 2022-08-18 | MDU535 | 4G_FD900_MDU535 | 4G_FD2100_MDU535 | 4G_TD_MDU535 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361026 | 2022-08-28 | P/FVC/MDS/1094674/2022 | 2022-09-07 | ST202208364605 | 2022-08-29 | P/FVC/MDS/1094739/2022 | 2022-09-07 |  |  |  |  | ST202208355502 | 2022-08-26 | P/FBW/MDS/1094609/2022 | 2022-09-07
2054 | KVPT53 | KVPT53 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-3137110 | R/NN-665005 |  | On Air | 2022-08-24 | KVPT53 | 4G_FD900_KVPT53 | 4G_FD2100_KVPT53 | 4G_TD_KVPT53 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209402528 | 2022-09-08 | P/FVC/MDS/1096536/2022 | 2022-09-16 | ST202209403745 | 2022-09-08 | P/FVC/MDS/1096445/2022 | 2022-09-16 |  |  |  |  | ST202209398936 | 2022-09-07 | P/FVC/MDS/1096351/2022 | 2022-09-16
2055 | SVKI81 | SVKI81 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/23234 | - |  | On Air | 2022-07-20 | SVKI81 | 4G_FD900_SVKI81 | 4G_FD2100_SVKI81 | 4G_TD_SVKI81 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298980 | 2022-07-29 | P/FVC/MDS/1093324/2022 | 2022-08-09 |  |  |  |  | ST202207295419 | 2022-07-28 | P/FBW/MDS/1093207/2022 | 2022-08-09
2056 | WJPT25 | WJPT25 | Vellore | Vellore |  | ROTN | ATC |  |  |  | SRB(Surrender) | 2022-07-29 | WJPT25 | 4G_FD900_WJPT25 | 4G_FD2100_WJPT25 | 4G_TD_WJPT25 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313054 | 2022-08-05 | P/FVC/MDS/1093831/2022 | 2022-08-19 | ST202208320591 | 2022-08-09 | P/FVC/MDS/1093969/2022 | 2022-08-19 |  |  |  |  | ST202208306011 | 2022-08-02 | P/FBW/MDS/1093734/2022 | 2022-08-19
2057 | TUT151 | TUT151 | Thoothukkudi | Madurai |  | ROTN | ATC | TN/TH/AT/23386 | T22TN05294 |  | On Air | 2022-08-24 | TUT151 | 4G_FD900_TUT151 | 4G_FD2100_TUT151 | 4G_TD_TUT151 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402501 | 2022-09-08 | P/FVC/MDS/1096534/2022 | 2022-09-16 | ST202209402626 | 2022-09-08 | P/FVC/MDS/1096443/2022 | 2022-09-16 |  |  |  |  | ST202209398934 | 2022-09-07 | P/FVC/MDS/1096349/2022 | 2022-09-16
2058 | THOND3 | THOND3 | Coimbatore | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-07-25 | THOND3 | 4G_FD900_THOND3 | 4G_FD2100_THOND3 | 4G_TD_THOND3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298086 | 2022-07-29 | P/FVC/MDS/1093439/2022 | 2022-08-09 | ST202207300350 | 2022-07-30 | P/FVC/MDS/1093362/2022 | 2022-08-09 |  |  |  |  | ST202207300790 | 2022-07-30 | P/FBW/MDS/1093561/2022 | 2022-08-09
2059 | PLDM21 | PLDM21 | Tiruppur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-08-02 | PLDM21 | 4G_FD900_PLDM21 | 4G_FD2100_PLDM21 | 4G_TD_PLDM21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313300 | 2022-08-05 | P/FVC/MDS/1093870/2022 | 2022-08-19 | ST202208327121 | 2022-08-11 | P/FVC/MDS/1094018/2022 | 2022-08-19 |  |  |  |  | ST202208307099 | 2022-08-03 | P/FBW/MDS/1093782/2022 | 2022-08-19
2060 | PLDM22 | PLDM22 | Tiruppur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-08-02 | PLDM22 | 4G_FD900_PLDM22 | 4G_FD2100_PLDM22 | 4G_TD_PLDM22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313299 | 2022-08-05 | P/FVC/MDS/1093869/2022 | 2022-08-19 | ST202208327120 | 2022-08-11 | P/FVC/MDS/1094017/2022 | 2022-08-19 |  |  |  |  | ST202208307098 | 2022-08-03 | P/FBW/MDS/1093781/2022 | 2022-08-19
2061 | AVNI34 | AVNI34 | Tiruppur | Coimbatore |  | ROTN | ATC | - |  |  | SO | 2022-07-25 | AVNI34 | 4G_FD900_AVNI34 | 4G_FD2100_AVNI34 | 4G_TD_AVNI34 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298071 | 2022-07-29 | P/FVC/MDS/1093435/2022 | 2022-08-09 | ST202207300334 | 2022-07-30 | P/FVC/MDS/1093358/2022 | 2022-08-09 |  |  |  |  | ST202207295979 | 2022-07-28 | P/FBW/MDS/1093241/2022 | 2022-08-09
2062 | TCGD78 | TCGD78 | Namakkal | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-07-25 | TCGD78 | 4G_FD900_TCGD78 | 4G_FD2100_TCGD78 | 4G_TD_TCGD78 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298045 | 2022-07-29 | P/FVC/MDS/1093433/2022 | 2022-08-09 | ST202207299228 | 2022-07-29 | P/FVC/MDS/1093356/2022 | 2022-08-09 |  |  |  |  | ST202207295970 | 2022-07-28 | P/FBW/MDS/1093239/2022 | 2022-08-09
2063 | KRR105 | KRR105 | Karur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-07-29 | KRR105 | 4G_FD900_KRR105 | 4G_FD2100_KRR105 | 4G_TD_KRR105 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313052 | 2022-08-05 | P/FVC/MDS/1093829/2022 | 2022-08-19 | ST202208320589 | 2022-08-09 | P/FVC/MDS/1093967/2022 | 2022-08-19 |  |  |  |  | ST202208306007 | 2022-08-02 | P/FBW/MDS/1093732/2022 | 2022-08-19
2064 | PMKD33 | PMKD33 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-07-20 | PMKD33 | 4G_FD900_PMKD33 | 4G_FD2100_PMKD33 | 4G_TD_PMKD33 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297673 | 2022-07-29 | P/FVC/MDS/1093402/2022 | 2022-08-09 | ST202207298944 | 2022-07-29 | P/FVC/MDS/1093313/2022 | 2022-08-09 |  |  |  |  | ST202207295369 | 2022-07-28 | P/FBW/MDS/1093196/2022 | 2022-08-09
2065 | PMKD34 | PMKD34 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-07-20 | PMKD34 | 4G_FD900_PMKD34 | 4G_FD2100_PMKD34 | 4G_TD_PMKD34 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297694 | 2022-07-29 | P/FVC/MDS/1093408/2022 | 2022-08-09 | ST202207298967 | 2022-07-29 | P/FVC/MDS/1093321/2022 | 2022-08-09 |  |  |  |  | ST202207295411 | 2022-07-28 | P/FBW/MDS/1093204/2022 | 2022-08-09
2066 | AMNR08 | AMNR08 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-07-20 | AMNR08 | 4G_FD900_AMNR08 | 4G_FD2100_AMNR08 | 4G_TD_AMNR08 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297689 | 2022-07-29 | P/FVC/MDS/1093407/2022 | 2022-08-09 | ST202207298959 | 2022-07-29 | P/FVC/MDS/1093320/2022 | 2022-08-09 |  |  |  |  | ST202207295410 | 2022-07-28 | P/FBW/MDS/1093203/2022 | 2022-08-09
2067 | KRR107 | KRR107 | Karur | Coimbatore |  | ROTN | ATC | TN/KU/AT/23259 | T22TN04115 |  | On Air | 2022-08-12 | KRR107 | 4G_FD900_KRR107 | 4G_FD2100_KRR107 | 4G_TD_KRR107 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360967 | 2022-08-28 | P/FVC/MDS/1094643/2022 | 2022-09-07 | ST202208364530 | 2022-08-29 | P/FVC/MDS/1094708/2022 | 2022-09-07 |  |  |  |  | ST202208355357 | 2022-08-26 | P/FBW/MDS/1094580/2022 | 2022-09-07
2068 | TIR496 | TIR496 | Tiruppur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-07-25 | TIR496 | 4G_FD900_TIR496 | 4G_FD2100_TIR496 | 4G_TD_TIR496 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298072 | 2022-07-29 | P/FVC/MDS/1093436/2022 | 2022-08-09 | ST202207300335 | 2022-07-30 | P/FVC/MDS/1093359/2022 | 2022-08-09 |  |  |  |  | ST202207295980 | 2022-07-28 | P/FBW/MDS/1093242/2022 | 2022-08-09
2069 | TIR498 | TIR498 | Tiruppur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-07-25 | TIR498 | 4G_FD900_TIR498 | 4G_FD2100_TIR498 | 4G_TD_TIR498 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298085 | 2022-07-29 | P/FVC/MDS/1093438/2022 | 2022-08-09 | ST202207300341 | 2022-07-30 | P/FVC/MDS/1093361/2022 | 2022-08-09 |  |  |  |  | ST202207295994 | 2022-07-28 | P/FBW/MDS/1093244/2022 | 2022-08-09
2070 | JOLR23 | JOLR23 | Vellore | Vellore |  | ROTN | ATC | - |  |  | SO | 2022-08-02 | JOLR23 | 4G_FD900_JOLR23 | 4G_FD2100_JOLR23 | 4G_TD_JOLR23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313739 | 2022-08-06 | P/FVC/MDS/1093890/2022 | 2022-08-19 | ST202208327441 | 2022-08-11 | P/FVC/MDS/1094046/2022 | 2022-08-19 |  |  |  |  | ST202208307562 | 2022-08-03 | P/FBW/MDS/1093805/2022 | 2022-08-19
2071 | ATURE2 | ATURE2 | Krishnagiri | Vellore |  | ROTN | ATC | - |  |  | On Air | 2022-07-25 | ATURE2 | 4G_FD900_ATURE2 | 4G_FD2100_ATURE2 | 4G_TD_ATURE2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298032 | 2022-07-29 | P/FVC/MDS/1093431/2022 | 2022-08-09 | ST202207299201 | 2022-07-29 | P/FVC/MDS/1093354/2022 | 2022-08-09 |  |  |  |  | ST202207295957 | 2022-07-28 | P/FBW/MDS/1093237/2022 | 2022-08-09
2072 | HSR185 | HSR185 | Krishnagiri | Vellore |  | ROTN | ATC | - |  |  | On Air | 2022-08-10 | HSR185 | 4G_FD900_HSR185 | 4G_FD2100_HSR185 | 4G_TD_HSR185 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331460 | 2022-08-13 | P/FVC/MDS/1094144/2022 | 2022-08-25 | ST202208339587 | 2022-08-18 | P/FVC/MDS/1094320/2022 | 2022-08-25 |  |  |  |  | ST202208331319 | 2022-08-13 | P/FBW/MDS/1094219/2022 | 2022-08-25
2073 | HSR188 | HSR188 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/23268 | - |  | On Air | 2022-07-20 | HSR188 | 4G_FD900_HSR188 | 4G_FD2100_HSR188 | 4G_TD_HSR188 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207299185 | 2022-07-29 | P/FVC/MDS/1093338/2022 | 2022-08-09 |  |  |  |  | ST202207295490 | 2022-07-28 | P/FBW/MDS/1093222/2022 | 2022-08-09
2074 | HSR192 | HSR192 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/23250 | - |  | On Air | 2022-07-20 | HSR192 | 4G_FD900_HSR192 | 4G_FD2100_HSR192 | 4G_TD_HSR192 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298979 | 2022-07-29 | P/FVC/MDS/1093323/2022 | 2022-08-09 |  |  |  |  | ST202207295418 | 2022-07-28 | P/FBW/MDS/1093206/2022 | 2022-08-09
2075 | SLM422 | SLM422 | Salem | Vellore |  | ROTN | ATC | - |  |  | On Air | 2022-07-25 | SLM422 | 4G_FD900_SLM422 | 4G_FD2100_SLM422 | 4G_TD_SLM422 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298033 | 2022-07-29 | P/FVC/MDS/1093432/2022 | 2022-08-09 | ST202207299202 | 2022-07-29 | P/FVC/MDS/1093355/2022 | 2022-08-09 |  |  |  |  | ST202207295969 | 2022-07-28 | P/FBW/MDS/1093238/2022 | 2022-08-09
2076 | SLM423 | SLM423 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/23273 | T22TN04129 |  | On Air | 2022-08-18 | SLM423 | 4G_FD900_SLM423 | 4G_FD2100_SLM423 | 4G_TD_SLM423 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360969 | 2022-08-28 | P/FVC/MDS/1094645/2022 | 2022-09-07 | ST202208364532 | 2022-08-29 | P/FVC/MDS/1094710/2022 | 2022-09-07 |  |  |  |  | ST202208355359 | 2022-08-26 | P/FBW/MDS/1094582/2022 | 2022-09-07
2077 | SLM424 | SLM424 | Salem | Vellore |  | ROTN | ATC | - |  |  | On Air | 2022-07-25 | SLM424 | 4G_FD900_SLM424 | 4G_FD2100_SLM424 | 4G_TD_SLM424 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207298084 | 2022-07-29 | P/FVC/MDS/1093437/2022 | 2022-08-09 | ST202207300340 | 2022-07-30 | P/FVC/MDS/1093360/2022 | 2022-08-09 |  |  |  |  | ST202207295981 | 2022-07-28 | P/FBW/MDS/1093243/2022 | 2022-08-09
2078 | EDGSL5 | EDGSL5 | Salem | Vellore |  | ROTN | ATC | - |  |  | SRB(Surrender) | 2022-07-29 | EDGSL5 | 4G_FD900_EDGSL5 | 4G_FD2100_EDGSL5 | 4G_TD_EDGSL5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208308172 | 2022-08-03 | P/FVC/MDS/1093823/2022 | 2022-08-19 | ST202208319515 | 2022-08-09 | P/FVC/MDS/1093960/2022 | 2022-08-19 |  |  |  |  | ST202208305999 | 2022-08-02 | P/FBW/MDS/1093725/2022 | 2022-08-19
2079 | EDGSL6 | EDGSL6 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/23277 | T22TN04133 |  | On Air | 2022-08-24 | EDGSL6 | 4G_FD900_EDGSL6 | 4G_FD2100_EDGSL6 | 4G_TD_EDGSL6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402499 | 2022-09-08 | P/FVC/MDS/1096532/2022 | 2022-09-16 | ST202209402571 | 2022-09-08 | P/FVC/MDS/1096441/2022 | 2022-09-16 |  |  |  |  | ST202209398928 | 2022-09-07 | P/FVC/MDS/1096347/2022 | 2022-09-16
2080 | DPI062 | DPI062 | Dharmapuri | Vellore |  | ROTN | ATC | TN/DH/AT/23278 | T22TN04134 |  | On Air | 2022-08-12 | DPI062 | 4G_FD900_DPI062 | 4G_FD2100_DPI062 | 4G_TD_DPI062 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334523 | 2022-08-15 | P/FVC/MDS/1094169/2022 | 2022-08-25 | ST202208340343 | 2022-08-18 | P/FVC/MDS/1094345/2022 | 2022-08-25 |  |  |  |  | ST202208331391 | 2022-08-13 | P/FBW/MDS/1094244/2022 | 2022-08-25
2081 | BODI23 | BODI23 | Theni | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-07-20 | BODI23 | 4G_FD900_BODI23 | 4G_FD2100_BODI23 | 4G_TD_BODI23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297680 | 2022-07-29 | P/FVC/MDS/1093405/2022 | 2022-08-09 | ST202207298950 | 2022-07-29 | P/FVC/MDS/1093316/2022 | 2022-08-09 |  |  |  |  | ST202207295392 | 2022-07-28 | P/FBW/MDS/1093199/2022 | 2022-08-09
2082 | AMZI20 | AMZI20 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-08-12 | AMZI20 | 4G_FD900_AMZI20 | 4G_FD2100_AMZI20 | 4G_TD_AMZI20 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334957 | 2022-08-16 | P/FVC/MDS/1094185/2022 | 2022-08-25 | ST202208340536 | 2022-08-18 | P/FVC/MDS/1094361/2022 | 2022-08-25 |  |  |  |  | ST202208331427 | 2022-08-13 | P/FBW/MDS/1094260/2022 | 2022-08-25
2083 | SVKI84 | SVKI84 | Virudhunagar | Madurai |  | ROTN | Indus | IN-3142444 | R/NN-671807 |  | SO | 2022-08-18 | SVKI84 | 4G_FD900_SVKI84 | 4G_FD2100_SVKI84 | 4G_TD_SVKI84 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361018 | 2022-08-28 | P/FVC/MDS/1094671/2022 | 2022-09-07 | ST202208364591 | 2022-08-29 | P/FVC/MDS/1094736/2022 | 2022-09-07 |  |  |  |  | ST202208355473 | 2022-08-26 | P/FBW/MDS/1094606/2022 | 2022-09-07
2084 | KNATK2 | KNATK2 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/23280 | T22TN04136 |  | On Air | 2022-08-12 | KNATK2 | 4G_FD900_KNATK2 | 4G_FD2100_KNATK2 | 4G_TD_KNATK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334490 | 2022-08-15 | P/FVC/MDS/1094166/2022 | 2022-08-25 | ST202208340209 | 2022-08-18 | P/FVC/MDS/1094342/2022 | 2022-08-25 |  |  |  |  | ST202208331381 | 2022-08-13 | P/FBW/MDS/1094241/2022 | 2022-08-25
2085 | MDU549 | MDU549 | Madurai | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-08-12 | MDU549 | 4G_FD900_MDU549 | 4G_FD2100_MDU549 | 4G_TD_MDU549 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208334559 | 2022-08-15 | P/FVC/MDS/1094179/2022 | 2022-08-25 | ST202208340489 | 2022-08-18 | P/FVC/MDS/1094355/2022 | 2022-08-25 |  |  |  |  | ST202208331411 | 2022-08-13 | P/FBW/MDS/1094254/2022 | 2022-08-25
2086 | TRY420 | TRY420 | Tiruchirappalli | Trichy |  | ROTN | ATC | TN/TC/AT/23282 | - |  | SO | 2022-07-20 | TRY420 | 4G_FD900_TRY420 | 4G_FD2100_TRY420 | 4G_TD_TRY420 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202207297901 | 2022-07-29 | P/FVC/MDS/1093411/2022 | 2022-08-09 | ST202207299114 | 2022-07-29 | P/FVC/MDS/1093326/2022 | 2022-08-09 |  |  |  |  | ST202207295431 | 2022-07-28 | P/FBW/MDS/1093209/2022 | 2022-08-09
2087 | PLPT11 | PLPT11 | Karur | Coimbatore |  | ROTN | ATC | TN/KU/AT/23284 | T22TN04140 |  | On Air | 2022-08-18 | PLPT11 | 4G_FD900_PLPT11 | 4G_FD2100_PLPT11 | 4G_TD_PLPT11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208361036 | 2022-08-28 | P/FVC/MDS/1094677/2022 | 2022-09-07 | ST202208364611 | 2022-08-29 | P/FVC/MDS/1094742/2022 | 2022-09-07 |  |  |  |  | ST202208355520 | 2022-08-26 | P/FBW/MDS/1094612/2022 | 2022-09-07
2088 | PORYR3 | PORYR3 | Nagapattinam | Trichy |  | ROTN | Ascend | - |  |  | SO | 2022-08-10 | PORYR3 | 4G_FD900_PORYR3 | 4G_FD2100_PORYR3 | 4G_TD_PORYR3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210539060 | 2022-10-08 | P/FVC/MDS/1114009/2022 | 2022-10-21 | ST202210537860 | 2022-10-07 | P/FVC/MDS/1113823/2022 | 2022-10-21 |  |  |  |  | ST202210535568 | 2022-10-07 | P/FBW/MDS/1113742/2022 | 2022-10-21
2089 | PLPT12 | PLPT12 | Karur | Coimbatore |  | ROTN | ATC | - |  |  | On Air | 2022-08-02 | PLPT12 | 4G_FD900_PLPT12 | 4G_FD2100_PLPT12 | 4G_TD_PLPT12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 | 1906-04-18 | ST202208313755 | 2022-08-06 | P/FVC/MDS/1093895/2022 | 2022-08-19 | ST202208327792 | 2022-08-11 | P/FVC/MDS/1094051/2022 | 2022-08-19
2090 | SVTRM4 | SVTRM4 | Tirunelveli | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-07-20 | SVTRM4 | 4G_FD900_SVTRM4 | 4G_FD2100_SVTRM4 | 4G_TD_SVTRM4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202207298958 | 2022-07-29 | P/FVC/MDS/1093319/2022 | 2022-08-09 |  |  |  |  | ST202207295403 | 2022-07-28 | P/FBW/MDS/1093202/2022 | 2022-08-09
2091 | KNJIP2 | KNJIP2 | Kancheepuram | Chennai |  | ROTN | Ascend |  |  |  | On Air | 2022-07-29 | KNJIP2 | 4G_FD900_KNJIP2 | 4G_FD2100_KNJIP2 | 4G_TD_KNJIP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313088 | 2022-08-05 | P/FVC/MDS/1093836/2022 | 2022-08-19 | ST202208320604 | 2022-08-09 | P/FVC/MDS/1093974/2022 | 2022-08-19 |  |  |  |  | ST202208306018 | 2022-08-02 | P/FBW/MDS/1093739/2022 | 2022-08-19
2092 | PLMDU3 | PLMDU3 | Madurai | Madurai |  | ROTN | Summit |  | SR-TN001034 |  | On Air | 2022-08-02 | PLMDU3 | 4G_FD900_PLMDU3 | 4G_FD2100_PLMDU3 | 4G_TD_PLMDU3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313358 | 2022-08-05 | P/FVC/MDS/1093882/2022 | 2022-08-19 | ST202208327228 | 2022-08-11 | P/FVC/MDS/1094033/2022 | 2022-08-19 |  |  |  |  | ST202208307175 | 2022-08-03 | P/FBW/MDS/1093796/2022 | 2022-08-19
2093 | ANAVA2 | ANAVA2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3144055 | R/NN-674824 |  | On Air | 2022-08-18 | ANAVA2 | 4G_FD900_ANAVA2 | 4G_FD2100_ANAVA2 | 4G_TD_ANAVA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361025 | 2022-08-28 | P/FVC/MDS/1094673/2022 | 2022-09-07 | ST202208364600 | 2022-08-29 | P/FVC/MDS/1094738/2022 | 2022-09-07 |  |  |  |  | ST202208355501 | 2022-08-26 | P/FBW/MDS/1094608/2022 | 2022-09-07
2094 | PRUCP2 | PRUCP2 | Coimbatore | Coimbatore |  | ROTN | Summit |  | SR-TN001035 |  | On Air | 2022-08-02 | PRUCP2 | 4G_FD900_PRUCP2 | 4G_FD2100_PRUCP2 | 4G_TD_PRUCP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313365 | 2022-08-05 | P/FVC/MDS/1093884/2022 | 2022-08-19 | ST202208327239 | 2022-08-11 | P/FVC/MDS/1094035/2022 | 2022-08-19 |  |  |  |  | ST202208307181 | 2022-08-03 | P/FBW/MDS/1093798/2022 | 2022-08-19
2095 | KNPYM4 | KNPYM4 | Coimbatore | Coimbatore |  | ROTN | ATC |  |  |  | SO | 2022-07-29 | KNPYM4 | 4G_FD900_KNPYM4 | 4G_FD2100_KNPYM4 | 4G_TD_KNPYM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313071 | 2022-08-05 | P/FVC/MDS/1093833/2022 | 2022-08-19 | ST202208320597 | 2022-08-09 | P/FVC/MDS/1093971/2022 | 2022-08-19 |  |  |  |  | ST202208306013 | 2022-08-02 | P/FBW/MDS/1093736/2022 | 2022-08-19
2096 | TCGD55 | TCGD55 | Namakkal | Coimbatore |  | ROTN | Summit |  | SR-TN001036 |  | On Air | 2022-08-02 | TCGD55 | 4G_FD900_TCGD55 | 4G_FD2100_TCGD55 | 4G_TD_TCGD55 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313369 | 2022-08-05 | P/FVC/MDS/1093886/2022 | 2022-08-19 | ST202208327242 | 2022-08-11 | P/FVC/MDS/1094037/2022 | 2022-08-19 |  |  |  |  | ST202208307539 | 2022-08-03 | P/FBW/MDS/1093800/2022 | 2022-08-19
2097 | PRDLU2 | PRDLU2 | Erode | Coimbatore |  | ROTN | Summit |  | SR-TN001037 |  | On Air | 2022-08-02 | PRDLU2 | 4G_FD900_PRDLU2 | 4G_FD2100_PRDLU2 | 4G_TD_PRDLU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313364 | 2022-08-05 | P/FVC/MDS/1093883/2022 | 2022-08-19 | ST202208327229 | 2022-08-11 | P/FVC/MDS/1094034/2022 | 2022-08-19 |  |  |  |  | ST202208307180 | 2022-08-03 | P/FBW/MDS/1093797/2022 | 2022-08-19
2098 | APKDL3 | APKDL3 | Erode | Coimbatore |  | ROTN | Summit | I-TN-BHVN-ENB-9051 | SR-TN001067 |  | On Air | 2022-08-18 | APKDL3 | 4G_FD900_APKDL3 | 4G_FD2100_APKDL3 | 4G_TD_APKDL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361084 | 2022-08-28 | P/FVC/MDS/1094687/2022 | 2022-09-07 | ST202208364635 | 2022-08-29 | P/FVC/MDS/1094752/2022 | 2022-09-07 |  |  |  |  | ST202208355562 | 2022-08-26 | P/FBW/MDS/1094622/2022 | 2022-09-07
2099 | ELNKI2 | ELNKI2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/23338 | T22TN04329 |  | On Air | 2022-08-12 | ELNKI2 | 4G_FD900_ELNKI2 | 4G_FD2100_ELNKI2 | 4G_TD_ELNKI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334491 | 2022-08-15 | P/FVC/MDS/1094167/2022 | 2022-08-25 | ST202208340218 | 2022-08-18 | P/FVC/MDS/1094343/2022 | 2022-08-25 |  |  |  |  | ST202208331382 | 2022-08-13 | P/FBW/MDS/1094242/2022 | 2022-08-25
2100 | VDMVO2 | VDMVO2 | Erode | Coimbatore |  | ROTN | Summit |  | SR-TN001039 |  | On Air | 2022-08-02 | VDMVO2 | 4G_FD900_VDMVO2 | 4G_FD2100_VDMVO2 | 4G_TD_VDMVO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313370 | 2022-08-05 | P/FVC/MDS/1093887/2022 | 2022-08-19 | ST202208327255 | 2022-08-11 | P/FVC/MDS/1094038/2022 | 2022-08-19 |  |  |  |  | ST202208307540 | 2022-08-03 | P/FBW/MDS/1093801/2022 | 2022-08-19
2101 | KADMP2 | KADMP2 | Namakkal | Coimbatore |  | ROTN | ATC |  |  |  | On Air | 2022-08-02 | KADMP2 | 4G_FD900_KADMP2 | 4G_FD2100_KADMP2 | 4G_TD_KADMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313740 | 2022-08-06 | P/FVC/MDS/1093891/2022 | 2022-08-19 | ST202208327768 | 2022-08-11 | P/FVC/MDS/1094047/2022 | 2022-08-19 |  |  |  |  | ST202208307579 | 2022-08-03 | P/FBW/MDS/1093806/2022 | 2022-08-19
2102 | SENUP2 | SENUP2 | Namakkal | Coimbatore |  | ROTN | ATC |  |  |  | On Air | 2022-08-02 | SENUP2 | 4G_FD900_SENUP2 | 4G_FD2100_SENUP2 | 4G_TD_SENUP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313749 | 2022-08-06 | P/FVC/MDS/1093894/2022 | 2022-08-19 | ST202208327791 | 2022-08-11 | P/FVC/MDS/1094050/2022 | 2022-08-19 |  |  |  |  | ST202208307591 | 2022-08-03 | P/FBW/MDS/1093809/2022 | 2022-08-19
2103 | PALKP2 | PALKP2 | Namakkal | Coimbatore |  | ROTN | ATC |  |  |  | On Air | 2022-08-02 | PALKP2 | 4G_FD900_PALKP2 | 4G_FD2100_PALKP2 | 4G_TD_PALKP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313747 | 2022-08-06 | P/FVC/MDS/1093892/2022 | 2022-08-19 | ST202208327769 | 2022-08-11 | P/FVC/MDS/1094048/2022 | 2022-08-19 |  |  |  |  | ST202208307580 | 2022-08-03 | P/FBW/MDS/1093807/2022 | 2022-08-19
2104 | VELYP3 | VELYP3 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/23344 | T22TN04335 |  | On Air | 2022-08-12 | VELYP3 | 4G_FD900_VELYP3 | 4G_FD2100_VELYP3 | 4G_TD_VELYP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334478 | 2022-08-15 | P/FVC/MDS/1094165/2022 | 2022-08-25 | ST202208340208 | 2022-08-18 | P/FVC/MDS/1094341/2022 | 2022-08-25 |  |  |  |  | ST202208331380 | 2022-08-13 | P/FBW/MDS/1094240/2022 | 2022-08-25
2105 | NAJUK2 | NAJUK2 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/23346 | T22TN04337 |  | On Air | 2022-08-12 | NAJUK2 | 4G_FD900_NAJUK2 | 4G_FD2100_NAJUK2 | 4G_TD_NAJUK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334522 | 2022-08-15 | P/FVC/MDS/1094168/2022 | 2022-08-25 | ST202208340219 | 2022-08-18 | P/FVC/MDS/1094344/2022 | 2022-08-25 |  |  |  |  | ST202208331390 | 2022-08-13 | P/FBW/MDS/1094243/2022 | 2022-08-25
2106 | KOKUL2 | KOKUL2 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/23349 | T22TN04340 |  | SO | 2022-08-18 | KOKUL2 | 4G_FD900_KOKUL2 | 4G_FD2100_KOKUL2 | 4G_TD_KOKUL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361100 | 2022-08-28 | P/FVC/MDS/1094693/2022 | 2022-09-07 | ST202208364703 | 2022-08-29 | P/FVC/MDS/1094758/2022 | 2022-09-07 |  |  |  |  | ST202208355587 | 2022-08-26 | P/FBW/MDS/1094628/2022 | 2022-09-07
2107 | TVSRI2 | TVSRI2 | Madurai | Madurai |  | ROTN | ATC |  |  |  | On Air | 2022-08-02 | TVSRI2 | 4G_FD900_TVSRI2 | 4G_FD2100_TVSRI2 | 4G_TD_TVSRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313248 | 2022-08-05 | P/FVC/MDS/1093863/2022 | 2022-08-19 | ST202208327085 | 2022-08-11 | P/FVC/MDS/1094011/2022 | 2022-08-19 |  |  |  |  | ST202208307077 | 2022-08-03 | P/FBW/MDS/1093775/2022 | 2022-08-19
2108 | CHAPM2 | CHAPM2 | Coimbatore | Coimbatore |  | ROTN | Indus | - | R/RES-512198 |  | On Air | 2022-07-29 | CHAPM2 | 4G_FD900_CHAPM2 | 4G_FD2100_CHAPM2 | 4G_TD_CHAPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202203086085 | 2022-03-30 | P/FVC/MDS/1078189/2022 | 2022-04-15 | ST202203084999 | 2022-03-29 | P/FVC/MDS/1078143/2022 | 2022-04-15 |  |  |  |  | ST202203085821 | 2022-03-30 | P/FBW/MDS/1077897/2022 | 2022-04-14
2109 | MTKLP2 | MTKLP2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/23350 | T22TN04341 |  | On Air | 2022-08-18 | MTKLP2 | 4G_FD900_MTKLP2 | 4G_FD2100_MTKLP2 | 4G_TD_MTKLP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361096 | 2022-08-28 | P/FVC/MDS/1094692/2022 | 2022-09-07 | ST202208364697 | 2022-08-29 | P/FVC/MDS/1094757/2022 | 2022-09-07 |  |  |  |  | ST202208355585 | 2022-08-26 | P/FBW/MDS/1094627/2022 | 2022-09-07
2110 | NZRTH3 | NZRTH3 | Thoothukkudi | Madurai |  | ROTN | SUMMIT |  | SR-TN001040 |  | On Air | 2022-08-02 | NZRTH3 | 4G_FD900_NZRTH3 | 4G_FD2100_NZRTH3 | 4G_TD_NZRTH3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313357 | 2022-08-05 | P/FVC/MDS/1093881/2022 | 2022-08-19 | ST202208327218 | 2022-08-11 | P/FVC/MDS/1094032/2022 | 2022-08-19 |  |  |  |  | ST202208307174 | 2022-08-03 | P/FBW/MDS/1093795/2022 | 2022-08-19
2111 | NPLI04 | NPLI04 | Vellore | Vellore |  | ROTN | Indus | - | R/NN-674916 |  | On Air | 2022-08-10 | NPLI04 | 4G_FD900_NPLI04 | 4G_FD2100_NPLI04 | 4G_TD_NPLI04 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334356 | 2022-08-15 | P/FVC/MDS/1094152/2022 | 2022-08-25 | ST202208339615 | 2022-08-18 | P/FVC/MDS/1094328/2022 | 2022-08-25 |  |  |  |  | ST202208331343 | 2022-08-13 | P/FBW/MDS/1094227/2022 | 2022-08-25
2112 | BODCP2 | BODCP2 | Krishnagiri | Vellore |  | ROTN | Summit |  | SR-TN001041 |  | On Air | 2022-08-02 | BODCP2 | 4G_FD900_BODCP2 | 4G_FD2100_BODCP2 | 4G_TD_BODCP2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202208327192 | 2022-08-11 | P/FVC/MDS/1094028/2022 | 2022-08-19 |  |  |  |  | ST202208307148 | 2022-08-03 | P/FBW/MDS/1093791/2022 | 2022-08-19
2113 | BUDHM2 | BUDHM2 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3144065 | R/NN-675169 |  | On Air | 2022-08-18 | BUDHM2 | 4G_FD900_BUDHM2 | 4G_FD2100_BUDHM2 | 4G_TD_BUDHM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361016 | 2022-08-28 | P/FVC/MDS/1094669/2022 | 2022-09-07 | ST202208364585 | 2022-08-29 | P/FVC/MDS/1094734/2022 | 2022-09-07 |  |  |  |  | ST202208355471 | 2022-08-26 | P/FBW/MDS/1094604/2022 | 2022-09-07
2114 | KURUP2 | KURUP2 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3144067 | R/NN-675207 |  | SRB(Surrender) | 2022-08-18 | KURUP2 | 4G_FD900_KURUP2 | 4G_FD2100_KURUP2 | 4G_TD_KURUP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361011 | 2022-08-28 | P/FVC/MDS/1094667/2022 | 2022-09-07 | ST202208364583 | 2022-08-29 | P/FVC/MDS/1094732/2022 | 2022-09-07 |  |  |  |  | ST202208355457 | 2022-08-26 | P/FBW/MDS/1094602/2022 | 2022-09-07
2115 | PTPRM2 | PTPRM2 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3144068 | R/NN-675235 |  | SO | 2022-08-24 | PTPRM2 | 4G_FD900_PTPRM2 | 4G_FD2100_PTPRM2 | 4G_TD_PTPRM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402637 | 2022-09-08 | P/FVC/MDS/1096548/2022 | 2022-09-16 | ST202209403935 | 2022-09-08 | P/FVC/MDS/1096457/2022 | 2022-09-16 |  |  |  |  | ST202209398990 | 2022-09-07 | P/FVC/MDS/1096363/2022 | 2022-09-16
2116 | AYOTP2 | AYOTP2 | Salem | Vellore |  | ROTN | Summit | I-TN-AYPT-ENB-9001 | SR-TN001068 |  | On Air | 2022-08-18 | AYOTP2 | 4G_FD900_AYOTP2 | 4G_FD2100_AYOTP2 | 4G_TD_AYOTP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361092 | 2022-08-28 | P/FVC/MDS/1094690/2022 | 2022-09-07 | ST202208364695 | 2022-08-29 | P/FVC/MDS/1094755/2022 | 2022-09-07 |  |  |  |  | ST202208355577 | 2022-08-26 | P/FBW/MDS/1094625/2022 | 2022-09-07
2117 | CHIKA2 | CHIKA2 | Salem | Vellore |  | ROTN | Indus | IN-3144083 | R/NN-675345 |  |  | 2022-08-18 | CHIKA2 | 4G_FD900_CHIKA2 | 4G_FD2100_CHIKA2 | 4G_TD_CHIKA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361007 | 2022-08-28 | P/FVC/MDS/1094666/2022 | 2022-09-07 | ST202208364580 | 2022-08-29 | P/FVC/MDS/1094731/2022 | 2022-09-07 |  |  |  |  | ST202208355448 | 2022-08-26 | P/FBW/MDS/1094601/2022 | 2022-09-07
2118 | PSGP03 | PSGP03 | Salem | Vellore |  | ROTN | Indus | IN-3144069 | R/NN-675254 |  | On Air | 2022-08-12 | PSGP03 | 4G_FD900_PSGP03 | 4G_FD2100_PSGP03 | 4G_TD_PSGP03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334552 | 2022-08-15 | P/FVC/MDS/1094176/2022 | 2022-08-25 | ST202208340458 | 2022-08-18 | P/FVC/MDS/1094352/2022 | 2022-08-25 |  |  |  |  | ST202208331404 | 2022-08-13 | P/FBW/MDS/1094251/2022 | 2022-08-25
2119 | SLM426 | SLM426 | Salem | Vellore |  | ROTN | Summit |  | SR-TN001043 |  | On Air | 2022-08-02 | SLM426 | 4G_FD900_SLM426 | 4G_FD2100_SLM426 | 4G_TD_SLM426 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313366 | 2022-08-05 | P/FVC/MDS/1093885/2022 | 2022-08-19 | ST202208327241 | 2022-08-11 | P/FVC/MDS/1094036/2022 | 2022-08-19 |  |  |  |  | ST202208307182 | 2022-08-03 | P/FBW/MDS/1093799/2022 | 2022-08-19
2120 | MUKLP2 | MUKLP2 | Salem | Vellore |  | ROTN | Indus | - | R/NN-675271 |  | On Air | 2022-08-10 | MUKLP2 | 4G_FD900_MUKLP2 | 4G_FD2100_MUKLP2 | 4G_TD_MUKLP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331470 | 2022-08-13 | P/FVC/MDS/1094146/2022 | 2022-08-25 | ST202208339598 | 2022-08-18 | P/FVC/MDS/1094322/2022 | 2022-08-25 |  |  |  |  | ST202208331326 | 2022-08-13 | P/FBW/MDS/1094221/2022 | 2022-08-25
2121 | PAGAL6 | PAGAL6 | Salem | Vellore |  | ROTN | Indus | - | R/NN-675313 |  | On Air | 2022-08-10 | PAGAL6 | 4G_FD900_PAGAL6 | 4G_FD2100_PAGAL6 | 4G_TD_PAGAL6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208331422 | 2022-08-13 | P/FVC/MDS/1094137/2022 | 2022-08-25 | ST202208339381 | 2022-08-18 | P/FVC/MDS/1094313/2022 | 2022-08-25 |  |  |  |  | ST202208331304 | 2022-08-13 | P/FBW/MDS/1094212/2022 | 2022-08-25
2122 | KINDN2 | KINDN2 | Salem | Vellore |  | ROTN | Indus | - | R/NN-675408 |  | On Air | 2022-08-10 | KINDN2 | 4G_FD900_KINDN2 | 4G_FD2100_KINDN2 | 4G_TD_KINDN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334357 | 2022-08-15 | P/FVC/MDS/1094153/2022 | 2022-08-25 | ST202208339616 | 2022-08-18 | P/FVC/MDS/1094329/2022 | 2022-08-25 |  |  |  |  | ST202208331344 | 2022-08-13 | P/FBW/MDS/1094228/2022 | 2022-08-25
2123 | KLGD03 | KLGD03 | Madurai | Madurai |  | ROTN | Summit |  | SR-TN001045 |  | On Air | 2022-08-02 | KLGD03 | 4G_FD900_KLGD03 | 4G_FD2100_KLGD03 | 4G_TD_KLGD03 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313345 | 2022-08-05 | P/FVC/MDS/1093879/2022 | 2022-08-19 | ST202208327207 | 2022-08-11 | P/FVC/MDS/1094030/2022 | 2022-08-19 |  |  |  |  | ST202208307157 | 2022-08-03 | P/FBW/MDS/1093793/2022 | 2022-08-19
2124 | KALUK2 | KALUK2 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | SR(Surrender) | 2022-08-12 | KALUK2 | 4G_FD900_KALUK2 | 4G_FD2100_KALUK2 | 4G_TD_KALUK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334560 | 2022-08-15 | P/FVC/MDS/1094180/2022 | 2022-08-25 | ST202208340490 | 2022-08-18 | P/FVC/MDS/1094356/2022 | 2022-08-25 |  |  |  |  | ST202208331413 | 2022-08-13 | P/FBW/MDS/1094255/2022 | 2022-08-25
2125 | VLSUR2 | VLSUR2 | Salem | Vellore |  | ROTN | Indus | - | R/NN-675409 |  | On Air | 2022-08-08 | VLSUR2 | 4G_FD900_VLSUR2 | 4G_FD2100_VLSUR2 | 4G_TD_VLSUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208335010 | 2022-08-16 | P/FVC/MDS/1094195/2022 | 2022-08-25 | ST202208340606 | 2022-08-18 | P/FVC/MDS/1094371/2022 | 2022-08-25 |  |  |  |  | ST202208331453 | 2022-08-13 | P/FBW/MDS/1094270/2022 | 2022-08-25
2126 | TTYN09 | TTYN09 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3144604 | R/NN-675412 |  |  | 2022-08-12 | TTYN09 | 4G_FD900_TTYN09 | 4G_FD2100_TTYN09 | 4G_TD_TTYN09 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334965 | 2022-08-16 | P/FVC/MDS/1094187/2022 | 2022-08-25 | ST202208340556 | 2022-08-18 | P/FVC/MDS/1094363/2022 | 2022-08-25 |  |  |  |  | ST202208331433 | 2022-08-13 | P/FBW/MDS/1094262/2022 | 2022-08-25
2127 | MDKUR7 | MDKUR7 | Thanjavur | Trichy |  | ROTN | Ascend |  |  |  | SO | 2022-07-29 | MDKUR7 | 4G_FD900_MDKUR7 | 4G_FD2100_MDKUR7 | 4G_TD_MDKUR7 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202208320613 | 2022-08-09 | P/FVC/MDS/1093976/2022 | 2022-08-19 |  |  |  |  | ST202208306021 | 2022-08-02 | P/FBW/MDS/1093741/2022 | 2022-08-19
2128 | GGVLI3 | GGVLI3 | Salem | Vellore |  | ROTN | Summit |  | SR-TN001047 |  | On Air | 2022-08-02 | GGVLI3 | 4G_FD900_GGVLI3 | 4G_FD2100_GGVLI3 | 4G_TD_GGVLI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313344 | 2022-08-05 | P/FVC/MDS/1093878/2022 | 2022-08-19 | ST202208327206 | 2022-08-11 | P/FVC/MDS/1094029/2022 | 2022-08-19 |  |  |  |  | ST202208307156 | 2022-08-03 | P/FBW/MDS/1093792/2022 | 2022-08-19
2129 | BOOTI6 | BOOTI6 | Theni | Madurai |  | ROTN | ATC |  |  |  | SO | 2022-08-10 | BOOTI6 | 4G_FD900_BOOTI6 | 4G_FD2100_BOOTI6 | 4G_TD_BOOTI6 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209486441 | 2022-09-27 | P/FVC/MDS/1101268/2022 | 2022-10-10 | ST202209493263 | 2022-09-28 | P/FVC/MDS/1101437/2022 | 2022-10-10 |  |  |  |  | ST202209484128 | 2022-09-26 | P/FBW/MDS/1101161/2022 | 2022-10-10
2130 | SLMAN7 | SLMAN7 | Sivaganga | Madurai |  | ROTN | ATC | TN/SI/AT/23353 | T22TN04344 |  | On Air | 2022-08-18 | SLMAN7 | 4G_FD900_SLMAN7 | 4G_FD2100_SLMAN7 | 4G_TD_SLMAN7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361044 | 2022-08-28 | P/FVC/MDS/1094679/2022 | 2022-09-07 | ST202208364616 | 2022-08-29 | P/FVC/MDS/1094744/2022 | 2022-09-07 |  |  |  |  | ST202208355537 | 2022-08-26 | P/FBW/MDS/1094614/2022 | 2022-09-07
2131 | KRKCH2 | KRKCH2 | Tirunelveli | Madurai |  | ROTN | Summit |  | SR-TN001048 |  | On Air | 2022-08-02 | KRKCH2 | 4G_FD900_KRKCH2 | 4G_FD2100_KRKCH2 | 4G_TD_KRKCH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313356 | 2022-08-05 | P/FVC/MDS/1093880/2022 | 2022-08-19 | ST202208327217 | 2022-08-11 | P/FVC/MDS/1094031/2022 | 2022-08-19 |  |  |  |  | ST202208307158 | 2022-08-03 | P/FBW/MDS/1093794/2022 | 2022-08-19
2132 | PNLR07 | PNLR07 | Tiruppur | Coimbatore |  | ROTN | ATC | TN/TI/AT/23354 | T22TN04345 |  | On Air | 2022-08-24 | PNLR07 | 4G_FD900_PNLR07 | 4G_FD2100_PNLR07 | 4G_TD_PNLR07 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538974 | 2022-10-08 | P/FVC/MDS/1113971/2022 | 2022-10-21 | ST202210537785 | 2022-10-07 | P/FVC/MDS/1113784/2022 | 2022-10-21 |  |  |  |  | ST202210534978 | 2022-10-06 | P/FBW/MDS/1113703/2022 | 2022-10-21
2133 | USPT11 | USPT11 | Madurai | Madurai |  | ROTN | ATC |  |  |  | SRB(Surrender) | 2022-08-08 | USPT11 | 4G_FD900_USPT11 | 4G_FD2100_USPT11 | 4G_TD_USPT11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208335017 | 2022-08-16 | P/FVC/MDS/1094197/2022 | 2022-08-25 | ST202208340620 | 2022-08-18 | P/FVC/MDS/1094373/2022 | 2022-08-25 |  |  |  |  | ST202208331462 | 2022-08-13 | P/FBW/MDS/1094272/2022 | 2022-08-25
2134 | TIR516 | TIR516 | Tiruppur | Coimbatore |  | ROTN | ATC | TN/TI/AT/23370 | T22TN05267 |  | On Air | 2022-08-24 | TIR516 | 4G_FD900_TIR516 | 4G_FD2100_TIR516 | 4G_TD_TIR516 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402610 | 2022-09-08 | P/FVC/MDS/1096545/2022 | 2022-09-16 | ST202209403913 | 2022-09-08 | P/FVC/MDS/1096454/2022 | 2022-09-16 |  |  |  |  | ST202209398978 | 2022-09-07 | P/FVC/MDS/1096360/2022 | 2022-09-16
2135 | CBE960 | CBE960 | Coimbatore | Coimbatore |  | ROTN | ATC | TN/CO/AT/23374 | T22TN05271 |  | On Air | 2022-08-18 | CBE960 | 4G_FD900_CBE960 | 4G_FD2100_CBE960 | 4G_TD_CBE960 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208361053 | 2022-08-28 | P/FVC/MDS/1094681/2022 | 2022-09-07 | ST202208364622 | 2022-08-29 | P/FVC/MDS/1094746/2022 | 2022-09-07 |  |  |  |  | ST202208355543 | 2022-08-26 | P/FBW/MDS/1094616/2022 | 2022-09-07
2136 | TRY424 | TRY424 | Tiruchirappalli | Trichy |  | ROTN | Summit | I-TN-TCPP-ENB-0234 | SR-TN001070 |  | On Air | 2022-08-18 | TRY424 | 4G_FD900_TRY424 | 4G_FD2100_TRY424 | 4G_TD_TRY424 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208361091 | 2022-08-28 | P/FVC/MDS/1094689/2022 | 2022-09-07 | ST202208364692 | 2022-08-29 | P/FVC/MDS/1094754/2022 | 2022-09-07 |  |  |  |  | ST202208355576 | 2022-08-26 | P/FBW/MDS/1094624/2022 | 2022-09-07
2137 | YNMREG | YNMREG | Thiruvallur | Chennai |  | ROTN | ATC | TN/TU/AT/20782 | - |  | SO | 2022-08-08 | YNMREG | 4G_FD900_YNMREG | 4G_FD2100_YNMREG | 4G_TD_YNMREG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208335035 | 2022-08-16 | P/FVC/MDS/1094198/2022 | 2022-08-25 | ST202208340621 | 2022-08-18 | P/FVC/MDS/1094374/2022 | 2022-08-25 |  |  |  |  | ST202208331463 | 2022-08-13 | P/FBW/MDS/1094273/2022 | 2022-08-25
2138 | BGLUR8 | BGLUR8 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/23362 | T22TN04622 |  | On Air | 2022-08-18 | BGLUR8 | 4G_FD900_BGLUR8 | 4G_FD2100_BGLUR8 | 4G_TD_BGLUR8 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208361077 | 2022-08-28 | P/FVC/MDS/1094684/2022 | 2022-09-07 | ST202208364629 | 2022-08-29 | P/FVC/MDS/1094749/2022 | 2022-09-07 |  |  |  |  | ST202208355552 | 2022-08-26 | P/FBW/MDS/1094619/2022 | 2022-09-07
2139 | NEDRA2 | NEDRA2 | Sivaganga | Madurai |  | ROTN | Summit | I-TN-TPTI-ENB-9008 | SR-TN001072 |  | On Air | 2022-08-24 | NEDRA2 | 4G_FD900_NEDRA2 | 4G_FD2100_NEDRA2 | 4G_TD_NEDRA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402566 | 2022-09-08 | P/FVC/MDS/1096541/2022 | 2022-09-16 | ST202209403853 | 2022-09-08 | P/FVC/MDS/1096450/2022 | 2022-09-16 |  |  |  |  | ST202209398956 | 2022-09-07 | P/FVC/MDS/1096356/2022 | 2022-09-16
2140 | VGNI10 | VGNI10 | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-VLKN-ENB-9005 | SR-TN001074 |  | On Air | 2022-08-24 | VGNI10 | 4G_FD900_VGNI10 | 4G_FD2100_VGNI10 | 4G_TD_VGNI10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208327979 | 2022-08-11 | P/FVC/MDS/1093896/2022 | 2022-08-19 | ST202208327814 | 2022-08-11 | P/FVC/MDS/1094052/2022 | 2022-08-19 | ST202208328018 | 2022-08-11 | P/FVC/MDS/1093943/2022 | 2022-08-19 | ST202208327928 | 2022-08-11 | P/FBW/MDS/1093695/2022 | 2022-08-19
2141 | ABSM11 | ABSM11 | Tirunelveli | Madurai |  | ROTN | Summit | I-TN-ABAM-ENB-0023 | SR-TN001032 |  | On Air | 2022-08-12 | ABSM11 | 4G_FD900_ABSM11 | 4G_FD2100_ABSM11 | 4G_TD_ABSM11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208334385 | 2022-08-15 | P/FVC/MDS/1094159/2022 | 2022-08-25 | ST202208339886 | 2022-08-18 | P/FVC/MDS/1094335/2022 | 2022-08-25 |  |  |  |  | ST202208331365 | 2022-08-13 | P/FBW/MDS/1094234/2022 | 2022-08-25
2142 | PATT17 | PATT17 | chennai | Central |  | CHN | Indus | IN-3142918 | R/NN-672352 |  | SO | 2022-08-18 | PATT17 | 4G_FD900_PATT17 | 4G_FD2100_PATT17 | 4G_TD_PATT17 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208361001 | 2022-08-28 | P/FVC/MDS/1094663/2022 | 2022-09-07 | ST202208364575 | 2022-08-29 | P/FVC/MDS/1094728/2022 | 2022-09-07 |  |  |  |  | ST202208355432 | 2022-08-26 | P/FBW/MDS/1094598/2022 | 2022-09-07
2143 | TOND37 | TOND37 | chennai | North |  | CHN | Indus |  | R/NN-673651 |  | SO | 2022-08-02 | TOND37 | 4G_FD900_TOND37 | 4G_FD2100_TOND37 | 4G_TD_TOND37 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313331 | 2022-08-05 | P/FVC/MDS/1093876/2022 | 2022-08-19 | ST202208327175 | 2022-08-11 | P/FVC/MDS/1094024/2022 | 2022-08-19 |  |  |  |  | ST202208307127 | 2022-08-03 | P/FBW/MDS/1093787/2022 | 2022-08-19
2144 | MAHE20 | MAHE20 | chennai | South |  | CHN | ATC | - | - |  | On air | 2022-08-02 | MAHE20 | 4G_FD900_MAHE20 | 4G_FD2100_MAHE20 | 4G_TD_MAHE20 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313261 | 2022-08-05 | P/FVC/MDS/1093864/2022 | 2022-08-19 | ST202208327086 | 2022-08-11 | P/FVC/MDS/1094012/2022 | 2022-08-19 |  |  |  |  | ST202208307078 | 2022-08-03 | P/FBW/MDS/1093776/2022 | 2022-08-19
2145 | ANNAB2 | ANNAB2 | chennai | Central |  | CHN | TVI | - | - |  | SRB(Surrender) | 2022-08-10 | ANNAB2 | 4G_FD900_ANNAB2 | 4G_FD2100_ANNAB2 | 4G_TD_ANNAB2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208331423 | 2022-08-13 | P/FVC/MDS/1094138/2022 | 2022-08-25 | ST202208339382 | 2022-08-18 | P/FVC/MDS/1094314/2022 | 2022-08-25 |  |  |  |  | ST202208331305 | 2022-08-13 | P/FBW/MDS/1094213/2022 | 2022-08-25
2146 | KOVOR2 | KOVOR2 | chennai | South |  | CHN | Indus | IN-3137089 | R/NN-664972 |  | SO | 2022-08-18 | KOVOR2 | 4G_FD900_KOVOR2 | 4G_FD2100_KOVOR2 | 4G_TD_KOVOR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208360986 | 2022-08-28 | P/FVC/MDS/1094656/2022 | 2022-09-07 | ST202208364559 | 2022-08-29 | P/FVC/MDS/1094721/2022 | 2022-09-07 |  |  |  |  | ST202208355415 | 2022-08-26 | P/FBW/MDS/1094593/2022 | 2022-09-07
2147 | MANG21 | MANG21 | chennai | Central |  | CHN | Indus | - | R/NN-664976 |  | On air | 2022-08-02 | MANG21 | 4G_FD900_MANG21 | 4G_FD2100_MANG21 | 4G_TD_MANG21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202208327256 | 2022-08-11 | P/FVC/MDS/1094039/2022 | 2022-08-19 |  |  |  |  | ST202208307541 | 2022-08-03 | P/FBW/MDS/1093802/2022 | 2022-08-19
2148 | NAZRP2 | NAZRP2 | chennai | Central |  | CHN | Indus | IN-3137092 | R/NN-664981 |  | SO | 2022-08-10 | NAZRP2 | 4G_FD900_NAZRP2 | 4G_FD2100_NAZRP2 | 4G_TD_NAZRP2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208331777 | 2022-08-13 | P/FVC/MDS/1094150/2022 | 2022-08-25 | ST202208339611 | 2022-08-18 | P/FVC/MDS/1094326/2022 | 2022-08-25 |  |  |  |  | ST202208331335 | 2022-08-13 | P/FBW/MDS/1094225/2022 | 2022-08-25
2149 | URAP25 | URAP25 | chennai | South |  | CHN | Indus | IN-3142376 | R/NN-671758 |  | On air | 2022-08-10 | URAP25 | 4G_FD900_URAP25 | 4G_FD2100_URAP25 | 4G_TD_URAP25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208331436 | 2022-08-13 | P/FVC/MDS/1094140/2022 | 2022-08-25 | ST202208339396 | 2022-08-18 | P/FVC/MDS/1094316/2022 | 2022-08-25 |  |  |  |  | ST202208331307 | 2022-08-13 | P/FBW/MDS/1094215/2022 | 2022-08-25
2150 | BHAR21 | BHAR21 | chennai | South |  | CHN | Indus | - | R/NN-671797 |  |  | 2022-08-02 | BHAR21 | 4G_FD900_BHAR21 | 4G_FD2100_BHAR21 | 4G_TD_BHAR21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202208327190 | 2022-08-11 | P/FVC/MDS/1094027/2022 | 2022-08-19 |  |  |  |  | ST202208307147 | 2022-08-03 | P/FBW/MDS/1093790/2022 | 2022-08-19
2151 | VTPT21 | VTPT21 | chennai | Central |  | CHN | Indus | IN-3142330 | R/NN-671728 |  | SO | 2022-08-18 | VTPT21 | 4G_FD900_VTPT21 | 4G_FD2100_VTPT21 | 4G_TD_VTPT21 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361000 | 2022-08-28 | P/FVC/MDS/1094662/2022 | 2022-09-07 | ST202208364574 | 2022-08-29 | P/FVC/MDS/1094727/2022 | 2022-09-07 |  |  |  |  | ST202208355426 | 2022-08-26 | P/FBW/MDS/1094597/2022 | 2022-09-07
2152 | ERNA12 | ERNA12 | chennai | North |  | CHN | Indus | IN-3142331 | R/NN-671736 |  | SO | 2022-08-12 | ERNA12 | 4G_FD900_ERNA12 | 4G_FD2100_ERNA12 | 4G_TD_ERNA12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208334468 | 2022-08-15 | P/FVC/MDS/1094163/2022 | 2022-08-25 | ST202208340195 | 2022-08-18 | P/FVC/MDS/1094339/2022 | 2022-08-25 |  |  |  |  | ST202208331375 | 2022-08-13 | P/FBW/MDS/1094238/2022 | 2022-08-25
2153 | KAND37 | KAND37 | chennai | South |  | CHN | Indus | IN-3142369 | R/NN-671754 |  | SO | 2022-08-10 | KAND37 | 4G_FD900_KAND37 | 4G_FD2100_KAND37 | 4G_TD_KAND37 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208331778 | 2022-08-13 | P/FVC/MDS/1094151/2022 | 2022-08-25 | ST202208339612 | 2022-08-18 | P/FVC/MDS/1094327/2022 | 2022-08-25 |  |  |  |  | ST202208331336 | 2022-08-13 | P/FBW/MDS/1094226/2022 | 2022-08-25
2154 | ANAK21 | ANAK21 | chennai | South |  | CHN | Indus | IN-3142385 | R/NN-671766 |  | On air | 2022-08-18 | ANAK21 | 4G_FD900_ANAK21 | 4G_FD2100_ANAK21 | 4G_TD_ANAK21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208360971 | 2022-08-28 | P/FVC/MDS/1094647/2022 | 2022-09-07 | ST202208364538 | 2022-08-29 | P/FVC/MDS/1094712/2022 | 2022-09-07 |  |  |  |  | ST202208355378 | 2022-08-26 | P/FBW/MDS/1094584/2022 | 2022-09-07
2155 | PATT35 | PATT35 | chennai | Central |  | CHN | Indus | IN-3142436 | R/NN-671793 |  | SRB(Surrender) | 2022-08-12 | PATT35 | 4G_FD900_PATT35 | 4G_FD2100_PATT35 | 4G_TD_PATT35 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202208334477 | 2022-08-15 | P/FVC/MDS/1094164/2022 | 2022-08-25 | ST202208340196 | 2022-08-18 | P/FVC/MDS/1094340/2022 | 2022-08-25 |  |  |  |  | ST202208331376 | 2022-08-13 | P/FBW/MDS/1094239/2022 | 2022-08-25
2156 | TIRZ11 | TIRZ11 | chennai | CENTRAL |  | CHN | Indus | IN-3142928 | R/NN-672610 |  | SO | 2022-08-18 | TIRZ11 | 4G_FD900_TIRZ11 | 4G_FD2100_TIRZ11 | 4G_TD_TIRZ11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208360973 | 2022-08-28 | P/FVC/MDS/1094648/2022 | 2022-09-07 | ST202208364542 | 2022-08-29 | P/FVC/MDS/1094713/2022 | 2022-09-07 |  |  |  |  | ST202208355379 | 2022-08-26 | P/FBW/MDS/1094585/2022 | 2022-09-07
2157 | KPAD14 | KPAD14 | chennai |  |  | CHN | ATC | TN/CH/AT/23366 | T22TN05263 |  | SRB(Surrender) | 2022-08-24 | KPAD14 | 4G_FD900_KPAD14 | 4G_FD2100_KPAD14 | 4G_TD_KPAD14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209402587 | 2022-09-08 | P/FVC/MDS/1096544/2022 | 2022-09-16 | ST202209403891 | 2022-09-08 | P/FVC/MDS/1096453/2022 | 2022-09-16 |  |  |  |  | ST202209398977 | 2022-09-07 | P/FVC/MDS/1096359/2022 | 2022-09-16
2158 | RNPT42 | RNPT42 |  |  |  | ROTN | Indus | IN-3134639 | R/NN-659799 |  |  | 2022-08-10 | RNPT42 | 4G_FD900_RNPT42 | 4G_FD2100_RNPT42 | 4G_TD_RNPT42 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208331353 | 2022-08-13 | P/FVC/MDS/1094125/2022 | 2022-08-25 | ST202208339185 | 2022-08-17 | P/FVC/MDS/1094301/2022 | 2022-08-25 | ST202208337229 | 2022-08-17 | P/FVC/MDS/1094279/2022 | 2022-08-25 | ST202208331285 | 2022-08-13 | P/FBW/MDS/1094200/2022 | 2022-08-25
2159 | TECGE3 | TECGE3 |  |  |  | ROTN | Indus | IN-3144602 | R/NN-674251 |  |  | 2022-08-02 | TECGE3 | 4G_FD900_TECGE3 | 4G_FD2100_TECGE3 | 4G_TD_TECGE3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313330 | 2022-08-05 | P/FVC/MDS/1093875/2022 | 2022-08-19 | ST202208327161 | 2022-08-11 | P/FVC/MDS/1094023/2022 | 2022-08-19 | ST202208317248 | 2022-08-08 | P/FVC/MDS/1093941/2022 | 2022-08-19 | ST202208307126 | 2022-08-03 | P/FBW/MDS/1093786/2022 | 2022-08-19
2160 | SNGRC2 | SNGRC2 |  |  |  | ROTN | Indus | IN-3146678 | R/NN-677715 |  |  | 2022-08-18 | SNGRC2 | 4G_FD900_SNGRC2 | 4G_FD2100_SNGRC2 | 4G_TD_SNGRC2 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202208360974 | 2022-08-28 | P/FVC/MDS/1094649/2022 | 2022-09-07 | ST202208364543 | 2022-08-29 | P/FVC/MDS/1094714/2022 | 2022-09-07 | ST202208364739 | 2022-08-29 | P/FVC/MDS/1094773/2022 | 2022-09-07 | ST202208355392 | 2022-08-26 | P/FBW/MDS/1094586/2022 | 2022-09-07
2161 | VMBD18 | VMBD18 |  |  |  | ROTN | Indus | IN-3146679 | R/NN-677716 |  |  | 2022-08-10 | VMBD18 | 4G_FD900_VMBD18 | 4G_FD2100_VMBD18 | 4G_TD_VMBD18 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202208334362 | 2022-08-15 | P/FVC/MDS/1094154/2022 | 2022-08-25 | ST202208339617 | 2022-08-18 | P/FVC/MDS/1094330/2022 | 2022-08-25 | ST202208337374 | 2022-08-17 | P/FVC/MDS/1094285/2022 | 2022-08-25 | ST202208331350 | 2022-08-13 | P/FBW/MDS/1094229/2022 | 2022-08-25
2162 | TIR513 | TIR513 |  |  |  | ROTN | Indus | IN-1074957 | R/RES-511997 |  |  | 2022-08-08 | TIR513 | 4G_FD900_TIR513 | 4G_FD2100_TIR513 | 4G_TD_TIR513 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202208334976 | 2022-08-16 | P/FVC/MDS/1094190/2022 | 2022-08-25 | ST202208340581 | 2022-08-18 | P/FVC/MDS/1094366/2022 | 2022-08-25 | ST202208337431 | 2022-08-17 | P/FVC/MDS/1094296/2022 | 2022-08-25 | ST202208331439 | 2022-08-13 | P/FBW/MDS/1094265/2022 | 2022-08-25
2163 | TNJ364 | TNJ364 |  |  |  | ROTN | Indus | IN-3134687 | R/NN-658854 |  |  | 2022-08-18 | TNJ364 | 4G_FD900_TNJ364 | 4G_FD2100_TNJ364 | 4G_TD_TNJ364 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202208361120 | 2022-08-28 | P/FVC/MDS/1094703/2022 | 2022-09-07 | ST202208364722 | 2022-08-29 | P/FVC/MDS/1094768/2022 | 2022-09-07 | ST202208364769 | 2022-08-29 | P/FVC/MDS/1094792/2022 | 2022-09-07 | ST202208360947 | 2022-08-28 | P/FBW/MDS/1094638/2022 | 2022-09-07
2164 | CBE929 | CBE929 |  |  |  | ROTN | ATC | TN/CO/AT/23065 | CBEM65 |  |  | 2022-08-24 | CBE929 | 4G_FD900_CBE929 | 4G_FD2100_CBE929 | 4G_TD_CBE929 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209402409 | 2022-09-08 | P/FVC/MDS/1096527/2022 | 2022-09-16 | ST202209402310 | 2022-09-08 | P/FVC/MDS/1096436/2022 | 2022-09-16 |  |  |  |  | ST202209398911 | 2022-09-07 | P/FVC/MDS/1096342/2022 | 2022-09-16
2165 | TSMDM2 | TSMDM2 |  |  |  | ROTN | Indus | IN-3132117 | R/NN-656084 |  |  | 2022-08-10 | TSMDM2 | 4G_FD900_TSMDM2 | 4G_FD2100_TSMDM2 | 4G_TD_TSMDM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208331338 | 2022-08-13 | P/FVC/MDS/1094124/2022 | 2022-08-25 | ST202208339184 | 2022-08-17 | P/FVC/MDS/1094300/2022 | 2022-08-25 | ST202208337228 | 2022-08-17 | P/FVC/MDS/1094278/2022 | 2022-08-25 | ST202208331284 | 2022-08-13 | P/FBW/MDS/1094199/2022 | 2022-08-25
2166 | MOGPM4 | MOGPM4 |  |  |  | ROTN | Indus | IN-3134700 | R/NN-659038 |  |  | 2022-08-02 | MOGPM4 | 4G_FD900_MOGPM4 | 4G_FD2100_MOGPM4 | 4G_TD_MOGPM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487182 | 2022-09-27 | P/FVC/MDS/1101547/2022 | 2022-10-10 | ST202209497183 | 2022-09-29 | P/FVC/MDS/1101506/2022 | 2022-10-10 | ST202209487724 | 2022-09-28 | P/FVC/MDS/1101350/2022 | 2022-10-10 | ST202209489370 | 2022-09-28 | P/FBW/MDS/1101082/2022 | 2022-10-10
2167 | ERD247 | ERD247 |  |  |  | ROTN | Indus | IN-3136109 | R/NN-662605 |  |  | 2022-08-02 | ERD247 | 4G_FD900_ERD247 | 4G_FD2100_ERD247 | 4G_TD_ERD247 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313157 | 2022-08-05 | P/FVC/MDS/1093845/2022 | 2022-08-19 | ST202208320646 | 2022-08-09 | P/FVC/MDS/1093993/2022 | 2022-08-19 | ST202208317102 | 2022-08-08 | P/FVC/MDS/1093925/2022 | 2022-08-19 | ST202208306772 | 2022-08-03 | P/FBW/MDS/1093758/2022 | 2022-08-19
2168 | MALVD2 | MALVD2 |  |  |  | ROTN | Indus | IN-3136044 | R/NN-662509 |  |  | 2022-08-18 | MALVD2 | 4G_FD900_MALVD2 | 4G_FD2100_MALVD2 | 4G_TD_MALVD2 | 2G+L1800+L900 | WPC ID Available 2G1800+FD1800+L900 |  | ST202208360997 | 2022-08-28 | P/FVC/MDS/1094661/2022 | 2022-09-07 | ST202208364573 | 2022-08-29 | P/FVC/MDS/1094726/2022 | 2022-09-07 |  |  |  |  | ST202211758535 | 2022-11-16 | P/FBW/MDS/1116828/2022 | 2022-11-29
2169 | MTR040 | MTR040 |  |  |  | ROTN | Indus | IN-3136085 | R/NN-662564 |  |  | 2022-08-02 | MTR040 | 4G_FD900_MTR040 | 4G_FD2100_MTR040 | 4G_TD_MTR040 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313156 | 2022-08-05 | P/FVC/MDS/1093844/2022 | 2022-08-19 | ST202208320645 | 2022-08-09 | P/FVC/MDS/1093992/2022 | 2022-08-19 | ST202208317101 | 2022-08-08 | P/FVC/MDS/1093924/2022 | 2022-08-19 | ST202208306761 | 2022-08-03 | P/FBW/MDS/1093757/2022 | 2022-08-19
2170 | PDY386 | PDY386 |  |  |  | ROTN | Indus | IN-3135964 | R/NN-662415 |  |  | 2022-08-10 | PDY386 | 4G_FD900_PDY386 | 4G_FD2100_PDY386 | 4G_TD_PDY386 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202208331447 | 2022-08-13 | P/FVC/MDS/1094141/2022 | 2022-08-25 | ST202208339408 | 2022-08-18 | P/FVC/MDS/1094317/2022 | 2022-08-25 | ST202208337354 | 2022-08-17 | P/FVC/MDS/1094282/2022 | 2022-08-25 | ST202208331308 | 2022-08-13 | P/FBW/MDS/1094216/2022 | 2022-08-25
2171 | SRGNR3 | SRGNR3 |  |  |  | ROTN | Indus | IN-3136092 | R/NN-662577 |  |  | 2022-08-18 | SRGNR3 | 4G_FD900_SRGNR3 | 4G_FD2100_SRGNR3 | 4G_TD_SRGNR3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361024 | 2022-08-28 | P/FVC/MDS/1094672/2022 | 2022-09-07 | ST202208364599 | 2022-08-29 | P/FVC/MDS/1094737/2022 | 2022-09-07 | ST202208364755 | 2022-08-29 | P/FVC/MDS/1094781/2022 | 2022-09-07 | ST202208355488 | 2022-08-26 | P/FBW/MDS/1094607/2022 | 2022-09-07
2172 | TAMKM2 | TAMKM2 |  |  |  | ROTN | Indus | IN-3136138 | R/NN-662663 |  |  | 2022-08-18 | TAMKM2 | 4G_FD900_TAMKM2 | 4G_FD2100_TAMKM2 | 4G_TD_TAMKM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361017 | 2022-08-28 | P/FVC/MDS/1094670/2022 | 2022-09-07 | ST202208364590 | 2022-08-29 | P/FVC/MDS/1094735/2022 | 2022-09-07 | ST202208364753 | 2022-08-29 | P/FVC/MDS/1094780/2022 | 2022-09-07 | ST202208355472 | 2022-08-26 | P/FBW/MDS/1094605/2022 | 2022-09-07
2173 | TOTNU2 | TOTNU2 |  |  |  | ROTN | Indus | IN-3136093 | R/NN-662581 |  |  | 2022-08-02 | TOTNU2 | 4G_FD900_TOTNU2 | 4G_FD2100_TOTNU2 | 4G_TD_TOTNU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313222 | 2022-08-05 | P/FVC/MDS/1093855/2022 | 2022-08-19 | ST202208320670 | 2022-08-09 | P/FVC/MDS/1094003/2022 | 2022-08-19 | ST202208317197 | 2022-08-08 | P/FVC/MDS/1093932/2022 | 2022-08-19 | ST202208307048 | 2022-08-03 | P/FBW/MDS/1093767/2022 | 2022-08-19
2174 | VLR145 | VLR145 |  |  |  | ROTN | Indus | IN-3136100 | R/NN-662426 |  |  | 2022-08-02 | VLR145 | 4G_FD900_VLR145 | 4G_FD2100_VLR145 | 4G_TD_VLR145 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202208320637 | 2022-08-09 | P/FVC/MDS/1093988/2022 | 2022-08-19 | ST202208317083 | 2022-08-08 | P/FVC/MDS/1093920/2022 | 2022-08-19 | ST202208306753 | 2022-08-03 | P/FBW/MDS/1093753/2022 | 2022-08-19
2175 | VMBD41 | VMBD41 |  |  |  | ROTN | Indus | IN-3138483 | R/NN-662728 |  |  | 2022-08-18 | VMBD41 | 4G_FD900_VMBD41 | 4G_FD2100_VMBD41 | 4G_TD_VMBD41 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208360985 | 2022-08-28 | P/FVC/MDS/1094655/2022 | 2022-09-07 | ST202208364558 | 2022-08-29 | P/FVC/MDS/1094720/2022 | 2022-09-07 | ST202208364741 | 2022-08-29 | P/FVC/MDS/1094775/2022 | 2022-09-07 | ST202208355414 | 2022-08-26 | P/FBW/MDS/1094592/2022 | 2022-09-07
2176 | NLGRI4 | NLGRI4 |  |  |  | ROTN | Summit | I-TN-TJVR-ENB-0043 | SR-TN001033 |  |  | 2022-08-12 | NLGRI4 | 4G_FD900_NLGRI4 | 4G_FD2100_NLGRI4 | 4G_TD_NLGRI4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334556 | 2022-08-15 | P/FVC/MDS/1094178/2022 | 2022-08-25 | ST202208340473 | 2022-08-18 | P/FVC/MDS/1094354/2022 | 2022-08-25 | ST202208337402 | 2022-08-17 | P/FVC/MDS/1094292/2022 | 2022-08-25 | ST202208331410 | 2022-08-13 | P/FBW/MDS/1094253/2022 | 2022-08-25
2177 | KNKPM2 | KNKPM2 |  |  |  | ROTN | Indus | IN-3143442 | R/NN-672944 |  |  | 2022-08-18 | KNKPM2 | 4G_FD900_KNKPM2 | 4G_FD2100_KNKPM2 | 4G_TD_KNKPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361114 | 2022-08-28 | P/FVC/MDS/1094700/2022 | 2022-09-07 | ST202208364718 | 2022-08-29 | P/FVC/MDS/1094765/2022 | 2022-09-07 | ST202208364765 | 2022-08-29 | P/FVC/MDS/1094789/2022 | 2022-09-07 | ST202208355632 | 2022-08-26 | P/FBW/MDS/1094635/2022 | 2022-09-07
2178 | POOLM3 | POOLM3 |  |  |  | ROTN | Indus | IN-3138611 | R/NN-664299 |  |  | 2022-08-02 | POOLM3 | 4G_FD900_POOLM3 | 4G_FD2100_POOLM3 | 4G_TD_POOLM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313229 | 2022-08-05 | P/FVC/MDS/1093859/2022 | 2022-08-19 | ST202208320679 | 2022-08-09 | P/FVC/MDS/1094007/2022 | 2022-08-19 | ST202208317222 | 2022-08-08 | P/FVC/MDS/1093935/2022 | 2022-08-19 | ST202208307065 | 2022-08-03 | P/FBW/MDS/1093771/2022 | 2022-08-19
2179 | AGLKC2 | AGLKC2 |  |  |  | ROTN | Indus | IN-3138578 | R/NN-663213 |  |  | 2022-08-02 | AGLKC2 | 4G_FD900_AGLKC2 | 4G_FD2100_AGLKC2 | 4G_TD_AGLKC2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313223 | 2022-08-05 | P/FVC/MDS/1093856/2022 | 2022-08-19 | ST202208320673 | 2022-08-09 | P/FVC/MDS/1094004/2022 | 2022-08-19 | ST202208317198 | 2022-08-08 | P/FVC/MDS/1093933/2022 | 2022-08-19 | ST202208307049 | 2022-08-03 | P/FBW/MDS/1093768/2022 | 2022-08-19
2180 | PRNDM2 | PRNDM2 |  |  |  | ROTN | Indus | IN-3143443 | R/NN-672950 |  |  | 2022-08-24 | PRNDM2 | 4G_FD900_PRNDM2 | 4G_FD2100_PRNDM2 | 4G_TD_PRNDM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209402585 | 2022-09-08 | P/FVC/MDS/1096542/2022 | 2022-09-16 | ST202209403854 | 2022-09-08 | P/FVC/MDS/1096451/2022 | 2022-09-16 | ST202209401221 | 2022-09-08 | P/FVC/MDS/1096421/2022 | 2022-09-16 | ST202209398958 | 2022-09-07 | P/FVC/MDS/1096357/2022 | 2022-09-16
2181 | VLR144 | VLR144 |  |  |  | ROTN | Indus | IN-1031427 | R/RES-511178 |  |  | 2022-08-02 | VLR144 | 4G_FD900_VLR144 | 4G_FD2100_VLR144 | 4G_TD_VLR144 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313210 | 2022-08-05 | P/FVC/MDS/1093854/2022 | 2022-08-19 | ST202208320669 | 2022-08-09 | P/FVC/MDS/1094002/2022 | 2022-08-19 | ST202208317175 | 2022-08-08 | P/FVC/MDS/1093931/2022 | 2022-08-19 | ST202208306800 | 2022-08-03 | P/FBW/MDS/1093766/2022 | 2022-08-19
2182 | SNYPT3 | SNYPT3 |  |  |  | ROTN | Indus | IN-3138579 | R/NN-663217 |  |  | 2022-08-12 | SNYPT3 | 4G_FD900_SNYPT3 | 4G_FD2100_SNYPT3 | 4G_TD_SNYPT3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334958 | 2022-08-16 | P/FVC/MDS/1094186/2022 | 2022-08-25 | ST202208340555 | 2022-08-18 | P/FVC/MDS/1094362/2022 | 2022-08-25 | ST202208337411 | 2022-08-17 | P/FVC/MDS/1094293/2022 | 2022-08-25 | ST202208331432 | 2022-08-13 | P/FBW/MDS/1094261/2022 | 2022-08-25
2183 | PUNAM3 | PUNAM3 |  |  |  | ROTN | Indus | IN-3138575 | R/NN-663221 |  |  | 2022-08-02 | PUNAM3 | 4G_FD900_PUNAM3 | 4G_FD2100_PUNAM3 | 4G_TD_PUNAM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313224 | 2022-08-05 | P/FVC/MDS/1093857/2022 | 2022-08-19 | ST202208320674 | 2022-08-09 | P/FVC/MDS/1094005/2022 | 2022-08-19 | ST202208317199 | 2022-08-08 | P/FVC/MDS/1093934/2022 | 2022-08-19 | ST202208307050 | 2022-08-03 | P/FBW/MDS/1093769/2022 | 2022-08-19
2184 | CBE945 | CBE945 |  |  |  | ROTN | Indus | IN-3136225 | R/NN-662838 |  |  | 2022-08-02 | CBE945 | 4G_FD900_CBE945 | 4G_FD2100_CBE945 | 4G_TD_CBE945 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202208320628 | 2022-08-09 | P/FVC/MDS/1093984/2022 | 2022-08-19 |  |  |  |  | ST202208306039 | 2022-08-02 | P/FBW/MDS/1093749/2022 | 2022-08-19
2185 | KAPYM3 | KAPYM3 |  |  |  | ROTN | Indus | IN-3138622 | R/NN-664405 |  |  | 2022-08-02 | KAPYM3 | 4G_FD900_KAPYM3 | 4G_FD2100_KAPYM3 | 4G_TD_KAPYM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313315 | 2022-08-05 | P/FVC/MDS/1093872/2022 | 2022-08-19 | ST202208327143 | 2022-08-11 | P/FVC/MDS/1094020/2022 | 2022-08-19 | ST202208317238 | 2022-08-08 | P/FVC/MDS/1093939/2022 | 2022-08-19 | ST202208307110 | 2022-08-03 | P/FBW/MDS/1093784/2022 | 2022-08-19
2186 | VADAK2 | VADAK2 |  |  |  | ROTN | Indus | IN-3138591 | R/NN-664204 |  |  | 2022-08-12 | VADAK2 | 4G_FD900_VADAK2 | 4G_FD2100_VADAK2 | 4G_TD_VADAK2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334975 | 2022-08-16 | P/FVC/MDS/1094189/2022 | 2022-08-25 | ST202208340569 | 2022-08-18 | P/FVC/MDS/1094365/2022 | 2022-08-25 | ST202208337413 | 2022-08-17 | P/FVC/MDS/1094295/2022 | 2022-08-25 | ST202208331438 | 2022-08-13 | P/FBW/MDS/1094264/2022 | 2022-08-25
2187 | PNPTT2 | PNPTT2 |  |  |  | ROTN | Indus | IN-3138580 | R/NN-663234 |  |  | 2022-08-02 | PNPTT2 | 4G_FD900_PNPTT2 | 4G_FD2100_PNPTT2 | 4G_TD_PNPTT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313228 | 2022-08-05 | P/FVC/MDS/1093858/2022 | 2022-08-19 | ST202208320675 | 2022-08-09 | P/FVC/MDS/1094006/2022 | 2022-08-19 |  |  |  |  | ST202208307064 | 2022-08-03 | P/FBW/MDS/1093770/2022 | 2022-08-19
2188 | TRY409 | TRY409 |  |  |  | ROTN | Indus | IN-3138606 | R/NN-664212 |  |  | 2022-08-24 | TRY409 | 4G_FD900_TRY409 | 4G_FD2100_TRY409 | 4G_TD_TRY409 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209402411 | 2022-09-08 | P/FVC/MDS/1096529/2022 | 2022-09-16 | ST202209402381 | 2022-09-08 | P/FVC/MDS/1096438/2022 | 2022-09-16 | ST202209401206 | 2022-09-08 | P/FVC/MDS/1096420/2022 | 2022-09-16 | ST202209398913 | 2022-09-07 | P/FVC/MDS/1096344/2022 | 2022-09-16
2189 | EGMO16 | EGMO16 |  |  |  | CHN | ATC | TN/CH/TT/13100 | - |  |  | 2022-06-24 | EGMO16 | 4G_FD900_EGMO16 | 4G_FD2100_EGMO16 | 4G_TD_EGMO16 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202207225973 | 2022-07-07 | P/FVC/MDS/1087994/2022 | 2022-07-18 | ST202207224760 | 2022-07-06 | P/FVC/MDS/1087887/2022 | 2022-07-18 | ST202207228362 | 2022-07-07 | P/FVC/MDS/1087954/2022 | 2022-07-18 | ST202207222789 | 2022-07-06 | P/FBW/MDS/1087802/2022 | 2022-07-18
2190 | MUDIC8 | MUDIC8 |  |  |  | CHN | Srigom | SG0021 | - |  |  | 2022-08-10 | MUDIC8 | 4G_FD900_MUDIC8 | 4G_FD2100_MUDIC8 | 4G_TD_MUDIC8 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208331514 | 2022-08-13 | P/FVC/MDS/1094148/2022 | 2022-08-25 | ST202208339605 | 2022-08-18 | P/FVC/MDS/1094324/2022 | 2022-08-25 | ST202208337365 | 2022-08-17 | P/FVC/MDS/1094283/2022 | 2022-08-25 | ST202208331331 | 2022-08-13 | P/FBW/MDS/1094223/2022 | 2022-08-25
2191 | ATIP15 | ATIP15 |  |  |  | CHN | Indus | IN-3134675 | R/NN-659273 |  |  | 2022-08-18 | ATIP15 | 4G_FD900_ATIP15 | 4G_FD2100_ATIP15 | 4G_TD_ATIP15 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361107 | 2022-08-28 | P/FVC/MDS/1094696/2022 | 2022-09-07 | ST202208364710 | 2022-08-29 | P/FVC/MDS/1094761/2022 | 2022-09-07 | ST202208364761 | 2022-08-29 | P/FVC/MDS/1094785/2022 | 2022-09-07 | ST202208355596 | 2022-08-26 | P/FBW/MDS/1094631/2022 | 2022-09-07
2192 | RANGA7 | RANGA7 |  |  |  | CHN | Indus | IN-3138678 | R/NN-663266 |  |  | 2022-08-10 | RANGA7 | 4G_FD900_RANGA7 | 4G_FD2100_RANGA7 | 4G_TD_RANGA7 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208331542 | 2022-08-13 | P/FVC/MDS/1094149/2022 | 2022-08-25 | ST202208339606 | 2022-08-18 | P/FVC/MDS/1094325/2022 | 2022-08-25 | ST202208337366 | 2022-08-17 | P/FVC/MDS/1094284/2022 | 2022-08-25 | ST202208331334 | 2022-08-13 | P/FBW/MDS/1094224/2022 | 2022-08-25
2193 | RAJAK9 | RAJAK9 |  |  |  | CHN | Indus | IN-3147856 | R/NN-678680 |  |  | 2022-08-18 | RAJAK9 | 4G_FD900_RAJAK9 | 4G_FD2100_RAJAK9 | 4G_TD_RAJAK9 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361121 | 2022-08-28 | P/FVC/MDS/1094704/2022 | 2022-09-07 | ST202208364723 | 2022-08-29 | P/FVC/MDS/1094769/2022 | 2022-09-07 | ST202208364771 | 2022-08-29 | P/FVC/MDS/1094793/2022 | 2022-09-07 | ST202208360952 | 2022-08-28 | P/FBW/MDS/1094639/2022 | 2022-09-07
2194 | ASHO23 | ASHO23 |  |  |  | CHN | Indus | IN-3042571 | R/RES-512028 |  |  | 2022-08-08 | ASHO23 | 4G_FD900_ASHO23 | 4G_FD2100_ASHO23 | 4G_TD_ASHO23 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334985 | 2022-08-16 | P/FVC/MDS/1094192/2022 | 2022-08-25 | ST202208340583 | 2022-08-18 | P/FVC/MDS/1094368/2022 | 2022-08-25 | ST202208337433 | 2022-08-17 | P/FVC/MDS/1094298/2022 | 2022-08-25 | ST202208331445 | 2022-08-13 | P/FBW/MDS/1094267/2022 | 2022-08-25
2195 | TOND36 | TOND36 |  |  |  | CHN | Indus | IN-1007206 | R/RES-512027 |  |  | 2022-08-18 | TOND36 | 4G_FD900_TOND36 | 4G_FD2100_TOND36 | 4G_TD_TOND36 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361113 | 2022-08-28 | P/FVC/MDS/1094699/2022 | 2022-09-07 | ST202208364716 | 2022-08-29 | P/FVC/MDS/1094764/2022 | 2022-09-07 | ST202208364764 | 2022-08-29 | P/FVC/MDS/1094788/2022 | 2022-09-07 | ST202208355631 | 2022-08-26 | P/FBW/MDS/1094634/2022 | 2022-09-07
2196 | BHAR19 | BHAR19 |  |  |  | CHN | Indus | IN-3138679 | R/NN-664411 |  |  | 2022-08-18 | BHAR19 | 4G_FD900_BHAR19 | 4G_FD2100_BHAR19 | 4G_TD_BHAR19 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361122 | 2022-08-28 | P/FVC/MDS/1094705/2022 | 2022-09-07 | ST202208364726 | 2022-08-29 | P/FVC/MDS/1094770/2022 | 2022-09-07 | ST202208364772 | 2022-08-29 | P/FVC/MDS/1094794/2022 | 2022-09-07 | ST202208360953 | 2022-08-28 | P/FBW/MDS/1094640/2022 | 2022-09-07
2197 | MAHA22 | MAHA22 |  |  |  | CHN | Indus | IN-3136412 | R/NN-664227 |  |  | 2022-08-02 | MAHA22 | 4G_FD900_MAHA22 | 4G_FD2100_MAHA22 | 4G_TD_MAHA22 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313107 | 2022-08-05 | P/FVC/MDS/1093842/2022 | 2022-08-19 | ST202208320638 | 2022-08-09 | P/FVC/MDS/1093989/2022 | 2022-08-19 | ST202208317084 | 2022-08-08 | P/FVC/MDS/1093921/2022 | 2022-08-19 | ST202208306754 | 2022-08-03 | P/FBW/MDS/1093754/2022 | 2022-08-19
2198 | ADNRM2 | ADNRM2 |  |  |  | ROTN | Indus | IN-3138943 | R/NN-667504 |  |  | 2022-08-12 | ADNRM2 | 4G_FD900_ADNRM2 | 4G_FD2100_ADNRM2 | 4G_TD_ADNRM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334546 | 2022-08-15 | P/FVC/MDS/1094174/2022 | 2022-08-25 | ST202208340456 | 2022-08-18 | P/FVC/MDS/1094350/2022 | 2022-08-25 | ST202208337390 | 2022-08-17 | P/FVC/MDS/1094290/2022 | 2022-08-25 | ST202208331402 | 2022-08-13 | P/FBW/MDS/1094249/2022 | 2022-08-25
2199 | AMPKM2 | AMPKM2 |  |  |  | ROTN | Indus | IN-3138944 | R/NN-667506 |  |  | 2022-08-18 | AMPKM2 | 4G_FD900_AMPKM2 | 4G_FD2100_AMPKM2 | 4G_TD_AMPKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208361035 | 2022-08-28 | P/FVC/MDS/1094676/2022 | 2022-09-07 | ST202208364610 | 2022-08-29 | P/FVC/MDS/1094741/2022 | 2022-09-07 | ST202208364756 | 2022-08-29 | P/FVC/MDS/1094782/2022 | 2022-09-07 | ST202208355519 | 2022-08-26 | P/FBW/MDS/1094611/2022 | 2022-09-07
2200 | CDPRM2 | CDPRM2 |  |  |  | ROTN | Indus | IN-3138902 | R/NN-667432 |  |  | 2022-08-02 | CDPRM2 | 4G_FD900_CDPRM2 | 4G_FD2100_CDPRM2 | 4G_TD_CDPRM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313209 | 2022-08-05 | P/FVC/MDS/1093853/2022 | 2022-08-19 | ST202208320663 | 2022-08-09 | P/FVC/MDS/1094001/2022 | 2022-08-19 | ST202208317174 | 2022-08-08 | P/FVC/MDS/1093930/2022 | 2022-08-19 | ST202208306799 | 2022-08-03 | P/FBW/MDS/1093765/2022 | 2022-08-19
2201 | CTRPT2 | CTRPT2 |  |  |  | ROTN | Indus | IN-3138950 | R/NN-667514 |  |  | 2022-08-02 | CTRPT2 | 4G_FD900_CTRPT2 | 4G_FD2100_CTRPT2 | 4G_TD_CTRPT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313247 | 2022-08-05 | P/FVC/MDS/1093862/2022 | 2022-08-19 | ST202208327084 | 2022-08-11 | P/FVC/MDS/1094010/2022 | 2022-08-19 | ST202208317237 | 2022-08-08 | P/FVC/MDS/1093938/2022 | 2022-08-19 | ST202208307073 | 2022-08-03 | P/FBW/MDS/1093774/2022 | 2022-08-19
2202 | DGL122 | DGL122 |  |  |  | ROTN | Indus | IN-3138629 | R/NN-666906 |  |  | 2022-08-02 | DGL122 | 4G_FD900_DGL122 | 4G_FD2100_DGL122 | 4G_TD_DGL122 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202208320639 | 2022-08-09 | P/FVC/MDS/1093990/2022 | 2022-08-19 | ST202208317085 | 2022-08-08 | P/FVC/MDS/1093922/2022 | 2022-08-19 | ST202208306759 | 2022-08-03 | P/FBW/MDS/1093755/2022 | 2022-08-19
2203 | DGL123 | DGL123 |  |  |  | ROTN | Summit | I-TN-DDGL-ENB-0038 | SR-TN001021 |  |  | 2022-08-18 | DGL123 | 4G_FD900_DGL123 | 4G_FD2100_DGL123 | 4G_TD_DGL123 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361104 | 2022-08-28 | P/FVC/MDS/1094695/2022 | 2022-09-07 | ST202208364705 | 2022-08-29 | P/FVC/MDS/1094760/2022 | 2022-09-07 | ST202208364760 | 2022-08-29 | P/FVC/MDS/1094784/2022 | 2022-09-07 | ST202208355595 | 2022-08-26 | P/FBW/MDS/1094630/2022 | 2022-09-07
2204 | DGL124 | DGL124 |  |  |  | ROTN | Indus | IN-3138440 | R/NN-667057 |  |  | 2022-08-02 | DGL124 | 4G_FD900_DGL124 | 4G_FD2100_DGL124 | 4G_TD_DGL124 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313191 | 2022-08-05 | P/FVC/MDS/1093852/2022 | 2022-08-19 | ST202208320662 | 2022-08-09 | P/FVC/MDS/1094000/2022 | 2022-08-19 | ST202208317173 | 2022-08-08 | P/FVC/MDS/1093929/2022 | 2022-08-19 | ST202208306798 | 2022-08-03 | P/FBW/MDS/1093764/2022 | 2022-08-19
2205 | ECGUD2 | ECGUD2 |  |  |  | ROTN | Indus | IN-3138951 | R/NN-667516 |  |  | 2022-08-12 | ECGUD2 | 4G_FD900_ECGUD2 | 4G_FD2100_ECGUD2 | 4G_TD_ECGUD2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334551 | 2022-08-15 | P/FVC/MDS/1094175/2022 | 2022-08-25 | ST202208340457 | 2022-08-18 | P/FVC/MDS/1094351/2022 | 2022-08-25 | ST202208337401 | 2022-08-17 | P/FVC/MDS/1094291/2022 | 2022-08-25 | ST202208331403 | 2022-08-13 | P/FBW/MDS/1094250/2022 | 2022-08-25
2206 | HSR196 | HSR196 |  |  |  | ROTN | Indus | IN-3147861 | R/NN-678943 |  |  | 2022-08-18 | HSR196 | 4G_FD900_HSR196 | 4G_FD2100_HSR196 | 4G_TD_HSR196 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208360975 | 2022-08-28 | P/FVC/MDS/1094650/2022 | 2022-09-07 | ST202208364547 | 2022-08-29 | P/FVC/MDS/1094715/2022 | 2022-09-07 | ST202208364740 | 2022-08-29 | P/FVC/MDS/1094774/2022 | 2022-09-07 | ST202208355393 | 2022-08-26 | P/FBW/MDS/1094587/2022 | 2022-09-07
2207 | IDVPM3 | IDVPM3 |  |  |  | ROTN | Indus | IN-3138517 | R/NN-667157 |  |  | 2022-08-12 | IDVPM3 | 4G_FD900_IDVPM3 | 4G_FD2100_IDVPM3 | 4G_TD_IDVPM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334541 | 2022-08-15 | P/FVC/MDS/1094172/2022 | 2022-08-25 | ST202208340418 | 2022-08-18 | P/FVC/MDS/1094348/2022 | 2022-08-25 | ST202208337387 | 2022-08-17 | P/FVC/MDS/1094288/2022 | 2022-08-25 | ST202208331397 | 2022-08-13 | P/FBW/MDS/1094247/2022 | 2022-08-25
2208 | KALYR2 | KALYR2 |  |  |  | ROTN | Indus | IN-3138295 | R/NN-666796 |  |  | 2022-08-02 | KALYR2 | 4G_FD900_KALYR2 | 4G_FD2100_KALYR2 | 4G_TD_KALYR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313166 | 2022-08-05 | P/FVC/MDS/1093846/2022 | 2022-08-19 | ST202208320650 | 2022-08-09 | P/FVC/MDS/1093994/2022 | 2022-08-19 |  |  |  |  | ST202208306773 | 2022-08-03 | P/FBW/MDS/1093759/2022 | 2022-08-19
2209 | KMKPM2 | KMKPM2 |  |  |  | ROTN | Indus | IN-3138296 | R/NN-666800 |  |  | 2022-08-02 | KMKPM2 | 4G_FD900_KMKPM2 | 4G_FD2100_KMKPM2 | 4G_TD_KMKPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313181 | 2022-08-05 | P/FVC/MDS/1093850/2022 | 2022-08-19 | ST202208320657 | 2022-08-09 | P/FVC/MDS/1093998/2022 | 2022-08-19 |  |  |  |  | ST202208306790 | 2022-08-03 | P/FBW/MDS/1093763/2022 | 2022-08-19
2210 | KNBKM2 | KNBKM2 |  |  |  | ROTN | Indus | IN-3138297 | R/NN-666803 |  |  | 2022-08-02 | KNBKM2 | 4G_FD900_KNBKM2 | 4G_FD2100_KNBKM2 | 4G_TD_KNBKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208313190 | 2022-08-05 | P/FVC/MDS/1093851/2022 | 2022-08-19 | ST202208320661 | 2022-08-09 | P/FVC/MDS/1093999/2022 | 2022-08-19 |  |  |  |  | ST202208314499 | 2022-08-06 | P/FBW/MDS/1093679/2022 | 2022-08-19
2211 | KPKTR2 | KPKTR2 |  |  |  | ROTN | Indus | IN-3138952 | R/NN-667518 |  |  | 2022-08-10 | KPKTR2 | 4G_FD900_KPKTR2 | 4G_FD2100_KPKTR2 | 4G_TD_KPKTR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208331408 | 2022-08-13 | P/FVC/MDS/1094135/2022 | 2022-08-25 | ST202208339374 | 2022-08-18 | P/FVC/MDS/1094311/2022 | 2022-08-25 | ST202208337352 | 2022-08-17 | P/FVC/MDS/1094280/2022 | 2022-08-25 | ST202208331301 | 2022-08-13 | P/FBW/MDS/1094210/2022 | 2022-08-25
2212 | KRR114 | KRR114 |  |  |  | ROTN | Indus | IN-3138903 | R/NN-667433 |  |  | 2022-08-18 | KRR114 | 4G_FD900_KRR114 | 4G_FD2100_KRR114 | 4G_TD_KRR114 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361012 | 2022-08-28 | P/FVC/MDS/1094668/2022 | 2022-09-07 | ST202208364584 | 2022-08-29 | P/FVC/MDS/1094733/2022 | 2022-09-07 | ST202208364752 | 2022-08-29 | P/FVC/MDS/1094779/2022 | 2022-09-07 | ST202208355458 | 2022-08-26 | P/FBW/MDS/1094603/2022 | 2022-09-07
2213 | MGRN18 | MGRN18 |  |  |  | CHN | Indus | IN-3138521 | R/NN-667161 |  |  | 2022-08-18 | MGRN18 | 4G_FD900_MGRN18 | 4G_FD2100_MGRN18 | 4G_TD_MGRN18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361119 | 2022-08-28 | P/FVC/MDS/1094702/2022 | 2022-09-07 | ST202208364720 | 2022-08-29 | P/FVC/MDS/1094767/2022 | 2022-09-07 | ST202208364768 | 2022-08-29 | P/FVC/MDS/1094791/2022 | 2022-09-07 | ST202208360946 | 2022-08-28 | P/FBW/MDS/1094637/2022 | 2022-09-07
2214 | MNDUR2 | MNDUR2 |  |  |  | ROTN | Indus | IN-3138337 | R/NN-666898 |  |  | 2022-08-18 | MNDUR2 | 4G_FD900_MNDUR2 | 4G_FD2100_MNDUR2 | 4G_TD_MNDUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361118 | 2022-08-28 | P/FVC/MDS/1094701/2022 | 2022-09-07 | ST202208364719 | 2022-08-29 | P/FVC/MDS/1094766/2022 | 2022-09-07 | ST202208364766 | 2022-08-29 | P/FVC/MDS/1094790/2022 | 2022-09-07 | ST202208360945 | 2022-08-28 | P/FBW/MDS/1094636/2022 | 2022-09-07
2215 | NLGKP4 | NLGKP4 |  |  |  | ROTN | Indus | IN-3139952 | R/NN-667522 |  |  | 2022-08-12 | NLGKP4 | 4G_FD900_NLGKP4 | 4G_FD2100_NLGKP4 | 4G_TD_NLGKP4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334467 | 2022-08-15 | P/FVC/MDS/1094162/2022 | 2022-08-25 | ST202208339915 | 2022-08-18 | P/FVC/MDS/1094338/2022 | 2022-08-25 | ST202208337376 | 2022-08-17 | P/FVC/MDS/1094287/2022 | 2022-08-25 | ST202208331374 | 2022-08-13 | P/FBW/MDS/1094237/2022 | 2022-08-25
2216 | NLTUR2 | NLTUR2 |  |  |  | ROTN | Indus | IN-3138726 | R/NN-667301 |  |  | 2022-08-02 | NLTUR2 | 4G_FD900_NLTUR2 | 4G_FD2100_NLTUR2 | 4G_TD_NLTUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313246 | 2022-08-05 | P/FVC/MDS/1093861/2022 | 2022-08-19 | ST202208320681 | 2022-08-09 | P/FVC/MDS/1094009/2022 | 2022-08-19 | ST202208317236 | 2022-08-08 | P/FVC/MDS/1093937/2022 | 2022-08-19 | ST202208307072 | 2022-08-03 | P/FBW/MDS/1093773/2022 | 2022-08-19
2217 | NYSRU2 | NYSRU2 |  |  |  | ROTN | Indus | IN-3138729 | R/NN-667303 |  |  | 2022-08-12 | NYSRU2 | 4G_FD900_NYSRU2 | 4G_FD2100_NYSRU2 | 4G_TD_NYSRU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334545 | 2022-08-15 | P/FVC/MDS/1094173/2022 | 2022-08-25 | ST202208340420 | 2022-08-18 | P/FVC/MDS/1094349/2022 | 2022-08-25 | ST202208337389 | 2022-08-17 | P/FVC/MDS/1094289/2022 | 2022-08-25 | ST202208331398 | 2022-08-13 | P/FBW/MDS/1094248/2022 | 2022-08-25
2218 | SLM420 | SLM420 |  |  |  | ROTN | Indus | IN-3138350 | R/NN-666934 |  |  | 2022-08-18 | SLM420 | 4G_FD900_SLM420 | 4G_FD2100_SLM420 | 4G_TD_SLM420 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361112 | 2022-08-28 | P/FVC/MDS/1094698/2022 | 2022-09-07 | ST202208364715 | 2022-08-29 | P/FVC/MDS/1094763/2022 | 2022-09-07 | ST202208364763 | 2022-08-29 | P/FVC/MDS/1094787/2022 | 2022-09-07 | ST202208355609 | 2022-08-26 | P/FBW/MDS/1094633/2022 | 2022-09-07
2219 | SNMTR2 | SNMTR2 |  |  |  | ROTN | Indus | IN-3138335 | R/NN-666818 |  |  | 2022-08-02 | SNMTR2 | 4G_FD900_SNMTR2 | 4G_FD2100_SNMTR2 | 4G_TD_SNMTR2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202208313329 | 2022-08-05 | P/FVC/MDS/1093874/2022 | 2022-08-19 | ST202208327160 | 2022-08-11 | P/FVC/MDS/1094022/2022 | 2022-08-19 | ST202208317247 | 2022-08-08 | P/FVC/MDS/1093940/2022 | 2022-08-19
2220 | SORTR2 | SORTR2 |  |  |  | ROTN | Indus | IN-3139025 | R/NN-667660 |  |  | 2022-08-10 | SORTR2 | 4G_FD900_SORTR2 | 4G_FD2100_SORTR2 | 4G_TD_SORTR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208331421 | 2022-08-13 | P/FVC/MDS/1094136/2022 | 2022-08-25 | ST202208339375 | 2022-08-18 | P/FVC/MDS/1094312/2022 | 2022-08-25 | ST202208337353 | 2022-08-17 | P/FVC/MDS/1094281/2022 | 2022-08-25 | ST202208331303 | 2022-08-13 | P/FBW/MDS/1094211/2022 | 2022-08-25
2221 | SVPLM2 | SVPLM2 |  |  |  | ROTN | Indus | IN-3138737 | R/NN-667320 |  |  | 2022-08-18 | SVPLM2 | 4G_FD900_SVPLM2 | 4G_FD2100_SVPLM2 | 4G_TD_SVPLM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361006 | 2022-08-28 | P/FVC/MDS/1094665/2022 | 2022-09-07 | ST202208364578 | 2022-08-29 | P/FVC/MDS/1094730/2022 | 2022-09-07 | ST202208364748 | 2022-08-29 | P/FVC/MDS/1094778/2022 | 2022-09-07 | ST202208355434 | 2022-08-26 | P/FBW/MDS/1094600/2022 | 2022-09-07
2222 | TINDL2 | TINDL2 |  |  |  | ROTN | Indus | IN-3138660 | R/NN-667258 |  |  | 2022-08-02 | TINDL2 | 4G_FD900_TINDL2 | 4G_FD2100_TINDL2 | 4G_TD_TINDL2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313180 | 2022-08-05 | P/FVC/MDS/1093849/2022 | 2022-08-19 | ST202208320656 | 2022-08-09 | P/FVC/MDS/1093997/2022 | 2022-08-19 | ST202208317156 | 2022-08-08 | P/FVC/MDS/1093928/2022 | 2022-08-19 | ST202208306789 | 2022-08-03 | P/FBW/MDS/1093762/2022 | 2022-08-19
2223 | TRY412 | TRY412 |  |  |  | ROTN | Indus | IN-3138371 | R/NN-666991 |  |  | 2022-08-02 | TRY412 | 4G_FD900_TRY412 | 4G_FD2100_TRY412 | 4G_TD_TRY412 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313179 | 2022-08-05 | P/FVC/MDS/1093848/2022 | 2022-08-19 | ST202208320655 | 2022-08-09 | P/FVC/MDS/1093996/2022 | 2022-08-19 | ST202208317155 | 2022-08-08 | P/FVC/MDS/1093927/2022 | 2022-08-19 | ST202208306788 | 2022-08-03 | P/FBW/MDS/1093761/2022 | 2022-08-19
2224 | UDYPT3 | UDYPT3 |  |  |  | ROTN | Indus | IN-3138340 | R/NN-666901 |  |  | 2022-08-02 | UDYPT3 | 4G_FD900_UDYPT3 | 4G_FD2100_UDYPT3 | 4G_TD_UDYPT3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313230 | 2022-08-05 | P/FVC/MDS/1093860/2022 | 2022-08-19 | ST202208320680 | 2022-08-09 | P/FVC/MDS/1094008/2022 | 2022-08-19 | ST202208317223 | 2022-08-08 | P/FVC/MDS/1093936/2022 | 2022-08-19 | ST202208307068 | 2022-08-03 | P/FBW/MDS/1093772/2022 | 2022-08-19
2225 | CDL105 | CDL105 |  |  |  | ROTN | Indus | IN-3139161 | R/NN-666750 |  |  | 2022-08-02 | CDL105 | 4G_FD900_CDL105 | 4G_FD2100_CDL105 | 4G_TD_CDL105 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313096 | 2022-08-05 | P/FVC/MDS/1093839/2022 | 2022-08-19 | ST202208320632 | 2022-08-09 | P/FVC/MDS/1093985/2022 | 2022-08-19 | ST202208317066 | 2022-08-08 | P/FVC/MDS/1093918/2022 | 2022-08-19 | ST202208306040 | 2022-08-02 | P/FBW/MDS/1093750/2022 | 2022-08-19
2226 | GOVTC3 | GOVTC3 |  |  |  | ROTN | Indus | IN-3139160 | R/NN-666801 |  |  | 2022-08-02 | GOVTC3 | 4G_FD900_GOVTC3 | 4G_FD2100_GOVTC3 | 4G_TD_GOVTC3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313167 | 2022-08-05 | P/FVC/MDS/1093847/2022 | 2022-08-19 | ST202208320651 | 2022-08-09 | P/FVC/MDS/1093995/2022 | 2022-08-19 | ST202208317154 | 2022-08-08 | P/FVC/MDS/1093926/2022 | 2022-08-19 | ST202208306774 | 2022-08-03 | P/FBW/MDS/1093760/2022 | 2022-08-19
2227 | AMNCH2 | AMNCH2 |  |  |  | ROTN | Indus | IN-3138661 | R/NN-666647 |  |  | 2022-08-18 | AMNCH2 | 4G_FD900_AMNCH2 | 4G_FD2100_AMNCH2 | 4G_TD_AMNCH2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202208360991 | 2022-08-28 | P/FVC/MDS/1094658/2022 | 2022-09-07 | ST202208364565 | 2022-08-29 | P/FVC/MDS/1094723/2022 | 2022-09-07 | ST202208364746 | 2022-08-29 | P/FVC/MDS/1094776/2022 | 2022-09-07
2228 | KASIM3 | KASIM3 |  |  |  | CHN | Indus | IN-3138263 | R/NN-666776 |  |  | 2022-08-02 | KASIM3 | 4G_FD900_KASIM3 | 4G_FD2100_KASIM3 | 4G_TD_KASIM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313105 | 2022-08-05 | P/FVC/MDS/1093840/2022 | 2022-08-19 | ST202208320633 | 2022-08-09 | P/FVC/MDS/1093986/2022 | 2022-08-19 | ST202208317067 | 2022-08-08 | P/FVC/MDS/1093919/2022 | 2022-08-19 | ST202208306041 | 2022-08-02 | P/FBW/MDS/1093751/2022 | 2022-08-19
2229 | CBE892 | CBE892 |  |  |  | ROTN | Indus | IN-3138669 | R/NN-666903 |  |  | 2022-08-08 | CBE892 | 4G_FD900_CBE892 | 4G_FD2100_CBE892 | 4G_TD_CBE892 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202208334984 | 2022-08-16 | P/FVC/MDS/1094191/2022 | 2022-08-25 | ST202208340582 | 2022-08-18 | P/FVC/MDS/1094367/2022 | 2022-08-25 | ST202208337432 | 2022-08-17 | P/FVC/MDS/1094297/2022 | 2022-08-25 | ST202208331444 | 2022-08-13 | P/FBW/MDS/1094266/2022 | 2022-08-25
2230 | TARA33 | TARA33 |  |  |  | CHN | TVI | - | - |  |  | 2022-08-24 | TARA33 | 4G_FD900_TARA33 | 4G_FD2100_TARA33 | 4G_TD_TARA33 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202209402410 | 2022-09-08 | P/FVC/MDS/1096528/2022 | 2022-09-16 | ST202209402380 | 2022-09-08 | P/FVC/MDS/1096437/2022 | 2022-09-16 | ST202209401205 | 2022-09-08 | P/FVC/MDS/1096419/2022 | 2022-09-16 | ST202209398912 | 2022-09-07 | P/FVC/MDS/1096343/2022 | 2022-09-16
2231 | MDU526 | MDU526 |  |  |  | ROTN | Indus | IN-3105732 | R/NN-639064 |  |  | 2022-08-18 | MDU526 | 4G_FD900_MDU526 | 4G_FD2100_MDU526 | 4G_TD_MDU526 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361109 | 2022-08-28 | P/FVC/MDS/1094697/2022 | 2022-09-07 | ST202208364711 | 2022-08-29 | P/FVC/MDS/1094762/2022 | 2022-09-07 | ST202208364762 | 2022-08-29 | P/FVC/MDS/1094786/2022 | 2022-09-07 | ST202208355608 | 2022-08-26 | P/FBW/MDS/1094632/2022 | 2022-09-07
2232 | CBE954 | CBE954 |  |  |  | ROTN | Indus | IN-3139958 | R/NN-668203 |  |  | 2022-08-18 | CBE954 | 4G_FD900_CBE954 | 4G_FD2100_CBE954 | 4G_TD_CBE954 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208361101 | 2022-08-28 | P/FVC/MDS/1094694/2022 | 2022-09-07 | ST202208364704 | 2022-08-29 | P/FVC/MDS/1094759/2022 | 2022-09-07 | ST202208364757 | 2022-08-29 | P/FVC/MDS/1094783/2022 | 2022-09-07 | ST202208355594 | 2022-08-26 | P/FBW/MDS/1094629/2022 | 2022-09-07
2233 | GDLR18 | GDLR18 |  |  |  | ROTN | Indus | IN-3140383 | R/NN-669002 |  |  | 2022-08-02 | GDLR18 | 4G_FD900_GDLR18 | 4G_FD2100_GDLR18 | 4G_TD_GDLR18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208313371 | 2022-08-05 | P/FVC/MDS/1093888/2022 | 2022-08-19 | ST202208327265 | 2022-08-11 | P/FVC/MDS/1094040/2022 | 2022-08-19 | ST202208317259 | 2022-08-08 | P/FVC/MDS/1093942/2022 | 2022-08-19 | ST202208307545 | 2022-08-03 | P/FBW/MDS/1093803/2022 | 2022-08-19
2234 | NGL146 | NGL146 |  |  |  | ROTN | Indus | IN-3096522 | R/RES-512461 |  |  | 2022-08-12 | NGL146 | 4G_FD900_NGL146 | 4G_FD2100_NGL146 | 4G_TD_NGL146 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202208334394 | 2022-08-15 | P/FVC/MDS/1094161/2022 | 2022-08-25 | ST202208339914 | 2022-08-18 | P/FVC/MDS/1094337/2022 | 2022-08-25 | ST202208337375 | 2022-08-17 | P/FVC/MDS/1094286/2022 | 2022-08-25 | ST202208331368 | 2022-08-13 | P/FBW/MDS/1094236/2022 | 2022-08-25
2235 | BELLS6 | BELLS6 |  |  |  | CHN | Indus | IN-3147352 | R/NN-678054 |  |  | 2022-08-12 | BELLS6 | 4G_FD900_BELLS6 | 4G_FD2100_BELLS6 | 4G_TD_BELLS6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202208334966 | 2022-08-16 | P/FVC/MDS/1094188/2022 | 2022-08-25 | ST202208340568 | 2022-08-18 | P/FVC/MDS/1094364/2022 | 2022-08-25 | ST202208337412 | 2022-08-17 | P/FVC/MDS/1094294/2022 | 2022-08-25 | ST202208331437 | 2022-08-13 | P/FBW/MDS/1094263/2022 | 2022-08-25
2236 | KMPT16 | KMPT16 |  |  |  | ROTN | Airtel | - | - |  | SO |  | KMPT16 | 4G_FD900_KMPT16 | 4G_FD2100_KMPT16 | 4G_TD_KMPT16 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442315 | 2022-09-18 | P/FVC/MDS/1098042/2022 | 2022-09-27 | ST202209445731 | 2022-09-19 | P/FVC/MDS/1098130/2022 | 2022-09-27 |  |  |  |  | ST202209431114 | 2022-09-17 | P/FVC/MDS/1097914/2022 | 2022-09-27
2237 | TIVR32 | TIVR32 |  |  |  | ROTN | Airtel | - | - |  | SO |  | TIVR32 | 4G_FD900_TIVR32 | 4G_FD2100_TIVR32 | 4G_TD_TIVR32 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485718 | 2022-09-27 | P/FVC/MDS/1101223/2022 | 2022-10-10 | ST202209492779 | 2022-09-28 | P/FVC/MDS/1101393/2022 | 2022-10-10 |  |  |  |  | ST202209483588 | 2022-09-26 | P/FBW/MDS/1101117/2022 | 2022-10-10
2238 | CBE762 | CBE762 |  |  |  | ROTN | Ascend |  |  |  | SP |  | CBE762 | 4G_FD900_CBE762 | 4G_FD2100_CBE762 | 4G_TD_CBE762 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442429 | 2022-09-18 | P/FVC/MDS/1098072/2022 | 2022-09-27 | ST202209446286 | 2022-09-19 | P/FVC/MDS/1098160/2022 | 2022-09-27 |  |  |  |  | ST202209431746 | 2022-09-17 | P/FVC/MDS/1097945/2022 | 2022-09-27
2239 | VLRM59 | VLRM59 |  |  |  | ROTN | TVI | - | - |  | SO |  | VLRM59 | 4G_FD900_VLRM59 | 4G_FD2100_VLRM59 | 4G_TD_VLRM59 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442305 | 2022-09-18 | P/FVC/MDS/1098040/2022 | 2022-09-27 | ST202209445729 | 2022-09-19 | P/FVC/MDS/1098128/2022 | 2022-09-27 | ST202107393754 | 2021-07-23 | P/FVC/MDS/1057236/2021 | 2021-09-09 | ST202209431102 | 2022-09-17 | P/FVC/MDS/1097912/2022 | 2022-09-27
2240 | CBE821 | CBE821 |  |  |  | ROTN | Airtel |  | R/NN-669059 |  | SO |  | CBE821 | 4G_FD900_CBE821 | 4G_FD2100_CBE821 | 4G_TD_CBE821 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209442405 | 2022-09-18 | P/FVC/MDS/1098063/2022 | 2022-09-27 | ST202209446091 | 2022-09-19 | P/FVC/MDS/1098151/2022 | 2022-09-27 |  |  |  |  | ST202209431510 | 2022-09-17 | P/FVC/MDS/1097933/2022 | 2022-09-27
2241 | AVNI23 | AVNI23 |  |  |  | ROTN | Ascend | - | - |  | Dropped |  | AVNI23 | 4G_FD900_AVNI23 | 4G_FD2100_AVNI23 | 4G_TD_AVNI23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405140 | 2022-09-09 | P/FVC/MDS/1096581/2022 | 2022-09-16 | ST202209405618 | 2022-09-09 | P/FVC/MDS/1096490/2022 | 2022-09-16 |  |  |  |  | ST202209399897 | 2022-09-08 | P/FVC/MDS/1096396/2022 | 2022-09-16
2242 | MDKKUR | MDKKUR |  |  |  | ROTN | Ascend |  |  |  | On Air |  | MDKKUR | 4G_FD900_MDKKUR | 4G_FD2100_MDKKUR | 4G_TD_MDKKUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209404996 | 2022-09-09 | P/FVC/MDS/1096569/2022 | 2022-09-16 | ST202209404074 | 2022-09-08 | P/FVC/MDS/1096478/2022 | 2022-09-16 |  |  |  |  | ST202209399823 | 2022-09-08 | P/FVC/MDS/1096384/2022 | 2022-09-16
2243 | SATR22 | SATR22 |  |  |  | ROTN | Ascend |  |  |  | On Air |  | SATR22 | 4G_FD900_SATR22 | 4G_FD2100_SATR22 | 4G_TD_SATR22 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442452 | 2022-09-18 | P/FVC/MDS/1098077/2022 | 2022-09-27 | ST202209446372 | 2022-09-19 | P/FVC/MDS/1098165/2022 | 2022-09-27 |  |  |  |  | ST202209431801 | 2022-09-17 | P/FVC/MDS/1097949/2022 | 2022-09-27
2244 | BLPLM4 | BLPLM4 |  |  |  | ROTN | Indus |  | R/NN-682108 |  |  |  | BLPLM4 | 4G_FD900_BLPLM4 | 4G_FD2100_BLPLM4 | 4G_TD_BLPLM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442399 | 2022-09-18 | P/FVC/MDS/1098057/2022 | 2022-09-27 | ST202209445998 | 2022-09-19 | P/FVC/MDS/1098145/2022 | 2022-09-27 |  |  |  |  | ST202209431413 | 2022-09-17 | P/FVC/MDS/1097927/2022 | 2022-09-27
2245 | EDUTH1 | EDUTH1 |  |  |  | ROTN | Ascend | TN/VLP/AT/22435 | T21TN01772 |  | On Air |  | EDUTH1 | 4G_FD900_EDUTH1 | 4G_FD2100_EDUTH1 | 4G_TD_EDUTH1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403762 | 2022-09-08 | P/FVC/MDS/1096553/2022 | 2022-09-16 | ST202209403966 | 2022-09-08 | P/FVC/MDS/1096462/2022 | 2022-09-16 |  |  |  |  | ST202209399010 | 2022-09-07 | P/FVC/MDS/1096368/2022 | 2022-09-16
2246 | PAZYAR | PAZYAR |  |  |  | ROTN | ATC | TN/NA/AT/23063 | T22TN01075 |  | SO |  | PAZYAR | 4G_FD900_PAZYAR | 4G_FD2100_PAZYAR | 4G_TD_PAZYAR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405107 | 2022-09-09 | P/FVC/MDS/1096573/2022 | 2022-09-16 | ST202209405586 | 2022-09-09 | P/FVC/MDS/1096482/2022 | 2022-09-16 |  |  |  |  | ST202209399846 | 2022-09-08 | P/FVC/MDS/1096388/2022 | 2022-09-16
2247 | VIKSLR | VIKSLR |  |  |  | ROTN | Airtel |  |  |  | SO |  | VIKSLR | 4G_FD900_VIKSLR | 4G_FD2100_VIKSLR | 4G_TD_VIKSLR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442306 | 2022-09-18 | P/FVC/MDS/1098041/2022 | 2022-09-27 | ST202209445730 | 2022-09-19 | P/FVC/MDS/1098129/2022 | 2022-09-27 |  |  |  |  | ST202209431113 | 2022-09-17 | P/FVC/MDS/1097913/2022 | 2022-09-27
2248 | SASIMl | SASIMl |  |  |  | ROTN | Airtel | - | - |  | SO |  | SASIMl | 4G_FD900_SASIMl | 4G_FD2100_SASIMl | 4G_TD_SASIMl | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539112 | 2022-10-08 | P/FVC/MDS/1114032/2022 | 2022-10-21 | ST202210538165 | 2022-10-08 | P/FVC/MDS/1113846/2022 | 2022-10-21 |  |  |  |  | ST202210549242 | 2022-10-11 | P/FBW/MDS/1113761/2022 | 2022-10-21
2249 | KALAI4 | KALAI4 |  |  |  | ROTN | Ascend | - | - |  | On Air |  | KALAI4 | 4G_FD900_KALAI4 | 4G_FD2100_KALAI4 | 4G_TD_KALAI4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485122 | 2022-09-27 | P/FVC/MDS/1101188/2022 | 2022-10-10 | ST202209491543 | 2022-09-28 | P/FVC/MDS/1101358/2022 | 2022-10-10 |  |  |  |  | ST202209483122 | 2022-09-26 | P/FBW/MDS/1101088/2022 | 2022-10-10
2250 | VLNKI3 | VLNKI3 |  |  |  | ROTN | Summit | I-TN-VDSD-ENB-9073 |  |  | On Air |  | VLNKI3 | 4G_FD900_VLNKI3 | 4G_FD2100_VLNKI3 | 4G_TD_VLNKI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403759 | 2022-09-08 | P/FVC/MDS/1096551/2022 | 2022-09-16 | ST202209403964 | 2022-09-08 | P/FVC/MDS/1096460/2022 | 2022-09-16 |  |  |  |  | ST202209432405 | 2022-09-17 | P/FVC/MDS/1097987/2022 | 2022-09-27
2251 | CONR28 | CONR28 |  |  |  | ROTN | Indus | - | R/NN-677551 |  | On Air |  | CONR28 | 4G_FD900_CONR28 | 4G_FD2100_CONR28 | 4G_TD_CONR28 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403827 | 2022-09-08 | P/FVC/MDS/1096560/2022 | 2022-09-16 | ST202209404015 | 2022-09-08 | P/FVC/MDS/1096469/2022 | 2022-09-16 |  |  |  |  | ST202209399022 | 2022-09-07 | P/FVC/MDS/1096375/2022 | 2022-09-16
2252 | PLAPN2 | PLAPN2 |  |  |  | ROTN | Ascend | - | - |  | On Air |  | PLAPN2 | 4G_FD900_PLAPN2 | 4G_FD2100_PLAPN2 | 4G_TD_PLAPN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485121 | 2022-09-27 | P/FVC/MDS/1101187/2022 | 2022-10-10 | ST202209491542 | 2022-09-28 | P/FVC/MDS/1101357/2022 | 2022-10-10 |  |  |  |  | ST202209483121 | 2022-09-26 | P/FBW/MDS/1101087/2022 | 2022-10-10
2253 | VELUR3 | VELUR3 |  |  |  | ROTN | ATC | TN/NM/AT/23150 | T22TN01402 |  | SO |  | VELUR3 | 4G_FD900_VELUR3 | 4G_FD2100_VELUR3 | 4G_TD_VELUR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486424 | 2022-09-27 | P/FVC/MDS/1101265/2022 | 2022-10-10 | ST202209493231 | 2022-09-28 | P/FVC/MDS/1101434/2022 | 2022-10-10 |  |  |  |  | ST202209484090 | 2022-09-26 | P/FBW/MDS/1101158/2022 | 2022-10-10
2254 | UCHPT2 | UCHPT2 |  |  |  | ROTN | Indus | - | R/NN-654448 |  | On Air |  | UCHPT2 | 4G_FD900_UCHPT2 | 4G_FD2100_UCHPT2 | 4G_TD_UCHPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403800 | 2022-09-08 | P/FVC/MDS/1096556/2022 | 2022-09-16 | ST202209403995 | 2022-09-08 | P/FVC/MDS/1096465/2022 | 2022-09-16 |  |  |  |  | ST202209399017 | 2022-09-07 | P/FVC/MDS/1096371/2022 | 2022-09-16
2255 | PUNGP2 | PUNGP2 |  |  |  | ROTN | ATC | TN/ER/AT/23160 | T22TN01412 |  | On Air |  | PUNGP2 | 4G_FD900_PUNGP2 | 4G_FD2100_PUNGP2 | 4G_TD_PUNGP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209404962 | 2022-09-09 | P/FVC/MDS/1096562/2022 | 2022-09-16 | ST202209404037 | 2022-09-08 | P/FVC/MDS/1096471/2022 | 2022-09-16 |  |  |  |  | ST202209399057 | 2022-09-07 | P/FVC/MDS/1096377/2022 | 2022-09-16
2256 | MLPTY2 | MLPTY2 |  |  |  | ROTN | Ascend | - | - |  | SO |  | MLPTY2 | 4G_FD900_MLPTY2 | 4G_FD2100_MLPTY2 | 4G_TD_MLPTY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485093 | 2022-09-27 | P/FVC/MDS/1101184/2022 | 2022-10-10 | ST202209491444 | 2022-09-28 | P/FVC/MDS/1101354/2022 | 2022-10-10 |  |  |  |  | ST202209483037 | 2022-09-26 | P/FBW/MDS/1101084/2022 | 2022-10-10
2257 | NATMP2 | NATMP2 |  |  |  | ROTN | Ascend | - | - |  | SO |  | NATMP2 | 4G_FD900_NATMP2 | 4G_FD2100_NATMP2 | 4G_TD_NATMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485131 | 2022-09-27 | P/FVC/MDS/1101189/2022 | 2022-10-10 | ST202209491544 | 2022-09-28 | P/FVC/MDS/1101359/2022 | 2022-10-10 |  |  |  |  | ST202209483123 | 2022-09-26 | P/FBW/MDS/1101089/2022 | 2022-10-10
2258 | ILPUR4 | ILPUR4 |  |  |  | ROTN | Ascend | - | - |  | On Air |  | ILPUR4 | 4G_FD900_ILPUR4 | 4G_FD2100_ILPUR4 | 4G_TD_ILPUR4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209442293 | 2022-09-18 | P/FVC/MDS/1098038/2022 | 2022-09-27 | ST202209445693 | 2022-09-19 | P/FVC/MDS/1098127/2022 | 2022-09-27 |  |  |  |  | ST202209431101 | 2022-09-17 | P/FVC/MDS/1097911/2022 | 2022-09-27
2259 | KILUR2 | KILUR2 |  |  |  | ROTN | Ascend | - | - |  | SO |  | KILUR2 | 4G_FD900_KILUR2 | 4G_FD2100_KILUR2 | 4G_TD_KILUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485095 | 2022-09-27 | P/FVC/MDS/1101186/2022 | 2022-10-10 | ST202209491446 | 2022-09-28 | P/FVC/MDS/1101356/2022 | 2022-10-10 |  |  |  |  | ST202209483040 | 2022-09-26 | P/FBW/MDS/1101086/2022 | 2022-10-10
2260 | METKD2 | METKD2 |  |  |  | ROTN | Ascend |  |  |  | SO |  | METKD2 | 4G_FD900_METKD2 | 4G_FD2100_METKD2 | 4G_TD_METKD2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209402638 | 2022-09-08 | P/FVC/MDS/1096549/2022 | 2022-09-16 | ST202209403948 | 2022-09-08 | P/FVC/MDS/1096458/2022 | 2022-09-16 |  |  |  |  | ST202209398991 | 2022-09-07 | P/FVC/MDS/1096364/2022 | 2022-09-16
2261 | PETAI2 | PETAI2 |  |  |  | ROTN | Ascend |  |  |  | On Air |  | PETAI2 | 4G_FD900_PETAI2 | 4G_FD2100_PETAI2 | 4G_TD_PETAI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403785 | 2022-09-08 | P/FVC/MDS/1096555/2022 | 2022-09-16 | ST202209403984 | 2022-09-08 | P/FVC/MDS/1096464/2022 | 2022-09-16 |  |  |  |  | ST202209399012 | 2022-09-07 | P/FVC/MDS/1096370/2022 | 2022-09-16
2262 | NEDNG3 | NEDNG3 |  |  |  | ROTN | Ascend | - | - |  | On Air |  | NEDNG3 | 4G_FD900_NEDNG3 | 4G_FD2100_NEDNG3 | 4G_TD_NEDNG3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485094 | 2022-09-27 | P/FVC/MDS/1101185/2022 | 2022-10-10 | ST202209491445 | 2022-09-28 | P/FVC/MDS/1101355/2022 | 2022-10-10 |  |  |  |  | ST202209483039 | 2022-09-26 | P/FBW/MDS/1101085/2022 | 2022-10-10
2263 | ALYKD2 | ALYKD2 |  |  |  | ROTN | Ascend |  |  |  | On Air |  | ALYKD2 | 4G_FD900_ALYKD2 | 4G_FD2100_ALYKD2 | 4G_TD_ALYKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442408 | 2022-09-18 | P/FVC/MDS/1098066/2022 | 2022-09-27 | ST202209446138 | 2022-09-19 | P/FVC/MDS/1098154/2022 | 2022-09-27 |  |  |  |  | ST202209431546 | 2022-09-17 | P/FVC/MDS/1097936/2022 | 2022-09-27
2264 | TNJ182 | TNJ182 |  |  |  | ROTN | Indus | IN-3138195 | R/NN-666101 |  |  |  | TNJ182 | 4G_FD900_TNJ182 | 4G_FD2100_TNJ182 | 4G_TD_TNJ182 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485664 | 2022-09-27 | P/FVC/MDS/1101210/2022 | 2022-10-10 | ST202209491908 | 2022-09-28 | P/FVC/MDS/1101380/2022 | 2022-10-10 |  |  |  |  | ST202209483503 | 2022-09-26 | P/FBW/MDS/1101106/2022 | 2022-10-10
2265 | SVPRI2 | SVPRI2 |  |  |  | ROTN | Ascend |  |  |  | SO |  | SVPRI2 | 4G_FD900_SVPRI2 | 4G_FD2100_SVPRI2 | 4G_TD_SVPRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209402639 | 2022-09-08 | P/FVC/MDS/1096550/2022 | 2022-09-16 | ST202209403949 | 2022-09-08 | P/FVC/MDS/1096459/2022 | 2022-09-16 |  |  |  |  | ST202209398997 | 2022-09-07 | P/FVC/MDS/1096365/2022 | 2022-09-16
2266 | MDU534 | MDU534 |  |  |  | ROTN | Indus |  | R/NN-664948 |  | On Air |  | MDU534 | 4G_FD900_MDU534 | 4G_FD2100_MDU534 | 4G_TD_MDU534 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209442779 | 2022-09-19 | P/FVC/MDS/1098115/2022 | 2022-09-27 | ST202209447427 | 2022-09-19 | P/FVC/MDS/1098203/2022 | 2022-09-27 |  |  |  |  | ST202209432315 | 2022-09-17 | P/FVC/MDS/1097980/2022 | 2022-09-27
2267 | TRKCI5 | TRKCI5 |  |  |  | ROTN | Ascend |  |  |  | SO |  | TRKCI5 | 4G_FD900_TRKCI5 | 4G_FD2100_TRKCI5 | 4G_TD_TRKCI5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209403802 | 2022-09-08 | P/FVC/MDS/1096558/2022 | 2022-09-16 | ST202209404013 | 2022-09-08 | P/FVC/MDS/1096467/2022 | 2022-09-16 |  |  |  |  | ST202209399020 | 2022-09-07 | P/FVC/MDS/1096373/2022 | 2022-09-16
2268 | BVNI33 | BVNI33 |  |  |  | ROTN | ATC | TN/ER/AT/23256 | T22TN04112 |  | On Air |  | BVNI33 | 4G_FD900_BVNI33 | 4G_FD2100_BVNI33 | 4G_TD_BVNI33 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485703 | 2022-09-27 | P/FVC/MDS/1101218/2022 | 2022-10-10 | ST202209492042 | 2022-09-28 | P/FVC/MDS/1101388/2022 | 2022-10-10 |  |  |  |  | ST202209483555 | 2022-09-26 | P/FBW/MDS/1101112/2022 | 2022-10-10
2269 | PMKD35 | PMKD35 |  |  |  | ROTN | Ascend | - |  |  | SO |  | PMKD35 | 4G_FD900_PMKD35 | 4G_FD2100_PMKD35 | 4G_TD_PMKD35 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209404983 | 2022-09-09 | P/FVC/MDS/1096566/2022 | 2022-09-16 | ST202209404061 | 2022-09-08 | P/FVC/MDS/1096475/2022 | 2022-09-16 |  |  |  |  | ST202209399068 | 2022-09-07 | P/FVC/MDS/1096381/2022 | 2022-09-16
2270 | RJPM60 | RJPM60 |  |  |  | ROTN | Ascend | - |  |  | On Air |  | RJPM60 | 4G_FD900_RJPM60 | 4G_FD2100_RJPM60 | 4G_TD_RJPM60 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209404984 | 2022-09-09 | P/FVC/MDS/1096567/2022 | 2022-09-16 | ST202209404067 | 2022-09-08 | P/FVC/MDS/1096476/2022 | 2022-09-16 |  |  |  |  | ST202209399805 | 2022-09-08 | P/FVC/MDS/1096382/2022 | 2022-09-16
2271 | SLVN10 | SLVN10 |  |  |  | ROTN | Indus | IN-3142333 | R/NN-671733 |  | On Air |  | SLVN10 | 4G_FD900_SLVN10 | 4G_FD2100_SLVN10 | 4G_TD_SLVN10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487132 | 2022-09-27 | P/FVC/MDS/1101532/2022 | 2022-10-10 | ST202209495861 | 2022-09-29 | P/FVC/MDS/1101475/2022 | 2022-10-10 |  |  |  |  | ST202209484389 | 2022-09-26 | P/FBW/MDS/1101066/2022 | 2022-10-10
2272 | KLNGL3 | KLNGL3 |  |  |  | ROTN | Indus |  | R/NN-673595 |  | On Air |  | KLNGL3 | 4G_FD900_KLNGL3 | 4G_FD2100_KLNGL3 | 4G_TD_KLNGL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202208327980 | 2022-08-11 | P/FVC/MDS/1093897/2022 | 2022-08-19 | ST202208327815 | 2022-08-11 | P/FVC/MDS/1094053/2022 | 2022-08-19 | ST202208328019 | 2022-08-11 | P/FVC/MDS/1093944/2022 | 2022-08-19 | ST202208327928 | 2022-08-11 | P/FBW/MDS/1093696/2022 | 2022-08-19
2273 | VMBTI4 | VMBTI4 |  |  |  | ROTN | ATC |  |  |  | SO |  | VMBTI4 | 4G_FD900_VMBTI4 | 4G_FD2100_VMBTI4 | 4G_TD_VMBTI4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405108 | 2022-09-09 | P/FVC/MDS/1096574/2022 | 2022-09-16 | ST202209405587 | 2022-09-09 | P/FVC/MDS/1096483/2022 | 2022-09-16 |  |  |  |  | ST202209399860 | 2022-09-08 | P/FVC/MDS/1096389/2022 | 2022-09-16
2274 | PNJDV2 | PNJDV2 |  |  |  | ROTN | Ascend |  |  |  | On Air |  | PNJDV2 | 4G_FD900_PNJDV2 | 4G_FD2100_PNJDV2 | 4G_TD_PNJDV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442409 | 2022-09-18 | P/FVC/MDS/1098067/2022 | 2022-09-27 | ST202209446170 | 2022-09-19 | P/FVC/MDS/1098155/2022 | 2022-09-27 |  |  |  |  | ST202209431578 | 2022-09-17 | P/FVC/MDS/1097937/2022 | 2022-09-27
2275 | AYMPL2 | AYMPL2 |  |  |  | ROTN | ATC | TN/TI/AT/23339 | T22TN04330 |  | On Air |  | AYMPL2 | 4G_FD900_AYMPL2 | 4G_FD2100_AYMPL2 | 4G_TD_AYMPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405180 | 2022-09-09 | P/FVC/MDS/1096586/2022 | 2022-09-16 | ST202209405633 | 2022-09-09 | P/FVC/MDS/1096495/2022 | 2022-09-16 |  |  |  |  | ST202209399943 | 2022-09-08 | P/FVC/MDS/1096401/2022 | 2022-09-16
2276 | PCMKT2 | PCMKT2 |  |  |  | ROTN | ATC |  |  |  | On Air |  | PCMKT2 | 4G_FD900_PCMKT2 | 4G_FD2100_PCMKT2 | 4G_TD_PCMKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209403801 | 2022-09-08 | P/FVC/MDS/1096557/2022 | 2022-09-16 | ST202209403996 | 2022-09-08 | P/FVC/MDS/1096466/2022 | 2022-09-16 |  |  |  |  | ST202209399018 | 2022-09-07 | P/FVC/MDS/1096372/2022 | 2022-09-16
2277 | SYLGI2 | SYLGI2 |  |  |  | ROTN | Ascend |  |  |  | On Air |  | SYLGI2 | 4G_FD900_SYLGI2 | 4G_FD2100_SYLGI2 | 4G_TD_SYLGI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209404995 | 2022-09-09 | P/FVC/MDS/1096568/2022 | 2022-09-16 | ST202209404069 | 2022-09-08 | P/FVC/MDS/1096477/2022 | 2022-09-16 |  |  |  |  | ST202209399807 | 2022-09-08 | P/FVC/MDS/1096383/2022 | 2022-09-16
2278 | COLOR4 | COLOR4 |  |  |  | ROTN | Indus | IN-3144061 | R/NN-674975 |  | On Air |  | COLOR4 | 4G_FD900_COLOR4 | 4G_FD2100_COLOR4 | 4G_TD_COLOR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405220 | 2022-09-09 | P/FVC/MDS/1096591/2022 | 2022-09-16 | ST202209406112 | 2022-09-09 | P/FVC/MDS/1096500/2022 | 2022-09-16 |  |  |  |  | ST202209400121 | 2022-09-08 | P/FVC/MDS/1096406/2022 | 2022-09-16
2279 | MTGRI5 | MTGRI5 |  |  |  | ROTN | Indus | - | R/NN-675418 |  | SO |  | MTGRI5 | 4G_FD900_MTGRI5 | 4G_FD2100_MTGRI5 | 4G_TD_MTGRI5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209442326 | 2022-09-18 | P/FVC/MDS/1098045/2022 | 2022-09-27 | ST202209445811 | 2022-09-19 | P/FVC/MDS/1098133/2022 | 2022-09-27 |  |  |  |  | ST202209431134 | 2022-09-17 | P/FVC/MDS/1097917/2022 | 2022-09-27
2280 | CHIKA3 | CHIKA3 |  |  |  | ROTN | Indus | IN-3150951 | R/NN-682945 |  | On Air |  | CHIKA3 | 4G_FD900_CHIKA3 | 4G_FD2100_CHIKA3 | 4G_TD_CHIKA3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485140 | 2022-09-27 | P/FVC/MDS/1101192/2022 | 2022-10-10 | ST202209491727 | 2022-09-28 | P/FVC/MDS/1101362/2022 | 2022-10-10 |  |  |  |  | ST202209483174 | 2022-09-26 | P/FBW/MDS/1101092/2022 | 2022-10-10
2281 | AGSRM3 | AGSRM3 |  |  |  | ROTN | Indus | - | R/NN-675284 |  | SO |  | AGSRM3 | 4G_FD900_AGSRM3 | 4G_FD2100_AGSRM3 | 4G_TD_AGSRM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442325 | 2022-09-18 | P/FVC/MDS/1098044/2022 | 2022-09-27 | ST202209445771 | 2022-09-19 | P/FVC/MDS/1098132/2022 | 2022-09-27 |  |  |  |  | ST202209431133 | 2022-09-17 | P/FVC/MDS/1097916/2022 | 2022-09-27
2282 | PRPRM3 | PRPRM3 |  |  |  | ROTN | Ascend |  |  |  | SO |  | PRPRM3 | 4G_FD900_PRPRM3 | 4G_FD2100_PRPRM3 | 4G_TD_PRPRM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442407 | 2022-09-18 | P/FVC/MDS/1098065/2022 | 2022-09-27 | ST202209446137 | 2022-09-19 | P/FVC/MDS/1098153/2022 | 2022-09-27 |  |  |  |  | ST202209431545 | 2022-09-17 | P/FVC/MDS/1097935/2022 | 2022-09-27
2283 | MRNDL3 | MRNDL3 |  |  |  | ROTN | Indus | IN-1126802 | R/RES-513072 |  | On Air |  | MRNDL3 | 4G_FD900_MRNDL3 | 4G_FD2100_MRNDL3 | 4G_TD_MRNDL3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209486408 | 2022-09-27 | P/FVC/MDS/1101263/2022 | 2022-10-10 | ST202209493202 | 2022-09-28 | P/FVC/MDS/1101432/2022 | 2022-10-10 |  |  |  |  | ST202209484088 | 2022-09-26 | P/FBW/MDS/1101156/2022 | 2022-10-10
2284 | KLRPM3 | KLRPM3 |  |  |  | ROTN | Ascend | - | - |  | On Air |  | KLRPM3 | 4G_FD900_KLRPM3 | 4G_FD2100_KLRPM3 | 4G_TD_KLRPM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405158 | 2022-09-09 | P/FVC/MDS/1096583/2022 | 2022-09-16 | ST202209405626 | 2022-09-09 | P/FVC/MDS/1096492/2022 | 2022-09-16 |  |  |  |  | ST202209399914 | 2022-09-08 | P/FVC/MDS/1096398/2022 | 2022-09-16
2285 | PUTHU2 | PUTHU2 |  |  |  | ROTN | Ascend |  |  |  | SR |  | PUTHU2 | 4G_FD900_PUTHU2 | 4G_FD2100_PUTHU2 | 4G_TD_PUTHU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442421 | 2022-09-18 | P/FVC/MDS/1098071/2022 | 2022-09-27 | ST202209446250 | 2022-09-19 | P/FVC/MDS/1098159/2022 | 2022-09-27 |  |  |  |  | ST202209431614 | 2022-09-17 | P/FVC/MDS/1097941/2022 | 2022-09-27
2286 | KKDVU9 | KKDVU9 |  |  |  | ROTN | ATC |  |  |  | On Air |  | KKDVU9 | 4G_FD900_KKDVU9 | 4G_FD2100_KKDVU9 | 4G_TD_KKDVU9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405095 | 2022-09-09 | P/FVC/MDS/1096572/2022 | 2022-09-16 | ST202209405583 | 2022-09-09 | P/FVC/MDS/1096481/2022 | 2022-09-16 |  |  |  |  | ST202209399845 | 2022-09-08 | P/FVC/MDS/1096387/2022 | 2022-09-16
2287 | ERD255 | ERD255 |  |  |  | ROTN | ATC |  |  |  | On Air |  | ERD255 | 4G_FD900_ERD255 | 4G_FD2100_ERD255 | 4G_TD_ERD255 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405117 | 2022-09-09 | P/FVC/MDS/1096575/2022 | 2022-09-16 | ST202209405592 | 2022-09-09 | P/FVC/MDS/1096484/2022 | 2022-09-16 |  |  |  |  | ST202209399861 | 2022-09-08 | P/FVC/MDS/1096390/2022 | 2022-09-16
2288 | TIR514 | TIR514 |  |  |  | ROTN | ATC | TN/TI/AT/23357 | T22TN04348 |  | On Air |  | TIR514 | 4G_FD900_TIR514 | 4G_FD2100_TIR514 | 4G_TD_TIR514 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405160 | 2022-09-09 | P/FVC/MDS/1096584/2022 | 2022-09-16 | ST202209405627 | 2022-09-09 | P/FVC/MDS/1096493/2022 | 2022-09-16 |  |  |  |  | ST202209399927 | 2022-09-08 | P/FVC/MDS/1096399/2022 | 2022-09-16
2289 | ODKMN8 | ODKMN8 |  |  |  | ROTN | ATC |  |  |  | On Air |  | ODKMN8 | 4G_FD900_ODKMN8 | 4G_FD2100_ODKMN8 | 4G_TD_ODKMN8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442512 | 2022-09-18 | P/FVC/MDS/1098078/2022 | 2022-09-27 | ST202209446373 | 2022-09-19 | P/FVC/MDS/1098166/2022 | 2022-09-27 |  |  |  |  | ST202209431802 | 2022-09-17 | P/FVC/MDS/1097950/2022 | 2022-09-27
2290 | TIR517 | TIR517 |  |  |  | ROTN | ATC | TN/TI/AT/23371 | T22TN05268 |  | On Air |  | TIR517 | 4G_FD900_TIR517 | 4G_FD2100_TIR517 | 4G_TD_TIR517 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209405197 | 2022-09-09 | P/FVC/MDS/1096587/2022 | 2022-09-16 | ST202209406054 | 2022-09-09 | P/FVC/MDS/1096496/2022 | 2022-09-16 |  |  |  |  | ST202209399945 | 2022-09-08 | P/FVC/MDS/1096402/2022 | 2022-09-16
2291 | TIR518 | TIR518 |  |  |  | ROTN | ATC | TN/TI/AT/23372 | T22TN05269 |  | On Air |  | TIR518 | 4G_FD900_TIR518 | 4G_FD2100_TIR518 | 4G_TD_TIR518 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405136 | 2022-09-09 | P/FVC/MDS/1096580/2022 | 2022-09-16 | ST202209405610 | 2022-09-09 | P/FVC/MDS/1096489/2022 | 2022-09-16 |  |  |  |  | ST202209399896 | 2022-09-08 | P/FVC/MDS/1096395/2022 | 2022-09-16
2292 | CBE959 | CBE959 |  |  |  | ROTN | ATC | - | - |  | On Air |  | CBE959 | 4G_FD900_CBE959 | 4G_FD2100_CBE959 | 4G_TD_CBE959 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442370 | 2022-09-18 | P/FVC/MDS/1098049/2022 | 2022-09-27 | ST202209445854 | 2022-09-19 | P/FVC/MDS/1098137/2022 | 2022-09-27 |  |  |  |  | ST202209431164 | 2022-09-17 | P/FVC/MDS/1097921/2022 | 2022-09-27
2293 | TIR519 | TIR519 |  |  |  | ROTN | ATC | TN/TI/AT/23375 | T22TN05272 |  | On Air |  | TIR519 | 4G_FD900_TIR519 | 4G_FD2100_TIR519 | 4G_TD_TIR519 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405179 | 2022-09-09 | P/FVC/MDS/1096585/2022 | 2022-09-16 | ST202209405632 | 2022-09-09 | P/FVC/MDS/1096494/2022 | 2022-09-16 |  |  |  |  | ST202209399928 | 2022-09-08 | P/FVC/MDS/1096400/2022 | 2022-09-16
2294 | CONR33 | CONR33 |  |  |  | ROTN | Indus | - | R/NN-677560 |  | SO |  | CONR33 | 4G_FD900_CONR33 | 4G_FD2100_CONR33 | 4G_TD_CONR33 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442401 | 2022-09-18 | P/FVC/MDS/1098059/2022 | 2022-09-27 | ST202209446027 | 2022-09-19 | P/FVC/MDS/1098147/2022 | 2022-09-27 |  |  |  |  | ST202209431461 | 2022-09-17 | P/FVC/MDS/1097929/2022 | 2022-09-27
2295 | CONR36 | CONR36 |  |  |  | ROTN | Indus | IN-3146638 | R/NN-677563 |  | SO |  | CONR36 | 4G_FD900_CONR36 | 4G_FD2100_CONR36 | 4G_TD_CONR36 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485576 | 2022-09-27 | P/FVC/MDS/1101199/2022 | 2022-10-10 | ST202209491794 | 2022-09-28 | P/FVC/MDS/1101369/2022 | 2022-10-10 |  |  |  |  | ST202209483248 | 2022-09-26 | P/FBW/MDS/1101097/2022 | 2022-10-10
2296 | MNDPM5 | MNDPM5 |  |  |  | ROTN | Summit | I-TN-MNDM-ENB-9002 | SR-TN001073 |  | On Air |  | MNDPM5 | 4G_FD900_MNDPM5 | 4G_FD2100_MNDPM5 | 4G_TD_MNDPM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442777 | 2022-09-19 | P/FVC/MDS/1098113/2022 | 2022-09-27 | ST202209447424 | 2022-09-19 | P/FVC/MDS/1098201/2022 | 2022-09-27 |  |  |  |  | ST202209432278 | 2022-09-17 | P/FVC/MDS/1097978/2022 | 2022-09-27
2297 | AGSTM9 | AGSTM9 |  |  |  | ROTN | Summit | I-TN-NGCL-ENB-9015 | SR-TN001102 |  | On Air |  | AGSTM9 | 4G_FD900_AGSTM9 | 4G_FD2100_AGSTM9 | 4G_TD_AGSTM9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442773 | 2022-09-19 | P/FVC/MDS/1098112/2022 | 2022-09-27 | ST202209447422 | 2022-09-19 | P/FVC/MDS/1098200/2022 | 2022-09-27 |  |  |  |  | ST202209432277 | 2022-09-17 | P/FVC/MDS/1097977/2022 | 2022-09-27
2298 | MNDPM6 | MNDPM6 |  |  |  | ROTN | Ascend |  |  |  | On Air |  | MNDPM6 | 4G_FD900_MNDPM6 | 4G_FD2100_MNDPM6 | 4G_TD_MNDPM6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442406 | 2022-09-18 | P/FVC/MDS/1098064/2022 | 2022-09-27 | ST202209446092 | 2022-09-19 | P/FVC/MDS/1098152/2022 | 2022-09-27 |  |  |  |  | ST202209431544 | 2022-09-17 | P/FVC/MDS/1097934/2022 | 2022-09-27
2299 | ADANU2 | ADANU2 |  |  |  | ROTN | ATC | TN/TV/AT/23492 | T22TN06007 |  | On Air |  | ADANU2 | 4G_FD900_ADANU2 | 4G_FD2100_ADANU2 | 4G_TD_ADANU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485772 | 2022-09-27 | P/FVC/MDS/1101237/2022 | 2022-10-10 | ST202209492891 | 2022-09-28 | P/FVC/MDS/1101406/2022 | 2022-10-10 |  |  |  |  | ST202209483707 | 2022-09-26 | P/FBW/MDS/1101130/2022 | 2022-10-10
2300 | PAARA2 | PAARA2 |  |  |  | ROTN | ATC | TN/VE/AT/23507 | T22TN06047 |  | SO |  | PAARA2 | 4G_FD900_PAARA2 | 4G_FD2100_PAARA2 | 4G_TD_PAARA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486314 | 2022-09-27 | P/FVC/MDS/1101245/2022 | 2022-10-10 | ST202209493052 | 2022-09-28 | P/FVC/MDS/1101414/2022 | 2022-10-10 |  |  |  |  | ST202209484001 | 2022-09-26 | P/FBW/MDS/1101138/2022 | 2022-10-10
2301 | KELER2 | KELER2 |  |  |  | ROTN | ATC | TN/TR/AT/23495 | T22TN06014 |  | On Air |  | KELER2 | 4G_FD900_KELER2 | 4G_FD2100_KELER2 | 4G_TD_KELER2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485729 | 2022-09-27 | P/FVC/MDS/1101227/2022 | 2022-10-10 | ST202209492803 | 2022-09-28 | P/FVC/MDS/1101397/2022 | 2022-10-10 |  |  |  |  | ST202209483650 | 2022-09-26 | P/FBW/MDS/1101121/2022 | 2022-10-10
2302 | PNRI32 | PNRI32 |  |  |  | ROTN | ATC | TN/TU/AT/23493 | T22TN06008 |  | On Air |  | PNRI32 | 4G_FD900_PNRI32 | 4G_FD2100_PNRI32 | 4G_TD_PNRI32 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485773 | 2022-09-27 | P/FVC/MDS/1101238/2022 | 2022-10-10 | ST202209492929 | 2022-09-28 | P/FVC/MDS/1101407/2022 | 2022-10-10 |  |  |  |  | ST202209483716 | 2022-09-26 | P/FBW/MDS/1101131/2022 | 2022-10-10
2303 | MDRM13 | MDRM13 |  |  |  | ROTN | ATC | TN/KA/AT/23503 | T22TN06022 |  | On Air |  | MDRM13 | 4G_FD900_MDRM13 | 4G_FD2100_MDRM13 | 4G_TD_MDRM13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486301 | 2022-09-27 | P/FVC/MDS/1101244/2022 | 2022-10-10 | ST202209493051 | 2022-09-28 | P/FVC/MDS/1101413/2022 | 2022-10-10 |  |  |  |  | ST202209484000 | 2022-09-26 | P/FBW/MDS/1101137/2022 | 2022-10-10
2304 | AGOOR2 | AGOOR2 |  |  |  | ROTN | ATC | TN/TU/AT/23499 | T22TN06018 |  | On Air |  | AGOOR2 | 4G_FD900_AGOOR2 | 4G_FD2100_AGOOR2 | 4G_TD_AGOOR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485743 | 2022-09-27 | P/FVC/MDS/1101231/2022 | 2022-10-10 | ST202209492850 | 2022-09-28 | P/FVC/MDS/1101401/2022 | 2022-10-10 |  |  |  |  | ST202209483668 | 2022-09-26 | P/FBW/MDS/1101125/2022 | 2022-10-10
2305 | TTNI20 | TTNI20 |  |  |  | ROTN | ATC | TN/TU/AT/23496 | T22TN06015 |  | On Air |  | TTNI20 | 4G_FD900_TTNI20 | 4G_FD2100_TTNI20 | 4G_TD_TTNI20 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485738 | 2022-09-27 | P/FVC/MDS/1101228/2022 | 2022-10-10 | ST202209492804 | 2022-09-28 | P/FVC/MDS/1101398/2022 | 2022-10-10 |  |  |  |  | ST202209483651 | 2022-09-26 | P/FBW/MDS/1101122/2022 | 2022-10-10
2306 | PADVD2 | PADVD2 |  |  |  | ROTN | ATC | TN/TV/AT/23498 | T22TN06017 |  | On Air |  | PADVD2 | 4G_FD900_PADVD2 | 4G_FD2100_PADVD2 | 4G_TD_PADVD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485740 | 2022-09-27 | P/FVC/MDS/1101230/2022 | 2022-10-10 | ST202209492831 | 2022-09-28 | P/FVC/MDS/1101400/2022 | 2022-10-10 |  |  |  |  | ST202209483667 | 2022-09-26 | P/FBW/MDS/1101124/2022 | 2022-10-10
2307 | MALYN2 | MALYN2 |  |  |  | ROTN | ATC | TN/SA/AT/23494 | T22TN06009 |  | On Air |  | MALYN2 | 4G_FD900_MALYN2 | 4G_FD2100_MALYN2 | 4G_TD_MALYN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485719 | 2022-09-27 | P/FVC/MDS/1101224/2022 | 2022-10-10 | ST202209492780 | 2022-09-28 | P/FVC/MDS/1101394/2022 | 2022-10-10 |  |  |  |  | ST202209483619 | 2022-09-26 | P/FBW/MDS/1101118/2022 | 2022-10-10
2308 | PULIM2 | PULIM2 |  |  |  | ROTN | ATC | TN/VI/AT/23504 | T22TN06023 |  | On Air |  | PULIM2 | 4G_FD900_PULIM2 | 4G_FD2100_PULIM2 | 4G_TD_PULIM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485744 | 2022-09-27 | P/FVC/MDS/1101232/2022 | 2022-10-10 | ST202209492851 | 2022-09-28 | P/FVC/MDS/1101402/2022 | 2022-10-10 |  |  |  |  | ST202209483680 | 2022-09-26 | P/FBW/MDS/1101126/2022 | 2022-10-10
2309 | PNDTM2 | PNDTM2 |  |  |  | ROTN | ATC | TN/VI/AT/23497 | T22TN06016 |  | On Air |  | PNDTM2 | 4G_FD900_PNDTM2 | 4G_FD2100_PNDTM2 | 4G_TD_PNDTM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485739 | 2022-09-27 | P/FVC/MDS/1101229/2022 | 2022-10-10 | ST202209492829 | 2022-09-28 | P/FVC/MDS/1101399/2022 | 2022-10-10 |  |  |  |  | ST202209483666 | 2022-09-26 | P/FBW/MDS/1101123/2022 | 2022-10-10
2310 | KONDA2 | KONDA2 |  |  |  | CHN | Ascend | - | - |  | On air |  | KONDA2 | 4G_FD900_KONDA2 | 4G_FD2100_KONDA2 | 4G_TD_KONDA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442438 | 2022-09-18 | P/FVC/MDS/1098074/2022 | 2022-09-27 | ST202209446327 | 2022-09-19 | P/FVC/MDS/1098162/2022 | 2022-09-27 |  |  |  |  | ST202209431775 | 2022-09-17 | P/FVC/MDS/1097946/2022 | 2022-09-27
2311 | AVAD35 | AVAD35 |  |  |  | CHN | Indus | IN-3148308 | R/NN-680646 |  | On air |  | AVAD35 | 4G_FD900_AVAD35 | 4G_FD2100_AVAD35 | 4G_TD_AVAD35 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442781 | 2022-09-19 | P/FVC/MDS/1098117/2022 | 2022-09-27 | ST202209447451 | 2022-09-19 | P/FVC/MDS/1098213/2022 | 2022-09-27 |  |  |  |  | ST202209432354 | 2022-09-17 | P/FVC/MDS/1097982/2022 | 2022-09-27
2312 | PUDUC3 | PUDUC3 |  |  |  | CHN | ATC | TN/CH/AT/23208 | T22TN02920 |  | On air |  | PUDUC3 | 4G_FD900_PUDUC3 | 4G_FD2100_PUDUC3 | 4G_TD_PUDUC3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209486423 | 2022-09-27 | P/FVC/MDS/1101264/2022 | 2022-10-10 | ST202209493230 | 2022-09-28 | P/FVC/MDS/1101433/2022 | 2022-10-10 |  |  |  |  | ST202209484089 | 2022-09-26 | P/FBW/MDS/1101157/2022 | 2022-10-10
2313 | GUDU31 | GUDU31 |  |  |  | CHN | Indus | IN-3142361 | R/NN-671747 |  |  |  | GUDU31 | 4G_FD900_GUDU31 | 4G_FD2100_GUDU31 | 4G_TD_GUDU31 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442402 | 2022-09-18 | P/FVC/MDS/1098060/2022 | 2022-09-27 | ST202209446028 | 2022-09-19 | P/FVC/MDS/1098148/2022 | 2022-09-27 |  |  |  |  | ST202209431462 | 2022-09-17 | P/FVC/MDS/1097930/2022 | 2022-09-27
2314 | KAND36 | KAND36 |  |  |  | CHN | Indus | IN-3142387 | R/NN-671765 |  | SO |  | KAND36 | 4G_FD900_KAND36 | 4G_FD2100_KAND36 | 4G_TD_KAND36 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442403 | 2022-09-18 | P/FVC/MDS/1098061/2022 | 2022-09-27 | ST202209446029 | 2022-09-19 | P/FVC/MDS/1098149/2022 | 2022-09-27 |  |  |  |  | ST202209431507 | 2022-09-17 | P/FVC/MDS/1097931/2022 | 2022-09-27
2315 | PONM11 | PONM11 |  |  |  | CHN | Indus | IN-3142416 | R/NN-671770 |  | SO |  | PONM11 | 4G_FD900_PONM11 | 4G_FD2100_PONM11 | 4G_TD_PONM11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209442400 | 2022-09-18 | P/FVC/MDS/1098058/2022 | 2022-09-27 | ST202209445999 | 2022-09-19 | P/FVC/MDS/1098146/2022 | 2022-09-27 |  |  |  |  | ST202209431459 | 2022-09-17 | P/FVC/MDS/1097928/2022 | 2022-09-27
2316 | MMNA31 | MMNA31 |  |  |  | CHN | Indus | IN-3142377 | R/NN-671764 |  | On air |  | MMNA31 | 4G_FD900_MMNA31 | 4G_FD2100_MMNA31 | 4G_TD_MMNA31 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209486329 | 2022-09-27 | P/FVC/MDS/1101250/2022 | 2022-10-10 | ST202209493092 | 2022-09-28 | P/FVC/MDS/1101419/2022 | 2022-10-10 |  |  |  |  | ST202209484033 | 2022-09-26 | P/FBW/MDS/1101143/2022 | 2022-10-10
2317 | VELTE8 | VELTE8 |  |  |  | CHN | Ascend | - | - |  | On air |  | VELTE8 | 4G_FD900_VELTE8 | 4G_FD2100_VELTE8 | 4G_TD_VELTE8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442439 | 2022-09-18 | P/FVC/MDS/1098075/2022 | 2022-09-27 | ST202209446328 | 2022-09-19 | P/FVC/MDS/1098163/2022 | 2022-09-27 |  |  |  |  | ST202209431776 | 2022-09-17 | P/FVC/MDS/1097947/2022 | 2022-09-27
2318 | SOWC11 | SOWC11 |  |  |  | CHN | Airtel | - | - |  | SO |  | SOWC11 | 4G_FD900_SOWC11 | 4G_FD2100_SOWC11 | 4G_TD_SOWC11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209442404 | 2022-09-18 | P/FVC/MDS/1098062/2022 | 2022-09-27 | ST202209446090 | 2022-09-19 | P/FVC/MDS/1098150/2022 | 2022-09-27 | ST202212858134 | 2022-12-27 | 0 |  | ST202209431508 | 2022-09-17 | P/FVC/MDS/1097932/2022 | 2022-09-27
2319 | GNGE08 | GNGE08 |  |  |  | ROTN | Indus | IN-3136104 | R/NN-662517 |  |  |  | GNGE08 | 4G_FD900_GNGE08 | 4G_FD2100_GNGE08 | 4G_TD_GNGE08 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202209486468 | 2022-09-27 | P/FVC/MDS/1101275/2022 | 2022-10-10 | ST202209493304 | 2022-09-28 | P/FVC/MDS/1101444/2022 | 2022-10-10 | ST202209487304 | 2022-09-27 | P/FVC/MDS/1101319/2022 | 2022-10-10 | ST202209484165 | 2022-09-26 | P/FBW/MDS/1101168/2022 | 2022-10-10
2320 | PDY380 | PDY380 |  |  |  | ROTN | Indus | IN-3134705 | R/NN-659361 |  |  |  | PDY380 | 4G_FD900_PDY380 | 4G_FD2100_PDY380 | 4G_TD_PDY380 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202209405135 | 2022-09-09 | P/FVC/MDS/1096579/2022 | 2022-09-16 | ST202209405609 | 2022-09-09 | P/FVC/MDS/1096488/2022 | 2022-09-16 | ST202209401250 | 2022-09-08 | P/FVC/MDS/1096424/2022 | 2022-09-16 | ST202209399895 | 2022-09-08 | P/FVC/MDS/1096394/2022 | 2022-09-16
2321 | CBE878 | CBE878 |  |  |  | ROTN | TVI | BSTNCBE1678 | - |  |  |  | CBE878 | 4G_FD900_CBE878 | 4G_FD2100_CBE878 | 4G_TD_CBE878 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487181 | 2022-09-27 | P/FVC/MDS/1101546/2022 | 2022-10-10 | ST202209496932 | 2022-09-29 | P/FVC/MDS/1101489/2022 | 2022-10-10 | ST202209487714 | 2022-09-28 | P/FVC/MDS/1101348/2022 | 2022-10-10 | ST202209473505 | 2022-09-24 | P/FBW/MDS/1101031/2022 | 2022-10-10
2322 | CDLR96 | CDLR96 |  |  |  | ROTN | ATC | TN/PO/TN/14958 | - |  |  |  | CDLR96 | 4G_FD900_CDLR96 | 4G_FD2100_CDLR96 | 4G_TD_CDLR96 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485132 | 2022-09-27 | P/FVC/MDS/1101190/2022 | 2022-10-10 | ST202209491625 | 2022-09-28 | P/FVC/MDS/1101360/2022 | 2022-10-10 | ST202209487231 | 2022-09-27 | P/FVC/MDS/1101284/2022 | 2022-10-10 | ST202209483172 | 2022-09-26 | P/FBW/MDS/1101090/2022 | 2022-10-10
2323 | GMPD32 | GMPD32 |  |  |  | ROTN | TVI | -- | -- |  |  |  | GMPD32 | 4G_FD900_GMPD32 | 4G_FD2100_GMPD32 | 4G_TD_GMPD32 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405118 | 2022-09-09 | P/FVC/MDS/1096576/2022 | 2022-09-16 | ST202209405593 | 2022-09-09 | P/FVC/MDS/1096485/2022 | 2022-09-16 | ST202208364747 | 2022-08-29 | P/FVC/MDS/1094777/2022 | 2022-09-07 | ST202209399862 | 2022-09-08 | P/FVC/MDS/1096391/2022 | 2022-09-16
2324 | TCGD53 | TCGD53 |  |  |  | ROTN | Indus | IN-3148893 | R/NN-681189 |  |  |  | TCGD53 | 4G_FD900_TCGD53 | 4G_FD2100_TCGD53 | 4G_TD_TCGD53 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485685 | 2022-09-27 | P/FVC/MDS/1101215/2022 | 2022-10-10 | ST202209491984 | 2022-09-28 | P/FVC/MDS/1101385/2022 | 2022-10-10 | ST202209487256 | 2022-09-27 | P/FVC/MDS/1101297/2022 | 2022-10-10 | ST202209483534 | 2022-09-26 | P/FBW/MDS/1101111/2022 | 2022-10-10
2325 | SITAR4 | SITAR4 |  |  |  | ROTN | Indus | IN-3150150 | R/NN-682935 |  |  |  | SITAR4 | 4G_FD900_SITAR4 | 4G_FD2100_SITAR4 | 4G_TD_SITAR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486792 | 2022-09-27 | P/FVC/MDS/1101515/2022 | 2022-10-10 | ST202209495126 | 2022-09-29 | P/FVC/MDS/1101458/2022 | 2022-10-10 | ST202209487344 | 2022-09-27 | P/FVC/MDS/1101328/2022 | 2022-10-10 | ST202209484233 | 2022-09-26 | P/FBW/MDS/1101181/2022 | 2022-10-10
2326 | KRR111 | KRR111 |  |  |  | ROTN | Indus | IN-3138614 | R/NN-664362 |  |  |  | KRR111 | 4G_FD900_KRR111 | 4G_FD2100_KRR111 | 4G_TD_KRR111 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442345 | 2022-09-18 | P/FVC/MDS/1098046/2022 | 2022-09-27 | ST202209445812 | 2022-09-19 | P/FVC/MDS/1098134/2022 | 2022-09-27 | ST202209432139 | 2022-09-17 | P/FVC/MDS/1098000/2022 | 2022-09-27 | ST202209431135 | 2022-09-17 | P/FVC/MDS/1097918/2022 | 2022-09-27
2327 | TRUST8 | TRUST8 |  |  |  | CHN | ATC | TN/CH/VD/12654 | - |  |  |  | TRUST8 | 4G_FD900_TRUST8 | 4G_FD2100_TRUST8 | 4G_TD_TRUST8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486849 | 2022-09-27 | P/FVC/MDS/1101520/2022 | 2022-10-10 | ST202209495200 | 2022-09-29 | P/FVC/MDS/1101463/2022 | 2022-10-10 |  |  |  |  | ST202209484346 | 2022-09-26 | P/FBW/MDS/1101054/2022 | 2022-10-10
2328 | MOGW31 | MOGW31 |  |  |  | CHN | ATC | TN/CH/VO/10915 | - |  |  |  | MOGW31 | 4G_FD900_MOGW31 | 4G_FD2100_MOGW31 | 4G_TD_MOGW31 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486826 | 2022-09-27 | P/FVC/MDS/1101518/2022 | 2022-10-10 | ST202209495167 | 2022-09-29 | P/FVC/MDS/1101461/2022 | 2022-10-10 | ST202209487349 | 2022-09-27 | P/FVC/MDS/1101330/2022 | 2022-10-10 | ST202209474108 | 2022-09-24 | P/FBW/MDS/1101052/2022 | 2022-10-10
2329 | CBE948 | CBE948 |  |  |  | ROTN | TVI | VDTNCBE1774 | - |  |  |  | CBE948 | 4G_FD900_CBE948 | 4G_FD2100_CBE948 | 4G_TD_CBE948 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405126 | 2022-09-09 | P/FVC/MDS/1096577/2022 | 2022-09-16 | ST202209405602 | 2022-09-09 | P/FVC/MDS/1096486/2022 | 2022-09-16 | ST202209401223 | 2022-09-08 | P/FVC/MDS/1096422/2022 | 2022-09-16 | ST202209399883 | 2022-09-08 | P/FVC/MDS/1096392/2022 | 2022-09-16
2330 | DPI061 | DPI061 |  |  |  | ROTN | Summit | I-TN-DMPI-ENB-0010 | SR-TN001022 |  |  |  | DPI061 | 4G_FD900_DPI061 | 4G_FD2100_DPI061 | 4G_TD_DPI061 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405127 | 2022-09-09 | P/FVC/MDS/1096578/2022 | 2022-09-16 | ST202209405603 | 2022-09-09 | P/FVC/MDS/1096487/2022 | 2022-09-16 | ST202209401224 | 2022-09-08 | P/FVC/MDS/1096423/2022 | 2022-09-16 | ST202209399884 | 2022-09-08 | P/FVC/MDS/1096393/2022 | 2022-09-16
2331 | TRY410 | TRY410 |  |  |  | ROTN | Indus | IN-3149244 | R/NN-681837 |  |  |  | TRY410 | 4G_FD900_TRY410 | 4G_FD2100_TRY410 | 4G_TD_TRY410 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405198 | 2022-09-09 | P/FVC/MDS/1096588/2022 | 2022-09-16 | ST202209406055 | 2022-09-09 | P/FVC/MDS/1096497/2022 | 2022-09-16 | ST202209401251 | 2022-09-08 | P/FVC/MDS/1096425/2022 | 2022-09-16 | ST202209399946 | 2022-09-08 | P/FVC/MDS/1096403/2022 | 2022-09-16
2332 | NMRO3 | NMRO3 |  |  |  | CHN | ATC | TN/CH/TT/12843 | - |  |  |  | NMRO3 | 4G_FD900_NMRO3 | 4G_FD2100_NMRO3 | 4G_TD_NMRO3 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202209486850 | 2022-09-27 | P/FVC/MDS/1101521/2022 | 2022-10-10 | ST202209495568 | 2022-09-29 | P/FVC/MDS/1101464/2022 | 2022-10-10 | ST202209487358 | 2022-09-27 | P/FVC/MDS/1101332/2022 | 2022-10-10 | ST202209484347 | 2022-09-26 | P/FBW/MDS/1101055/2022 | 2022-10-10
2333 | TIR511 | TIR511 |  |  |  | ROTN | ATC | TN/CO/TT/14843 | - |  |  |  | TIR511 | 4G_FD900_TIR511 | 4G_FD2100_TIR511 | 4G_TD_TIR511 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486851 | 2022-09-27 | P/FVC/MDS/1101522/2022 | 2022-10-10 | ST202209495569 | 2022-09-29 | P/FVC/MDS/1101465/2022 | 2022-10-10 | ST202209487359 | 2022-09-27 | P/FVC/MDS/1101333/2022 | 2022-10-10 | ST202209484352 | 2022-09-26 | P/FBW/MDS/1101056/2022 | 2022-10-10
2334 | TRY418 | TRY418 |  |  |  | ROTN | Indus | IN-3141953 | R/NN-670875 |  |  |  | TRY418 | 4G_FD900_TRY418 | 4G_FD2100_TRY418 | 4G_TD_TRY418 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486328 | 2022-09-27 | P/FVC/MDS/1101249/2022 | 2022-10-10 | ST202209493091 | 2022-09-28 | P/FVC/MDS/1101418/2022 | 2022-10-10 | ST202209487279 | 2022-09-27 | P/FVC/MDS/1101308/2022 | 2022-10-10 | ST202209484032 | 2022-09-26 | P/FBW/MDS/1101142/2022 | 2022-10-10
2335 | VALU12 | VALU12 |  |  |  | CHN | ATC | TN/CH/TT/13318 | - |  |  |  | VALU12 | 4G_FD900_VALU12 | 4G_FD2100_VALU12 | 4G_TD_VALU12 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486827 | 2022-09-27 | P/FVC/MDS/1101519/2022 | 2022-10-10 | ST202209495199 | 2022-09-29 | P/FVC/MDS/1101462/2022 | 2022-10-10 | ST202209487350 | 2022-09-27 | P/FVC/MDS/1101331/2022 | 2022-10-10 | ST202209484345 | 2022-09-26 | P/FBW/MDS/1101053/2022 | 2022-10-10
2336 | CBE955 | CBE955 |  |  |  | ROTN | Indus | IN-3141960 | R/NN-670891 |  |  |  | CBE955 | 4G_FD900_CBE955 | 4G_FD2100_CBE955 | 4G_TD_CBE955 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487158 | 2022-09-27 | P/FVC/MDS/1101541/2022 | 2022-10-10 | ST202209496874 | 2022-09-29 | P/FVC/MDS/1101484/2022 | 2022-10-10 | ST202209487691 | 2022-09-28 | P/FVC/MDS/1101345/2022 | 2022-10-10 | ST202209484412 | 2022-09-26 | P/FBW/MDS/1101075/2022 | 2022-10-10
2337 | SNDRP2 | SNDRP2 |  |  |  | ROTN | Indus | IN-3147357 | R/NN-678026 |  |  |  | SNDRP2 | 4G_FD900_SNDRP2 | 4G_FD2100_SNDRP2 | 4G_TD_SNDRP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405221 | 2022-09-09 | P/FVC/MDS/1096592/2022 | 2022-09-16 | ST202209406113 | 2022-09-09 | P/FVC/MDS/1096501/2022 | 2022-09-16 |  |  |  |  | ST202209400138 | 2022-09-08 | P/FVC/MDS/1096407/2022 | 2022-09-16
2338 | SULR29 | SULR29 |  |  |  | ROTN | Indus | IN-3147358 | R/NN-678027 |  |  |  | SULR29 | 4G_FD900_SULR29 | 4G_FD2100_SULR29 | 4G_TD_SULR29 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202209485133 | 2022-09-27 | P/FVC/MDS/1101191/2022 | 2022-10-10 | ST202209491626 | 2022-09-28 | P/FVC/MDS/1101361/2022 | 2022-10-10 | ST202209487232 | 2022-09-27 | P/FVC/MDS/1101285/2022 | 2022-10-10 | ST202209483173 | 2022-09-26 | P/FBW/MDS/1101091/2022 | 2022-10-10
2339 | TRY425 | TRY425 |  |  |  | ROTN | Indus | IN-3147367 | R/NN-678070 |  |  |  | TRY425 | 4G_FD900_TRY425 | 4G_FD2100_TRY425 | 4G_TD_TRY425 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486794 | 2022-09-27 | P/FVC/MDS/1101516/2022 | 2022-10-10 | ST202209495127 | 2022-09-29 | P/FVC/MDS/1101459/2022 | 2022-10-10 | ST202209487348 | 2022-09-27 | P/FVC/MDS/1101329/2022 | 2022-10-10 | ST202209484256 | 2022-09-26 | P/FBW/MDS/1101182/2022 | 2022-10-10
2340 | NEWC18 | NEWC18 |  |  |  | CHN | TVI | - | - |  |  |  | NEWC18 | 4G_FD900_NEWC18 | 4G_FD2100_NEWC18 | 4G_TD_NEWC18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487157 | 2022-09-27 | P/FVC/MDS/1101540/2022 | 2022-10-10 | ST202209496873 | 2022-09-29 | P/FVC/MDS/1101483/2022 | 2022-10-10 | ST202209487690 | 2022-09-28 | P/FVC/MDS/1101344/2022 | 2022-10-10 | ST202209484411 | 2022-09-26 | P/FBW/MDS/1101074/2022 | 2022-10-10
2341 | AYAN35 | AYAN35 |  |  |  | CHN | TVI | - | - |  |  |  | AYAN35 | 4G_FD900_AYAN35 | 4G_FD2100_AYAN35 | 4G_TD_AYAN35 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485717 | 2022-09-27 | P/FVC/MDS/1101222/2022 | 2022-10-10 | ST202209492066 | 2022-09-28 | P/FVC/MDS/1101392/2022 | 2022-10-10 | ST202209487262 | 2022-09-27 | P/FVC/MDS/1101301/2022 | 2022-10-10 | ST202209483587 | 2022-09-26 | P/FBW/MDS/1101116/2022 | 2022-10-10
2342 | CHINO2 | CHINO2 |  |  |  | ROTN | Indus | IN-3150148 | R/NN-682470 |  |  |  | CHINO2 | 4G_FD900_CHINO2 | 4G_FD2100_CHINO2 | 4G_TD_CHINO2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486504 | 2022-09-27 | P/FVC/MDS/1101279/2022 | 2022-10-10 | ST202209493360 | 2022-09-28 | P/FVC/MDS/1101448/2022 | 2022-10-10 | ST202209487326 | 2022-09-27 | P/FVC/MDS/1101323/2022 | 2022-10-10 | ST202209484178 | 2022-09-26 | P/FBW/MDS/1101172/2022 | 2022-10-10
2343 | MANIY2 | MANIY2 |  |  |  | ROTN | ATC | TN/TR/AT/23390 | T22TN05705 |  |  |  | MANIY2 | 4G_FD900_MANIY2 | 4G_FD2100_MANIY2 | 4G_TD_MANIY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485745 | 2022-09-27 | P/FVC/MDS/1101233/2022 | 2022-10-10 | ST202209492869 | 2022-09-28 | P/FVC/MDS/1101403/2022 | 2022-10-10 |  |  |  |  | ST202209474106 | 2022-09-24 | P/FBW/MDS/1101051/2022 | 2022-10-10
2344 | VLYNK2 | VLYNK2 |  |  |  | ROTN | ATC | TN/TR/AT/23391 | T22TN05706 |  |  |  | VLYNK2 | 4G_FD900_VLYNK2 | 4G_FD2100_VLYNK2 | 4G_TD_VLYNK2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442570 | 2022-09-18 | P/FVC/MDS/1098094/2022 | 2022-09-27 | ST202209446656 | 2022-09-19 | P/FVC/MDS/1098182/2022 | 2022-09-27 | ST202209432636 | 2022-09-17 | P/FVC/MDS/1098017/2022 | 2022-09-27 | ST202209432046 | 2022-09-17 | P/FVC/MDS/1097962/2022 | 2022-09-27
2345 | KLPYM2 | KLPYM2 |  |  |  | ROTN | Indus | IN-3149570 | R/NN-682348 |  |  |  | KLPYM2 | 4G_FD900_KLPYM2 | 4G_FD2100_KLPYM2 | 4G_TD_KLPYM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486503 | 2022-09-27 | P/FVC/MDS/1101278/2022 | 2022-10-10 | ST202209493329 | 2022-09-28 | P/FVC/MDS/1101447/2022 | 2022-10-10 | ST202209487320 | 2022-09-27 | P/FVC/MDS/1101322/2022 | 2022-10-10 | ST202209484177 | 2022-09-26 | P/FBW/MDS/1101171/2022 | 2022-10-10
2346 | PRVAG2 | PRVAG2 |  |  |  | ROTN | ATC | TN/VLP/AT/23393 | T22TN05708 |  |  |  | PRVAG2 | 4G_FD900_PRVAG2 | 4G_FD2100_PRVAG2 | 4G_TD_PRVAG2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486454 | 2022-09-27 | P/FVC/MDS/1101270/2022 | 2022-10-10 | ST202209493281 | 2022-09-28 | P/FVC/MDS/1101439/2022 | 2022-10-10 | ST202209487293 | 2022-09-27 | P/FVC/MDS/1101316/2022 | 2022-10-10 | ST202209484143 | 2022-09-26 | P/FBW/MDS/1101163/2022 | 2022-10-10
2347 | SUNKR3 | SUNKR3 |  |  |  | ROTN | ATC | TN/DH/AT/23394 | T22TN05709 |  |  |  | SUNKR3 | 4G_FD900_SUNKR3 | 4G_FD2100_SUNKR3 | 4G_TD_SUNKR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442515 | 2022-09-18 | P/FVC/MDS/1098081/2022 | 2022-09-27 | ST202209446411 | 2022-09-19 | P/FVC/MDS/1098169/2022 | 2022-09-27 |  |  |  |  | ST202209431832 | 2022-09-17 | P/FVC/MDS/1097953/2022 | 2022-09-27
2348 | RTRPM2 | RTRPM2 |  |  |  | ROTN | Indus | IN-3149778 | R/NN-670781 |  |  |  | RTRPM2 | 4G_FD900_RTRPM2 | 4G_FD2100_RTRPM2 | 4G_TD_RTRPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486327 | 2022-09-27 | P/FVC/MDS/1101248/2022 | 2022-10-10 | ST202209493079 | 2022-09-28 | P/FVC/MDS/1101417/2022 | 2022-10-10 | ST202209487276 | 2022-09-27 | P/FVC/MDS/1101307/2022 | 2022-10-10 | ST202209484017 | 2022-09-26 | P/FBW/MDS/1101141/2022 | 2022-10-10
2349 | KRKNU2 | KRKNU2 |  |  |  | ROTN | ATC | TN/SA/AT/23397 | T22TN05712 |  |  |  | KRKNU2 | 4G_FD900_KRKNU2 | 4G_FD2100_KRKNU2 | 4G_TD_KRKNU2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442755 | 2022-09-19 | P/FVC/MDS/1098100/2022 | 2022-09-27 | ST202209447388 | 2022-09-19 | P/FVC/MDS/1098188/2022 | 2022-09-27 | ST202209432744 | 2022-09-17 | P/FVC/MDS/1098022/2022 | 2022-09-27
2350 | SRING2 | SRING2 |  |  |  | ROTN | ATC | TN/TR/AT/23398 | T22TN05713 |  |  |  | SRING2 | 4G_FD900_SRING2 | 4G_FD2100_SRING2 | 4G_TD_SRING2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442756 | 2022-09-19 | P/FVC/MDS/1098101/2022 | 2022-09-27 | ST202209447403 | 2022-09-19 | P/FVC/MDS/1098189/2022 | 2022-09-27 |  |  |  |  | ST202209432102 | 2022-09-17 | P/FVC/MDS/1097966/2022 | 2022-09-27
2351 | LNGKI2 | LNGKI2 |  |  |  | ROTN | Indus | IN-3149462 | R/NN-682223 |  |  |  | LNGKI2 | 4G_FD900_LNGKI2 | 4G_FD2100_LNGKI2 | 4G_TD_LNGKI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486343 | 2022-09-27 | P/FVC/MDS/1101251/2022 | 2022-10-10 | ST202209493093 | 2022-09-28 | P/FVC/MDS/1101420/2022 | 2022-10-10 | ST202209487280 | 2022-09-27 | P/FVC/MDS/1101309/2022 | 2022-10-10 | ST202209484047 | 2022-09-26 | P/FBW/MDS/1101144/2022 | 2022-10-10
2352 | THIYM2 | THIYM2 |  |  |  | ROTN | ATC | TN/TR/AT/23399 | T22TN05714 |  |  |  | THIYM2 | 4G_FD900_THIYM2 | 4G_FD2100_THIYM2 | 4G_TD_THIYM2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209485702 | 2022-09-27 | P/FVC/MDS/1101217/2022 | 2022-10-10 | ST202209491986 | 2022-09-28 | P/FVC/MDS/1101387/2022 | 2022-10-10 | ST202209487260 | 2022-09-27 | P/FVC/MDS/1101299/2022 | 2022-10-10
2353 | KADOR2 | KADOR2 |  |  |  | ROTN | Ascend | - | - |  |  |  | KADOR2 | 4G_FD900_KADOR2 | 4G_FD2100_KADOR2 | 4G_TD_KADOR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442411 | 2022-09-18 | P/FVC/MDS/1098069/2022 | 2022-09-27 | ST202209446172 | 2022-09-19 | P/FVC/MDS/1098157/2022 | 2022-09-27 |  |  |  |  | ST202209431580 | 2022-09-17 | P/FVC/MDS/1097939/2022 | 2022-09-27
2354 | SENGP2 | SENGP2 |  |  |  | ROTN | Indus | IN-3149464 | R/NN-682225 |  |  |  | SENGP2 | 4G_FD900_SENGP2 | 4G_FD2100_SENGP2 | 4G_TD_SENGP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486344 | 2022-09-27 | P/FVC/MDS/1101252/2022 | 2022-10-10 | ST202209493119 | 2022-09-28 | P/FVC/MDS/1101421/2022 | 2022-10-10 | ST202209487281 | 2022-09-27 | P/FVC/MDS/1101310/2022 | 2022-10-10 | ST202209484048 | 2022-09-26 | P/FBW/MDS/1101145/2022 | 2022-10-10
2355 | MRDUR2 | MRDUR2 |  |  |  | ROTN | ATC | TN/TR/AT/23400 | T22TN05715 |  |  |  | MRDUR2 | 4G_FD900_MRDUR2 | 4G_FD2100_MRDUR2 | 4G_TD_MRDUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485708 | 2022-09-27 | P/FVC/MDS/1101219/2022 | 2022-10-10 | ST202209492043 | 2022-09-28 | P/FVC/MDS/1101389/2022 | 2022-10-10 | ST202209487799 | 2022-09-28 | P/FVC/MDS/1101352/2022 | 2022-10-10 | ST202209483557 | 2022-09-26 | P/FBW/MDS/1101113/2022 | 2022-10-10
2356 | SKPLA2 | SKPLA2 |  |  |  | ROTN | Indus | IN-3150142 | R/NN-682228 |  |  |  | SKPLA2 | 4G_FD900_SKPLA2 | 4G_FD2100_SKPLA2 | 4G_TD_SKPLA2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485634 | 2022-09-27 | P/FVC/MDS/1101207/2022 | 2022-10-10 | ST202209491884 | 2022-09-28 | P/FVC/MDS/1101377/2022 | 2022-10-10 | ST202209487252 | 2022-09-27 | P/FVC/MDS/1101294/2022 | 2022-10-10 | ST202209483481 | 2022-09-26 | P/FBW/MDS/1101103/2022 | 2022-10-10
2357 | MERPU2 | MERPU2 |  |  |  | ROTN | Indus | IN-3149816 | R/NN-682565 |  |  |  | MERPU2 | 4G_FD900_MERPU2 | 4G_FD2100_MERPU2 | 4G_TD_MERPU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487131 | 2022-09-27 | P/FVC/MDS/1101531/2022 | 2022-10-10 | ST202209495672 | 2022-09-29 | P/FVC/MDS/1101474/2022 | 2022-10-10 |  |  |  |  | ST202209484388 | 2022-09-26 | P/FBW/MDS/1101065/2022 | 2022-10-10
2358 | PLPTI2 | PLPTI2 |  |  |  | ROTN | ATC | TN/SA/AT/23401 | T22TN05716 |  |  |  | PLPTI2 | 4G_FD900_PLPTI2 | 4G_FD2100_PLPTI2 | 4G_TD_PLPTI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442757 | 2022-09-19 | P/FVC/MDS/1098102/2022 | 2022-09-27 | ST202209447404 | 2022-09-19 | P/FVC/MDS/1098190/2022 | 2022-09-27 | ST202209432829 | 2022-09-17 | P/FVC/MDS/1098023/2022 | 2022-09-27 | ST202209432103 | 2022-09-17 | P/FVC/MDS/1097967/2022 | 2022-09-27
2359 | ANTRC2 | ANTRC2 |  |  |  | ROTN | Indus | IN-3149607 | R/NN-682354 |  |  |  | ANTRC2 | 4G_FD900_ANTRC2 | 4G_FD2100_ANTRC2 | 4G_TD_ANTRC2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486357 | 2022-09-27 | P/FVC/MDS/1101255/2022 | 2022-10-10 | ST202209493143 | 2022-09-28 | P/FVC/MDS/1101424/2022 | 2022-10-10 | ST202209487287 | 2022-09-27 | P/FVC/MDS/1101313/2022 | 2022-10-10 | ST202209484053 | 2022-09-26 | P/FBW/MDS/1101148/2022 | 2022-10-10
2360 | VMGMD2 | VMGMD2 |  |  |  | ROTN | Indus | IN-3149741 | R/NN-682468 |  |  |  | VMGMD2 | 4G_FD900_VMGMD2 | 4G_FD2100_VMGMD2 | 4G_TD_VMGMD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485142 | 2022-09-27 | P/FVC/MDS/1101194/2022 | 2022-10-10 | ST202209491759 | 2022-09-28 | P/FVC/MDS/1101364/2022 | 2022-10-10 |  |  |  |  | ST202209483219 | 2022-09-26 | P/FBW/MDS/1101094/2022 | 2022-10-10
2361 | THUPN2 | THUPN2 |  |  |  | ROTN | ATC | TN/DH/AT/23402 | T22TN05717 |  |  |  | THUPN2 | 4G_FD900_THUPN2 | 4G_FD2100_THUPN2 | 4G_TD_THUPN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442388 | 2022-09-18 | P/FVC/MDS/1098052/2022 | 2022-09-27 | ST202209445888 | 2022-09-19 | P/FVC/MDS/1098140/2022 | 2022-09-27 |  |  |  |  | ST202209431375 | 2022-09-17 | P/FVC/MDS/1097922/2022 | 2022-09-27
2362 | STHIN2 | STHIN2 |  |  |  | ROTN | ATC | TN/TH/AT/23404 | T22TN05719 |  |  |  | STHIN2 | 4G_FD900_STHIN2 | 4G_FD2100_STHIN2 | 4G_TD_STHIN2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442760 | 2022-09-19 | P/FVC/MDS/1098103/2022 | 2022-09-27 | ST202209447405 | 2022-09-19 | P/FVC/MDS/1098191/2022 | 2022-09-27 | ST202209432830 | 2022-09-17 | P/FVC/MDS/1098024/2022 | 2022-09-27 | ST202209432146 | 2022-09-17 | P/FVC/MDS/1097968/2022 | 2022-09-27
2363 | NJPYM2 | NJPYM2 |  |  |  | ROTN | Indus | IN-3149761 | R/NN-682502 |  |  |  | NJPYM2 | 4G_FD900_NJPYM2 | 4G_FD2100_NJPYM2 | 4G_TD_NJPYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486372 | 2022-09-27 | P/FVC/MDS/1101256/2022 | 2022-10-10 | ST202209493144 | 2022-09-28 | P/FVC/MDS/1101425/2022 | 2022-10-10 |  |  |  |  | ST202209484060 | 2022-09-26 | P/FBW/MDS/1101149/2022 | 2022-10-10
2364 | VAYLR2 | VAYLR2 |  |  |  | ROTN | ATC | TN/TR/AT/23405 | T22TN05720 |  |  |  | VAYLR2 | 4G_FD900_VAYLR2 | 4G_FD2100_VAYLR2 | 4G_TD_VAYLR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486299 | 2022-09-27 | P/FVC/MDS/1101242/2022 | 2022-10-10 | ST202209493026 | 2022-09-28 | P/FVC/MDS/1101411/2022 | 2022-10-10 | ST202209487274 | 2022-09-27 | P/FVC/MDS/1101305/2022 | 2022-10-10 | ST202209483984 | 2022-09-26 | P/FBW/MDS/1101135/2022 | 2022-10-10
2365 | SMUUR2 | SMUUR2 |  |  |  | ROTN | Indus | IN-3149750 | R/NN-682476 |  |  |  | SMUUR2 | 4G_FD900_SMUUR2 | 4G_FD2100_SMUUR2 | 4G_TD_SMUUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486825 | 2022-09-27 | P/FVC/MDS/1101517/2022 | 2022-10-10 | ST202209495166 | 2022-09-29 | P/FVC/MDS/1101460/2022 | 2022-10-10 |  |  |  |  | ST202209484257 | 2022-09-26 | P/FBW/MDS/1101183/2022 | 2022-10-10
2366 | RAVNP2 | RAVNP2 |  |  |  | ROTN | Indus | IN-3149469 | R/NN-682230 |  |  |  | RAVNP2 | 4G_FD900_RAVNP2 | 4G_FD2100_RAVNP2 | 4G_TD_RAVNP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486493 | 2022-09-27 | P/FVC/MDS/1101276/2022 | 2022-10-10 | ST202209493327 | 2022-09-28 | P/FVC/MDS/1101445/2022 | 2022-10-10 | ST202209487318 | 2022-09-27 | P/FVC/MDS/1101320/2022 | 2022-10-10 | ST202209484166 | 2022-09-26 | P/FBW/MDS/1101169/2022 | 2022-10-10
2367 | KNDPT2 | KNDPT2 |  |  |  | ROTN | Indus | IN-3149471 | R/NN-682234 |  |  |  | KNDPT2 | 4G_FD900_KNDPT2 | 4G_FD2100_KNDPT2 | 4G_TD_KNDPT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485684 | 2022-09-27 | P/FVC/MDS/1101214/2022 | 2022-10-10 | ST202209491957 | 2022-09-28 | P/FVC/MDS/1101384/2022 | 2022-10-10 | ST202209487255 | 2022-09-27 | P/FVC/MDS/1101296/2022 | 2022-10-10 | ST202209483533 | 2022-09-26 | P/FBW/MDS/1101110/2022 | 2022-10-10
2368 | ANKDN2 | ANKDN2 |  |  |  | ROTN | Indus | IN-3149762 | R/NN-682505 |  |  |  | ANKDN2 | 4G_FD900_ANKDN2 | 4G_FD2100_ANKDN2 | 4G_TD_ANKDN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485636 | 2022-09-27 | P/FVC/MDS/1101208/2022 | 2022-10-10 | ST202209491885 | 2022-09-28 | P/FVC/MDS/1101378/2022 | 2022-10-10 |  |  |  |  | ST202209483482 | 2022-09-26 | P/FBW/MDS/1101104/2022 | 2022-10-10
2369 | SNKT12 | SNKT12 |  |  |  | ROTN | ATC | TN/TR/AT/23407 | T22TN05722 |  |  |  | SNKT12 | 4G_FD900_SNKT12 | 4G_FD2100_SNKT12 | 4G_TD_SNKT12 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442348 | 2022-09-18 | P/FVC/MDS/1098047/2022 | 2022-09-27 | ST202209445813 | 2022-09-19 | P/FVC/MDS/1098135/2022 | 2022-09-27 | ST202209432213 | 2022-09-17 | P/FVC/MDS/1098001/2022 | 2022-09-27 | ST202209431162 | 2022-09-17 | P/FVC/MDS/1097919/2022 | 2022-09-27
2370 | ALTUR2 | ALTUR2 |  |  |  | ROTN | Indus | IN-3149476 | R/NN-682256 |  |  |  | ALTUR2 | 4G_FD900_ALTUR2 | 4G_FD2100_ALTUR2 | 4G_TD_ALTUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486502 | 2022-09-27 | P/FVC/MDS/1101277/2022 | 2022-10-10 | ST202209493328 | 2022-09-28 | P/FVC/MDS/1101446/2022 | 2022-10-10 | ST202209487319 | 2022-09-27 | P/FVC/MDS/1101321/2022 | 2022-10-10 | ST202209484167 | 2022-09-26 | P/FBW/MDS/1101170/2022 | 2022-10-10
2371 | PLLYM2 | PLLYM2 |  |  |  | ROTN | ATC | TN/ER/AT/23408 | T22TN05723 |  |  |  | PLLYM2 | 4G_FD900_PLLYM2 | 4G_FD2100_PLLYM2 | 4G_TD_PLLYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442524 | 2022-09-18 | P/FVC/MDS/1098089/2022 | 2022-09-27 | ST202209446561 | 2022-09-19 | P/FVC/MDS/1098177/2022 | 2022-09-27 | ST202212858218 | 2022-12-27 | 0 |  | ST202209431917 | 2022-09-17 | P/FVC/MDS/1097958/2022 | 2022-09-27
2372 | ANGNR2 | ANGNR2 |  |  |  | ROTN | ATC | TN/NM/AT/23409 | T22TN05724 |  |  |  | ANGNR2 | 4G_FD900_ANGNR2 | 4G_FD2100_ANGNR2 | 4G_TD_ANGNR2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442571 | 2022-09-18 | P/FVC/MDS/1098095/2022 | 2022-09-27 | ST202209446710 | 2022-09-19 | P/FVC/MDS/1098183/2022 | 2022-09-27 | ST202209432637 | 2022-09-17 | P/FVC/MDS/1098018/2022 | 2022-09-27
2373 | MOINR2 | MOINR2 |  |  |  | ROTN | ATC | TN/SA/AT/23410 | T22TN05725 |  |  |  | MOINR2 | 4G_FD900_MOINR2 | 4G_FD2100_MOINR2 | 4G_TD_MOINR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442577 | 2022-09-18 | P/FVC/MDS/1098097/2022 | 2022-09-27 | ST202209446713 | 2022-09-19 | P/FVC/MDS/1098185/2022 | 2022-09-27 | ST202209432687 | 2022-09-17 | P/FVC/MDS/1098019/2022 | 2022-09-27 | ST202209432050 | 2022-09-17 | P/FVC/MDS/1097964/2022 | 2022-09-27
2374 | ATRPL2 | ATRPL2 |  |  |  | ROTN | ATC | TN/TR/AT/23411 | T22TN05726 |  |  |  | ATRPL2 | 4G_FD900_ATRPL2 | 4G_FD2100_ATRPL2 | 4G_TD_ATRPL2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442371 | 2022-09-18 | P/FVC/MDS/1098050/2022 | 2022-09-27 | ST202209445855 | 2022-09-19 | P/FVC/MDS/1098138/2022 | 2022-09-27 | ST202209432269 | 2022-09-17 | P/FVC/MDS/1098003/2022 | 2022-09-27
2375 | ATMPM2 | ATMPM2 |  |  |  | ROTN | Indus | IN-3149821 | R/NN-682572 |  |  |  | ATMPM2 | 4G_FD900_ATMPM2 | 4G_FD2100_ATMPM2 | 4G_TD_ATMPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485604 | 2022-09-27 | P/FVC/MDS/1101202/2022 | 2022-10-10 | ST202209491842 | 2022-09-28 | P/FVC/MDS/1101372/2022 | 2022-10-10 |  |  |  |  | ST202209483250 | 2022-09-26 | P/FBW/MDS/1101099/2022 | 2022-10-10
2376 | MNSRT2 | MNSRT2 |  |  |  | ROTN | Indus | IN-1030546 | R/RES-512827 |  |  |  | MNSRT2 | 4G_FD900_MNSRT2 | 4G_FD2100_MNSRT2 | 4G_TD_MNSRT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405538 | 2022-09-09 | P/FVC/MDS/1096601/2022 | 2022-09-16 | ST202209406238 | 2022-09-09 | P/FVC/MDS/1096510/2022 | 2022-09-16 | ST202209402079 | 2022-09-08 | P/FVC/MDS/1096433/2022 | 2022-09-16 | ST202209400222 | 2022-09-08 | P/FVC/MDS/1096415/2022 | 2022-09-16
2377 | AGLM11 | AGLM11 |  |  |  | ROTN | ATC | TN/TR/AT/23414 | T22TN05729 |  |  |  | AGLM11 | 4G_FD900_AGLM11 | 4G_FD2100_AGLM11 | 4G_TD_AGLM11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485727 | 2022-09-27 | P/FVC/MDS/1101225/2022 | 2022-10-10 | ST202209492781 | 2022-09-28 | P/FVC/MDS/1101395/2022 | 2022-10-10 | ST202209487267 | 2022-09-27 | P/FVC/MDS/1101302/2022 | 2022-10-10 | ST202209483620 | 2022-09-26 | P/FBW/MDS/1101119/2022 | 2022-10-10
2378 | AMMAM4 | AMMAM4 |  |  |  | ROTN | ATC | TN/SA/AT/23415 | T22TN05730 |  |  |  | AMMAM4 | 4G_FD900_AMMAM4 | 4G_FD2100_AMMAM4 | 4G_TD_AMMAM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485756 | 2022-09-27 | P/FVC/MDS/1101234/2022 | 2022-10-10 | ST202209492870 | 2022-09-28 | P/FVC/MDS/1101404/2022 | 2022-10-10 |  |  |  |  | ST202209483681 | 2022-09-26 | P/FBW/MDS/1101127/2022 | 2022-10-10
2379 | CHKMO2 | CHKMO2 |  |  |  | ROTN | ATC | TN/CO/AT/23416 | T22TN05731 |  |  |  | CHKMO2 | 4G_FD900_CHKMO2 | 4G_FD2100_CHKMO2 | 4G_TD_CHKMO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485757 | 2022-09-27 | P/FVC/MDS/1101235/2022 | 2022-10-10 | ST202209495067 | 2022-09-29 | P/FVC/MDS/1101454/2022 | 2022-10-10 |  |  |  |  | ST202209483682 | 2022-09-26 | P/FBW/MDS/1101128/2022 | 2022-10-10
2380 | KRHPY2 | KRHPY2 |  |  |  | ROTN | ATC | TN/NM/AT/23418 | T22TN05733 |  |  |  | KRHPY2 | 4G_FD900_KRHPY2 | 4G_FD2100_KRHPY2 | 4G_TD_KRHPY2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442387 | 2022-09-18 | P/FVC/MDS/1098051/2022 | 2022-09-27 | ST202209445887 | 2022-09-19 | P/FVC/MDS/1098139/2022 | 2022-09-27 | ST202209432270 | 2022-09-17 | P/FVC/MDS/1098004/2022 | 2022-09-27
2381 | ERKNR2 | ERKNR2 |  |  |  | ROTN | Indus | IN-3149491 | R/NN-682261 |  |  |  | ERKNR2 | 4G_FD900_ERKNR2 | 4G_FD2100_ERKNR2 | 4G_TD_ERKNR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486896 | 2022-09-27 | P/FVC/MDS/1101526/2022 | 2022-10-10 | ST202209495603 | 2022-09-29 | P/FVC/MDS/1101469/2022 | 2022-10-10 | ST202209487366 | 2022-09-27 | P/FVC/MDS/1101337/2022 | 2022-10-10 | ST202209484369 | 2022-09-26 | P/FBW/MDS/1101060/2022 | 2022-10-10
2382 | THPTI3 | THPTI3 |  |  |  | ROTN | ATC | TN/SA/AT/23421 | T22TN05736 |  |  |  | THPTI3 | 4G_FD900_THPTI3 | 4G_FD2100_THPTI3 | 4G_TD_THPTI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486442 | 2022-09-27 | P/FVC/MDS/1101269/2022 | 2022-10-10 | ST202209493264 | 2022-09-28 | P/FVC/MDS/1101438/2022 | 2022-10-10 | ST202211757911 | 2022-11-22 | P/FVC/MDS/1116753/2022 | 2022-11-29 | ST202209484129 | 2022-09-26 | P/FBW/MDS/1101162/2022 | 2022-10-10
2383 | CMPYM2 | CMPYM2 |  |  |  | ROTN | Indus | IN-1030592 | R/RES-512808 |  |  |  | CMPYM2 | 4G_FD900_CMPYM2 | 4G_FD2100_CMPYM2 | 4G_TD_CMPYM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405533 | 2022-09-09 | P/FVC/MDS/1096599/2022 | 2022-09-16 | ST202209406219 | 2022-09-09 | P/FVC/MDS/1096508/2022 | 2022-09-16 | ST202209402068 | 2022-09-08 | P/FVC/MDS/1096431/2022 | 2022-09-16 | ST202209400220 | 2022-09-08 | P/FVC/MDS/1096413/2022 | 2022-09-16
2384 | SNMBP3 | SNMBP3 |  |  |  | ROTN | Indus | IN-3149875 | R/NN-682640 |  |  |  | SNMBP3 | 4G_FD900_SNMBP3 | 4G_FD2100_SNMBP3 | 4G_TD_SNMBP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487169 | 2022-09-27 | P/FVC/MDS/1101543/2022 | 2022-10-10 | ST202209496895 | 2022-09-29 | P/FVC/MDS/1101486/2022 | 2022-10-10 |  |  |  |  | ST202209484420 | 2022-09-26 | P/FBW/MDS/1101077/2022 | 2022-10-10
2385 | THGVI2 | THGVI2 |  |  |  | ROTN | Indus | IN-3149839 | R/NN-682598 |  |  |  | THGVI2 | 4G_FD900_THGVI2 | 4G_FD2100_THGVI2 | 4G_TD_THGVI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485678 | 2022-09-27 | P/FVC/MDS/1101212/2022 | 2022-10-10 | ST202209491910 | 2022-09-28 | P/FVC/MDS/1101382/2022 | 2022-10-10 |  |  |  |  | ST202209483505 | 2022-09-26 | P/FBW/MDS/1101108/2022 | 2022-10-10
2386 | ILMPR2 | ILMPR2 |  |  |  | ROTN | Indus | IN-3149650 | R/NN-682426 |  |  |  | ILMPR2 | 4G_FD900_ILMPR2 | 4G_FD2100_ILMPR2 | 4G_TD_ILMPR2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209485603 | 2022-09-27 | P/FVC/MDS/1101201/2022 | 2022-10-10 | ST202209491821 | 2022-09-28 | P/FVC/MDS/1101371/2022 | 2022-10-10 | ST202209487245 | 2022-09-27 | P/FVC/MDS/1101290/2022 | 2022-10-10
2387 | ICHPA2 | ICHPA2 |  |  |  | ROTN | Indus | IN-3149858 | R/NN-682628 |  |  |  | ICHPA2 | 4G_FD900_ICHPA2 | 4G_FD2100_ICHPA2 | 4G_TD_ICHPA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485157 | 2022-09-27 | P/FVC/MDS/1101196/2022 | 2022-10-10 | ST202209491761 | 2022-09-28 | P/FVC/MDS/1101366/2022 | 2022-10-10 | ST202211757933 | 2022-11-22 | P/FVC/MDS/1116756/2022 | 2022-11-29 | ST202209483221 | 2022-09-26 | P/FBW/MDS/1101096/2022 | 2022-10-10
2388 | PNGTR2 | PNGTR2 |  |  |  | ROTN | ATC | TN/ER/AT/23424 | T22TN05739 |  |  |  | PNGTR2 | 4G_FD900_PNGTR2 | 4G_FD2100_PNGTR2 | 4G_TD_PNGTR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487150 | 2022-09-27 | P/FVC/MDS/1101539/2022 | 2022-10-10 | ST202209495921 | 2022-09-29 | P/FVC/MDS/1101482/2022 | 2022-10-10 | ST202211757934 | 2022-11-22 | P/FVC/MDS/1116757/2022 | 2022-11-29 | ST202209484410 | 2022-09-26 | P/FBW/MDS/1101073/2022 | 2022-10-10
2389 | JDPLM2 | JDPLM2 |  |  |  | ROTN | ATC | TN/NM/AT/23426 | T22TN05741 |  |  |  | JDPLM2 | 4G_FD900_JDPLM2 | 4G_FD2100_JDPLM2 | 4G_TD_JDPLM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442562 | 2022-09-18 | P/FVC/MDS/1098092/2022 | 2022-09-27 | ST202209446654 | 2022-09-19 | P/FVC/MDS/1098180/2022 | 2022-09-27 | ST202209432599 | 2022-09-17 | P/FVC/MDS/1098016/2022 | 2022-09-27 | ST202209431945 | 2022-09-17 | P/FVC/MDS/1097960/2022 | 2022-09-27
2390 | SGALM2 | SGALM2 |  |  |  | ROTN | ATC | TN/TR/AT/23427 | T22TN05742 |  |  |  | SGALM2 | 4G_FD900_SGALM2 | 4G_FD2100_SGALM2 | 4G_TD_SGALM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486300 | 2022-09-27 | P/FVC/MDS/1101243/2022 | 2022-10-10 | ST202209493027 | 2022-09-28 | P/FVC/MDS/1101412/2022 | 2022-10-10 | ST202209487275 | 2022-09-27 | P/FVC/MDS/1101306/2022 | 2022-10-10 | ST202209483999 | 2022-09-26 | P/FBW/MDS/1101136/2022 | 2022-10-10
2391 | UDYDU2 | UDYDU2 |  |  |  | ROTN | Ascend | - | - |  |  |  | UDYDU2 | 4G_FD900_UDYDU2 | 4G_FD2100_UDYDU2 | 4G_TD_UDYDU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442451 | 2022-09-18 | P/FVC/MDS/1098076/2022 | 2022-09-27 | ST202209446329 | 2022-09-19 | P/FVC/MDS/1098164/2022 | 2022-09-27 | ST202209432422 | 2022-09-17 | P/FVC/MDS/1098009/2022 | 2022-09-27 | ST202209431777 | 2022-09-17 | P/FVC/MDS/1097948/2022 | 2022-09-27
2392 | AGARM2 | AGARM2 |  |  |  | ROTN | Indus | IN-3149496 | R/NN-682265 |  |  |  | AGARM2 | 4G_FD900_AGARM2 | 4G_FD2100_AGARM2 | 4G_TD_AGARM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486355 | 2022-09-27 | P/FVC/MDS/1101253/2022 | 2022-10-10 | ST202209493120 | 2022-09-28 | P/FVC/MDS/1101422/2022 | 2022-10-10 | ST202209487285 | 2022-09-27 | P/FVC/MDS/1101311/2022 | 2022-10-10 | ST202209484051 | 2022-09-26 | P/FBW/MDS/1101146/2022 | 2022-10-10
2393 | KLKIR2 | KLKIR2 |  |  |  | ROTN | Indus | IN-3149612 | R/NN-682366 |  |  |  | KLKIR2 | 4G_FD900_KLKIR2 | 4G_FD2100_KLKIR2 | 4G_TD_KLKIR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486874 | 2022-09-27 | P/FVC/MDS/1101525/2022 | 2022-10-10 | ST202209495602 | 2022-09-29 | P/FVC/MDS/1101468/2022 | 2022-10-10 | ST202209487365 | 2022-09-27 | P/FVC/MDS/1101336/2022 | 2022-10-10 | ST202209484364 | 2022-09-26 | P/FBW/MDS/1101059/2022 | 2022-10-10
2394 | KAPLM2 | KAPLM2 |  |  |  | ROTN | Indus | IN-3149822 | R/NN-682574 |  |  |  | KAPLM2 | 4G_FD900_KAPLM2 | 4G_FD2100_KAPLM2 | 4G_TD_KAPLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442783 | 2022-09-19 | P/FVC/MDS/1098119/2022 | 2022-09-27 | ST202209447431 | 2022-09-19 | P/FVC/MDS/1098206/2022 | 2022-09-27 |  |  |  |  | ST202209432356 | 2022-09-17 | P/FVC/MDS/1097984/2022 | 2022-09-27
2395 | KLVNG2 | KLVNG2 |  |  |  | ROTN | ATC | TN/ER/AT/23428 | T22TN05743 |  |  |  | KLVNG2 | 4G_FD900_KLVNG2 | 4G_FD2100_KLVNG2 | 4G_TD_KLVNG2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442517 | 2022-09-18 | P/FVC/MDS/1098083/2022 | 2022-09-27 | ST202209446479 | 2022-09-19 | P/FVC/MDS/1098171/2022 | 2022-09-27 | ST202209432469 | 2022-09-17 | P/FVC/MDS/1098012/2022 | 2022-09-27 | ST202209431887 | 2022-09-17 | P/FVC/MDS/1097954/2022 | 2022-09-27
2396 | PLMLM3 | PLMLM3 |  |  |  | ROTN | Indus | IN-1059566 | R/RES-512810 |  |  |  | PLMLM3 | 4G_FD900_PLMLM3 | 4G_FD2100_PLMLM3 | 4G_TD_PLMLM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405240 | 2022-09-09 | P/FVC/MDS/1096595/2022 | 2022-09-16 | ST202209406173 | 2022-09-09 | P/FVC/MDS/1096504/2022 | 2022-09-16 | ST202209401300 | 2022-09-08 | P/FVC/MDS/1096429/2022 | 2022-09-16 | ST202209400154 | 2022-09-08 | P/FVC/MDS/1096410/2022 | 2022-09-16
2397 | KADKI2 | KADKI2 |  |  |  | ROTN | Indus | IN-3149504 | R/NN-682268 |  |  |  | KADKI2 | 4G_FD900_KADKI2 | 4G_FD2100_KADKI2 | 4G_TD_KADKI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486897 | 2022-09-27 | P/FVC/MDS/1101527/2022 | 2022-10-10 | ST202209495640 | 2022-09-29 | P/FVC/MDS/1101470/2022 | 2022-10-10 | ST202209487370 | 2022-09-27 | P/FVC/MDS/1101338/2022 | 2022-10-10 | ST202209484370 | 2022-09-26 | P/FBW/MDS/1101061/2022 | 2022-10-10
2398 | KANUR2 | KANUR2 |  |  |  | ROTN | Ascend | - | - |  |  |  | KANUR2 | 4G_FD900_KANUR2 | 4G_FD2100_KANUR2 | 4G_TD_KANUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442420 | 2022-09-18 | P/FVC/MDS/1098070/2022 | 2022-09-27 | ST202209446246 | 2022-09-19 | P/FVC/MDS/1098158/2022 | 2022-09-27 |  |  |  |  | ST202209431613 | 2022-09-17 | P/FVC/MDS/1097940/2022 | 2022-09-27
2399 | KNVKI2 | KNVKI2 |  |  |  | ROTN | ATC | TN4251 | - |  |  |  | KNVKI2 | 4G_FD900_KNVKI2 | 4G_FD2100_KNVKI2 | 4G_TD_KNVKI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487170 | 2022-09-27 | P/FVC/MDS/1101544/2022 | 2022-10-10 | ST202209496896 | 2022-09-29 | P/FVC/MDS/1101487/2022 | 2022-10-10 |  |  |  |  | ST202209484421 | 2022-09-26 | P/FBW/MDS/1101078/2022 | 2022-10-10
2400 | KRTPL2 | KRTPL2 |  |  |  | ROTN | Indus | IN-3149766 | R/NN-682511 |  |  |  | KRTPL2 | 4G_FD900_KRTPL2 | 4G_FD2100_KRTPL2 | 4G_TD_KRTPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486373 | 2022-09-27 | P/FVC/MDS/1101257/2022 | 2022-10-10 | ST202209493145 | 2022-09-28 | P/FVC/MDS/1101426/2022 | 2022-10-10 |  |  |  |  | ST202209484061 | 2022-09-26 | P/FBW/MDS/1101150/2022 | 2022-10-10
2401 | KRAMR2 | KRAMR2 |  |  |  | ROTN | ATC | TN/NM/AT/23430 | T22TN05745 |  |  |  | KRAMR2 | 4G_FD900_KRAMR2 | 4G_FD2100_KRAMR2 | 4G_TD_KRAMR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442761 | 2022-09-19 | P/FVC/MDS/1098104/2022 | 2022-09-27 | ST202209447411 | 2022-09-19 | P/FVC/MDS/1098192/2022 | 2022-09-27 | ST202209432870 | 2022-09-17 | P/FVC/MDS/1098025/2022 | 2022-09-27 | ST202209432147 | 2022-09-17 | P/FVC/MDS/1097969/2022 | 2022-09-27
2402 | KKMBI2 | KKMBI2 |  |  |  | ROTN | Indus | IN-1074780 | R/RES-512828 |  |  |  | KKMBI2 | 4G_FD900_KKMBI2 | 4G_FD2100_KKMBI2 | 4G_TD_KKMBI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405534 | 2022-09-09 | P/FVC/MDS/1096600/2022 | 2022-09-16 | ST202209406220 | 2022-09-09 | P/FVC/MDS/1096509/2022 | 2022-09-16 | ST202209402069 | 2022-09-08 | P/FVC/MDS/1096432/2022 | 2022-09-16 | ST202209400221 | 2022-09-08 | P/FVC/MDS/1096414/2022 | 2022-09-16
2403 | KILKT2 | KILKT2 |  |  |  | ROTN | Indus | IN-3149863 | R/NN-671441 |  |  |  | KILKT2 | 4G_FD900_KILKT2 | 4G_FD2100_KILKT2 | 4G_TD_KILKT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486872 | 2022-09-27 | P/FVC/MDS/1101523/2022 | 2022-10-10 | ST202209495570 | 2022-09-29 | P/FVC/MDS/1101466/2022 | 2022-10-10 | ST202209487360 | 2022-09-27 | P/FVC/MDS/1101334/2022 | 2022-10-10 | ST202209484353 | 2022-09-26 | P/FBW/MDS/1101057/2022 | 2022-10-10
2404 | KKIEM2 | KKIEM2 |  |  |  | ROTN | ATC | TN/NM/AT/23431 | T22TN05746 |  |  |  | KKIEM2 | 4G_FD900_KKIEM2 | 4G_FD2100_KKIEM2 | 4G_TD_KKIEM2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442518 | 2022-09-18 | P/FVC/MDS/1098084/2022 | 2022-09-27 | ST202209446480 | 2022-09-19 | P/FVC/MDS/1098172/2022 | 2022-09-27 | ST202209432521 | 2022-09-17 | P/FVC/MDS/1098013/2022 | 2022-09-27
2405 | KNPTL2 | KNPTL2 |  |  |  | ROTN | ATC | TN/SA/AT/23432 | T22TN05747 |  |  |  | KNPTL2 | 4G_FD900_KNPTL2 | 4G_FD2100_KNPTL2 | 4G_TD_KNPTL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442514 | 2022-09-18 | P/FVC/MDS/1098080/2022 | 2022-09-27 | ST202209446409 | 2022-09-19 | P/FVC/MDS/1098168/2022 | 2022-09-27 |  |  |  |  | ST202209431831 | 2022-09-17 | P/FVC/MDS/1097952/2022 | 2022-09-27
2406 | KONYR2 | KONYR2 |  |  |  | ROTN | ATC | TN/NM/AT/23433 | T22TN05748 |  |  |  | KONYR2 | 4G_FD900_KONYR2 | 4G_FD2100_KONYR2 | 4G_TD_KONYR2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209485686 | 2022-09-27 | P/FVC/MDS/1101216/2022 | 2022-10-10 | ST202209491985 | 2022-09-28 | P/FVC/MDS/1101386/2022 | 2022-10-10 | ST202209487257 | 2022-09-27 | P/FVC/MDS/1101298/2022 | 2022-10-10
2407 | KRVAM2 | KRVAM2 |  |  |  | ROTN | Indus | IN-3149771 | R/NN-682516 |  |  |  | KRVAM2 | 4G_FD900_KRVAM2 | 4G_FD2100_KRVAM2 | 4G_TD_KRVAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485802 | 2022-09-27 | P/FVC/MDS/1101240/2022 | 2022-10-10 | ST202209492931 | 2022-09-28 | P/FVC/MDS/1101409/2022 | 2022-10-10 |  |  |  |  | ST202209483718 | 2022-09-26 | P/FBW/MDS/1101133/2022 | 2022-10-10
2408 | AMKTR2 | AMKTR2 |  |  |  | ROTN | ATC | TN/SA/AT/23434 | T22TN05749 |  |  |  | AMKTR2 | 4G_FD900_AMKTR2 | 4G_FD2100_AMKTR2 | 4G_TD_AMKTR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442765 | 2022-09-19 | P/FVC/MDS/1098105/2022 | 2022-09-27 | ST202209447412 | 2022-09-19 | P/FVC/MDS/1098193/2022 | 2022-09-27 | ST202209432871 | 2022-09-17 | P/FVC/MDS/1098026/2022 | 2022-09-27 | ST202209432148 | 2022-09-17 | P/FVC/MDS/1097970/2022 | 2022-09-27
2409 | KNYUR3 | KNYUR3 |  |  |  | ROTN | ATC | TN/SA/AT/23435 | T22TN05750 |  |  |  | KNYUR3 | 4G_FD900_KNYUR3 | 4G_FD2100_KNYUR3 | 4G_TD_KNYUR3 | G1800+L1800+L2100 | WPC ID Available 2G1800+FD1800+FD2100 |  | ST202209442516 | 2022-09-18 | P/FVC/MDS/1098082/2022 | 2022-09-27 | ST202209446478 | 2022-09-19 | P/FVC/MDS/1098170/2022 | 2022-09-27 | ST202209432468 | 2022-09-17 | P/FVC/MDS/1098011/2022 | 2022-09-27
2410 | KNCHM2 | KNCHM2 |  |  |  | ROTN | Indus | IN-3149860 | R/NN-682629 |  |  |  | KNCHM2 | 4G_FD900_KNCHM2 | 4G_FD2100_KNCHM2 | 4G_TD_KNCHM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485605 | 2022-09-27 | P/FVC/MDS/1101203/2022 | 2022-10-10 | ST202209491843 | 2022-09-28 | P/FVC/MDS/1101373/2022 | 2022-10-10 |  |  |  |  | ST202209483456 | 2022-09-26 | P/FBW/MDS/1101100/2022 | 2022-10-10
2411 | KUKLT2 | KUKLT2 |  |  |  | ROTN | Indus | IN-3149772 | R/NN-682518 |  |  |  | KUKLT2 | 4G_FD900_KUKLT2 | 4G_FD2100_KUKLT2 | 4G_TD_KUKLT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485666 | 2022-09-27 | P/FVC/MDS/1101211/2022 | 2022-10-10 | ST202209491909 | 2022-09-28 | P/FVC/MDS/1101381/2022 | 2022-10-10 |  |  |  |  | ST202209483504 | 2022-09-26 | P/FBW/MDS/1101107/2022 | 2022-10-10
2412 | KUKLM2 | KUKLM2 |  |  |  | ROTN | Indus | IN-3149809 | R/NN-682555 |  |  |  | KUKLM2 | 4G_FD900_KUKLM2 | 4G_FD2100_KUKLM2 | 4G_TD_KUKLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485156 | 2022-09-27 | P/FVC/MDS/1101195/2022 | 2022-10-10 | ST202209491760 | 2022-09-28 | P/FVC/MDS/1101365/2022 | 2022-10-10 |  |  |  |  | ST202209483220 | 2022-09-26 | P/FBW/MDS/1101095/2022 | 2022-10-10
2413 | SRGMN6 | SRGMN6 |  |  |  | ROTN | ATC | TN/TR/AT/23437 | T22TN05752 |  |  |  | SRGMN6 | 4G_FD900_SRGMN6 | 4G_FD2100_SRGMN6 | 4G_TD_SRGMN6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442766 | 2022-09-19 | P/FVC/MDS/1098106/2022 | 2022-09-27 | ST202209447413 | 2022-09-19 | P/FVC/MDS/1098194/2022 | 2022-09-27 | ST202209432910 | 2022-09-17 | P/FVC/MDS/1098027/2022 | 2022-09-27 | ST202209432185 | 2022-09-17 | P/FVC/MDS/1097971/2022 | 2022-09-27
2414 | RENGM2 | RENGM2 |  |  |  | ROTN | ATC | TN/DH/AT/23438 | T22TN05753 |  |  |  | RENGM2 | 4G_FD900_RENGM2 | 4G_FD2100_RENGM2 | 4G_TD_RENGM2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442753 | 2022-09-19 | P/FVC/MDS/1098098/2022 | 2022-09-27 | ST202209447386 | 2022-09-19 | P/FVC/MDS/1098186/2022 | 2022-09-27 | ST202209432689 | 2022-09-17 | P/FVC/MDS/1098020/2022 | 2022-09-27
2415 | NMBYP2 | NMBYP2 |  |  |  | ROTN | Indus | IN-3149784 | R/NN-682533 |  |  |  | NMBYP2 | 4G_FD900_NMBYP2 | 4G_FD2100_NMBYP2 | 4G_TD_NMBYP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486898 | 2022-09-27 | P/FVC/MDS/1101528/2022 | 2022-10-10 | ST202209495641 | 2022-09-29 | P/FVC/MDS/1101471/2022 | 2022-10-10 | ST202209487371 | 2022-09-27 | P/FVC/MDS/1101339/2022 | 2022-10-10 | ST202209484371 | 2022-09-26 | P/FBW/MDS/1101062/2022 | 2022-10-10
2416 | MANNR2 | MANNR2 |  |  |  | ROTN | ATC | TN/TR/AT/23439 | T22TN05754 |  |  |  | MANNR2 | 4G_FD900_MANNR2 | 4G_FD2100_MANNR2 | 4G_TD_MANNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442393 | 2022-09-18 | P/FVC/MDS/1098053/2022 | 2022-09-27 | ST202209445920 | 2022-09-19 | P/FVC/MDS/1098141/2022 | 2022-09-27 |  |  |  |  | ST202209431376 | 2022-09-17 | P/FVC/MDS/1097923/2022 | 2022-09-27
2417 | KKVAD2 | KKVAD2 |  |  |  | ROTN | Indus | IN-3149862 | R/NN-682632 |  |  |  | KKVAD2 | 4G_FD900_KKVAD2 | 4G_FD2100_KKVAD2 | 4G_TD_KKVAD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486791 | 2022-09-27 | P/FVC/MDS/1101514/2022 | 2022-10-10 | ST202209495124 | 2022-09-29 | P/FVC/MDS/1101457/2022 | 2022-10-10 | ST202211757913 | 2022-11-22 | P/FVC/MDS/1116755/2022 | 2022-11-29 | ST202209484232 | 2022-09-26 | P/FBW/MDS/1101180/2022 | 2022-10-10
2418 | TUPGN2 | TUPGN2 |  |  |  | ROTN | ATC | TN/DH/AT/23441 | T22TN05756 |  |  |  | TUPGN2 | 4G_FD900_TUPGN2 | 4G_FD2100_TUPGN2 | 4G_TD_TUPGN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442767 | 2022-09-19 | P/FVC/MDS/1098107/2022 | 2022-09-27 | ST202209447414 | 2022-09-19 | P/FVC/MDS/1098195/2022 | 2022-09-27 |  |  |  |  | ST202209432186 | 2022-09-17 | P/FVC/MDS/1097972/2022 | 2022-09-27
2419 | MMNKR2 | MMNKR2 |  |  |  | ROTN | ATC | TN/TR/AT/23442 | T22TN05757 |  |  |  | MMNKR2 | 4G_FD900_MMNKR2 | 4G_FD2100_MMNKR2 | 4G_TD_MMNKR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442528 | 2022-09-18 | P/FVC/MDS/1098091/2022 | 2022-09-27 | ST202209446621 | 2022-09-19 | P/FVC/MDS/1098179/2022 | 2022-09-27 |  |  |  |  | ST202209432904 | 2022-09-17 | P/FVC/MDS/1097990/2022 | 2022-09-27
2420 | MEVNI2 | MEVNI2 |  |  |  | ROTN | Indus | IN-3149617 | R/NN-682384 |  |  |  | MEVNI2 | 4G_FD900_MEVNI2 | 4G_FD2100_MEVNI2 | 4G_TD_MEVNI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485577 | 2022-09-27 | P/FVC/MDS/1101200/2022 | 2022-10-10 | ST202209491820 | 2022-09-28 | P/FVC/MDS/1101370/2022 | 2022-10-10 | ST202209487240 | 2022-09-27 | P/FVC/MDS/1101289/2022 | 2022-10-10 | ST202209483249 | 2022-09-26 | P/FBW/MDS/1101098/2022 | 2022-10-10
2421 | NLGDM2 | NLGDM2 |  |  |  | ROTN | Indus | IN-3149864 | R/NN-682633 |  |  |  | NLGDM2 | 4G_FD900_NLGDM2 | 4G_FD2100_NLGDM2 | 4G_TD_NLGDM2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209485158 | 2022-09-27 | P/FVC/MDS/1101197/2022 | 2022-10-10 | ST202209491792 | 2022-09-28 | P/FVC/MDS/1101367/2022 | 2022-10-10 | ST202209487238 | 2022-09-27 | P/FVC/MDS/1101287/2022 | 2022-10-10
2422 | MNROD2 | MNROD2 |  |  |  | ROTN | Indus | IN-3149546 | R/NN-682309 |  |  |  | MNROD2 | 4G_FD900_MNROD2 | 4G_FD2100_MNROD2 | 4G_TD_MNROD2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486356 | 2022-09-27 | P/FVC/MDS/1101254/2022 | 2022-10-10 | ST202209493121 | 2022-09-28 | P/FVC/MDS/1101423/2022 | 2022-10-10 | ST202209487286 | 2022-09-27 | P/FVC/MDS/1101312/2022 | 2022-10-10 | ST202209484052 | 2022-09-26 | P/FBW/MDS/1101147/2022 | 2022-10-10
2423 | KTLPM2 | KTLPM2 |  |  |  | ROTN | ATC | TN/NM/AT/23444 | T22TN05759 |  |  |  | KTLPM2 | 4G_FD900_KTLPM2 | 4G_FD2100_KTLPM2 | 4G_TD_KTLPM2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442523 | 2022-09-18 | P/FVC/MDS/1098088/2022 | 2022-09-27 | ST202209446560 | 2022-09-19 | P/FVC/MDS/1098176/2022 | 2022-09-27 | ST202209432598 | 2022-09-17 | P/FVC/MDS/1098015/2022 | 2022-09-27
2424 | SENML2 | SENML2 |  |  |  | ROTN | Indus | IN-3149549 | R/NN-682311 |  |  |  | SENML2 | 4G_FD900_SENML2 | 4G_FD2100_SENML2 | 4G_TD_SENML2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485774 | 2022-09-27 | P/FVC/MDS/1101239/2022 | 2022-10-10 | ST202209492930 | 2022-09-28 | P/FVC/MDS/1101408/2022 | 2022-10-10 | ST202209487269 | 2022-09-27 | P/FVC/MDS/1101304/2022 | 2022-10-10 | ST202209483717 | 2022-09-26 | P/FBW/MDS/1101132/2022 | 2022-10-10
2425 | ADKRT2 | ADKRT2 |  |  |  | ROTN | Indus | IN-1031286 | R/RES-512802 |  |  |  | ADKRT2 | 4G_FD900_ADKRT2 | 4G_FD2100_ADKRT2 | 4G_TD_ADKRT2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209405522 | 2022-09-09 | P/FVC/MDS/1096597/2022 | 2022-09-16 | ST202209406201 | 2022-09-09 | P/FVC/MDS/1096506/2022 | 2022-09-16 | ST202209401301 | 2022-09-08 | P/FVC/MDS/1096430/2022 | 2022-09-16
2426 | KNGPM2 | KNGPM2 |  |  |  | ROTN | Indus | IN-3149824 | R/NN-682576 |  |  |  | KNGPM2 | 4G_FD900_KNGPM2 | 4G_FD2100_KNGPM2 | 4G_TD_KNGPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486396 | 2022-09-27 | P/FVC/MDS/1101261/2022 | 2022-10-10 | ST202209493199 | 2022-09-28 | P/FVC/MDS/1101430/2022 | 2022-10-10 |  |  |  |  | ST202209484081 | 2022-09-26 | P/FBW/MDS/1101154/2022 | 2022-10-10
2427 | ENMAN2 | ENMAN2 |  |  |  | ROTN | Indus | IN-3149559 | R/NN-682339 |  |  |  | ENMAN2 | 4G_FD900_ENMAN2 | 4G_FD2100_ENMAN2 | 4G_TD_ENMAN2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487168 | 2022-09-27 | P/FVC/MDS/1101542/2022 | 2022-10-10 | ST202209496894 | 2022-09-29 | P/FVC/MDS/1101485/2022 | 2022-10-10 | ST202209487703 | 2022-09-28 | P/FVC/MDS/1101346/2022 | 2022-10-10 | ST202209484419 | 2022-09-26 | P/FBW/MDS/1101076/2022 | 2022-10-10
2428 | MUTHK2 | MUTHK2 |  |  |  | ROTN | ATC | TN/TR/AT/23446 | T22TN05761 |  |  |  | MUTHK2 | 4G_FD900_MUTHK2 | 4G_FD2100_MUTHK2 | 4G_TD_MUTHK2 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202209485728 | 2022-09-27 | P/FVC/MDS/1101226/2022 | 2022-10-10 | ST202209492802 | 2022-09-28 | P/FVC/MDS/1101396/2022 | 2022-10-10 | ST202209487268 | 2022-09-27 | P/FVC/MDS/1101303/2022 | 2022-10-10 | ST202209483621 | 2022-09-26 | P/FBW/MDS/1101120/2022 | 2022-10-10
2429 | MNKPI3 | MNKPI3 |  |  |  | ROTN | Indus | IN-3149826 | R/NN-682577 |  |  |  | MNKPI3 | 4G_FD900_MNKPI3 | 4G_FD2100_MNKPI3 | 4G_TD_MNKPI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486407 | 2022-09-27 | P/FVC/MDS/1101262/2022 | 2022-10-10 | ST202209493201 | 2022-09-28 | P/FVC/MDS/1101431/2022 | 2022-10-10 |  |  |  |  | ST202209484082 | 2022-09-26 | P/FBW/MDS/1101155/2022 | 2022-10-10
2430 | NLROD2 | NLROD2 |  |  |  | ROTN | Indus | IN-3149620 | R/NN-682388 |  |  |  | NLROD2 | 4G_FD900_NLROD2 | 4G_FD2100_NLROD2 | 4G_TD_NLROD2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487123 | 2022-09-27 | P/FVC/MDS/1101530/2022 | 2022-10-10 | ST202209495671 | 2022-09-29 | P/FVC/MDS/1101473/2022 | 2022-10-10 | ST202209487677 | 2022-09-28 | P/FVC/MDS/1101341/2022 | 2022-10-10 | ST202209484383 | 2022-09-26 | P/FBW/MDS/1101064/2022 | 2022-10-10
2431 | NALPM2 | NALPM2 |  |  |  | ROTN | Indus | IN-3149624 | R/NN-682390 |  |  |  | NALPM2 | 4G_FD900_NALPM2 | 4G_FD2100_NALPM2 | 4G_TD_NALPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485141 | 2022-09-27 | P/FVC/MDS/1101193/2022 | 2022-10-10 | ST202209491728 | 2022-09-28 | P/FVC/MDS/1101363/2022 | 2022-10-10 | ST202209487233 | 2022-09-27 | P/FVC/MDS/1101286/2022 | 2022-10-10 | ST202209483206 | 2022-09-26 | P/FBW/MDS/1101093/2022 | 2022-10-10
2432 | PANRS2 | PANRS2 |  |  |  | ROTN | ATC | TN/DH/AT/23449 | T22TN05764 |  |  |  | PANRS2 | 4G_FD900_PANRS2 | 4G_FD2100_PANRS2 | 4G_TD_PANRS2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442397 | 2022-09-18 | P/FVC/MDS/1098055/2022 | 2022-09-27 | ST202209445948 | 2022-09-19 | P/FVC/MDS/1098143/2022 | 2022-09-27 | ST202209432320 | 2022-09-17 | P/FVC/MDS/1098005/2022 | 2022-09-27 | ST202209431411 | 2022-09-17 | P/FVC/MDS/1097925/2022 | 2022-09-27
2433 | NDMGM2 | NDMGM2 |  |  |  | ROTN | ATC | TN/SA/AT/23450 | T22TN05765 |  |  |  | NDMGM2 | 4G_FD900_NDMGM2 | 4G_FD2100_NDMGM2 | 4G_TD_NDMGM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442521 | 2022-09-18 | P/FVC/MDS/1098087/2022 | 2022-09-27 | ST202209446559 | 2022-09-19 | P/FVC/MDS/1098175/2022 | 2022-09-27 |  |  |  |  | ST202209431916 | 2022-09-17 | P/FVC/MDS/1097957/2022 | 2022-09-27
2434 | MEBVI2 | MEBVI2 |  |  |  | ROTN | Indus | IN-3149566 | R/NN-682345 |  |  |  | MEBVI2 | 4G_FD900_MEBVI2 | 4G_FD2100_MEBVI2 | 4G_TD_MEBVI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486873 | 2022-09-27 | P/FVC/MDS/1101524/2022 | 2022-10-10 | ST202209495601 | 2022-09-29 | P/FVC/MDS/1101467/2022 | 2022-10-10 | ST202209487364 | 2022-09-27 | P/FVC/MDS/1101335/2022 | 2022-10-10 | ST202209484363 | 2022-09-26 | P/FBW/MDS/1101058/2022 | 2022-10-10
2435 | KAYAM2 | KAYAM2 |  |  |  | ROTN | Indus | IN-3149785 | R/NN-682534 |  |  |  | KAYAM2 | 4G_FD900_KAYAM2 | 4G_FD2100_KAYAM2 | 4G_TD_KAYAM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442782 | 2022-09-19 | P/FVC/MDS/1098118/2022 | 2022-09-27 | ST202209447430 | 2022-09-19 | P/FVC/MDS/1098205/2022 | 2022-09-27 | ST202209432993 | 2022-09-17 | P/FVC/MDS/1098032/2022 | 2022-09-27 | ST202209432355 | 2022-09-17 | P/FVC/MDS/1097983/2022 | 2022-09-27
2436 | MLPFR2 | MLPFR2 |  |  |  | ROTN | Indus | IN-3149810 | R/NN-682556 |  |  |  | MLPFR2 | 4G_FD900_MLPFR2 | 4G_FD2100_MLPFR2 | 4G_TD_MLPFR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487133 | 2022-09-27 | P/FVC/MDS/1101533/2022 | 2022-10-10 | ST202209495862 | 2022-09-29 | P/FVC/MDS/1101476/2022 | 2022-10-10 |  |  |  |  | ST202209484390 | 2022-09-26 | P/FBW/MDS/1101067/2022 | 2022-10-10
2437 | POMPM2 | POMPM2 |  |  |  | ROTN | ATC | TN/TR/AT/23452 | T22TN05767 |  |  |  | POMPM2 | 4G_FD900_POMPM2 | 4G_FD2100_POMPM2 | 4G_TD_POMPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442768 | 2022-09-19 | P/FVC/MDS/1098108/2022 | 2022-09-27 | ST202209447415 | 2022-09-19 | P/FVC/MDS/1098196/2022 | 2022-09-27 | ST202209432911 | 2022-09-17 | P/FVC/MDS/1098028/2022 | 2022-09-27 | ST202209432222 | 2022-09-17 | P/FVC/MDS/1097973/2022 | 2022-09-27
2438 | ONPRM3 | ONPRM3 |  |  |  | ROTN | ATC | TN/TV/AT/23454 | T22TN05769 |  |  |  | ONPRM3 | 4G_FD900_ONPRM3 | 4G_FD2100_ONPRM3 | 4G_TD_ONPRM3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442754 | 2022-09-19 | P/FVC/MDS/1098099/2022 | 2022-09-27 | ST202209447387 | 2022-09-19 | P/FVC/MDS/1098187/2022 | 2022-09-27 | ST202209432742 | 2022-09-17 | P/FVC/MDS/1098021/2022 | 2022-09-27 | ST202209432101 | 2022-09-17 | P/FVC/MDS/1097965/2022 | 2022-09-27
2439 | SLYUR2 | SLYUR2 |  |  |  | ROTN | Indus | IN-3149786 | R/NN-682535 |  |  |  | SLYUR2 | 4G_FD900_SLYUR2 | 4G_FD2100_SLYUR2 | 4G_TD_SLYUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486533 | 2022-09-27 | P/FVC/MDS/1101281/2022 | 2022-10-10 | ST202209493388 | 2022-09-28 | P/FVC/MDS/1101450/2022 | 2022-10-10 | ST202209487328 | 2022-09-27 | P/FVC/MDS/1101325/2022 | 2022-10-10 | ST202209484192 | 2022-09-26 | P/FBW/MDS/1101174/2022 | 2022-10-10
2440 | PAIPR2 | PAIPR2 |  |  |  | ROTN | ATC | TN/SA/AT/23455 | T22TN05770 |  |  |  | PAIPR2 | 4G_FD900_PAIPR2 | 4G_FD2100_PAIPR2 | 4G_TD_PAIPR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442513 | 2022-09-18 | P/FVC/MDS/1098079/2022 | 2022-09-27 | ST202209446374 | 2022-09-19 | P/FVC/MDS/1098167/2022 | 2022-09-27 | ST202209432423 | 2022-09-17 | P/FVC/MDS/1098010/2022 | 2022-09-27 | ST202209431830 | 2022-09-17 | P/FVC/MDS/1097951/2022 | 2022-09-27
2441 | VDSTR2 | VDSTR2 |  |  |  | ROTN | Indus | IN-3150149 | R/NN-682536 |  |  |  | VDSTR2 | 4G_FD900_VDSTR2 | 4G_FD2100_VDSTR2 | 4G_TD_VDSTR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485679 | 2022-09-27 | P/FVC/MDS/1101213/2022 | 2022-10-10 | ST202209491956 | 2022-09-28 | P/FVC/MDS/1101383/2022 | 2022-10-10 | ST202209487253 | 2022-09-27 | P/FVC/MDS/1101295/2022 | 2022-10-10 | ST202209483532 | 2022-09-26 | P/FBW/MDS/1101109/2022 | 2022-10-10
2442 | PAKMP2 | PAKMP2 |  |  |  | ROTN | Indus | IN-3149787 | R/NN-682537 |  |  |  | PAKMP2 | 4G_FD900_PAKMP2 | 4G_FD2100_PAKMP2 | 4G_TD_PAKMP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486534 | 2022-09-27 | P/FVC/MDS/1101282/2022 | 2022-10-10 | ST202209493389 | 2022-09-28 | P/FVC/MDS/1101451/2022 | 2022-10-10 | ST202209487342 | 2022-09-27 | P/FVC/MDS/1101326/2022 | 2022-10-10 | ST202209484193 | 2022-09-26 | P/FBW/MDS/1101175/2022 | 2022-10-10
2443 | PATAM2 | PATAM2 |  |  |  | ROTN | Indus | IN-3149754 | R/NN-682475 |  |  |  | PATAM2 | 4G_FD900_PATAM2 | 4G_FD2100_PATAM2 | 4G_TD_PATAM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486532 | 2022-09-27 | P/FVC/MDS/1101280/2022 | 2022-10-10 | ST202209493361 | 2022-09-28 | P/FVC/MDS/1101449/2022 | 2022-10-10 | ST202209487327 | 2022-09-27 | P/FVC/MDS/1101324/2022 | 2022-10-10 | ST202209484179 | 2022-09-26 | P/FBW/MDS/1101173/2022 | 2022-10-10
2444 | PPUTH2 | PPUTH2 |  |  |  | ROTN | Indus | IN-3149842 | R/NN-682600 |  |  |  | PPUTH2 | 4G_FD900_PPUTH2 | 4G_FD2100_PPUTH2 | 4G_TD_PPUTH2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485663 | 2022-09-27 | P/FVC/MDS/1101209/2022 | 2022-10-10 | ST202209491886 | 2022-09-28 | P/FVC/MDS/1101379/2022 | 2022-10-10 |  |  |  |  | ST202209483483 | 2022-09-26 | P/FBW/MDS/1101105/2022 | 2022-10-10
2445 | PTMPT2 | PTMPT2 |  |  |  | ROTN | ATC | TN/SA/AT/23457 | T22TN05772 |  |  |  | PTMPT2 | 4G_FD900_PTMPT2 | 4G_FD2100_PTMPT2 | 4G_TD_PTMPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442563 | 2022-09-18 | P/FVC/MDS/1098093/2022 | 2022-09-27 | ST202209446655 | 2022-09-19 | P/FVC/MDS/1098181/2022 | 2022-09-27 | ST202211757889 | 2022-11-22 | P/FVC/MDS/1116752/2022 | 2022-11-29 | ST202209431946 | 2022-09-17 | P/FVC/MDS/1097961/2022 | 2022-09-27
2446 | PTPYM2 | PTPYM2 |  |  |  | ROTN | ATC | TN/NM/AT/23458 | T22TN05773 |  |  |  | PTPYM2 | 4G_FD900_PTPYM2 | 4G_FD2100_PTPYM2 | 4G_TD_PTPYM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485709 | 2022-09-27 | P/FVC/MDS/1101220/2022 | 2022-10-10 | ST202209492064 | 2022-09-28 | P/FVC/MDS/1101390/2022 | 2022-10-10 | ST202209487261 | 2022-09-27 | P/FVC/MDS/1101300/2022 | 2022-10-10 | ST202209483558 | 2022-09-26 | P/FBW/MDS/1101114/2022 | 2022-10-10
2447 | ARORI2 | ARORI2 |  |  |  | ROTN | Indus | IN-3149866 | R/NN-682634 |  |  |  | ARORI2 | 4G_FD900_ARORI2 | 4G_FD2100_ARORI2 | 4G_TD_ARORI2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209485621 | 2022-09-27 | P/FVC/MDS/1101205/2022 | 2022-10-10 | ST202209491865 | 2022-09-28 | P/FVC/MDS/1101375/2022 | 2022-10-10 | ST202209487247 | 2022-09-27 | P/FVC/MDS/1101292/2022 | 2022-10-10
2448 | MUDPL2 | MUDPL2 |  |  |  | ROTN | Indus | IN-3149841 | R/NN-671803 |  |  |  | MUDPL2 | 4G_FD900_MUDPL2 | 4G_FD2100_MUDPL2 | 4G_TD_MUDPL2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485622 | 2022-09-27 | P/FVC/MDS/1101206/2022 | 2022-10-10 | ST202209491866 | 2022-09-28 | P/FVC/MDS/1101376/2022 | 2022-10-10 | ST202209487251 | 2022-09-27 | P/FVC/MDS/1101293/2022 | 2022-10-10 | ST202209483458 | 2022-09-26 | P/FBW/MDS/1101102/2022 | 2022-10-10
2449 | THKMR2 | THKMR2 |  |  |  | ROTN | Indus | IN-3149813 | R/NN-682559 |  |  |  | THKMR2 | 4G_FD900_THKMR2 | 4G_FD2100_THKMR2 | 4G_TD_THKMR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486315 | 2022-09-27 | P/FVC/MDS/1101246/2022 | 2022-10-10 | ST202209493053 | 2022-09-28 | P/FVC/MDS/1101415/2022 | 2022-10-10 |  |  |  |  | ST202209484015 | 2022-09-26 | P/FBW/MDS/1101139/2022 | 2022-10-10
2450 | AYPRP2 | AYPRP2 |  |  |  | ROTN | Indus | IN-3149844 | R/NN-682602 |  |  |  | AYPRP2 | 4G_FD900_AYPRP2 | 4G_FD2100_AYPRP2 | 4G_TD_AYPRP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487142 | 2022-09-27 | P/FVC/MDS/1101534/2022 | 2022-10-10 | ST202209495878 | 2022-09-29 | P/FVC/MDS/1101477/2022 | 2022-10-10 |  |  |  |  | ST202209484395 | 2022-09-26 | P/FBW/MDS/1101068/2022 | 2022-10-10
2451 | KLINR2 | KLINR2 |  |  |  | ROTN | ATC | TN/NM/AT/23461 | T22TN05776 |  |  |  | KLINR2 | 4G_FD900_KLINR2 | 4G_FD2100_KLINR2 | 4G_TD_KLINR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442398 | 2022-09-18 | P/FVC/MDS/1098056/2022 | 2022-09-27 | ST202209445949 | 2022-09-19 | P/FVC/MDS/1098144/2022 | 2022-09-27 | ST202209432321 | 2022-09-17 | P/FVC/MDS/1098006/2022 | 2022-09-27 | ST202209431412 | 2022-09-17 | P/FVC/MDS/1097926/2022 | 2022-09-27
2452 | MOREP2 | MOREP2 |  |  |  | ROTN | ATC | TN/NM/AT/23462 | T22TN05777 |  |  |  | MOREP2 | 4G_FD900_MOREP2 | 4G_FD2100_MOREP2 | 4G_TD_MOREP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442770 | 2022-09-19 | P/FVC/MDS/1098109/2022 | 2022-09-27 | ST202209447416 | 2022-09-19 | P/FVC/MDS/1098197/2022 | 2022-09-27 | ST202209432957 | 2022-09-17 | P/FVC/MDS/1098029/2022 | 2022-09-27 | ST202209432223 | 2022-09-17 | P/FVC/MDS/1097974/2022 | 2022-09-27
2453 | KANAA2 | KANAA2 |  |  |  | ROTN | Ascend | - | - |  |  |  | KANAA2 | 4G_FD900_KANAA2 | 4G_FD2100_KANAA2 | 4G_TD_KANAA2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442410 | 2022-09-18 | P/FVC/MDS/1098068/2022 | 2022-09-27 | ST202209446171 | 2022-09-19 | P/FVC/MDS/1098156/2022 | 2022-09-27 | ST202209432366 | 2022-09-17 | P/FVC/MDS/1098007/2022 | 2022-09-27 | ST202209431579 | 2022-09-17 | P/FVC/MDS/1097938/2022 | 2022-09-27
2454 | THPBR2 | THPBR2 |  |  |  | ROTN | ATC | TN/TA/AT/23464 | T22TN05779 |  |  |  | THPBR2 | 4G_FD900_THPBR2 | 4G_FD2100_THPBR2 | 4G_TD_THPBR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209485758 | 2022-09-27 | P/FVC/MDS/1101236/2022 | 2022-10-10 | ST202209492890 | 2022-09-28 | P/FVC/MDS/1101405/2022 | 2022-10-10 | ST202212858201 | 2022-12-27 | 0 |  | ST202209483706 | 2022-09-26 | P/FBW/MDS/1101129/2022 | 2022-10-10
2455 | PLAGR2 | PLAGR2 |  |  |  | ROTN | ATC | TN/DH/AT/23467 | T22TN05782 |  |  |  | PLAGR2 | 4G_FD900_PLAGR2 | 4G_FD2100_PLAGR2 | 4G_TD_PLAGR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486466 | 2022-09-27 | P/FVC/MDS/1101273/2022 | 2022-10-10 | ST202209493301 | 2022-09-28 | P/FVC/MDS/1101442/2022 | 2022-10-10 |  |  |  |  | ST202209484157 | 2022-09-26 | P/FBW/MDS/1101166/2022 | 2022-10-10
2456 | SMRYP2 | SMRYP2 |  |  |  | ROTN | Indus | IN-3149789 | R/NN-682539 |  |  |  | SMRYP2 | 4G_FD900_SMRYP2 | 4G_FD2100_SMRYP2 | 4G_TD_SMRYP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486374 | 2022-09-27 | P/FVC/MDS/1101258/2022 | 2022-10-10 | ST202209493173 | 2022-09-28 | P/FVC/MDS/1101427/2022 | 2022-10-10 | ST202209487291 | 2022-09-27 | P/FVC/MDS/1101314/2022 | 2022-10-10 | ST202209484062 | 2022-09-26 | P/FBW/MDS/1101151/2022 | 2022-10-10
2457 | SMJLM2 | SMJLM2 |  |  |  | ROTN | Indus | IN-3149814 | R/NN-682561 |  |  |  | SMJLM2 | 4G_FD900_SMJLM2 | 4G_FD2100_SMJLM2 | 4G_TD_SMJLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486316 | 2022-09-27 | P/FVC/MDS/1101247/2022 | 2022-10-10 | ST202209493076 | 2022-09-28 | P/FVC/MDS/1101416/2022 | 2022-10-10 |  |  |  |  | ST202209484016 | 2022-09-26 | P/FBW/MDS/1101140/2022 | 2022-10-10
2458 | KONGH2 | KONGH2 |  |  |  | ROTN | ATC | TN/DH/AT/23468 | T22TN05783 |  |  |  | KONGH2 | 4G_FD900_KONGH2 | 4G_FD2100_KONGH2 | 4G_TD_KONGH2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442520 | 2022-09-18 | P/FVC/MDS/1098086/2022 | 2022-09-27 | ST202209446525 | 2022-09-19 | P/FVC/MDS/1098174/2022 | 2022-09-27 | ST202209432522 | 2022-09-17 | P/FVC/MDS/1098014/2022 | 2022-09-27 | ST202209431915 | 2022-09-17 | P/FVC/MDS/1097956/2022 | 2022-09-27
2459 | PRDI59 | PRDI59 |  |  |  | ROTN | Indus | IN-3149847 | R/NN-672909 |  |  |  | PRDI59 | 4G_FD900_PRDI59 | 4G_FD2100_PRDI59 | 4G_TD_PRDI59 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487143 | 2022-09-27 | P/FVC/MDS/1101535/2022 | 2022-10-10 | ST202209495879 | 2022-09-29 | P/FVC/MDS/1101478/2022 | 2022-10-10 | ST202209487678 | 2022-09-28 | P/FVC/MDS/1101342/2022 | 2022-10-10 | ST202209484396 | 2022-09-26 | P/FBW/MDS/1101069/2022 | 2022-10-10
2460 | MJNKN2 | MJNKN2 |  |  |  | ROTN | Indus | IN-3149790 | R/NN-682540 |  |  |  | MJNKN2 | 4G_FD900_MJNKN2 | 4G_FD2100_MJNKN2 | 4G_TD_MJNKN2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487144 | 2022-09-27 | P/FVC/MDS/1101536/2022 | 2022-10-10 | ST202209495897 | 2022-09-29 | P/FVC/MDS/1101479/2022 | 2022-10-10 | ST202209487689 | 2022-09-28 | P/FVC/MDS/1101343/2022 | 2022-10-10 | ST202209484399 | 2022-09-26 | P/FBW/MDS/1101070/2022 | 2022-10-10
2461 | VELNP3 | VELNP3 |  |  |  | ROTN | Indus | IN-3150039 | R/NN-682825 |  |  |  | VELNP3 | 4G_FD900_VELNP3 | 4G_FD2100_VELNP3 | 4G_TD_VELNP3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209487122 | 2022-09-27 | P/FVC/MDS/1101529/2022 | 2022-10-10 | ST202209495669 | 2022-09-29 | P/FVC/MDS/1101472/2022 | 2022-10-10 | ST202209487372 | 2022-09-27 | P/FVC/MDS/1101340/2022 | 2022-10-10 | ST202209484382 | 2022-09-26 | P/FBW/MDS/1101063/2022 | 2022-10-10
2462 | KNJMT2 | KNJMT2 |  |  |  | ROTN | Indus | IN-3149791 | R/NN-682541 |  |  |  | KNJMT2 | 4G_FD900_KNJMT2 | 4G_FD2100_KNJMT2 | 4G_TD_KNJMT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486556 | 2022-09-27 | P/FVC/MDS/1101283/2022 | 2022-10-10 | ST202209493390 | 2022-09-28 | P/FVC/MDS/1101452/2022 | 2022-10-10 | ST202209487343 | 2022-09-27 | P/FVC/MDS/1101327/2022 | 2022-10-10 | ST202209484206 | 2022-09-26 | P/FBW/MDS/1101176/2022 | 2022-10-10
2463 | ATMRV2 | ATMRV2 |  |  |  | ROTN | Indus | IN-3149846 | R/NN-682606 |  |  |  | ATMRV2 | 4G_FD900_ATMRV2 | 4G_FD2100_ATMRV2 | 4G_TD_ATMRV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486665 | 2022-09-27 | P/FVC/MDS/1101512/2022 | 2022-10-10 | ST202209495068 | 2022-09-29 | P/FVC/MDS/1101455/2022 | 2022-10-10 |  |  |  |  | ST202209484208 | 2022-09-26 | P/FBW/MDS/1101178/2022 | 2022-10-10
2464 | POLPM2 | POLPM2 |  |  |  | ROTN | ATC | TN/ER/AT/23472 | TN/ER/AT/23472 |  |  |  | POLPM2 | 4G_FD900_POLPM2 | 4G_FD2100_POLPM2 | 4G_TD_POLPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487149 | 2022-09-27 | P/FVC/MDS/1101538/2022 | 2022-10-10 | ST202209495918 | 2022-09-29 | P/FVC/MDS/1101481/2022 | 2022-10-10 |  |  |  |  | ST202209484401 | 2022-09-26 | P/FBW/MDS/1101072/2022 | 2022-10-10
2465 | NARPI2 | NARPI2 |  |  |  | ROTN | Indus | IN-3149852 | R/NN-682617 |  |  |  | NARPI2 | 4G_FD900_NARPI2 | 4G_FD2100_NARPI2 | 4G_TD_NARPI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486666 | 2022-09-27 | P/FVC/MDS/1101513/2022 | 2022-10-10 | ST202209495069 | 2022-09-29 | P/FVC/MDS/1101456/2022 | 2022-10-10 |  |  |  |  | ST202209484231 | 2022-09-26 | P/FBW/MDS/1101179/2022 | 2022-10-10
2466 | ORVND2 | ORVND2 |  |  |  | ROTN | ATC | TN/NM/AT/23473 | T22TN05788 |  |  |  | ORVND2 | 4G_FD900_ORVND2 | 4G_FD2100_ORVND2 | 4G_TD_ORVND2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486456 | 2022-09-27 | P/FVC/MDS/1101272/2022 | 2022-10-10 | ST202209493283 | 2022-09-28 | P/FVC/MDS/1101441/2022 | 2022-10-10 | ST202209487302 | 2022-09-27 | P/FVC/MDS/1101317/2022 | 2022-10-10 | ST202209484145 | 2022-09-26 | P/FBW/MDS/1101165/2022 | 2022-10-10
2467 | SNTKD2 | SNTKD2 |  |  |  | ROTN | Indus | IN-3149868 | R/NN-682638 |  |  |  | SNTKD2 | 4G_FD900_SNTKD2 | 4G_FD2100_SNTKD2 | 4G_TD_SNTKD2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209442785 | 2022-09-19 | P/FVC/MDS/1098121/2022 | 2022-09-27 | ST202209447434 | 2022-09-19 | P/FVC/MDS/1098208/2022 | 2022-09-27 | ST202209433029 | 2022-09-17 | P/FVC/MDS/1098033/2022 | 2022-09-27 | ST202209483982 | 2022-09-26 | P/FBW/MDS/1101134/2022 | 2022-10-10
2468 | VADGI2 | VADGI2 |  |  |  | ROTN | ATC | TN/VI/AT/23474 | T22TN05789 |  |  |  | VADGI2 | 4G_FD900_VADGI2 | 4G_FD2100_VADGI2 | 4G_TD_VADGI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486455 | 2022-09-27 | P/FVC/MDS/1101271/2022 | 2022-10-10 | ST202209493282 | 2022-09-28 | P/FVC/MDS/1101440/2022 | 2022-10-10 |  |  |  |  | ST202209484144 | 2022-09-26 | P/FBW/MDS/1101164/2022 | 2022-10-10
2469 | SHBAR2 | SHBAR2 |  |  |  | ROTN | Indus | IN-3149853 | R/NN-682622 |  |  |  | SHBAR2 | 4G_FD900_SHBAR2 | 4G_FD2100_SHBAR2 | 4G_TD_SHBAR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209487148 | 2022-09-27 | P/FVC/MDS/1101537/2022 | 2022-10-10 | ST202209495898 | 2022-09-29 | P/FVC/MDS/1101480/2022 | 2022-10-10 |  |  |  |  | ST202209484400 | 2022-09-26 | P/FBW/MDS/1101071/2022 | 2022-10-10
2470 | PNJPI2 | PNJPI2 |  |  |  | ROTN | Indus | IN-3150143 | R/NN-682544 |  |  |  | PNJPI2 | 4G_FD900_PNJPI2 | 4G_FD2100_PNJPI2 | 4G_TD_PNJPI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486394 | 2022-09-27 | P/FVC/MDS/1101259/2022 | 2022-10-10 | ST202209493174 | 2022-09-28 | P/FVC/MDS/1101428/2022 | 2022-10-10 | ST202209487292 | 2022-09-27 | P/FVC/MDS/1101315/2022 | 2022-10-10 | ST202209484067 | 2022-09-26 | P/FBW/MDS/1101152/2022 | 2022-10-10
2471 | VPDAI3 | VPDAI3 |  |  |  | ROTN | Indus | IN-1030622 | R/RES-512816 |  |  |  | VPDAI3 | 4G_FD900_VPDAI3 | 4G_FD2100_VPDAI3 | 4G_TD_VPDAI3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405539 | 2022-09-09 | P/FVC/MDS/1096602/2022 | 2022-09-16 | ST202209406239 | 2022-09-09 | P/FVC/MDS/1096511/2022 | 2022-09-16 | ST202209402080 | 2022-09-08 | P/FVC/MDS/1096434/2022 | 2022-09-16 | ST202209400236 | 2022-09-08 | P/FVC/MDS/1096416/2022 | 2022-09-16
2472 | AMWAR4 | AMWAR4 |  |  |  | ROTN | Indus | IN-1031086 | R/RES-512774 |  |  |  | AMWAR4 | 4G_FD900_AMWAR4 | 4G_FD2100_AMWAR4 | 4G_TD_AMWAR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405523 | 2022-09-09 | P/FVC/MDS/1096598/2022 | 2022-09-16 | ST202209406202 | 2022-09-09 | P/FVC/MDS/1096507/2022 | 2022-09-16 |  |  |  |  | ST202209400204 | 2022-09-08 | P/FVC/MDS/1096412/2022 | 2022-09-16
2473 | TPKIT2 | TPKIT2 |  |  |  | ROTN | Indus | IN-3149817 | R/NN-682569 |  |  |  | TPKIT2 | 4G_FD900_TPKIT2 | 4G_FD2100_TPKIT2 | 4G_TD_TPKIT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209486664 | 2022-09-27 | P/FVC/MDS/1101511/2022 | 2022-10-10 | ST202209493419 | 2022-09-28 | P/FVC/MDS/1101453/2022 | 2022-10-10 |  |  |  |  | ST202209484207 | 2022-09-26 | P/FBW/MDS/1101177/2022 | 2022-10-10
2474 | PALYM2 | PALYM2 |  |  |  | ROTN | ATC | TN/DH/AT/23477 | T22TN05792 |  |  |  | PALYM2 | 4G_FD900_PALYM2 | 4G_FD2100_PALYM2 | 4G_TD_PALYM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442771 | 2022-09-19 | P/FVC/MDS/1098110/2022 | 2022-09-27 | ST202209447420 | 2022-09-19 | P/FVC/MDS/1098198/2022 | 2022-09-27 |  |  |  |  | ST202209432224 | 2022-09-17 | P/FVC/MDS/1097975/2022 | 2022-09-27
2475 | INDNR2 | INDNR2 |  |  |  | ROTN | ATC | TN/ER/AT/23478 | T22TN05793 |  |  |  | INDNR2 | 4G_FD900_INDNR2 | 4G_FD2100_INDNR2 | 4G_TD_INDNR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486467 | 2022-09-27 | P/FVC/MDS/1101274/2022 | 2022-10-10 | ST202209493303 | 2022-09-28 | P/FVC/MDS/1101443/2022 | 2022-10-10 | ST202209487303 | 2022-09-27 | P/FVC/MDS/1101318/2022 | 2022-10-10 | ST202209484158 | 2022-09-26 | P/FBW/MDS/1101167/2022 | 2022-10-10
2476 | KTVMP2 | KTVMP2 |  |  |  | ROTN | ATC | TN/PU/AT/23479 | T22TN05794 |  |  |  | KTVMP2 | 4G_FD900_KTVMP2 | 4G_FD2100_KTVMP2 | 4G_TD_KTVMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442527 | 2022-09-18 | P/FVC/MDS/1098090/2022 | 2022-09-27 | ST202209446620 | 2022-09-19 | P/FVC/MDS/1098178/2022 | 2022-09-27 |  |  |  |  | ST202209431944 | 2022-09-17 | P/FVC/MDS/1097959/2022 | 2022-09-27
2477 | CHPLM2 | CHPLM2 |  |  |  | ROTN | Indus | IN-1274271 | R/RES-512813 |  |  |  | CHPLM2 | 4G_FD900_CHPLM2 | 4G_FD2100_CHPLM2 | 4G_TD_CHPLM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405229 | 2022-09-09 | P/FVC/MDS/1096593/2022 | 2022-09-16 | ST202209406149 | 2022-09-09 | P/FVC/MDS/1096502/2022 | 2022-09-16 | ST202209401275 | 2022-09-08 | P/FVC/MDS/1096427/2022 | 2022-09-16 | ST202209400139 | 2022-09-08 | P/FVC/MDS/1096408/2022 | 2022-09-16
2478 | UMRYU2 | UMRYU2 |  |  |  | ROTN | Indus | IN-3149794 | R/NN-682545 |  |  |  | UMRYU2 | 4G_FD900_UMRYU2 | 4G_FD2100_UMRYU2 | 4G_TD_UMRYU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209486395 | 2022-09-27 | P/FVC/MDS/1101260/2022 | 2022-10-10 | ST202209493175 | 2022-09-28 | P/FVC/MDS/1101429/2022 | 2022-10-10 | ST202209487800 | 2022-09-28 | P/FVC/MDS/1101353/2022 | 2022-10-10 | ST202209484068 | 2022-09-26 | P/FBW/MDS/1101153/2022 | 2022-10-10
2479 | KGVLU2 | KGVLU2 |  |  |  | ROTN | Indus | IN-1074416 | R/RES-512814 |  |  |  | KGVLU2 | 4G_FD900_KGVLU2 | 4G_FD2100_KGVLU2 | 4G_TD_KGVLU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405230 | 2022-09-09 | P/FVC/MDS/1096594/2022 | 2022-09-16 | ST202209406150 | 2022-09-09 | P/FVC/MDS/1096503/2022 | 2022-09-16 | ST202209401276 | 2022-09-08 | P/FVC/MDS/1096428/2022 | 2022-09-16 | ST202209400153 | 2022-09-08 | P/FVC/MDS/1096409/2022 | 2022-09-16
2480 | URLPT2 | URLPT2 |  |  |  | ROTN | Indus | IN-3149869 | R/NN-682639 |  |  |  | URLPT2 | 4G_FD900_URLPT2 | 4G_FD2100_URLPT2 | 4G_TD_URLPT2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202209485575 | 2022-09-27 | P/FVC/MDS/1101198/2022 | 2022-10-10 | ST202209491793 | 2022-09-28 | P/FVC/MDS/1101368/2022 | 2022-10-10 | ST202209487239 | 2022-09-27 | P/FVC/MDS/1101288/2022 | 2022-10-10 | ST202211758530 | 2022-11-16 | P/FBW/MDS/1116827/2022 | 2022-11-29
2481 | ACHNP2 | ACHNP2 |  |  |  | ROTN | Ascend | - | - |  |  |  | ACHNP2 | 4G_FD900_ACHNP2 | 4G_FD2100_ACHNP2 | 4G_TD_ACHNP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209442430 | 2022-09-18 | P/FVC/MDS/1098073/2022 | 2022-09-27 | ST202209446287 | 2022-09-19 | P/FVC/MDS/1098161/2022 | 2022-09-27 | ST202209432367 | 2022-09-17 | P/FVC/MDS/1098008/2022 | 2022-09-27 | ST202209431615 | 2022-09-17 | P/FVC/MDS/1097942/2022 | 2022-09-27
2482 | VAGIK2 | VAGIK2 |  |  |  | ROTN | ATC | TN/TR/AT/23480 | T22TN05795 |  |  |  | VAGIK2 | 4G_FD900_VAGIK2 | 4G_FD2100_VAGIK2 | 4G_TD_VAGIK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442394 | 2022-09-18 | P/FVC/MDS/1098054/2022 | 2022-09-27 | ST202209445921 | 2022-09-19 | P/FVC/MDS/1098142/2022 | 2022-09-27 | ST202211757912 | 2022-11-22 | P/FVC/MDS/1116754/2022 | 2022-11-29 | ST202209431377 | 2022-09-17 | P/FVC/MDS/1097924/2022 | 2022-09-27
2483 | VLKTI2 | VLKTI2 |  |  |  | ROTN | ATC | TN/SA/AT/23481 | T22TN05796 |  |  |  | VLKTI2 | 4G_FD900_VLKTI2 | 4G_FD2100_VLKTI2 | 4G_TD_VLKTI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442772 | 2022-09-19 | P/FVC/MDS/1098111/2022 | 2022-09-27 | ST202209447421 | 2022-09-19 | P/FVC/MDS/1098199/2022 | 2022-09-27 |  |  |  |  | ST202209432276 | 2022-09-17 | P/FVC/MDS/1097976/2022 | 2022-09-27
2484 | VDGPI2 | VDGPI2 |  |  |  | ROTN | Indus | IN-1059252 | R/RES-512806 |  |  |  | VDGPI2 | 4G_FD900_VDGPI2 | 4G_FD2100_VDGPI2 | 4G_TD_VDGPI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209405241 | 2022-09-09 | P/FVC/MDS/1096596/2022 | 2022-09-16 | ST202209406174 | 2022-09-09 | P/FVC/MDS/1096505/2022 | 2022-09-16 |  |  |  |  | ST202209400203 | 2022-09-08 | P/FVC/MDS/1096411/2022 | 2022-09-16
2485 | OTNGP2 | OTNGP2 |  |  |  | ROTN | Indus | IN-3149855 | R/NN-682625 |  |  |  | OTNGP2 | 4G_FD900_OTNGP2 | 4G_FD2100_OTNGP2 | 4G_TD_OTNGP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442784 | 2022-09-19 | P/FVC/MDS/1098120/2022 | 2022-09-27 | ST202209447432 | 2022-09-19 | P/FVC/MDS/1098207/2022 | 2022-09-27 |  |  |  |  | ST202209432402 | 2022-09-17 | P/FVC/MDS/1097985/2022 | 2022-09-27
2486 | MNGPI2 | MNGPI2 |  |  |  | ROTN | Indus | IN-3149797 | R/NN-682549 |  |  |  | MNGPI2 | 4G_FD900_MNGPI2 | 4G_FD2100_MNGPI2 | 4G_TD_MNGPI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209485620 | 2022-09-27 | P/FVC/MDS/1101204/2022 | 2022-10-10 | ST202209491844 | 2022-09-28 | P/FVC/MDS/1101374/2022 | 2022-10-10 | ST202209487246 | 2022-09-27 | P/FVC/MDS/1101291/2022 | 2022-10-10 | ST202209483457 | 2022-09-26 | P/FBW/MDS/1101101/2022 | 2022-10-10
2487 | KDSLM2 | KDSLM2 |  |  |  | ROTN | ATC | TN/SA/AT/23482 | T22TN05797 |  |  |  | KDSLM2 | 4G_FD900_KDSLM2 | 4G_FD2100_KDSLM2 | 4G_TD_KDSLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442519 | 2022-09-18 | P/FVC/MDS/1098085/2022 | 2022-09-27 | ST202209446524 | 2022-09-19 | P/FVC/MDS/1098173/2022 | 2022-09-27 |  |  |  |  | ST202209431888 | 2022-09-17 | P/FVC/MDS/1097955/2022 | 2022-09-27
2488 | UTHIG2 | UTHIG2 |  |  |  | ROTN | ATC | TN/NM/AT/23483 | T22TN05798 |  |  |  | UTHIG2 | 4G_FD900_UTHIG2 | 4G_FD2100_UTHIG2 | 4G_TD_UTHIG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202209442575 | 2022-09-18 | P/FVC/MDS/1098096/2022 | 2022-09-27 | ST202209446711 | 2022-09-19 | P/FVC/MDS/1098184/2022 | 2022-09-27 |  |  |  |  | ST202209432047 | 2022-09-17 | P/FVC/MDS/1097963/2022 | 2022-09-27
2489 | SVKI85 | SVKI85 |  |  |  | ROTN | ATC | TN/MU/TN/13620 | - |  |  |  | SVKI85 | 4G_FD900_SVKI85 | 4G_FD2100_SVKI85 | 4G_TD_SVKI85 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539102 | 2022-10-08 | P/FVC/MDS/1114031/2022 | 2022-10-21 | ST202210538105 | 2022-10-08 | P/FVC/MDS/1113845/2022 | 2022-10-21 | ST202210538349 | 2022-10-08 | P/FVC/MDS/1113881/2022 | 2022-10-21 | ST202210534791 | 2022-10-06 | P/FBW/MDS/1113682/2022 | 2022-10-21
2490 | TIR436 | TIR436 | Tiruppur | Coimbatore |  | ROTN | Airtel | - | - |  | SR | 2022-09-29 | TIR436 | 4G_FD900_TIR436 | 4G_FD2100_TIR436 | 4G_TD_TIR436 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538898 | 2022-10-08 | P/FVC/MDS/1113963/2022 | 2022-10-21 | ST202210537729 | 2022-10-07 | P/FVC/MDS/1113776/2022 | 2022-10-21 |  |  |  |  | ST202210534959 | 2022-10-06 | P/FBW/MDS/1113696/2022 | 2022-10-21
2491 | AZHAG2 | AZHAG2 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-09-30 | AZHAG2 | 4G_FD900_AZHAG2 | 4G_FD2100_AZHAG2 | 4G_TD_AZHAG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539026 | 2022-10-08 | P/FVC/MDS/1113987/2022 | 2022-10-21 | ST202210538225 | 2022-10-08 | P/FVC/MDS/1113850/2022 | 2022-10-21 |  |  |  |  | ST202210535021 | 2022-10-06 | P/FBW/MDS/1113720/2022 | 2022-10-21
2492 | NAJUK3 | NAJUK3 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/23389 | T22TN05322 |  | SO | 2022-09-29 | NAJUK3 | 4G_FD900_NAJUK3 | 4G_FD2100_NAJUK3 | 4G_TD_NAJUK3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538841 | 2022-10-08 | P/FVC/MDS/1113950/2022 | 2022-10-21 | ST202210537305 | 2022-10-07 | P/FVC/MDS/1113763/2022 | 2022-10-21 |  |  |  |  | ST202210534909 | 2022-10-06 | P/FBW/MDS/1113683/2022 | 2022-10-21
2493 | TRKLB2 | TRKLB2 | Thiruvarur | Trichy |  | ROTN | Summit | I-TN-KDVS-ENB-9024 | SR-TN000947 |  | On Air | 2022-09-30 | TRKLB2 | 4G_FD900_TRKLB2 | 4G_FD2100_TRKLB2 | 4G_TD_TRKLB2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539005 | 2022-10-08 | P/FVC/MDS/1113978/2022 | 2022-10-21 | ST202210537803 | 2022-10-07 | P/FVC/MDS/1113792/2022 | 2022-10-21 |  |  |  |  | ST202210534999 | 2022-10-06 | P/FBW/MDS/1113711/2022 | 2022-10-21
2494 | ETPLK2 | ETPLK2 | Thanjavur | Trichy |  | ROTN | Summit | I-TN-PTKT-ENB-9056 | SR-TN000956 |  | On Air | 2022-09-30 | ETPLK2 | 4G_FD900_ETPLK2 | 4G_FD2100_ETPLK2 | 4G_TD_ETPLK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539004 | 2022-10-08 | P/FVC/MDS/1113977/2022 | 2022-10-21 | ST202210537802 | 2022-10-07 | P/FVC/MDS/1113791/2022 | 2022-10-21 |  |  |  |  | ST202210534995 | 2022-10-06 | P/FBW/MDS/1113710/2022 | 2022-10-21
2495 | SLM427 | SLM427 | Salem | Vellore |  | ROTN | Summit | I-TN-SLEM-ENB-9062 | SR-TN001116 |  | On Air | 2022-09-30 | SLM427 | 4G_FD900_SLM427 | 4G_FD2100_SLM427 | 4G_TD_SLM427 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539058 | 2022-10-08 | P/FVC/MDS/1114007/2022 | 2022-10-21 | ST202210537858 | 2022-10-07 | P/FVC/MDS/1113821/2022 | 2022-10-21 |  |  |  |  | ST202210535557 | 2022-10-07 | P/FBW/MDS/1113740/2022 | 2022-10-21
2496 | ACPKM6 | ACPKM6 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-MDRT-ENB-9071 | SR-TN001117 |  | On Air | 2022-09-30 | ACPKM6 | 4G_FD900_ACPKM6 | 4G_FD2100_ACPKM6 | 4G_TD_ACPKM6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539065 | 2022-10-08 | P/FVC/MDS/1114014/2022 | 2022-10-21 | ST202210537871 | 2022-10-07 | P/FVC/MDS/1113828/2022 | 2022-10-21 |  |  |  |  | ST202210535593 | 2022-10-07 | P/FBW/MDS/1113747/2022 | 2022-10-21
2497 | VERMG2 | VERMG2 | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-PLPU-ENB-9034 | SR-TN001139 |  | On Air | 2022-09-29 | VERMG2 | 4G_FD900_VERMG2 | 4G_FD2100_VERMG2 | 4G_TD_VERMG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538995 | 2022-10-08 | P/FVC/MDS/1113975/2022 | 2022-10-21 | ST202210537799 | 2022-10-07 | P/FVC/MDS/1113789/2022 | 2022-10-21 |  |  |  |  | ST202210534990 | 2022-10-06 | P/FBW/MDS/1113708/2022 | 2022-10-21
2498 | TKLRR4 | TKLRR4 | Tiruppur | Coimbatore |  | ROTN | Summit | I-TN-TAVF-ENB-9002 | SR-TN001140 |  | On Air | 2022-09-29 | TKLRR4 | 4G_FD900_TKLRR4 | 4G_FD2100_TKLRR4 | 4G_TD_TKLRR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538986 | 2022-10-08 | P/FVC/MDS/1113974/2022 | 2022-10-21 | ST202210537798 | 2022-10-07 | P/FVC/MDS/1113788/2022 | 2022-10-21 |  |  |  |  | ST202210534989 | 2022-10-06 | P/FBW/MDS/1113707/2022 | 2022-10-21
2499 | KADPI2 | KADPI2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3152436 | R/NN-685408 |  | On Air | 2022-09-29 | KADPI2 | 4G_FD900_KADPI2 | 4G_FD2100_KADPI2 | 4G_TD_KADPI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538880 | 2022-10-08 | P/FVC/MDS/1113958/2022 | 2022-10-21 | ST202210537365 | 2022-10-07 | P/FVC/MDS/1113771/2022 | 2022-10-21 |  |  |  |  | ST202210534949 | 2022-10-06 | P/FBW/MDS/1113691/2022 | 2022-10-21
2500 | MULMP2 | MULMP2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-EROD-ENB-9116 | SR-TN001141 |  | On Air | 2022-09-29 | MULMP2 | 4G_FD900_MULMP2 | 4G_FD2100_MULMP2 | 4G_TD_MULMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538996 | 2022-10-08 | P/FVC/MDS/1113976/2022 | 2022-10-21 | ST202210537800 | 2022-10-07 | P/FVC/MDS/1113790/2022 | 2022-10-21 |  |  |  |  | ST202210534994 | 2022-10-06 | P/FBW/MDS/1113709/2022 | 2022-10-21
2501 | PLARK2 | PLARK2 | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TVLR-ENB-9085 | SR-TN001142 |  | On Air | 2022-09-30 | PLARK2 | 4G_FD900_PLARK2 | 4G_FD2100_PLARK2 | 4G_TD_PLARK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539055 | 2022-10-08 | P/FVC/MDS/1114004/2022 | 2022-10-21 | ST202210537853 | 2022-10-07 | P/FVC/MDS/1113818/2022 | 2022-10-21 |  |  |  |  | ST202210535550 | 2022-10-07 | P/FBW/MDS/1113737/2022 | 2022-10-21
2502 | SELAI2 | SELAI2 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-09-29 | SELAI2 | 4G_FD900_SELAI2 | 4G_FD2100_SELAI2 | 4G_TD_SELAI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538944 | 2022-10-08 | P/FVC/MDS/1113969/2022 | 2022-10-21 | ST202210537741 | 2022-10-07 | P/FVC/MDS/1113782/2022 | 2022-10-21 |  |  |  |  | ST202210534976 | 2022-10-06 | P/FBW/MDS/1113701/2022 | 2022-10-21
2503 | KDUVL2 | KDUVL2 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-09-29 | KDUVL2 | 4G_FD900_KDUVL2 | 4G_FD2100_KDUVL2 | 4G_TD_KDUVL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538919 | 2022-10-08 | P/FVC/MDS/1113967/2022 | 2022-10-21 | ST202210537739 | 2022-10-07 | P/FVC/MDS/1113780/2022 | 2022-10-21 |  |  |  |  | ST202210534968 | 2022-10-06 | P/FBW/MDS/1113700/2022 | 2022-10-21
2504 | WJBD11 | WJBD11 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-URMR-ENB-9053 | SR-TN001144 |  | On Air | 2022-09-30 | WJBD11 | 4G_FD900_WJBD11 | 4G_FD2100_WJBD11 | 4G_TD_WJBD11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539053 | 2022-10-08 | P/FVC/MDS/1114002/2022 | 2022-10-21 | ST202210537850 | 2022-10-07 | P/FVC/MDS/1113816/2022 | 2022-10-21 |  |  |  |  | ST202210535548 | 2022-10-07 | P/FBW/MDS/1113735/2022 | 2022-10-21
2505 | PANIY2 | PANIY2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-CYYR-ENB-9056 | SR-TN001145 |  | On Air | 2022-09-30 | PANIY2 | 4G_FD900_PANIY2 | 4G_FD2100_PANIY2 | 4G_TD_PANIY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539048 | 2022-10-08 | P/FVC/MDS/1113998/2022 | 2022-10-21 | ST202210537838 | 2022-10-07 | P/FVC/MDS/1113812/2022 | 2022-10-21 |  |  |  |  | ST202210535536 | 2022-10-07 | P/FBW/MDS/1113731/2022 | 2022-10-21
2506 | MULKT2 | MULKT2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-TRKD-ENB-9008 | SR-TN001147 |  | On Air | 2022-09-30 | MULKT2 | 4G_FD900_MULKT2 | 4G_FD2100_MULKT2 | 4G_TD_MULKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539046 | 2022-10-08 | P/FVC/MDS/1113997/2022 | 2022-10-21 | ST202210537837 | 2022-10-07 | P/FVC/MDS/1113811/2022 | 2022-10-21 |  |  |  |  | ST202210535535 | 2022-10-07 | P/FBW/MDS/1113730/2022 | 2022-10-21
2507 | CNPTM2 | CNPTM2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-CGLP-ENB-9068 | SR-TN001148 |  | On Air | 2022-09-30 | CNPTM2 | 4G_FD900_CNPTM2 | 4G_FD2100_CNPTM2 | 4G_TD_CNPTM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539061 | 2022-10-08 | P/FVC/MDS/1114010/2022 | 2022-10-21 | ST202210537863 | 2022-10-07 | P/FVC/MDS/1113824/2022 | 2022-10-21 |  |  |  |  | ST202210535569 | 2022-10-07 | P/FBW/MDS/1113743/2022 | 2022-10-21
2508 | ARMPK2 | ARMPK2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-SPRM-ENB-0075 | SR-TN001149 |  | On Air | 2022-09-30 | ARMPK2 | 4G_FD900_ARMPK2 | 4G_FD2100_ARMPK2 | 4G_TD_ARMPK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539054 | 2022-10-08 | P/FVC/MDS/1114003/2022 | 2022-10-21 | ST202210537852 | 2022-10-07 | P/FVC/MDS/1113817/2022 | 2022-10-21 |  |  |  |  | ST202210535549 | 2022-10-07 | P/FBW/MDS/1113736/2022 | 2022-10-21
2509 | PRMBK2 | PRMBK2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-KCPM-ENB-0063 | SR-TN001150 |  | On Air | 2022-09-30 | PRMBK2 | 4G_FD900_PRMBK2 | 4G_FD2100_PRMBK2 | 4G_TD_PRMBK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539052 | 2022-10-08 | P/FVC/MDS/1114001/2022 | 2022-10-21 | ST202210537849 | 2022-10-07 | P/FVC/MDS/1113815/2022 | 2022-10-21 |  |  |  |  | ST202210535541 | 2022-10-07 | P/FBW/MDS/1113734/2022 | 2022-10-21
2510 | VIPDU2 | VIPDU2 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-KCPM-ENB-9065 | SR-TN001151 |  | On Air | 2022-09-30 | VIPDU2 | 4G_FD900_VIPDU2 | 4G_FD2100_VIPDU2 | 4G_TD_VIPDU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539041 | 2022-10-08 | P/FVC/MDS/1113994/2022 | 2022-10-21 | ST202210537833 | 2022-10-07 | P/FVC/MDS/1113808/2022 | 2022-10-21 |  |  |  |  | ST202210535529 | 2022-10-07 | P/FBW/MDS/1113727/2022 | 2022-10-21
2511 | MURGP2 | MURGP2 | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TRTN-ENB-9060 | SR-TN001152 |  | On Air | 2022-09-30 | MURGP2 | 4G_FD900_MURGP2 | 4G_FD2100_MURGP2 | 4G_TD_MURGP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539042 | 2022-10-08 | P/FVC/MDS/1113995/2022 | 2022-10-21 | ST202210537834 | 2022-10-07 | P/FVC/MDS/1113809/2022 | 2022-10-21 |  |  |  |  | ST202210535530 | 2022-10-07 | P/FBW/MDS/1113728/2022 | 2022-10-21
2512 | TAILA2 | TAILA2 | Salem | Vellore |  | ROTN | Summit | I-TN-SLEM-ENB-9075 | SR-TN001153 |  | On Air | 2022-09-30 | TAILA2 | 4G_FD900_TAILA2 | 4G_FD2100_TAILA2 | 4G_TD_TAILA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539049 | 2022-10-08 | P/FVC/MDS/1113999/2022 | 2022-10-21 | ST202210537845 | 2022-10-07 | P/FVC/MDS/1113813/2022 | 2022-10-21 |  |  |  |  | ST202210535539 | 2022-10-07 | P/FBW/MDS/1113732/2022 | 2022-10-21
2513 | JVRNM3 | JVRNM3 | Salem | Vellore |  | ROTN | Summit | I-TN-SLEM-ENB-9074 | SR-TN001154 |  | On Air | 2022-09-30 | JVRNM3 | 4G_FD900_JVRNM3 | 4G_FD2100_JVRNM3 | 4G_TD_JVRNM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539050 | 2022-10-08 | P/FVC/MDS/1114000/2022 | 2022-10-21 | ST202210537846 | 2022-10-07 | P/FVC/MDS/1113814/2022 | 2022-10-21 |  |  |  |  | ST202210535540 | 2022-10-07 | P/FBW/MDS/1113733/2022 | 2022-10-21
2514 | MDMGM2 | MDMGM2 | Dharmapuri | Vellore |  | ROTN | ATC | TN/DH/AT/23516 | T22TN06056 |  | On Air | 2022-09-29 | MDMGM2 | 4G_FD900_MDMGM2 | 4G_FD2100_MDMGM2 | 4G_TD_MDMGM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538985 | 2022-10-08 | P/FVC/MDS/1113973/2022 | 2022-10-21 | ST202210537793 | 2022-10-07 | P/FVC/MDS/1113787/2022 | 2022-10-21 |  |  |  |  | ST202210534983 | 2022-10-06 | P/FBW/MDS/1113706/2022 | 2022-10-21
2515 | GURUO2 | GURUO2 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-09-29 | GURUO2 | 4G_FD900_GURUO2 | 4G_FD2100_GURUO2 | 4G_TD_GURUO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 | 1906-04-18 | ST202210538934 | 2022-10-08 | P/FVC/MDS/1113968/2022 | 2022-10-21 | ST202210537740 | 2022-10-07 | P/FVC/MDS/1113781/2022 | 2022-10-21 |  |  |  |  | ST202211684663 | 2022-11-05 | P/FBW/MDS/1114695/2022 | 2022-11-16
2516 | BMUTL2 | BMUTL2 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-09-29 | BMUTL2 | 4G_FD900_BMUTL2 | 4G_FD2100_BMUTL2 | 4G_TD_BMUTL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538908 | 2022-10-08 | P/FVC/MDS/1113965/2022 | 2022-10-21 | ST202210537735 | 2022-10-07 | P/FVC/MDS/1113778/2022 | 2022-10-21 |  |  |  |  | ST202210534966 | 2022-10-06 | P/FBW/MDS/1113698/2022 | 2022-10-21
2517 | ADIYV2 | ADIYV2 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-09-29 | ADIYV2 | 4G_FD900_ADIYV2 | 4G_FD2100_ADIYV2 | 4G_TD_ADIYV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538945 | 2022-10-08 | P/FVC/MDS/1113970/2022 | 2022-10-21 | ST202210537784 | 2022-10-07 | P/FVC/MDS/1113783/2022 | 2022-10-21 |  |  |  |  | ST202210534977 | 2022-10-06 | P/FBW/MDS/1113702/2022 | 2022-10-21
2518 | TETMP2 | TETMP2 | Cuddalore | Trichy |  | ROTN | Summit | I-TN-CMBM-ENB-9048 | SR-TN001157 |  | On Air | 2022-09-30 | TETMP2 | 4G_FD900_TETMP2 | 4G_FD2100_TETMP2 | 4G_TD_TETMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539067 | 2022-10-08 | P/FVC/MDS/1114016/2022 | 2022-10-21 | ST202210537873 | 2022-10-07 | P/FVC/MDS/1113830/2022 | 2022-10-21 |  |  |  |  | ST202210535595 | 2022-10-07 | P/FBW/MDS/1113749/2022 | 2022-10-21
2519 | CDL107 | CDL107 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-09-29 | CDL107 | 4G_FD900_CDL107 | 4G_FD2100_CDL107 | 4G_TD_CDL107 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538918 | 2022-10-08 | P/FVC/MDS/1113966/2022 | 2022-10-21 | ST202210537736 | 2022-10-07 | P/FVC/MDS/1113779/2022 | 2022-10-21 |  |  |  |  | ST202210534967 | 2022-10-06 | P/FBW/MDS/1113699/2022 | 2022-10-21
2520 | SRPDL2 | SRPDL2 | Tiruvannamalai | Vellore |  | ROTN | ATC | TN/TV/AT/23500 | T22TN06019 |  | On Air | 2022-09-29 | SRPDL2 | 4G_FD900_SRPDL2 | 4G_FD2100_SRPDL2 | 4G_TD_SRPDL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538864 | 2022-10-08 | P/FVC/MDS/1113952/2022 | 2022-10-21 | ST202210537327 | 2022-10-07 | P/FVC/MDS/1113765/2022 | 2022-10-21 |  |  |  |  | ST202210534921 | 2022-10-06 | P/FBW/MDS/1113685/2022 | 2022-10-21
2521 | PKGD12 | PKGD12 | Tirunelveli | Madurai |  | ROTN | ATC | TN/TR/AT/23517 | T22TN06057 |  | On Air | 2022-09-29 | PKGD12 | 4G_FD900_PKGD12 | 4G_FD2100_PKGD12 | 4G_TD_PKGD12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538975 | 2022-10-08 | P/FVC/MDS/1113972/2022 | 2022-10-21 | ST202210537792 | 2022-10-07 | P/FVC/MDS/1113786/2022 | 2022-10-21 |  |  |  |  | ST202210534982 | 2022-10-06 | P/FBW/MDS/1113705/2022 | 2022-10-21
2522 | TVLR54 | TVLR54 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3152409 | R/NN-685370 |  | SO | 2022-09-29 | TVLR54 | 4G_FD900_TVLR54 | 4G_FD2100_TVLR54 | 4G_TD_TVLR54 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538907 | 2022-10-08 | P/FVC/MDS/1113964/2022 | 2022-10-21 | ST202210537734 | 2022-10-07 | P/FVC/MDS/1113777/2022 | 2022-10-21 |  |  |  |  | ST202210534960 | 2022-10-06 | P/FBW/MDS/1113697/2022 | 2022-10-21
2523 | HSR199 | HSR199 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/23519 | T22TN06059 |  | SRB(Surrender) | 2022-09-29 | HSR199 | 4G_FD900_HSR199 | 4G_FD2100_HSR199 | 4G_TD_HSR199 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202210537786 | 2022-10-07 | P/FVC/MDS/1113785/2022 | 2022-10-21 |  |  |  |  | ST202210534981 | 2022-10-06 | P/FBW/MDS/1113704/2022 | 2022-10-21
2524 | KMBLM5 | KMBLM5 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBR-ENB-0458 | SR-TN001160 |  | On Air | 2022-09-30 | KMBLM5 | 4G_FD900_KMBLM5 | 4G_FD2100_KMBLM5 | 4G_TD_KMBLM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539043 | 2022-10-08 | P/FVC/MDS/1113996/2022 | 2022-10-21 | ST202210537836 | 2022-10-07 | P/FVC/MDS/1113810/2022 | 2022-10-21 |  |  |  |  | ST202210535534 | 2022-10-07 | P/FBW/MDS/1113729/2022 | 2022-10-21
2525 | PLDM24 | PLDM24 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3152432 | R/NN-685405 |  | SO | 2022-09-29 | PLDM24 | 4G_FD900_PLDM24 | 4G_FD2100_PLDM24 | 4G_TD_PLDM24 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538896 | 2022-10-08 | P/FVC/MDS/1113961/2022 | 2022-10-21 | ST202210537727 | 2022-10-07 | P/FVC/MDS/1113774/2022 | 2022-10-21 |  |  |  |  | ST202210534955 | 2022-10-06 | P/FBW/MDS/1113694/2022 | 2022-10-21
2526 | DPTNM5 | DPTNM5 | Ramanathapuram | Madurai |  | ROTN | ATC | TN/RA/AT/23520 | T22TN06060 |  | On Air | 2022-09-29 | DPTNM5 | 4G_FD900_DPTNM5 | 4G_FD2100_DPTNM5 | 4G_TD_DPTNM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538870 | 2022-10-08 | P/FVC/MDS/1113954/2022 | 2022-10-21 | ST202210537330 | 2022-10-07 | P/FVC/MDS/1113767/2022 | 2022-10-21 |  |  |  |  | ST202210534923 | 2022-10-06 | P/FBW/MDS/1113687/2022 | 2022-10-21
2527 | MAHA25 | MAHA25 | chennai | chennai |  | chn | Indus | IN-1099848 | R/RES-513201 |  | On air | 2022-09-29 | MAHA25 | 4G_FD900_MAHA25 | 4G_FD2100_MAHA25 | 4G_TD_MAHA25 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538879 | 2022-10-08 | P/FVC/MDS/1113957/2022 | 2022-10-21 | ST202210537346 | 2022-10-07 | P/FVC/MDS/1113770/2022 | 2022-10-21 |  |  |  |  | ST202210534948 | 2022-10-06 | P/FBW/MDS/1113690/2022 | 2022-10-21
2528 | TIRP13 | TIRP13 | chennai | chennai |  | chn | Indus | IN-3152489 | R/NN-685458 |  | SO | 2022-09-29 | TIRP13 | 4G_FD900_TIRP13 | 4G_FD2100_TIRP13 | 4G_TD_TIRP13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538897 | 2022-10-08 | P/FVC/MDS/1113962/2022 | 2022-10-21 | ST202210537728 | 2022-10-07 | P/FVC/MDS/1113775/2022 | 2022-10-21 |  |  |  |  | ST202210534958 | 2022-10-06 | P/FBW/MDS/1113695/2022 | 2022-10-21
2529 | TIRP13 | SLM419 |  |  |  | ROTN | Indus | IN-3152150 | R/NN-685122 |  |  | 2022-09-30 | SLM419 | 4G_FD900_SLM419 | 4G_FD2100_SLM419 | 4G_TD_SLM419 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539015 | 2022-10-08 | P/FVC/MDS/1113981/2022 | 2022-10-21 | ST202210537811 | 2022-10-07 | P/FVC/MDS/1113796/2022 | 2022-10-21 | ST202210538256 | 2022-10-08 | P/FVC/MDS/1113857/2022 | 2022-10-21 | ST202210535007 | 2022-10-06 | P/FBW/MDS/1113714/2022 | 2022-10-21
2530 | TIRP13 | DVKT20 |  |  |  | ROTN | Indus | IN-3136103 | R/NN-662515 |  |  | 2022-09-30 | DVKT20 | 4G_FD900_DVKT20 | 4G_FD2100_DVKT20 | 4G_TD_DVKT20 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202210537809 | 2022-10-07 | P/FVC/MDS/1113794/2022 | 2022-10-21 | ST202210538250 | 2022-10-08 | P/FVC/MDS/1113855/2022 | 2022-10-21 | ST202210549241 | 2022-10-11 | P/FBW/MDS/1113760/2022 | 2022-10-21
2531 | TIRP13 | IRBDU5 |  |  |  | ROTN | Indus | IN-3136124 | R/NN-662634 |  |  | 2022-09-30 | IRBDU5 | 4G_FD900_IRBDU5 | 4G_FD2100_IRBDU5 | 4G_TD_IRBDU5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539011 | 2022-10-08 | P/FVC/MDS/1113980/2022 | 2022-10-21 | ST202210537810 | 2022-10-07 | P/FVC/MDS/1113795/2022 | 2022-10-21 | ST202210538255 | 2022-10-08 | P/FVC/MDS/1113856/2022 | 2022-10-21 | ST202210535001 | 2022-10-06 | P/FBW/MDS/1113713/2022 | 2022-10-21
2532 | TIRP13 | AYAP33 |  |  |  | CHN | Indus | IN-3138345 | R/NN-666916 |  |  | 2022-09-30 | AYAP33 | 4G_FD900_AYAP33 | 4G_FD2100_AYAP33 | 4G_TD_AYAP33 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539010 | 2022-10-08 | P/FVC/MDS/1113979/2022 | 2022-10-21 | ST202210537804 | 2022-10-07 | P/FVC/MDS/1113793/2022 | 2022-10-21 | ST202210538249 | 2022-10-08 | P/FVC/MDS/1113854/2022 | 2022-10-21 | ST202210535000 | 2022-10-06 | P/FBW/MDS/1113712/2022 | 2022-10-21
2533 | TIRP13 | NMROA3 |  |  |  | CHN | ATC | TN/CH/TT/12843 | - |  |  | 2022-09-17 | NMROA3 | 4G_FD900_NMROA3 | 4G_FD2100_NMROA3 | 4G_TD_NMROA3 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202211761155 | 2022-11-25 | P/FVC/MDS/1116884/2022 | 2022-11-29 | ST202209495568 | 2022-09-29 | P/FVC/MDS/1101464/2022 | 2022-10-10 | ST202209487358 | 2022-09-27 | P/FVC/MDS/1101332/2022 | 2022-10-10 | ST202209484347 | 2022-09-26 | P/FBW/MDS/1101055/2022 | 2022-10-10
2534 | TIRP13 | PLKOL2 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-09-30 | PLKOL2 | 4G_FD900_PLKOL2 | 4G_FD2100_PLKOL2 | 4G_TD_PLKOL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539018 | 2022-10-08 | P/FVC/MDS/1113983/2022 | 2022-10-21 | ST202210537815 | 2022-10-07 | P/FVC/MDS/1113798/2022 | 2022-10-21 |  |  |  |  | ST202210535009 | 2022-10-06 | P/FBW/MDS/1113716/2022 | 2022-10-21
2535 | TIRP13 | IRMBP2 |  |  |  | ROTN | Summit | I-TN-VLUR-ENB-9054 | SR-TN001104 |  |  | 2022-09-30 | IRMBP2 | 4G_FD900_IRMBP2 | 4G_FD2100_IRMBP2 | 4G_TD_IRMBP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539062 | 2022-10-08 | P/FVC/MDS/1114011/2022 | 2022-10-21 | ST202210537864 | 2022-10-07 | P/FVC/MDS/1113825/2022 | 2022-10-21 |  |  |  |  | ST202210535575 | 2022-10-07 | P/FBW/MDS/1113744/2022 | 2022-10-21
2536 | TIRP13 | TPSIK2 |  |  |  | ROTN | Summit | I-TN-OMLR-ENB-9013 | SR-TN001105 |  |  | 2022-09-30 | TPSIK2 | 4G_FD900_TPSIK2 | 4G_FD2100_TPSIK2 | 4G_TD_TPSIK2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539063 | 2022-10-08 | P/FVC/MDS/1114012/2022 | 2022-10-21 | ST202210537867 | 2022-10-07 | P/FVC/MDS/1113826/2022 | 2022-10-21 | ST202210538292 | 2022-10-08 | P/FVC/MDS/1113865/2022 | 2022-10-21 | ST202210535576 | 2022-10-07 | P/FBW/MDS/1113745/2022 | 2022-10-21
2537 | TIRP13 | SINVD2 |  |  |  | ROTN | Summit | I-TN-PLLC-ENB-9108 | SR-TN001108 |  |  | 2022-09-30 | SINVD2 | 4G_FD900_SINVD2 | 4G_FD2100_SINVD2 | 4G_TD_SINVD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539057 | 2022-10-08 | P/FVC/MDS/1114006/2022 | 2022-10-21 | ST202210537857 | 2022-10-07 | P/FVC/MDS/1113820/2022 | 2022-10-21 | ST202211757888 | 2022-11-22 | P/FVC/MDS/1116751/2022 | 2022-11-29 | ST202210535556 | 2022-10-07 | P/FBW/MDS/1113739/2022 | 2022-10-21
2538 | TIRP13 | KLNIV2 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-09-30 | KLNIV2 | 4G_FD900_KLNIV2 | 4G_FD2100_KLNIV2 | 4G_TD_KLNIV2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539019 | 2022-10-08 | P/FVC/MDS/1113984/2022 | 2022-10-21 | ST202210537818 | 2022-10-07 | P/FVC/MDS/1113799/2022 | 2022-10-21 | ST202210538265 | 2022-10-08 | P/FVC/MDS/1113859/2022 | 2022-10-21 | ST202210535016 | 2022-10-06 | P/FBW/MDS/1113717/2022 | 2022-10-21
2539 | TIRP13 | KARSL2 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-09-30 | KARSL2 | 4G_FD900_KARSL2 | 4G_FD2100_KARSL2 | 4G_TD_KARSL2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539024 | 2022-10-08 | P/FVC/MDS/1113985/2022 | 2022-10-21 | ST202210537819 | 2022-10-07 | P/FVC/MDS/1113800/2022 | 2022-10-21 | ST202210538269 | 2022-10-08 | P/FVC/MDS/1113860/2022 | 2022-10-21 | ST202210535017 | 2022-10-06 | P/FBW/MDS/1113718/2022 | 2022-10-21
2540 | TIRP13 | KRPUR2 |  |  |  | ROTN | ATC | TN/SA/AT/23420 | T22TN05735 |  |  | 2022-09-30 | KRPUR2 | 4G_FD900_KRPUR2 | 4G_FD2100_KRPUR2 | 4G_TD_KRPUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539028 | 2022-10-08 | P/FVC/MDS/1113989/2022 | 2022-10-21 | ST202210537823 | 2022-10-07 | P/FVC/MDS/1113803/2022 | 2022-10-21 | ST202210538283 | 2022-10-08 | P/FVC/MDS/1113862/2022 | 2022-10-21 | ST202210535023 | 2022-10-06 | P/FBW/MDS/1113722/2022 | 2022-10-21
2541 | TIRP13 | GRYNR2 |  |  |  | ROTN | Indus | IN-3149494 | R/NN-682263 |  |  | 2022-09-29 | GRYNR2 | 4G_FD900_GRYNR2 | 4G_FD2100_GRYNR2 | 4G_TD_GRYNR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210538885 | 2022-10-08 | P/FVC/MDS/1113959/2022 | 2022-10-21 | ST202210537366 | 2022-10-07 | P/FVC/MDS/1113772/2022 | 2022-10-21 | ST202210538244 | 2022-10-08 | P/FVC/MDS/1113852/2022 | 2022-10-21 | ST202210534953 | 2022-10-06 | P/FBW/MDS/1113692/2022 | 2022-10-21
2542 | TIRP13 | GUMNR2 |  |  |  | ROTN | ATC | TN/DH/AT/23422 | T22TN05737 |  |  | 2022-09-29 | GUMNR2 | 4G_FD900_GUMNR2 | 4G_FD2100_GUMNR2 | 4G_TD_GUMNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538863 | 2022-10-08 | P/FVC/MDS/1113951/2022 | 2022-10-21 | ST202210537306 | 2022-10-07 | P/FVC/MDS/1113764/2022 | 2022-10-21 | ST202210538243 | 2022-10-08 | P/FVC/MDS/1113851/2022 | 2022-10-21 | ST202210534910 | 2022-10-06 | P/FBW/MDS/1113684/2022 | 2022-10-21
2543 | TIRP13 | ANJHI2 |  |  |  | ROTN | ATC | TN/DH/AT/23423 | T22TN05738 |  |  | 2022-09-29 | ANJHI2 | 4G_FD900_ANJHI2 | 4G_FD2100_ANJHI2 | 4G_TD_ANJHI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210538875 | 2022-10-08 | P/FVC/MDS/1113956/2022 | 2022-10-21 | ST202210537345 | 2022-10-07 | P/FVC/MDS/1113769/2022 | 2022-10-21 |  |  |  |  | ST202210534937 | 2022-10-06 | P/FBW/MDS/1113689/2022 | 2022-10-21
2544 | TIRP13 | VENKM2 |  |  |  | ROTN | ATC | TN/DH/AT/23425 | T22TN05740 |  |  | 2022-09-30 | VENKM2 | 4G_FD900_VENKM2 | 4G_FD2100_VENKM2 | 4G_TD_VENKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539038 | 2022-10-08 | P/FVC/MDS/1113992/2022 | 2022-10-21 | ST202210537828 | 2022-10-07 | P/FVC/MDS/1113806/2022 | 2022-10-21 |  |  |  |  | ST202210535031 | 2022-10-06 | P/FBW/MDS/1113725/2022 | 2022-10-21
2545 | TIRP13 | AYGDP2 |  |  |  | ROTN | Indus | IN-3149540 | R/NN-682291 |  |  | 2022-09-29 | AYGDP2 | 4G_FD900_AYGDP2 | 4G_FD2100_AYGDP2 | 4G_TD_AYGDP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210538886 | 2022-10-08 | P/FVC/MDS/1113960/2022 | 2022-10-21 | ST202210537367 | 2022-10-07 | P/FVC/MDS/1113773/2022 | 2022-10-21 | ST202210538245 | 2022-10-08 | P/FVC/MDS/1113853/2022 | 2022-10-21 | ST202210534954 | 2022-10-06 | P/FBW/MDS/1113693/2022 | 2022-10-21
2546 | TIRP13 | JNKLR2 |  |  |  | ROTN | ATC | TN/DH/AT/23436 | T22TN05751 |  |  | 2022-09-30 | JNKLR2 | 4G_FD900_JNKLR2 | 4G_FD2100_JNKLR2 | 4G_TD_JNKLR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539039 | 2022-10-08 | P/FVC/MDS/1113993/2022 | 2022-10-21 | ST202210537829 | 2022-10-07 | P/FVC/MDS/1113807/2022 | 2022-10-21 |  |  |  |  | ST202210535528 | 2022-10-07 | P/FBW/MDS/1113726/2022 | 2022-10-21
2547 | TIRP13 | MAKRI2 |  |  |  | ROTN | ATC | TN/TR/AT/23440 | T22TN05755 |  |  | 2022-09-30 | MAKRI2 | 4G_FD900_MAKRI2 | 4G_FD2100_MAKRI2 | 4G_TD_MAKRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539032 | 2022-10-08 | P/FVC/MDS/1113990/2022 | 2022-10-21 | ST202210537824 | 2022-10-07 | P/FVC/MDS/1113804/2022 | 2022-10-21 |  |  |  |  | ST202210535029 | 2022-10-06 | P/FBW/MDS/1113723/2022 | 2022-10-21
2548 | TIRP13 | NMSNM2 |  |  |  | ROTN | Summit | I-TN-PLLC-ENB-9047 | SR-TN001113 |  |  | 2022-09-30 | NMSNM2 | 4G_FD900_NMSNM2 | 4G_FD2100_NMSNM2 | 4G_TD_NMSNM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539056 | 2022-10-08 | P/FVC/MDS/1114005/2022 | 2022-10-21 | ST202210537854 | 2022-10-07 | P/FVC/MDS/1113819/2022 | 2022-10-21 | ST202210538291 | 2022-10-08 | P/FVC/MDS/1113864/2022 | 2022-10-21 | ST202210535555 | 2022-10-07 | P/FBW/MDS/1113738/2022 | 2022-10-21
2549 | TIRP13 | VELAK2 |  |  |  | ROTN | Summit | I-TN-BHVN-ENB-9065 | SR-TN001114 |  |  | 2022-09-30 | VELAK2 | 4G_FD900_VELAK2 | 4G_FD2100_VELAK2 | 4G_TD_VELAK2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539064 | 2022-10-08 | P/FVC/MDS/1114013/2022 | 2022-10-21 | ST202210537868 | 2022-10-07 | P/FVC/MDS/1113827/2022 | 2022-10-21 | ST202210538293 | 2022-10-08 | P/FVC/MDS/1113866/2022 | 2022-10-21 | ST202210535577 | 2022-10-07 | P/FBW/MDS/1113746/2022 | 2022-10-21
2550 | TIRP13 | SHPDU2 |  |  |  | ROTN | Indus | IN-3149840 | R/NN-682599 |  |  | 2022-09-30 | SHPDU2 | 4G_FD900_SHPDU2 | 4G_FD2100_SHPDU2 | 4G_TD_SHPDU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539066 | 2022-10-08 | P/FVC/MDS/1114015/2022 | 2022-10-21 | ST202210537872 | 2022-10-07 | P/FVC/MDS/1113829/2022 | 2022-10-21 |  |  |  |  | ST202210535594 | 2022-10-07 | P/FBW/MDS/1113748/2022 | 2022-10-21
2551 | TIRP13 | SAMPI2 |  |  |  | ROTN | ATC | TN/TR/AT/23463 | T22TN05778 |  |  | 2022-09-30 | SAMPI2 | 4G_FD900_SAMPI2 | 4G_FD2100_SAMPI2 | 4G_TD_SAMPI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539027 | 2022-10-08 | P/FVC/MDS/1113988/2022 | 2022-10-21 | ST202210537822 | 2022-10-07 | P/FVC/MDS/1113802/2022 | 2022-10-21 |  |  |  |  | ST202210535022 | 2022-10-06 | P/FBW/MDS/1113721/2022 | 2022-10-21
2552 | TIRP13 | SINTR2 |  |  |  | ROTN | ATC | TN/SA/AT/23469 | T22TN05784 |  |  | 2022-09-30 | SINTR2 | 4G_FD900_SINTR2 | 4G_FD2100_SINTR2 | 4G_TD_SINTR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539033 | 2022-10-08 | P/FVC/MDS/1113991/2022 | 2022-10-21 | ST202210537827 | 2022-10-07 | P/FVC/MDS/1113805/2022 | 2022-10-21 | ST202210538284 | 2022-10-08 | P/FVC/MDS/1113863/2022 | 2022-10-21 | ST202210535030 | 2022-10-06 | P/FBW/MDS/1113724/2022 | 2022-10-21
2553 | TIRP13 | NLTNU2 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-09-30 | NLTNU2 | 4G_FD900_NLTNU2 | 4G_FD2100_NLTNU2 | 4G_TD_NLTNU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539025 | 2022-10-08 | P/FVC/MDS/1113986/2022 | 2022-10-21 | ST202210537820 | 2022-10-07 | P/FVC/MDS/1113801/2022 | 2022-10-21 | ST202210538270 | 2022-10-08 | P/FVC/MDS/1113861/2022 | 2022-10-21 | ST202210535018 | 2022-10-06 | P/FBW/MDS/1113719/2022 | 2022-10-21
2554 | TIRP13 | PDY406 |  |  |  | ROTN | ATC | TN/PO/TT/15118 | - |  |  | 2022-10-03 | PDY406 | 4G_FD900_PDY406 | 4G_FD2100_PDY406 | 4G_TD_PDY406 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539069 | 2022-10-08 | P/FVC/MDS/1114018/2022 | 2022-10-21 | ST202210537877 | 2022-10-07 | P/FVC/MDS/1113832/2022 | 2022-10-21 | ST202210538303 | 2022-10-08 | P/FVC/MDS/1113868/2022 | 2022-10-21 | ST202210535606 | 2022-10-07 | P/FBW/MDS/1113751/2022 | 2022-10-21
2555 | TIRP13 | CNPT14 |  |  |  | ROTN | BSNL | 488 | - |  |  | 2022-10-03 | CNPT14 | 4G_FD900_CNPT14 | 4G_FD2100_CNPT14 | 4G_TD_CNPT14 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539068 | 2022-10-08 | P/FVC/MDS/1114017/2022 | 2022-10-21 | ST202210537876 | 2022-10-07 | P/FVC/MDS/1113831/2022 | 2022-10-21 | ST202210538302 | 2022-10-08 | P/FVC/MDS/1113867/2022 | 2022-10-21 | ST202210535605 | 2022-10-07 | P/FBW/MDS/1113750/2022 | 2022-10-21
2556 | TIR431 | TIR431 | Tiruppur | Coimbatore |  | ROTN | ATC | TN/TI/AT/23489 | T22TN05990 |  | SO | 2022-10-10 | TIR431 | 4G_FD900_TIR431 | 4G_FD2100_TIR431 | 4G_TD_TIR431 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573763 | 2022-10-14 | P/FVC/MDS/1113291/2022 | 2022-10-20 | ST202210574139 | 2022-10-14 | P/FVC/MDS/1113336/2022 | 2022-10-20 | ST202211757955 | 2022-11-22 | P/FVC/MDS/1116760/2022 | 2022-11-29 | ST202210559978 | 2022-10-12 | P/FBW/MDS/1114071/2022 | 2022-10-30
2557 | MELPL2 | MELPL2 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3147858 | R/NN-678670 |  | SO | 2022-10-10 | MELPL2 | 4G_FD900_MELPL2 | 4G_FD2100_MELPL2 | 4G_TD_MELPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572095 | 2022-10-14 | P/FVC/MDS/1113250/2022 | 2022-10-20 | ST202210574061 | 2022-10-14 | P/FVC/MDS/1113318/2022 | 2022-10-20 |  |  |  |  | ST202210559773 | 2022-10-12 | P/FBW/MDS/1114055/2022 | 2022-10-30
2558 | UMPT44 | UMPT44 | Tiruppur | Coimbatore |  | ROTN | Airtel | - | - |  | SO | 2022-10-10 | UMPT44 | 4G_FD900_UMPT44 | 4G_FD2100_UMPT44 | 4G_TD_UMPT44 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572006 | 2022-10-14 | P/FVC/MDS/1113246/2022 | 2022-10-20 | ST202210574057 | 2022-10-14 | P/FVC/MDS/1113314/2022 | 2022-10-20 |  |  |  |  | ST202210559764 | 2022-10-12 | P/FBW/MDS/1114051/2022 | 2022-10-30
2559 | KODYK1 | KODYK1 | Tiruppur | Coimbatore |  | ROTN | Airtel | - | - |  | SO | 2022-10-10 | KODYK1 | 4G_FD900_KODYK1 | 4G_FD2100_KODYK1 | 4G_TD_KODYK1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572123 | 2022-10-14 | P/FVC/MDS/1113252/2022 | 2022-10-20 | ST202210574063 | 2022-10-14 | P/FVC/MDS/1113320/2022 | 2022-10-20 |  |  |  |  | ST202210559828 | 2022-10-12 | P/FBW/MDS/1114057/2022 | 2022-10-30
2560 | KALAM2 | KALAM2 | Viluppuram | Trichy |  | ROTN | Ascend | - | - |  | Drop-Sales Not Required | 2022-10-14 | KALAM2 | 4G_FD900_KALAM2 | 4G_FD2100_KALAM2 | 4G_TD_KALAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572974 | 2022-10-14 | P/FVC/MDS/1113272/2022 | 2022-10-20 | ST202210574714 | 2022-10-15 | P/FVC/MDS/1113357/2022 | 2022-10-20 |  |  |  |  | ST202210569088 | 2022-10-14 | P/FBW/MDS/1114092/2022 | 2022-10-30
2561 | OTIVK2 | OTIVK2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-10-14 | OTIVK2 | 4G_FD900_OTIVK2 | 4G_FD2100_OTIVK2 | 4G_TD_OTIVK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572963 | 2022-10-14 | P/FVC/MDS/1113271/2022 | 2022-10-20 | ST202210574707 | 2022-10-15 | P/FVC/MDS/1113356/2022 | 2022-10-20 |  |  |  |  | ST202210568930 | 2022-10-14 | P/FBW/MDS/1114091/2022 | 2022-10-30
2562 | MDTI47 | MDTI47 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-10-14 | MDTI47 | 4G_FD900_MDTI47 | 4G_FD2100_MDTI47 | 4G_TD_MDTI47 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572988 | 2022-10-14 | P/FVC/MDS/1113274/2022 | 2022-10-20 | ST202210574723 | 2022-10-15 | P/FVC/MDS/1113359/2022 | 2022-10-20 |  |  |  |  | ST202210569103 | 2022-10-14 | P/FBW/MDS/1114094/2022 | 2022-10-30
2563 | MTUPT3 | MTUPT3 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3153658 | R/NN-686716 |  | SO | 2022-10-10 | MTUPT3 | 4G_FD900_MTUPT3 | 4G_FD2100_MTUPT3 | 4G_TD_MTUPT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573064 | 2022-10-14 | P/FVC/MDS/1113287/2022 | 2022-10-20 | ST202210574128 | 2022-10-14 | P/FVC/MDS/1113332/2022 | 2022-10-20 |  |  |  |  | ST202210559963 | 2022-10-12 | P/FBW/MDS/1114067/2022 | 2022-10-30
2564 | KLVLM2 | KLVLM2 | Sivaganga | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-10-14 | KLVLM2 | 4G_FD900_KLVLM2 | 4G_FD2100_KLVLM2 | 4G_TD_KLVLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573003 | 2022-10-14 | P/FVC/MDS/1113276/2022 | 2022-10-20 | ST202210574725 | 2022-10-15 | P/FVC/MDS/1113361/2022 | 2022-10-20 |  |  |  |  | ST202210569141 | 2022-10-14 | P/FBW/MDS/1114096/2022 | 2022-10-30
2565 | VMBD40 | VMBD40 | Vellore | Vellore |  | ROTN | Summit | I-TN-ARKM-ENB-9081 | SR-TN001165 |  | On Air | 2022-10-11 | VMBD40 | 4G_FD900_VMBD40 | 4G_FD2100_VMBD40 | 4G_TD_VMBD40 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539085 | 2022-10-08 | P/FVC/MDS/1114025/2022 | 2022-10-21 | ST202210537890 | 2022-10-07 | P/FVC/MDS/1113839/2022 | 2022-10-21 | ST202210538329 | 2022-10-08 | P/FVC/MDS/1113875/2022 | 2022-10-21 | ST202210534763 | 2022-10-06 | P/FBW/MDS/1113676/2022 | 2022-10-21
2566 | PNGND2 | PNGND2 | Krishnagiri | Vellore |  | ROTN | Ascend | - | - |  | On Air | 2022-10-14 | PNGND2 | 4G_FD900_PNGND2 | 4G_FD2100_PNGND2 | 4G_TD_PNGND2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572975 | 2022-10-14 | P/FVC/MDS/1113273/2022 | 2022-10-20 | ST202210574715 | 2022-10-15 | P/FVC/MDS/1113358/2022 | 2022-10-20 |  |  |  |  | ST202210569089 | 2022-10-14 | P/FBW/MDS/1114093/2022 | 2022-10-30
2567 | TRVNG2 | TRVNG2 | Nagapattinam | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-10-14 | TRVNG2 | 4G_FD900_TRVNG2 | 4G_FD2100_TRVNG2 | 4G_TD_TRVNG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573004 | 2022-10-14 | P/FVC/MDS/1113277/2022 | 2022-10-20 | ST202210574739 | 2022-10-15 | P/FVC/MDS/1113362/2022 | 2022-10-20 |  |  |  |  | ST202210569142 | 2022-10-14 | P/FBW/MDS/1114097/2022 | 2022-10-30
2568 | SLUKD2 | SLUKD2 | Pudukkottai | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-10-14 | SLUKD2 | 4G_FD900_SLUKD2 | 4G_FD2100_SLUKD2 | 4G_TD_SLUKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572989 | 2022-10-14 | P/FVC/MDS/1113275/2022 | 2022-10-20 | ST202210574724 | 2022-10-15 | P/FVC/MDS/1113360/2022 | 2022-10-20 |  |  |  |  | ST202210569107 | 2022-10-14 | P/FBW/MDS/1114095/2022 | 2022-10-30
2569 | MDU533 | MDU533 | Madurai | Madurai |  | ROTN | Summit | I-TN-MDAI-ENB-9001 | SR-TN001115 |  | On Air | 2022-10-10 | MDU533 | 4G_FD900_MDU533 | 4G_FD2100_MDU533 | 4G_TD_MDU533 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539071 | 2022-10-08 | P/FVC/MDS/1114019/2022 | 2022-10-21 | ST202210537879 | 2022-10-07 | P/FVC/MDS/1113833/2022 | 2022-10-21 | ST202210538304 | 2022-10-08 | P/FVC/MDS/1113869/2022 | 2022-10-21 | ST202210534748 | 2022-10-06 | P/FBW/MDS/1113670/2022 | 2022-10-21
2570 | CDBM70 | CDBM70 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-10-14 | CDBM70 | 4G_FD900_CDBM70 | 4G_FD2100_CDBM70 | 4G_TD_CDBM70 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573015 | 2022-10-14 | P/FVC/MDS/1113278/2022 | 2022-10-20 | ST202210574740 | 2022-10-15 | P/FVC/MDS/1113363/2022 | 2022-10-20 |  |  |  |  | ST202210569177 | 2022-10-14 | P/FBW/MDS/1114098/2022 | 2022-10-30
2571 | MDU557 | MDU557 | Madurai | Madurai |  | ROTN | Indus | IN-3153013 | R/NN-685978 |  | SO | 2022-10-10 | MDU557 | 4G_FD900_MDU557 | 4G_FD2100_MDU557 | 4G_TD_MDU557 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573765 | 2022-10-14 | P/FVC/MDS/1113293/2022 | 2022-10-20 | ST202210574649 | 2022-10-15 | P/FVC/MDS/1113338/2022 | 2022-10-20 | ST202212858228 | 2022-12-27 | 0 |  | ST202210559984 | 2022-10-12 | P/FBW/MDS/1114073/2022 | 2022-10-30
2572 | SATH19 | SATH19 | Erode | Coimbatore |  | ROTN | Indus | IN-3140121 | R/NN-669061 |  | SO | 2022-10-14 | SATH19 | 4G_FD900_SATH19 | 4G_FD2100_SATH19 | 4G_TD_SATH19 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573045 | 2022-10-14 | P/FVC/MDS/1113282/2022 | 2022-10-20 | ST202210574766 | 2022-10-15 | P/FVC/MDS/1113367/2022 | 2022-10-20 |  |  |  |  | ST202210569399 | 2022-10-14 | P/FBW/MDS/1114102/2022 | 2022-10-30
2573 | LBKAD2 | LBKAD2 | Perambalur | Trichy |  | ROTN | Indus | IN-3144095 | R/NN-675410 |  | SO | 2022-10-10 | LBKAD2 | 4G_FD900_LBKAD2 | 4G_FD2100_LBKAD2 | 4G_TD_LBKAD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572094 | 2022-10-14 | P/FVC/MDS/1113249/2022 | 2022-10-20 | ST202210574060 | 2022-10-14 | P/FVC/MDS/1113317/2022 | 2022-10-20 |  |  |  |  | ST202210559771 | 2022-10-12 | P/FBW/MDS/1114054/2022 | 2022-10-30
2574 | TRY422 | TRY422 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3144096 | R/NN-675411 |  | SO | 2022-10-14 | TRY422 | 4G_FD900_TRY422 | 4G_FD2100_TRY422 | 4G_TD_TRY422 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573046 | 2022-10-14 | P/FVC/MDS/1113283/2022 | 2022-10-20 | ST202210574775 | 2022-10-15 | P/FVC/MDS/1113368/2022 | 2022-10-20 |  |  |  |  | ST202210569401 | 2022-10-14 | P/FBW/MDS/1114103/2022 | 2022-10-30
2575 | VLODE2 | VLODE2 | Erode | Coimbatore |  | ROTN | Indus | IN-3146559 | R/NN-677511 |  | SO | 2022-10-10 | VLODE2 | 4G_FD900_VLODE2 | 4G_FD2100_VLODE2 | 4G_TD_VLODE2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573779 | 2022-10-14 | P/FVC/MDS/1113295/2022 | 2022-10-20 | ST202210574651 | 2022-10-15 | P/FVC/MDS/1113340/2022 | 2022-10-20 |  |  |  |  | ST202210559997 | 2022-10-12 | P/FBW/MDS/1114075/2022 | 2022-10-30
2576 | TIR515 | TIR515 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3146895 | R/NN-677524 |  | SO | 2022-10-10 | TIR515 | 4G_FD900_TIR515 | 4G_FD2100_TIR515 | 4G_TD_TIR515 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210573778 | 2022-10-14 | P/FVC/MDS/1113294/2022 | 2022-10-20 | ST202210574650 | 2022-10-15 | P/FVC/MDS/1113339/2022 | 2022-10-20 | ST202211757969 | 2022-11-22 | P/FVC/MDS/1116761/2022 | 2022-11-29 | ST202210559996 | 2022-10-12 | P/FBW/MDS/1114074/2022 | 2022-10-30
2577 | POKMP2 | POKMP2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3152442 | R/NN-685415 |  | SO | 2022-10-11 | POKMP2 | 4G_FD900_POKMP2 | 4G_FD2100_POKMP2 | 4G_TD_POKMP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572859 | 2022-10-14 | P/FVC/MDS/1113267/2022 | 2022-10-20 | ST202210574700 | 2022-10-15 | P/FVC/MDS/1113352/2022 | 2022-10-20 |  |  |  |  | ST202210568911 | 2022-10-14 | P/FBW/MDS/1114087/2022 | 2022-10-30
2578 | SMNTM2 | SMNTM2 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/23509 | T22TN06049 |  | On Air | 2022-10-10 | SMNTM2 | 4G_FD900_SMNTM2 | 4G_FD2100_SMNTM2 | 4G_TD_SMNTM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573739 | 2022-10-14 | P/FVC/MDS/1113289/2022 | 2022-10-20 | ST202210574131 | 2022-10-14 | P/FVC/MDS/1113334/2022 | 2022-10-20 |  |  |  |  | ST202210559976 | 2022-10-12 | P/FBW/MDS/1114069/2022 | 2022-10-30
2579 | PULRM2 | PULRM2 | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TVLR-ENB-9115 | SR-TN001143 |  | On Air | 2022-10-11 | PULRM2 | 4G_FD900_PULRM2 | 4G_FD2100_PULRM2 | 4G_TD_PULRM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539092 | 2022-10-08 | P/FVC/MDS/1114028/2022 | 2022-10-21 | ST202210538094 | 2022-10-08 | P/FVC/MDS/1113842/2022 | 2022-10-21 | ST202210538341 | 2022-10-08 | P/FVC/MDS/1113878/2022 | 2022-10-21 | ST202210534776 | 2022-10-06 | P/FBW/MDS/1113679/2022 | 2022-10-21
2580 | SNKPU2 | SNKPU2 | Vellore | Vellore |  | ROTN | ATC | TN/VE/AT/23512 | T22TN06052 |  | On Air | 2022-10-10 | SNKPU2 | 4G_FD900_SNKPU2 | 4G_FD2100_SNKPU2 | 4G_TD_SNKPU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572280 | 2022-10-14 | P/FVC/MDS/1113260/2022 | 2022-10-20 | ST202210574084 | 2022-10-14 | P/FVC/MDS/1113328/2022 | 2022-10-20 |  |  |  |  | ST202210559949 | 2022-10-12 | P/FBW/MDS/1114064/2022 | 2022-10-30
2581 | PYMTR2 | PYMTR2 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/23514 | T22TN06054 |  | On Air | 2022-10-10 | PYMTR2 | 4G_FD900_PYMTR2 | 4G_FD2100_PYMTR2 | 4G_TD_PYMTR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573764 | 2022-10-14 | P/FVC/MDS/1113292/2022 | 2022-10-20 | ST202210574140 | 2022-10-14 | P/FVC/MDS/1113337/2022 | 2022-10-20 |  |  |  |  | ST202210559983 | 2022-10-12 | P/FBW/MDS/1114072/2022 | 2022-10-30
2582 | KLPLM9 | KLPLM9 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBR-ENB-9114 | SR-TN001155 |  | On Air | 2022-10-10 | KLPLM9 | 4G_FD900_KLPLM9 | 4G_FD2100_KLPLM9 | 4G_TD_KLPLM9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539072 | 2022-10-08 | P/FVC/MDS/1114020/2022 | 2022-10-21 | ST202210537881 | 2022-10-07 | P/FVC/MDS/1113834/2022 | 2022-10-21 | ST202210538314 | 2022-10-08 | P/FVC/MDS/1113870/2022 | 2022-10-21 | ST202210534749 | 2022-10-06 | P/FBW/MDS/1113671/2022 | 2022-10-21
2583 | PDIRS2 | PDIRS2 | Erode | Coimbatore |  | ROTN | Indus | IN-3152251 | R/NN-685253 |  | SO | 2022-10-10 | PDIRS2 | 4G_FD900_PDIRS2 | 4G_FD2100_PDIRS2 | 4G_TD_PDIRS2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573780 | 2022-10-14 | P/FVC/MDS/1113296/2022 | 2022-10-20 | ST202210574659 | 2022-10-15 | P/FVC/MDS/1113341/2022 | 2022-10-20 |  |  |  |  | ST202210559998 | 2022-10-12 | P/FBW/MDS/1114076/2022 | 2022-10-30
2584 | SVPET8 | SVPET8 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3152410 | R/NN-685371 |  | SO | 2022-10-10 | SVPET8 | 4G_FD900_SVPET8 | 4G_FD2100_SVPET8 | 4G_TD_SVPET8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210570609 | 2022-10-14 | P/FVC/MDS/1113242/2022 | 2022-10-20 | ST202210574053 | 2022-10-14 | P/FVC/MDS/1113310/2022 | 2022-10-20 |  |  |  |  | ST202210559758 | 2022-10-12 | P/FBW/MDS/1114047/2022 | 2022-10-30
2585 | PLKPM5 | PLKPM5 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-PAVN-ENB-9002 | SR-TN001159 |  | On Air | 2022-10-11 | PLKPM5 | 4G_FD900_PLKPM5 | 4G_FD2100_PLKPM5 | 4G_TD_PLKPM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572962 | 2022-10-14 | P/FVC/MDS/1113270/2022 | 2022-10-20 | ST202210574706 | 2022-10-15 | P/FVC/MDS/1113355/2022 | 2022-10-20 |  |  |  |  | ST202210568929 | 2022-10-14 | P/FBW/MDS/1114090/2022 | 2022-10-30
2586 | CBE964 | CBE964 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3152431 | R/NN-685401 |  | SO | 2022-10-14 | CBE964 | 4G_FD900_CBE964 | 4G_FD2100_CBE964 | 4G_TD_CBE964 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573062 | 2022-10-14 | P/FVC/MDS/1113285/2022 | 2022-10-20 | ST202210574784 | 2022-10-15 | P/FVC/MDS/1113370/2022 | 2022-10-20 | ST202211757936 | 2022-11-22 | P/FVC/MDS/1116758/2022 | 2022-11-29 | ST202210569421 | 2022-10-14 | P/FBW/MDS/1114105/2022 | 2022-10-30
2587 | WJBAD7 | WJBAD7 | Kancheepuram | Chennai |  | ROTN | TVI | - | - |  | SO | 2022-10-14 | WJBAD7 | 4G_FD900_WJBAD7 | 4G_FD2100_WJBAD7 | 4G_TD_WJBAD7 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573047 | 2022-10-14 | P/FVC/MDS/1113284/2022 | 2022-10-20 | ST202210574776 | 2022-10-15 | P/FVC/MDS/1113369/2022 | 2022-10-20 |  |  |  |  | ST202210569420 | 2022-10-14 | P/FBW/MDS/1114104/2022 | 2022-10-30
2588 | TLNGD3 | TLNGD3 | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TRTN-ENB-9063 | SR-TN001161 |  | On Air | 2022-10-11 | TLNGD3 | 4G_FD900_TLNGD3 | 4G_FD2100_TLNGD3 | 4G_TD_TLNGD3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539078 | 2022-10-08 | P/FVC/MDS/1114022/2022 | 2022-10-21 | ST202210537883 | 2022-10-07 | P/FVC/MDS/1113836/2022 | 2022-10-21 | ST202210538322 | 2022-10-08 | P/FVC/MDS/1113872/2022 | 2022-10-21 | ST202210534759 | 2022-10-06 | P/FBW/MDS/1113673/2022 | 2022-10-21
2589 | MLMR11 | MLMR11 | Kancheepuram | Chennai |  | ROTN | ATC | TN/KA/AT/23529 | T22TN06175 |  | On Air | 2022-10-10 | MLMR11 | 4G_FD900_MLMR11 | 4G_FD2100_MLMR11 | 4G_TD_MLMR11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572245 | 2022-10-14 | P/FVC/MDS/1113258/2022 | 2022-10-20 | ST202210574083 | 2022-10-14 | P/FVC/MDS/1113327/2022 | 2022-10-20 |  |  |  |  | ST202210559835 | 2022-10-12 | P/FBW/MDS/1114062/2022 | 2022-10-30
2590 | STIRI2 | STIRI2 | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TVLR-ENB-9081 | SR-TN001162 |  | On Air | 2022-10-11 | STIRI2 | 4G_FD900_STIRI2 | 4G_FD2100_STIRI2 | 4G_TD_STIRI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539079 | 2022-10-08 | P/FVC/MDS/1114023/2022 | 2022-10-21 | ST202210537884 | 2022-10-07 | P/FVC/MDS/1113837/2022 | 2022-10-21 | ST202210538323 | 2022-10-08 | P/FVC/MDS/1113873/2022 | 2022-10-21 | ST202210534760 | 2022-10-06 | P/FBW/MDS/1113674/2022 | 2022-10-21
2591 | VZMDI3 | VZMDI3 | Nagapattinam | Trichy |  | ROTN | Summit | Summit | I-TN-KLVR-ENB-9021 |  | SO | 2022-10-20 | VZMDI3 | 4G_FD900_VZMDI3 | 4G_FD2100_VZMDI3 | 4G_TD_VZMDI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539088 | 2022-10-08 | P/FVC/MDS/1114026/2022 | 2022-10-21 | ST202210537891 | 2022-10-07 | P/FVC/MDS/1113840/2022 | 2022-10-21 | ST202210538330 | 2022-10-08 | P/FVC/MDS/1113876/2022 | 2022-10-21 | ST202210534774 | 2022-10-06 | P/FBW/MDS/1113677/2022 | 2022-10-21
2592 | KILVR2 | KILVR2 | Nagapattinam | Trichy |  | ROTN | Summit | I-TN-KLVR-ENB-9027 | SR-TN001164 |  | On Air | 2022-10-11 | KILVR2 | 4G_FD900_KILVR2 | 4G_FD2100_KILVR2 | 4G_TD_KILVR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539089 | 2022-10-08 | P/FVC/MDS/1114027/2022 | 2022-10-21 | ST202210538093 | 2022-10-08 | P/FVC/MDS/1113841/2022 | 2022-10-21 | ST202210538331 | 2022-10-08 | P/FVC/MDS/1113877/2022 | 2022-10-21 | ST202210534775 | 2022-10-06 | P/FBW/MDS/1113678/2022 | 2022-10-21
2593 | TUT159 | TUT159 | Thoothukkudi | Madurai |  | ROTN | ATC | TN/TH/AT/23537 | T22TN06183 |  | On Air | 2022-10-10 | TUT159 | 4G_FD900_TUT159 | 4G_FD2100_TUT159 | 4G_TD_TUT159 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572246 | 2022-10-14 | P/FVC/MDS/1113259/2022 | 2022-10-20 | ST202210574082 | 2022-10-14 | P/FVC/MDS/1113326/2022 | 2022-10-20 |  |  |  |  | ST202210559948 | 2022-10-12 | P/FBW/MDS/1114063/2022 | 2022-10-30
2594 | ARIUR2 | ARIUR2 |  |  |  | ROTN | Indus | IN-3138486 | R/NN-662602 |  |  | 2022-10-10 | ARIUR2 | 4G_FD900_ARIUR2 | 4G_FD2100_ARIUR2 | 4G_TD_ARIUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210572007 | 2022-10-14 | P/FVC/MDS/1113247/2022 | 2022-10-20 | ST202210574058 | 2022-10-14 | P/FVC/MDS/1113315/2022 | 2022-10-20 | ST202210570222 | 2022-10-14 | P/FVC/MDS/1113222/2022 | 2022-10-20 | ST202210559769 | 2022-10-12 | P/FBW/MDS/1114052/2022 | 2022-10-30
2595 | KGRI44 | KGRI44 |  |  |  | ROTN | Indus | IN-3153610 | R/NN-686483 |  |  | 2022-10-11 | KGRI44 | 4G_FD900_KGRI44 | 4G_FD2100_KGRI44 | 4G_TD_KGRI44 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210572944 | 2022-10-14 | P/FVC/MDS/1113268/2022 | 2022-10-20 | ST202210574701 | 2022-10-15 | P/FVC/MDS/1113353/2022 | 2022-10-20 | ST202210570421 | 2022-10-14 | P/FVC/MDS/1113234/2022 | 2022-10-20 | ST202210568914 | 2022-10-14 | P/FBW/MDS/1114088/2022 | 2022-10-30
2596 | CBE866 | CBE866 |  |  |  | ROTN | Indus | IN-3151424 | R/NN-683687 |  |  | 2022-10-10 | CBE866 | 4G_FD900_CBE866 | 4G_FD2100_CBE866 | 4G_TD_CBE866 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209442788 | 2022-09-19 | P/FVC/MDS/1098123/2022 | 2022-09-27 | ST202209447439 | 2022-09-19 | P/FVC/MDS/1098210/2022 | 2022-09-27 |  |  |  |  | ST202209432492 | 2022-09-17 | P/FVC/MDS/1097988/2022 | 2022-09-27
2597 | VLR135 | VLR135 |  |  |  | ROTN | TVI | - | - |  |  | 2022-10-10 | VLR135 | 4G_FD900_VLR135 | 4G_FD2100_VLR135 | 4G_TD_VLR135 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202210572281 | 2022-10-14 | P/FVC/MDS/1113261/2022 | 2022-10-20 | ST202210574121 | 2022-10-14 | P/FVC/MDS/1113329/2022 | 2022-10-20 | ST202210570307 | 2022-10-14 | P/FVC/MDS/1113227/2022 | 2022-10-20
2598 | VLRM79 | VLRM79 |  |  |  | ROTN | Indus | IN-3148292 | R/NN-680623 |  |  | 2022-10-10 | VLRM79 | 4G_FD900_VLRM79 | 4G_FD2100_VLRM79 | 4G_TD_VLRM79 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202210572008 | 2022-10-14 | P/FVC/MDS/1113248/2022 | 2022-10-20 | ST202210574059 | 2022-10-14 | P/FVC/MDS/1113316/2022 | 2022-10-20 | ST202210570223 | 2022-10-14 | P/FVC/MDS/1113223/2022 | 2022-10-20 | ST202210559770 | 2022-10-12 | P/FBW/MDS/1114053/2022 | 2022-10-30
2599 | VISHW4 | VISHW4 |  |  |  | ROTN | Indus | IN-3154338 | R/NN-687581 |  |  | 2022-10-20 | VISHW4 | 4G_FD900_VISHW4 | 4G_FD2100_VISHW4 | 4G_TD_VISHW4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210539101 | 2022-10-08 | P/FVC/MDS/1114030/2022 | 2022-10-21 | ST202210538104 | 2022-10-08 | P/FVC/MDS/1113844/2022 | 2022-10-21 | ST202210538343 | 2022-10-08 | P/FVC/MDS/1113880/2022 | 2022-10-21 | ST202210534790 | 2022-10-06 | P/FBW/MDS/1113681/2022 | 2022-10-21
2600 | TRY404 | TRY404 |  |  |  | ROTN | ATC | TN/TR/TN/15002 | - |  |  | 2022-10-10 | TRY404 | 4G_FD900_TRY404 | 4G_FD2100_TRY404 | 4G_TD_TRY404 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202210572172 | 2022-10-14 | P/FVC/MDS/1113253/2022 | 2022-10-20 | ST202210574064 | 2022-10-14 | P/FVC/MDS/1113321/2022 | 2022-10-20 | ST202210570275 | 2022-10-14 | P/FVC/MDS/1113225/2022 | 2022-10-20 | ST202210559829 | 2022-10-12 | P/FBW/MDS/1114058/2022 | 2022-10-30
2601 | CBE944 | CBE944 |  |  |  | ROTN | Indus | IN-3152146 | R/NN-685115 |  |  | 2022-10-11 | CBE944 | 4G_FD900_CBE944 | 4G_FD2100_CBE944 | 4G_TD_CBE944 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210572324 | 2022-10-14 | P/FVC/MDS/1113265/2022 | 2022-10-20 | ST202210574694 | 2022-10-15 | P/FVC/MDS/1113350/2022 | 2022-10-20 | ST202210570420 | 2022-10-14 | P/FVC/MDS/1113233/2022 | 2022-10-20 | ST202210563516 | 2022-10-13 | P/FBW/MDS/1114085/2022 | 2022-10-30
2602 | MELR22 | MELR22 |  |  |  | ROTN | Indus | IN-3153415 | R/NN-686718 |  |  | 2022-10-10 | MELR22 | 4G_FD900_MELR22 | 4G_FD2100_MELR22 | 4G_TD_MELR22 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210573738 | 2022-10-14 | P/FVC/MDS/1113288/2022 | 2022-10-20 | ST202210574129 | 2022-10-14 | P/FVC/MDS/1113333/2022 | 2022-10-20 | ST202210570324 | 2022-10-14 | P/FVC/MDS/1113229/2022 | 2022-10-20 | ST202210559964 | 2022-10-12 | P/FBW/MDS/1114068/2022 | 2022-10-30
2603 | DNDPM2 | DNDPM2 |  |  |  | ROTN | Indus | IN-3138630 | R/NN-664431 |  |  | 2022-09-03 | DNDPM2 | 4G_FD900_DNDPM2 | 4G_FD2100_DNDPM2 | 4G_TD_DNDPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202209405208 | 2022-09-09 | P/FVC/MDS/1096590/2022 | 2022-09-16 | ST202209406085 | 2022-09-09 | P/FVC/MDS/1096499/2022 | 2022-09-16 | ST202209401274 | 2022-09-08 | P/FVC/MDS/1096426/2022 | 2022-09-16 | ST202209400120 | 2022-09-08 | P/FVC/MDS/1096405/2022 | 2022-09-16
2604 | TVDNI6 | TVDNI6 |  |  |  | ROTN | Indus | IN-1030528 | R/RES-513599 |  |  | 2022-10-11 | TVDNI6 | 4G_FD900_TVDNI6 | 4G_FD2100_TVDNI6 | 4G_TD_TVDNI6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573793 | 2022-10-14 | P/FVC/MDS/1113298/2022 | 2022-10-20 | ST202210574663 | 2022-10-15 | P/FVC/MDS/1113343/2022 | 2022-10-20 |  |  |  |  | ST202210560008 | 2022-10-12 | P/FBW/MDS/1114078/2022 | 2022-10-30
2605 | THKUM2 | THKUM2 |  |  |  | ROTN | ATC | TN/TR/AT/23392 | T22TN05707 |  |  | 2022-10-10 | THKUM2 | 4G_FD900_THKUM2 | 4G_FD2100_THKUM2 | 4G_TD_THKUM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572218 | 2022-10-14 | P/FVC/MDS/1113256/2022 | 2022-10-20 | ST202210574072 | 2022-10-14 | P/FVC/MDS/1113324/2022 | 2022-10-20 |  |  |  |  | ST202210559834 | 2022-10-12 | P/FBW/MDS/1114061/2022 | 2022-10-30
2606 | ANTPM2 | ANTPM2 |  |  |  | ROTN | Indus | IN-3149765 | R/NN-682508 |  |  | 2022-10-10 | ANTPM2 | 4G_FD900_ANTPM2 | 4G_FD2100_ANTPM2 | 4G_TD_ANTPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210570631 | 2022-10-14 | P/FVC/MDS/1113243/2022 | 2022-10-20 | ST202210574054 | 2022-10-14 | P/FVC/MDS/1113311/2022 | 2022-10-20 |  |  |  |  | ST202210559759 | 2022-10-12 | P/FBW/MDS/1114048/2022 | 2022-10-30
2607 | VTKAD2 | VTKAD2 |  |  |  | ROTN | ATC | TN/NM/AT/23429 | T22TN05744 |  |  | 2022-10-10 | VTKAD2 | 4G_FD900_VTKAD2 | 4G_FD2100_VTKAD2 | 4G_TD_VTKAD2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202210572219 | 2022-10-14 | P/FVC/MDS/1113257/2022 | 2022-10-20 | ST202210574073 | 2022-10-14 | P/FVC/MDS/1113325/2022 | 2022-10-20 | ST202210570306 | 2022-10-14 | P/FVC/MDS/1113226/2022 | 2022-10-20
2608 | KRUKD2 | KRUKD2 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-10-10 | KRUKD2 | 4G_FD900_KRUKD2 | 4G_FD2100_KRUKD2 | 4G_TD_KRUKD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210570534 | 2022-10-14 | P/FVC/MDS/1113236/2022 | 2022-10-20 | ST202210574032 | 2022-10-14 | P/FVC/MDS/1113304/2022 | 2022-10-20 |  |  |  |  | ST202210559750 | 2022-10-12 | P/FBW/MDS/1114041/2022 | 2022-10-30
2609 | MTNUR2 | MTNUR2 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-10-14 | MTNUR2 | 4G_FD900_MTNUR2 | 4G_FD2100_MTNUR2 | 4G_TD_MTNUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573028 | 2022-10-14 | P/FVC/MDS/1113280/2022 | 2022-10-20 | ST202210574745 | 2022-10-15 | P/FVC/MDS/1113365/2022 | 2022-10-20 |  |  |  |  | ST202210569385 | 2022-10-14 | P/FBW/MDS/1114100/2022 | 2022-10-30
2610 | PUVNK2 | PUVNK2 |  |  |  | ROTN | Ascend | - | - |  |  | 2022-10-14 | PUVNK2 | 4G_FD900_PUVNK2 | 4G_FD2100_PUVNK2 | 4G_TD_PUVNK2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 | 1905-09-30 | ST202210573016 | 2022-10-14 | P/FVC/MDS/1113279/2022 | 2022-10-20 | ST202210574744 | 2022-10-15 | P/FVC/MDS/1113364/2022 | 2022-10-20 | ST202211684536 | 2022-11-05 | P/FVC/MDS/1114603/2022 | 2022-11-15 | ST202210569178 | 2022-10-14 | P/FBW/MDS/1114099/2022 | 2022-10-30
2611 | PALTU3 | PALTU3 |  |  |  | ROTN | Indus | IN-3149845 | R/NN-682604 |  |  | 2022-10-10 | PALTU3 | 4G_FD900_PALTU3 | 4G_FD2100_PALTU3 | 4G_TD_PALTU3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210570632 | 2022-10-14 | P/FVC/MDS/1113244/2022 | 2022-10-20 | ST202210574055 | 2022-10-14 | P/FVC/MDS/1113312/2022 | 2022-10-20 |  |  |  |  | ST202210559760 | 2022-10-12 | P/FBW/MDS/1114049/2022 | 2022-10-30
2612 | PTLPT2 | PTLPT2 |  |  |  | ROTN | ATC | TN/TR/AT/23466 | T22TN05781 |  |  | 2022-10-10 | PTLPT2 | 4G_FD900_PTLPT2 | 4G_FD2100_PTLPT2 | 4G_TD_PTLPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572175 | 2022-10-14 | P/FVC/MDS/1113255/2022 | 2022-10-20 | ST202210574071 | 2022-10-14 | P/FVC/MDS/1113323/2022 | 2022-10-20 |  |  |  |  | ST202210559833 | 2022-10-12 | P/FBW/MDS/1114060/2022 | 2022-10-30
2613 | VRPAM2 | VRPAM2 |  |  |  | ROTN | Indus | IN-3149795 | R/NN-682546 |  |  | 2022-10-11 | VRPAM2 | 4G_FD900_VRPAM2 | 4G_FD2100_VRPAM2 | 4G_TD_VRPAM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210572323 | 2022-10-14 | P/FVC/MDS/1113264/2022 | 2022-10-20 | ST202210574693 | 2022-10-15 | P/FVC/MDS/1113349/2022 | 2022-10-20 | ST202210570349 | 2022-10-14 | P/FVC/MDS/1113232/2022 | 2022-10-20 | ST202210563515 | 2022-10-13 | P/FBW/MDS/1114084/2022 | 2022-10-30
2614 | CNPTU2 | CNPTU2 |  |  |  | ROTN | Indus | IN-3149798 | R/NN-682550 |  |  | 2022-10-10 | CNPTU2 | 4G_FD900_CNPTU2 | 4G_FD2100_CNPTU2 | 4G_TD_CNPTU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210572282 | 2022-10-14 | P/FVC/MDS/1113262/2022 | 2022-10-20 | ST202210574122 | 2022-10-14 | P/FVC/MDS/1113330/2022 | 2022-10-20 | ST202210570323 | 2022-10-14 | P/FVC/MDS/1113228/2022 | 2022-10-20 | ST202210559950 | 2022-10-12 | P/FBW/MDS/1114065/2022 | 2022-10-30
2615 | AVAD38 | AVAD38 |  |  |  | CHN | Indus | IN-3152268 | R/NN-684833 |  |  | 2022-10-10 | AVAD38 | 4G_FD900_AVAD38 | 4G_FD2100_AVAD38 | 4G_TD_AVAD38 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210570561 | 2022-10-14 | P/FVC/MDS/1113240/2022 | 2022-10-20 | ST202210574049 | 2022-10-14 | P/FVC/MDS/1113308/2022 | 2022-10-20 | ST202210570221 | 2022-10-14 | P/FVC/MDS/1113221/2022 | 2022-10-20 | ST202210559755 | 2022-10-12 | P/FBW/MDS/1114045/2022 | 2022-10-30
2616 | KLMBI4 | KLMBI4 |  |  |  | ROTN | Indus | IN-3153609 | R/NN-686309 |  |  | 2022-10-11 | KLMBI4 | 4G_FD900_KLMBI4 | 4G_FD2100_KLMBI4 | 4G_TD_KLMBI4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210573794 | 2022-10-14 | P/FVC/MDS/1113299/2022 | 2022-10-20 | ST202210574664 | 2022-10-15 | P/FVC/MDS/1113344/2022 | 2022-10-20 | ST202210570326 | 2022-10-14 | P/FVC/MDS/1113230/2022 | 2022-10-20 | ST202210560009 | 2022-10-12 | P/FBW/MDS/1114079/2022 | 2022-10-30
2617 | TKREC2 | TKREC2 |  |  |  | ROTN | Indus | IN-3153666 | R/NN-686864 |  |  | 2022-10-11 | TKREC2 | 4G_FD900_TKREC2 | 4G_FD2100_TKREC2 | 4G_TD_TKREC2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210572945 | 2022-10-14 | P/FVC/MDS/1113269/2022 | 2022-10-20 | ST202210574705 | 2022-10-15 | P/FVC/MDS/1113354/2022 | 2022-10-20 | ST202210570442 | 2022-10-14 | P/FVC/MDS/1113235/2022 | 2022-10-20 | ST202210568915 | 2022-10-14 | P/FBW/MDS/1114089/2022 | 2022-10-30
2618 | SLM437 | SLM437 | Salem | Vellore |  | ROTN | Indus | Indus | IN-3154341 |  | SO | 2022-10-20 | SLM437 | 4G_FD900_SLM437 | 4G_FD2100_SLM437 | 4G_TD_SLM437 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210638977 | 2022-10-28 | P/FVC/MDS/1114464/2022 | 2022-11-06 | ST202210643272 | 2022-10-28 | P/FVC/MDS/1114512/2022 | 2022-11-06 | ST202212839567 | 2022-12-22 |  |  | ST202210636913 | 2022-10-27 | P/FBW/MDS/1114405/2022 | 2022-11-06
2619 | TUT142 | TUT142 | Thoothukkudi | Madurai |  | ROTN | Indus | Indus | IN-3140385 |  | SO | 2022-10-20 | TUT142 | 4G_FD900_TUT142 | 4G_FD2100_TUT142 | 4G_TD_TUT142 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210642765 | 2022-10-28 | P/FVC/MDS/1114484/2022 | 2022-11-06 | ST202210651580 | 2022-10-29 | P/FVC/MDS/1114532/2022 | 2022-11-06 |  |  |  |  | ST202210636979 | 2022-10-27 | P/FBW/MDS/1114425/2022 | 2022-11-06
2620 | SNKL15 | SNKL15 | Tirunelveli | Madurai |  | ROTN | Indus | Indus | IN-3155416 |  |  | 2022-10-20 | SNKL15 | 4G_FD900_SNKL15 | 4G_FD2100_SNKL15 | 4G_TD_SNKL15 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642740 | 2022-10-28 | P/FVC/MDS/1114483/2022 | 2022-11-06 | ST202210651557 | 2022-10-29 | P/FVC/MDS/1114531/2022 | 2022-11-06 |  |  |  |  | ST202210636972 | 2022-10-27 | P/FBW/MDS/1114424/2022 | 2022-11-06
2621 | PRAVI6 | PRAVI6 | Madurai | Madurai |  | ROTN | Indus | Indus | IN-3142363 |  | SO | 2022-10-20 | PRAVI6 | 4G_FD900_PRAVI6 | 4G_FD2100_PRAVI6 | 4G_TD_PRAVI6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642904 | 2022-10-28 | P/FVC/MDS/1114493/2022 | 2022-11-06 | ST202210651650 | 2022-10-29 | P/FVC/MDS/1114541/2022 | 2022-11-06 |  |  |  |  | ST202210637012 | 2022-10-27 | P/FBW/MDS/1114434/2022 | 2022-11-06
2622 | KUNTR2 | KUNTR2 | Tiruvannamalai | Vellore |  | ROTN | Indus | Indus | IN-3153345 |  | SO | 2022-10-20 | KUNTR2 | 4G_FD900_KUNTR2 | 4G_FD2100_KUNTR2 | 4G_TD_KUNTR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642959 | 2022-10-28 | P/FVC/MDS/1114497/2022 | 2022-11-06 | ST202210651692 | 2022-10-29 | P/FVC/MDS/1114545/2022 | 2022-11-06 |  |  |  |  | ST202210637021 | 2022-10-27 | P/FBW/MDS/1114438/2022 | 2022-11-06
2623 | PONMD2 | PONMD2 | Erode | Coimbatore |  | ROTN | Indus | Indus | IN-3152438 |  | SO | 2022-10-20 | PONMD2 | 4G_FD900_PONMD2 | 4G_FD2100_PONMD2 | 4G_TD_PONMD2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642767 | 2022-10-28 | P/FVC/MDS/1114486/2022 | 2022-11-06 | ST202210651583 | 2022-10-29 | P/FVC/MDS/1114534/2022 | 2022-11-06 |  |  |  |  | ST202210636981 | 2022-10-27 | P/FBW/MDS/1114427/2022 | 2022-11-06
2624 | KRMDA2 | KRMDA2 | Coimbatore | Coimbatore |  | ROTN | Indus | Indus | IN-3152498 |  | SO | 2022-10-20 | KRMDA2 | 4G_FD900_KRMDA2 | 4G_FD2100_KRMDA2 | 4G_TD_KRMDA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642825 | 2022-10-28 | P/FVC/MDS/1114488/2022 | 2022-11-06 | ST202210651605 | 2022-10-29 | P/FVC/MDS/1114536/2022 | 2022-11-06 |  |  |  |  | ST202210636992 | 2022-10-27 | P/FBW/MDS/1114429/2022 | 2022-11-06
2625 | ATPLM2 | ATPLM2 | Namakkal | Coimbatore |  | ROTN | Indus | Indus | IN-3152445 |  | On Air | 2022-10-20 | ATPLM2 | 4G_FD900_ATPLM2 | 4G_FD2100_ATPLM2 | 4G_TD_ATPLM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639081 | 2022-10-28 | P/FVC/MDS/1114471/2022 | 2022-11-06 | ST202210651487 | 2022-10-29 | P/FVC/MDS/1114519/2022 | 2022-11-06 |  |  |  |  | ST202210636933 | 2022-10-27 | P/FBW/MDS/1114412/2022 | 2022-11-06
2626 | KODIM2 | KODIM2 | Madurai | Madurai |  | ROTN | ATC | ATC | TN/MU/AT/23523 |  | SO | 2022-10-20 | KODIM2 | 4G_FD900_KODIM2 | 4G_FD2100_KODIM2 | 4G_TD_KODIM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639179 | 2022-10-28 | P/FVC/MDS/1114476/2022 | 2022-11-06 | ST202210651514 | 2022-10-29 | P/FVC/MDS/1114524/2022 | 2022-11-06 |  |  |  |  | ST202210636953 | 2022-10-27 | P/FBW/MDS/1114417/2022 | 2022-11-06
2627 | SLM433 | SLM433 | Salem | Vellore |  | ROTN | ATC | ATC | TN/SA/AT/23515 |  | On Air | 2022-10-20 | SLM433 | 4G_FD900_SLM433 | 4G_FD2100_SLM433 | 4G_TD_SLM433 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639083 | 2022-10-28 | P/FVC/MDS/1114473/2022 | 2022-11-06 | ST202210651497 | 2022-10-29 | P/FVC/MDS/1114521/2022 | 2022-11-06 |  |  |  |  | ST202210636944 | 2022-10-27 | P/FBW/MDS/1114414/2022 | 2022-11-06
2628 | VLLUR9 | VLLUR9 | Coimbatore | Coimbatore |  | ROTN | Indus | Indus | IN-3152390 |  | SO | 2022-10-20 | VLLUR9 | 4G_FD900_VLLUR9 | 4G_FD2100_VLLUR9 | 4G_TD_VLLUR9 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642766 | 2022-10-28 | P/FVC/MDS/1114485/2022 | 2022-11-06 | ST202210651581 | 2022-10-29 | P/FVC/MDS/1114533/2022 | 2022-11-06 |  |  |  |  | ST202210636980 | 2022-10-27 | P/FBW/MDS/1114426/2022 | 2022-11-06
2629 | MOLPL2 | MOLPL2 | Coimbatore | Coimbatore |  | ROTN | Indus | Indus | IN-3153936 |  | SO | 2022-10-20 | MOLPL2 | 4G_FD900_MOLPL2 | 4G_FD2100_MOLPL2 | 4G_TD_MOLPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210638976 | 2022-10-28 | P/FVC/MDS/1114463/2022 | 2022-11-06 | ST202210643220 | 2022-10-28 | P/FVC/MDS/1114511/2022 | 2022-11-06 |  |  |  |  | ST202210636912 | 2022-10-27 | P/FBW/MDS/1114404/2022 | 2022-11-06
2630 | MNYPT3 | MNYPT3 | Vellore | Vellore |  | ROTN | ATC | ATC | TN/VE/AT/23518 |  | SO | 2022-10-20 | MNYPT3 | 4G_FD900_MNYPT3 | 4G_FD2100_MNYPT3 | 4G_TD_MNYPT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639180 | 2022-10-28 | P/FVC/MDS/1114477/2022 | 2022-11-06 | ST202210651515 | 2022-10-29 | P/FVC/MDS/1114525/2022 | 2022-11-06 |  |  |  |  | ST202210636954 | 2022-10-27 | P/FBW/MDS/1114418/2022 | 2022-11-06
2631 | NPLI09 | NPLI09 | Vellore | Vellore |  | ROTN | Indus | Indus | IN-3152806 |  |  | 2022-10-20 | NPLI09 | 4G_FD900_NPLI09 | 4G_FD2100_NPLI09 | 4G_TD_NPLI09 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639288 | 2022-10-28 | P/FVC/MDS/1114479/2022 | 2022-11-06 | ST202210651533 | 2022-10-29 | P/FVC/MDS/1114527/2022 | 2022-11-06 |  |  |  |  | ST202210636962 | 2022-10-27 | P/FBW/MDS/1114420/2022 | 2022-11-06
2632 | VDSN10 | VDSN10 | Dindigul | Coimbatore |  | ROTN | Indus | Indus | IN-3152807 |  | SO | 2022-10-20 | VDSN10 | 4G_FD900_VDSN10 | 4G_FD2100_VDSN10 | 4G_TD_VDSN10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642826 | 2022-10-28 | P/FVC/MDS/1114489/2022 | 2022-11-06 | ST202210651606 | 2022-10-29 | P/FVC/MDS/1114537/2022 | 2022-11-06 |  |  |  |  | ST202210636993 | 2022-10-27 | P/FBW/MDS/1114430/2022 | 2022-11-06
2633 | THNUT2 | THNUT2 | Tirunelveli | Madurai |  | ROTN | Indus | Indus | IN-3152809 |  | SO | 2022-10-20 | THNUT2 | 4G_FD900_THNUT2 | 4G_FD2100_THNUT2 | 4G_TD_THNUT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642958 | 2022-10-28 | P/FVC/MDS/1114496/2022 | 2022-11-06 | ST202210651690 | 2022-10-29 | P/FVC/MDS/1114544/2022 | 2022-11-06 |  |  |  |  | ST202210637020 | 2022-10-27 | P/FBW/MDS/1114437/2022 | 2022-11-06
2634 | SLM363 | SLM363 | Salem | Vellore |  | ROTN | TVI | TVI | - |  | SO | 2022-10-20 | SLM363 | 4G_FD900_SLM363 | 4G_FD2100_SLM363 | 4G_TD_SLM363 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210642989 | 2022-10-28 | P/FVC/MDS/1114499/2022 | 2022-11-06 | ST202210651714 | 2022-10-29 | P/FVC/MDS/1114547/2022 | 2022-11-06 |  |  |  |  | ST202210637027 | 2022-10-27 | P/FBW/MDS/1114440/2022 | 2022-11-06
2635 | KRDPM2 | KRDPM2 | Erode | Coimbatore |  | ROTN | Indus | Indus | IN-3154364 |  | SO | 2022-10-20 | KRDPM2 | 4G_FD900_KRDPM2 | 4G_FD2100_KRDPM2 | 4G_TD_KRDPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210640936 | 2022-10-28 | P/FVC/MDS/1114481/2022 | 2022-11-06 | ST202210651555 | 2022-10-29 | P/FVC/MDS/1114529/2022 | 2022-11-06 |  |  |  |  | ST202210636970 | 2022-10-27 | P/FBW/MDS/1114422/2022 | 2022-11-06
2636 | SMNR08 | SMNR08 | Coimbatore | Coimbatore |  | ROTN | TVI | TVI | - |  | On Air | 2022-10-20 | SMNR08 | 4G_FD900_SMNR08 | 4G_FD2100_SMNR08 | 4G_TD_SMNR08 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210643007 | 2022-10-28 | P/FVC/MDS/1114500/2022 | 2022-11-06 | ST202210651715 | 2022-10-29 | P/FVC/MDS/1114548/2022 | 2022-11-06 |  |  |  |  | ST202210637028 | 2022-10-27 | P/FBW/MDS/1114441/2022 | 2022-11-06
2637 | ACMGM6 | ACMGM6 |  |  |  | ROTN | Indus | IN-3155156 | R/NN-688730 |  |  | 2022-10-20 | ACMGM6 | 4G_FD900_ACMGM6 | 4G_FD2100_ACMGM6 | 4G_TD_ACMGM6 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202210642739 | 2022-10-28 | P/FVC/MDS/1114482/2022 | 2022-11-06 | ST202210651556 | 2022-10-29 | P/FVC/MDS/1114530/2022 | 2022-11-06 | ST202210638748 | 2022-10-28 | P/FVC/MDS/1114454/2022 | 2022-11-06 | ST202210636971 | 2022-10-27 | P/FBW/MDS/1114423/2022 | 2022-11-06
2638 | SLM395 | SLM395 |  |  |  | ROTN | TVI | - | - |  |  | 2022-10-20 | SLM395 | 4G_FD900_SLM395 | 4G_FD2100_SLM395 | 4G_TD_SLM395 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202210642988 | 2022-10-28 | P/FVC/MDS/1114498/2022 | 2022-11-06 | ST202210651693 | 2022-10-29 | P/FVC/MDS/1114546/2022 | 2022-11-06 | ST202210638819 | 2022-10-28 | P/FVC/MDS/1114458/2022 | 2022-11-06 | ST202210637026 | 2022-10-27 | P/FBW/MDS/1114439/2022 | 2022-11-06
2639 | PDY378 | PDY378 |  |  |  | ROTN | Indus | IN-3135027 | R/NN-659707 |  |  | 2022-10-20 | PDY378 | 4G_FD900_PDY378 | 4G_FD2100_PDY378 | 4G_TD_PDY378 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202210639033 | 2022-10-28 | P/FVC/MDS/1114468/2022 | 2022-11-06 | ST202210651463 | 2022-10-29 | P/FVC/MDS/1114516/2022 | 2022-11-06 | ST202210638686 | 2022-10-28 | P/FVC/MDS/1114449/2022 | 2022-11-06 | ST202210636922 | 2022-10-27 | P/FBW/MDS/1114409/2022 | 2022-11-06
2640 | SAIM11 | SAIM11 |  |  |  | CHN | TVI | - | - |  |  | 2022-10-20 | SAIM11 | 4G_FD900_SAIM11 | 4G_FD2100_SAIM11 | 4G_TD_SAIM11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210639035 | 2022-10-28 | P/FVC/MDS/1114470/2022 | 2022-11-06 | ST202210651486 | 2022-10-29 | P/FVC/MDS/1114518/2022 | 2022-11-06 | ST202210638688 | 2022-10-28 | P/FVC/MDS/1114451/2022 | 2022-11-06 | ST202210636932 | 2022-10-27 | P/FBW/MDS/1114411/2022 | 2022-11-06
2641 | ILKD07 | ILKD07 |  |  |  | ROTN | Indus | IN-3147362 | R/NN-678051 |  |  | 2022-10-20 | ILKD07 | 4G_FD900_ILKD07 | 4G_FD2100_ILKD07 | 4G_TD_ILKD07 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210639182 | 2022-10-28 | P/FVC/MDS/1114478/2022 | 2022-11-06 | ST202210651532 | 2022-10-29 | P/FVC/MDS/1114526/2022 | 2022-11-06 | ST202210638747 | 2022-10-28 | P/FVC/MDS/1114453/2022 | 2022-11-06 | ST202210636961 | 2022-10-27 | P/FBW/MDS/1114419/2022 | 2022-11-06
2642 | TMGM18 | TMGM18 |  |  |  | ROTN | Indus | IN-3147368 | R/NN-678072 |  |  | 2022-10-20 | TMGM18 | 4G_FD900_TMGM18 | 4G_FD2100_TMGM18 | 4G_TD_TMGM18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210638975 | 2022-10-28 | P/FVC/MDS/1114462/2022 | 2022-11-06 | ST202210643219 | 2022-10-28 | P/FVC/MDS/1114510/2022 | 2022-11-06 | ST202210638645 | 2022-10-28 | P/FVC/MDS/1114447/2022 | 2022-11-06 | ST202210636899 | 2022-10-27 | P/FBW/MDS/1114403/2022 | 2022-11-06
2643 | PATT36 | PATT36 |  |  |  | CHN | TVI | - | - |  |  | 2022-10-20 | PATT36 | 4G_FD900_PATT36 | 4G_FD2100_PATT36 | 4G_TD_PATT36 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210638949 | 2022-10-28 | P/FVC/MDS/1114461/2022 | 2022-11-06 | ST202210643218 | 2022-10-28 | P/FVC/MDS/1114509/2022 | 2022-11-06 | ST202210638609 | 2022-10-28 | P/FVC/MDS/1114446/2022 | 2022-11-06 | ST202210636898 | 2022-10-27 | P/FBW/MDS/1114402/2022 | 2022-11-06
2644 | MULMP3 | MULMP3 |  |  |  | ROTN | Indus | IN-3149861 | R/NN-682631 |  |  | 2022-10-20 | MULMP3 | 4G_FD900_MULMP3 | 4G_FD2100_MULMP3 | 4G_TD_MULMP3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639289 | 2022-10-28 | P/FVC/MDS/1114480/2022 | 2022-11-06 | ST202210651534 | 2022-10-29 | P/FVC/MDS/1114528/2022 | 2022-11-06 |  |  |  |  | ST202210636963 | 2022-10-27 | P/FBW/MDS/1114421/2022 | 2022-11-06
2645 | VZVDI2 | VZVDI2 |  |  |  | ROTN | Indus | IN-3150144 | R/NN-682383 |  |  | 2022-10-20 | VZVDI2 | 4G_FD900_VZVDI2 | 4G_FD2100_VZVDI2 | 4G_TD_VZVDI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210639005 | 2022-10-28 | P/FVC/MDS/1114465/2022 | 2022-11-06 | ST202210643273 | 2022-10-28 | P/FVC/MDS/1114513/2022 | 2022-11-06 | ST202210638646 | 2022-10-28 | P/FVC/MDS/1114448/2022 | 2022-11-06 | ST202210636914 | 2022-10-27 | P/FBW/MDS/1114406/2022 | 2022-11-06
2646 | MELPN2 | MELPN2 |  |  |  | ROTN | Summit | I-TN-TRMY-ENB-9023 | SR-TN001112 |  |  | 2022-10-20 | MELPN2 | 4G_FD900_MELPN2 | 4G_FD2100_MELPN2 | 4G_TD_MELPN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639082 | 2022-10-28 | P/FVC/MDS/1114472/2022 | 2022-11-06 | ST202210651496 | 2022-10-29 | P/FVC/MDS/1114520/2022 | 2022-11-06 |  |  |  |  | ST202210636943 | 2022-10-27 | P/FBW/MDS/1114413/2022 | 2022-11-06
2647 | RMPUR2 | RMPUR2 |  |  |  | ROTN | Indus | IN-3149812 | R/NN-682557 |  |  | 2022-10-20 | RMPUR2 | 4G_FD900_RMPUR2 | 4G_FD2100_RMPUR2 | 4G_TD_RMPUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642905 | 2022-10-28 | P/FVC/MDS/1114494/2022 | 2022-11-06 | ST202210651651 | 2022-10-29 | P/FVC/MDS/1114542/2022 | 2022-11-06 |  |  |  |  | ST202210637013 | 2022-10-27 | P/FBW/MDS/1114435/2022 | 2022-11-06
2648 | PGOLA2 | PGOLA2 |  |  |  | ROTN | ATC | TN/DH/AT/23460 | TN/DH/AT/23460 |  |  | 2022-10-20 | PGOLA2 | 4G_FD900_PGOLA2 | 4G_FD2100_PGOLA2 | 4G_TD_PGOLA2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639126 | 2022-10-28 | P/FVC/MDS/1114475/2022 | 2022-11-06 | ST202210651513 | 2022-10-29 | P/FVC/MDS/1114523/2022 | 2022-11-06 |  |  |  |  | ST202210636952 | 2022-10-27 | P/FBW/MDS/1114416/2022 | 2022-11-06
2649 | NETUR2 | NETUR2 |  |  |  | ROTN | ATC | TN/TR/AT/23465 | TN/TR/AT/23465 |  |  | 2022-10-20 | NETUR2 | 4G_FD900_NETUR2 | 4G_FD2100_NETUR2 | 4G_TD_NETUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210639125 | 2022-10-28 | P/FVC/MDS/1114474/2022 | 2022-11-06 | ST202210651498 | 2022-10-29 | P/FVC/MDS/1114522/2022 | 2022-11-06 | ST202210638746 | 2022-10-28 | P/FVC/MDS/1114452/2022 | 2022-11-06 | ST202210636945 | 2022-10-27 | P/FBW/MDS/1114415/2022 | 2022-11-06
2650 | UDPLY2 | UDPLY2 |  |  |  | ROTN | Indus | IN-3149815 | R/NN-682562 |  |  | 2022-10-20 | UDPLY2 | 4G_FD900_UDPLY2 | 4G_FD2100_UDPLY2 | 4G_TD_UDPLY2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210639006 | 2022-10-28 | P/FVC/MDS/1114466/2022 | 2022-11-06 | ST202210643274 | 2022-10-28 | P/FVC/MDS/1114514/2022 | 2022-11-06 |  |  |  |  | ST202210636920 | 2022-10-27 | P/FBW/MDS/1114407/2022 | 2022-11-06
2651 | BROD11 | BROD11 |  |  |  | CHN | Indus | IN-3152266 | R/NN-684831 |  |  | 2022-10-20 | BROD11 | 4G_FD900_BROD11 | 4G_FD2100_BROD11 | 4G_TD_BROD11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210638948 | 2022-10-28 | P/FVC/MDS/1114460/2022 | 2022-11-06 | ST202210643204 | 2022-10-28 | P/FVC/MDS/1114508/2022 | 2022-11-06 | ST202210638608 | 2022-10-28 | P/FVC/MDS/1114445/2022 | 2022-11-06 | ST202210636897 | 2022-10-27 | P/FBW/MDS/1114401/2022 | 2022-11-06
2652 | UPPKT3 | UPPKT3 |  |  |  | ROTN | Indus | IN-3153268 | R/NN-686264 |  |  | 2022-10-20 | UPPKT3 | 4G_FD900_UPPKT3 | 4G_FD2100_UPPKT3 | 4G_TD_UPPKT3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210642867 | 2022-10-28 | P/FVC/MDS/1114490/2022 | 2022-11-06 | ST202210651628 | 2022-10-29 | P/FVC/MDS/1114538/2022 | 2022-11-06 | ST202210638793 | 2022-10-28 | P/FVC/MDS/1114455/2022 | 2022-11-06 | ST202210637005 | 2022-10-27 | P/FBW/MDS/1114431/2022 | 2022-11-06
2653 | TPDPT2 | TPDPT2 |  |  |  | ROTN | Indus | IN-3153270 | R/NN-686275 |  |  | 2022-10-20 | TPDPT2 | 4G_FD900_TPDPT2 | 4G_FD2100_TPDPT2 | 4G_TD_TPDPT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210642868 | 2022-10-28 | P/FVC/MDS/1114491/2022 | 2022-11-06 | ST202210651629 | 2022-10-29 | P/FVC/MDS/1114539/2022 | 2022-11-06 | ST202210638794 | 2022-10-28 | P/FVC/MDS/1114456/2022 | 2022-11-06 | ST202210637006 | 2022-10-27 | P/FBW/MDS/1114432/2022 | 2022-11-06
2654 | SPLKT2 | SPLKT2 |  |  |  | ROTN | Indus | IN-3153668 | R/NN-686884 |  |  | 2022-10-20 | SPLKT2 | 4G_FD900_SPLKT2 | 4G_FD2100_SPLKT2 | 4G_TD_SPLKT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210642870 | 2022-10-28 | P/FVC/MDS/1114492/2022 | 2022-11-06 | ST202210651630 | 2022-10-29 | P/FVC/MDS/1114540/2022 | 2022-11-06 | ST202210638795 | 2022-10-28 | P/FVC/MDS/1114457/2022 | 2022-11-06 | ST202210637011 | 2022-10-27 | P/FBW/MDS/1114433/2022 | 2022-11-06
2655 | PRNP19 | PRNP19 |  |  |  | ROTN | Indus | IN-1031780 | R/RES-513558 |  |  | 2022-10-20 | PRNP19 | 4G_FD900_PRNP19 | 4G_FD2100_PRNP19 | 4G_TD_PRNP19 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202210639034 | 2022-10-28 | P/FVC/MDS/1114469/2022 | 2022-11-06 | ST202210651464 | 2022-10-29 | P/FVC/MDS/1114517/2022 | 2022-11-06 | ST202210638687 | 2022-10-28 | P/FVC/MDS/1114450/2022 | 2022-11-06 | ST202210636931 | 2022-10-27 | P/FBW/MDS/1114410/2022 | 2022-11-06
2656 | PDPP17 | PDPP17 | Kancheepuram | Chennai |  | ROTN | Summit | I-TN-SPRM-ENB-0096 | SR-TN001158 |  | On Air | 2022-10-28 | PDPP17 | 4G_FD900_PDPP17 | 4G_FD2100_PDPP17 | 4G_TD_PDPP17 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210539073 | 2022-10-08 | P/FVC/MDS/1114021/2022 | 2022-10-21 | ST202210537882 | 2022-10-07 | P/FVC/MDS/1113835/2022 | 2022-10-21 | ST202210538315 | 2022-10-08 | P/FVC/MDS/1113871/2022 | 2022-10-21 | ST202210534750 | 2022-10-06 | P/FBW/MDS/1113672/2022 | 2022-10-21
2657 | ANJGM8 | ANJGM8 | Kanniyakumari | Madurai |  | ROTN | ATC | TN/KN/AT/23528 | T22TN06174 |  | SO | 2022-10-28 | ANJGM8 | 4G_FD900_ANJGM8 | 4G_FD2100_ANJGM8 | 4G_TD_ANJGM8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573740 | 2022-10-14 | P/FVC/MDS/1113290/2022 | 2022-10-20 | ST202210574138 | 2022-10-14 | P/FVC/MDS/1113335/2022 | 2022-10-20 | ST202211682947 | 2022-11-05 | P/FVC/MDS/1114589/2022 | 2022-11-15 | ST202210559977 | 2022-10-12 | P/FBW/MDS/1114070/2022 | 2022-10-30
2658 | NAVL24 | NAVL24 |  |  |  | CHN | Summit | I-TN-CHNN-ENB-2383 | SR-TN001118 |  | On air | 2022-10-20 | NAVL24 | 4G_FD900_NAVL24 | 4G_FD2100_NAVL24 | 4G_TD_NAVL24 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210638947 | 2022-10-28 | P/FVC/MDS/1114459/2022 | 2022-11-06 | ST202210643203 | 2022-10-28 | P/FVC/MDS/1114507/2022 | 2022-11-06 |  |  |  |  | ST202210636888 | 2022-10-27 | P/FBW/MDS/1114400/2022 | 2022-11-06
2659 | KUNR37 | KUNR37 |  |  |  | CHN | Indus | IN-3137087 | R/NN-664970 |  | SO | 2022-10-11 | KUNR37 | 4G_FD900_KUNR37 | 4G_FD2100_KUNR37 | 4G_TD_KUNR37 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210573808 | 2022-10-14 | P/FVC/MDS/1113302/2022 | 2022-10-20 | ST202210574681 | 2022-10-15 | P/FVC/MDS/1113347/2022 | 2022-10-20 |  |  |  |  | ST202210560018 | 2022-10-12 | P/FBW/MDS/1114082/2022 | 2022-10-30
2660 | TVTY35 | TVTY35 |  |  |  | CHN | Airtel | - | - |  | SO | 2022-10-10 | TVTY35 | 4G_FD900_TVTY35 | 4G_FD2100_TVTY35 | 4G_TD_TVTY35 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210572174 | 2022-10-14 | P/FVC/MDS/1113254/2022 | 2022-10-20 | ST202210574065 | 2022-10-14 | P/FVC/MDS/1113322/2022 | 2022-10-20 |  |  |  |  | ST202210559830 | 2022-10-12 | P/FBW/MDS/1114059/2022 | 2022-10-30
2661 | SOWC14 | SOWC14 |  |  |  | CHN | Airtel | - | - |  | SO | 2022-10-20 | SOWC14 | 4G_FD900_SOWC14 | 4G_FD2100_SOWC14 | 4G_TD_SOWC14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210639007 | 2022-10-28 | P/FVC/MDS/1114467/2022 | 2022-11-06 | ST202210651462 | 2022-10-29 | P/FVC/MDS/1114515/2022 | 2022-11-06 |  |  |  |  | ST202210636921 | 2022-10-27 | P/FBW/MDS/1114408/2022 | 2022-11-06
2662 | TINPK2 | TINPK2 |  |  |  | CHN | Indus | IN-3152462 | R/NN-685426 |  | SO | 2022-10-10 | TINPK2 | 4G_FD900_TINPK2 | 4G_FD2100_TINPK2 | 4G_TD_TINPK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573792 | 2022-10-14 | P/FVC/MDS/1113297/2022 | 2022-10-20 | ST202210574660 | 2022-10-15 | P/FVC/MDS/1113342/2022 | 2022-10-20 |  |  |  |  | ST202210560007 | 2022-10-12 | P/FBW/MDS/1114077/2022 | 2022-10-30
2663 | MINJ17 | MINJ17 |  |  |  | CHN | Indus | IN-3152467 | R/NN-685427 |  | SO | 2022-10-14 | MINJ17 | 4G_FD900_MINJ17 | 4G_FD2100_MINJ17 | 4G_TD_MINJ17 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573029 | 2022-10-14 | P/FVC/MDS/1113281/2022 | 2022-10-20 | ST202210574765 | 2022-10-15 | P/FVC/MDS/1113366/2022 | 2022-10-20 |  |  |  |  | ST202210569386 | 2022-10-14 | P/FBW/MDS/1114101/2022 | 2022-10-30
2664 | MBKPT2 | MBKPT2 |  |  |  | CHN | Indus | IN-3152469 | R/NN-685429 |  | SO | 2022-10-11 | MBKPT2 | 4G_FD900_MBKPT2 | 4G_FD2100_MBKPT2 | 4G_TD_MBKPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573806 | 2022-10-14 | P/FVC/MDS/1113300/2022 | 2022-10-20 | ST202210574676 | 2022-10-15 | P/FVC/MDS/1113345/2022 | 2022-10-20 |  |  |  |  | ST202210560015 | 2022-10-12 | P/FBW/MDS/1114080/2022 | 2022-10-30
2665 | KOLA54 | KOLA54 |  |  |  | CHN | Indus | IN-3152473 | R/NN-685435 |  | SO | 2022-10-11 | KOLA54 | 4G_FD900_KOLA54 | 4G_FD2100_KOLA54 | 4G_TD_KOLA54 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573807 | 2022-10-14 | P/FVC/MDS/1113301/2022 | 2022-10-20 | ST202210574677 | 2022-10-15 | P/FVC/MDS/1113346/2022 | 2022-10-20 |  |  |  |  | ST202210560016 | 2022-10-12 | P/FBW/MDS/1114081/2022 | 2022-10-30
2666 | PONM13 | PONM13 |  |  |  | CHN | Indus | IN-3152475 | R/NN-685438 |  | SO | 2022-10-14 | PONM13 | 4G_FD900_PONM13 | 4G_FD2100_PONM13 | 4G_TD_PONM13 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210573063 | 2022-10-14 | P/FVC/MDS/1113286/2022 | 2022-10-20 | ST202210574785 | 2022-10-15 | P/FVC/MDS/1113371/2022 | 2022-10-20 |  |  |  |  | ST202210569422 | 2022-10-14 | P/FBW/MDS/1114106/2022 | 2022-10-30
2667 | PONM14 | PONM14 |  |  |  | CHN | Indus | IN-3152477 | R/NN-685441 |  |  | 2022-10-20 | PONM14 | 4G_FD900_PONM14 | 4G_FD2100_PONM14 | 4G_TD_PONM14 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210642824 | 2022-10-28 | P/FVC/MDS/1114487/2022 | 2022-11-06 | ST202210651604 | 2022-10-29 | P/FVC/MDS/1114535/2022 | 2022-11-06 |  |  |  |  | ST202210636991 | 2022-10-27 | P/FBW/MDS/1114428/2022 | 2022-11-06
2668 | GUDU32 | GUDU32 |  |  |  | CHN | Indus | IN-3152250 | R/NN-685251 |  | On air | 2022-10-11 | GUDU32 | 4G_FD900_GUDU32 | 4G_FD2100_GUDU32 | 4G_TD_GUDU32 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210572858 | 2022-10-14 | P/FVC/MDS/1113266/2022 | 2022-10-20 | ST202210574695 | 2022-10-15 | P/FVC/MDS/1113351/2022 | 2022-10-20 |  |  |  |  | ST202210568910 | 2022-10-14 | P/FBW/MDS/1114086/2022 | 2022-10-30
2669 | VTPT23 | VTPT23 |  |  |  | CHN | Indus | IN-3152397 | R/NN-685365 |  | SO | 2022-10-10 | VTPT23 | 4G_FD900_VTPT23 | 4G_FD2100_VTPT23 | 4G_TD_VTPT23 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210572322 | 2022-10-14 | P/FVC/MDS/1113263/2022 | 2022-10-20 | ST202210574123 | 2022-10-14 | P/FVC/MDS/1113331/2022 | 2022-10-20 |  |  |  |  | ST202210559961 | 2022-10-12 | P/FBW/MDS/1114066/2022 | 2022-10-30
2670 | PONM15 | PONM15 |  |  |  | CHN | Indus | IN-3152408 | R/NN-685369 |  | SO | 2022-10-10 | PONM15 | 4G_FD900_PONM15 | 4G_FD2100_PONM15 | 4G_TD_PONM15 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202210570634 | 2022-10-14 | P/FVC/MDS/1113245/2022 | 2022-10-20 | ST202210574056 | 2022-10-14 | P/FVC/MDS/1113313/2022 | 2022-10-20 | ST202301004039 | 2023-01-03 | 0 |  | ST202210559763 | 2022-10-12 | P/FBW/MDS/1114050/2022 | 2022-10-30
2671 | MGDI08 | MGDI08 | Thiruvarur | Trichy |  | ROTN | Airtel | - | - |  | SO | 2022-10-28 | MGDI08 | 4G_FD900_MGDI08 | 4G_FD2100_MGDI08 | 4G_TD_MGDI08 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681023 | 2022-11-04 | P/FVC/MDS/1114800/2022 | 2022-11-22 | ST202211685830 | 2022-11-07 | P/FVC/MDS/1114642/2022 | 2022-11-15 | ST202211684513 | 2022-11-05 | P/FVC/MDS/1114593/2022 | 2022-11-15 | ST202211685484 | 2022-11-07 | P/FBW/MDS/1114722/2022 | 2022-11-16
2672 | TNJ378 | TNJ378 | Thanjavur | Trichy |  | ROTN | Indus | IN-3155415 | R/NN-688766 |  | SO | 2022-10-28 | TNJ378 | 4G_FD900_TNJ378 | 4G_FD2100_TNJ378 | 4G_TD_TNJ378 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211686063 | 2022-11-07 | P/FVC/MDS/1114846/2022 | 2022-11-22 | ST202211685762 | 2022-11-07 | P/FVC/MDS/1114622/2022 | 2022-11-15 | ST202211681248 | 2022-11-04 | P/FVC/MDS/1114577/2022 | 2022-11-15 | ST202211685318 | 2022-11-07 | P/FBW/MDS/1114702/2022 | 2022-11-16
2673 | PRTHC2 | PRTHC2 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/23382 | T22TN05279 |  | SO | 2022-10-28 | PRTHC2 | 4G_FD900_PRTHC2 | 4G_FD2100_PRTHC2 | 4G_TD_PRTHC2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680970 | 2022-11-04 | P/FVC/MDS/1114788/2022 | 2022-11-22 | ST202211685792 | 2022-11-07 | P/FVC/MDS/1114630/2022 | 2022-11-15 | ST202211682848 | 2022-11-05 | P/FVC/MDS/1114584/2022 | 2022-11-15 | ST202211685334 | 2022-11-07 | P/FBW/MDS/1114710/2022 | 2022-11-16
2674 | GDHM50 | GDHM50 | Vellore | Vellore |  | ROTN | Indus | IN-3137103 | R/NN-664985 |  | SO | 2022-10-28 | GDHM50 | 4G_FD900_GDHM50 | 4G_FD2100_GDHM50 | 4G_TD_GDHM50 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680682 | 2022-11-04 | P/FVC/MDS/1114778/2022 | 2022-11-22 | ST202211685757 | 2022-11-07 | P/FVC/MDS/1114619/2022 | 2022-11-15 | ST202211681244 | 2022-11-04 | P/FVC/MDS/1114575/2022 | 2022-11-15 | ST202211685310 | 2022-11-07 | P/FBW/MDS/1114700/2022 | 2022-11-16
2675 | ALTCB2 | ALTCB2 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/23345 | T22TN04336 |  | SO | 2022-10-28 | ALTCB2 | 4G_FD900_ALTCB2 | 4G_FD2100_ALTCB2 | 4G_TD_ALTCB2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681013 | 2022-11-04 | P/FVC/MDS/1114793/2022 | 2022-11-22 | ST202211685812 | 2022-11-07 | P/FVC/MDS/1114635/2022 | 2022-11-15 | ST202211682946 | 2022-11-05 | P/FVC/MDS/1114588/2022 | 2022-11-15 | ST202211685347 | 2022-11-07 | P/FBW/MDS/1114715/2022 | 2022-11-16
2676 | VLLPT3 | VLLPT3 | Salem | Vellore |  | ROTN | Indus | IN-3155418 | R/NN-688809 |  |  | 2022-10-28 | VLLPT3 | 4G_FD900_VLLPT3 | 4G_FD2100_VLLPT3 | 4G_TD_VLLPT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211678904 | 2022-11-02 | P/FVC/MDS/1114777/2022 | 2022-11-22 | ST202211685756 | 2022-11-07 | P/FVC/MDS/1114618/2022 | 2022-11-15 | ST202211681243 | 2022-11-04 | P/FVC/MDS/1114574/2022 | 2022-11-15 | ST202211685309 | 2022-11-07 | P/FBW/MDS/1114699/2022 | 2022-11-16
2677 | CHNGR2 | CHNGR2 | Salem | Vellore |  | ROTN | Indus | IN-3144081 | R/NN-675340 |  | SO | 2022-10-28 | CHNGR2 | 4G_FD900_CHNGR2 | 4G_FD2100_CHNGR2 | 4G_TD_CHNGR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680683 | 2022-11-04 | P/FVC/MDS/1114779/2022 | 2022-11-22 | ST202211685760 | 2022-11-07 | P/FVC/MDS/1114620/2022 | 2022-11-15 | ST202211681245 | 2022-11-04 | P/FVC/MDS/1114576/2022 | 2022-11-15 | ST202211685311 | 2022-11-07 | P/FBW/MDS/1114701/2022 | 2022-11-16
2678 | UTMER8 | UTMER8 | Kancheepuram | Chennai |  | ROTN | ATC | TN/KA/AT/23510 | T22TN06050 |  | SO | 2022-10-28 | UTMER8 | 4G_FD900_UTMER8 | 4G_FD2100_UTMER8 | 4G_TD_UTMER8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681000 | 2022-11-04 | P/FVC/MDS/1114792/2022 | 2022-11-22 | ST202211685804 | 2022-11-07 | P/FVC/MDS/1114634/2022 | 2022-11-15 | ST202211682945 | 2022-11-05 | P/FVC/MDS/1114587/2022 | 2022-11-15 | ST202211685346 | 2022-11-07 | P/FBW/MDS/1114714/2022 | 2022-11-16
2679 | KTKEN2 | KTKEN2 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/23527 | T22TN06173 |  | SO | 2022-10-28 | KTKEN2 | 4G_FD900_KTKEN2 | 4G_FD2100_KTKEN2 | 4G_TD_KTKEN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680969 | 2022-11-04 | P/FVC/MDS/1114787/2022 | 2022-11-22 | ST202211685791 | 2022-11-07 | P/FVC/MDS/1114629/2022 | 2022-11-15 | ST202211682847 | 2022-11-05 | P/FVC/MDS/1114583/2022 | 2022-11-15 | ST202211685333 | 2022-11-07 | P/FBW/MDS/1114709/2022 | 2022-11-16
2680 | PLDM23 | PLDM23 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3152411 | R/NN-685372 |  | SO | 2022-10-28 | PLDM23 | 4G_FD900_PLDM23 | 4G_FD2100_PLDM23 | 4G_TD_PLDM23 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211680685 | 2022-11-04 | P/FVC/MDS/1114781/2022 | 2022-11-22 | ST202211685770 | 2022-11-07 | P/FVC/MDS/1114623/2022 | 2022-11-15 | ST202211681249 | 2022-11-04 | P/FVC/MDS/1114578/2022 | 2022-11-15 | ST202211685319 | 2022-11-07 | P/FBW/MDS/1114703/2022 | 2022-11-16
2681 | TRY427 | TRY427 | Tiruchirappalli | Trichy |  | ROTN | ATC | TN/TC/AT/23502 | T22TN06021 |  | SO | 2022-10-28 | TRY427 | 4G_FD900_TRY427 | 4G_FD2100_TRY427 | 4G_TD_TRY427 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680689 | 2022-11-04 | P/FVC/MDS/1114784/2022 | 2022-11-22 | ST202211685777 | 2022-11-07 | P/FVC/MDS/1114626/2022 | 2022-11-15 | ST202211681257 | 2022-11-04 | P/FVC/MDS/1114580/2022 | 2022-11-15 | ST202211685325 | 2022-11-07 | P/FBW/MDS/1114706/2022 | 2022-11-16
2682 | ERIUR2 | ERIUR2 | Kancheepuram | Chennai |  | ROTN | ATC | TN/KA/AT/23531 | T22TN06177 |  | SO | 2022-10-28 | ERIUR2 | 4G_FD900_ERIUR2 | 4G_FD2100_ERIUR2 | 4G_TD_ERIUR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680690 | 2022-11-04 | P/FVC/MDS/1114785/2022 | 2022-11-22 | ST202211685778 | 2022-11-07 | P/FVC/MDS/1114627/2022 | 2022-11-15 | ST202211681258 | 2022-11-04 | P/FVC/MDS/1114581/2022 | 2022-11-15 | ST202211685326 | 2022-11-07 | P/FBW/MDS/1114707/2022 | 2022-11-16
2683 | ORND06 | ORND06 | Thanjavur | Trichy |  | ROTN | ATC | TN/TA/AT/23543 | T22TN07272 |  | SO | 2022-10-28 | ORND06 | 4G_FD900_ORND06 | 4G_FD2100_ORND06 | 4G_TD_ORND06 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680988 | 2022-11-04 | P/FVC/MDS/1114789/2022 | 2022-11-22 | ST202211685793 | 2022-11-07 | P/FVC/MDS/1114631/2022 | 2022-11-15 | ST202211682875 | 2022-11-05 | P/FVC/MDS/1114585/2022 | 2022-11-15 | ST202211685338 | 2022-11-07 | P/FBW/MDS/1114711/2022 | 2022-11-16
2684 | ALAN05 | ALAN05 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/23544 | T22TN07273 |  | On Air | 2022-10-28 | ALAN05 | 4G_FD900_ALAN05 | 4G_FD2100_ALAN05 | 4G_TD_ALAN05 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681015 | 2022-11-04 | P/FVC/MDS/1114795/2022 | 2022-11-22 | ST202211685814 | 2022-11-07 | P/FVC/MDS/1114637/2022 | 2022-11-15 | ST202211684498 | 2022-11-05 | P/FVC/MDS/1114590/2022 | 2022-11-15 | ST202211685351 | 2022-11-07 | P/FBW/MDS/1114717/2022 | 2022-11-16
2685 | SEMBA8 | SEMBA8 |  |  |  | CHN | Indus | IN-3152472 | R/NN-685432 |  | SO | 2022-10-28 | SEMBA8 | 4G_FD900_SEMBA8 | 4G_FD2100_SEMBA8 | 4G_TD_SEMBA8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681020 | 2022-11-04 | P/FVC/MDS/1114798/2022 | 2022-11-22 | ST202211685825 | 2022-11-07 | P/FVC/MDS/1114640/2022 | 2022-11-15 | ST202211684510 | 2022-11-05 | P/FVC/MDS/1114591/2022 | 2022-11-15 | ST202211685482 | 2022-11-07 | P/FBW/MDS/1114720/2022 | 2022-11-16
2686 | MADA34 | MADA34 |  |  |  | CHN | Indus | IN-3152387 | R/NN-685341 |  |  | 2022-10-28 | MADA34 | 4G_FD900_MADA34 | 4G_FD2100_MADA34 | 4G_TD_MADA34 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680688 | 2022-11-04 | P/FVC/MDS/1114783/2022 | 2022-11-22 | ST202211685772 | 2022-11-07 | P/FVC/MDS/1114625/2022 | 2022-11-15 | ST202211681256 | 2022-11-04 | P/FVC/MDS/1114579/2022 | 2022-11-15 | ST202211685324 | 2022-11-07 | P/FBW/MDS/1114705/2022 | 2022-11-16
2687 | ALMTI3 | ALMTI3 |  |  |  | CHN | ATC | TN/CH/AT/23542 | T22TN07271 |  | SO | 2022-10-28 | ALMTI3 | 4G_FD900_ALMTI3 | 4G_FD2100_ALMTI3 | 4G_TD_ALMTI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211680968 | 2022-11-04 | P/FVC/MDS/1114786/2022 | 2022-11-22 | ST202211685779 | 2022-11-07 | P/FVC/MDS/1114628/2022 | 2022-11-15 | ST202211682846 | 2022-11-05 | P/FVC/MDS/1114582/2022 | 2022-11-15 | ST202211685332 | 2022-11-07 | P/FBW/MDS/1114708/2022 | 2022-11-16
2688 | JEWEL6 | JEWEL6 |  |  |  | CHN | Indus | IN-3138674 | R/NN-664221 |  |  | 2022-10-28 | JEWEL6 | 4G_FD900_JEWEL6 | 4G_FD2100_JEWEL6 | 4G_TD_JEWEL6 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202211680686 | 2022-11-04 | P/FVC/MDS/1114782/2022 | 2022-11-22 | ST202211685771 | 2022-11-07 | P/FVC/MDS/1114624/2022 | 2022-11-15 | ST202211681217 | 2022-11-04 | P/FVC/MDS/1114568/2022 | 2022-11-15 | ST202211685320 | 2022-11-07 | P/FBW/MDS/1114704/2022 | 2022-11-16
2689 | CWM226 | CWM226 |  |  |  | CHN | Indus | IN-3136032 | R/RES-513752 |  |  | 2022-10-28 | CWM226 | 4G_FD900_CWM226 | 4G_FD2100_CWM226 | 4G_TD_CWM226 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681019 | 2022-11-04 | P/FVC/MDS/1114797/2022 | 2022-11-22 | ST202211685824 | 2022-11-07 | P/FVC/MDS/1114639/2022 | 2022-11-15 | ST202211681226 | 2022-11-04 | P/FVC/MDS/1114571/2022 | 2022-11-15 | ST202211685355 | 2022-11-07 | P/FBW/MDS/1114719/2022 | 2022-11-16
2690 | ARAN06 | ARAN06 |  |  |  | ROTN | Indus | IN-3156013 | R/NN-689746 |  |  | 2022-10-28 | ARAN06 | 4G_FD900_ARAN06 | 4G_FD2100_ARAN06 | 4G_TD_ARAN06 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681024 | 2022-11-04 | P/FVC/MDS/1114801/2022 | 2022-11-22 | ST202211685831 | 2022-11-07 | P/FVC/MDS/1114643/2022 | 2022-11-15 | ST202211681227 | 2022-11-04 | P/FVC/MDS/1114572/2022 | 2022-11-15 | ST202211685487 | 2022-11-07 | P/FBW/MDS/1114723/2022 | 2022-11-16
2691 | MDU428 | MDU428 | Madurai | Madurai |  | ROTN | TVI | - | - |  | On Air | 2022-11-02 | MDU428 | 4G_FD900_MDU428 | 4G_FD2100_MDU428 | 4G_TD_MDU428 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681035 | 2022-11-04 | P/FVC/MDS/1114809/2022 | 2022-11-22 | ST202211685854 | 2022-11-07 | P/FVC/MDS/1114651/2022 | 2022-11-15 | ST202211757971 | 2022-11-22 | P/FVC/MDS/1116763/2022 | 2022-11-29 | ST202211685508 | 2022-11-07 | P/FBW/MDS/1114731/2022 | 2022-11-16
2692 | AASTHA | AASTHA | Nagapattinam | Trichy |  | ROTN | TVI | - | - |  | SO | 2022-11-10 | AASTHA | 4G_FD900_AASTHA | 4G_FD2100_AASTHA | 4G_TD_AASTHA | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714367 | 2022-11-14 | P/FVC/MDS/1115030/2022 | 2022-11-24 | ST202211709428 | 2022-11-12 | P/FVC/MDS/1114904/2022 | 2022-11-24 |  |  |  |  | ST202211714026 | 2022-11-14 | P/FBW/MDS/1114968/2022 | 2022-11-24
2693 | KDBKM3 | KDBKM3 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3155992 | R/NN-689911 |  | SO | 2022-11-09 | KDBKM3 | 4G_FD900_KDBKM3 | 4G_FD2100_KDBKM3 | 4G_TD_KDBKM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714244 | 2022-11-14 | P/FVC/MDS/1115004/2022 | 2022-11-24 | ST202211709141 | 2022-11-12 | P/FVC/MDS/1114879/2022 | 2022-11-24 |  |  |  |  | ST202211713354 | 2022-11-14 | P/FBW/MDS/1114942/2022 | 2022-11-24
2694 | KRKTI2 | KRKTI2 | Thiruvarur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | KRKTI2 | 4G_FD900_KRKTI2 | 4G_FD2100_KRKTI2 | 4G_TD_KRKTI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714266 | 2022-11-14 | P/FVC/MDS/1115009/2022 | 2022-11-24 | ST202211709190 | 2022-11-12 | P/FVC/MDS/1114883/2022 | 2022-11-24 |  |  |  |  | ST202211713371 | 2022-11-14 | P/FBW/MDS/1114947/2022 | 2022-11-24
2695 | AZHGP1 | AZHGP1 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-10 | AZHGP1 | 4G_FD900_AZHGP1 | 4G_FD2100_AZHGP1 | 4G_TD_AZHGP1 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714941 | 2022-11-15 | P/FVC/MDS/1115032/2022 | 2022-11-24 | ST202211711615 | 2022-11-12 | P/FVC/MDS/1114906/2022 | 2022-11-24 |  |  |  |  | ST202211714028 | 2022-11-14 | P/FBW/MDS/1114970/2022 | 2022-11-24
2696 | BLPLM8 | BLPLM8 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3156129 | R/NN-689936 |  | SO | 2022-11-09 | BLPLM8 | 4G_FD900_BLPLM8 | 4G_FD2100_BLPLM8 | 4G_TD_BLPLM8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714219 | 2022-11-14 | P/FVC/MDS/1114998/2022 | 2022-11-24 | ST202211709048 | 2022-11-12 | P/FVC/MDS/1114874/2022 | 2022-11-24 |  |  |  |  | ST202211713339 | 2022-11-14 | P/FBW/MDS/1114936/2022 | 2022-11-24
2697 | MELAN2 | MELAN2 | Pudukkottai | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | MELAN2 | 4G_FD900_MELAN2 | 4G_FD2100_MELAN2 | 4G_TD_MELAN2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714194 | 2022-11-14 | P/FVC/MDS/1114989/2022 | 2022-11-24 | ST202211708856 | 2022-11-12 | P/FVC/MDS/1114865/2022 | 2022-11-24 |  |  |  |  | ST202211713308 | 2022-11-14 | P/FBW/MDS/1114927/2022 | 2022-11-24
2698 | THOZR3 | THOZR3 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | THOZR3 | 4G_FD900_THOZR3 | 4G_FD2100_THOZR3 | 4G_TD_THOZR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714278 | 2022-11-14 | P/FVC/MDS/1115015/2022 | 2022-11-24 | ST202211709258 | 2022-11-12 | P/FVC/MDS/1114889/2022 | 2022-11-24 |  |  |  |  | ST202211713384 | 2022-11-14 | P/FBW/MDS/1114953/2022 | 2022-11-24
2699 | MDLGM2 | MDLGM2 | Kanniyakumari | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | MDLGM2 | 4G_FD900_MDLGM2 | 4G_FD2100_MDLGM2 | 4G_TD_MDLGM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681105 | 2022-11-04 | P/FVC/MDS/1114829/2022 | 2022-11-22 | ST202211685909 | 2022-11-07 | P/FVC/MDS/1114671/2022 | 2022-11-15 |  |  |  |  | ST202211685568 | 2022-11-07 | P/FBW/MDS/1114750/2022 | 2022-11-16
2700 | VDIYM3 | VDIYM3 | Karur | Coimbatore |  | ROTN | Indus | IN-3156575 | R/NN-690553 |  | SO | 2022-11-09 | VDIYM3 | 4G_FD900_VDIYM3 | 4G_FD2100_VDIYM3 | 4G_TD_VDIYM3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714303 | 2022-11-14 | P/FVC/MDS/1115022/2022 | 2022-11-24 | ST202211709341 | 2022-11-12 | P/FVC/MDS/1114896/2022 | 2022-11-24 |  |  |  |  | ST202211713995 | 2022-11-14 | P/FBW/MDS/1114960/2022 | 2022-11-24
2701 | TNJ180 | TNJ180 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-10 | TNJ180 | 4G_FD900_TNJ180 | 4G_FD2100_TNJ180 | 4G_TD_TNJ180 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714942 | 2022-11-15 | P/FVC/MDS/1115033/2022 | 2022-11-24 | ST202211711616 | 2022-11-12 | P/FVC/MDS/1114907/2022 | 2022-11-24 | ST202212858167 | 2022-12-27 | 0 |  | ST202211714029 | 2022-11-14 | P/FBW/MDS/1114971/2022 | 2022-11-24
2702 | SLM376 | SLM376 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/23064 | T22TN01076 |  | SO | 2022-11-09 | SLM376 | 4G_FD900_SLM376 | 4G_FD2100_SLM376 | 4G_TD_SLM376 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714204 | 2022-11-14 | P/FVC/MDS/1114993/2022 | 2022-11-24 | ST202211709011 | 2022-11-12 | P/FVC/MDS/1114869/2022 | 2022-11-24 | ST202212839568 | 2022-12-22 |  |  | ST202211713326 | 2022-11-14 | P/FBW/MDS/1114931/2022 | 2022-11-24
2703 | VDKDU2 | VDKDU2 | Pudukkottai | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | VDKDU2 | 4G_FD900_VDKDU2 | 4G_FD2100_VDKDU2 | 4G_TD_VDKDU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681036 | 2022-11-04 | P/FVC/MDS/1114810/2022 | 2022-11-22 | ST202211685855 | 2022-11-07 | P/FVC/MDS/1114652/2022 | 2022-11-15 |  |  |  |  | ST202211685513 | 2022-11-07 | P/FBW/MDS/1114732/2022 | 2022-11-16
2704 | KUDYP2 | KUDYP2 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3154220 | R/NN-687580 |  | SO | 2022-11-09 | KUDYP2 | 4G_FD900_KUDYP2 | 4G_FD2100_KUDYP2 | 4G_TD_KUDYP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714366 | 2022-11-14 | P/FVC/MDS/1115029/2022 | 2022-11-24 | ST202211709426 | 2022-11-12 | P/FVC/MDS/1114903/2022 | 2022-11-24 |  |  |  |  | ST202211714018 | 2022-11-14 | P/FBW/MDS/1114967/2022 | 2022-11-24
2705 | TVLR53 | TVLR53 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | TVLR53 | 4G_FD900_TVLR53 | 4G_FD2100_TVLR53 | 4G_TD_TVLR53 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714267 | 2022-11-14 | P/FVC/MDS/1115010/2022 | 2022-11-24 | ST202211709232 | 2022-11-12 | P/FVC/MDS/1114884/2022 | 2022-11-24 |  |  |  |  | ST202211713372 | 2022-11-14 | P/FBW/MDS/1114948/2022 | 2022-11-24
2706 | DPI063 | DPI063 | Dharmapuri | Vellore |  | ROTN | ATC | TN/DH/AT/23279 | T22TN04135 |  | SO | 2022-11-02 | DPI063 | 4G_FD900_DPI063 | 4G_FD2100_DPI063 | 4G_TD_DPI063 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681148 | 2022-11-04 | P/FVC/MDS/1114841/2022 | 2022-11-22 | ST202211685940 | 2022-11-07 | P/FVC/MDS/1114683/2022 | 2022-11-15 |  |  |  |  | ST202211685592 | 2022-11-07 | P/FBW/MDS/1114762/2022 | 2022-11-16
2707 | TENI40 | TENI40 | Theni | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | TENI40 | 4G_FD900_TENI40 | 4G_FD2100_TENI40 | 4G_TD_TENI40 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681041 | 2022-11-04 | P/FVC/MDS/1114811/2022 | 2022-11-22 | ST202211685859 | 2022-11-07 | P/FVC/MDS/1114653/2022 | 2022-11-15 |  |  |  |  | ST202211685514 | 2022-11-07 | P/FBW/MDS/1114733/2022 | 2022-11-16
2708 | KPNM06 | KPNM06 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3148266 | R/RES-513865 |  | On Air | 2022-11-09 | KPNM06 | 4G_FD900_KPNM06 | 4G_FD2100_KPNM06 | 4G_TD_KPNM06 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714251 | 2022-11-14 | P/FVC/MDS/1115006/2022 | 2022-11-24 | ST202211709188 | 2022-11-12 | P/FVC/MDS/1114881/2022 | 2022-11-24 |  |  |  |  | ST202211713361 | 2022-11-14 | P/FBW/MDS/1114944/2022 | 2022-11-24
2709 | VMETP2 | VMETP2 | Salem | Vellore |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | VMETP2 | 4G_FD900_VMETP2 | 4G_FD2100_VMETP2 | 4G_TD_VMETP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714202 | 2022-11-14 | P/FVC/MDS/1114991/2022 | 2022-11-24 | ST202211708937 | 2022-11-12 | P/FVC/MDS/1114867/2022 | 2022-11-24 |  |  |  |  | ST202211713318 | 2022-11-14 | P/FBW/MDS/1114929/2022 | 2022-11-24
2710 | ERAL03 | ERAL03 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | On Air | 2022-11-02 | ERAL03 | 4G_FD900_ERAL03 | 4G_FD2100_ERAL03 | 4G_TD_ERAL03 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211681106 | 2022-11-04 | P/FVC/MDS/1114830/2022 | 2022-11-22 | ST202211685914 | 2022-11-07 | P/FVC/MDS/1114672/2022 | 2022-11-15 |  |  |  |  | ST202211685569 | 2022-11-07 | P/FBW/MDS/1114751/2022 | 2022-11-16
2711 | KLRPM2 | KLRPM2 | Thoothukkudi | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | KLRPM2 | 4G_FD900_KLRPM2 | 4G_FD2100_KLRPM2 | 4G_TD_KLRPM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681042 | 2022-11-04 | P/FVC/MDS/1114812/2022 | 2022-11-22 | ST202211685860 | 2022-11-07 | P/FVC/MDS/1114654/2022 | 2022-11-15 |  |  |  |  | ST202211685515 | 2022-11-07 | P/FBW/MDS/1114734/2022 | 2022-11-16
2712 | CHNPK2 | CHNPK2 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | On Air | 2022-11-02 | CHNPK2 | 4G_FD900_CHNPK2 | 4G_FD2100_CHNPK2 | 4G_TD_CHNPK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681043 | 2022-11-04 | P/FVC/MDS/1114813/2022 | 2022-11-22 | ST202211685861 | 2022-11-07 | P/FVC/MDS/1114655/2022 | 2022-11-15 |  |  |  |  | ST202211685517 | 2022-11-07 | P/FBW/MDS/1114735/2022 | 2022-11-16
2713 | PDVL04 | PDVL04 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | PDVL04 | 4G_FD900_PDVL04 | 4G_FD2100_PDVL04 | 4G_TD_PDVL04 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681051 | 2022-11-04 | P/FVC/MDS/1114814/2022 | 2022-11-22 | ST202211685872 | 2022-11-07 | P/FVC/MDS/1114656/2022 | 2022-11-15 |  |  |  |  | ST202211685518 | 2022-11-07 | P/FBW/MDS/1114736/2022 | 2022-11-16
2714 | NTHEM2 | NTHEM2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | NTHEM2 | 4G_FD900_NTHEM2 | 4G_FD2100_NTHEM2 | 4G_TD_NTHEM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714273 | 2022-11-14 | P/FVC/MDS/1115013/2022 | 2022-11-24 | ST202211709256 | 2022-11-12 | P/FVC/MDS/1114887/2022 | 2022-11-24 |  |  |  |  | ST202211713381 | 2022-11-14 | P/FBW/MDS/1114951/2022 | 2022-11-24
2715 | VITPL2 | VITPL2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | VITPL2 | 4G_FD900_VITPL2 | 4G_FD2100_VITPL2 | 4G_TD_VITPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714279 | 2022-11-14 | P/FVC/MDS/1115016/2022 | 2022-11-24 | ST202211709284 | 2022-11-12 | P/FVC/MDS/1114890/2022 | 2022-11-24 |  |  |  |  | ST202211713977 | 2022-11-14 | P/FBW/MDS/1114954/2022 | 2022-11-24
2716 | NEIKP2 | NEIKP2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | NEIKP2 | 4G_FD900_NEIKP2 | 4G_FD2100_NEIKP2 | 4G_TD_NEIKP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714268 | 2022-11-14 | P/FVC/MDS/1115011/2022 | 2022-11-24 | ST202211709233 | 2022-11-12 | P/FVC/MDS/1114885/2022 | 2022-11-24 |  |  |  |  | ST202211713379 | 2022-11-14 | P/FBW/MDS/1114949/2022 | 2022-11-24
2717 | PRPKM3 | PRPKM3 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | PRPKM3 | 4G_FD900_PRPKM3 | 4G_FD2100_PRPKM3 | 4G_TD_PRPKM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211681052 | 2022-11-04 | P/FVC/MDS/1114815/2022 | 2022-11-22 | ST202211685873 | 2022-11-07 | P/FVC/MDS/1114657/2022 | 2022-11-15 |  |  |  |  | ST202211685519 | 2022-11-07 | P/FBW/MDS/1114737/2022 | 2022-11-16
2718 | TTNI19 | TTNI19 | Thiruvallur | Chennai |  | ROTN | ATC | TN/TU/AT/23501 | T22TN06020 |  | SO | 2022-11-09 | TTNI19 | 4G_FD900_TTNI19 | 4G_FD2100_TTNI19 | 4G_TD_TTNI19 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714203 | 2022-11-14 | P/FVC/MDS/1114992/2022 | 2022-11-24 | ST202211708938 | 2022-11-12 | P/FVC/MDS/1114868/2022 | 2022-11-24 |  |  |  |  | ST202211713319 | 2022-11-14 | P/FBW/MDS/1114930/2022 | 2022-11-24
2719 | MANIM2 | MANIM2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | MANIM2 | 4G_FD900_MANIM2 | 4G_FD2100_MANIM2 | 4G_TD_MANIM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714280 | 2022-11-14 | P/FVC/MDS/1115017/2022 | 2022-11-24 | ST202211709285 | 2022-11-12 | P/FVC/MDS/1114891/2022 | 2022-11-24 |  |  |  |  | ST202211713978 | 2022-11-14 | P/FBW/MDS/1114955/2022 | 2022-11-24
2720 | TIRUR5 | TIRUR5 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | TIRUR5 | 4G_FD900_TIRUR5 | 4G_FD2100_TIRUR5 | 4G_TD_TIRUR5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681053 | 2022-11-04 | P/FVC/MDS/1114816/2022 | 2022-11-22 | ST202211685876 | 2022-11-07 | P/FVC/MDS/1114658/2022 | 2022-11-15 |  |  |  |  | ST202211685526 | 2022-11-07 | P/FBW/MDS/1114738/2022 | 2022-11-16
2721 | IKADU2 | IKADU2 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | IKADU2 | 4G_FD900_IKADU2 | 4G_FD2100_IKADU2 | 4G_TD_IKADU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681061 | 2022-11-04 | P/FVC/MDS/1114817/2022 | 2022-11-22 | ST202211685877 | 2022-11-07 | P/FVC/MDS/1114659/2022 | 2022-11-15 |  |  |  |  | ST202211685527 | 2022-11-07 | P/FBW/MDS/1114739/2022 | 2022-11-16
2722 | KRKDL3 | KRKDL3 | Cuddalore | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | KRKDL3 | 4G_FD900_KRKDL3 | 4G_FD2100_KRKDL3 | 4G_TD_KRKDL3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714292 | 2022-11-14 | P/FVC/MDS/1115018/2022 | 2022-11-24 | ST202211709286 | 2022-11-12 | P/FVC/MDS/1114892/2022 | 2022-11-24 |  |  |  |  | ST202211713979 | 2022-11-14 | P/FBW/MDS/1114956/2022 | 2022-11-24
2723 | MDU552 | MDU552 | Madurai | Madurai |  | ROTN | ATC | TN/MU/AT/23526 | T22TN06172 |  | SO | 2022-11-02 | MDU552 | 4G_FD900_MDU552 | 4G_FD2100_MDU552 | 4G_TD_MDU552 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681113 | 2022-11-04 | P/FVC/MDS/1114834/2022 | 2022-11-22 | ST202211685920 | 2022-11-07 | P/FVC/MDS/1114676/2022 | 2022-11-15 | ST202212839571 | 2022-12-22 |  |  | ST202211685579 | 2022-11-07 | P/FBW/MDS/1114755/2022 | 2022-11-16
2724 | TUT158 | TUT158 | Thoothukkudi | Madurai |  | ROTN | Indus | IN-3152391 | R/NN-685354 |  | SO | 2022-11-10 | TUT158 | 4G_FD900_TUT158 | 4G_FD2100_TUT158 | 4G_TD_TUT158 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714968 | 2022-11-15 | P/FVC/MDS/1115044/2022 | 2022-11-24 | ST202211711714 | 2022-11-12 | P/FVC/MDS/1114918/2022 | 2022-11-24 |  |  |  |  | ST202211714059 | 2022-11-14 | P/FBW/MDS/1114982/2022 | 2022-11-24
2725 | GMPD30 | GMPD30 | Thiruvallur | Chennai |  | ROTN | TVI | - | - |  | SO | 2022-11-09 | GMPD30 | 4G_FD900_GMPD30 | 4G_FD2100_GMPD30 | 4G_TD_GMPD30 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714263 | 2022-11-14 | P/FVC/MDS/1115008/2022 | 2022-11-24 | ST202211709189 | 2022-11-12 | P/FVC/MDS/1114882/2022 | 2022-11-24 |  |  |  |  | ST202211713363 | 2022-11-14 | P/FBW/MDS/1114946/2022 | 2022-11-24
2726 | GMPD34 | GMPD34 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | GMPD34 | 4G_FD900_GMPD34 | 4G_FD2100_GMPD34 | 4G_TD_GMPD34 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681093 | 2022-11-04 | P/FVC/MDS/1114826/2022 | 2022-11-22 | ST202211685900 | 2022-11-07 | P/FVC/MDS/1114668/2022 | 2022-11-15 |  |  |  |  | ST202211685565 | 2022-11-07 | P/FBW/MDS/1114747/2022 | 2022-11-16
2727 | KPTI08 | KPTI08 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | KPTI08 | 4G_FD900_KPTI08 | 4G_FD2100_KPTI08 | 4G_TD_KPTI08 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714195 | 2022-11-14 | P/FVC/MDS/1114990/2022 | 2022-11-24 | ST202211708936 | 2022-11-12 | P/FVC/MDS/1114866/2022 | 2022-11-24 |  |  |  |  | ST202211713317 | 2022-11-14 | P/FBW/MDS/1114928/2022 | 2022-11-24
2728 | VLLKT3 | VLLKT3 | Kancheepuram | Chennai |  | ROTN | ATC | TN/KA/AT/23532 | T22TN06178 |  | SO | 2022-11-02 | VLLKT3 | 4G_FD900_VLLKT3 | 4G_FD2100_VLLKT3 | 4G_TD_VLLKT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681127 | 2022-11-04 | P/FVC/MDS/1114840/2022 | 2022-11-22 | ST202211685938 | 2022-11-07 | P/FVC/MDS/1114682/2022 | 2022-11-15 |  |  |  |  | ST202211685591 | 2022-11-07 | P/FBW/MDS/1114761/2022 | 2022-11-16
2729 | NPLI10 | NPLI10 | Vellore | Vellore |  | ROTN | Indus | IN-3156964 | R/NN-691031 |  | SO | 2022-11-10 | NPLI10 | 4G_FD900_NPLI10 | 4G_FD2100_NPLI10 | 4G_TD_NPLI10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714950 | 2022-11-15 | P/FVC/MDS/1115037/2022 | 2022-11-24 | ST202211711660 | 2022-11-12 | P/FVC/MDS/1114911/2022 | 2022-11-24 | ST202301004041 | 2023-01-03 | 0 |  | ST202211714034 | 2022-11-14 | P/FBW/MDS/1114975/2022 | 2022-11-24
2730 | KOMBI2 | KOMBI2 | Theni | Madurai |  | ROTN | ATC | TN/TH/AT/23534 | T22TN06180 |  | SO | 2022-11-02 | KOMBI2 | 4G_FD900_KOMBI2 | 4G_FD2100_KOMBI2 | 4G_TD_KOMBI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681118 | 2022-11-04 | P/FVC/MDS/1114836/2022 | 2022-11-22 | ST202211685932 | 2022-11-07 | P/FVC/MDS/1114678/2022 | 2022-11-15 |  |  |  |  | ST202211685585 | 2022-11-07 | P/FBW/MDS/1114757/2022 | 2022-11-16
2731 | SLM435 | SLM435 | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/23536 | T22TN06182 |  | SO | 2022-11-02 | SLM435 | 4G_FD900_SLM435 | 4G_FD2100_SLM435 | 4G_TD_SLM435 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681126 | 2022-11-04 | P/FVC/MDS/1114839/2022 | 2022-11-22 | ST202211685937 | 2022-11-07 | P/FVC/MDS/1114681/2022 | 2022-11-15 |  |  |  |  | ST202211685590 | 2022-11-07 | P/FBW/MDS/1114760/2022 | 2022-11-16
2732 | TKOL10 | TKOL10 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | TKOL10 | 4G_FD900_TKOL10 | 4G_FD2100_TKOL10 | 4G_TD_TKOL10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681079 | 2022-11-04 | P/FVC/MDS/1114824/2022 | 2022-11-22 | ST202211685898 | 2022-11-07 | P/FVC/MDS/1114666/2022 | 2022-11-15 |  |  |  |  | ST202211685560 | 2022-11-07 | P/FBW/MDS/1114745/2022 | 2022-11-16
2733 | TKOL11 | TKOL11 | Vellore | Vellore |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | TKOL11 | 4G_FD900_TKOL11 | 4G_FD2100_TKOL11 | 4G_TD_TKOL11 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681080 | 2022-11-04 | P/FVC/MDS/1114825/2022 | 2022-11-22 | ST202211685899 | 2022-11-07 | P/FVC/MDS/1114667/2022 | 2022-11-15 |  |  |  |  | ST202211685561 | 2022-11-07 | P/FBW/MDS/1114746/2022 | 2022-11-16
2734 | ERRPK2 | ERRPK2 | Puducherry | Trichy |  | ROTN | ATC | TN/VLP/AT/23559 | T22TN07508 |  | SO | 2022-11-09 | ERRPK2 | 4G_FD900_ERRPK2 | 4G_FD2100_ERRPK2 | 4G_TD_ERRPK2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714315 | 2022-11-14 | P/FVC/MDS/1115026/2022 | 2022-11-24 | ST202211709369 | 2022-11-12 | P/FVC/MDS/1114900/2022 | 2022-11-24 |  |  |  |  | ST202211714003 | 2022-11-14 | P/FBW/MDS/1114964/2022 | 2022-11-24
2735 | THIRP2 | THIRP2 | Coimbatore | Coimbatore |  | ROTN | Ascend | - | - |  | SO | 2022-11-02 | THIRP2 | 4G_FD900_THIRP2 | 4G_FD2100_THIRP2 | 4G_TD_THIRP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681094 | 2022-11-04 | P/FVC/MDS/1114827/2022 | 2022-11-22 | ST202211685907 | 2022-11-07 | P/FVC/MDS/1114669/2022 | 2022-11-15 |  |  |  |  | ST202211685566 | 2022-11-07 | P/FBW/MDS/1114748/2022 | 2022-11-16
2736 | MDKI24 | MDKI24 | Coimbatore | Coimbatore |  | ROTN | Summit | I-TN-CMBR-ENB-0528 | SR-TN001193 |  | SO | 2022-11-10 | MDKI24 | 4G_FD900_MDKI24 | 4G_FD2100_MDKI24 | 4G_TD_MDKI24 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714965 | 2022-11-15 | P/FVC/MDS/1115042/2022 | 2022-11-24 | ST202211711689 | 2022-11-12 | P/FVC/MDS/1114916/2022 | 2022-11-24 |  |  |  |  | ST202211714046 | 2022-11-14 | P/FBW/MDS/1114980/2022 | 2022-11-24
2737 | TMPKM2 | TMPKM2 | Thiruvallur | Chennai |  | ROTN | Summit | I-TN-TMPK-ENB-9002 | SR-TN001195 |  | SO | 2022-11-09 | TMPKM2 | 4G_FD900_TMPKM2 | 4G_FD2100_TMPKM2 | 4G_TD_TMPKM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714210 | 2022-11-14 | P/FVC/MDS/1114994/2022 | 2022-11-24 | ST202211709012 | 2022-11-12 | P/FVC/MDS/1114870/2022 | 2022-11-24 |  |  |  |  | ST202211713327 | 2022-11-14 | P/FBW/MDS/1114932/2022 | 2022-11-24
2738 | PNRI37 | PNRI37 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | PNRI37 | 4G_FD900_PNRI37 | 4G_FD2100_PNRI37 | 4G_TD_PNRI37 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714272 | 2022-11-14 | P/FVC/MDS/1115012/2022 | 2022-11-24 | ST202211709234 | 2022-11-12 | P/FVC/MDS/1114886/2022 | 2022-11-24 |  |  |  |  | ST202211713380 | 2022-11-14 | P/FBW/MDS/1114950/2022 | 2022-11-24
2739 | UTKTI8 | UTKTI8 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | UTKTI8 | 4G_FD900_UTKTI8 | 4G_FD2100_UTKTI8 | 4G_TD_UTKTI8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714274 | 2022-11-14 | P/FVC/MDS/1115014/2022 | 2022-11-24 | ST202211709257 | 2022-11-12 | P/FVC/MDS/1114888/2022 | 2022-11-24 |  |  |  |  | ST202211713383 | 2022-11-14 | P/FBW/MDS/1114952/2022 | 2022-11-24
2740 | VLLR10 | VLLR10 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-09 | VLLR10 | 4G_FD900_VLLR10 | 4G_FD2100_VLLR10 | 4G_TD_VLLR10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714314 | 2022-11-14 | P/FVC/MDS/1115025/2022 | 2022-11-24 | ST202211709368 | 2022-11-12 | P/FVC/MDS/1114899/2022 | 2022-11-24 |  |  |  |  | ST202211714002 | 2022-11-14 | P/FBW/MDS/1114963/2022 | 2022-11-24
2741 | PNRI36 | PNRI36 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3154536 | R/NN-687881 |  | SO | 2022-11-09 | PNRI36 | 4G_FD900_PNRI36 | 4G_FD2100_PNRI36 | 4G_TD_PNRI36 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714252 | 2022-11-14 | P/FVC/MDS/1115007/2022 | 2022-11-24 | ST202211715023 | 2022-11-15 | P/FVC/MDS/1114925/2022 | 2022-11-24 |  |  |  |  | ST202211713362 | 2022-11-14 | P/FBW/MDS/1114945/2022 | 2022-11-24
2742 | KTPD26 | KTPD26 | Vellore | Vellore |  | ROTN | Indus | IN-3154428 | R/NN-687923 |  | SO | 2022-11-02 | KTPD26 | 4G_FD900_KTPD26 | 4G_FD2100_KTPD26 | 4G_TD_KTPD26 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211681032 | 2022-11-04 | P/FVC/MDS/1114807/2022 | 2022-11-22 | ST202211685850 | 2022-11-07 | P/FVC/MDS/1114649/2022 | 2022-11-15 |  |  |  |  | ST202211685506 | 2022-11-07 | P/FBW/MDS/1114729/2022 | 2022-11-16
2743 | ARPTI2 | ARPTI2 | Vellore | Vellore |  | ROTN | Indus | IN-3154431 | R/NN-687926 |  | SO | 2022-11-10 | ARPTI2 | 4G_FD900_ARPTI2 | 4G_FD2100_ARPTI2 | 4G_TD_ARPTI2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211714957 | 2022-11-15 | P/FVC/MDS/1115040/2022 | 2022-11-24 | ST202211711687 | 2022-11-12 | P/FVC/MDS/1114914/2022 | 2022-11-24 | ST202212780720 | 2022-12-02 | P/FVC/MDS/1118291/2022 | 2022-12-07 | ST202211714043 | 2022-11-14 | P/FBW/MDS/1114978/2022 | 2022-11-24
2744 | KRNPT6 | KRNPT6 | Vellore | Vellore |  | ROTN | ATC | TN/VE/BS/13778 | - |  | On Air | 2022-11-09 | KRNPT6 | 4G_FD900_KRNPT6 | 4G_FD2100_KRNPT6 | 4G_TD_KRNPT6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714250 | 2022-11-14 | P/FVC/MDS/1115005/2022 | 2022-11-24 | ST202211709142 | 2022-11-12 | P/FVC/MDS/1114880/2022 | 2022-11-24 |  |  |  |  | ST202211713355 | 2022-11-14 | P/FBW/MDS/1114943/2022 | 2022-11-24
2745 | KRSGM2 | KRSGM2 | Vellore | Vellore |  | ROTN | Indus | IN-3154381 | R/NN-687854 |  | SO | 2022-11-09 | KRSGM2 | 4G_FD900_KRSGM2 | 4G_FD2100_KRSGM2 | 4G_TD_KRSGM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714220 | 2022-11-14 | P/FVC/MDS/1114999/2022 | 2022-11-24 | ST202211709090 | 2022-11-12 | P/FVC/MDS/1114875/2022 | 2022-11-24 |  |  |  |  | ST202211713340 | 2022-11-14 | P/FBW/MDS/1114937/2022 | 2022-11-24
2746 | TRYR19 | TRYR19 | Tiruchirappalli | Trichy |  | ROTN | ATC | TN/TR/AT/23552 | T22TN07281 |  | SO | 2022-11-02 | TRYR19 | 4G_FD900_TRYR19 | 4G_FD2100_TRYR19 | 4G_TD_TRYR19 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681149 | 2022-11-04 | P/FVC/MDS/1114842/2022 | 2022-11-22 | ST202211685941 | 2022-11-07 | P/FVC/MDS/1114684/2022 | 2022-11-15 |  |  |  |  | ST202211685598 | 2022-11-07 | P/FBW/MDS/1114763/2022 | 2022-11-16
2747 | RSPM16 | RSPM16 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-RAZS-ENB-9002 | SR-TN001197 |  | On Air | 2022-11-10 | RSPM16 | 4G_FD900_RSPM16 | 4G_FD2100_RSPM16 | 4G_TD_RSPM16 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714964 | 2022-11-15 | P/FVC/MDS/1115041/2022 | 2022-11-24 | ST202211711688 | 2022-11-12 | P/FVC/MDS/1114915/2022 | 2022-11-24 |  |  |  |  | ST202211714045 | 2022-11-14 | P/FBW/MDS/1114979/2022 | 2022-11-24
2748 | MARKP2 | MARKP2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3154383 | R/NN-687856 |  | SO | 2022-11-10 | MARKP2 | 4G_FD900_MARKP2 | 4G_FD2100_MARKP2 | 4G_TD_MARKP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714955 | 2022-11-15 | P/FVC/MDS/1115038/2022 | 2022-11-24 | ST202211711661 | 2022-11-12 | P/FVC/MDS/1114912/2022 | 2022-11-24 |  |  |  |  | ST202211714035 | 2022-11-14 | P/FBW/MDS/1114976/2022 | 2022-11-24
2749 | CHRKT2 | CHRKT2 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-09 | CHRKT2 | 4G_FD900_CHRKT2 | 4G_FD2100_CHRKT2 | 4G_TD_CHRKT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714293 | 2022-11-14 | P/FVC/MDS/1115019/2022 | 2022-11-24 | ST202211709315 | 2022-11-12 | P/FVC/MDS/1114893/2022 | 2022-11-24 |  |  |  |  | ST202211713991 | 2022-11-14 | P/FBW/MDS/1114957/2022 | 2022-11-24
2750 | KUPNV2 | KUPNV2 | Ramanathapuram | Madurai |  | ROTN | Summit | I-TN-RMPM-ENB-9054 | SR-TN001198 |  | SO | 2022-11-09 | KUPNV2 | 4G_FD900_KUPNV2 | 4G_FD2100_KUPNV2 | 4G_TD_KUPNV2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714211 | 2022-11-14 | P/FVC/MDS/1114995/2022 | 2022-11-24 | ST202211709013 | 2022-11-12 | P/FVC/MDS/1114871/2022 | 2022-11-24 |  |  |  |  | ST202211713328 | 2022-11-14 | P/FBW/MDS/1114933/2022 | 2022-11-24
2751 | ERMPT4 | ERMPT4 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3154385 | R/NN-687858 |  | SO | 2022-11-09 | ERMPT4 | 4G_FD900_ERMPT4 | 4G_FD2100_ERMPT4 | 4G_TD_ERMPT4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714236 | 2022-11-14 | P/FVC/MDS/1115000/2022 | 2022-11-24 | ST202211709091 | 2022-11-12 | P/FVC/MDS/1114876/2022 | 2022-11-24 |  |  |  |  | ST202211713342 | 2022-11-14 | P/FBW/MDS/1114938/2022 | 2022-11-24
2752 | KANRP2 | KANRP2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3154394 | R/NN-687868 |  | SO | 2022-11-10 | KANRP2 | 4G_FD900_KANRP2 | 4G_FD2100_KANRP2 | 4G_TD_KANRP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714956 | 2022-11-15 | P/FVC/MDS/1115039/2022 | 2022-11-24 | ST202211711662 | 2022-11-12 | P/FVC/MDS/1114913/2022 | 2022-11-24 |  |  |  |  | ST202211714042 | 2022-11-14 | P/FBW/MDS/1114977/2022 | 2022-11-24
2753 | PULIG2 | PULIG2 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-10 | PULIG2 | 4G_FD900_PULIG2 | 4G_FD2100_PULIG2 | 4G_TD_PULIG2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714943 | 2022-11-15 | P/FVC/MDS/1115034/2022 | 2022-11-24 | ST202211711642 | 2022-11-12 | P/FVC/MDS/1114908/2022 | 2022-11-24 |  |  |  |  | ST202211714030 | 2022-11-14 | P/FBW/MDS/1114972/2022 | 2022-11-24
2754 | SLYPL2 | SLYPL2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3154396 | R/NN-687872 |  | SO | 2022-11-10 | SLYPL2 | 4G_FD900_SLYPL2 | 4G_FD2100_SLYPL2 | 4G_TD_SLYPL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714368 | 2022-11-14 | P/FVC/MDS/1115031/2022 | 2022-11-24 | ST202211709430 | 2022-11-12 | P/FVC/MDS/1114905/2022 | 2022-11-24 |  |  |  |  | ST202211714027 | 2022-11-14 | P/FBW/MDS/1114969/2022 | 2022-11-24
2755 | KAMTI8 | KAMTI8 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-10 | KAMTI8 | 4G_FD900_KAMTI8 | 4G_FD2100_KAMTI8 | 4G_TD_KAMTI8 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714948 | 2022-11-15 | P/FVC/MDS/1115035/2022 | 2022-11-24 | ST202211711643 | 2022-11-12 | P/FVC/MDS/1114909/2022 | 2022-11-24 |  |  |  |  | ST202211714031 | 2022-11-14 | P/FBW/MDS/1114973/2022 | 2022-11-24
2756 | OOTY49 | OOTY49 | The Nilgiris | Coimbatore |  | ROTN | Indus | IN-3154853 | R/NN-688431 |  | SO | 2022-11-10 | OOTY49 | 4G_FD900_OOTY49 | 4G_FD2100_OOTY49 | 4G_TD_OOTY49 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714949 | 2022-11-15 | P/FVC/MDS/1115036/2022 | 2022-11-24 | ST202211711644 | 2022-11-12 | P/FVC/MDS/1114910/2022 | 2022-11-24 |  |  |  |  | ST202211714033 | 2022-11-14 | P/FBW/MDS/1114974/2022 | 2022-11-24
2757 | PDY411 | PDY411 | Puducherry | Trichy |  | ROTN | Indus | IN-3156130 | R/NN-689940 |  | SO | 2022-11-10 | PDY411 | 4G_FD900_PDY411 | 4G_FD2100_PDY411 | 4G_TD_PDY411 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211714966 | 2022-11-15 | P/FVC/MDS/1115043/2022 | 2022-11-24 | ST202211711713 | 2022-11-12 | P/FVC/MDS/1114917/2022 | 2022-11-24 | ST202212839572 | 2022-12-22 |  |  | ST202211714047 | 2022-11-14 | P/FBW/MDS/1114981/2022 | 2022-11-24
2758 | IOCL02 | IOCL02 |  |  |  | CHN | Srigom | SG0015 | - |  | On air | 2022-11-09 | IOCL02 | 4G_FD900_IOCL02 | 4G_FD2100_IOCL02 | 4G_TD_IOCL02 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681161 | 2022-11-04 | P/FVC/MDS/1114844/2022 | 2022-11-22 | ST202211684682 | 2022-11-05 | P/FVC/MDS/1114612/2022 | 2022-11-15 |  |  |  |  | ST202211684657 | 2022-11-05 | P/FBW/MDS/1114693/2022 | 2022-11-16
2759 | MGRN19 | MGRN19 |  |  |  | CHN | Indus | IN-3142356 | R/NN-671744 |  | SO | 2022-11-09 | MGRN19 | 4G_FD900_MGRN19 | 4G_FD2100_MGRN19 | 4G_TD_MGRN19 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211714237 | 2022-11-14 | P/FVC/MDS/1115001/2022 | 2022-11-24 | ST202211715022 | 2022-11-15 | P/FVC/MDS/1114924/2022 | 2022-11-24 |  |  |  |  | ST202211713343 | 2022-11-14 | P/FBW/MDS/1114939/2022 | 2022-11-24
2760 | TNYKR3 | TNYKR3 |  |  |  | ROTN | Indus | IN-3155934 | R/NN-689765 |  |  | 2022-11-09 | TNYKR3 | 4G_FD900_TNYKR3 | 4G_FD2100_TNYKR3 | 4G_TD_TNYKR3 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 1905-09-30 | ST202211714218 | 2022-11-14 | P/FVC/MDS/1114997/2022 | 2022-11-24 | ST202211709047 | 2022-11-12 | P/FVC/MDS/1114873/2022 | 2022-11-24 | ST202211690557 | 2022-11-10 | P/FVC/MDS/1114606/2022 | 2022-11-15 | ST202211713335 | 2022-11-14 | P/FBW/MDS/1114935/2022 | 2022-11-24
2761 | TLNYR4 | TLNYR4 |  |  |  | ROTN | Indus | IN-3126445 | R/RES-513751 |  |  | 2022-11-02 | TLNYR4 | 4G_FD900_TLNYR4 | 4G_FD2100_TLNYR4 | 4G_TD_TLNYR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681030 | 2022-11-04 | P/FVC/MDS/1114805/2022 | 2022-11-22 | ST202211685848 | 2022-11-07 | P/FVC/MDS/1114647/2022 | 2022-11-15 | ST202211684515 | 2022-11-05 | P/FVC/MDS/1114594/2022 | 2022-11-15 | ST202211685503 | 2022-11-07 | P/FBW/MDS/1114727/2022 | 2022-11-16
2762 | VLR147 | VLR147 |  |  |  | ROTN | Indus | IN-3156127 | R/NN-689858 |  |  | 2022-11-09 | VLR147 | 4G_FD900_VLR147 | 4G_FD2100_VLR147 | 4G_TD_VLR147 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202211714243 | 2022-11-14 | P/FVC/MDS/1115003/2022 | 2022-11-24 | ST202211709140 | 2022-11-12 | P/FVC/MDS/1114878/2022 | 2022-11-24 | ST202211690583 | 2022-11-10 | P/FVC/MDS/1114608/2022 | 2022-11-15 | ST202211713353 | 2022-11-14 | P/FBW/MDS/1114941/2022 | 2022-11-24
2763 | KUMPA2 | KUMPA2 |  |  |  | ROTN | Indus | IN-3156012 | R/NN-689743 |  |  | 2022-11-09 | KUMPA2 | 4G_FD900_KUMPA2 | 4G_FD2100_KUMPA2 | 4G_TD_KUMPA2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211714193 | 2022-11-14 | P/FVC/MDS/1114988/2022 | 2022-11-24 | ST202211708855 | 2022-11-12 | P/FVC/MDS/1114864/2022 | 2022-11-24 | ST202211690554 | 2022-11-05 | P/FVC/MDS/1114604/2022 | 2022-11-15 | ST202211713307 | 2022-11-14 | P/FBW/MDS/1114926/2022 | 2022-11-24
2764 | PKT231 | PKT231 |  |  |  | ROTN | Indus | IN-3153266 | R/NN-686236 |  |  | 2022-11-02 | PKT231 | 4G_FD900_PKT231 | 4G_FD2100_PKT231 | 4G_TD_PKT231 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681031 | 2022-11-04 | P/FVC/MDS/1114806/2022 | 2022-11-22 | ST202211685849 | 2022-11-07 | P/FVC/MDS/1114648/2022 | 2022-11-15 | ST202211684520 | 2022-11-05 | P/FVC/MDS/1114595/2022 | 2022-11-15 | ST202211685504 | 2022-11-07 | P/FBW/MDS/1114728/2022 | 2022-11-16
2765 | UKLI04 | UKLI04 |  |  |  | ROTN | Indus | IN-3154478 | R/NN-687792 |  |  | 2022-11-09 | UKLI04 | 4G_FD900_UKLI04 | 4G_FD2100_UKLI04 | 4G_TD_UKLI04 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211714242 | 2022-11-14 | P/FVC/MDS/1115002/2022 | 2022-11-24 | ST202211709092 | 2022-11-12 | P/FVC/MDS/1114877/2022 | 2022-11-24 | ST202211690581 | 2022-11-10 | P/FVC/MDS/1114607/2022 | 2022-11-15 | ST202211713344 | 2022-11-14 | P/FBW/MDS/1114940/2022 | 2022-11-24
2766 | GERU40 | GERU40 |  |  |  | CHN | Indus | IN-3154466 | R/NN-687781 |  |  | 2022-11-09 | GERU40 | 4G_FD900_GERU40 | 4G_FD2100_GERU40 | 4G_TD_GERU40 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211714212 | 2022-11-14 | P/FVC/MDS/1114996/2022 | 2022-11-24 | ST202211709046 | 2022-11-12 | P/FVC/MDS/1114872/2022 | 2022-11-24 | ST202211690555 | 2022-11-10 | P/FVC/MDS/1114605/2022 | 2022-11-15 | ST202211713334 | 2022-11-14 | P/FBW/MDS/1114934/2022 | 2022-11-24
2767 | SRTDN2 | SRTDN2 |  |  |  | ROTN | Indus | IN-3156005 | R/NN-688902 |  |  | 2022-11-09 | SRTDN2 | 4G_FD900_SRTDN2 | 4G_FD2100_SRTDN2 | 4G_TD_SRTDN2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211714313 | 2022-11-14 | P/FVC/MDS/1115024/2022 | 2022-11-24 | ST202211709367 | 2022-11-12 | P/FVC/MDS/1114898/2022 | 2022-11-24 | ST202211690613 | 2022-11-10 | P/FVC/MDS/1114610/2022 | 2022-11-15 | ST202211714001 | 2022-11-14 | P/FBW/MDS/1114962/2022 | 2022-11-24
2768 | VAND32 | VAND32 |  |  |  | CHN | Indus | IN-3156002 | R/NN-689056 |  |  | 2022-11-09 | VAND32 | 4G_FD900_VAND32 | 4G_FD2100_VAND32 | 4G_TD_VAND32 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211714305 | 2022-11-14 | P/FVC/MDS/1115023/2022 | 2022-11-24 | ST202211709342 | 2022-11-12 | P/FVC/MDS/1114897/2022 | 2022-11-24 | ST202211690584 | 2022-11-10 | P/FVC/MDS/1114609/2022 | 2022-11-15 | ST202211713996 | 2022-11-14 | P/FBW/MDS/1114961/2022 | 2022-11-24
2769 | HSR179 | HSR179 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/22919 | T22TN00142 |  | SO | 2022-11-23 | HSR179 | 4G_FD900_HSR179 | 4G_FD2100_HSR179 | 4G_TD_HSR179 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202108405002 | 2021-08-02 | P/FVC/MDS/1052821/2021 | 2021-08-20 | ST202212779906 | 2022-12-02 | P/FVC/MDS/1118222/2022 | 2022-12-07 | ST202212780646 | 2022-12-02 | P/FVC/MDS/1118288/2022 | 2022-12-07 | ST202212779586 | 2022-12-01 | P/FBW/MDS/1118132/2022 | 2022-12-07
2770 | ARNI15 | ARNI15 | Tiruvannamalai | Vellore |  | ROTN | Ascend | - | - |  | SO | 2022-11-16 | ARNI15 | 4G_FD900_ARNI15 | 4G_FD2100_ARNI15 | 4G_TD_ARNI15 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106361837 | 2021-06-25 | P/FVC/MDS/1049900/2021 | 2021-08-09 | ST202211729839 | 2022-11-17 | P/FVC/MDS/1115159/2022 | 2022-11-24 |  |  |  |  | ST202211726215 | 2022-11-16 | P/FBW/MDS/1115079/2022 | 2022-11-24
2771 | THATHY | THATHY | Salem | Vellore |  | ROTN | Indus | IN-3158143 | R/NN-692814 |  |  | 2022-11-29 | THATHY | 4G_FD900_THATHY | 4G_FD2100_THATHY | 4G_TD_THATHY | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780579 | 2022-12-02 | P/FVC/MDS/1118339/2022 | 2022-12-08 | ST202212779985 | 2022-12-02 | P/FVC/MDS/1118247/2022 | 2022-12-07 |  |  |  |  | ST202212779634 | 2022-12-01 | P/FBW/MDS/1118155/2022 | 2022-12-07
2772 | PDY336 | PDY336 | Viluppuram | Trichy |  | ROTN | ATC | TN/VLP/AT/23541 | T22TN06187 |  | SO | 2022-11-23 | PDY336 | 4G_FD900_PDY336 | 4G_FD2100_PDY336 | 4G_TD_PDY336 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779861 | 2022-12-02 | P/FVC/MDS/1118207/2022 | 2022-12-07 |  |  |  |  | ST202212779504 | 2022-12-01 | P/FBW/MDS/1118118/2022 | 2022-12-07
2773 | ANIY11 | ANIY11 | Madurai | Madurai |  | ROTN | TVI | - | - |  | SO | 2022-11-16 | ANIY11 | 4G_FD900_ANIY11 | 4G_FD2100_ANIY11 | 4G_TD_ANIY11 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | 1905-09-30 | ST202211738383 | 2022-11-18 | P/FVC/MDS/1115218/2022 | 2022-11-24 | ST202211729836 | 2022-11-17 | P/FVC/MDS/1115156/2022 | 2022-11-24 | ST202212827177 | 2022-12-16 | P/FVC/MDS/1119671/2022 | 2022-12-22 | ST202211726207 | 2022-11-16 | P/FBW/MDS/1115076/2022 | 2022-11-24
2774 | VALGO2 | VALGO2 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3155123 | R/NN-688773 |  | SO | 2022-11-29 | VALGO2 | 4G_FD900_VALGO2 | 4G_FD2100_VALGO2 | 4G_TD_VALGO2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780587 | 2022-12-02 | P/FVC/MDS/1118342/2022 | 2022-12-08 | ST202212780425 | 2022-12-02 | P/FVC/MDS/1118264/2022 | 2022-12-07 |  |  |  |  | ST202212779664 | 2022-12-01 | P/FBW/MDS/1118173/2022 | 2022-12-07
2775 | VINAYA | VINAYA | Salem | Vellore |  | ROTN | ATC | TN/SA/AT/22886 | T21TN10494 |  | SO | 2022-11-29 | VINAYA | 4G_FD900_VINAYA | 4G_FD2100_VINAYA | 4G_TD_VINAYA | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780000 | 2022-12-02 | P/FVC/MDS/1118253/2022 | 2022-12-07 |  |  |  |  | ST202212779645 | 2022-12-01 | P/FBW/MDS/1118161/2022 | 2022-12-07
2776 | ARIYAP | ARIYAP | Tiruvannamalai | Vellore |  | ROTN | ATC | TN/TV/AT/23218 | T22TN02930 |  | SO | 2022-11-18 | ARIYAP | 4G_FD900_ARIYAP | 4G_FD2100_ARIYAP | 4G_TD_ARIYAP | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 | 1906-04-18 | ST202211760983 | 2022-11-25 | P/FVC/MDS/1116869/2022 | 2022-11-29 | ST202211758273 | 2022-11-23 | P/FVC/MDS/1116790/2022 | 2022-11-29 |  |  |  |  | ST202212825534 | 2022-12-16 | P/FBW/MDS/1119670/2022 | 2022-12-22
2777 | AVVOR2 | AVVOR2 | Pudukkottai | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-23 | AVVOR2 | 4G_FD900_AVVOR2 | 4G_FD2100_AVVOR2 | 4G_TD_AVVOR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780497 | 2022-12-02 | P/FVC/MDS/1118313/2022 | 2022-12-08 | ST202212779784 | 2022-12-02 | P/FVC/MDS/1118185/2022 | 2022-12-07 |  |  |  |  | ST202212779434 | 2022-12-01 | P/FBW/MDS/1118096/2022 | 2022-12-07
2778 | ORTHR2 | ORTHR2 | Kancheepuram | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-18 | ORTHR2 | 4G_FD900_ORTHR2 | 4G_FD2100_ORTHR2 | 4G_TD_ORTHR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758288 | 2022-11-23 | P/FVC/MDS/1116794/2022 | 2022-11-29 | ST202211758047 | 2022-11-22 | P/FVC/MDS/1116769/2022 | 2022-11-29 | ST202211758560 | 2022-11-16 | P/FBW/MDS/1116835/2022 | 2022-11-29
2779 | KRUDP2 | KRUDP2 | Erode | Coimbatore |  | ROTN | ATC | TN/ER/AT/23582 | T22TN07578 |  | SO | 2022-11-18 | KRUDP2 | 4G_FD900_KRUDP2 | 4G_FD2100_KRUDP2 | 4G_TD_KRUDP2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211761042 | 2022-11-25 | P/FVC/MDS/1116873/2022 | 2022-11-29 | ST202211758298 | 2022-11-23 | P/FVC/MDS/1116800/2022 | 2022-11-29 |  |  |  |  | ST202211758573 | 2022-11-16 | P/FBW/MDS/1116841/2022 | 2022-11-29
2780 | ILLAYG | ILLAYG | Sivaganga | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-18 | ILLAYG | 4G_FD900_ILLAYG | 4G_FD2100_ILLAYG | 4G_TD_ILLAYG | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211761010 | 2022-11-25 | P/FVC/MDS/1116870/2022 | 2022-11-29 | ST202211758281 | 2022-11-23 | P/FVC/MDS/1116792/2022 | 2022-11-29 |  |  |  |  | ST202211758556 | 2022-11-16 | P/FBW/MDS/1116833/2022 | 2022-11-29
2781 | KRMD16 | KRMD16 | Coimbatore | Coimbatore |  | ROTN | Ascend | - | - |  | SO | 2022-11-18 | KRMD16 | 4G_FD900_KRMD16 | 4G_FD2100_KRMD16 | 4G_TD_KRMD16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758282 | 2022-11-23 | P/FVC/MDS/1116793/2022 | 2022-11-29 | ST202211758026 | 2022-11-22 | P/FVC/MDS/1116768/2022 | 2022-11-29 | ST202211758559 | 2022-11-16 | P/FBW/MDS/1116834/2022 | 2022-11-29
2782 | KLRSR2 | KLRSR2 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3152778 | R/NN-685850 |  | SO | 2022-11-23 | KLRSR2 | 4G_FD900_KLRSR2 | 4G_FD2100_KLRSR2 | 4G_TD_KLRSR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780507 | 2022-12-02 | P/FVC/MDS/1118318/2022 | 2022-12-08 | ST202212779795 | 2022-12-02 | P/FVC/MDS/1118190/2022 | 2022-12-07 |  |  |  |  | ST202212779452 | 2022-12-01 | P/FBW/MDS/1118101/2022 | 2022-12-07
2783 | NGPM23 | NGPM23 | Nagapattinam | Trichy |  | ROTN | Indus | IN-3159455 | R/NN-694327 |  | SO | 2022-11-29 | NGPM23 | 4G_FD900_NGPM23 | 4G_FD2100_NGPM23 | 4G_TD_NGPM23 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780352 | 2022-12-02 | P/FVC/MDS/1118257/2022 | 2022-12-07 |  |  |  |  | ST202212779654 | 2022-12-01 | P/FBW/MDS/1118165/2022 | 2022-12-07
2784 | TATAM2 | TATAM2 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3152779 | R/NN-685851 |  | SO | 2022-11-23 | TATAM2 | 4G_FD900_TATAM2 | 4G_FD2100_TATAM2 | 4G_TD_TATAM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780516 | 2022-12-02 | P/FVC/MDS/1118319/2022 | 2022-12-08 | ST202212779802 | 2022-12-02 | P/FVC/MDS/1118191/2022 | 2022-12-07 |  |  |  |  | ST202212779453 | 2022-12-01 | P/FBW/MDS/1118102/2022 | 2022-12-07
2785 | SNKL16 | SNKL16 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3158603 | R/NN-693268 |  | SO | 2022-11-18 | SNKL16 | 4G_FD900_SNKL16 | 4G_FD2100_SNKL16 | 4G_TD_SNKL16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758302 | 2022-11-23 | P/FVC/MDS/1116804/2022 | 2022-11-29 | ST202211758095 | 2022-11-22 | P/FVC/MDS/1116776/2022 | 2022-11-29 | ST202211758585 | 2022-11-16 | P/FBW/MDS/1116845/2022 | 2022-11-29
2786 | PRNP18 | PRNP18 | Vellore | Vellore |  | ROTN | Indus | IN-3155153 | R/NN-688786 |  | SO | 2022-11-16 | PRNP18 | 4G_FD900_PRNP18 | 4G_FD2100_PRNP18 | 4G_TD_PRNP18 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738429 | 2022-11-18 | P/FVC/MDS/1115235/2022 | 2022-11-24 | ST202211729793 | 2022-11-17 | P/FVC/MDS/1115134/2022 | 2022-11-24 |  |  |  |  | ST202211726158 | 2022-11-16 | P/FBW/MDS/1115054/2022 | 2022-11-24
2787 | MNPTI3 | MNPTI3 | Salem | Vellore |  | ROTN | Indus | IN-3158857 | R/NN-693656 |  | SO | 2022-11-29 | MNPTI3 | 4G_FD900_MNPTI3 | 4G_FD2100_MNPTI3 | 4G_TD_MNPTI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780585 | 2022-12-02 | P/FVC/MDS/1118340/2022 | 2022-12-08 | ST202212780351 | 2022-12-02 | P/FVC/MDS/1118256/2022 | 2022-12-07 |  |  |  |  | ST202212779651 | 2022-12-01 | P/FBW/MDS/1118164/2022 | 2022-12-07
2788 | TTYN10 | TTYN10 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3158604 | R/NN-693269 |  | SO | 2022-11-23 | TTYN10 | 4G_FD900_TTYN10 | 4G_FD2100_TTYN10 | 4G_TD_TTYN10 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780536 | 2022-12-02 | P/FVC/MDS/1118325/2022 | 2022-12-08 | ST202212779859 | 2022-12-02 | P/FVC/MDS/1118205/2022 | 2022-12-07 |  |  |  |  | ST202212779501 | 2022-12-01 | P/FBW/MDS/1118116/2022 | 2022-12-07
2789 | MATH21 | MATH21 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3159839 | R/NN-694707 |  | SO | 2022-11-29 | MATH21 | 4G_FD900_MATH21 | 4G_FD2100_MATH21 | 4G_TD_MATH21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780435 | 2022-12-02 | P/FVC/MDS/1118265/2022 | 2022-12-07 |  |  |  |  | ST202212779669 | 2022-12-01 | P/FBW/MDS/1118174/2022 | 2022-12-07
2790 | PRNI16 | PRNI16 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-16 | PRNI16 | 4G_FD900_PRNI16 | 4G_FD2100_PRNI16 | 4G_TD_PRNI16 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738393 | 2022-11-18 | P/FVC/MDS/1115223/2022 | 2022-11-24 | ST202211729841 | 2022-11-17 | P/FVC/MDS/1115161/2022 | 2022-11-24 |  |  |  |  | ST202211726221 | 2022-11-16 | P/FBW/MDS/1115081/2022 | 2022-11-24
2791 | KNKCI5 | KNKCI5 | Salem | Vellore |  | ROTN | Indus | IN-3159457 | R/NN-694328 |  | SO | 2022-11-23 | KNKCI5 | 4G_FD900_KNKCI5 | 4G_FD2100_KNKCI5 | 4G_TD_KNKCI5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779880 | 2022-12-02 | P/FVC/MDS/1118213/2022 | 2022-12-07 |  |  |  |  | ST202212779512 | 2022-12-01 | P/FBW/MDS/1118123/2022 | 2022-12-07
2792 | PNRI33 | PNRI33 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3152425 | R/NN-685396 |  | SO | 2022-11-29 | PNRI33 | 4G_FD900_PNRI33 | 4G_FD2100_PNRI33 | 4G_TD_PNRI33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780353 | 2022-12-02 | P/FVC/MDS/1118258/2022 | 2022-12-07 |  |  |  |  | ST202212779655 | 2022-12-01 | P/FBW/MDS/1118166/2022 | 2022-12-07
2793 | KDBKM7 | KDBKM7 | Thiruvallur | Chennai |  | ROTN | Ascend | - | - |  | SO | 2022-11-16 | KDBKM7 | 4G_FD900_KDBKM7 | 4G_FD2100_KDBKM7 | 4G_TD_KDBKM7 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738395 | 2022-11-18 | P/FVC/MDS/1115224/2022 | 2022-11-24 | ST202211729845 | 2022-11-17 | P/FVC/MDS/1115162/2022 | 2022-11-24 |  |  |  |  | ST202211726222 | 2022-11-16 | P/FBW/MDS/1115082/2022 | 2022-11-24
2794 | TVLR55 | TVLR55 | Thiruvallur | Chennai |  | ROTN | Indus | IN-3152598 | R/NN-685398 |  | SO | 2022-11-23 | TVLR55 | 4G_FD900_TVLR55 | 4G_FD2100_TVLR55 | 4G_TD_TVLR55 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779816 | 2022-12-02 | P/FVC/MDS/1118194/2022 | 2022-12-07 | ST202301004040 | 2023-01-03 | 0 |  | ST202212779465 | 2022-12-01 | P/FBW/MDS/1118105/2022 | 2022-12-07
2795 | PDPP15 | PDPP15 | Kancheepuram | Chennai |  | ROTN | ATC | TN/KA/AT/23524 | T22TN06170 |  | SO | 2022-11-16 | PDPP15 | 4G_FD900_PDPP15 | 4G_FD2100_PDPP15 | 4G_TD_PDPP15 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738374 | 2022-11-18 | P/FVC/MDS/1115213/2022 | 2022-11-24 | ST202211729822 | 2022-11-17 | P/FVC/MDS/1115151/2022 | 2022-11-24 |  |  |  |  | ST202211726191 | 2022-11-16 | P/FBW/MDS/1115071/2022 | 2022-11-24
2796 | HSR200 | HSR200 | Krishnagiri | Vellore |  | ROTN | ATC | TN/DH/AT/23513 | T22TN06053 |  | SO | 2022-11-16 | HSR200 | 4G_FD900_HSR200 | 4G_FD2100_HSR200 | 4G_TD_HSR200 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738365 | 2022-11-18 | P/FVC/MDS/1115211/2022 | 2022-11-24 | ST202211729818 | 2022-11-17 | P/FVC/MDS/1115149/2022 | 2022-11-24 |  |  |  |  | ST202211726189 | 2022-11-16 | P/FBW/MDS/1115069/2022 | 2022-11-24
2797 | ENATI2 | ENATI2 | Thanjavur | Trichy |  | ROTN | Ascend | - | - |  | SO | 2022-11-16 | ENATI2 | 4G_FD900_ENATI2 | 4G_FD2100_ENATI2 | 4G_TD_ENATI2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738396 | 2022-11-18 | P/FVC/MDS/1115225/2022 | 2022-11-24 | ST202211729846 | 2022-11-17 | P/FVC/MDS/1115163/2022 | 2022-11-24 |  |  |  |  | ST202211726223 | 2022-11-16 | P/FBW/MDS/1115083/2022 | 2022-11-24
2798 | CBE965 | CBE965 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3152412 | R/NN-685373 |  | SO | 2022-11-18 | CBE965 | 4G_FD900_CBE965 | 4G_FD2100_CBE965 | 4G_TD_CBE965 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100 | [5 empty] | ST202211758300 | 2022-11-23 | P/FVC/MDS/1116802/2022 | 2022-11-29 | ST202211758090 | 2022-11-22 | P/FVC/MDS/1116774/2022 | 2022-11-29 | ST202211758580 | 2022-11-16 | P/FBW/MDS/1116843/2022 | 2022-11-29
2799 | SULR28 | SULR28 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-18 | SULR28 | 4G_FD900_SULR28 | 4G_FD2100_SULR28 | 4G_TD_SULR28 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758319 | 2022-11-23 | P/FVC/MDS/1116808/2022 | 2022-11-29 | ST202211758097 | 2022-11-22 | P/FVC/MDS/1116778/2022 | 2022-11-29 | ST202211758600 | 2022-11-16 | P/FBW/MDS/1116849/2022 | 2022-11-29
2800 | KNDNJ2 | KNDNJ2 | Thiruvallur | Chennai |  | ROTN | ATC | TN/TU/AT/23533 | T22TN06179 |  | SO | 2022-11-23 | KNDNJ2 | 4G_FD900_KNDNJ2 | 4G_FD2100_KNDNJ2 | 4G_TD_KNDNJ2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780548 | 2022-12-02 | P/FVC/MDS/1118329/2022 | 2022-12-08 | ST202212779914 | 2022-12-02 | P/FVC/MDS/1118223/2022 | 2022-12-07 |  |  |  |  | ST202212779589 | 2022-12-01 | P/FBW/MDS/1118133/2022 | 2022-12-07
2801 | ILUPR2 | ILUPR2 | Pudukkottai | Trichy |  | ROTN | Indus | IN-3152810 | R/NN-685880 |  | SO | 2022-11-16 | ILUPR2 | 4G_FD900_ILUPR2 | 4G_FD2100_ILUPR2 | 4G_TD_ILUPR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738069 | 2022-11-18 | P/FVC/MDS/1115196/2022 | 2022-11-24 | ST202211729792 | 2022-11-17 | P/FVC/MDS/1115133/2022 | 2022-11-24 | ST202211758001 | 2022-11-22 | P/FVC/MDS/1116766/2022 | 2022-11-29 | ST202211726157 | 2022-11-16 | P/FBW/MDS/1115053/2022 | 2022-11-24
2802 | VLR247 | VLR247 | Vellore | Vellore |  | ROTN | ATC | TN/VE/AT/23539 | T22TN06185 |  | SO | 2022-11-29 | VLR247 | 4G_FD900_VLR247 | 4G_FD2100_VLR247 | 4G_TD_VLR247 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779971 | 2022-12-02 | P/FVC/MDS/1118241/2022 | 2022-12-07 | ST202212780725 | 2022-12-02 | P/FVC/MDS/1118294/2022 | 2022-12-07 | ST202212779628 | 2022-12-01 | P/FBW/MDS/1118149/2022 | 2022-12-07
2803 | PSMU11 | PSMU11 | Erode | Coimbatore |  | ROTN | Indus | IN-3154339 | R/NN-687633 |  | SO | 2022-11-29 | PSMU11 | 4G_FD900_PSMU11 | 4G_FD2100_PSMU11 | 4G_TD_PSMU11 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779957 | 2022-12-02 | P/FVC/MDS/1118238/2022 | 2022-12-07 | ST202212780722 | 2022-12-02 | P/FVC/MDS/1118293/2022 | 2022-12-07 | ST202212779624 | 2022-12-01 | P/FBW/MDS/1118146/2022 | 2022-12-07
2804 | KNCPL3 | KNCPL3 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-18 | KNCPL3 | 4G_FD900_KNCPL3 | 4G_FD2100_KNCPL3 | 4G_TD_KNCPL3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758280 | 2022-11-23 | P/FVC/MDS/1116791/2022 | 2022-11-29 | ST202211758025 | 2022-11-22 | P/FVC/MDS/1116767/2022 | 2022-11-29 | ST202211758555 | 2022-11-16 | P/FBW/MDS/1116832/2022 | 2022-11-29
2805 | KRNPT4 | KRNPT4 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3154399 | R/NN-687876 |  | SO | 2022-11-18 | KRNPT4 | 4G_FD900_KRNPT4 | 4G_FD2100_KRNPT4 | 4G_TD_KRNPT4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758299 | 2022-11-23 | P/FVC/MDS/1116801/2022 | 2022-11-29 | ST202211758074 | 2022-11-22 | P/FVC/MDS/1116773/2022 | 2022-11-29 | ST202211758579 | 2022-11-16 | P/FBW/MDS/1116842/2022 | 2022-11-29
2806 | KDIPL2 | KDIPL2 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3154401 | R/NN-687877 |  | SO | 2022-11-16 | KDIPL2 | 4G_FD900_KDIPL2 | 4G_FD2100_KDIPL2 | 4G_TD_KDIPL2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202210643027 | 2022-10-28 | P/FVC/MDS/1114502/2022 | 2022-11-06 | ST202210651744 | 2022-10-29 | P/FVC/MDS/1114550/2022 | 2022-11-06 |  |  |  |  | ST202210637039 | 2022-10-27 | P/FBW/MDS/1114443/2022 | 2022-11-06
2807 | VLLR11 | VLLR11 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-23 | VLLR11 | 4G_FD900_VLLR11 | 4G_FD2100_VLLR11 | 4G_TD_VLLR11 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779930 | 2022-12-02 | P/FVC/MDS/1118230/2022 | 2022-12-07 |  |  |  |  | ST202212779609 | 2022-12-01 | P/FBW/MDS/1118140/2022 | 2022-12-07
2808 | PPMPT5 | PPMPT5 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-16 | PPMPT5 | 4G_FD900_PPMPT5 | 4G_FD2100_PPMPT5 | 4G_TD_PPMPT5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738364 | 2022-11-18 | P/FVC/MDS/1115210/2022 | 2022-11-24 | ST202211729817 | 2022-11-17 | P/FVC/MDS/1115148/2022 | 2022-11-24 |  |  |  |  | ST202211726179 | 2022-11-16 | P/FBW/MDS/1115068/2022 | 2022-11-24
2809 | PPMPT4 | PPMPT4 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-18 | PPMPT4 | 4G_FD900_PPMPT4 | 4G_FD2100_PPMPT4 | 4G_TD_PPMPT4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758321 | 2022-11-23 | P/FVC/MDS/1116810/2022 | 2022-11-29 | ST202211758103 | 2022-11-22 | P/FVC/MDS/1116780/2022 | 2022-11-29 | ST202211758605 | 2022-11-16 | P/FBW/MDS/1116851/2022 | 2022-11-29
2810 | PDMPL4 | PDMPL4 | Coimbatore | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-18 | PDMPL4 | 4G_FD900_PDMPL4 | 4G_FD2100_PDMPL4 | 4G_TD_PDMPL4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758320 | 2022-11-23 | P/FVC/MDS/1116809/2022 | 2022-11-29 | ST202211758102 | 2022-11-22 | P/FVC/MDS/1116779/2022 | 2022-11-29 | ST202211758604 | 2022-11-16 | P/FBW/MDS/1116850/2022 | 2022-11-29
2811 | VELAM3 | VELAM3 | Vellore | Vellore |  | ROTN | Indus | IN-3154369 | R/NN-687841 |  | SO | 2022-11-18 | VELAM3 | 4G_FD900_VELAM3 | 4G_FD2100_VELAM3 | 4G_TD_VELAM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758310 | 2022-11-23 | P/FVC/MDS/1116806/2022 | 2022-11-29 | ST202211758096 | 2022-11-22 | P/FVC/MDS/1116777/2022 | 2022-11-29 | ST202211758598 | 2022-11-16 | P/FBW/MDS/1116847/2022 | 2022-11-29
2812 | KTPD27 | KTPD27 | Vellore | Vellore |  | ROTN | ATC | TN/VE/AT/23545 | T22TN07274 |  | SO | 2022-11-23 | KTPD27 | 4G_FD900_KTPD27 | 4G_FD2100_KTPD27 | 4G_TD_KTPD27 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779895 | 2022-12-02 | P/FVC/MDS/1118217/2022 | 2022-12-07 | ST202212780636 | 2022-12-02 | P/FVC/MDS/1118285/2022 | 2022-12-07 | ST202212779579 | 2022-12-01 | P/FBW/MDS/1118127/2022 | 2022-12-07
2813 | KGNLR2 | KGNLR2 | Vellore | Vellore |  | ROTN | ATC | TN/VE/AT/23546 | T22TN07275 |  | SO | 2022-11-29 | KGNLR2 | 4G_FD900_KGNLR2 | 4G_FD2100_KGNLR2 | 4G_TD_KGNLR2 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212780001 | 2022-12-02 | P/FVC/MDS/1118254/2022 | 2022-12-07 | ST202212780748 | 2022-12-02 | P/FVC/MDS/1118305/2022 | 2022-12-07 | ST202212779649 | 2022-12-01 | P/FBW/MDS/1118162/2022 | 2022-12-07
2814 | SEVOR3 | SEVOR3 | Vellore | Vellore |  | ROTN | Indus | IN-3154374 | R/NN-687852 |  | SO | 2022-11-29 | SEVOR3 | 4G_FD900_SEVOR3 | 4G_FD2100_SEVOR3 | 4G_TD_SEVOR3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780424 | 2022-12-02 | P/FVC/MDS/1118263/2022 | 2022-12-07 |  |  |  |  | ST202212779663 | 2022-12-01 | P/FBW/MDS/1118172/2022 | 2022-12-07
2815 | KTPD28 | KTPD28 | Vellore | Vellore |  | ROTN | ATC | TN/VE/AT/23548 | T22TN07277 |  | SO | 2022-11-29 | KTPD28 | 4G_FD900_KTPD28 | 4G_FD2100_KTPD28 | 4G_TD_KTPD28 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779972 | 2022-12-02 | P/FVC/MDS/1118242/2022 | 2022-12-07 | ST202212780726 | 2022-12-02 | P/FVC/MDS/1118295/2022 | 2022-12-07 | ST202212779629 | 2022-12-01 | P/FBW/MDS/1118150/2022 | 2022-12-07
2816 | ADIVR2 | ADIVR2 | Tiruchirappalli | Trichy |  | ROTN | ATC | TN/TR/AT/23550 | T22TN07279 |  | SO | 2022-11-18 | ADIVR2 | 4G_FD900_ADIVR2 | 4G_FD2100_ADIVR2 | 4G_TD_ADIVR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758293 | 2022-11-23 | P/FVC/MDS/1116797/2022 | 2022-11-29 | ST202211758073 | 2022-11-22 | P/FVC/MDS/1116772/2022 | 2022-11-29 | ST202211758565 | 2022-11-16 | P/FBW/MDS/1116838/2022 | 2022-11-29
2817 | TRYR21 | TRYR21 | Tiruchirappalli | Trichy |  | ROTN | Indus | IN-3154415 | R/NN-687907 |  | SO | 2022-11-23 | TRYR21 | 4G_FD900_TRYR21 | 4G_FD2100_TRYR21 | 4G_TD_TRYR21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779848 | 2022-12-02 | P/FVC/MDS/1118204/2022 | 2022-12-07 |  |  |  |  | ST202212779498 | 2022-12-01 | P/FBW/MDS/1118115/2022 | 2022-12-07
2818 | MUTPU2 | MUTPU2 | Ramanathapuram | Madurai |  | ROTN | Ascend | - | - |  | SO | 2022-11-16 | MUTPU2 | 4G_FD900_MUTPU2 | 4G_FD2100_MUTPU2 | 4G_TD_MUTPU2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738397 | 2022-11-18 | P/FVC/MDS/1115226/2022 | 2022-11-24 | ST202211729847 | 2022-11-17 | P/FVC/MDS/1115164/2022 | 2022-11-24 |  |  |  |  | ST202211726231 | 2022-11-16 | P/FBW/MDS/1115084/2022 | 2022-11-24
2819 | DNKTI8 | DNKTI8 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3154417 | R/NN-687909 |  | SO | 2022-11-16 | DNKTI8 | 4G_FD900_DNKTI8 | 4G_FD2100_DNKTI8 | 4G_TD_DNKTI8 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738382 | 2022-11-18 | P/FVC/MDS/1115217/2022 | 2022-11-24 | ST202211729831 | 2022-11-17 | P/FVC/MDS/1115155/2022 | 2022-11-24 |  |  |  |  | ST202211726206 | 2022-11-16 | P/FBW/MDS/1115075/2022 | 2022-11-24
2820 | VPDAI4 | VPDAI4 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3154418 | R/NN-687910 |  | SO | 2022-11-23 | VPDAI4 | 4G_FD900_VPDAI4 | 4G_FD2100_VPDAI4 | 4G_TD_VPDAI4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779846 | 2022-12-02 | P/FVC/MDS/1118202/2022 | 2022-12-07 |  |  |  |  | ST202212779490 | 2022-12-01 | P/FBW/MDS/1118113/2022 | 2022-12-07
2821 | HSR203 | HSR203 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3156146 | R/NN-690093 |  | SO | 2022-11-16 | HSR203 | 4G_FD900_HSR203 | 4G_FD2100_HSR203 | 4G_TD_HSR203 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | 1905-09-30 | ST202211738378 | 2022-11-18 | P/FVC/MDS/1115215/2022 | 2022-11-24 | ST202211729829 | 2022-11-17 | P/FVC/MDS/1115153/2022 | 2022-11-24 | ST202212826699 | 2022-12-16 | P/AFC/MDS/1119510/2022 | 2022-12-22 | ST202211726200 | 2022-11-16 | P/FBW/MDS/1115073/2022 | 2022-11-24
2822 | HSR204 | HSR204 | Krishnagiri | Vellore |  | ROTN | Indus | IN-3154435 | R/NN-687935 |  | SO | 2022-11-23 | HSR204 | 4G_FD900_HSR204 | 4G_FD2100_HSR204 | 4G_TD_HSR204 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779828 | 2022-12-02 | P/FVC/MDS/1118197/2022 | 2022-12-07 | ST202212780623 | 2022-12-02 | P/FVC/MDS/1118280/2022 | 2022-12-07 | ST202212779472 | 2022-12-01 | P/FBW/MDS/1118108/2022 | 2022-12-07
2823 | KLPPT2 | KLPPT2 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3154420 | R/NN-687914 |  | SO | 2022-11-16 | KLPPT2 | 4G_FD900_KLPPT2 | 4G_FD2100_KLPPT2 | 4G_TD_KLPPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738359 | 2022-11-18 | P/FVC/MDS/1115209/2022 | 2022-11-24 | ST202211729814 | 2022-11-17 | P/FVC/MDS/1115147/2022 | 2022-11-24 |  |  |  |  | ST202211726178 | 2022-11-16 | P/FBW/MDS/1115067/2022 | 2022-11-24
2824 | KTGRI5 | KTGRI5 | The Nilgiris | Coimbatore |  | ROTN | BSNL | 79 | - |  | SO | 2022-11-29 | KTGRI5 | 4G_FD900_KTGRI5 | 4G_FD2100_KTGRI5 | 4G_TD_KTGRI5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779956 | 2022-12-02 | P/FVC/MDS/1118237/2022 | 2022-12-07 |  |  |  |  | ST202212779623 | 2022-12-01 | P/FBW/MDS/1118145/2022 | 2022-12-07
2825 | KTGRI8 | KTGRI8 | The Nilgiris | Coimbatore |  | ROTN | Summit | I-TN-KOTG-ENB-9030 | SR-TN001189 |  | SO | 2022-11-16 | KTGRI8 | 4G_FD900_KTGRI8 | 4G_FD2100_KTGRI8 | 4G_TD_KTGRI8 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738375 | 2022-11-18 | P/FVC/MDS/1115214/2022 | 2022-11-24 | ST202211729823 | 2022-11-17 | P/FVC/MDS/1115152/2022 | 2022-11-24 |  |  |  |  | ST202211726199 | 2022-11-16 | P/FBW/MDS/1115072/2022 | 2022-11-24
2826 | OOTY51 | OOTY51 | The Nilgiris | Coimbatore |  | ROTN | Indus | IN-3154967 | R/NN-688434 |  | SO | 2022-11-23 | OOTY51 | 4G_FD900_OOTY51 | 4G_FD2100_OOTY51 | 4G_TD_OOTY51 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779879 | 2022-12-02 | P/FVC/MDS/1118212/2022 | 2022-12-07 |  |  |  |  | ST202212779511 | 2022-12-01 | P/FBW/MDS/1118122/2022 | 2022-12-07
2827 | OOTY55 | OOTY55 | The Nilgiris | Coimbatore |  | ROTN | Indus | IN-3154855 | R/NN-688437 |  | SO | 2022-11-23 | OOTY55 | 4G_FD900_OOTY55 | 4G_FD2100_OOTY55 | 4G_TD_OOTY55 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779860 | 2022-12-02 | P/FVC/MDS/1118206/2022 | 2022-12-07 |  |  |  |  | ST202212779502 | 2022-12-01 | P/FBW/MDS/1118117/2022 | 2022-12-07
2828 | KMPTI6 | KMPTI6 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3158524 | R/NN-693311 |  | SO | 2022-11-23 | KMPTI6 | 4G_FD900_KMPTI6 | 4G_FD2100_KMPTI6 | 4G_TD_KMPTI6 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779934 | 2022-12-02 | P/FVC/MDS/1118231/2022 | 2022-12-07 |  |  |  |  | ST202212779610 | 2022-12-01 | P/FBW/MDS/1118141/2022 | 2022-12-07
2829 | MRTPM2 | MRTPM2 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3158539 | R/NN-693329 |  | SO | 2022-11-29 | MRTPM2 | 4G_FD900_MRTPM2 | 4G_FD2100_MRTPM2 | 4G_TD_MRTPM2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780360 | 2022-12-02 | P/FVC/MDS/1118260/2022 | 2022-12-07 |  |  |  |  | ST202212779659 | 2022-12-01 | P/FBW/MDS/1118168/2022 | 2022-12-07
2830 | DGL127 | DGL127 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23561 | T22TN07557 |  | SO | 2022-11-29 | DGL127 | 4G_FD900_DGL127 | 4G_FD2100_DGL127 | 4G_TD_DGL127 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779958 | 2022-12-02 | P/FVC/MDS/1118239/2022 | 2022-12-07 |  |  |  |  | ST202212779626 | 2022-12-01 | P/FBW/MDS/1118147/2022 | 2022-12-07
2831 | DGL128 | DGL128 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23562 | T22TN07558 |  | SO | 2022-11-23 | DGL128 | 4G_FD900_DGL128 | 4G_FD2100_DGL128 | 4G_TD_DGL128 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779915 | 2022-12-02 | P/FVC/MDS/1118224/2022 | 2022-12-07 | ST202212839569 | 2022-12-22 |  |  | ST202212779590 | 2022-12-01 | P/FBW/MDS/1118134/2022 | 2022-12-07
2832 | DGL133 | DGL133 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23567 | T22TN07563 |  | SO | 2022-11-23 | DGL133 | 4G_FD900_DGL133 | 4G_FD2100_DGL133 | 4G_TD_DGL133 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779896 | 2022-12-02 | P/FVC/MDS/1118218/2022 | 2022-12-07 |  |  |  |  | ST202212779580 | 2022-12-01 | P/FBW/MDS/1118128/2022 | 2022-12-07
2833 | ERD256 | ERD256 | Erode | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-29 | ERD256 | 4G_FD900_ERD256 | 4G_FD2100_ERD256 | 4G_TD_ERD256 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779991 | 2022-12-02 | P/FVC/MDS/1118250/2022 | 2022-12-07 | ST202212780742 | 2022-12-02 | P/FVC/MDS/1118302/2022 | 2022-12-07 | ST202212779638 | 2022-12-01 | P/FBW/MDS/1118158/2022 | 2022-12-07
2834 | ERD259 | ERD259 | Erode | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-29 | ERD259 | 4G_FD900_ERD259 | 4G_FD2100_ERD259 | 4G_TD_ERD259 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779992 | 2022-12-02 | P/FVC/MDS/1118251/2022 | 2022-12-07 | ST202212780746 | 2022-12-02 | P/FVC/MDS/1118303/2022 | 2022-12-07 | ST202212779643 | 2022-12-01 | P/FBW/MDS/1118159/2022 | 2022-12-07
2835 | MMPYM2 | MMPYM2 | Erode | Coimbatore |  | ROTN | Summit | I-TN-EROD-ENB-9092 | SR-TN001199 |  | SO | 2022-11-16 | MMPYM2 | 4G_FD900_MMPYM2 | 4G_FD2100_MMPYM2 | 4G_TD_MMPYM2 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202211738400 | 2022-11-18 | P/FVC/MDS/1115227/2022 | 2022-11-24 | ST202211729851 | 2022-11-17 | P/FVC/MDS/1115165/2022 | 2022-11-24 | ST202211757999 | 2022-11-22 | P/FVC/MDS/1116764/2022 | 2022-11-29 | ST202211726232 | 2022-11-16 | P/FBW/MDS/1115085/2022 | 2022-11-24
2836 | PAPAT2 | PAPAT2 | Salem | Vellore |  | ROTN | Indus | IN-3158579 | R/NN-693343 |  | SO | 2022-11-23 | PAPAT2 | 4G_FD900_PAPAT2 | 4G_FD2100_PAPAT2 | 4G_TD_PAPAT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780560 | 2022-12-02 | P/FVC/MDS/1118332/2022 | 2022-12-08 | ST202212779935 | 2022-12-02 | P/FVC/MDS/1118232/2022 | 2022-12-07 | ST202301004042 | 2023-01-03 | 0 |  | ST202212779613 | 2022-12-01 | P/FBW/MDS/1118142/2022 | 2022-12-07
2837 | MLSDM5 | MLSDM5 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/23569 | T22TN07565 |  | SO | 2022-11-18 | MLSDM5 | 4G_FD900_MLSDM5 | 4G_FD2100_MLSDM5 | 4G_TD_MLSDM5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211761121 | 2022-11-25 | P/FVC/MDS/1116880/2022 | 2022-11-29 | ST202211758346 | 2022-11-23 | P/FVC/MDS/1116816/2022 | 2022-11-29 |  |  |  |  | ST202211758623 | 2022-11-16 | P/FBW/MDS/1116857/2022 | 2022-11-29
2838 | MLSDM6 | MLSDM6 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/23570 | T22TN07566 |  | SO | 2022-11-18 | MLSDM6 | 4G_FD900_MLSDM6 | 4G_FD2100_MLSDM6 | 4G_TD_MLSDM6 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211761120 | 2022-11-25 | P/FVC/MDS/1116879/2022 | 2022-11-29 | ST202211758341 | 2022-11-23 | P/FVC/MDS/1116815/2022 | 2022-11-29 |  |  |  |  | ST202211758622 | 2022-11-16 | P/FBW/MDS/1116856/2022 | 2022-11-29
2839 | MNJUR3 | MNJUR3 | Ramanathapuram | Madurai |  | ROTN | Indus | IN-3158583 | R/NN-693382 |  | SO | 2022-11-29 | MNJUR3 | 4G_FD900_MNJUR3 | 4G_FD2100_MNJUR3 | 4G_TD_MNJUR3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212780586 | 2022-12-02 | P/FVC/MDS/1118341/2022 | 2022-12-08 | ST202212780488 | 2022-12-02 | P/FVC/MDS/1118269/2022 | 2022-12-07 |  |  |  |  | ST202212779660 | 2022-12-01 | P/FBW/MDS/1118169/2022 | 2022-12-07
2840 | MDKLR4 | MDKLR4 | Ramanathapuram | Madurai |  | ROTN | Summit | I-TN-MDKL-ENB-9036 | SR-TN001201 |  | SO | 2022-11-16 | MDKLR4 | 4G_FD900_MDKLR4 | 4G_FD2100_MDKLR4 | 4G_TD_MDKLR4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738401 | 2022-11-18 | P/FVC/MDS/1115228/2022 | 2022-11-24 | ST202211729852 | 2022-11-17 | P/FVC/MDS/1115166/2022 | 2022-11-24 | ST202211737947 | 2022-11-18 | P/FVC/MDS/1115122/2022 | 2022-11-24 | ST202211726233 | 2022-11-16 | P/FBW/MDS/1115086/2022 | 2022-11-24
2841 | MNGLP2 | MNGLP2 | Krishnagiri | Vellore |  | ROTN | ATC | TN6029 | - |  | SO | 2022-11-18 | MNGLP2 | 4G_FD900_MNGLP2 | 4G_FD2100_MNGLP2 | 4G_TD_MNGLP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738412 | 2022-11-18 | P/FVC/MDS/1115234/2022 | 2022-11-24 | ST202211737935 | 2022-11-18 | P/FVC/MDS/1115187/2022 | 2022-11-24 | ST202211737948 | 2022-11-18 | P/FVC/MDS/1115123/2022 | 2022-11-24 | ST202211737920 | 2022-11-18 | P/FBW/MDS/1115108/2022 | 2022-11-24
2842 | KARNP2 | KARNP2 | Krishnagiri | Vellore |  | ROTN | Summit | I-TN-HSUR-ENB-9070 | SR-TN001202 |  | SO | 2022-11-16 | KARNP2 | 4G_FD900_KARNP2 | 4G_FD2100_KARNP2 | 4G_TD_KARNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738402 | 2022-11-18 | P/FVC/MDS/1115229/2022 | 2022-11-24 | ST202211729853 | 2022-11-17 | P/FVC/MDS/1115167/2022 | 2022-11-24 |  |  |  |  | ST202211726234 | 2022-11-16 | P/FBW/MDS/1115087/2022 | 2022-11-24
2843 | KNMKP2 | KNMKP2 | Namakkal | Coimbatore |  | ROTN | ATC | TN/NM/AT/23573 | T22TN07569 |  | SO | 2022-11-23 | KNMKP2 | 4G_FD900_KNMKP2 | 4G_FD2100_KNMKP2 | 4G_TD_KNMKP2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779916 | 2022-12-02 | P/FVC/MDS/1118225/2022 | 2022-12-07 |  |  |  |  | ST202212779591 | 2022-12-01 | P/FBW/MDS/1118135/2022 | 2022-12-07
2844 | NKL069 | NKL069 | Namakkal | Coimbatore |  | ROTN | Summit | I-TN-NMKK-ENB-9084 | SR-TN001203 |  | SO | 2022-11-16 | NKL069 | 4G_FD900_NKL069 | 4G_FD2100_NKL069 | 4G_TD_NKL069 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738406 | 2022-11-18 | P/FVC/MDS/1115230/2022 | 2022-11-24 | ST202211729854 | 2022-11-17 | P/FVC/MDS/1115168/2022 | 2022-11-24 |  |  |  |  | ST202211726235 | 2022-11-16 | P/FBW/MDS/1115088/2022 | 2022-11-24
2845 | VELPT2 | VELPT2 | Tiruvannamalai | Vellore |  | ROTN | ATC | TN/TV/AT/23579 | T22TN07575 |  | SO | 2022-11-23 | VELPT2 | 4G_FD900_VELPT2 | 4G_FD2100_VELPT2 | 4G_TD_VELPT2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779868 | 2022-12-02 | P/FVC/MDS/1118208/2022 | 2022-12-07 |  |  |  |  | ST202212779505 | 2022-12-01 | P/FBW/MDS/1118119/2022 | 2022-12-07
2846 | SURYA2 | SURYA2 | Thiruvallur | Chennai |  | ROTN | ATC | TN/TU/AT/23580 | T22TN07576 |  | SO | 2022-11-18 | SURYA2 | 4G_FD900_SURYA2 | 4G_FD2100_SURYA2 | 4G_TD_SURYA2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758347 | 2022-11-23 | P/FVC/MDS/1116817/2022 | 2022-11-29 | ST202211758111 | 2022-11-22 | P/FVC/MDS/1116784/2022 | 2022-11-29 | ST202211758625 | 2022-11-16 | P/FBW/MDS/1116858/2022 | 2022-11-29
2847 | THRML2 | THRML2 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3158533 | R/NN-693321 |  | SO | 2022-11-29 | THRML2 | 4G_FD900_THRML2 | 4G_FD2100_THRML2 | 4G_TD_THRML2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780359 | 2022-12-02 | P/FVC/MDS/1118259/2022 | 2022-12-07 |  |  |  |  | ST202212779656 | 2022-12-01 | P/FBW/MDS/1118167/2022 | 2022-12-07
2848 | VEPN06 | VEPN06 | Theni | Madurai |  | ROTN | ATC | TN/TH/AT/23581 | T22TN07577 |  | SO | 2022-11-18 | VEPN06 | 4G_FD900_VEPN06 | 4G_FD2100_VEPN06 | 4G_TD_VEPN06 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211761123 | 2022-11-25 | P/FVC/MDS/1116881/2022 | 2022-11-29 | ST202211758348 | 2022-11-23 | P/FVC/MDS/1116818/2022 | 2022-11-29 |  |  |  |  | ST202211758626 | 2022-11-16 | P/FBW/MDS/1116859/2022 | 2022-11-29
2849 | ANJGM9 | ANJGM9 | Kanniyakumari | Madurai |  | ROTN | Indus | IN-3158640 | R/NN-693465 |  | SO | 2022-11-29 | ANJGM9 | 4G_FD900_ANJGM9 | 4G_FD2100_ANJGM9 | 4G_TD_ANJGM9 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780361 | 2022-12-02 | P/FVC/MDS/1118261/2022 | 2022-12-07 |  |  |  |  | ST202212779661 | 2022-12-01 | P/FBW/MDS/1118170/2022 | 2022-12-07
2850 | PDY412 | PDY412 | Puducherry | Trichy |  | ROTN | Indus | IN-3159022 | R/NN-693816 |  | SO | 2022-12-02 | PDY412 | 4G_FD900_PDY412 | 4G_FD2100_PDY412 | 4G_TD_PDY412 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | 180021002300 |  |  |  |  | ST202212809235 | 2022-12-14 | P/FVC/MDS/1119100/2022 | 2022-12-20 | ST202212811727 | 2022-12-14 | P/FVC/MDS/1119338/2022 | 2022-12-20 | ST202212808941 | 2022-12-14 | P/FBW/MDS/1119200/2022 | 2022-12-20
2851 | ERD264 | ERD264 | Erode | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-23 | ERD264 | 4G_FD900_ERD264 | 4G_FD2100_ERD264 | 4G_TD_ERD264 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779929 | 2022-12-02 | P/FVC/MDS/1118229/2022 | 2022-12-07 | ST202212780648 | 2022-12-02 | P/FVC/MDS/1118290/2022 | 2022-12-07 | ST202212779608 | 2022-12-01 | P/FBW/MDS/1118139/2022 | 2022-12-07
2852 | ERD265 | ERD265 | Erode | Coimbatore |  | ROTN | Summit | I-TN-EROD-ENB-0139 | SR-TN001204 |  | SO | 2022-11-23 | ERD265 | 4G_FD900_ERD265 | 4G_FD2100_ERD265 | 4G_TD_ERD265 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779878 | 2022-12-02 | P/FVC/MDS/1118211/2022 | 2022-12-07 | ST202212780634 | 2022-12-02 | P/FVC/MDS/1118283/2022 | 2022-12-07 | ST202212780821 | 2022-12-02 | P/FBW/MDS/1118180/2022 | 2022-12-07
2853 | ERD267 | ERD267 | Erode | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-29 | ERD267 | 4G_FD900_ERD267 | 4G_FD2100_ERD267 | 4G_TD_ERD267 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779993 | 2022-12-02 | P/FVC/MDS/1118252/2022 | 2022-12-07 | ST202212780747 | 2022-12-02 | P/FVC/MDS/1118304/2022 | 2022-12-07 | ST202212779644 | 2022-12-01 | P/FBW/MDS/1118160/2022 | 2022-12-07
2854 | ERD268 | ERD268 | Erode | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-11-29 | ERD268 | 4G_FD900_ERD268 | 4G_FD2100_ERD268 | 4G_TD_ERD268 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212779987 | 2022-12-02 | P/FVC/MDS/1118249/2022 | 2022-12-07 | ST202212780741 | 2022-12-02 | P/FVC/MDS/1118301/2022 | 2022-12-07 | ST202212779637 | 2022-12-01 | P/FBW/MDS/1118157/2022 | 2022-12-07
2855 | BVNI35 | BVNI35 | Erode | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-12-02 | BVNI35 | 4G_FD900_BVNI35 | 4G_FD2100_BVNI35 | 4G_TD_BVNI35 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809366 | 2022-12-14 | P/FVC/MDS/1119108/2022 | 2022-12-20 |  |  |  |  | ST202212809112 | 2022-12-14 | P/FBW/MDS/1119208/2022 | 2022-12-20
2856 | DRPM25 | DRPM25 | Tiruppur | Coimbatore |  | ROTN | Indus | IN-3159033 | R/NN-693825 |  | SO | 2022-12-02 | DRPM25 | 4G_FD900_DRPM25 | 4G_FD2100_DRPM25 | 4G_TD_DRPM25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809103 | 2022-12-14 | P/FVC/MDS/1119084/2022 | 2022-12-20 |  |  |  |  | ST202212807846 | 2022-12-14 | P/FBW/MDS/1119184/2022 | 2022-12-20
2857 | TCGD79 | TCGD79 | Namakkal | Coimbatore |  | ROTN | Indus | IN-3159040 | R/NN-693827 |  | SO | 2022-12-02 | TCGD79 | 4G_FD900_TCGD79 | 4G_FD2100_TCGD79 | 4G_TD_TCGD79 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809259 | 2022-12-14 | P/FVC/MDS/1119101/2022 | 2022-12-20 |  |  |  |  | ST202212808985 | 2022-12-14 | P/FBW/MDS/1119201/2022 | 2022-12-20
2858 | PLNI41 | PLNI41 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23586 | T22TN07602 |  | SO | 2022-11-23 | PLNI41 | 4G_FD900_PLNI41 | 4G_FD2100_PLNI41 | 4G_TD_PLNI41 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779897 | 2022-12-02 | P/FVC/MDS/1118219/2022 | 2022-12-07 |  |  |  |  | ST202212779581 | 2022-12-01 | P/FBW/MDS/1118129/2022 | 2022-12-07
2859 | AKUD08 | AKUD08 | Dindigul | Coimbatore |  | ROTN | ATC | TN/DI/AT/23588 | T22TN07604 |  | SO | 2022-11-18 | AKUD08 | 4G_FD900_AKUD08 | 4G_FD2100_AKUD08 | 4G_TD_AKUD08 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211758352 | 2022-11-23 | P/FVC/MDS/1116819/2022 | 2022-11-29 | ST202211758113 | 2022-11-22 | P/FVC/MDS/1116785/2022 | 2022-11-29 | ST202211758627 | 2022-11-16 | P/FBW/MDS/1116860/2022 | 2022-11-29
2860 | SATH25 | SATH25 | Erode | Coimbatore |  | ROTN | TVI | - | - |  | SO | 2022-12-02 | SATH25 | 4G_FD900_SATH25 | 4G_FD2100_SATH25 | 4G_TD_SATH25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809367 | 2022-12-14 | P/FVC/MDS/1119109/2022 | 2022-12-20 |  |  |  |  | ST202212809127 | 2022-12-14 | P/FBW/MDS/1119209/2022 | 2022-12-20
2861 | CBE973 | CBE973 | Coimbatore | Coimbatore |  | ROTN | Indus | IN-3159053 | R/NN-693844 |  | SO | 2022-11-29 | CBE973 | 4G_FD900_CBE973 | 4G_FD2100_CBE973 | 4G_TD_CBE973 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212780423 | 2022-12-02 | P/FVC/MDS/1118262/2022 | 2022-12-07 | ST202212780763 | 2022-12-02 | P/FVC/MDS/1118306/2022 | 2022-12-07 | ST202212779662 | 2022-12-01 | P/FBW/MDS/1118171/2022 | 2022-12-07
2862 | APKT72 | APKT72 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/23589 | T22TN07605 |  | SO | 2022-11-23 | APKT72 | 4G_FD900_APKT72 | 4G_FD2100_APKT72 | 4G_TD_APKT72 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779869 | 2022-12-02 | P/FVC/MDS/1118209/2022 | 2022-12-07 |  |  |  |  | ST202212779509 | 2022-12-01 | P/FBW/MDS/1118120/2022 | 2022-12-07
2863 | VLUR13 | VLUR13 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3159058 | R/NN-693848 |  | SO | 2022-12-02 | VLUR13 | 4G_FD900_VLUR13 | 4G_FD2100_VLUR13 | 4G_TD_VLUR13 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809025 | 2022-12-14 | P/FVC/MDS/1119075/2022 | 2022-12-20 |  |  |  |  | ST202212807661 | 2022-12-14 | P/FBW/MDS/1119175/2022 | 2022-12-20
2864 | VNGR65 | VNGR65 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/23593 | T22TN07609 |  | SO | 2022-11-23 | VNGR65 | 4G_FD900_VNGR65 | 4G_FD2100_VNGR65 | 4G_TD_VNGR65 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779870 | 2022-12-02 | P/FVC/MDS/1118210/2022 | 2022-12-07 |  |  |  |  | ST202212779510 | 2022-12-01 | P/FBW/MDS/1118121/2022 | 2022-12-07
2865 | VNGR66 | VNGR66 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/23594 | T22TN07610 |  | SO | 2022-11-23 | VNGR66 | 4G_FD900_VNGR66 | 4G_FD2100_VNGR66 | 4G_TD_VNGR66 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779922 | 2022-12-02 | P/FVC/MDS/1118226/2022 | 2022-12-07 |  |  |  |  | ST202212779603 | 2022-12-01 | P/FBW/MDS/1118136/2022 | 2022-12-07
2866 | VNGR68 | VNGR68 | Virudhunagar | Madurai |  | ROTN | ATC | TN/VI/AT/23596 | T22TN07612 |  | SO | 2022-11-23 | VNGR68 | 4G_FD900_VNGR68 | 4G_FD2100_VNGR68 | 4G_TD_VNGR68 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779889 | 2022-12-02 | P/FVC/MDS/1118216/2022 | 2022-12-07 |  |  |  |  | ST202212779517 | 2022-12-01 | P/FBW/MDS/1118126/2022 | 2022-12-07
2867 | TENI42 | TENI42 | Theni | Madurai |  | ROTN | ATC | TN/TH/AT/23599 | T22TN07615 |  | SO | 2022-11-29 | TENI42 | 4G_FD900_TENI42 | 4G_FD2100_TENI42 | 4G_TD_TENI42 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779965 | 2022-12-02 | P/FVC/MDS/1118240/2022 | 2022-12-07 |  |  |  |  | ST202212779627 | 2022-12-01 | P/FBW/MDS/1118148/2022 | 2022-12-07
2868 | SNKL17 | SNKL17 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3159104 | R/NN-693895 |  | SO | 2022-12-02 | SNKL17 | 4G_FD900_SNKL17 | 4G_FD2100_SNKL17 | 4G_TD_SNKL17 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809045 | 2022-12-14 | P/FVC/MDS/1119076/2022 | 2022-12-20 |  |  |  |  | ST202212807662 | 2022-12-14 | P/FBW/MDS/1119176/2022 | 2022-12-20
2869 | SNKL18 | SNKL18 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3159108 | R/NN-693898 |  | SO | 2022-12-02 | SNKL18 | 4G_FD900_SNKL18 | 4G_FD2100_SNKL18 | 4G_TD_SNKL18 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809046 | 2022-12-14 | P/FVC/MDS/1119077/2022 | 2022-12-20 |  |  |  |  | ST202212807723 | 2022-12-14 | P/FBW/MDS/1119177/2022 | 2022-12-20
2870 | KDNL29 | KDNL29 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3159117 | R/NN-693906 |  | SO | 2022-12-02 | KDNL29 | 4G_FD900_KDNL29 | 4G_FD2100_KDNL29 | 4G_TD_KDNL29 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809277 | 2022-12-14 | P/FVC/MDS/1119103/2022 | 2022-12-20 |  |  |  |  | ST202212809012 | 2022-12-14 | P/FBW/MDS/1119203/2022 | 2022-12-20
2871 | KDNL30 | KDNL30 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3159127 | R/NN-693924 |  | SO | 2022-12-02 | KDNL30 | 4G_FD900_KDNL30 | 4G_FD2100_KDNL30 | 4G_TD_KDNL30 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212808968 | 2022-12-14 | P/FVC/MDS/1119068/2022 | 2022-12-20 |  |  |  |  | ST202212807264 | 2022-12-14 | P/FBW/MDS/1119168/2022 | 2022-12-20
2872 | VTRLM3 | VTRLM3 | Tirunelveli | Madurai |  | ROTN | Indus | IN-3159124 | R/NN-693915 |  | SO | 2022-12-02 | VTRLM3 | 4G_FD900_VTRLM3 | 4G_FD2100_VTRLM3 | 4G_TD_VTRLM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809047 | 2022-12-14 | P/FVC/MDS/1119078/2022 | 2022-12-20 |  |  |  |  | ST202212807724 | 2022-12-14 | P/FBW/MDS/1119178/2022 | 2022-12-20
2873 | PADUR2 | PADUR2 | chennai | chennai |  | CHN | Indus | IN-3142353 | R/NN-671743 |  | SO | 2022-11-16 | PADUR2 | 4G_FD900_PADUR2 | 4G_FD2100_PADUR2 | 4G_TD_PADUR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211738070 | 2022-11-18 | P/FVC/MDS/1115197/2022 | 2022-11-24 | ST202211729794 | 2022-11-17 | P/FVC/MDS/1115135/2022 | 2022-11-24 |  |  |  |  | ST202211726162 | 2022-11-16 | P/FBW/MDS/1115055/2022 | 2022-11-24
2874 | GUDU33 | GUDU33 | chennai | chennai |  | CHN | Indus | IN-3158459 | R/NN-693255 |  | SO | 2022-11-29 | GUDU33 | 4G_FD900_GUDU33 | 4G_FD2100_GUDU33 | 4G_TD_GUDU33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212780002 | 2022-12-02 | P/FVC/MDS/1118255/2022 | 2022-12-07 |  |  |  |  | ST202212779650 | 2022-12-01 | P/FBW/MDS/1118163/2022 | 2022-12-07
2875 | PONM12 | PONM12 | chennai | chennai |  | CHN | Indus | IN-3142435 | R/NN-671789 |  | SO | 2022-11-16 | PONM12 | 4G_FD900_PONM12 | 4G_FD2100_PONM12 | 4G_TD_PONM12 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202211737990 | 2022-11-18 | P/FVC/MDS/1115192/2022 | 2022-11-24 | ST202211729785 | 2022-11-17 | P/FVC/MDS/1115129/2022 | 2022-11-24 |  |  |  |  | ST202211726152 | 2022-11-16 | P/FBW/MDS/1115049/2022 | 2022-11-24
2876 | BHAR22 | BHAR22 | chennai | chennai |  | CHN | Indus | IN-3156962 | R/NN-691030 |  | SO | 2022-11-23 | BHAR22 | 4G_FD900_BHAR22 | 4G_FD2100_BHAR22 | 4G_TD_BHAR22 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212779829 | 2022-12-02 | P/FVC/MDS/1118198/2022 | 2022-12-07 |  |  |  |  | ST202212779476 | 2022-12-01 | P/FBW/MDS/1118109/2022 | 2022-12-07
2877 | NAVL25 | NAVL25 | chennai | chennai |  | CHN | Indus | IN-3152483 | R/NN-685452 |  | SO | 2022-12-02 | NAVL25 | 4G_FD900_NAVL25 | 4G_FD2100_NAVL25 | 4G_TD_NAVL25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809073 | 2022-12-14 | P/FVC/MDS/1119079/2022 | 2022-12-20 |  |  |  |  | ST202212807756 | 2022-12-14 | P/FBW/MDS/1119179/2022 | 2022-12-20
2878 | VTPT22 | VTPT22 | chennai | chennai |  | CHN | Indus | IN-3152394 | R/NN-685359 |  | SO | 2022-12-02 | VTPT22 | 4G_FD900_VTPT22 | 4G_FD2100_VTPT22 | 4G_TD_VTPT22 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | G1800+L1800+L2300 |  |  |  |  | ST202212809199 | 2022-12-14 | P/FVC/MDS/1119094/2022 | 2022-12-20 |  |  |  |  | ST202212808092 | 2022-12-14 | P/FBW/MDS/1119194/2022 | 2022-12-20
2879 | ERESID | ERESID | chennai | chennai |  | CHN | IBUS | - | - |  | SO | 2022-10-12 | ERESID | 4G_FD900_ERESID | 4G_FD2100_ERESID | 4G_TD_ERESID | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202211729780 | 2022-11-17 | P/FVC/MDS/1115124/2022 | 2022-11-24 |  |  |  |  | ST202211729899 | 2022-11-17 | P/FBW/MDS/1115106/2022 | 2022-11-24
2880 | KZK109 | KZK109 | Keezhakarai |  |  | ROTN | ATC | TN/RA/AT/23490 | T22TN05991 |  |  | 2022-11-16 | KZK109 | 4G_FD900_KZK109 | 4G_FD2100_KZK109 | 4G_TD_KZK109 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211738373 | 2022-11-18 | P/FVC/MDS/1115212/2022 | 2022-11-24 | ST202211729821 | 2022-11-17 | P/FVC/MDS/1115150/2022 | 2022-11-24 | ST202211729699 | 2022-11-17 | P/FVC/MDS/1115116/2022 | 2022-11-24 | ST202211726190 | 2022-11-16 | P/FBW/MDS/1115070/2022 | 2022-11-24
2881 | VLRM81 | VLRM81 | Villupuram Sports Stadium |  |  | ROTN | Indus | IN-3158601 | R/NN-693272 |  |  | 2022-11-18 | VLRM81 | 4G_FD900_VLRM81 | 4G_FD2100_VLRM81 | 4G_TD_VLRM81 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100 | [5 empty] | ST202211758331 | 2022-11-23 | P/FVC/MDS/1116813/2022 | 2022-11-29 | ST202211758110 | 2022-11-22 | P/FVC/MDS/1116783/2022 | 2022-11-29 | ST202211758613 | 2022-11-16 | P/FBW/MDS/1116854/2022 | 2022-11-29
2882 | VMBD43 | VMBD43 | New Town |  |  | ROTN | Indus | IN-3158607 | R/NN-693273 |  |  | 2022-11-18 | VMBD43 | 4G_FD900_VMBD43 | 4G_FD2100_VMBD43 | 4G_TD_VMBD43 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211761078 | 2022-11-25 | P/FVC/MDS/1116877/2022 | 2022-11-29 | ST202211758329 | 2022-11-23 | P/FVC/MDS/1116811/2022 | 2022-11-29 | ST202211758107 | 2022-11-22 | P/FVC/MDS/1116781/2022 | 2022-11-29 | ST202211758606 | 2022-11-16 | P/FBW/MDS/1116852/2022 | 2022-11-29
2883 | PLCH56 | PLCH56 | venkatesha colony |  |  | ROTN | Airtel | - | - |  |  | 2022-11-29 | PLCH56 | 4G_FD900_PLCH56 | 4G_FD2100_PLCH56 | 4G_TD_PLCH56 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 1902-06-18 | ST202212827886 | 2022-12-16 | P/FVC/MDS/1119683/2022 | 2022-12-22 | ST202212779986 | 2022-12-02 | P/FVC/MDS/1118248/2022 | 2022-12-07 | ST202212780740 | 2022-12-02 | P/FVC/MDS/1118300/2022 | 2022-12-07 | ST202212779636 | 2022-12-01 | P/FBW/MDS/1118156/2022 | 2022-12-07
2884 | NMRD05 | NMRD05 | NM Road5 |  |  | CHN | Indus | IN-3138689 | R/NN-664233 |  |  | 2022-11-18 | NMRD05 | 4G_FD900_NMRD05 | 4G_FD2100_NMRD05 | 4G_TD_NMRD05 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211761043 | 2022-11-25 | P/FVC/MDS/1116874/2022 | 2022-11-29 | ST202211758301 | 2022-11-23 | P/FVC/MDS/1116803/2022 | 2022-11-29 | ST202211758091 | 2022-11-22 | P/FVC/MDS/1116775/2022 | 2022-11-29 | ST202211758584 | 2022-11-16 | P/FBW/MDS/1116844/2022 | 2022-11-29
2885 | ITCER6 | ITCER6 | ITC4,ERNAVUR |  |  | CHN | Indus | IN-3138198 | R/NN-665562 |  |  | 2022-11-14 | ITCER6 | 4G_FD900_ITCER6 | 4G_FD2100_ITCER6 | 4G_TD_ITCER6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211737976 | 2022-11-18 | P/FVC/MDS/1115190/2022 | 2022-11-24 | ST202211729783 | 2022-11-17 | P/FVC/MDS/1115127/2022 | 2022-11-24 | ST202211729676 | 2022-11-17 | P/FVC/MDS/1115111/2022 | 2022-11-24 | ST202211726148 | 2022-11-16 | P/FBW/MDS/1115047/2022 | 2022-11-24
2886 | SOWC15 | SOWC15 | Sowcarpet2 |  |  | CHN | Indus | IN-3154963 | R/NN-686340 |  |  | 2022-11-16 | SOWC15 | 4G_FD900_SOWC15 | 4G_FD2100_SOWC15 | 4G_TD_SOWC15 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211738056 | 2022-11-18 | P/FVC/MDS/1115193/2022 | 2022-11-24 | ST202211729786 | 2022-11-17 | P/FVC/MDS/1115130/2022 | 2022-11-24 | ST202211729677 | 2022-11-17 | P/FVC/MDS/1115112/2022 | 2022-11-24 | ST202211726153 | 2022-11-16 | P/FBW/MDS/1115050/2022 | 2022-11-24
2887 | KUNR41 | KUNR41 | KUNDRATHUR41 |  |  | CHN | Indus | IN-3160550 | R/NN-695527 |  |  | 2022-12-02 | KUNR41 | 4G_FD900_KUNR41 | 4G_FD2100_KUNR41 | 4G_TD_KUNR41 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 900,1800,2100,2300 SACFA | ST202212812020 | 2022-12-15 | P/FVC/MDS/1119375/2022 | 2022-12-20 | ST202212809183 | 2022-12-14 | P/FVC/MDS/1119092/2022 | 2022-12-20 | ST202212811723 | 2022-12-14 | P/FVC/MDS/1119336/2022 | 2022-12-20 | ST202212808066 | 2022-12-14 | P/FBW/MDS/1119192/2022 | 2022-12-20
2888 | KAND34 | KAND34 | Kandanchavadi34 |  |  | CHN | Indus | IN-3138677 | R/NN-664423 |  |  | 2022-12-02 | KAND34 | 4G_FD900_KAND34 | 4G_FD2100_KAND34 | 4G_TD_KAND34 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 900,1800,2100,2300 SACFA | ST202212812015 | 2022-12-15 | P/FVC/MDS/1119372/2022 | 2022-12-20 | ST202212809120 | 2022-12-14 | P/FVC/MDS/1119085/2022 | 2022-12-20 | ST202212811656 | 2022-12-14 | P/FVC/MDS/1119333/2022 | 2022-12-20 | ST202212807883 | 2022-12-14 | P/FBW/MDS/1119185/2022 | 2022-12-20
2889 | DVMPT5 | DVMPT5 | DEVAM PATTU 3 |  |  | ROTN | Indus | IN-3157540 | R/NN-691528 |  |  | 2022-11-29 | DVMPT5 | 4G_FD900_DVMPT5 | 4G_FD2100_DVMPT5 | 4G_TD_DVMPT5 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212780574 | 2022-12-02 | P/FVC/MDS/1118335/2022 | 2022-12-08 | ST202212779973 | 2022-12-02 | P/FVC/MDS/1118243/2022 | 2022-12-07 | ST202212780727 | 2022-12-02 | P/FVC/MDS/1118296/2022 | 2022-12-07 | ST202212779630 | 2022-12-01 | P/FBW/MDS/1118151/2022 | 2022-12-07
2890 | PLMPM6 | PLMPM6 | Palampalayam |  |  | ROTN | Indus | IN-3152278 | R/NN-684849 |  |  | 2022-11-14 | PLMPM6 | 4G_FD900_PLMPM6 | 4G_FD2100_PLMPM6 | 4G_TD_PLMPM6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211737975 | 2022-11-18 | P/FVC/MDS/1115189/2022 | 2022-11-24 | ST202211729782 | 2022-11-17 | P/FVC/MDS/1115126/2022 | 2022-11-24 | ST202211729673 | 2022-11-17 | P/FVC/MDS/1115110/2022 | 2022-11-24 | ST202211726147 | 2022-11-16 | P/FBW/MDS/1115046/2022 | 2022-11-24
2891 | TRY419 | TRY419 | Thuvakudi Industrial estate-II |  |  | ROTN | Indus | IN-3141959 | R/NN-670889 |  |  | 2022-11-23 | TRY419 | 4G_FD900_TRY419 | 4G_FD2100_TRY419 | 4G_TD_TRY419 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212780537 | 2022-12-02 | P/FVC/MDS/1118326/2022 | 2022-12-08 | ST202212779887 | 2022-12-02 | P/FVC/MDS/1118214/2022 | 2022-12-07 | ST202212780635 | 2022-12-02 | P/FVC/MDS/1118284/2022 | 2022-12-07 | ST202212779515 | 2022-12-01 | P/FBW/MDS/1118124/2022 | 2022-12-07
2892 | OGALR2 | OGALR2 | Ogalur 2 (East) |  |  | ROTN | Indus | IN-3147360 | R/NN-678031 |  |  | 2022-11-29 | OGALR2 | 4G_FD900_OGALR2 | 4G_FD2100_OGALR2 | 4G_TD_OGALR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212780577 | 2022-12-02 | P/FVC/MDS/1118337/2022 | 2022-12-08 | ST202212779978 | 2022-12-02 | P/FVC/MDS/1118245/2022 | 2022-12-07 | ST202212780736 | 2022-12-02 | P/FVC/MDS/1118298/2022 | 2022-12-07 | ST202212779632 | 2022-12-01 | P/FBW/MDS/1118153/2022 | 2022-12-07
2893 | KTTR04 | KTTR04 | Balaji Mess |  |  | ROTN | Indus | IN-3147370 | R/NN-678101 |  |  | 2022-11-14 | KTTR04 | 4G_FD900_KTTR04 | 4G_FD2100_KTTR04 | 4G_TD_KTTR04 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211737974 | 2022-11-18 | P/FVC/MDS/1115188/2022 | 2022-11-24 | ST202211729781 | 2022-11-17 | P/FVC/MDS/1115125/2022 | 2022-11-24 | ST202211729672 | 2022-11-17 | P/FVC/MDS/1115109/2022 | 2022-11-24 | ST202211726145 | 2022-11-16 | P/FBW/MDS/1115045/2022 | 2022-11-24
2894 | CBE968 | CBE968 | Mtp Road |  |  | ROTN | Indus | IN-3151964 | R/NN-684674 |  |  | 2022-11-16 | CBE968 | 4G_FD900_CBE968 | 4G_FD2100_CBE968 | 4G_TD_CBE968 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202211738071 | 2022-11-18 | P/FVC/MDS/1115198/2022 | 2022-11-24 | ST202211729795 | 2022-11-17 | P/FVC/MDS/1115136/2022 | 2022-11-24 | ST202211729694 | 2022-11-17 | P/FVC/MDS/1115115/2022 | 2022-11-24 | ST202211726163 | 2022-11-16 | P/FBW/MDS/1115056/2022 | 2022-11-24
2895 | MADH32 | MADH32 | Madhavaram 32 |  |  | CHN | Indus | IN-3153262 | R/NN-686244 |  |  | 2022-11-29 | MADH32 | 4G_FD900_MADH32 | 4G_FD2100_MADH32 | 4G_TD_MADH32 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212780578 | 2022-12-02 | P/FVC/MDS/1118338/2022 | 2022-12-08 | ST202212779979 | 2022-12-02 | P/FVC/MDS/1118246/2022 | 2022-12-07 | ST202212780737 | 2022-12-02 | P/FVC/MDS/1118299/2022 | 2022-12-07 | ST202212779633 | 2022-12-01 | P/FBW/MDS/1118154/2022 | 2022-12-07
2896 | KTRPU2 | KTRPU2 | Kottaieruppu 2 |  |  | ROTN | Indus | IN-3153274 | R/NN-686336 |  |  | 2022-11-16 | KTRPU2 | 4G_FD900_KTRPU2 | 4G_FD2100_KTRPU2 | 4G_TD_KTRPU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211738058 | 2022-11-18 | P/FVC/MDS/1115195/2022 | 2022-11-24 | ST202211729791 | 2022-11-17 | P/FVC/MDS/1115132/2022 | 2022-11-24 | ST202211729693 | 2022-11-17 | P/FVC/MDS/1115114/2022 | 2022-11-24 | ST202211726156 | 2022-11-16 | P/FBW/MDS/1115052/2022 | 2022-11-24
2897 | SEMB18 | SEMB18 | Sembiam 18 |  |  | CHN | Indus | IN-3160551 | R/NN-695530 |  |  | 2022-12-02 | SEMB18 | 4G_FD900_SEMB18 | 4G_FD2100_SEMB18 | 4G_TD_SEMB18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 900,1800,2100,2300 SACFA | ST202212812021 | 2022-12-15 | P/FVC/MDS/1119376/2022 | 2022-12-20 | ST202212809184 | 2022-12-14 | P/FVC/MDS/1119093/2022 | 2022-12-20 | ST202212811724 | 2022-12-14 | P/FVC/MDS/1119337/2022 | 2022-12-20 | ST202212808091 | 2022-12-14 | P/FBW/MDS/1119193/2022 | 2022-12-20
2898 | KILK18 | KILK18 | KEELKATALAI 18 |  |  | CHN | Indus | IN-3160549 | R/NN-695445 |  |  | 2022-12-02 | KILK18 | 4G_FD900_KILK18 | 4G_FD2100_KILK18 | 4G_TD_KILK18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 900,1800,2100,2300 SACFA | ST202212812019 | 2022-12-15 | P/FVC/MDS/1119374/2022 | 2022-12-20 | ST202212809162 | 2022-12-14 | P/FVC/MDS/1119091/2022 | 2022-12-20 | ST202212811722 | 2022-12-14 | P/FVC/MDS/1119335/2022 | 2022-12-20 | ST202212808065 | 2022-12-14 | P/FBW/MDS/1119191/2022 | 2022-12-20
2899 | MYPRI2 | MYPRI2 | Mayiladumparai 2 |  |  | ROTN | Indus | IN-3153662 | R/NN-686852 |  |  | 2022-11-29 | MYPRI2 | 4G_FD900_MYPRI2 | 4G_FD2100_MYPRI2 | 4G_TD_MYPRI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212780575 | 2022-12-02 | P/FVC/MDS/1118336/2022 | 2022-12-08 | ST202212779977 | 2022-12-02 | P/FVC/MDS/1118244/2022 | 2022-12-07 | ST202212780735 | 2022-12-02 | P/FVC/MDS/1118297/2022 | 2022-12-07 | ST202212779631 | 2022-12-01 | P/FBW/MDS/1118152/2022 | 2022-12-07
2900 | CDL109 | CDL109 | CDLR - Old Town |  |  | ROTN | Indus | IN-3153665 | R/NN-686855 |  |  | 2022-12-02 | CDL109 | 4G_FD900_CDL109 | 4G_FD2100_CDL109 | 4G_TD_CDL109 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD | 900,1800,2100,2300 SACFA | ST202212812016 | 2022-12-15 | P/FVC/MDS/1119373/2022 | 2022-12-20 | ST202212809136 | 2022-12-14 | P/FVC/MDS/1119086/2022 | 2022-12-20 | ST202212811721 | 2022-12-14 | P/FVC/MDS/1119334/2022 | 2022-12-20 | ST202212807885 | 2022-12-14 | P/FBW/MDS/1119186/2022 | 2022-12-20
2901 | GMPD37 | GMPD37 | Vivekananda St |  |  | ROTN | Indus | IN-3154472 | R/NN-687790 |  |  | 2022-11-16 | GMPD37 | 4G_FD900_GMPD37 | 4G_FD2100_GMPD37 | 4G_TD_GMPD37 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202211738379 | 2022-11-18 | P/FVC/MDS/1115216/2022 | 2022-11-24 | ST202211729830 | 2022-11-17 | P/FVC/MDS/1115154/2022 | 2022-11-24 | ST202211729700 | 2022-11-17 | P/FVC/MDS/1115117/2022 | 2022-11-24 | ST202211726201 | 2022-11-16 | P/FBW/MDS/1115074/2022 | 2022-11-24
2902 | VPTO11 | VPTO11 | Vysarpadi Town 11 |  |  | CHN | Indus | IN-3154343 | R/NN-687793 |  |  | 2022-11-16 | VPTO11 | 4G_FD900_VPTO11 | 4G_FD2100_VPTO11 | 4G_TD_VPTO11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211738387 | 2022-11-18 | P/FVC/MDS/1115219/2022 | 2022-11-24 | ST202211729837 | 2022-11-17 | P/FVC/MDS/1115157/2022 | 2022-11-24 | ST202211729705 | 2022-11-17 | P/FVC/MDS/1115118/2022 | 2022-11-24 | ST202211726208 | 2022-11-16 | P/FBW/MDS/1115077/2022 | 2022-11-24
2903 | KPLMM4 | KPLMM4 | Lg Industries |  |  | ROTN | Indus | IN-3154479 | R/NN-687795 |  |  | 2022-11-18 | KPLMM4 | 4G_FD900_KPLMM4 | 4G_FD2100_KPLMM4 | 4G_TD_KPLMM4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211761044 | 2022-11-25 | P/FVC/MDS/1116875/2022 | 2022-11-29 | ST202211758303 | 2022-11-23 | P/FVC/MDS/1116805/2022 | 2022-11-29 |  |  |  |  | ST202211758586 | 2022-11-16 | P/FBW/MDS/1116846/2022 | 2022-11-29
2904 | TIVR52 | TIVR52 | T.Nagar |  |  | ROTN | Indus | IN-3154964 | R/NN-687791 |  |  | 2022-11-16 | TIVR52 | 4G_FD900_TIVR52 | 4G_FD2100_TIVR52 | 4G_TD_TIVR52 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211738407 | 2022-11-18 | P/FVC/MDS/1115231/2022 | 2022-11-24 | ST202211729855 | 2022-11-17 | P/FVC/MDS/1115169/2022 | 2022-11-24 | ST202211729706 | 2022-11-17 | P/FVC/MDS/1115119/2022 | 2022-11-24 | ST202211726236 | 2022-11-16 | P/FBW/MDS/1115089/2022 | 2022-11-24
2905 | AGLM12 | AGLM12 | Sardar Raj College Of Engg |  |  | ROTN | Indus | IN-3155287 | R/NN-688968 |  |  | 2022-11-16 | AGLM12 | 4G_FD900_AGLM12 | 4G_FD2100_AGLM12 | 4G_TD_AGLM12 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211738080 | 2022-11-18 | P/FVC/MDS/1115199/2022 | 2022-11-24 | ST202211729799 | 2022-11-17 | P/FVC/MDS/1115137/2022 | 2022-11-24 |  |  |  |  | ST202211726164 | 2022-11-16 | P/FBW/MDS/1115057/2022 | 2022-11-24
2906 | VNDV11 | VNDV11 | Vandavasi Rd |  |  | ROTN | ATC | TN/TV/AT/23558 | T22TN07506 |  |  | 2022-11-16 | VNDV11 | 4G_FD900_VNDV11 | 4G_FD2100_VNDV11 | 4G_TD_VNDV11 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211738057 | 2022-11-18 | P/FVC/MDS/1115194/2022 | 2022-11-24 | ST202211729790 | 2022-11-17 | P/FVC/MDS/1115131/2022 | 2022-11-24 | ST202211729692 | 2022-11-17 | P/FVC/MDS/1115113/2022 | 2022-11-24 | ST202211726154 | 2022-11-16 | P/FBW/MDS/1115051/2022 | 2022-11-24
2907 | NKL034 | NKL034 | Namakkal |  |  | ROTN | Indus | IN-3154340 | R/NN-687621 |  | SO | 2022-12-09 | NKL034 | 4G_FD900_NKL034 | 4G_FD2100_NKL034 | 4G_TD_NKL034 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212810997 | 2022-12-14 | P/FVC/MDS/1119161/2022 | 2022-12-20 |  |  |  |  | ST202212811059 | 2022-12-14 | P/FBW/MDS/1119259/2022 | 2022-12-20
2908 | KNKI21 | KNKI21 | Kanniyakumari |  |  | ROTN | Indus | IN-3161277 | R/NN-696627 |  | SO | 2022-12-09 | KNKI21 | 4G_FD900_KNKI21 | 4G_FD2100_KNKI21 | 4G_TD_KNKI21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811419 | 2022-12-14 | P/FVC/MDS/1119326/2022 | 2022-12-20 |  |  |  |  | ST202212811394 | 2022-12-14 | P/FBW/MDS/1119292/2022 | 2022-12-20
2909 | MGDI14 | MGDI14 | Thiruvarur |  |  | ROTN | Airtel | - | - |  | SO | 2022-12-09 | MGDI14 | 4G_FD900_MGDI14 | 4G_FD2100_MGDI14 | 4G_TD_MGDI14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202106362387 | 2021-06-25 | P/FVC/MDS/1049990/2021 | 2021-08-09 | ST202212811057 | 2022-12-14 | P/FVC/MDS/1119163/2022 | 2022-12-20 |  |  |  |  | ST202212811070 | 2022-12-14 | P/FBW/MDS/1119261/2022 | 2022-12-20
2910 | OKDI09 | OKDI09 | Madurai |  |  | ROTN | Indus | IN-3160847 | R/NN-696158 |  | SO | 2022-12-09 | OKDI09 | 4G_FD900_OKDI09 | 4G_FD2100_OKDI09 | 4G_TD_OKDI09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811417 | 2022-12-14 | P/FVC/MDS/1119324/2022 | 2022-12-20 |  |  |  |  | ST202212811380 | 2022-12-14 | P/FBW/MDS/1119290/2022 | 2022-12-20
2911 | PDY413 | PDY413 | Puducherry |  |  | ROTN | Indus | IN-3161313 | R/NN-696684 |  | SO | 2022-12-09 | PDY413 | 4G_FD900_PDY413 | 4G_FD2100_PDY413 | 4G_TD_PDY413 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212811428 | 2022-12-14 | P/FVC/MDS/1119328/2022 | 2022-12-20 | ST202212811920 | 2022-12-14 | P/FVC/MDS/1119357/2022 | 2022-12-20 | ST202212811405 | 2022-12-14 | P/FBW/MDS/1119294/2022 | 2022-12-20
2912 | KAGIT3 | KAGIT3 | Karur |  |  | ROTN | Indus | IN-3160848 | R/NN-696161 |  | SO | 2022-12-09 | KAGIT3 | 4G_FD900_KAGIT3 | 4G_FD2100_KAGIT3 | 4G_TD_KAGIT3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811253 | 2022-12-14 | P/FVC/MDS/1119300/2022 | 2022-12-20 |  |  |  |  | ST202212811223 | 2022-12-14 | P/FBW/MDS/1119266/2022 | 2022-12-20
2913 | KUNNA4 | KUNNA4 | Tiruppur |  |  | ROTN | Indus | IN-3160849 | R/NN-696165 |  | SO | 2022-12-09 | KUNNA4 | 4G_FD900_KUNNA4 | 4G_FD2100_KUNNA4 | 4G_TD_KUNNA4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812062 | 2022-12-15 | P/FVC/MDS/1119399/2022 | 2022-12-20 | ST202212811264 | 2022-12-14 | P/FVC/MDS/1119301/2022 | 2022-12-20 |  |  |  |  | ST202212811224 | 2022-12-14 | P/FBW/MDS/1119267/2022 | 2022-12-20
2914 | GDHM29 | GDHM29 | Vellore |  |  | ROTN | Indus | IN-3156003 | R/NN-688776 |  | SO | 2022-12-09 | GDHM29 | 4G_FD900_GDHM29 | 4G_FD2100_GDHM29 | 4G_TD_GDHM29 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811412 | 2022-12-14 | P/FVC/MDS/1119323/2022 | 2022-12-20 |  |  |  |  | ST202212811370 | 2022-12-14 | P/FBW/MDS/1119289/2022 | 2022-12-20
2915 | TIR500 | TIR500 | Tiruppur |  |  | ROTN | Indus | IN-3130131 | R/NN-653789 |  | SO | 2022-12-09 | TIR500 | 4G_FD900_TIR500 | 4G_FD2100_TIR500 | 4G_TD_TIR500 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212811055 | 2022-12-14 | P/FVC/MDS/1119162/2022 | 2022-12-20 | ST202212811909 | 2022-12-14 | P/FVC/MDS/1119354/2022 | 2022-12-20 | ST202212811060 | 2022-12-14 | P/FBW/MDS/1119260/2022 | 2022-12-20
2916 | KRMD15 | KRMD15 | Coimbatore |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-02 | KRMD15 | 4G_FD900_KRMD15 | 4G_FD2100_KRMD15 | 4G_TD_KRMD15 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809278 | 2022-12-14 | P/FVC/MDS/1119104/2022 | 2022-12-20 |  |  |  |  | ST202212809013 | 2022-12-14 | P/FBW/MDS/1119204/2022 | 2022-12-20
2917 | THOPR2 | THOPR2 | Madurai |  |  | ROTN | Indus | IN-3149703 | R/NN-682448 |  | SO | 2022-12-09 | THOPR2 | 4G_FD900_THOPR2 | 4G_FD2100_THOPR2 | 4G_TD_THOPR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202209402550 | 2022-09-08 | P/FVC/MDS/1096537/2022 | 2022-09-16 | ST202212811366 | 2022-12-14 | P/FVC/MDS/1119318/2022 | 2022-12-20 |  |  |  |  | ST202212811341 | 2022-12-14 | P/FBW/MDS/1119284/2022 | 2022-12-20
2918 | PLYNR2 | PLYNR2 | Thiruvarur |  |  | ROTN | ATC | TN/TI/AT/23381 | T22TN05278 |  | SO | 2022-12-09 | PLYNR2 | 4G_FD900_PLYNR2 | 4G_FD2100_PLYNR2 | 4G_TD_PLYNR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812070 | 2022-12-15 | P/FVC/MDS/1119403/2022 | 2022-12-20 | ST202212811431 | 2022-12-14 | P/FVC/MDS/1119330/2022 | 2022-12-20 |  |  |  |  | ST202212811413 | 2022-12-14 | P/FBW/MDS/1119296/2022 | 2022-12-20
2919 | ELPLI9 | ELPLI9 | Salem |  |  | ROTN | Indus | IN-3155147 | R/NN-688784 |  | SO | 2022-12-09 | ELPLI9 | 4G_FD900_ELPLI9 | 4G_FD2100_ELPLI9 | 4G_TD_ELPLI9 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212810921 | 2022-12-14 | P/FVC/MDS/1119151/2022 | 2022-12-20 |  |  |  |  | ST202212810946 | 2022-12-14 | P/FBW/MDS/1119250/2022 | 2022-12-20
2920 | SMNLR5 | SMNLR5 | Madurai |  |  | ROTN | Indus | IN-3142355 | R/NN-671745 |  | SO | 2022-12-09 | SMNLR5 | 4G_FD900_SMNLR5 | 4G_FD2100_SMNLR5 | 4G_TD_SMNLR5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811345 | 2022-12-14 | P/FVC/MDS/1119315/2022 | 2022-12-20 |  |  |  |  | ST202212811319 | 2022-12-14 | P/FBW/MDS/1119281/2022 | 2022-12-20
2921 | ANPT07 | ANPT07 | Theni |  |  | ROTN | Indus | IN-3143435 | R/NN-671749 |  | SO | 2022-12-02 | ANPT07 | 4G_FD900_ANPT07 | 4G_FD2100_ANPT07 | 4G_TD_ANPT07 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809368 | 2022-12-14 | P/FVC/MDS/1119110/2022 | 2022-12-20 |  |  |  |  | ST202212809144 | 2022-12-14 | P/FBW/MDS/1119210/2022 | 2022-12-20
2922 | MTGRI4 | MTGRI4 | Krishnagiri |  |  | ROTN | Indus | IN-3144064 | R/NN-675079 |  | SO | 2022-12-02 | MTGRI4 | 4G_FD900_MTGRI4 | 4G_FD2100_MTGRI4 | 4G_TD_MTGRI4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809200 | 2022-12-14 | P/FVC/MDS/1119095/2022 | 2022-12-20 |  |  |  |  | ST202212808128 | 2022-12-14 | P/FBW/MDS/1119195/2022 | 2022-12-20
2923 | VLLPT4 | VLLPT4 | Salem |  |  | ROTN | Indus | IN-3160685 | R/NN-695753 |  | SO | 2022-12-09 | VLLPT4 | 4G_FD900_VLLPT4 | 4G_FD2100_VLLPT4 | 4G_TD_VLLPT4 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812061 | 2022-12-15 | P/FVC/MDS/1119398/2022 | 2022-12-20 | ST202212811252 | 2022-12-14 | P/FVC/MDS/1119299/2022 | 2022-12-20 |  |  |  |  | ST202212811084 | 2022-12-14 | P/FBW/MDS/1119264/2022 | 2022-12-20
2924 | HSR194 | HSR194 | Krishnagiri |  |  | ROTN | Indus | IN-3146561 | R/NN-677515 |  | SO | 2022-12-02 | HSR194 | 4G_FD900_HSR194 | 4G_FD2100_HSR194 | 4G_TD_HSR194 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212808969 | 2022-12-14 | P/FVC/MDS/1119069/2022 | 2022-12-20 |  |  |  |  | ST202212807265 | 2022-12-14 | P/FBW/MDS/1119169/2022 | 2022-12-20
2925 | TRY423 | TRY423 | Tiruchirappalli |  |  | ROTN | Indus | IN-3146563 | R/NN-677519 |  | SO | 2022-12-09 | TRY423 | 4G_FD900_TRY423 | 4G_FD2100_TRY423 | 4G_TD_TRY423 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  | ST202211761153 | 2022-11-25 | P/FVC/MDS/1116882/2022 | 2022-11-29 | ST202211758353 | 2022-11-23 | P/FVC/MDS/1116820/2022 | 2022-11-29 | ST202211758114 | 2022-11-22 | P/FVC/MDS/1116786/2022 | 2022-11-29 | ST202211758633 | 2022-11-16 | P/FBW/MDS/1116861/2022 | 2022-11-29
2926 | TTNI17 | TTNI17 | Thiruvallur |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | TTNI17 | 4G_FD900_TTNI17 | 4G_FD2100_TTNI17 | 4G_TD_TTNI17 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811266 | 2022-12-14 | P/FVC/MDS/1119303/2022 | 2022-12-20 |  |  |  |  | ST202212811251 | 2022-12-14 | P/FBW/MDS/1119269/2022 | 2022-12-20
2927 | DGL083 | DGL083 | Dindigul |  |  | ROTN | Indus | IN-3154252 | R/NN-687630 |  | SO | 2022-12-02 | DGL083 | 4G_FD900_DGL083 | 4G_FD2100_DGL083 | 4G_TD_DGL083 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809074 | 2022-12-14 | P/FVC/MDS/1119080/2022 | 2022-12-20 |  |  |  |  | ST202212807757 | 2022-12-14 | P/FBW/MDS/1119180/2022 | 2022-12-20
2928 | SLM352 | SLM352 | Salem |  |  | ROTN | TVI | - | - |  | SO | 2022-12-09 | SLM352 | 4G_FD900_SLM352 | 4G_FD2100_SLM352 | 4G_TD_SLM352 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212811344 | 2022-12-14 | P/FVC/MDS/1119314/2022 | 2022-12-20 | ST202212811915 | 2022-12-14 | P/FVC/MDS/1119355/2022 | 2022-12-20 | ST202212811318 | 2022-12-14 | P/FBW/MDS/1119280/2022 | 2022-12-20
2929 | MDKI25 | MDKI25 | Coimbatore |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-02 | MDKI25 | 4G_FD900_MDKI25 | 4G_FD2100_MDKI25 | 4G_TD_MDKI25 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809299 | 2022-12-14 | P/FVC/MDS/1119105/2022 | 2022-12-20 |  |  |  |  | ST202212809069 | 2022-12-14 | P/FBW/MDS/1119205/2022 | 2022-12-20
2930 | ARAN07 | ARAN07 | Thiruvallur |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | ARAN07 | 4G_FD900_ARAN07 | 4G_FD2100_ARAN07 | 4G_TD_ARAN07 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812068 | 2022-12-15 | P/FVC/MDS/1119401/2022 | 2022-12-20 | ST202212811327 | 2022-12-14 | P/FVC/MDS/1119311/2022 | 2022-12-20 |  |  |  |  | ST202212811297 | 2022-12-14 | P/FBW/MDS/1119277/2022 | 2022-12-20
2931 | PNRI35 | PNRI35 | Thiruvallur |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | PNRI35 | 4G_FD900_PNRI35 | 4G_FD2100_PNRI35 | 4G_TD_PNRI35 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811316 | 2022-12-14 | P/FVC/MDS/1119309/2022 | 2022-12-20 |  |  |  |  | ST202212811285 | 2022-12-14 | P/FBW/MDS/1119275/2022 | 2022-12-20
2932 | KELCR2 | KELCR2 | Thiruvallur |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | KELCR2 | 4G_FD900_KELCR2 | 4G_FD2100_KELCR2 | 4G_TD_KELCR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812067 | 2022-12-15 | P/FVC/MDS/1119400/2022 | 2022-12-20 | ST202212811317 | 2022-12-14 | P/FVC/MDS/1119310/2022 | 2022-12-20 |  |  |  |  | ST202212811296 | 2022-12-14 | P/FBW/MDS/1119276/2022 | 2022-12-20
2933 | TVLR81 | TVLR81 | Thiruvallur |  |  | ROTN | Indus | IN-3154402 | R/NN-687879 |  | SO | 2022-12-09 | TVLR81 | 4G_FD900_TVLR81 | 4G_FD2100_TVLR81 | 4G_TD_TVLR81 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811359 | 2022-12-14 | P/FVC/MDS/1119316/2022 | 2022-12-20 |  |  |  |  | ST202212811331 | 2022-12-14 | P/FBW/MDS/1119282/2022 | 2022-12-20
2934 | TRYR16 | TRYR16 | Tiruchirappalli |  |  | ROTN | ATC | TN/TR/AT/23549 | T22TN07278 |  | SO | 2022-12-09 | TRYR16 | 4G_FD900_TRYR16 | 4G_FD2100_TRYR16 | 4G_TD_TRYR16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811429 | 2022-12-14 | P/FVC/MDS/1119329/2022 | 2022-12-20 |  |  |  |  | ST202212811406 | 2022-12-14 | P/FBW/MDS/1119295/2022 | 2022-12-20
2935 | ERVDI5 | ERVDI5 | Ramanathapuram |  |  | ROTN | Indus | IN-3154392 | R/NN-687864 |  | SO | 2022-12-09 | ERVDI5 | 4G_FD900_ERVDI5 | 4G_FD2100_ERVDI5 | 4G_TD_ERVDI5 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812069 | 2022-12-15 | P/FVC/MDS/1119402/2022 | 2022-12-20 | ST202212811411 | 2022-12-14 | P/FVC/MDS/1119322/2022 | 2022-12-20 |  |  |  |  | ST202212811369 | 2022-12-14 | P/FBW/MDS/1119288/2022 | 2022-12-20
2936 | HSR202 | HSR202 | Krishnagiri |  |  | ROTN | Indus | IN-3154445 | R/NN-687912 |  | SO | 2022-12-02 | HSR202 | 4G_FD900_HSR202 | 4G_FD2100_HSR202 | 4G_TD_HSR202 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212809260 | 2022-12-14 | P/FVC/MDS/1119102/2022 | 2022-12-20 | ST202212811728 | 2022-12-14 | P/FVC/MDS/1119339/2022 | 2022-12-20 | ST202212808987 | 2022-12-14 | P/FBW/MDS/1119202/2022 | 2022-12-20
2937 | KDKL54 | KDKL54 | Dindigul |  |  | ROTN | Indus | IN-3154846 | R/NN-688422 |  | SO | 2022-12-09 | KDKL54 | 4G_FD900_KDKL54 | 4G_FD2100_KDKL54 | 4G_TD_KDKL54 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212810995 | 2022-12-14 | P/FVC/MDS/1119159/2022 | 2022-12-20 |  |  |  |  | ST202212811046 | 2022-12-14 | P/FBW/MDS/1119257/2022 | 2022-12-20
2938 | RMSM16 | RMSM16 | Ramanathapuram |  |  | ROTN | Indus | IN-3159231 | R/NN-694143 |  | SO | 2022-12-09 | RMSM16 | 4G_FD900_RMSM16 | 4G_FD2100_RMSM16 | 4G_TD_RMSM16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811068 | 2022-12-14 | P/FVC/MDS/1119165/2022 | 2022-12-20 |  |  |  |  | ST202212811083 | 2022-12-14 | P/FBW/MDS/1119263/2022 | 2022-12-20
2939 | ASUR14 | ASUR14 | Coimbatore |  |  | ROTN | Summit | I-TN-CMBR-ENB-0611 | SR-TN001215 |  | SO | 2022-12-02 | ASUR14 | 4G_FD900_ASUR14 | 4G_FD2100_ASUR14 | 4G_TD_ASUR14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809233 | 2022-12-14 | P/FVC/MDS/1119098/2022 | 2022-12-20 |  |  |  |  | ST202212808284 | 2022-12-14 | P/FBW/MDS/1119198/2022 | 2022-12-20
2940 | VLKNP2 | VLKNP2 | Tiruppur |  |  | ROTN | Indus | IN-3158541 | R/NN-693335 |  | SO | 2022-12-02 | VLKNP2 | 4G_FD900_VLKNP2 | 4G_FD2100_VLKNP2 | 4G_TD_VLKNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812014 | 2022-12-15 | P/FVC/MDS/1119371/2022 | 2022-12-20 | ST202212809101 | 2022-12-14 | P/FVC/MDS/1119082/2022 | 2022-12-20 |  |  |  |  | ST202212807796 | 2022-12-14 | P/FBW/MDS/1119182/2022 | 2022-12-20
2941 | DGL130 | DGL130 | Dindigul |  |  | ROTN | ATC | TN/DI/AT/23564 | T22TN07560 |  | SO | 2022-12-02 | DGL130 | 4G_FD900_DGL130 | 4G_FD2100_DGL130 | 4G_TD_DGL130 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809139 | 2022-12-14 | P/FVC/MDS/1119088/2022 | 2022-12-20 |  |  |  |  | ST202212807965 | 2022-12-14 | P/FBW/MDS/1119188/2022 | 2022-12-20
2942 | DGL131 | DGL131 | Dindigul |  |  | ROTN | ATC | TN/DI/AT/23565 | T22TN07561 |  | SO | 2022-12-02 | DGL131 | 4G_FD900_DGL131 | 4G_FD2100_DGL131 | 4G_TD_DGL131 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809160 | 2022-12-14 | P/FVC/MDS/1119089/2022 | 2022-12-20 |  |  |  |  | ST202212807970 | 2022-12-14 | P/FBW/MDS/1119189/2022 | 2022-12-20
2943 | DGL134 | DGL134 | Dindigul |  |  | ROTN | ATC | TN/DI/AT/23568 | T22TN07564 |  | SO | 2022-12-02 | DGL134 | 4G_FD900_DGL134 | 4G_FD2100_DGL134 | 4G_TD_DGL134 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809161 | 2022-12-14 | P/FVC/MDS/1119090/2022 | 2022-12-20 |  |  |  |  | ST202212807972 | 2022-12-14 | P/FBW/MDS/1119190/2022 | 2022-12-20
2944 | ERD260 | ERD260 | Erode |  |  | ROTN | TVI | - | - |  | SO | 2022-12-02 | ERD260 | 4G_FD900_ERD260 | 4G_FD2100_ERD260 | 4G_TD_ERD260 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212809314 | 2022-12-14 | P/FVC/MDS/1119107/2022 | 2022-12-20 | ST202212811736 | 2022-12-14 | P/FVC/MDS/1119340/2022 | 2022-12-20 | ST202212809111 | 2022-12-14 | P/FBW/MDS/1119207/2022 | 2022-12-20
2945 | KPNM07 | KPNM07 | Krishnagiri |  |  | ROTN | Indus | IN-3158529 | R/NN-693320 |  | SO | 2022-12-02 | KPNM07 | 4G_FD900_KPNM07 | 4G_FD2100_KPNM07 | 4G_TD_KPNM07 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212811669 | 2022-12-14 | P/FVC/MDS/1119368/2022 | 2022-12-20 | ST202212809075 | 2022-12-14 | P/FVC/MDS/1119081/2022 | 2022-12-20 |  |  |  |  | ST202212807795 | 2022-12-14 | P/FBW/MDS/1119181/2022 | 2022-12-20
2946 | VANI02 | VANI02 | Ramanathapuram |  |  | ROTN | Indus | IN-3158544 | R/NN-693337 |  | SO | 2022-12-09 | VANI02 | 4G_FD900_VANI02 | 4G_FD2100_VANI02 | 4G_TD_VANI02 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809690 | 2022-12-14 | P/FVC/MDS/1119137/2022 | 2022-12-20 |  |  |  |  | ST202212811222 | 2022-12-14 | P/FBW/MDS/1119265/2022 | 2022-12-20
2947 | NRPYR2 | NRPYR2 | Ramanathapuram |  |  | ROTN | Indus | IN-3158585 | R/NN-693387 |  | SO | 2022-12-09 | NRPYR2 | 4G_FD900_NRPYR2 | 4G_FD2100_NRPYR2 | 4G_TD_NRPYR2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812056 | 2022-12-15 | P/FVC/MDS/1119397/2022 | 2022-12-20 | ST202212811067 | 2022-12-14 | P/FVC/MDS/1119164/2022 | 2022-12-20 |  |  |  |  | ST202212811071 | 2022-12-14 | P/FBW/MDS/1119262/2022 | 2022-12-20
2948 | DPI065 | DPI065 | Dharmapuri |  |  | ROTN | Indus | IN-3158590 | R/NN-693391 |  | SO | 2022-12-02 | DPI065 | 4G_FD900_DPI065 | 4G_FD2100_DPI065 | 4G_TD_DPI065 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212808998 | 2022-12-14 | P/FVC/MDS/1119071/2022 | 2022-12-20 |  |  |  |  | ST202212807542 | 2022-12-14 | P/FBW/MDS/1119171/2022 | 2022-12-20
2949 | NLPL02 | NLPL02 | Dharmapuri |  |  | ROTN | Summit | I-TN-ABEG-ENB-0002 | SR-TN001216 |  | SO | 2022-12-02 | NLPL02 | 4G_FD900_NLPL02 | 4G_FD2100_NLPL02 | 4G_TD_NLPL02 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809217 | 2022-12-14 | P/FVC/MDS/1119096/2022 | 2022-12-20 |  |  |  |  | ST202212808129 | 2022-12-14 | P/FBW/MDS/1119196/2022 | 2022-12-20
2950 | NALLA4 | NALLA4 | Dharmapuri |  |  | ROTN | Indus | IN-3158592 | R/NN-693396 |  | SO | 2022-12-02 | NALLA4 | 4G_FD900_NALLA4 | 4G_FD2100_NALLA4 | 4G_TD_NALLA4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212808999 | 2022-12-14 | P/FVC/MDS/1119072/2022 | 2022-12-20 |  |  |  |  | ST202212807543 | 2022-12-14 | P/FBW/MDS/1119172/2022 | 2022-12-20
2951 | DRPM24 | DRPM24 | Tiruppur |  |  | ROTN | Indus | IN-3158595 | R/NN-693399 |  | SO | 2022-12-02 | DRPM24 | 4G_FD900_DRPM24 | 4G_FD2100_DRPM24 | 4G_TD_DRPM24 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809022 | 2022-12-14 | P/FVC/MDS/1119073/2022 | 2022-12-20 |  |  |  |  | ST202212807604 | 2022-12-14 | P/FBW/MDS/1119173/2022 | 2022-12-20
2952 | GOBI43 | GOBI43 | Erode |  |  | ROTN | Summit | I-TN-GBPM-ENB-0015 | SR-TN001217 |  | SO | 2022-12-02 | GOBI43 | 4G_FD900_GOBI43 | 4G_FD2100_GOBI43 | 4G_TD_GOBI43 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809234 | 2022-12-14 | P/FVC/MDS/1119099/2022 | 2022-12-20 |  |  |  |  | ST202212808940 | 2022-12-14 | P/FBW/MDS/1119199/2022 | 2022-12-20
2953 | PAVAL2 | PAVAL2 | Virudhunagar |  |  | ROTN | Summit | I-TN-VDGR-ENB-0031 | SR-TN001218 |  | SO | 2022-12-02 | PAVAL2 | 4G_FD900_PAVAL2 | 4G_FD2100_PAVAL2 | 4G_TD_PAVAL2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809218 | 2022-12-14 | P/FVC/MDS/1119097/2022 | 2022-12-20 |  |  |  |  | ST202212808283 | 2022-12-14 | P/FBW/MDS/1119197/2022 | 2022-12-20
2954 | REDRP2 | REDRP2 | Virudhunagar |  |  | ROTN | Indus | IN-3158597 | R/NN-693402 |  | SO | 2022-12-02 | REDRP2 | 4G_FD900_REDRP2 | 4G_FD2100_REDRP2 | 4G_TD_REDRP2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809023 | 2022-12-14 | P/FVC/MDS/1119074/2022 | 2022-12-20 |  |  |  |  | ST202212807606 | 2022-12-14 | P/FBW/MDS/1119174/2022 | 2022-12-20
2955 | KATNP2 | KATNP2 | Virudhunagar |  |  | ROTN | Indus | IN-3158602 | R/NN-693406 |  | SO | 2022-12-09 | KATNP2 | 4G_FD900_KATNP2 | 4G_FD2100_KATNP2 | 4G_TD_KATNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812055 | 2022-12-15 | P/FVC/MDS/1119396/2022 | 2022-12-20 | ST202212810996 | 2022-12-14 | P/FVC/MDS/1119160/2022 | 2022-12-20 |  |  |  |  | ST202212811047 | 2022-12-14 | P/FBW/MDS/1119258/2022 | 2022-12-20
2956 | KLKI06 | KLKI06 | Kanniyakumari |  |  | ROTN | Indus | IN-3158536 | R/NN-693324 |  | SO | 2022-12-02 | KLKI06 | 4G_FD900_KLKI06 | 4G_FD2100_KLKI06 | 4G_TD_KLKI06 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212808997 | 2022-12-14 | P/FVC/MDS/1119070/2022 | 2022-12-20 |  |  |  |  | ST202212807541 | 2022-12-14 | P/FBW/MDS/1119170/2022 | 2022-12-20
2957 | TNV081 | TNV081 | Tirunelveli |  |  | ROTN | Indus | IN-3159010 | R/NN-693811 |  | SO | 2022-12-02 | TNV081 | 4G_FD900_TNV081 | 4G_FD2100_TNV081 | 4G_TD_TNV081 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212809102 | 2022-12-14 | P/FVC/MDS/1119083/2022 | 2022-12-20 | ST202212811655 | 2022-12-14 | P/FVC/MDS/1119332/2022 | 2022-12-20 | ST202212807845 | 2022-12-14 | P/FBW/MDS/1119183/2022 | 2022-12-20
2958 | KZKI17 | KZKI17 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | KZKI17 | 4G_FD900_KZKI17 | 4G_FD2100_KZKI17 | 4G_TD_KZKI17 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811279 | 2022-12-14 | P/FVC/MDS/1119305/2022 | 2022-12-20 |  |  |  |  | ST202212811261 | 2022-12-14 | P/FBW/MDS/1119271/2022 | 2022-12-20
2959 | KZKI18 | KZKI18 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | KZKI18 | 4G_FD900_KZKI18 | 4G_FD2100_KZKI18 | 4G_TD_KZKI18 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811308 | 2022-12-14 | P/FVC/MDS/1119307/2022 | 2022-12-20 |  |  |  |  | ST202212811275 | 2022-12-14 | P/FBW/MDS/1119273/2022 | 2022-12-20
2960 | SATH27 | SATH27 | Erode |  |  | ROTN | TVI | - | - |  | SO | 2022-12-09 | SATH27 | 4G_FD900_SATH27 | 4G_FD2100_SATH27 | 4G_TD_SATH27 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811338 | 2022-12-14 | P/FVC/MDS/1119313/2022 | 2022-12-20 |  |  |  |  | ST202212811306 | 2022-12-14 | P/FBW/MDS/1119279/2022 | 2022-12-20
2961 | VLUR14 | VLUR14 | Tirunelveli |  |  | ROTN | Indus | IN-3159061 | R/NN-693852 |  | SO | 2022-12-09 | VLUR14 | 4G_FD900_VLUR14 | 4G_FD2100_VLUR14 | 4G_TD_VLUR14 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811360 | 2022-12-14 | P/FVC/MDS/1119317/2022 | 2022-12-20 |  |  |  |  | ST202212811332 | 2022-12-14 | P/FBW/MDS/1119283/2022 | 2022-12-20
2962 | VLUR15 | VLUR15 | Tirunelveli |  |  | ROTN | Indus | IN-3159091 | R/NN-693853 |  | SO | 2022-12-09 | VLUR15 | 4G_FD900_VLUR15 | 4G_FD2100_VLUR15 | 4G_TD_VLUR15 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811410 | 2022-12-14 | P/FVC/MDS/1119321/2022 | 2022-12-20 |  |  |  |  | ST202212811354 | 2022-12-14 | P/FBW/MDS/1119287/2022 | 2022-12-20
2963 | RMSM17 | RMSM17 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | RMSM17 | 4G_FD900_RMSM17 | 4G_FD2100_RMSM17 | 4G_TD_RMSM17 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811280 | 2022-12-14 | P/FVC/MDS/1119306/2022 | 2022-12-20 |  |  |  |  | ST202212811274 | 2022-12-14 | P/FBW/MDS/1119272/2022 | 2022-12-20
2964 | RMSM19 | RMSM19 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | RMSM19 | 4G_FD900_RMSM19 | 4G_FD2100_RMSM19 | 4G_TD_RMSM19 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811278 | 2022-12-14 | P/FVC/MDS/1119304/2022 | 2022-12-20 |  |  |  |  | ST202212811260 | 2022-12-14 | P/FBW/MDS/1119270/2022 | 2022-12-20
2965 | RMSM21 | RMSM21 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | RMSM21 | 4G_FD900_RMSM21 | 4G_FD2100_RMSM21 | 4G_TD_RMSM21 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811309 | 2022-12-14 | P/FVC/MDS/1119308/2022 | 2022-12-20 |  |  |  |  | ST202212811284 | 2022-12-14 | P/FBW/MDS/1119274/2022 | 2022-12-20
2966 | BHELI4 | BHELI4 | Vellore |  |  | ROTN | ATC | TN/CO/AI/11388 | - |  | SO | 2022-12-16 | BHELI4 | 4G_FD900_BHELI4 | 4G_FD2100_BHELI4 | 4G_TD_BHELI4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809631 | 2022-12-14 | P/FVC/MDS/1119130/2022 | 2022-12-20 |  |  |  |  | ST202212809524 | 2022-12-14 | P/FBW/MDS/1119230/2022 | 2022-12-20
2967 | MLNMN3 | MLNMN3 | Kanniyakumari |  |  | ROTN | TVI | RJTNKKR2003 | - |  | SO | 2022-12-16 | MLNMN3 | 4G_FD900_MLNMN3 | 4G_FD2100_MLNMN3 | 4G_TD_MLNMN3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809718 | 2022-12-14 | P/FVC/MDS/1119140/2022 | 2022-12-20 |  |  |  |  | ST202212809713 | 2022-12-14 | P/FBW/MDS/1119240/2022 | 2022-12-20
2968 | KATUR2 | KATUR2 | chennai |  |  | CHN | Ascend | - | - |  | SO | 2022-12-09 | KATUR2 | 4G_FD900_KATUR2 | 4G_FD2100_KATUR2 | 4G_TD_KATUR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202202053436 | 2022-02-23 | P/FVC/MDS/1076401/2022 | 2022-03-13 | ST202212811328 | 2022-12-14 | P/FVC/MDS/1119312/2022 | 2022-12-20 |  |  |  |  | ST202212811305 | 2022-12-14 | P/FBW/MDS/1119278/2022 | 2022-12-20
2969 | KAND41 | KAND41 | chennai |  |  | CHN | Indus | IN-3160851 | R/NN-696171 |  | SO | 2022-12-09 | KAND41 | 4G_FD900_KAND41 | 4G_FD2100_KAND41 | 4G_TD_KAND41 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811418 | 2022-12-14 | P/FVC/MDS/1119325/2022 | 2022-12-20 |  |  |  |  | ST202212811381 | 2022-12-14 | P/FBW/MDS/1119291/2022 | 2022-12-20
2970 | PONM16 | PONM16 | chennai |  |  | CHN | Indus | IN-3160852 | R/NN-696173 |  | SO | 2022-12-09 | PONM16 | 4G_FD900_PONM16 | 4G_FD2100_PONM16 | 4G_TD_PONM16 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811265 | 2022-12-14 | P/FVC/MDS/1119302/2022 | 2022-12-20 |  |  |  |  | ST202212811250 | 2022-12-14 | P/FBW/MDS/1119268/2022 | 2022-12-20
2971 | HIET09 | HIET09 | chennai |  |  | CHN | Srigom | - | - |  | SO | 2022-12-09 | HIET09 | 4G_FD900_HIET09 | 4G_FD2100_HIET09 | 4G_TD_HIET09 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811367 | 2022-12-14 | P/FVC/MDS/1119319/2022 | 2022-12-20 |  |  |  |  | ST202212811342 | 2022-12-14 | P/FBW/MDS/1119285/2022 | 2022-12-20
2972 | MADA37 | MADA37 | chennai |  |  | CHN | Indus | IN-3161317 | R/NN-696687 |  | SO | 2022-12-09 | MADA37 | 4G_FD900_MADA37 | 4G_FD2100_MADA37 | 4G_TD_MADA37 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212811368 | 2022-12-14 | P/FVC/MDS/1119320/2022 | 2022-12-20 |  |  |  |  | ST202212811353 | 2022-12-14 | P/FBW/MDS/1119286/2022 | 2022-12-20
2973 | ARMSOT | ARMSOT | chennai |  |  | CHN | Airtel | - | - |  | SO | 2022-12-03 | ARMSOT | 4G_FD900_ARMSOT | 4G_FD2100_ARMSOT | 4G_TD_MADA37 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212799131 | 2022-12-12 | P/FVC/MDS/1118926/2022 | 2022-12-16 |  |  |  |  | ST202212799164 | 2022-12-12 | P/FBW/MDS/1118954/2022 | 2022-12-16
2974 | NGL103 | NGL103 | Kanniyakumari |  |  | ROTN | Indus | IN-3140118 | R/NN-669056 |  | SO | 2022-12-16 | NGL103 | 4G_FD900_NGL103 | 4G_FD2100_NGL103 | 4G_TD_NGL103 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854923 | 2022-12-27 | P/FVC/MDS/1120683/2023 | 2023-01-06 |  |  | #N/A | #N/A | ST202212853458 | 2022-12-27 | P/FBW/MDS/1120627/2023 | 2023-01-06
2975 | VALKD2 | VALKD2 | Theni |  |  | ROTN | ATC | TN/TH/AT/23615 | T22TN07924 |  | SO | 2022-12-16 | VALKD2 | 4G_FD900_VALKD2 | 4G_FD2100_VALKD2 | 4G_TD_VALKD2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854947 | 2022-12-27 | P/FVC/MDS/1120686/2023 | 2023-01-06 |  |  |  |  | ST202212853485 | 2022-12-27 | P/FBW/MDS/1120630/2023 | 2023-01-06
2976 | PKLPT2 | PKLPT2 | Puducherry |  |  | ROTN | Indus | IN-3161278 | R/NN-696648 |  | SO | 2022-12-16 | PKLPT2 | 4G_FD900_PKLPT2 | 4G_FD2100_PKLPT2 | 4G_TD_PKLPT2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854900 | 2022-12-27 | P/FVC/MDS/1120682/2023 | 2023-01-06 |  |  |  |  | ST202212853457 | 2022-12-27 | P/FBW/MDS/1120626/2023 | 2023-01-06
2977 | MUPAT4 | MUPAT4 | Tiruppur |  |  | ROTN | Indus | IN-3160850 | R/NN-696168 |  | SO | 2022-12-28 | MUPAT4 | 4G_FD900_MUPAT4 | 4G_FD2100_MUPAT4 | 4G_TD_MUPAT4 | G1800+L1800+L2300+L900 | Full Site WPC ID WIP |  | ST202301003120 | 2023-01-03 | 0 | 0 | ST202301003329 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003996 | 2023-01-03 | 0 | 0
2978 | TLNGD2 | TLNGD2 | Nagapattinam |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-02 | TLNGD2 | 4G_FD900_TLNGD2 | 4G_FD2100_TLNGD2 | 4G_TD_TLNGD2 | G1800+L1800+L2300+L900 | All site WPC wip |  |  |  | #N/A | #N/A |  |  | #N/A | #N/A | [6 empty] | #N/A | #N/A
2979 | TIVM33 | TIVM33 | Viluppuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | TIVM33 | 4G_FD900_TIVM33 | 4G_FD2100_TIVM33 | 4G_TD_TIVM33 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854826 | 2022-12-27 | P/FVC/MDS/1120672/2023 | 2023-01-06 |  |  |  |  | ST202212853388 | 2022-12-27 | P/FBW/MDS/1120616/2023 | 2023-01-06
2980 | ANPT06 | ANPT06 | Theni |  |  | ROTN | Indus | IN-3142344 | R/NN-671741 |  | SO | 2022-12-28 | ANPT06 | 4G_FD900_ANPT06 | 4G_FD2100_ANPT06 | 4G_TD_ANPT06 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003303 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003980 | 2023-01-03 | 0 | 0
2981 | AGANI2 | AGANI2 | Nagapattinam |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | AGANI2 | 4G_FD900_AGANI2 | 4G_FD2100_AGANI2 | 4G_TD_AGANI2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854825 | 2022-12-27 | P/FVC/MDS/1120671/2023 | 2023-01-06 |  |  |  |  | ST202212853386 | 2022-12-27 | P/FBW/MDS/1120615/2023 | 2023-01-06
2982 | MELUR2 | MELUR2 | Nagapattinam |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | MELUR2 | 4G_FD900_MELUR2 | 4G_FD2100_MELUR2 | 4G_TD_MELUR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854853 | 2022-12-27 | P/FVC/MDS/1120676/2023 | 2023-01-06 |  |  |  |  | ST202212853426 | 2022-12-27 | P/FBW/MDS/1120620/2023 | 2023-01-06
2983 | MDTI51 | MDTI51 | Nagapattinam |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | MDTI51 | 4G_FD900_MDTI51 | 4G_FD2100_MDTI51 | 4G_TD_MDTI51 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854827 | 2022-12-27 | P/FVC/MDS/1120673/2023 | 2023-01-06 |  |  |  |  | ST202212853409 | 2022-12-27 | P/FBW/MDS/1120617/2023 | 2023-01-06
2984 | TRY428 | TRY428 | Tiruchirappalli |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | TRY428 | 4G_FD900_TRY428 | 4G_FD2100_TRY428 | 4G_TD_TRY428 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  |  |  | #N/A | #N/A | ST202212854803 | 2022-12-27 | P/FVC/MDS/1120670/2023 | 2023-01-06 | ST202212857120 | 2022-12-27 | P/FVC/MDS/1120721/2023 | 2023-01-06 | ST202212853385 | 2022-12-27 | P/FBW/MDS/1120614/2023 | 2023-01-06
2985 | PDY327 | PDY327 | Puducherry |  |  | ROTN | ATC | TN/PO/AT/23636 | T22TN08052 |  | SO | 2022-12-16 | PDY327 | 4G_FD900_PDY327 | 4G_FD2100_PDY327 | 4G_TD_PDY327 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  |  |  | #N/A | #N/A | ST202212854948 | 2022-12-27 | P/FVC/MDS/1120687/2023 | 2023-01-06 | ST202212857122 | 2022-12-27 | P/FVC/MDS/1120723/2023 | 2023-01-06 | ST202212853573 | 2022-12-27 | P/FBW/MDS/1120631/2023 | 2023-01-06
2986 | MOPRP2 | MOPRP2 | Coimbatore |  |  | ROTN | TVI | - | - |  | SO | 2022-12-23 | MOPRP2 | 4G_FD900_MOPRP2 | 4G_FD2100_MOPRP2 | 4G_TD_MOPRP2 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003360 | 2023-01-03 | 0 | 0 |  |  | #N/A | #N/A | ST202212868119 | 31-12-2022 | 0 | 0
2987 | DVMNL2 | DVMNL2 | Ariyalur |  |  | ROTN | Summit | I-TN-DPYM-ENB-9059 | SR-TN001214 |  | SO | 2022-12-02 | DVMNL2 | 4G_FD900_DVMNL2 | 4G_FD2100_DVMNL2 | 4G_TD_DVMNL2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212835730 | 2022-12-21 | P/FVC/MDS/1120298/2022 | 2022-12-27 | ST202212835702 | 2022-12-21 | P/FVC/MDS/1120288/2022 | 2022-12-27 |  |  |  |  | ST202212831682 | 2022-12-19 | P/FBW/MDS/1120287/2022 | 2022-12-27
2988 | ERD257 | ERD257 | Erode |  |  | ROTN | TVI | - | - |  | SO | 2022-12-16 | ERD257 | 4G_FD900_ERD257 | 4G_FD2100_ERD257 | 4G_TD_ERD257 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  |  |  | #N/A | #N/A | ST202212854802 | 2022-12-27 | P/FVC/MDS/1120669/2023 | 2023-01-06 | ST202212857093 | 2022-12-27 | P/FVC/MDS/1120720/2023 | 2023-01-06 | ST202212853364 | 2022-12-27 | P/FBW/MDS/1120613/2023 | 2023-01-06
2989 | ERD261 | ERD261 | Erode |  |  | ROTN | TVI | - | - |  | SO | 2022-12-16 | ERD261 | 4G_FD900_ERD261 | 4G_FD2100_ERD261 | 4G_TD_ERD261 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  |  |  | #N/A | #N/A | ST202212854924 | 2022-12-27 | P/FVC/MDS/1120684/2023 | 2023-01-06 | ST202212857121 | 2022-12-27 | P/FVC/MDS/1120722/2023 | 2023-01-06 | ST202212853483 | 2022-12-27 | P/FBW/MDS/1120628/2023 | 2023-01-06
2990 | PDCRM5 | PDCRM5 | Namakkal |  |  | ROTN | ATC | TN/NM/AT/23577 | T22TN07573 |  | SO | 2022-12-28 | PDCRM5 | 4G_FD900_PDCRM5 | 4G_FD2100_PDCRM5 | 4G_TD_PDCRM5 | G1800+L1800+L2300+L900 | Full Site WPC ID WIP |  | ST202301003121 | 2023-01-03 | 0 | 0 | ST202301003347 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301004005 | 2023-01-03 | 0 | 0
2991 | TCMDM5 | TCMDM5 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | TCMDM5 | 4G_FD900_TCMDM5 | 4G_FD2100_TCMDM5 | 4G_TD_TCMDM5 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854776 | 2022-12-27 | P/FVC/MDS/1120666/2023 | 2023-01-06 |  |  |  |  | ST202212853343 | 2022-12-27 | P/FBW/MDS/1120610/2023 | 2023-01-06
2992 | RMPM52 | RMPM52 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | RMPM52 | 4G_FD900_RMPM52 | 4G_FD2100_RMPM52 | 4G_TD_RMPM52 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854851 | 2022-12-27 | P/FVC/MDS/1120674/2023 | 2023-01-06 |  |  |  |  | ST202212853410 | 2022-12-27 | P/FBW/MDS/1120618/2023 | 2023-01-06
2993 | RMPM53 | RMPM53 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | RMPM53 | 4G_FD900_RMPM53 | 4G_FD2100_RMPM53 | 4G_TD_RMPM53 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854777 | 2022-12-27 | P/FVC/MDS/1120667/2023 | 2023-01-06 |  |  |  |  | ST202212853362 | 2022-12-27 | P/FBW/MDS/1120611/2023 | 2023-01-06
2994 | PLNI40 | PLNI40 | Dindigul |  |  | ROTN | ATC | TN/DI/AT/23585 | T22TN07601 |  | SO | 2022-12-16 | PLNI40 | 4G_FD900_PLNI40 | 4G_FD2100_PLNI40 | 4G_TD_PLNI40 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854898 | 2022-12-27 | P/FVC/MDS/1120680/2023 | 2023-01-06 |  |  |  |  | ST202212853441 | 2022-12-27 | P/FBW/MDS/1120624/2023 | 2023-01-06
2995 | PLNI42 | PLNI42 | Dindigul |  |  | ROTN | ATC | TN/DI/AT/23587 | T22TN07603 |  | SO | 2022-12-16 | PLNI42 | 4G_FD900_PLNI42 | 4G_FD2100_PLNI42 | 4G_TD_PLNI42 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854925 | 2022-12-27 | P/FVC/MDS/1120685/2023 | 2023-01-06 |  |  |  |  | ST202212853484 | 2022-12-27 | P/FBW/MDS/1120629/2023 | 2023-01-06
2996 | APKT75 | APKT75 | Virudhunagar |  |  | ROTN | ATC | TN/VI/AT/23592 | T22TN07608 |  | SO | 2022-12-16 | APKT75 | 4G_FD900_APKT75 | 4G_FD2100_APKT75 | 4G_TD_APKT75 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854876 | 2022-12-27 | P/FVC/MDS/1120679/2023 | 2023-01-06 |  |  |  |  | ST202212853440 | 2022-12-27 | P/FBW/MDS/1120623/2023 | 2023-01-06
2997 | RMSM20 | RMSM20 | Ramanathapuram |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-16 | RMSM20 | 4G_FD900_RMSM20 | 4G_FD2100_RMSM20 | 4G_TD_RMSM20 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854852 | 2022-12-27 | P/FVC/MDS/1120675/2023 | 2023-01-06 |  |  |  |  | ST202212853411 | 2022-12-27 | P/FBW/MDS/1120619/2023 | 2023-01-06
2998 | SRMLJ2 | SRMLJ2 | Tirunelveli |  |  | ROTN | Summit | I-TN-DABK-ENB-9001 | SR-TN001241 |  | SO | 2022-12-28 | SRMLJ2 | 4G_FD900_SRMLJ2 | 4G_FD2100_SRMLJ2 | 4G_TD_SRMLJ2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809396 | 2022-12-14 | P/FVC/MDS/1119111/2022 | 2022-12-20 |  |  |  |  | ST202212809145 | 2022-12-14 | P/FBW/MDS/1119211/2022 | 2022-12-20
2999 | PERNH2 | PERNH2 | Nagapattinam |  |  | ROTN | Summit | I-TN-KUTM-ENB-9014 | SR-TN001225 |  | SO | 2022-12-28 | PERNH2 | 4G_FD900_PERNH2 | 4G_FD2100_PERNH2 | 4G_TD_PERNH2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809429 | 2022-12-14 | P/FVC/MDS/1119114/2022 | 2022-12-20 |  |  |  |  | ST202212809204 | 2022-12-14 | P/FBW/MDS/1119214/2022 | 2022-12-20
3000 | PLAKUR | PLAKUR | Ariyalur |  |  | ROTN | Indus | IN-3161758 | R/NN-697362 |  | SO | 2022-12-16 | PLAKUR | 4G_FD900_PLAKUR | 4G_FD2100_PLAKUR | 4G_TD_PLAKUR | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212853120 | 2022-12-27 | P/FVC/MDS/1120588/2023 | 2023-01-06 | ST202212854899 | 2022-12-27 | P/FVC/MDS/1120681/2023 | 2023-01-06 |  |  |  |  | ST202212853456 | 2022-12-27 | P/FBW/MDS/1120625/2023 | 2023-01-06
3001 | AZGPRM | AZGPRM | Kanniyakumari |  |  | ROTN | Summit | I-TN-TSUR-ENB-0002 | SR-TN001227 |  | SO | 2022-12-28 | AZGPRM | 4G_FD900_AZGPRM | 4G_FD2100_AZGPRM | 4G_TD_AZGPRM | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809501 | 2022-12-14 | P/FVC/MDS/1119117/2022 | 2022-12-20 |  |  |  |  | ST202212809239 | 2022-12-14 | P/FBW/MDS/1119217/2022 | 2022-12-20
3002 | MELR23 | MELR23 | Madurai |  |  | ROTN | Summit | I-TN-MELU-ENB-9062 | SR-TN001228 |  | SO | 2022-12-28 | MELR23 | 4G_FD900_MELR23 | 4G_FD2100_MELR23 | 4G_TD_MELR23 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809502 | 2022-12-14 | P/FVC/MDS/1119118/2022 | 2022-12-20 |  |  |  |  | ST202212809311 | 2022-12-14 | P/FBW/MDS/1119218/2022 | 2022-12-20
3003 | SLM445 | SLM445 | Salem |  |  | ROTN | Summit | I-TN-SLEM-ENB-0284 | SR-TN001244 |  | SO | 2022-12-28 | SLM445 | 4G_FD900_SLM445 | 4G_FD2100_SLM445 | 4G_TD_SLM445 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212809530 | 2022-12-14 | P/FVC/MDS/1119120/2022 | 2022-12-20 | ST202301004047 | 2023-01-03 | 0 |  | ST202212809335 | 2022-12-14 | P/FBW/MDS/1119220/2022 | 2022-12-20
3004 | ARNI39 | ARNI39 | Tiruvannamalai |  |  | ROTN | Summit | I-TN-ARNI-ENB-0025 | SR-TN001239 |  | SO | 2022-12-28 | ARNI39 | 4G_FD900_ARNI39 | 4G_FD2100_ARNI39 | 4G_TD_ARNI39 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  | ST202212812023 | 2022-12-15 | P/FVC/MDS/1119378/2022 | 2022-12-20 | ST202212809532 | 2022-12-14 | P/FVC/MDS/1119122/2022 | 2022-12-20 |  |  |  |  | ST202212809362 | 2022-12-14 | P/FBW/MDS/1119222/2022 | 2022-12-20
3005 | MRDLR2 | MRDLR2 | Thanjavur |  |  | ROTN | Summit | I-TN-KBKM-ENB-0058 | SR-TN001229 |  | SO | 2022-12-28 | MRDLR2 | 4G_FD900_MRDLR2 | 4G_FD2100_MRDLR2 | 4G_TD_MRDLR2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809562 | 2022-12-14 | P/FVC/MDS/1119123/2022 | 2022-12-20 |  |  |  |  | ST202212809363 | 2022-12-14 | P/FBW/MDS/1119223/2022 | 2022-12-20
3006 | TIRPY2 | TIRPY2 | Thanjavur |  |  | ROTN | Summit | I-TN-KBKM-ENB-9035 | SR-TN001245 |  | SO | 2022-12-28 | TIRPY2 | 4G_FD900_TIRPY2 | 4G_FD2100_TIRPY2 | 4G_TD_TIRPY2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809563 | 2022-12-14 | P/FVC/MDS/1119124/2022 | 2022-12-20 |  |  |  |  | ST202212809412 | 2022-12-14 | P/FBW/MDS/1119224/2022 | 2022-12-20
3007 | KKLAM2 | KKLAM2 | Tirunelveli |  |  | ROTN | Summit | I-TN-RDHP-ENB-9069 | SR-TN001230 |  | SO | 2022-12-28 | KKLAM2 | 4G_FD900_KKLAM2 | 4G_FD2100_KKLAM2 | 4G_TD_KKLAM2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809585 | 2022-12-14 | P/FVC/MDS/1119126/2022 | 2022-12-20 |  |  |  |  | ST202212809467 | 2022-12-14 | P/FBW/MDS/1119226/2022 | 2022-12-20
3008 | POTHMP | POTHMP | Coimbatore |  |  | ROTN | Indus | IN-3161907 | R/NN-697465 |  | SO | 2022-12-28 | POTHMP | 4G_FD900_POTHMP | 4G_FD2100_POTHMP | 4G_TD_POTHMP | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003177 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003538 | 2023-01-03 | 0 | 0
3009 | NELMBR | NELMBR | Coimbatore |  |  | ROTN | Indus | IN-3162743 | R/NN-698534 |  | SO | 2022-12-28 | NELMBR | 4G_FD900_NELMBR | 4G_FD2100_NELMBR | 4G_TD_NELMBR | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003302 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003968 | 2023-01-03 | 0 | 0
3010 | NCIPL2 | NCIPL2 | Tiruppur |  |  | ROTN | Summit | I-TN-TPPR-ENB-9080 | SR-TN001252 |  | SO | 2022-12-28 | NCIPL2 | 4G_FD900_NCIPL2 | 4G_FD2100_NCIPL2 | 4G_TD_NCIPL2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809630 | 2022-12-14 | P/FVC/MDS/1119129/2022 | 2022-12-20 |  |  |  |  | ST202212809493 | 2022-12-14 | P/FBW/MDS/1119229/2022 | 2022-12-20
3011 | KATERI | KATERI | Vellore |  |  | ROTN | Indus | IN-3161765 | R/NN-697379 |  | SO | 2022-12-23 | KATERI | 4G_FD900_KATERI | 4G_FD2100_KATERI | 4G_TD_KATERI | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212856334 | 2022-12-27 | P/FVC/MDS/1120695/2023 | 2023-01-06 |  |  |  |  | ST202212853634 | 2022-12-27 | P/FBW/MDS/1120639/2023 | 2023-01-06
3012 | MOPRI2 | MOPRI2 | Coimbatore |  |  | ROTN | Indus | IN-3161909 | R/NN-697467 |  | SO | 2022-12-16 | MOPRI2 | 4G_FD900_MOPRI2 | 4G_FD2100_MOPRI2 | 4G_TD_MOPRI2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854874 | 2022-12-27 | P/FVC/MDS/1120677/2023 | 2023-01-06 |  |  |  |  | ST202212853427 | 2022-12-27 | P/FBW/MDS/1120621/2023 | 2023-01-06
3013 | KSING2 | KSING2 | Vellore |  |  | ROTN | Indus | IN-3161768 | R/NN-697385 |  | SO | 2022-12-23 | KSING2 | 4G_FD900_KSING2 | 4G_FD2100_KSING2 | 4G_TD_KSING2 | G1800+L1800+L2300 | Partial Tech Application WIP | 2300 sacfa pending |  |  | #N/A | #N/A | ST202212856335 | 2022-12-27 | P/FVC/MDS/1120696/2023 | 2023-01-06 | [6 empty] | #N/A | #N/A
3014 | PAGAL7 | PAGAL7 | Salem |  |  | ROTN | Indus | IN-3161910 | R/NN-697468 |  | SO | 2022-12-28 | PAGAL7 | 4G_FD900_PAGAL7 | 4G_FD2100_PAGAL7 | 4G_TD_PAGAL7 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003301 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003967 | 2023-01-03 | 0 | 0
3015 | ADMGM3 | ADMGM3 | Thiruvarur |  |  | ROTN | Indus | IN-3161770 | R/NN-697388 |  | SO | 2022-12-28 | ADMGM3 | 4G_FD900_ADMGM3 | 4G_FD2100_ADMGM3 | 4G_TD_ADMGM3 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003160 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003436 | 2023-01-03 | 0 | 0
3016 | POTHM2 | POTHM2 | Thiruvarur |  |  | ROTN | Summit | I-TN-VLGM-ENB-9012 | SR-TN001238 |  | SO | 2022-12-28 | POTHM2 | 4G_FD900_POTHM2 | 4G_FD2100_POTHM2 | 4G_TD_POTHM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812024 | 2022-12-15 | P/FVC/MDS/1119379/2022 | 2022-12-20 | ST202212809633 | 2022-12-14 | P/FVC/MDS/1119131/2022 | 2022-12-20 |  |  |  |  | ST202212809553 | 2022-12-14 | P/FBW/MDS/1119232/2022 | 2022-12-20
3017 | PLVNG2 | PLVNG2 | Sivaganga |  |  | ROTN | Summit | I-TN-KKKD-ENB-9043 | SR-TN001231 |  | SO | 2022-12-28 | PLVNG2 | 4G_FD900_PLVNG2 | 4G_FD2100_PLVNG2 | 4G_TD_PLVNG2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809660 | 2022-12-14 | P/FVC/MDS/1119132/2022 | 2022-12-20 |  |  |  |  | ST202212809554 | 2022-12-14 | P/FBW/MDS/1119233/2022 | 2022-12-20
3018 | AVRPT2 | AVRPT2 | Viluppuram |  |  | ROTN | Summit | I-TN-ACFD-ENB-9001 | SR-TN001240 |  | SO | 2022-12-28 | AVRPT2 | 4G_FD900_AVRPT2 | 4G_FD2100_AVRPT2 | 4G_TD_AVRPT2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812028 | 2022-12-15 | P/FVC/MDS/1119380/2022 | 2022-12-20 | ST202212809661 | 2022-12-14 | P/FVC/MDS/1119133/2022 | 2022-12-20 |  |  |  |  | ST202212809579 | 2022-12-14 | P/FBW/MDS/1119234/2022 | 2022-12-20
3019 | SHSUM3 | SHSUM3 | Theni |  |  | ROTN | Summit | I-TN-ADPJ-ENB-9003 | SR-TN001232 |  | SO | 2022-12-28 | SHSUM3 | 4G_FD900_SHSUM3 | 4G_FD2100_SHSUM3 | 4G_TD_SHSUM3 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809662 | 2022-12-14 | P/FVC/MDS/1119134/2022 | 2022-12-20 |  |  |  |  | ST202212809580 | 2022-12-14 | P/FBW/MDS/1119235/2022 | 2022-12-20
3020 | MNDPT4 | MNDPT4 | Dindigul |  |  | ROTN | Indus | IN-3161784 | R/NN-697403 |  | SO | 2022-12-23 | MNDPT4 | 4G_FD900_MNDPT4 | 4G_FD2100_MNDPT4 | 4G_TD_MNDPT4 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212856336 | 2022-12-27 | P/FVC/MDS/1120697/2023 | 2023-01-06 |  |  |  |  | ST202212853666 | 2022-12-27 | P/FBW/MDS/1120640/2023 | 2023-01-06
3021 | DGL135 | DGL135 | Dindigul |  |  | ROTN | Indus | IN-3161787 | R/NN-697406 |  | SO | 2022-12-28 | DGL135 | 4G_FD900_DGL135 | 4G_FD2100_DGL135 | 4G_TD_DGL135 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003345 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003997 | 2023-01-03 | 0 | 0
3022 | SEMDK1 | SEMDK1 | Dharmapuri |  |  | ROTN | Indus | IN-3161742 | R/NN-697323 |  | SO | 2022-12-28 | SEMDK1 | 4G_FD900_SEMDK1 | 4G_FD2100_SEMDK1 | 4G_TD_SEMDK1 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003176 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003537 | 2023-01-03 | 0 | 0
3023 | VDLR24 | VDLR24 | Cuddalore |  |  | ROTN | Summit | I-TN-KURJ-ENB-0001 | SR-TN001249 |  | SO | 2022-12-28 | VDLR24 | 4G_FD900_VDLR24 | 4G_FD2100_VDLR24 | 4G_TD_VDLR24 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809688 | 2022-12-14 | P/FVC/MDS/1119135/2022 | 2022-12-20 |  |  |  |  | ST202212809609 | 2022-12-14 | P/FBW/MDS/1119236/2022 | 2022-12-20
3024 | NVKTI4 | NVKTI4 | Thiruvarur |  |  | ROTN | Indus | IN-3161857 | R/NN-697420 |  | SO | 2022-12-28 | NVKTI4 | 4G_FD900_NVKTI4 | 4G_FD2100_NVKTI4 | 4G_TD_NVKTI4 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003161 | 2023-01-03 | 0 | 0 |  |  |  |  | ST202301003437 | 2023-01-03 | 0 | 0
3025 | KATRI2 | KATRI2 | Vellore |  |  | ROTN | Indus | IN-3161861 | R/NN-697423 |  | SO | 2022-12-23 | KATRI2 | 4G_FD900_KATRI2 | 4G_FD2100_KATRI2 | 4G_TD_KATRI2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212856377 | 2022-12-27 | P/FVC/MDS/1120698/2023 | 2023-01-06 |  |  |  |  | ST202212853667 | 2022-12-27 | P/FBW/MDS/1120641/2023 | 2023-01-06
3026 | KTYR10 | KTYR10 | Sivaganga |  |  | ROTN | Summit | I-TN-KYRT-ENB-0003 | SR-TN001235 |  | SO | 2022-12-28 | KTYR10 | 4G_FD900_KTYR10 | 4G_FD2100_KTYR10 | 4G_TD_KTYR10 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809760 | 2022-12-14 | P/FVC/MDS/1119141/2022 | 2022-12-20 |  |  |  |  | ST202212809714 | 2022-12-14 | P/FBW/MDS/1119241/2022 | 2022-12-20
3027 | NTHMP2 | NTHMP2 | Pudukkottai |  |  | ROTN | Summit | I-TN-PDKK-ENB-0023 | SR-TN001251 |  | SO | 2022-12-28 | NTHMP2 | 4G_FD900_NTHMP2 | 4G_FD2100_NTHMP2 | 4G_TD_NTHMP2 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD | [5 empty] | ST202212809761 | 2022-12-14 | P/FVC/MDS/1119142/2022 | 2022-12-20 |  |  |  |  | ST202212809743 | 2022-12-14 | P/FBW/MDS/1119242/2022 | 2022-12-20
3028 | KDPARI | KDPARI | Karur |  |  | ROTN | Indus | IN-3161913 | R/NN-697472 |  | SO | 2022-12-28 | KDPARI | 4G_FD900_KDPARI | 4G_FD2100_KDPARI | 4G_TD_KDPARI | G1800+L1800+L2100+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003373 | 2023-01-03 | 0 | 0 | ST202301004045 | 2023-01-03 | 0 | 0 | ST202301004012 | 2023-01-03 | 0 | 0
3029 | KRR117 | KRR117 | Karur |  |  | ROTN | Indus | IN-3161914 | R/NN-697473 |  | SO | 2022-12-28 | KRR117 | 4G_FD900_KRR117 | 4G_FD2100_KRR117 | 4G_TD_KRR117 | G1800+L1800+L2100+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003374 | 2023-01-03 | 0 | 0 | ST202301004046 | 2023-01-03 | 0 | 0 | ST202301004013 | 2023-01-03 | 0 | 0
3030 | ELAPP2 | ELAPP2 | Coimbatore |  |  | ROTN | Indus | IN-3162762 | R/NN-698542 |  | SO | 2022-12-28 | ELAPP2 | 4G_FD900_ELAPP2 | 4G_FD2100_ELAPP2 | 4G_TD_ELAPP2 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003178 | 2023-01-03 | 0 | 0 |  |  | #N/A | #N/A | ST202301004028 | 2023-01-03 | 0 | 0
3031 | KRR116 | KRR116 | Karur |  |  | ROTN | Indus | IN-3162767 | R/NN-698546 |  | SO | 2022-12-28 | KRR116 | 4G_FD900_KRR116 | 4G_FD2100_KRR116 | 4G_TD_KRR116 | G1800+L1800+L2300 | Full Site WPC ID WIP |  |  |  | #N/A | #N/A | ST202301003346 | 2023-01-03 | 0 | 0 |  |  | #N/A | #N/A | ST202301003998 | 2023-01-03 | 0 | 0
3032 | SPAKM8 | SPAKM8 | chennai |  |  | CHN | Ascend | - | - |  | SO | 2022-12-15 | SPAKM8 | 4G_FD900_SPAKM8 | 4G_FD2100_SPAKM8 | 4G_TD_SPAKM8 | G1800+L1800+L2300 | WPC ID Available 2G1800+FD1800+TD |  |  |  | #N/A | #N/A | ST202212854801 | 2022-12-27 | P/FVC/MDS/1120668/2023 | 2023-01-06 |  |  | #N/A | #N/A | ST202212853363 | 2022-12-27 | P/FBW/MDS/1120612/2023 | 2023-01-06
3033 | PATWM6 | PATWM6 |  |  |  | ROTN | Indus | IN-3146221 | R/RES-514540 |  | SO | 2022-12-18 | PATWM6 | 4G_FD900_PATWM6 | 4G_FD2100_PATWM6 | 4G_TD_PATWM6 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD |  |  |  | #N/A | #N/A | ST202212854971 | 2022-12-27 | P/FVC/MDS/1120689/2023 | 2023-01-06 | ST202212857145 | 2022-12-27 | P/FVC/MDS/1120725/2023 | 2023-01-06 | ST202212853576 | 2022-12-27 | P/FBW/MDS/1120633/2023 | 2023-01-06
3034 | TKNPT3 | TKNPT3 |  |  |  | ROTN | Indus | IN-3138300 | R/NN-666815 |  | SO | 2022-12-09 | TKNPT3 | 4G_FD900_TKNPT3 | 4G_FD2100_TKNPT3 | 4G_TD_TKNPT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211761077 | 2022-11-25 | P/FVC/MDS/1116876/2022 | 2022-11-29 | ST202211758311 | 2022-11-23 | P/FVC/MDS/1116807/2022 | 2022-11-29 |  |  |  |  | ST202211758599 | 2022-11-16 | P/FBW/MDS/1116848/2022 | 2022-11-29
3035 | GKMC13 | GKMC13 |  |  |  | CHN | Srigom | SG0023 | - |  | SO | 2022-12-18 | GKMC13 | 4G_FD900_GKMC13 | 4G_FD2100_GKMC13 | 4G_TD_GKMC13 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853185 | 2022-12-27 | P/FVC/MDS/1120594/2023 | 2023-01-06 | ST202212856253 | 2022-12-27 | P/FVC/MDS/1120694/2023 | 2023-01-06 | ST202212857196 | 2022-12-27 | P/FVC/MDS/1120730/2023 | 2023-01-06 | ST202212853633 | 2022-12-27 | P/FBW/MDS/1120638/2023 | 2023-01-06
3036 | CWM224 | CWM224 |  |  |  | CHN | TVI | - | - |  | SO | 2022-12-15 | CWM224 | 4G_FD900_CWM224 | 4G_FD2100_CWM224 | 4G_TD_CWM224 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853095 | 2022-12-27 | P/FVC/MDS/1120586/2023 | 2023-01-06 | ST202212854602 | 2022-12-27 | P/FVC/MDS/1120662/2023 | 2023-01-06 | ST202212857060 | 2022-12-27 | P/FVC/MDS/1120716/2023 | 2023-01-06 | ST202212853320 | 2022-12-27 | P/FBW/MDS/1120606/2023 | 2023-01-06
3037 | VELC26 | VELC26 |  |  |  | CHN | CNIL | CHN/RTT/K/09887 | R/NN-687248 |  | SO | 2022-12-12 | VELC26 | 4G_FD900_VELC26 | 4G_FD2100_VELC26 | 4G_TD_VELC26 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212798338 | 2022-12-10 | P/FVC/MDS/1118908/2022 | 2022-12-16 | ST202212798341 | 2022-12-10 | P/FVC/MDS/1118916/2022 | 2022-12-16 | ST202212798347 | 2022-12-10 | P/FVC/MDS/1118938/2022 | 2022-12-16 | ST202212798349 | 2022-12-10 | P/FBW/MDS/1118944/2022 | 2022-12-16
3038 | NGL145 | NGL145 |  |  |  | ROTN | Indus | IN-3147857 | R/NN-670873 |  | SO | 2022-12-18 | NGL145 | 4G_FD900_NGL145 | 4G_FD2100_NGL145 | 4G_TD_NGL145 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853144 | 2022-12-27 | P/FVC/MDS/1120591/2023 | 2023-01-06 | ST202212854973 | 2022-12-27 | P/FVC/MDS/1120691/2023 | 2023-01-06 | ST202212857172 | 2022-12-27 | P/FVC/MDS/1120727/2023 | 2023-01-06 | ST202212853604 | 2022-12-27 | P/FBW/MDS/1120635/2023 | 2023-01-06
3039 | AYAN34 | AYAN34 |  |  |  | CHN | TVI | - | - |  | SO | 2022-12-15 | AYAN34 | 4G_FD900_AYAN34 | 4G_FD2100_AYAN34 | 4G_TD_AYAN34 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853025 | 2022-12-27 | P/FVC/MDS/1120577/2023 | 2023-01-06 | ST202212854532 | 2022-12-27 | P/FVC/MDS/1120653/2023 | 2023-01-06 | ST202212857009 | 2022-12-27 | P/FVC/MDS/1120710/2023 | 2023-01-06 | ST202212853259 | 2022-12-27 | P/FBW/MDS/1120597/2023 | 2023-01-06
3040 | MMIN18 | MMIN18 |  |  |  | CHN | TVI | - | - |  | SO | 2022-12-15 | MMIN18 | 4G_FD900_MMIN18 | 4G_FD2100_MMIN18 | 4G_TD_MMIN18 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853094 | 2022-12-27 | P/FVC/MDS/1120585/2023 | 2023-01-06 | ST202212854601 | 2022-12-27 | P/FVC/MDS/1120661/2023 | 2023-01-06 | ST202212857059 | 2022-12-27 | P/FVC/MDS/1120715/2023 | 2023-01-06 | ST202212853318 | 2022-12-27 | P/FBW/MDS/1120605/2023 | 2023-01-06
3041 | KRBLM2 | KRBLM2 |  |  |  | ROTN | Summit | I-TN-PLLC-ENB-9115 | SR-TN001205 |  | SO | 2022-12-09 | KRBLM2 | 4G_FD900_KRBLM2 | 4G_FD2100_KRBLM2 | 4G_TD_KRBLM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812052 | 2022-12-15 | P/FVC/MDS/1119394/2022 | 2022-12-20 | ST202212810969 | 2022-12-14 | P/FVC/MDS/1119157/2022 | 2022-12-20 | ST202212811908 | 2022-12-14 | P/FVC/MDS/1119353/2022 | 2022-12-20 | ST202212811031 | 2022-12-14 | P/FBW/MDS/1119255/2022 | 2022-12-20
3042 | KARUM2 | KARUM2 |  |  |  | ROTN | ATC | TN/TR/AT/23396 | T22TN05711 |  | SO | 2022-12-09 | KARUM2 | 4G_FD900_KARUM2 | 4G_FD2100_KARUM2 | 4G_TD_KARUM2 | L900+L1800+L2100+TD | Partial Tech Application WIP | 2100 sacfa | ST202211681107 | 2022-11-04 | P/FVC/MDS/1114831/2022 | 2022-11-22 | ST202211685915 | 2022-11-07 | P/FVC/MDS/1114673/2022 | 2022-11-15 |  |  | #N/A | #N/A | ST202211685574 | 2022-11-07 | P/FBW/MDS/1114752/2022 | 2022-11-16
3043 | POOKI2 | POOKI2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-15 | POOKI2 | 4G_FD900_POOKI2 | 4G_FD2100_POOKI2 | 4G_TD_POOKI2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681062 | 2022-11-04 | P/FVC/MDS/1114818/2022 | 2022-11-22 | ST202211685884 | 2022-11-07 | P/FVC/MDS/1114660/2022 | 2022-11-15 | ST202211684521 | 2022-11-05 | P/FVC/MDS/1114596/2022 | 2022-11-15 | ST202211685528 | 2022-11-07 | P/FBW/MDS/1114740/2022 | 2022-11-16
3044 | DVPYM2 | DVPYM2 |  |  |  | ROTN | Indus | IN-3149466 | R/NN-682229 |  | SO | 2022-12-09 | DVPYM2 | 4G_FD900_DVPYM2 | 4G_FD2100_DVPYM2 | 4G_TD_DVPYM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812042 | 2022-12-15 | P/FVC/MDS/1119390/2022 | 2022-12-20 | ST202212810933 | 2022-12-14 | P/FVC/MDS/1119153/2022 | 2022-12-20 | ST202212811889 | 2022-12-14 | P/FVC/MDS/1119349/2022 | 2022-12-20 | ST202212810973 | 2022-12-14 | P/FBW/MDS/1119251/2022 | 2022-12-20
3045 | VILND2 | VILND2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-15 | VILND2 | 4G_FD900_VILND2 | 4G_FD2100_VILND2 | 4G_TD_VILND2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853046 | 2022-12-27 | P/FVC/MDS/1120579/2023 | 2023-01-06 | ST202212854555 | 2022-12-27 | P/FVC/MDS/1120655/2023 | 2023-01-06 | ST202212857037 | 2022-12-27 | P/FVC/MDS/1120712/2023 | 2023-01-06 | ST202212853276 | 2022-12-27 | 0
3046 | PATHR2 | PATHR2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | PATHR2 | 4G_FD900_PATHR2 | 4G_FD2100_PATHR2 | 4G_TD_PATHR2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202211681063 | 2022-11-04 | P/FVC/MDS/1114819/2022 | 2022-11-22 | ST202211685885 | 2022-11-07 | P/FVC/MDS/1114661/2022 | 2022-11-15 | ST202211684522 | 2022-11-05 | P/FVC/MDS/1114597/2022 | 2022-11-15
3047 | SHSUM2 | SHSUM2 |  |  |  | ROTN | Summit | I-TN-BDKK-ENB-9012 | SR-TN001109 |  | SO | 2022-12-09 | SHSUM2 | 4G_FD900_SHSUM2 | 4G_FD2100_SHSUM2 | 4G_TD_SHSUM2 | L900+L1800+L2100+TD | Partial Tech Application WIP | 2100 sacfa | ST202212812029 | 2022-12-15 | P/FVC/MDS/1119381/2022 | 2022-12-20 | ST202212809803 | 2022-12-14 | P/FVC/MDS/1119144/2022 | 2022-12-20 |  |  | #N/A | #N/A | ST202212809770 | 2022-12-14 | P/FBW/MDS/1119244/2022 | 2022-12-20
3048 | VRPNT3 | VRPNT3 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-15 | VRPNT3 | 4G_FD900_VRPNT3 | 4G_FD2100_VRPNT3 | 4G_TD_VRPNT3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681068 | 2022-11-04 | P/FVC/MDS/1114820/2022 | 2022-11-22 | ST202211685887 | 2022-11-07 | P/FVC/MDS/1114662/2022 | 2022-11-15 |  |  |  |  | ST202211685533 | 2022-11-07 | P/FBW/MDS/1114741/2022 | 2022-11-16
3049 | ARSMP2 | ARSMP2 |  |  |  | ROTN | Indus | IN-3149647 | R/NN-682420 |  | SO | 2022-12-09 | ARSMP2 | 4G_FD900_ARSMP2 | 4G_FD2100_ARSMP2 | 4G_TD_ARSMP2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202211678903 | 2022-11-02 | P/FVC/MDS/1114776/2022 | 2022-11-22 | ST202211685755 | 2022-11-07 | P/FVC/MDS/1114617/2022 | 2022-11-15 | ST202211681209 | 2022-11-04 | P/FVC/MDS/1114566/2022 | 2022-11-15
3050 | KTNUR2 | KTNUR2 |  |  |  | ROTN | Indus | IN-3149488 | R/NN-682259 |  | SO | 2022-12-09 | KTNUR2 | 4G_FD900_KTNUR2 | 4G_FD2100_KTNUR2 | 4G_TD_KTNUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211678902 | 2022-11-02 | P/FVC/MDS/1114775/2022 | 2022-11-22 | ST202211685748 | 2022-11-07 | P/FVC/MDS/1114616/2022 | 2022-11-15 | ST202211681208 | 2022-11-04 | P/FVC/MDS/1114565/2022 | 2022-11-15 | ST202211685304 | 2022-11-07 | P/FBW/MDS/1114698/2022 | 2022-11-16
3051 | MUGTU2 | MUGTU2 |  |  |  | ROTN | Indus | IN-3153004 | R/NN-686230 |  | SO | 2022-12-09 | MUGTU2 | 4G_FD900_MUGTU2 | 4G_FD2100_MUGTU2 | 4G_TD_MUGTU2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202212812039 | 2022-12-15 | P/FVC/MDS/1119389/2022 | 2022-12-20 | ST202212810932 | 2022-12-14 | P/FVC/MDS/1119152/2022 | 2022-12-20 | ST202212811888 | 2022-12-14 | P/FVC/MDS/1119348/2022 | 2022-12-20
3052 | EMPKE2 | EMPKE2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-18 | EMPKE2 | 4G_FD900_EMPKE2 | 4G_FD2100_EMPKE2 | 4G_TD_EMPKE2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853145 | 2022-12-27 | P/FVC/MDS/1120592/2023 | 2023-01-06 | ST202212856251 | 2022-12-27 | P/FVC/MDS/1120692/2023 | 2023-01-06 | ST202212857173 | 2022-12-27 | P/FVC/MDS/1120728/2023 | 2023-01-06 | ST202212853605 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3053 | ERISN2 | ERISN2 |  |  |  | ROTN | Indus | IN-3149493 | R/NN-682262 |  | SO | 2022-12-09 | ERISN2 | 4G_FD900_ERISN2 | 4G_FD2100_ERISN2 | 4G_TD_ERISN2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211680684 | 2022-11-04 | P/FVC/MDS/1114780/2022 | 2022-11-22 | ST202211685761 | 2022-11-07 | P/FVC/MDS/1114621/2022 | 2022-11-15 | ST202211681216 | 2022-11-04 | P/FVC/MDS/1114567/2022 | 2022-11-15 | ST202211685599 | 2022-11-07 | P/FBW/MDS/1114764/2022 | 2022-11-16
3054 | TNTHR2 | TNTHR2 |  |  |  | ROTN | Indus | IN-3149611 | R/NN-682358 |  | SO | 2022-12-09 | TNTHR2 | 4G_FD900_TNTHR2 | 4G_FD2100_TNTHR2 | 4G_TD_TNTHR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812035 | 2022-12-15 | P/FVC/MDS/1119385/2022 | 2022-12-20 | ST202212809838 | 2022-12-14 | P/FVC/MDS/1119148/2022 | 2022-12-20 | ST202212811878 | 2022-12-14 | P/FVC/MDS/1119344/2022 | 2022-12-20 | ST202212809797 | 2022-12-14 | P/FBW/MDS/1119247/2022 | 2022-12-20
3055 | PETHI3 | PETHI3 |  |  |  | ROTN | Summit | I-TN-CMBR-ENB-9094 | SR-TN001206 |  | SO | 2022-12-09 | PETHI3 | 4G_FD900_PETHI3 | 4G_FD2100_PETHI3 | 4G_TD_PETHI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212812053 | 2022-12-15 | P/FVC/MDS/1119395/2022 | 2022-12-20 | ST202212810970 | 2022-12-14 | P/FVC/MDS/1119158/2022 | 2022-12-20 |  |  |  |  | ST202212811032 | 2022-12-14 | P/FBW/MDS/1119256/2022 | 2022-12-20
3056 | KMPTU2 | KMPTU2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | KMPTU2 | 4G_FD900_KMPTU2 | 4G_FD2100_KMPTU2 | 4G_TD_KMPTU2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681069 | 2022-11-04 | P/FVC/MDS/1114821/2022 | 2022-11-22 | ST202211685888 | 2022-11-07 | P/FVC/MDS/1114663/2022 | 2022-11-15 | ST202211684528 | 2022-11-05 | P/FVC/MDS/1114598/2022 | 2022-11-15 | ST202211685534 | 2022-11-07 | P/FBW/MDS/1114742/2022 | 2022-11-16
3057 | TTMDM2 | TTMDM2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-15 | TTMDM2 | 4G_FD900_TTMDM2 | 4G_FD2100_TTMDM2 | 4G_TD_TTMDM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681070 | 2022-11-04 | P/FVC/MDS/1114822/2022 | 2022-11-22 | ST202211685889 | 2022-11-07 | P/FVC/MDS/1114664/2022 | 2022-11-15 | ST202211684529 | 2022-11-05 | P/FVC/MDS/1114599/2022 | 2022-11-15 | ST202211685535 | 2022-11-07 | P/FBW/MDS/1114743/2022 | 2022-11-16
3058 | VYLAR2 | VYLAR2 |  |  |  | ROTN | Indus | IN-3149544 | R/NN-682302 |  | SO | 2022-12-09 | VYLAR2 | 4G_FD900_VYLAR2 | 4G_FD2100_VYLAR2 | 4G_TD_VYLAR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812043 | 2022-12-15 | P/FVC/MDS/1119391/2022 | 2022-12-20 | ST202212810951 | 2022-12-14 | P/FVC/MDS/1119154/2022 | 2022-12-20 | ST202212811890 | 2022-12-14 | P/FVC/MDS/1119350/2022 | 2022-12-20 | ST202212810974 | 2022-12-14 | P/FBW/MDS/1119252/2022 | 2022-12-20
3059 | ZMTUR2 | ZMTUR2 |  |  |  | ROTN | Indus | IN-3152758 | R/NN-685789 |  | SO | 2022-12-09 | ZMTUR2 | 4G_FD900_ZMTUR2 | 4G_FD2100_ZMTUR2 | 4G_TD_ZMTUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812031 | 2022-12-15 | P/FVC/MDS/1119383/2022 | 2022-12-20 | ST202212809805 | 2022-12-14 | P/FVC/MDS/1119146/2022 | 2022-12-20 | ST202212811744 | 2022-12-14 | P/FVC/MDS/1119342/2022 | 2022-12-20 | ST202212809796 | 2022-12-14 | P/FBW/MDS/1119246/2022 | 2022-12-20
3060 | MAVAD2 | MAVAD2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | MAVAD2 | 4G_FD900_MAVAD2 | 4G_FD2100_MAVAD2 | 4G_TD_MAVAD2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211681095 | 2022-11-04 | P/FVC/MDS/1114828/2022 | 2022-11-22 | ST202211685908 | 2022-11-07 | P/FVC/MDS/1114670/2022 | 2022-11-15 | ST202211684530 | 2022-11-05 | P/FVC/MDS/1114600/2022 | 2022-11-15 | ST202211685567 | 2022-11-07 | P/FBW/MDS/1114749/2022 | 2022-11-16
3061 | METLA2 | METLA2 |  |  |  | ROTN | ATC | TN/NM/AT/23443 | T22TN05758 |  | SO | 2022-12-15 | METLA2 | 4G_FD900_METLA2 | 4G_FD2100_METLA2 | 4G_TD_METLA2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202211680999 | 2022-11-04 | P/FVC/MDS/1114791/2022 | 2022-11-22 | ST202211685803 | 2022-11-07 | P/FVC/MDS/1114633/2022 | 2022-11-15 | ST202211681218 | 2022-11-04 | P/FVC/MDS/1114569/2022 | 2022-11-15 | ST202211685340 | 2022-11-07 | P/FBW/MDS/1114713/2022 | 2022-11-16
3062 | RMSM14 | RMSM14 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-15 | RMSM14 | 4G_FD900_RMSM14 | 4G_FD2100_RMSM14 | 4G_TD_RMSM14 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853048 | 2022-12-27 | P/FVC/MDS/1120581/2023 | 2023-01-06 | ST202212854557 | 2022-12-27 | P/FVC/MDS/1120657/2023 | 2023-01-06 | ST202212857038 | 2022-12-27 | P/FVC/MDS/1120713/2023 | 2023-01-06 | ST202212853279 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3063 | POMLR2 | POMLR2 |  |  |  | ROTN | Indus | IN-3149561 | R/NN-682343 |  | SO | 2022-12-09 | POMLR2 | 4G_FD900_POMLR2 | 4G_FD2100_POMLR2 | 4G_TD_POMLR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812030 | 2022-12-15 | P/FVC/MDS/1119382/2022 | 2022-12-20 | ST202212809804 | 2022-12-14 | P/FVC/MDS/1119145/2022 | 2022-12-20 | ST202212811737 | 2022-12-14 | P/FVC/MDS/1119341/2022 | 2022-12-20 | ST202212809771 | 2022-12-14 | P/FBW/MDS/1119245/2022 | 2022-12-20
3064 | NMBNP2 | NMBNP2 |  |  |  | ROTN | ATC | TN/PU/AT/23448 | T22TN05763 |  | SO | 2022-12-15 | NMBNP2 | 4G_FD900_NMBNP2 | 4G_FD2100_NMBNP2 | 4G_TD_NMBNP2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212853070 | 2022-12-27 | P/FVC/MDS/1120584/2023 | 2023-01-06 | ST202212854600 | 2022-12-27 | P/FVC/MDS/1120660/2023 | 2023-01-06 |  |  | #N/A | #N/A | ST202212853301 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3065 | NDMZR6 | NDMZR6 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | NDMZR6 | 4G_FD900_NDMZR6 | 4G_FD2100_NDMZR6 | 4G_TD_NDMZR6 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812037 | 2022-12-15 | P/FVC/MDS/1119387/2022 | 2022-12-20 | ST202212809839 | 2022-12-14 | P/FVC/MDS/1119149/2022 | 2022-12-20 | ST202212811881 | 2022-12-14 | P/FVC/MDS/1119346/2022 | 2022-12-20 | ST202212809824 | 2022-12-14 | P/FBW/MDS/1119248/2022 | 2022-12-20
3066 | ECHOR4 | ECHOR4 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-15 | ECHOR4 | 4G_FD900_ECHOR4 | 4G_FD2100_ECHOR4 | 4G_TD_ECHOR4 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853026 | 2022-12-27 | P/FVC/MDS/1120578/2023 | 2023-01-06 | ST202212854533 | 2022-12-27 | P/FVC/MDS/1120654/2023 | 2023-01-06 | ST202212857010 | 2022-12-27 | P/FVC/MDS/1120711/2023 | 2023-01-06 | ST202212853260 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3067 | KMPM10 | KMPM10 |  |  |  | ROTN | ATC | TN/NM/AT/23456 | T22TN05771 |  | SO | 2022-12-15 | KMPM10 | 4G_FD900_KMPM10 | 4G_FD2100_KMPM10 | 4G_TD_KMPM10 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853024 | 2022-12-27 | P/FVC/MDS/1120576/2023 | 2023-01-06 | ST202212854531 | 2022-12-27 | P/FVC/MDS/1120652/2023 | 2023-01-06 | ST202212857008 | 2022-12-27 | P/FVC/MDS/1120709/2023 | 2023-01-06 | ST202212853258 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3068 | KSLPT2 | KSLPT2 |  |  |  | ROTN | ATC | TN/SI/AT/23459 | T22TN05774 |  | SO | 2022-12-15 | KSLPT2 | 4G_FD900_KSLPT2 | 4G_FD2100_KSLPT2 | 4G_TD_KSLPT2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853068 | 2022-12-27 | P/FVC/MDS/1120582/2023 | 2023-01-06 | ST202212854583 | 2022-12-27 | P/FVC/MDS/1120658/2023 | 2023-01-06 | ST202212857039 | 2022-12-27 | P/FVC/MDS/1120714/2023 | 2023-01-06 | ST202212853299 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3069 | GNPLM2 | GNPLM2 |  |  |  | ROTN | Indus | IN-3149867 | R/NN-682637 |  | SO | 2022-12-09 | GNPLM2 | 4G_FD900_GNPLM2 | 4G_FD2100_GNPLM2 | 4G_TD_GNPLM2 | G1800+L1800+L2100+L900 | WPC ID Available 2G900+FD1800+FD2100 |  | ST202212812034 | 2022-12-15 | P/FVC/MDS/1119384/2022 | 2022-12-20 | ST202212809837 | 2022-12-14 | P/FVC/MDS/1119147/2022 | 2022-12-20 | ST202212811745 | 2022-12-14 | P/FVC/MDS/1119343/2022 | 2022-12-20
3070 | KRTHI3 | KRTHI3 |  |  |  | ROTN | ATC | TN/CO/AT/23470 | T22TN05785 |  | SO | 2022-12-15 | KRTHI3 | 4G_FD900_KRTHI3 | 4G_FD2100_KRTHI3 | 4G_TD_KRTHI3 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681125 | 2022-11-04 | P/FVC/MDS/1114838/2022 | 2022-11-22 | ST202211685936 | 2022-11-07 | P/FVC/MDS/1114680/2022 | 2022-11-15 |  |  |  |  | ST202211685587 | 2022-11-07 | P/FBW/MDS/1114759/2022 | 2022-11-16
3071 | PONPM2 | PONPM2 |  |  |  | ROTN | Indus | IN-3149792 | R/NN-682542 |  | SO | 2022-12-09 | PONPM2 | 4G_FD900_PONPM2 | 4G_FD2100_PONPM2 | 4G_TD_PONPM2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812044 | 2022-12-15 | P/FVC/MDS/1119392/2022 | 2022-12-20 | ST202212810952 | 2022-12-14 | P/FVC/MDS/1119155/2022 | 2022-12-20 | ST202212811905 | 2022-12-14 | P/FVC/MDS/1119351/2022 | 2022-12-20 | ST202212811004 | 2022-12-14 | P/FBW/MDS/1119253/2022 | 2022-12-20
3072 | KTTUR2 | KTTUR2 |  |  |  | ROTN | Indus | IN-3149793 | R/NN-682543 |  | SO | 2022-12-09 | KTTUR2 | 4G_FD900_KTTUR2 | 4G_FD2100_KTTUR2 | 4G_TD_KTTUR2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812051 | 2022-12-15 | P/FVC/MDS/1119393/2022 | 2022-12-20 | ST202212810968 | 2022-12-14 | P/FVC/MDS/1119156/2022 | 2022-12-20 | ST202212811906 | 2022-12-14 | P/FVC/MDS/1119352/2022 | 2022-12-20 | ST202212811005 | 2022-12-14 | P/FBW/MDS/1119254/2022 | 2022-12-20
3073 | ANPNI2 | ANPNI2 |  |  |  | ROTN | ATC | TN/NM/AT/23475 | T22TN05790 |  | SO | 2022-12-15 | ANPNI2 | 4G_FD900_ANPNI2 | 4G_FD2100_ANPNI2 | 4G_TD_ANPNI2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212853069 | 2022-12-27 | P/FVC/MDS/1120583/2023 | 2023-01-06 | ST202212854584 | 2022-12-27 | P/FVC/MDS/1120659/2023 | 2023-01-06 |  |  | #N/A | #N/A | ST202212853300 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3074 | AGNML2 | AGNML2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-15 | AGNML2 | 4G_FD900_AGNML2 | 4G_FD2100_AGNML2 | 4G_TD_AGNML2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202212853047 | 2022-12-27 | P/FVC/MDS/1120580/2023 | 2023-01-06 | ST202212854556 | 2022-12-27 | P/FVC/MDS/1120656/2023 | 2023-01-06 |  |  | #N/A | #N/A | ST202212853278 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3075 | ERLMP2 | ERLMP2 |  |  |  | ROTN | ATC | TN/VLP/AT/23476 | T22TN05791 |  | SO | 2022-12-09 | ERLMP2 | 4G_FD900_ERLMP2 | 4G_FD2100_ERLMP2 | 4G_TD_ERLMP2 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212812038 | 2022-12-15 | P/FVC/MDS/1119388/2022 | 2022-12-20 | ST202212810920 | 2022-12-14 | P/FVC/MDS/1119150/2022 | 2022-12-20 | ST202212811882 | 2022-12-14 | P/FVC/MDS/1119347/2022 | 2022-12-20 | ST202212810945 | 2022-12-14 | P/FBW/MDS/1119249/2022 | 2022-12-20
3076 | RJPTM2 | RJPTM2 |  |  |  | ROTN | Ascend | - | - |  | SO | 2022-12-09 | RJPTM2 | 4G_FD900_RJPTM2 | 4G_FD2100_RJPTM2 | 4G_TD_RJPTM2 | G1800+L1800+L2300+L900 | WPC ID Available 2G1800+FD1800+TD+L900 |  | ST202211681078 | 2022-11-04 | P/FVC/MDS/1114823/2022 | 2022-11-22 | ST202211685890 | 2022-11-07 | P/FVC/MDS/1114665/2022 | 2022-11-15 |  |  |  |  | ST202211685559 | 2022-11-07 | P/FBW/MDS/1114744/2022 | 2022-11-16
3077 | KOLA55 | KOLA55 |  |  |  | CHN | Indus | IN-3151957 | R/NN-684718 |  | SO | 2022-12-18 | KOLA55 | 4G_FD900_KOLA55 | 4G_FD2100_KOLA55 | 4G_TD_KOLA55 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853143 | 2022-12-27 | P/FVC/MDS/1120590/2023 | 2023-01-06 | ST202212854972 | 2022-12-27 | P/FVC/MDS/1120690/2023 | 2023-01-06 | ST202212857146 | 2022-12-27 | P/FVC/MDS/1120726/2023 | 2023-01-06 | ST202212853602 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3078 | MDU558 | MDU558 |  |  |  | ROTN | Indus | IN-3153667 | R/NN-686882 |  | SO | 2022-12-18 | MDU558 | 4G_FD900_MDU558 | 4G_FD2100_MDU558 | 4G_TD_MDU558 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853184 | 2022-12-27 | P/FVC/MDS/1120593/2023 | 2023-01-06 | ST202212856252 | 2022-12-27 | P/FVC/MDS/1120693/2023 | 2023-01-06 | ST202212857195 | 2022-12-27 | P/FVC/MDS/1120729/2023 | 2023-01-06 | ST202212853632 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3079 | MDU561 | MDU561 |  |  |  | ROTN | Indus | IN-3154534 | R/NN-687789 |  | SO | 2022-12-15 | MDU561 | 4G_FD900_MDU561 | 4G_FD2100_MDU561 | 4G_TD_MDU561 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853096 | 2022-12-27 | P/FVC/MDS/1120587/2023 | 2023-01-06 | ST202212854659 | 2022-12-27 | P/FVC/MDS/1120663/2023 | 2023-01-06 | ST202212857072 | 2022-12-27 | P/FVC/MDS/1120717/2023 | 2023-01-06 | ST202212853321 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3080 | GERU42 | GERU42 |  |  |  | CHN | Indus | IN-3161316 | R/NN-696676 |  | SO | 2022-12-18 | GERU42 | 4G_FD900_GERU42 | 4G_FD2100_GERU42 | 4G_TD_GERU42 | L900+L1800+L2100+TD | WPC ID Available 2G900+FD1800+FD2100+TD |  | ST202212853121 | 2022-12-27 | P/FVC/MDS/1120589/2023 | 2023-01-06 | ST202212854950 | 2022-12-27 | P/FVC/MDS/1120688/2023 | 2023-01-06 | ST202212857144 | 2022-12-27 | P/FVC/MDS/1120724/2023 | 2023-01-06 | ST202212853574 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3081 | KPLYM2 | KPLYM2 |  |  |  | ROTN | Indus | IN-3155417 | R/NN-688798 |  | SO | 2022-12-15 | KPLYM2 | 4G_FD900_KPLYM2 | 4G_FD2100_KPLYM2 | 4G_TD_KPLYM2 | G1800+L1800+L2100+L2300 | WPC ID Available 2G1800+FD1800+FD2100+TD | [5 empty] | ST202212854662 | 2022-12-27 | P/FVC/MDS/1120664/2023 | 2023-01-06 | ST202212857073 | 2022-12-27 | P/FVC/MDS/1120718/2023 | 2023-01-06 | ST202212853341 | 2022-12-27 | P/FBW/MDS/1114752/2022 | 2022-11-16
3082 | ITC003 | ITC2 |  |  | Relocation | CH | [13 empty] | ST202203061402 | 2022-03-03 | P/FVC/MDS/1076622/2022 | 2022-03-13 | ST202203061569 | 2022-03-03 | P/FVC/MDS/1076574/2022 | 2022-03-13 | ST202203062902 | 2022-03-04 | P/FVC/MDS/1076636/2022 | 2022-03-13 | ST202203062290 | 2022-03-04 | P/FBW/MDS/1076518/2022 | 2022-03-13
3083 | AYAN31 | AYANAV |  |  | Relocation | CH | [13 empty] | ST202203061398 | 2022-03-03 | P/FVC/MDS/1076620/2022 | 2022-03-13 | ST202203061566 | 2022-03-03 | P/FVC/MDS/1076572/2022 | 2022-03-13 | ST202203062894 | 2022-03-04 | P/FVC/MDS/1076634/2022 | 2022-03-13 | ST202203061639 | 2022-03-03 | P/FBW/MDS/1076516/2022 | 2022-03-13
3084 | VADA12 | VADAP5 |  |  | Relocation | CH | [13 empty] | ST202202029967 | 2022-02-04 | P/FVC/MDS/1074510/2022 | 2022-02-22 | ST202202029931 | 2022-02-04 | P/FVC/MDS/1074450/2022 | 2022-02-22 | ST202202040258 | 2022-02-09 | P/FVC/MDS/1074524/2022 | 2022-02-22 | ST202202039106 | 2022-02-08 | P/FBW/MDS/1074390/2022 | 2022-02-22
3085 | PAMLP2 | PAMLPO |  |  | Relocation | CH | [13 empty] | ST202202027997 | 2022-02-02 | P/FVC/MDS/1074481/2022 | 2022-02-22 | ST202202029882 | 2022-02-04 | P/FVC/MDS/1074424/2022 | 2022-02-22 | ST202202040226 | 2022-02-09 | P/FVC/MDS/1074517/2022 | 2022-02-22 | ST202202039048 | 2022-02-08 | P/FBW/MDS/1074364/2022 | 2022-02-22
3086 | TIRU43 | TIRU31 |  |  | Relocation | CH | [13 empty] | ST202201022593 | 2022-01-28 | P/FVC/MDS/1072949/2022 | 2022-02-04 | ST202201022764 | 2022-01-28 | P/FVC/MDS/1072982/2022 | 2022-02-04 |  |  |  |  | ST202201022873 | 2022-01-28 | P/FBW/MDS/1073009/2022 | 2022-02-04
3087 | RICHI8 | RICHIE |  |  | Relocation | CH | [13 empty] | ST202203085611 | 2022-03-29 | P/FVC/MDS/1078067/2022 | 2022-04-14 | ST202203084669 | 2022-03-29 | P/FVC/MDS/1077968/2022 | 2022-04-14 | ST202203086212 | 2022-03-30 | P/FVC/MDS/1078212/2022 | 2022-04-15 | ST202203082646 | 2022-03-26 | P/FBW/MDS/1077806/2022 | 2022-04-14
3088 | VELMA6 | VELMA2 |  |  | Relocation | CH | [13 empty] | ST202204111691 | 2022-04-20 | P/FVC/MDS/1078937/2022 | 2022-05-02 | ST202204110022 | 2022-04-19 | P/FVC/MDS/1078999/2022 | 2022-05-03 | ST202204111905 | 2022-04-20 | P/FVC/MDS/1079021/2022 | 2022-05-03 | ST202204109585 | 2022-04-19 | P/FVC/MDS/1078895/2022 | 2022-05-02
3089 | KODU36 | KODUN3 |  |  | Relocation | CH | [13 empty] | ST202203061403 | 2022-03-03 | P/FVC/MDS/1076623/2022 | 2022-03-13 | ST202203061570 | 2022-03-03 | P/FVC/MDS/1076575/2022 | 2022-03-13 | ST202203062903 | 2022-03-04 | P/FVC/MDS/1076637/2022 | 2022-03-13 | ST202203062291 | 2022-03-04 | P/FBW/MDS/1076519/2022 | 2022-03-13
3090 | CWM225 | CWM109 |  |  | Relocation | CH | [13 empty] | ST202206165550 | 2022-06-07 | P/FVC/MDS/1082460/2022 | 2022-06-14 | ST202206165163 | 2022-06-07 | P/FVC/MDS/1082412/2022 | 2022-06-14 | ST202206165648 | 2022-06-07 | P/FVC/MDS/1082496/2022 | 2022-06-14 | ST202206164316 | 2022-06-07 | P/FBW/MDS/1082361/2022 | 2022-06-14
3091 | CBE901 | CBE159 |  |  | Relocation | TN | [13 empty] | ST202202052198 | 2022-02-22 | P/FVC/MDS/1076288/2022 | 2022-03-13 | ST202202054420 | 2022-02-24 | P/FVC/MDS/1076183/2022 | 2022-03-13 | ST202202049485 | 2022-02-19 | P/FVC/MDS/1074802/2022 | 2022-02-25 | ST202202053465 | 2022-02-23 | P/FBW/MDS/1076084/2022 | 2022-03-13
3092 | VKLM03 | VKLM1 |  |  | Relocation | TN | [13 empty] | ST202201022568 | 2022-01-28 | P/FVC/MDS/1072939/2022 | 2022-02-04 | ST202201022725 | 2022-01-28 | P/FVC/MDS/1072972/2022 | 2022-02-04 | ST202201022905 | 2022-01-28 | P/FVC/MDS/1073021/2022 | 2022-02-04 | ST202201022852 | 2022-01-28 | P/FBW/MDS/1072999/2022 | 2022-02-04
3093 | TUT121 | TUT11 |  |  | Relocation | TN | [13 empty] | ST202108405006 | 2021-08-02 | P/FVC/MDS/1052825/2021 | 2021-08-20 | ST202104125404 | 2021-04-05 | P/FVC/MDS/1017794/2021 | 2021-05-15 | ST202104126273 | 2021-04-06 | P/FVC/MDS/1017833/2021 | 2021-05-15 | ST202104119374 | 2021-04-03 | P/FBW/MDS/1020235/2021 | 2021-05-23
3094 | PDMUP2 | PDMUP1 |  |  | Relocation | TN | [13 empty] | ST202202029939 | 2022-02-04 | P/FVC/MDS/1074500/2022 | 2022-02-22 | ST202202029919 | 2022-02-04 | P/FVC/MDS/1074445/2022 | 2022-02-22 | ST202202040256 | 2022-02-09 | P/FVC/MDS/1074522/2022 | 2022-02-22 | ST202202039077 | 2022-02-08 | P/FBW/MDS/1074383/2022 | 2022-02-22
3095 | UAUNM2 | UAUNM1 |  |  | Relocation | TN | [13 empty] | ST202202048182 | 2022-02-18 | P/FVC/MDS/1074996/2022 | 2022-02-28 | ST202202049426 | 2022-02-19 | P/FVC/MDS/1074941/2022 | 2022-02-28 | ST202202040271 | 2022-02-09 | P/FVC/MDS/1074526/2022 | 2022-02-22 | ST202202048672 | 2022-02-18 | P/FBW/MDS/1074882/2022 | 2022-02-28
3096 | MTHKL5 | MTHKL1 |  |  | Relocation | TN | [13 empty] | ST202202052225 | 2022-02-22 | P/FVC/MDS/1076300/2022 | 2022-03-13 | ST202202054454 | 2022-02-24 | P/FVC/MDS/1076194/2022 | 2022-03-13 | ST202202040293 | 2022-02-09 | P/FVC/MDS/1074529/2022 | 2022-02-22 | ST202202053476 | 2022-02-23 | P/FBW/MDS/1076094/2022 | 2022-03-13
3097 | DGL110 | DGL13 |  |  | Relocation | TN | [13 empty] | ST202112623318 | 2021-12-21 | P/FVC/MDS/1070045/2021 | 2021-12-29 | ST202112625887 | 2021-12-23 | P/FVC/MDS/1069719/2021 | 2021-12-28 | ST202201003480 | 2022-01-06 | P/FVC/MDS/1071115/2022 | 2022-01-10 | ST202112616590 | 2021-12-15 | P/FBW/MDS/1069564/2021 | 2021-12-22
3098 | VLR235 | VLR52 |  |  | Relocation | TN | [13 empty] | ST202202053445 | 2022-02-23 | P/FVC/MDS/1076405/2022 | 2022-03-13 | ST202204097848 | 2022-04-11 | P/FVC/MDS/1078354/2022 | 2022-04-21 | ST202202056744 | 2022-02-27 | P/FVC/MDS/1075697/2022 | 2022-03-10 | ST202202055940 | 2022-02-26 | P/FBW/MDS/1075525/2022 | 2022-03-10
3099 | PNPT15 | PNPT3 |  |  | Relocation | TN | [13 empty] | ST202201022594 | 2022-01-28 | P/FVC/MDS/1072950/2022 | 2022-02-04 | ST202201022772 | 2022-01-28 | P/FVC/MDS/1072983/2022 | 2022-02-04 | ST202201022914 | 2022-01-28 | P/FVC/MDS/1073029/2022 | 2022-02-04 | ST202201022874 | 2022-01-28 | P/FBW/MDS/1073010/2022 | 2022-02-04
3100 | PCHYR2 | PCHYR1 |  |  | Relocation | TN | [13 empty] | ST202203086039 | 2022-03-30 | P/FVC/MDS/1078177/2022 | 2022-04-15 | ST202203084967 | 2022-03-29 | P/FVC/MDS/1078131/2022 | 2022-04-15 | ST202204095033 | 2022-04-08 | P/FVC/MDS/1078396/2022 | 2022-04-21 | ST202203083991 | 2022-03-28 | P/FBW/MDS/1077888/2022 | 2022-04-14
3101 | COWKVP | KSVMP1 |  |  | Relocation | TN | [13 empty] | ST202203085649 | 2022-03-29 | P/FVC/MDS/1078076/2022 | 2022-04-14 | ST202203084683 | 2022-03-29 | P/FVC/MDS/1077977/2022 | 2022-04-14 | ST202204111904 | 2022-04-20 | P/FVC/MDS/1079020/2022 | 2022-05-03 | ST202203082664 | 2022-03-26 | P/FBW/MDS/1077818/2022 | 2022-04-14
3102 | MTRM05 | MTRM3 |  |  | Relocation | TN | [13 empty] | ST202110573618 | 2021-10-27 | P/FVC/MDS/1065759/2021 | 2021-11-16 | ST202110574128 | 2021-10-28 | P/FVC/MDS/1065819/2021 | 2021-11-16 | ST202110573977 | 2021-10-28 | P/FVC/MDS/1065789/2021 | 2021-11-16 | ST202110572528 | 2021-10-27 | P/FBW/MDS/1066531/2021 | 2021-11-19
3103 | KLNJR3 | KLNJR1 |  |  | Relocation | TN | [13 empty] | ST202201007771 | 2022-01-11 | P/FVC/MDS/1071684/2022 | 2022-01-20 | ST202201008589 | 2022-01-12 | P/FVC/MDS/1071606/2022 | 2022-01-20 | ST202201003476 | 2022-01-06 | P/FVC/MDS/1071121/2022 | 2022-01-10 | ST202201003469 | 2022-01-06 | P/FBW/MDS/1071109/2022 | 2022-01-10
3104 | TKVL14 | TKVLR3 |  |  | Relocation | TN | [13 empty] | ST202109504497 | 2021-09-02 | P/FVC/MDS/1058583/2021 | 2021-09-10 | ST202102032293 | 2021-02-01 | P/FVC/MDS/1011680/2021 | 2021-03-05 | ST202101029054 | 2021-01-29 | P/FVC/MDS/1010931/2021 | 2021-02-24 | ST202101028234 | 2021-01-29 | P/FBW/MDS/1011068/2021 | 2021-02-25
3105 | PKT215 | PKT01 |  |  | Relocation | TN | [13 empty] | ST202201025239 | 2022-01-31 | P/FVC/MDS/1074464/2022 | 2022-02-22 | ST202201025350 | 2022-01-31 | P/FVC/MDS/1074407/2022 | 2022-02-22 | ST202201025485 | 2022-01-31 | P/FVC/MDS/1074515/2022 | 2022-02-22 | ST202201025410 | 2022-01-31 | P/FBW/MDS/1074347/2022 | 2022-02-22
3106 | TKMB18 | TKMB1 |  |  | Relocation | TN | [13 empty] | ST202203086040 | 2022-03-30 | P/FVC/MDS/1078178/2022 | 2022-04-15 | ST202203084971 | 2022-03-29 | P/FVC/MDS/1078132/2022 | 2022-04-15 | ST202201008993 | 2022-01-13 | P/FVC/MDS/1071733/2022 | 2022-01-20 | ST202203082312 | 2022-03-26 | P/FBW/MDS/1077759/2022 | 2022-04-14
3107 | PRLAM3 | PRLAM1 |  |  | Relocation | TN | [13 empty] | ST202202052203 | 2022-02-22 | P/FVC/MDS/1076291/2022 | 2022-03-13 | ST202202054440 | 2022-02-24 | P/FVC/MDS/1076186/2022 | 2022-03-13 | ST202202049488 | 2022-02-19 | P/FVC/MDS/1074805/2022 | 2022-02-25 | ST202202053468 | 2022-02-23 | P/FBW/MDS/1076087/2022 | 2022-03-13
3108 | CBE890 | CBE512 |  |  | Relocation | TN | [13 empty] | ST202201007777 | 2022-01-11 | P/FVC/MDS/1071688/2022 | 2022-01-20 | ST202201008596 | 2022-01-12 | P/FVC/MDS/1071610/2022 | 2022-01-20 | ST202202054764 | 2022-02-25 | P/FVC/MDS/1075695/2022 | 2022-03-10 | ST202201008051 | 2022-01-12 | P/FBW/MDS/1071527/2022 | 2022-01-20
3109 | TRY385 | TRY04 |  |  | Relocation | TN | [13 empty] | ST202202052224 | 2022-02-22 | P/FVC/MDS/1076299/2022 | 2022-03-13 | ST202202054453 | 2022-02-24 | P/FVC/MDS/1076193/2022 | 2022-03-13 | ST202202040286 | 2022-02-09 | P/FVC/MDS/1074528/2022 | 2022-02-22 | ST202202053475 | 2022-02-23 | P/FBW/MDS/1076093/2022 | 2022-03-13
3110 | SINGA2 | SINGA1 |  |  | Relocation | TN | [13 empty] | ST202201004412 | 2022-01-07 | P/FVC/MDS/1071742/2022 | 2022-01-21 | ST202201008641 | 2022-01-12 | P/FVC/MDS/1071621/2022 | 2022-01-20 | ST202201014850 | 2022-01-20 | P/FVC/MDS/1072417/2022 | 2022-01-31 | ST202201007271 | 2022-01-11 | P/FVC/MDS/1071739/2022 | 2022-01-21
3111 | SKGI22 | SKGI5 |  |  | Relocation | TN | [13 empty] | ST202107379972 | 2021-07-10 | P/FVC/MDS/1051833/2021 | 2021-08-15 | ST202107380161 | 2021-07-10 | P/FVC/MDS/1056107/2021 | 2021-09-07 | ST202107388471 | 2021-07-19 | P/FVC/MDS/1056658/2021 | 2021-09-08 | ST202107379924 | 2021-07-10 | P/FBW/MDS/1057106/2021 | 2021-09-09
3112 | PDYRM2 | PDYRM1 |  |  | Relocation | TN | [13 empty] | ST202202052199 | 2022-02-22 | P/FVC/MDS/1076289/2022 | 2022-03-13 | ST202202054436 | 2022-02-24 | P/FVC/MDS/1076184/2022 | 2022-03-13 | ST202202049486 | 2022-02-19 | P/FVC/MDS/1074803/2022 | 2022-02-25 | ST202202053466 | 2022-02-23 | P/FBW/MDS/1076085/2022 | 2022-03-13
3113 | PKT010 | PKT02 |  |  | Relocation | TN | [13 empty] | ST202201003439 | 2022-01-05 | P/FVC/MDS/1071084/2022 | 2022-01-10 | ST202201003453 | 2022-01-06 | P/FVC/MDS/1071093/2022 | 2022-01-10 | ST202201003576 | 2022-01-06 | P/FVC/MDS/1071405/2022 | 2022-01-11 | ST202201003471 | 2022-01-06 | P/FBW/MDS/1071111/2022 | 2022-01-10
3114 | MNPTI2 | MNPTI1 |  |  | Relocation | TN | [13 empty] | ST202112623319 | 2021-12-21 | P/FVC/MDS/1070046/2021 | 2021-12-29 | ST202112625892 | 2021-12-23 | P/FVC/MDS/1069720/2021 | 2021-12-28 | ST202201003481 | 2022-01-06 | P/FVC/MDS/1071116/2022 | 2022-01-10 | ST202112616596 | 2021-12-15 | P/FBW/MDS/1069565/2021 | 2021-12-22
3115 | PPMPT3 | PPMPT1 |  |  | Relocation | TN | [13 empty] | ST202111585094 | 2021-11-09 | P/FVC/MDS/1068095/2021 | 2021-12-08 | ST202111585358 | 2021-11-09 | P/FVC/MDS/1068133/2021 | 2021-12-08 | ST202111585563 | 2021-11-09 | P/FVC/MDS/1068153/2021 | 2021-12-08 | ST202111584786 | 2021-11-09 | P/FBW/MDS/1068069/2021 | 2021-12-08
3116 | PTTNM2 | PTTNM1 |  |  | Relocation | TN | [13 empty] | ST202112627233 | 2021-12-24 | P/FVC/MDS/1070568/2022 | 2022-01-03 | ST202112627247 | 2021-12-24 | P/FVC/MDS/1070548/2022 | 2022-01-03 | ST202201003486 | 2022-01-06 | P/FVC/MDS/1071126/2022 | 2022-01-10 | ST202112627257 | 2021-12-24 | P/FBW/MDS/1070558/2022 | 2022-01-03
3117 | KLVLU3 | KLVLU1 |  |  | Relocation | TN | [13 empty] | ST202201007279 | 2022-01-11 | P/FVC/MDS/1071743/2022 | 2022-01-21 | ST202201008633 | 2022-01-12 | P/FVC/MDS/1071619/2022 | 2022-01-20 | ST202201014848 | 2022-01-20 | P/FVC/MDS/1072415/2022 | 2022-01-31 | ST202201008798 | 2022-01-12 | P/FBW/MDS/1071535/2022 | 2022-01-20
3118 | ELSPT2 | ELSPT1 |  |  | Relocation | TN | [13 empty] | ST202202052214 | 2022-02-22 | P/FVC/MDS/1076293/2022 | 2022-03-13 | ST202202054443 | 2022-02-24 | P/FVC/MDS/1076188/2022 | 2022-03-13 | ST202202049491 | 2022-02-19 | P/FVC/MDS/1074807/2022 | 2022-02-25 | ST202202053470 | 2022-02-23 | P/FBW/MDS/1076089/2022 | 2022-03-13
3119 | KLRM02 | KLRM1 |  |  | Relocation | TN | [13 empty] | ST202202028002 | 2022-02-02 | P/FVC/MDS/1074482/2022 | 2022-02-22 | ST202202029883 | 2022-02-04 | P/FVC/MDS/1074425/2022 | 2022-02-22 | ST202202040232 | 2022-02-09 | P/FVC/MDS/1074518/2022 | 2022-02-22 | ST202202039049 | 2022-02-08 | P/FBW/MDS/1074365/2022 | 2022-02-22
3120 | MURKD2 | MURKD1 |  |  | Relocation | TN | [13 empty] | ST202109533477 | 2021-09-25 | P/FVC/MDS/1062968/2021 | 2021-10-01 | ST202109532065 | 2021-09-24 | P/FVC/MDS/1062926/2021 | 2021-10-01 | ST202109530326 | 2021-09-24 | P/FVC/MDS/1063086/2021 | 2021-10-01 | ST202109533145 | 2021-09-25 | P/FVC/MDS/1062823/2021 | 2021-10-01
3121 | KTBS10 | KTBSL1 |  |  | Relocation | TN | [13 empty] | ST202109533460 | 2021-09-25 | P/FVC/MDS/1062965/2021 | 2021-10-01 | ST202109532062 | 2021-09-24 | P/FVC/MDS/1062923/2021 | 2021-10-01 | ST202109530323 | 2021-09-24 | P/FVC/MDS/1063083/2021 | 2021-10-01 | ST202109533142 | 2021-09-25 | P/FVC/MDS/1062820/2021 | 2021-10-01
3122 | AGAPM2 | AGAPM1 |  |  | Relocation | TN | [13 empty] | ST202110572147 | 2021-10-27 | P/FVC/MDS/1065690/2021 | 2021-11-16 | ST202110574154 | 2021-10-28 | P/FVC/MDS/1065825/2021 | 2021-11-16 | ST202110573981 | 2021-10-28 | P/FVC/MDS/1065792/2021 | 2021-11-16 | ST202110572550 | 2021-10-27 | P/FBW/MDS/1066537/2021 | 2021-11-19
3123 | PMPYR4 | PMPYR1 |  |  | Relocation | TN | [13 empty] | ST202106354475 | 2021-06-21 | P/FVC/MDS/1051698/2021 | 2021-08-14 | ST202106357019 | 2021-06-22 | P/FVC/MDS/1060926/2021 | 2021-09-14 | ST202106356472 | 2021-06-22 | P/FVC/MDS/1061401/2021 | 2021-09-15 | ST202106357042 | 2021-06-22 | P/FBW/MDS/1060903/2021 | 2021-09-13
3124 | PATU15 | PATT3 |  |  | Relocation | TN | [13 empty] | ST202202027970 | 2022-02-02 | P/FVC/MDS/1074470/2022 | 2022-02-22 | ST202202029853 | 2022-02-04 | P/FVC/MDS/1074413/2022 | 2022-02-22 | ST202202040225 | 2022-02-09 | P/FVC/MDS/1074516/2022 | 2022-02-22 | ST202202039031 | 2022-02-08 | P/FBW/MDS/1074353/2022 | 2022-02-22
3125 | PDCRM4 | PDCRM3 |  |  | Relocation | TN | [13 empty] | ST202203061478 | 2022-03-03 | P/FVC/MDS/1076624/2022 | 2022-03-13 | ST202203061573 | 2022-03-03 | P/FVC/MDS/1076576/2022 | 2022-03-13 | ST202203062906 | 2022-03-04 | P/FVC/MDS/1076638/2022 | 2022-03-13 | ST202203062296 | 2022-03-04 | P/FBW/MDS/1076520/2022 | 2022-03-13
3126 | TIR482 | TIR49 |  |  | Relocation | TN | [13 empty] | ST202202052215 | 2022-02-22 | P/FVC/MDS/1076294/2022 | 2022-03-13 | ST202202054444 | 2022-02-24 | P/FVC/MDS/1076189/2022 | 2022-03-13 | ST202202049492 | 2022-02-19 | P/FVC/MDS/1074808/2022 | 2022-02-25 | ST202202053471 | 2022-02-23 | P/FBW/MDS/1076090/2022 | 2022-03-13
3127 | SLM397 | SLM103 |  |  | Relocation | TN | [13 empty] | ST202207212392 | 2022-07-02 | P/FVC/MDS/1087990/2022 | 2022-07-18 | ST202207212361 | 2022-07-02 | P/FVC/MDS/1087882/2022 | 2022-07-18 | ST202207212376 | 2022-07-02 | P/FVC/MDS/1087951/2022 | 2022-07-18 | ST202206210045 | 2022-06-30 | P/FBW/MDS/1087797/2022 | 2022-07-18
3128 | STTPU7 | STTPU1 |  |  | Relocation | TN | [13 empty] | ST202203061393 | 2022-03-03 | P/FVC/MDS/1076619/2022 | 2022-03-13 | ST202203061563 | 2022-03-03 | P/FVC/MDS/1076571/2022 | 2022-03-13 | ST202203062888 | 2022-03-04 | P/FVC/MDS/1076633/2022 | 2022-03-13 | ST202203061636 | 2022-03-03 | P/FBW/MDS/1076515/2022 | 2022-03-13
3129 | MADM02 | MADM1 |  |  | Relocation | TN | [13 empty] | ST202203085489 | 2022-03-29 | P/FVC/MDS/1078064/2022 | 2022-04-14 | ST202203084663 | 2022-03-29 | P/FVC/MDS/1077965/2022 | 2022-04-14 | ST202203086208 | 2022-03-30 | P/FVC/MDS/1078210/2022 | 2022-04-15 | ST202203082637 | 2022-03-26 | P/FBW/MDS/1077803/2022 | 2022-04-14
3130 | BVGRI5 | BVGRI4 |  |  | Relocation | TN | [13 empty] | ST202203061392 | 2022-03-03 | P/FVC/MDS/1076618/2022 | 2022-03-13 | ST202203061562 | 2022-03-03 | P/FVC/MDS/1076570/2022 | 2022-03-13 | ST202203062887 | 2022-03-04 | P/FVC/MDS/1076632/2022 | 2022-03-13 | ST202203061635 | 2022-03-03 | P/FBW/MDS/1076514/2022 | 2022-03-13
3131 | PNPM53 | PNPM5 |  |  | Relocation | TN | [13 empty] | ST202203085503 | 2022-03-29 | P/FVC/MDS/1078066/2022 | 2022-04-14 | ST202203084665 | 2022-03-29 | P/FVC/MDS/1077967/2022 | 2022-04-14 | ST202203086209 | 2022-03-30 | P/FVC/MDS/1078211/2022 | 2022-04-15 | ST202203082645 | 2022-03-26 | P/FBW/MDS/1077805/2022 | 2022-04-14
3132 | KDVAI2 | KDVAI1 |  |  | Relocation | TN | [13 empty] | ST202203085612 | 2022-03-29 | P/FVC/MDS/1078068/2022 | 2022-04-14 | ST202203084670 | 2022-03-29 | P/FVC/MDS/1077969/2022 | 2022-04-14 | ST202203086213 | 2022-03-30 | P/FVC/MDS/1078213/2022 | 2022-04-15 | ST202203082650 | 2022-03-26 | P/FBW/MDS/1077807/2022 | 2022-04-14
3133 | CBE939 | CBE165 |  |  | Relocation | TN | [13 empty] | ST202204122022 | 2022-04-28 | P/FVC/MDS/1079415/2022 | 2022-05-16 | ST202204119735 | 2022-04-26 | P/FVC/MDS/1079365/2022 | 2022-05-13 | ST202204122036 | 2022-04-28 | P/FVC/MDS/1079493/2022 | 2022-05-16 | ST202204119481 | 2022-04-26 | P/FBW/MDS/1079278/2022 | 2022-05-13
3134 | NGL141 | NGL49 |  |  | Relocation | TN | [13 empty] | ST202206156602 | 2022-06-02 | P/FVC/MDS/1082426/2022 | 2022-06-14 | ST202205147185 | 2022-05-27 | P/FVC/MDS/1081101/2022 | 2022-06-03 | ST202205148272 | 2022-05-28 | P/FVC/MDS/1081248/2022 | 2022-06-03 | ST202205147762 | 2022-05-27 | P/FBW/MDS/1081175/2022 | 2022-06-03
3135 | VSNRM2 | VSNRM1 |  |  | Relocation | TN | [13 empty] | ST202111592514 | 2021-11-17 | P/FVC/MDS/1066619/2021 | 2021-11-26 | ST202111592947 | 2021-11-17 | P/FVC/MDS/1066597/2021 | 2021-11-26 | ST202202040270 | 2022-02-09 | P/FVC/MDS/1074525/2022 | 2022-02-22 | ST202111595305 | 2021-11-19 | P/FBW/MDS/1067042/2021 | 2021-12-01
3136 | MATTU3 | MATTU1 |  |  | Relocation | TN | [13 empty] | ST202204111695 | 2022-04-20 | P/FVC/MDS/1078939/2022 | 2022-05-02 | ST202204110040 | 2022-04-19 | P/FVC/MDS/1079001/2022 | 2022-05-03 | ST202204111913 | 2022-04-20 | P/FVC/MDS/1079023/2022 | 2022-05-03 | ST202204109607 | 2022-04-19 | P/FVC/MDS/1078897/2022 | 2022-05-02
3137 | TRY382 | TRY203 |  |  | Relocation | TN | [13 empty] | ST202109537829 | 2021-09-29 | P/FVC/MDS/1063295/2021 | 2021-10-11 | ST202109532067 | 2021-09-24 | P/FVC/MDS/1062928/2021 | 2021-10-01 | ST202109530328 | 2021-09-24 | P/FVC/MDS/1063088/2021 | 2021-10-01 | ST202109533147 | 2021-09-25 | P/FVC/MDS/1062825/2021 | 2021-10-01
3138 | SLM402 | SLM128 |  |  | Relocation | TN | [13 empty] | ST202201007772 | 2022-01-11 | P/FVC/MDS/1071685/2022 | 2022-01-20 | ST202201008590 | 2022-01-12 | P/FVC/MDS/1071607/2022 | 2022-01-20 | ST202201003575 | 2022-01-06 | P/FVC/MDS/1071404/2022 | 2022-01-11 | ST202201003470 | 2022-01-06 | P/FBW/MDS/1071110/2022 | 2022-01-10
3139 | VLR111 | VLR11 |  |  | Relocation | TN | [13 empty] | ST202201014669 | 2022-01-20 | P/FVC/MDS/1072383/2022 | 2022-01-31 | ST202201014734 | 2022-01-20 | P/FVC/MDS/1072353/2022 | 2022-01-31 | ST202201014835 | 2022-01-20 | P/FVC/MDS/1072405/2022 | 2022-01-31 | ST202201014789 | 2022-01-20 | P/FBW/MDS/1072324/2022 | 2022-01-31
3140 | SLM325 | SLM148 |  |  | Relocation | TN | [13 empty] | ST202109533459 | 2021-09-25 | P/FVC/MDS/1062964/2021 | 2021-10-01 | ST202109532061 | 2021-09-24 | P/FVC/MDS/1062922/2021 | 2021-10-01 | ST202109530322 | 2021-09-24 | P/FVC/MDS/1063082/2021 | 2021-10-01 | ST202109533141 | 2021-09-25 | P/FVC/MDS/1062819/2021 | 2021-10-01
3141 | MLVTN4 | MLVTN1 |  |  | Relocation | TN | [13 empty] | ST202109504522 | 2021-09-02 | P/FVC/MDS/1060756/2021 | 2021-09-13 | ST202109511405 | 2021-09-07 | P/FVC/MDS/1061788/2021 | 2021-09-16 | ST202109511992 | 2021-09-07 | P/FVC/MDS/1061735/2021 | 2021-09-16 | ST202109513226 | 2021-09-08 | P/FBW/MDS/1061652/2021 | 2021-09-16
3142 | ISWRG4 | ISWRG1 |  |  | Relocation | TN | [13 empty] | ST202111595156 | 2021-11-19 | P/FVC/MDS/1067076/2021 | 2021-12-01 | ST202111595250 | 2021-11-19 | P/FVC/MDS/1067063/2021 | 2021-12-01 | ST202112616160 | 2021-12-14 | P/FVC/MDS/1069542/2021 | 2021-12-20 | ST202111595315 | 2021-11-19 | P/FBW/MDS/1067052/2021 | 2021-12-01
3143 | MMDUR4 | MMDUR1 |  |  | Relocation | TN | [13 empty] | ST202201007765 | 2022-01-11 | P/FVC/MDS/1071680/2022 | 2022-01-20 | ST202201008575 | 2022-01-12 | P/FVC/MDS/1071602/2022 | 2022-01-20 | ST202203074583 | 2022-03-17 | P/FVC/MDS/1077193/2022 | 2022-03-30 | ST202201008045 | 2022-01-12 | P/FBW/MDS/1071521/2022 | 2022-01-20
3144 | SLM400 | SLM83 |  |  | Relocation | TN | [13 empty] | ST202202048211 | 2022-02-18 | P/FVC/MDS/1075006/2022 | 2022-02-28 | ST202202049437 | 2022-02-19 | P/FVC/MDS/1074952/2022 | 2022-02-28 | ST202202049481 | 2022-02-19 | P/FVC/MDS/1074799/2022 | 2022-02-25 | ST202202048690 | 2022-02-18 | P/FBW/MDS/1074894/2022 | 2022-02-28
3145 | KDKL45 | KDKL3 |  |  | Relocation | TN | [13 empty] | ST202108430684 | 2021-08-17 | P/FVC/MDS/1059639/2021 | 2021-09-12 | ST202108414427 | 2021-08-10 | P/FVC/MDS/1055948/2021 | 2021-09-05 | ST202108413612 | 2021-08-09 | P/FVC/MDS/1055895/2021 | 2021-09-05 | ST202108424126 | 2021-08-11 | P/FBW/MDS/1055970/2021 | 2021-09-05
3146 | WRGD13 | CWWRG |  |  | Relocation | TN | [13 empty] | ST202203086038 | 2022-03-30 | P/FVC/MDS/1078176/2022 | 2022-04-15 | ST202203084966 | 2022-03-29 | P/FVC/MDS/1078130/2022 | 2022-04-15 | ST202012176848 | 2020-12-17 | P/FVC/MDS/1007822/2020 | 2020-12-29 | ST202203083990 | 2022-03-28 | P/FBW/MDS/1077887/2022 | 2022-04-14
3147 | TNPLM6 | TNPLM1 |  |  | Relocation | TN | [13 empty] | ST202106354539 | 2021-06-21 | P/FVC/MDS/1051707/2021 | 2021-08-14 | ST202106357048 | 2021-06-22 | P/FVC/MDS/1060935/2021 | 2021-09-14 | ST202106356487 | 2021-06-22 | P/FVC/MDS/1061410/2021 | 2021-09-15 | ST202106359409 | 2021-06-24 | P/FBW/MDS/1060912/2021 | 2021-09-13
3148 | KLPTI6 | KLPTI2 |  |  | Relocation | TN | [13 empty] | ST202106354474 | 2021-06-21 | P/FVC/MDS/1051697/2021 | 2021-08-14 | ST202106357014 | 2021-06-22 | P/FVC/MDS/1060925/2021 | 2021-09-14 | ST202106356471 | 2021-06-22 | P/FVC/MDS/1061400/2021 | 2021-09-15 | ST202106357041 | 2021-06-22 | P/FBW/MDS/1060902/2021 | 2021-09-13
3149 | TIPPA2 | TIPPA1 |  |  | Relocation | TN | [13 empty] | ST202107396907 | 2021-07-26 | P/FVC/MDS/1052727/2021 | 2021-08-20 | ST202107393933 | 2021-07-23 | P/FVC/MDS/1056746/2021 | 2021-09-09 | ST202107393760 | 2021-07-23 | P/FVC/MDS/1057241/2021 | 2021-09-09 | ST202107393406 | 2021-07-23 | P/FBW/MDS/1056713/2021 | 2021-09-08
3150 | KMNPM3 | KMNPM1 |  |  | Relocation | TN | [13 empty] | ST202201022569 | 2022-01-28 | P/FVC/MDS/1072940/2022 | 2022-02-04 | ST202201022726 | 2022-01-28 | P/FVC/MDS/1072973/2022 | 2022-02-04 | ST202201022906 | 2022-01-28 | P/FVC/MDS/1073022/2022 | 2022-02-04 | ST202201022857 | 2022-01-28 | P/FBW/MDS/1073000/2022 | 2022-02-04
3151 | KLMBD4 | KLMBD1 |  |  | Relocation | TN | [13 empty] | ST202109527678 | 2021-09-22 | P/FVC/MDS/1062680/2021 | 2021-09-29 | ST202109526890 | 2021-09-21 | P/FVC/MDS/1062627/2021 | 2021-09-29 |  |  |  |  | ST202109527567 | 2021-09-22 | P/FBW/MDS/1062591/2021 | 2021-09-29
3152 | VENGA5 | VENGA1 |  |  | Relocation | TN | [13 empty] | ST202110572152 | 2021-10-27 | P/FVC/MDS/1065692/2021 | 2021-11-16 | ST202110574168 | 2021-10-28 | P/FVC/MDS/1065827/2021 | 2021-11-16 | ST202204111900 | 2022-04-20 | P/FVC/MDS/1079018/2022 | 2022-05-03 | ST202110572599 | 2021-10-27 | P/FBW/MDS/1066539/2021 | 2021-11-19
3153 | IPYRN4 | IPYRN1 |  |  | Relocation | TN | [13 empty] | ST202201003441 | 2022-01-05 | P/FVC/MDS/1071086/2022 | 2022-01-10 | ST202201003455 | 2022-01-06 | P/FVC/MDS/1071095/2022 | 2022-01-10 | ST202201014842 | 2022-01-20 | P/FVC/MDS/1072410/2022 | 2022-01-31 | ST202201003464 | 2022-01-06 | P/FBW/MDS/1071104/2022 | 2022-01-10
3154 | TIR355 | TIR44 |  |  | Relocation | TN | [13 empty] | ST202112610477 | 2021-12-10 | P/FVC/MDS/1069099/2021 | 2021-12-17 | ST202111595251 | 2021-11-19 | P/FVC/MDS/1067064/2021 | 2021-12-01 | ST202202049496 | 2022-02-19 | P/FVC/MDS/1074809/2022 | 2022-02-25 | ST202111595316 | 2021-11-19 | P/FBW/MDS/1067053/2021 | 2021-12-01
3155 | SLM378 | SLM134 |  |  | Relocation | TN | [13 empty] | ST202110559324 | 2021-10-14 | P/FVC/MDS/1063724/2021 | 2021-10-22 | ST202110560200 | 2021-10-14 | P/FVC/MDS/1063705/2021 | 2021-10-22 | ST202110573971 | 2021-10-28 | P/FVC/MDS/1065788/2021 | 2021-11-16 | ST202110555483 | 2021-10-09 | P/FBW/MDS/1063527/2021 | 2021-10-18
3156 | VADUG4 | VADUG1 |  |  | Relocation | TN | [13 empty] | ST202109537836 | 2021-09-29 | P/FVC/MDS/1063327/2021 | 2021-10-11 | ST202109538151 | 2021-09-29 | P/FVC/MDS/1063349/2021 | 2021-10-11 | ST202109530335 | 2021-09-24 | P/FVC/MDS/1063095/2021 | 2021-10-01 | ST202109533210 | 2021-09-25 | P/FVC/MDS/1062831/2021 | 2021-10-01
3157 | NRMPM3 | NRMPM1 |  |  | Relocation | TN | [13 empty] | ST202204093167 | 2022-04-07 | P/FVC/MDS/1078392/2022 | 2022-04-21 | ST202204094913 | 2022-04-08 | P/FVC/MDS/1078353/2022 | 2022-04-21 |  |  |  |  | ST202204094799 | 2022-04-08 | P/FBW/MDS/1078299/2022 | 2022-04-21
3158 | KDVPT2 | KDVPT1 |  |  | Relocation | TN | [13 empty] | ST202201007781 | 2022-01-11 | P/FVC/MDS/1071691/2022 | 2022-01-20 | ST202201008603 | 2022-01-12 | P/FVC/MDS/1071613/2022 | 2022-01-20 | ST202201008986 | 2022-01-13 | P/FVC/MDS/1071729/2022 | 2022-01-20 | ST202201008054 | 2022-01-12 | P/FBW/MDS/1071530/2022 | 2022-01-20
3159 | KCP135 | KCPM5 |  |  | Relocation | TN | [13 empty] | ST202201022589 | 2022-01-28 | P/FVC/MDS/1072948/2022 | 2022-02-04 | ST202201022763 | 2022-01-28 | P/FVC/MDS/1072981/2022 | 2022-02-04 | ST202201022913 | 2022-01-28 | P/FVC/MDS/1073028/2022 | 2022-02-04 | ST202201022872 | 2022-01-28 | P/FBW/MDS/1073008/2022 | 2022-02-04
3160 | KKVDI2 | KKVDI1 |  |  | Relocation | TN | [13 empty] | ST202110572285 | 2021-10-27 | P/FVC/MDS/1065701/2021 | 2021-11-16 | ST202110574219 | 2021-10-28 | P/FVC/MDS/1065834/2021 | 2021-11-16 | ST202110574000 | 2021-10-28 | P/FVC/MDS/1065800/2021 | 2021-11-16 | ST202110572655 | 2021-10-27 | P/FBW/MDS/1066546/2021 | 2021-11-19
3161 | NKDYR5 | NKDYR1 |  |  | Relocation | TN | [13 empty] | ST202203061399 | 2022-03-03 | P/FVC/MDS/1076621/2022 | 2022-03-13 | ST202203061567 | 2022-03-03 | P/FVC/MDS/1076573/2022 | 2022-03-13 | ST202203062895 | 2022-03-04 | P/FVC/MDS/1076635/2022 | 2022-03-13 | ST202203061640 | 2022-03-03 | P/FBW/MDS/1076517/2022 | 2022-03-13
3162 | DGL111 | DGL10 |  |  | Relocation | TN | [13 empty] | ST202112623417 | 2021-12-21 | P/FVC/MDS/1070048/2021 | 2021-12-29 | ST202112625894 | 2021-12-23 | P/FVC/MDS/1069722/2021 | 2021-12-28 | ST202201003483 | 2022-01-06 | P/FVC/MDS/1071123/2022 | 2022-01-10 | ST202112626676 | 2021-12-24 | P/FBW/MDS/1070156/2021 | 2021-12-29
3163 | PRDI57 | PRDI4 |  |  | Relocation | TN | [13 empty] | ST202110572281 | 2021-10-27 | P/FVC/MDS/1065699/2021 | 2021-11-16 | ST202110574217 | 2021-10-28 | P/FVC/MDS/1065832/2021 | 2021-11-16 | ST202110573998 | 2021-10-28 | P/FVC/MDS/1065798/2021 | 2021-11-16 | ST202110572636 | 2021-10-27 | P/FBW/MDS/1066544/2021 | 2021-11-19
3164 | NSNP6 | COW |  |  | RELOCATION | TN | [13 empty] | 2016805231 | 2016-07-22 | P/FVC/MDS/3494909/2016 | 2016-09-06 | 2017642605 | 2017-07-21 | P/FBW/MDS/4250029/2017 | 2017-08-11 | 2017371666 | 2017-01-30 | P/FVC/MDS/3887491/2017 | 2017-03-24 | 2017250324 | 2017-11-30 | P/FBW/MDS/4530159/2017 | 2017-12-19
3165 | NMKL63 | NKL23 |  |  | Relocation | TN | [13 empty] | ST202212780547 | 2022-12-02 | P/FVC/MDS/1118328/2022 | 2022-12-08 | ST202212779905 | 2022-12-02 | P/FVC/MDS/1118221/2022 | 2022-12-07 | ST202212780638 | 2022-12-02 | P/FVC/MDS/1118287/2022 | 2022-12-07 | ST202212779585 | 2022-12-01 | P/FBW/MDS/1118131/2022 | 2022-12-07
Note on I507: New SR Punch on 21may21
Note on L699: Retained on 19-Aug based on relocation discussion
Note on L1238: Retained as per msg from Judah - 28-Jul'21
Note on L1250: Retained post CEO Visit - 26Jul21
Note on J1934: New SR Punch on 21may21

## Sheet4
SI. No. | New Site ID | District | Site Name | Old ToCo | New ToCo | Config Tech | Status
1 | AMMAM4 | Salem | Ammapalayam 4 | CNIL / GTL | ATC | 2G+L1800+L2300+L900 | 2G+L1800- No alarm// L2300- No Alarm //L900 one Sector down (cpri faulty
2 | MELPN2 | Pudukottai | Melappanaiyur 2 | CNIL / GTL | Summit | 2G+L1800+L2300+L900 | No alarm
3 | CNPTU2 | Tiruppur | Chinnapapanuthu 2 | CNIL / GTL | Indus | 2G+L1800+L2100+L2300+L900 | 2G+L1800+L2300 No alarm// L2100+L900 each tech one cpri faulty
SI. No. | New Site ID | District | Site Name | Old ToCo | New ToCo | Config Tech | Status
1 | MOREP2 | Namakkal | Morepalayam 2 | CNIL / GTL | ATC | 2G+L1800+L2100+L2300+L900 | No alarm
2 | CMPYM2 | Coimbatore | Chinnamathampalayam 2 | CNIL / GTL | Indus | 2G+L1800+L2100+L2300+L900 | Integration wip
3 | SAMPI2 | Tiruchirappalli | Sampatti 2 | CNIL / GTL | ATC | 2G+L1800+L2300+L900 | No alarm
4 | CBE866 | Coimbatore | P.S.G.Science and Arts College | Indus | Indus | 2G+L1800+L2100+L2300 | 2G+L1800- No alarm// L2300- No Alarm //L2100 one cpri Alarm
SI. No. | New Site ID | Site Name | District | Old ToCo | New ToCo | Config Tech | Status
1 | NMBYP2 | Nambiampalayam 2 | Tiruppur | CNIL / GTL | ATC | G+L1800+L2100+L2300+L900+ttb c | 2G+L1800- No alarm// L2300-L2100+L900 integration wip
2 | TKREC2 | T.K.Raja Educational institues | Velur | Indus | Indus | 2G+L1800+L2100+L2300+L900 | 900+1800+2100 each one sector down//2300 no alarm//

## Sheet1 (hidden)
SI. No. | Circle | New Site ID | Old Site ID | Zone | RFAI Date | Old ToCo | New ToCo | AGEING | Status
1 | CHN | VAND31 | VANDA3 | CHN | 2022-09-29 | BSNL | INDUS | 134 | MS1 DONE
2 | TN | TRY410 | TRY195 | TRY | 2022-10-17 | Indus | Indus | 116 | TMRW RELOC PLAN
3 | CHN | BELLS6 | BELLS3 | CHN | 2022-10-26 | Indus | Indus | 107 | Installation completed, Media not ready
4 | CHN | ANNA34 | ANNAN7 | CHN | 2022-09-22 | GTL | Indus | 141 | Power cable approval pending, WIP
5 | CHN | NMRO3 | NMROA | CHN | 2022-09-25 | TVI | Indus | 138 | WIP
6 | TN | PDY391 | PDY04 | TRY | 2022-09-05 | GTL | Indus | 158 | After rerouting only possible
7 | CHN | PATT30 | PATT22 | CHN | 2022-09-25 | INDUS | TVI | 138 | AOM Approval Pending
8 | TN | TOTNU2 | TOTNU1 | MDU | 2022-09-25 | Indus | Summit | 138 | AOM Approval Pending
9 | TN | RMPM51 | RMPM32 | MDU | 2022-09-28 | Reliance | Indus | 135 | AOM Approval Pending
10 | TN | KMKPM2 | KMKPM1 | SLM | 2022-09-13 | ATC | ATC | 150 | AOM Approval Pending
11 | TN | CBE954 | CBE865 | CBE | 2022-10-17 | INDUS | ATC | 116 | MRN WIP
12 | TN | CHPRM2 | CHPRM1 | MDU | 2022-10-17 | INDUS | ATC | 116 | MRN WIP,FD SITE
13 | CHN | BESA12 | BESAN2 | CHN | 2022-09-19 | GTL | Indus | 144 | New site change to FD,then only we can relocate
14 | TN | TINDL2 | TINDL1 | CBE | 2022-09-17 | Reliance | Indus | 146 | New site change to FD,then only we can relocate ,
15 | TN | DPI061 | DPI10 | SLM | 2022-09-22 | GTL | Indus | 141 | Power cable approval pending
16 | TN | CBE929 | CBEM65 | CBE | 2022-09-25 | Indus | Indus | 138 | Power cable approval pending
17 | TN | NGPM24 | NGPM5 | TRY | 2022-10-04 | Indus | Indus | 129 | Power cable approval pending
18 | CHN | ANNA25 | ANNA11 | CHN | 2022-10-10 | Indus | Indus | 123 | Power cable approval pending
19 | CHN | BHAR19 | BHARA2 | CHN | 2022-10-17 | INDUS | ATC | 116 | Power cable approval pending
20 | TN | SLM420 | SLM157 | SLM | 2022-10-18 | CNIL / GTL | ATC | 115 | Power cable approval pending
21 | TN | AMMAM4 | AMMAM3 | SLM | 2022-10-20 | GTL | ATC | 113 | Power cable approval pending
22 | TN | GOVTC3 | GOVTC1 | MDU | 2022-10-26 | GTL | ATC | 107 | Power cable approval pending
23 | TN | TIR513 | TIR60 | CBE | 2022-09-30 | CNIL / GTL | ATC | 133 | Resurvey
24 | CHN | TRUST8 | TRUST3 | CHN | 2022-09-25 | CNIL / GTL | ATC | 138 | Survey wip,
25 | TN | KLVNG2 | KLVN1 | SLM | 2022-10-17 | CNIL / GTL | ATC | 116 | Survey wip,
26 | TN | TUPGN2 | TUPGN1 | SLM | 2022-10-17 | CNIL / GTL | ATC | 116 | Survey wip,
27 | TN | VLKTI2 | VLKT1 | SLM | 2022-10-17 | CNIL / GTL | ATC | 116 | Survey wip,
28 | TN | JDPLM2 | JDPL1 | SLM | 2022-10-17 | Indus | Indus | 116 | Survey wip,
29 | TN | UTHIG2 | UTHIG1 | SLM | 2022-10-17 | INDUS | Indus | 116 | Survey wip,
30 | TN | PLPTI2 | PLPTI1 | SLM | 2022-10-15 | TVI | Indus | 118 | Survey wip,
31 | TN | ATRPL2 | ATRPL1 | MDU | 2022-10-17 | INDUS | Indus | 116 | Survey wip,
32 | TN | KNYUR3 | KNYR1 | SLM | 2022-10-15 | CNIL / GTL | Indus | 118 | Survey wip,
33 | TN | KAYAM2 | KAYAM1 | CBE | 2022-10-17 | CNIL / GTL | Indus | 116 | Survey wip,
34 | TN | SNTKD2 | SNTKD1 | MDU | 2022-10-17 | CNIL / GTL | Summit | 116 | Survey wip,
35 | TN | SINVD2 | SINVD1 | CBE | 2022-10-18 | CNIL / GTL | Summit | 115 | Survey wip,
36 | TN | NMSNM2 | NMSN1 | CBE | 2022-10-18 | CNIL / GTL | Ascend | 115 | Survey wip,
37 | TN | KANAA2 | KANAA1 | TRY | 2022-10-28 | TVI | Indus | 105 | Survey wip,
38 | TN | RENGM2 | RENGM1 | SLM | 2022-10-18 | CNIL / GTL | ATC | 115 | Survey wip,
39 | TN | PALYM2 | PALYM1 | SLM | 2022-10-18 | CNIL / GTL | ATC | 115 | Survey wip,
40 | TN | INDNR2 | INDNR1 | CBE | 2022-10-18 | CNIL / GTL | ATC | 115 | Survey wip,
41 | TN | MOREP2 | MOREP1 | SLM | 2022-10-19 | CNIL / GTL | ATC | 114 | Survey wip,
42 | TN | KRAMR2 | KRAMR1 | SLM | 2022-10-19 | CNIL / GTL | ATC | 114 | Survey wip,
43 | TN | POMPM2 | POMPM1 | TRY | 2022-10-20 | CNIL / GTL | ATC | 113 | Survey wip,
44 | TN | VPDAI3 | VPDAI1 | SLM | 2022-10-20 | CNIL / GTL | ATC | 113 | Survey wip,
45 | TN | OTNGP2 | OTNGP1 | MDU | 2022-10-20 | CNIL / GTL | Indus | 113 | Survey wip,
46 | TN | PTMPT2 | PTMP1 | SLM | 2022-10-20 | CNIL / GTL | Indus | 113 | Survey wip,
47 | TN | KLINR2 | KLINR1 | SLM | 2022-10-20 | CNIL / GTL | ATC | 113 | Survey wip,
48 | TN | PLAGR2 | PLAGR1 | SLM | 2022-10-20 | CNIL / GTL | ATC | 113 | Survey wip,
49 | TN | CMPYM2 | CMPYM1 | CBE | 2022-10-21 | CNIL / GTL | ATC | 112 | Survey wip,
50 | TN | PLMLM3 | PLMLM2 | CBE | 2022-10-21 | CNIL / GTL | Indus | 112 | Survey wip,
51 | TN | VAGIK2 | VAGIK1 | MDU | 2022-10-21 | CNIL / GTL | Indus | 112 | Survey wip,
52 | TN | KAPLM2 | KAPLM1 | CBE | 2022-10-22 | CNIL / GTL | ATC | 111 | Survey wip,
53 | TN | THIYM2 | THIYM1 | TRY | 2022-10-22 | CNIL / GTL | Indus | 111 | Survey wip,
54 | TN | POLPM2 | POLPM1 | CBE | 2022-10-22 | CNIL / GTL | ATC | 111 | Survey wip,
55 | TN | KTVMP2 | KTVMP1 | TRY | 2022-10-22 | CNIL / GTL | ATC | 111 | Survey wip,
56 | TN | VLYNK2 | VLYN1 | MDU | 2022-10-25 | CNIL / GTL | ATC | 108 | Survey wip,
57 | TN | VAYLR2 | VAYL1 | TRY | 2022-10-25 | CNIL / GTL | ATC | 108 | Survey wip,
58 | TN | MNSRT2 | MNSRT1 | TRY | 2022-10-26 | CNIL / GTL | ATC | 107 | Survey wip,
59 | TN | KKMBI2 | KKMBI1 | TRY | 2022-10-26 | Indus | Indus | 107 | Survey wip,
60 | TN | KGVLU2 | KGVLU1 | CBE | 2022-10-26 | Indus | IN-1072210 | 107 | Survey wip,
61 | TN | NJPYM2 | NJPM1 | CBE | 2022-10-26 | CNIL / GTL | Indus | 107 | Survey wip,
62 | TN | KLKIR2 | KLKIR1 | CBE | 2022-10-26 | CNIL / GTL | Indus | 107 | Survey wip,
63 | TN | NMBYP2 | NMBYP1 | CBE | 2022-10-26 | CNIL / GTL | Indus | 107 | Survey wip,
64 | TN | SENML2 | SENM1 | CBE | 2022-10-26 | CNIL / GTL | Indus | 107 | Survey wip,
65 | TN | ATMRV2 | ATMR1 | MDU | 2022-10-26 | CNIL / GTL | Indus | 107 | Survey wip,
66 | TN | NARPI2 | NARPI1 | CBE | 2022-10-26 | CNIL / GTL | Indus | 107 | Survey wip,
67 | TN | PNJPI2 | PNJPI1 | MDU | 2022-10-26 | CNIL / GTL | Indus | 107 | Survey wip,
68 | TN | PRDI59 | SRLI1 | CBE | 2022-10-31 | CNIL / GTL | Indus | 102 | Survey wip,
69 | TN | SHBAR2 | SHBAR1 | CBE | 2022-10-31 | CNIL / GTL | Indus | 102 | Survey wip,
70 | TN | URLPT2 | URLPT1 | CBE | 2022-10-31 | CNIL / GTL | Indus | 102 | Survey wip,
71 | TN | ACHNP2 | ACHNP1 | MDU | 2022-10-12 | SRLI1 | Indus | 121 | Survey wip,
72 | TN | VELNP3 | VELNP1 | CBE | 2022-11-02 | SHBAR1 | Indus | 100 | Survey wip,
73 | TN | TPKIT2 | TPKT1 | CBE | 2022-11-02 | URLPT1 | Indus | 100 | Survey wip,
74 | TN | UMRYU2 | UMRY1 | CBE | 2022-11-02 | CNIL / GTL | Ascend | 100 | Survey wip,
75 | TN | SENGP2 | SENG1 | CBE | 2022-11-02 | CNIL / GTL |  | 100 | Survey wip,
76 | TN | KILKT2 | KILKT1 | SLM | 2022-11-02 | CNIL / GTL |  | 100 | Survey wip,
77 | TN | NSNP17 | NSNP6 | CBE | 2022-09-12 | CNIL / GTL |  | 151 | New Site RFAI issue
78 | TN | PLGA10 | PLGAM1 | TRY | 2022-08-17 | CNIL / GTL |  | 177 | Not possible because of public issue
79 | TN | VDGPI2 | VDGPI1 | CBE | 2022-09-19 | CNIL / GTL |  | 144 | Old site Honey bee clear we can relocate
Formulas:
AGEING = TODAY()-[RFAI Date]

## Summary-P.vo (hidden)
Count of New Site ID | Column Labels
Status | Relocated | MRN wip | Planned | (blank) | Not possible because of public issue | RTN available we can relocate | Alarm Clearance | New Site RFAI issue | AOM available we can relocate | HOP Material req | Old site Honey bee clear we can relocate | New site change to FD,then only we can relocate | Waiting for power Cpri approval, | RFAI rejected | Material Dispatched means we can relocate | Survey wip, | MS1 WIP | Material Dispatched means relocate. | Material Dispatched means relocate | Waiting for power Cpri approval | Grand Total
CHN |  |  | 2 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 2 |  | 1 |  |  | 9
High Opex | [7 empty] | 1 |  |  |  | 1 |  |  |  | 2 |  |  |  |  | 4
High Opex Saving_Sep'21 |  |  | 1 | [17 empty] | 1
LL Issue | [17 empty] | 1 |  |  | 1
Unsafe | [6 empty] | 1 | [13 empty] | 1
(blank) |  |  | 1 | 1 | [16 empty] | 2
TN | 16 | 2 | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 2 | 1 | 1 | 1 | 1 |  | 1 | 1 | 35
Agreement expiry | [7 empty] | 1 | [12 empty] | 1
BSNL Exit Feasible Sites | 3 | [15 empty] | 1 |  |  |  | 4
CNIL Free Exit Feasble Relocation |  |  |  | 1 | [6 empty] | 1 | [9 empty] | 2
High Opex Saving_Sep'21 | 3 |  |  |  | 1 | [15 empty] | 4
LL Issue | 3 | 1 | 1 | [16 empty] | 1 | 6
Opex Saving | 4 | [17 empty] | 1 |  | 5
Opex Saving(344) | 3 | 1 | [6 empty] | 1 | 1 |  |  | 1 | 1 | 1 | [5 empty] | 9
Unsafe | [5 empty] | 1 | [9 empty] | 1 |  |  |  |  | 2
Less AGL | [12 empty] | 1 | [7 empty] | 1
(blank) |  |  |  | 1 | [16 empty] | 1
Grand Total | 16 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 44

## Mis-Match (hidden)
S.NO | Old Site ID | FD Site | New Site ID | Zone | District | Remarks
1 | FD SITE DETAILS
2
3
4